## Title page
THE PLANNING ACT 2008
THE INFRASTRUCTURE PLANNING (EXAMINATION PROCEDURE) RULES
2010
Natural England's Action Log- Deadine 6 Submission.
For:
The construction and operation of Hornsea Project Four Offshore Wind Farm, located approximately 69 km from the East Riding of Yorkshire in the Southern North Sea, covering an area of approximately 468 km2.
Planning Inspectorate Reference EN010098
27th July 2022

## How to Read this Action Log
Natural England have created this Action Log to highlight measures that the Applicant may usefully adopt at this late stage in the Hornsea Four examination to allow us to close out issues or work towards points of agreement within our Statement of Common Ground. The action required could be: providing further information/clarification; securing additional mitigation; confirming commitments within within the DCO / dML or certified plan; amending or adding a commitment; or agreeing to specific monitoring. We have used our RAG colour scale to denote the level of significance of the issue and how this could change should the action be addressed. It should be noted that the colour scale is different from that used in the Statement of Common Ground provided by The Applicant. The Action Log is split into multiple tabs in line with the Appendices of our Relevant Representations submission. Marine Mammals Marine Processes Benthic & Intertidal Fish and Shellfish The actions log does not include offshore ornithology. This reflects that whilst there are profound disagreements between the Applicant and NE regarding the impacts of the proposal, progress has been made regarding the baseline characterisation and the provision of assessment outputs using our advised approach. Consequently, there are limited outstanding actions for the Applicant at this time and those that remain are captured in the Risk & Issues log. | PR
Purple
Note for Examiners and/or competent authority. May relate to DCO/DML
Red
Natural England considers that unless these issues are resolved it will have to advise that (in relation to any one of them, and as appropriate) it is not possible to ascertain beyond reasonable scientific doubt that the project will not affect the integrity of an SAC/SPA/Ramsar and/or significantly hinder the conservation objectives of an MCZ and/or damage or destroy the interest features of a SSSI and/or comply fully with the Environmental Impact Assessment requirements.
Natural England may use this category to highlight where there is a significant risk that an issue will not be sufficiently addressed within the Examination timescales.
Amber
Natural England does not agree with the applicant’s position or approach and consider that this could make a material difference to the outcome of the decision-making process for this project.
Yellow
Natural England doesn’t agree with the Applicant’s position or approach. We would ideally have liked this to be fully addressed but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process and would not expect these matters to be a ongoing focus of the examination. However, we reserve the right to revise our opinion should further evidence be presented.
It should be noted by interested parties that just because these issues/comments are not raised as significant concerns in this instance, it should not be understood or inferred that Natural England would be of the same view in other cases or circumstances.
Green
Natural England is in broad agreement with the Applicant’s approach and has no significant outstanding concerns.

## Marine Mammals
REF | Outstanding Issue | Detail | Current RAG | Proposed Action | RAG if Action addressed | Issue Log Refs
MM1 | Mitigating the PTS Zone | NE maintain that the full SELcum PTS zone must be taken into account when determining appropriate mitigation measures. We acknowledge that there is active research in this area and the final mitigation could be decided post-consent based on the latest available research. |  | We welcome the Applicant's commitment to mitigating cumulative PTS impact ranges that have been calculated using the latest research and methods available at the time of the final MMMP. However, it is imperative that this position is included in the Outline MMMP, as this document should outline the principles upon which mitigation is based, not solely the options for mitigation measures. |  | D2
MM2 | Marine Mammal Monitoring Objectives | We are concerned with the overall lack of monitoring detail included in the OMMP. There has been no consideration of the areas of the assessment where assumptions have been made and where the project could contribute to filling knowledge gaps (for example, with regards to operational WTG noise levels (D7), or the assumed distribution of bottlenose dolphin close to the coast (D9)) |  | We request that the OMMP is updated with the suggested monitoring objectives. |  | D7, D9, D30
MM3 | Geophysical surveys | Natural England defer to the MMO as to whether or not it is appropriate for geophysical surveys to not be covered in the DCO. However, as they are a known activity directly connected to the contruction (and in some cases, operation) of wind farm development they should be fully considered and assessed within the ES and RIAA. |  | Natural England request that the Applicant provide information on the likely geophysical equipment, and commit to mitigation and/or the inclusion of text in relation to the mitigation process for geophysical surveys. | As multiple rows of the issues log are covered by this point we cannot confirm a single RAG status | D13, D15, D17, D22
MM4 | SIPs - Lack of confidence in. | Natural England cannot agree with the conclusion of no AEOI for in-combination disturbance impacts to the SNS SAC due to lack of confidence in the SIP process. |  | Secure submission of the SIP 6-9 months prior to construction in the DCO. See also MM5. | As multiple rows of the issues log are covered by this point we cannot confirm a single RAG status | D12, D21, D24, D33
MM5 | Commitment to mitigation within the SIP | The approach taken by the Applicant relies heavily on the SIP for mitigation of adverse effect as, at this stage, the project has not committed to undertaking any mitigation measures. The in-combination assessment does not present the worst-case scenario, yet the thresholds for significant disturbance are already exceeded. Geophysical surveys typically go through the ML exemption route, through which there is no legally-binding condition to undertake marine mammal mitigation to reduce the risk of injury (and disturbance). We advise that the Applicant commit to mitigation for geophysical surveys. |  | Natural England's position is that a commitment should be made to deliver mitigation, with the option to demonstrate that it is not needed post-consent. We acknowledge Hornsea 4's position of not commiting to specific mitigation measures due to potential advances in technology, and welcome that the need for mitigation has been budgeted for (pers comm). We would therefore welcome the inclusion of text outlining the process for mitigation identification, to demonstrate that the requirement for mitigation has been factored into the Project's plans. | As multiple rows of the issues log are covered by this point we cannot confirm a single RAG status | D19, D20, D21, D25
MM6 | MMMitgation Plan and/or SIP | There is limited evidence that ADDs are effective for deterring dolphin species. Further discussion is needed on ADD duration for the PTS zone, this links to MM1. |  | Natural England recommend that Hornsea 4 commits to using PAM as well as MMObs and ADD for pre-piling searches. The exact timings of the ADD duration could be finalised post-consent. However, the principles which determine ADD duration should be discussed and agreed at this stage (i.e. whether ADD duration corresponds to the instantaneous PTS zone or the cumulative PTS zone). | As multiple rows of the issues log are covered by this point we cannot confirm a single RAG status | D27, D28
MM7 | Project overlap in-combo | We requested a figure be provided showing how overlap between projects can be taken into account in the in-combination assessment and offer a reduction in spatial area by 15-25% . This is important as the Applicant considers this approach provides certainty that primary mitigation will be sufficient. A figure was provided at DL2 but had two inconsistencies. An updated figure was due to be provided at DL5 but we do not think it has been provided. |  | Provide an updated figure to include: -the contribution of Hornsea 4 to winter area min/max figures - the contribution of Dogger Bank C to in-combination disturbance in the summer max scenario |  | D18

## Marine Processes
REF | Outstanding Issue | Detail | Current RAG | Proposed Action | RAG if Action addressed | Issue Log Refs
MP1 | Controlled Flow Excavator (CFE). | Although the use of a Controlled Flow Excavator has become standard within offshore windfarm applications, and assessments are made on the assumption that the seabed and associated habitats will recover in the short-term (up to 2 years), we highlight that there is very little evidence available to support this assumption. |  | Natural England would like to see monitoring secured within the Outline Marine Monitoring Plan which will validate the assumptions made in the ES and other assessments. |  | E13
MP2 | HDD Exit Pits | In order for Natural England to agree with the Applicant's conclusions regarding the signifcance of impact of the HDD exit pit, we would need confirmation that the sedbed profile will be restored and that the excavated material will be used to do this. The Applicant has indicated that this will be addressed in the Cable Specification and Installation Plan. |  | The current version of the outlined Cable specification and instlation plan does not mention HDD exit pits. Natural England would need to see this document updated to include our advice on restoring the seabed profile following excavation of exit pits before the issue can be resolved. |  | E19
MP3 | Cofferdams | Natural England requested further clarification from the Applicant regarding the duration of the placement of cofferdams. |  | This point has been addressed by the Applicant, however we would wish to see this clarity secured within the DCO in order to avoid future confusion. |  | E21
MP4 | Drill Arisings | Following review of REP5-083 G5.5 Clarification Note on Drill Arisings and Deposited Sediments Natural England would have concerns if the drilling mounds were as high as the MDS (10m), particularly if they did not winnow away as quickly as anticipated. |  | Natural England request the applicant confirms the number/location height of mounds post construction and that should any mounds stand at a height greater than 3m (i.e. the maximum height of the scour protection in the Array Area), we would expect further monitoring to determine if the material is winnowing away as expected, with the option for intervention to remove some of the material if it persists. If this can be appropriately secured within the DCO/DML or relevant certified document, Natural England would consider this issue resolved (subject to the clarification highlighted above). |  | Cell M57 of Natural England Risk and Issue Log (Marine Process Tab)
MP5 | Decommissioning and Post Operational Impacts | Throughout the Examination we advised that the Applicant / examiner gives full consideration to the management of the export cables and other infrastructure both through the lifetime of the project, and beyond, with particular consideration of the nearshore Zone. The impacts of infrastructure left in situ beyond the lifetime of the project needs to be assessed in terms of impacts on marine processes. Similarly, the benefits and impacts of infrastructure removal at decommissioning needs to be evaluated in terms of marine processes. |  | As this is unlikely to be addressed within the remaining examination period, we advise that this assessment is undertaken prior to the submission of the draft decommissioning plan and that this requirement is sercured within the DCO. |  | E53, E54,E55
MP6 | Smithic Bank
MP7 | Sandwave clearance and sediment disposal within Smithic Bank | The Marine Processes Supplementary report REP4-043 confirms that bedform clearance for sandwaves will not occur across Smithic Bank (2.4.1.2) and that excavated sediment will either be side cast or dispersed using a controlled flow excavator, therefore sediment should be retained within the sandbank system. This is yet to be secured within the DCO. |  | These points to be secured within the DCO. See also monitoring requirements highlighted in MP11 below |  | E28, E31
MP8 | Cable Installation repair and remediation within Smithic Bank | Moderate elevation changes to the sandbank and significant changes to sandbank morphology through cable installation activities, associated cable protection, and remedial works by Hornsea Four alone, or in-combination with other developments, could alter the nearshore hydrodynamic regime, sediment transport (including longshore flux), shoreline response to storms, and alter shoreline morphology over the long-term. |  | Natural England offered suggestions for the mitigation of these impacts within AS-048 and our joint memo with MMO/Cefas for our advice on proposed mitigation and monitoring for Smithic Bank. We would welcome further discussions with the Applicant as part of the SoCG process to determine if suitable measures to reduce these impacts can be identified. |  | E28
MP9 | Placement of cable protection accross Smithic Bank | The Applicant has committed to 5% cable protection across Smithic Bank. However, we remain concerned that cable protection placement on Smithic Bank by Hornsea Four alone, and in-combination, could affect the hydrodynamic and sediment transport processes, and lead to morphological change of the sandbank over the lifetime of the project. |  | We seek a commitment to have no cable protection inshore of the 20m depth contour in order to avoid impacts to sediment transport, and we would wish to see this secured in the dML/DCO in order to fully rule out the potential for significant impacts/adverse effects. Should the ExA/SoS take an alternative view and consider that a 5% requirement can remain, it remains the case that a more detailed assessment would be required to understand the potential impacts of rock placement on Smithic Bank, both alone and cumulatively/in combination. As the detail of the likely scale and location of the rock placement will not be understood until post consent survey work has been undertaken to inform a cable burial risk assessment, we would advise that the DCO/dML should require that a plan is produced prior to construction that quantifies a more precise requirement (i.e. location and extent) within and around Smithic Bank and then revisits the findings of the Environmental Statement and subsequent updates. This plan would then need to be be subject to Assessment/HRA prior to discharge by the MMO. If electing to pursue this option, the ExA/SoS may wish to seek assurance from the Applicant that suitable alternatives/mitigation/remediation would be available should significant impacts be determined at this stage. See also monitoring requirements highlighted in MP11 below |  | E28, E29, E30
MP10 | Dogger Bank A&B Cable Crossing | In G5.33, the Applicant states that some analysis has been carried out to confirm the geomorphological boundary of Smithic Bank. However, we have not seen this analysis. The Applicant has committed to moving the Dogger Bank A&B Cable Crossing as far east as possible, past the 20m depth contour. Any further mitigation to move the crossing further seawards, is dependent on the final location of the Dogger Bank A&B Cables and the decision to use a HVAC or HVDC electrical system. Therefore, we are currently awaiting updated information on the position of the Dogger Bank A&B Cables. |  | Natural England notes the response to our deadline 5 advice. Based on the proposed cable crossing location and the MDS for the rock berm height (3m) we would be unable to rule out the potential for significant impacts to Smithic Bank. However, should the berm height be set at 1.8m we would have confidence that the risk of impact was reduced to a more acceptable level. This should be secured in teh DCO/DmL. We note that the 3m option for the MDS is to allow for protection from anchor strike. Given the location of the cable crossing we would question if this level of precaution is necessary and whether a 1.8m berm would offer sufficient protection. We also advise that appropriate monitoring of the order limits between the Holderness Coast and 1km seawards of the Cable Crossing is secured in the DCO/dML, and that additional mitigation/remediation can be triggered through an appropriate mechanism if the impacts are greater than anticipated. We would also like to see options to move the crossing further seaward explored as part of the layout plan, to ensure that the mitigation heirarchy (avoid/reduce/mitigate) continues to be followed in the post consent phase of the project. We would welcome the inclusion of this as a commitment and would like to see this appropriately secured within the DCO/dML. See also monitoring requirements highlighted in MP11 below |  | E26, E27
MP11 | Monitoring plan | We are concerned that the form and integrity of Smithic Bank may be affected by construction and O&M activities over the lifetime of the Hornsea Four project alone, and in combination. We currently do not know whether Smithic Bank is a closed, semi-closed or open system with regards to sediment transfer to/from the Holderness Coast and further afield. The comparative study of bathymetric data presented in the Supplementary Report, G4.9, shows a general trend of lowering of South Smithic over the long-term. Given this uncertainty regarding the mechanism for sandbank lowering, we are concerned that instalation of cables across Smithic Bank could lead to scour, elevation or morphological changes to Smithic Bank. |  | Natural England welcome the proposal to monitor the cable corridor from the Dogger Bank cable crossing across Smithic Bank to the coastline REP5a-017 (G5.33). However, we advise high-resolution swath bathymetry, total seabed coverage surveys, of the Order Limits Area between the Holderness Coastline and Smithic Bank, between Smithic Bank and the Dogger Bank A&B Cable Crossing, and to 1km seawards of the Cable Crossing are all required. This is to confirm the conclusions of the ES that: (a) cable installation will have no detrimental impact on the sandbank (in terms of accelerated sandbank lowering or migration); and (b) any impacts from multiple cable remedial and maintenance activities over the lifetime of the project will not lead to morphological change of the sandbank. The first step in this monitoring plan should be a pre-construction survey, in order to establish a robust and accurate baseline. This should then be followed by a post-cable installation survey every 6 months for 2 years (including two winters periods and one summer) and further surveys every 5-years for the duration of the project. Comparison reports should be produced, incorporating a comparison with existing bathymetric survey data (as presented in G4.9 Supplementary Report). These will enable qualification and quantification of any volumetric and spatial extent changes to the sandbank. |  | E28, E29, E30
MP12 | Flamborough Front
MP13 | MDS for GBS foundation structures | In G5.33, the Applicant has stated that the Maximum Design Scenario has been reviewed for Gravity Base Foundations and confirms that they will be utilised at a maximum of 80 of the 180 WTG foundation locations. This refinement of the MDS is very welcome. However, we remain concerned that the Hornsea Four array, alone/in-combination, has the potential to lead to increased vertical mixing and have an adverse effect on the Flamborough Front. Due to variable nature and uncertanties associated with Flamborough Front, and the wide range of scenarios potentially available under the MDS it is difficult to identify and model a realistic worst case for each relevant marine process receptor in order to exclude the potential for signficant impacts and the potential for Adverse Effect on Integrity on the features of a number of desginated sites. Whilst these concerns remain for all foundation types, GBS have the potential to give rise to signficantly greater impacts and therefore their inclusion within the MDS substantially increases the risk of significant impacts occuring. |  | We advise that GBS foundations be removed as a design option, in order to reduce vertical mixing and minimise impacts to stratification as far as possible within the project design. See also rows MP14, 15 and 16 |  | E4, E5, E42, E46
MP14 | Minimum spacing between foundations across the array/wake-to-wake interactions | In G4.9 the Applicant suggests that with a minimum spacing of 810m between foundations across the array, that wake to wake interactions are unlikely to occur. However, there is considerable evidence that suggests that wakes could extend > 1km leading to wake-to-wake merging (see Foster, 2018). Therefore, the horizontal extent of the increased mixing of the water colum and decrease in stratification, could well extend beyond the footprint of the array. |  | A key concern is the underestimation of the spatial extent of wake/plume interaction due to monopile/pin pile foundations. Evidence from other OWFs in the North Sea has shown the potential for wakes to extend > 1km and for wake-to-wake merging to occur (see Foster, 2018). We have not been able to confirm array layout as the Applicant has not yet provided full details of their design. As further detail on on the foundation type and layout will be available at the post consent phase, should the ExA and SoS be minded to proceed on the basis of the information available, Natural England advise that a clear requirement is included within the DCO/dML conditions to fully assess the the proposed layout plan prior to discharge, with the option to include further measures to avoid, reduce or mitigate impacts until it can be demonstrated that signficant impacts can be ruled out. This approach of "deferred assessment" is not without its own challenges and risks. Therefore we would advise that this is only considered where the ExA/SoS are satisfied that signficant impacts can be avoided with all steps taken at this stage to reduce the risks as much as possible. i.e. through removing the Gravity Base option (See MP13 above) It is also essential that approprate monitoring to detect changes and trigger any necessary counter measures is secured ( See MP16 below) |  | E42, E46
MP15 | Minimum spacing between foundations across the array/scour | Natural England do not consider that sufficient evidence has been presented to support the Applicant's assumption that “All foundations are considered sufficiently separated to mitigate the chance of group scour.” Group scour is known to extend beyond the influence of the foundation with large diameter structures such as GBS or jacket structures and, therefore, has a large cumulative environmental effect when taking into the whole Hornsea 4 array. |  | At this stage in the Examination we do not expect that the Applicant will make further revisions to their assessments, therefore we would advise that the ExA and SoS should have regard to the high value of this receptor by ensuring that the risk of potential impacts are managed as far as possible and that approprate monitoring to detect changes and trigger any necessary counter measures is secured. whilst our concerns relate to the potential impact of all foundation types, the risk is significantly greater with the use of Gravity Base type foundations. Given this, our advice remains that GBS should be removed as the MDS for turbine foundations. As further detail on on the foundation type and layout will be available at the post consent phase, should the ExA and SoS be minded to proceed on the basis of the information available, Natural England advise that a clear requirement is included within the DCO/dML conditions to fully assess the the proposed layout plan prior to discharge, with the option to include further measures to avoid, reduce or mitigate impacts until it can be demonstrated that signficant impacts can be ruled out. This approach of "deferred assessment" is not without its own challenges and risks. Therefore we would advise that this is only considered where the ExA/SoS are satisfied that significant impacts can be avoided and that all steps have been taken by the Applicant to reduce the risks as much as possible prior to consent (i.e. through the removal of GBS). Natural England welcomes the Applicant's comment that pre and post construction surveys will be used to collect data on changes in seabed topography. However we require that this is adequately captured in the OMMP so it is clear that these post construction geophysical surveys are being used to validate assessments made within the Environmental Statement. This is important information for when the MMO is signing these documents off. |  | E51, E52
MP16 | Monitoring plan | The monitoring plan proposed in G5.33 focuses (initially) only on changes to near-field stratification at three GBS foundations across Hornsea Four array. We do not consider this to be sufficient to provide an adequate baseline against which long-term changes to stratification can be measured and assessed either across the Hornsea Four array, or within the wide zone of impact. |  | In order to understand the potential impacts of the Hornsea Four development, alone and in-combination, on the seasonally stratified sea will require a robust monitoring strategy for the lifetime of the project. The initial step to monitoring proposed in G5.33, aims to assess changes to stratification at three locations within the array This is useful in terms of understanding small-scale physical processes, but it would be difficult to identify three locations that are representative of the whole array based on this plan. Therefore, we advise that the first step should be to use high-resolution satellite imagery to examine wakes, sediment plumes, and chlorophyll concentrations across the array and the wider zone of impact beyond the array. We recommend this monitoring should cover a temporal period to include the build-up of seasonal stratification through to breakdown of seasonal stratification. Secondly, the array-scale monitoring should be used to identify representative locations for the near-field monitoring of changes to stratification. Further consideration is also needed of the sub-surface/mid water chlorophyll concentrations. Over the long-term, there is a need to carefully consider monitoring changes to stratification, currents, suspended sediment concentrations, pH, turbulence, light, and chlorophyll. This monitoring requirement should be captured within the Outline Monitoring Plan. |  | E42, E46

## Benthic and Intertidal
REF | Outstanding Issue | Detail | Current RAG | Proposed Action | RAG if Action addressed | Issue Log Refs
B1 | Priority Habitats | Where priority habitats are encountered (such as Sabellaria Reef or Stony reef) either during construction or operation and Maintenance activities, measures should be taken to ensure impacts are avoided in order to reduce the potential for significant impacts and to statisfy requirements under the Natural Environment and Rural Communities (NERC) Act 2006. Current commitments only seek to avoid impacts to priority habitat "where possible" through the micrositing of infrastructure and these commitments only relate to the construction activity. Natural England would like to see further consideration of measures to reduce or mitigate impacts where micrositing to avoid the habiats is not possible secured within the DCO/dML. Natural England would also like to see a similar commitment to avoid/reduce impacts to priority habitat at the O&M stage (noting that micrositing is less likely to be an option at this stage) secured appropriately within the DCO/dML. |  | Current commitments only seek to avoid impacts to priority habitat "where possible" through the micrositing of infrastructure and these commitments only relate to the construction activity. Natural England would like to see further consideration of measures to reduce or mitigate impacts where micrositing to avoid the habiats is not possible secured within the DCO/dML. e.g. through the addition of Priority habitat to condition 13 (1) (c) (ix) of Schedules 11 and 12. Co48 & Co84 should be explanded to include consideration of options to avoid/mitigate impacts to Priority Habitat where micrositing is not possible and we would welcome confirmation that Co48 and Co84, as well as the construction method statement, include all aspects of construction including site preparation works and sediment disposal. We would like to see a commitment to avoid/reduce/mitigate impacts to priority habitat as far as possible during the O&M phase, and a reference to this within the outline O&M plan. |  | F5, F6, F27
B2 | MDS sand wave clearance | Natural England are concerned that sand wave clearance is required along the full length of the cable corridor and no survey data has been used to refine this down in accordance with Paragraph 2.6.196 of NPS EN-3. As the applicant has made their position clear within the examination that they are not going to adjust this any further, therefore a more detailed assessment of the requirement for seabed preparation will not be made until the pre construction phase. |  | Natural England notes that whilst the commitment to no sandwave levelling over Smithic Bank may reduce the risk of significant impacts to nearshore bethic receptors and sites such as Flamborough Head SAC/SPA, the same cannot be said for those further offshore such as Holderness Offshore MCZ. Should the MDS be consented as it stands, there would be no mechanism to ensure that additional steps are taken in the pre construction phase to ensure impacts to designated sites and priority habitats are avoided, reduced or minimised as far as possible. We therefore suggest that condition 13 (1) (c) (ix) of schedules 11 and 12 of the DCO are expanded to ensure that the construction method statement includes details of the means to address impacts on national sites (ie. MCZs, SSSIs, HPMAs) and priority habitat. |  | F9

## Fish and Shellfish
REF | Outstanding Issue | Detail | Current RAG | Proposed Action | RAG if Action addressed | Issue Log Refs
F1 | EMF | Recent research has shown linkages between EMF and fish and shellfish behaviour. Natural England requested a full impact assessment was completed. Figures for EMF levels on the Hornsea 4 cables is stated by the Applicant to be below those shown in Scott et al to have impacts. |  | Natural England have reviewed the Applicants answer to ExQ NVL.2.2 and welcome the additional explanation as to why the EMF would be lower than levels suggested elsewhere. We would continue to advocate for a proper assessment of all information relating to this issue, but are generally satisfied that the information provided during examination provides sufficient justification. We recommend a reading of EMF levels over the cables is done once operational to provide some real life data to validate the predictions and provide additional evidence to support industry and research moving forward. Adaptive risk management style approach might be required if the recorded levels are higher than predicted. |  | G1
F2 | Piling/ herring | Natural England do not feel that the approach to identifying the peak herring spawning period is precautionary enough. We have put our views forward on the reasons for this. |  | Given the limited amount of time remaining within the Examination, and recognising that the MMO as advised by Cefas are also looking for the piling restriction period to be extended; we defer to Cefas’ expertise in determining a more suitable period. |  | G2