## Title page
THE PLANNING ACT 2008
THE INFRASTRUCTURE PLANNING (EXAMINATION PROCEDURE) RULES
2010
Natural England's Risk and Issues Log - Deadine 8 Submission.
For:
The construction and operation of Hornsea Project Four Offshore Wind Farm, located approximately 69 km from the East Riding of Yorkshire in the Southern North Sea, covering an area of approximately 468 km2.
Planning Inspectorate Reference EN010098
18th August 2022

## How to read Risks and Issue Log
"Natural England have created this Risk and Issues Log to track progress through the Hornsea Four examination process. We intend to submit the Risks and Issues Log at each deadline and mark issues with a colour from our RAG scale depending on the level of significance of the issue. It should be noted that the colour scale is different from that used in the Statement of Common Ground provided by The Applicant. The Risk and Issues Log is split into multiple tabs in line with the Appendices of our Relevant Representations submission. B - Ornithology C- Compensation D - Marine Mammals E - Marine Processes F - Benthic and Intertidal G - Fish and Shellfish H - Onshore Ecology, Landsacpe & Seascape - this tab has been hidden as we have no outstanding issues. I - DCO (added at deadline 6) The documents that we have considered in forming our position at each deadline Any issues added to the log during Examination (not included in Relevant Reps) are highlighted in Red and then coded according to RAG status. Natural England highlights that as this is the first time we have implemented the Risk and Issues log in this way, we may make revisions and updates to the format as the exmination progresses. Any changes we make will be captured on this tab, therefore we would request that it is reviewed in conjunction with our advice at each deadline." For submission at the final deadline Natural England have expanded each tab of the issues log to reveal previously closed out issues. We have also populated the final column with the last comment made on each issue to enable final status to be easily assessed. Please note, due to the short timeframe between Deadlines 7 and 8 we have been unable to review all documents submitted. There could therefore have been progress made beyond what is recorded here. [New Text is in red]
Purple Note for Examiners and/or competent authority. May relate to DCO/DML
Red Natural England considers that unless these issues are resolved it will have to advise that (in relation to any one of them, and as appropriate) it is not possible to ascertain beyond reasonable scientific doubt that the project will not affect the integrity of an SAC/SPA/Ramsar and/or significantly hinder the conservation objectives of an MCZ and/or damage or destroy the interest features of a SSSI and/or comply fully with the Environmental Impact Assessment requirements.
Addressing these concerns may require the following:
new baseline or survey data; and/or
significant revisions to baseline characterisation and/or impact modelling and/or
significant design changes; and/or
significant mitigation
In addition, Natural England may use this category to highlight where there is a significant risk that an issue will not be sufficiently addressed within the Examination timescales. Consequently, issues that start out as Amber may progress to Red in the latter stages of the examination.
Amber Natural England does not agree with the applicant’s position or approach and consider that this could make a material difference to the outcome of the decision-making process for this project.
Natural England considers that these matters may be resolved through:
provision of additional evidence or justification to support conclusions; and/or
revisions to impact assessment methodology and/or assessment conclusions; and/or
minor to moderate revisions to impact modelling; and/or
well-designed mitigation measures that are adequately secured through the draft DCO/dML and/or
amendments to draft plans
If these issues are not addressed or are unlikely to be resolved by the end of the Examination, then they may become a Red risk as set out above.
Yellow Natural England doesn’t agree with the Applicant’s position or approach. We would ideally have liked this to be addressed prior to the examination but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process and would not expect these matters to be a ongoing focus of the examination. However, we reserve the right to revise our opinion should further evidence be presented.
It should be noted by interested parties that just because these issues/comments are not raised as significant concerns in this instance, it should not be understood or inferred that Natural England would be of the same view in other cases or circumstances.
Once a Risk or Issue has been categorised as yellow, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be hidden at subsequent deadlines in order to rationalise the risk and issues log.
Green Natural England is in broad agreement with the Applicant’s approach and has no significant outstanding concerns. As above, we reserve the right to revise our opinion should new evidence be presented. Once a Risk or Issue has been categorised as green, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be hidden at subsequent deadlines in order to rationalise the risk and issues log.

## Summary
Point | Natural England’s Current Position | RAG Status | Actions Required to close out the issue
Offshore Ornithology (Appendix B)
Project Description | The project parameters are clearly defined with respect to offshore ornithology
Worst Case Scenario (WCS) and Maximum Design Scenario (MDS) | Natural England consider the maximum design scenarios for impacts on offshore and intertidal ornithology receptors to be clearly defined and are representative of the likely Worst Case Scenarios (WCS) to be used in the assessment.
Baseline Characterisation | Following further clarifications from the Applicant, Natural England agrees that the baseline data using the agreed updated approach and modelling is fit for purpose. The Applicant has supplied design-based data for all relevant species and has revised their modelling in line with advice from NE and CREEM. |  | We note that this has currently been provided as an additional document. We recommend that the ES is updated to inlcude the correct baseline and associated updated assessments.
Data Gaps | Sufficient data has been provided to run the CRM, PVA and displacement assessments. However, having identified significantly high numbers of auk within the development area in August and September, we requested further information from the Applicant to further our understanding of the apparent significance of this area to further inform our advice. This included: -The importance of the array area to auks – specifically the colony origin, behaviour and age structure of auks present in the site during August and September. -Site-specific age data (including the proportions of birds aged and numbers of adult and sub-adult birds) for focal species to inform the proportions of adults present within specific areas at different times of year for apportioning to colonies. |  | Given the stage we are at in the Examination this will need to be addressed through a more precautionary approach to determining the impacts. Consequently we're moving this to purple as we do not expect the Applicant to be making further data submissions.
EIA - Identified impacts | Natural England generally agree with the impact pathways identified and assessed, but do not consider that indirect effects have been adequately assessed for some relevant receptors (gannet, kittiwake, guillemot, razorbill and puffin). We note that the Applicant has provided an indirect effects report but note that this is largely inconclusive. |  | We do not consider this issue resolved, but at this stage in the Exmination it is best addressed through a more precautionary approach to considering the impacts of indirect effects.
Modelling | Natural England continue to fundamentally disagree with the Applicant’s approach to multiple aspects of the modelling, however with the exception of the two points below, we are satisfied that the Applicant has provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. We disagree with the exclusion of the counterfactual of population size from PVA modelling outputs. An error has been identified in the PVA tool which could affect some of the Applicant's kittiwake modelling. |  | Provide the counterfactual of population size for PVA modelling. Provide updated PVA modelling for kittiwake where necessary.
EIA - Methodology | Natural England continue to fundamentally disagree with the Applicant’s approach to multiple aspects of the ornithology assessment, however we are satisfied that sufficient information has been provided for Natural England to undertake an assessment of impacts in line with our SNCB advised approach.
EIA - CEA | Natural England agrees with the projects included within the cumulative assessment. Natural England have taken LBBG and herring gull through the cumulative assessment for EIA and note that, despite the very small numbers of predicted impacts, the cumulative total for LBBG would lead to an increase in baseline mortality of >1% based on the BDMPS population. We will take this into consideration when forming our positions on the impacts of the project therefore we do not require anything further from the Applicant at this time.
EIA - Conclusions | Natural England is not able to comment in full on this at this time. However, we note that our position in recent Examinations for cumulative impacts has been that we are unable to rule out significant adverse impacts at an EIA scale on kittiwake, razorbill, guillemot, gannet and greater black-backed gull due to cumulative collision mortality and/or displacement impacts for all projects up to and including Hornsea 3, Norfolk Vanguard, Norfolk Boreas, East Anglia One North and East Anglia Two. This conclusion is irrespective of whether Hornsea 4, or indeed Dudgeon Extension Project and Sheringham Shoal Extension Project (‘DEP and SEP’) and Rampion 2, are included in the cumulative totals or not. Any further impact to the existing totals from Hornsea 4 would reinforce Natural England’s EIA conclusions regarding these species.
HRA - Screening | The Applicant has not considered impacts from Hornsea 4 in the cumulative assessment if the project alone assessment was “negligible”. Natural England disagree with this approach.
HRA - Methodology | Natural England continue to fundamentally disagree with the Applicant’s approach to multiple aspects of the ornithology assessment, however we are satisfied that sufficient information has been provided for us to undertake out assessment.
HRA - Conclusions | As noted in Section 3 of our DL6 cover letter, we are now able to rule out adverse effects on gannet alone and in-combination with other consented plans and projects at FFC SPA. Our position on being unable to rule out AEoI for kittiwake in-combination with other plans or projects remain unchanged.
Marine Mammals (Appendix D)
Project Description | Project parameters are clearly defined in a marine mammals context
Worst Case Scenario (WCS) and Maximum Design Scenario (MDS) | Natural England is content that the WCS for the receptor under the MDS has been assessed.
Baseline characterisation | We consider the data collected, when used in conjunction with other available data, is sufficient.
Data Gaps | Natural England is content that there are no significant data gaps.
EIA - Identified impacts | All potential pressures have been identified.
EIA - Methodology | Natural England are content that our outstanding concerns with the EIA methodology have been resolved.
EIA - CEA | The information provided by the applicant is sufficient to address our outstanding concerns with respect to vessel collision risk, however as it is based on assumptions about other industries we are marking this yellow.
EIA conclusions | Natural England broadly agrees with the assessment conclusions.
HRA screening | The Applicant provided a note demonstrating no AEOI rather than no LSE to the harbour seal designated feature of The Wash and North Norfolk Coast SAC from vessel collision risk. Nevertheless, we agree with the conclusions of no AEoI and acknowledge that the Applicant has presented an assessment that can be utilised by the Examining Authority in its RIES. |  | For consistency and completeness the RIAA should be updated to reflect that LSE cannot be excluded for this pathway.
HRA Methodology | We are supportive of the novel methods used to apportion impacts to SACs, and believe it makes use of the best available evidence.
HRA Assessment | The Applicant provided a note demonstrating no AEOI rather than no LSE to the harbour seal designated feature of The Wash and North Norfolk Coast SAC from vessel collision risk. Nevertheless, we agree with the conclusions of no AEoI and acknowledge that the Applicant has presented an assessment that can be utilised by the Examining Authority in its RIES. |  | For consistency and completeness the RIAA should be updated to reflect that LSE cannot be excluded for this pathway.
HRA in-combination | Natural England defer to the MMO as to whether it is appropriate for geophysical surveys to not be covered in the DCO. However, as they are a known activity directly connected to the construction (and in some cases, operation) of wind farm development they should be given a high-level assessment within the ES and RIAA, even if they are then going to be undertaken under a separate licence (similar to UXO clearance operations). |  | Natural England request that the Applicant provide information on the likely geophysical equipment and commit to mitigation and/or the inclusion of text in relation to the mitigation process for geophysical surveys.
HRA Assessment conclusions | Owing to concerns regarding the current over-reliance on the SIP process to manage in-combination impacts to the SNS SAC, Natural England cannot rule out AEOI on the SNS SAC. Natural England's position is that a commitment should be made to deliver mitigation, with the option to demonstrate that it is not needed post-consent. We acknowledge Hornsea 4's position of not commiting to specific mitigation measures due to potential advances in technology and welcome that the need for mitigation has been budgeted for (pers comm). |  | We advise that the DCO condition is updated to secure submission of the SIP no later than 6 but no earlier than 9 months prior to construction.
Marine Processes (Appendix E)
Project Description | Natural England have raised a number of points for clarification and have suggested areas that should be secured within the DCO for future clarity. (See Tab E for further details).
Worst Case Scenario (WCS) and Maximum Design Scenario (MDS) | Although we welcome the elements of further refinement within REP4-043, Natural England's broad concerns relating to the precautionary nature of some of the MDS, and the difficulties this then poses in ensuring a realistic worst case scenario for marine process receptors is assessed, remain unchanged. This approach conflicts with the principles of the ‘mitigation hierarchy’ and the emphasis within it on avoiding and reducing impacts. |  | At this stage in the Examination we consider it unlikely that the applicant will provide further evidence or further refine their assessments. Therefore Natural England's advice now focusses on reducing the level of risk to designated sites and associated receptors through identifying potential design changes and/or advising on monitoring required
Baseline characterisation | Natural England note and welcome the Applicants supplementary report. We consider that the Applicant has now drawn upon all of the available evidence that we are aware of, however a large number of uncertainties in relation to Smithic Bank and its interrelationship with the Holderness Coastline and the form function and influence of the Flamborough Front. We also continue to disagree with the Applicant's characterisation of the environmental value of Smithic Bank, the Holderness coastline and Flamborough Front and continue to advise that these are considered High Value. We also maintain that Flamborough Front should be considered to be of high sensitivity in the absence of informaton to the contrary. |  | At this stage in the Examination we consider it unlikely that the applicant will provide further evidence or amend their position on environmental value and update their assessments accordingly. Therefore Natural England's advice now focusses on reducing the level of risk to designated sites and associated receptors through identifying potential design changes and/or advising on monitoring required
Data Gaps | In G4.9, the Supplementary Report, the Applicant provided further information on the position and formation of the Flamborough Front relative to the Hornsea Four array, and some further information on the geomorphology of Smithic Bank. However, there are still considerable gaps in the evidence for both these features. Based on recent research, there is the potential for large-scale changes to annual primary productivity due to the Hornsea Four array, either alone or in-combination with a cluster of OWFs, due to impacts to the Flamborough Front. In regards to Smithic Bank, the Applicant has used partial bathymetric data to inform the geomorphological baseline from which only macro-scale changes to the sandbank can be inferred. There are also insufficient data to inform understanding of the southern part of South Smithic and sediment exchange between this part of the sandbank and the Holderness coastline. |  | The Applicant has marshalled all of the evidence that we are aware of, nevertheless with the project as currently designed we are not able to exlclude the risk of significant/adverse effects arising. NE's advice now focusses on reducing the level of risk to designated sites and associated receptors, through identifying design changes and advising on the monitoring required to detect change and trigger counter measures.
EIA - Identified impacts | The Marine Process Supplementary works report went some way to addressing our concerns around the identification of impacts. Our expectation would be that this would then inform an updated ES chapter with updated assessments. It is possible that this could result in a material difference to the conclusions within the ES. We also maintain that designated sites should be considered as marine receptors within the ES. Whilst we acknowledge that this might result in a material risk for sites that are subject to HRA or MCZ assessments, this does not capture SSSIs, particularly those that are not undepinning an SAC/SPA and means that Dimilington Cliff SSSI remains unassessed. |  | At this stage of the Examination we consider that an update to the ES chapter and revised assessments are unlikely to be forthcoming. Therefore NE's advice now focusses on reducing the level of risk to designated sites and associated receptors, through identifying design changes and advising on the monitoring required to detect change and trigger counter measures.
EIA - Methodology | The Marine Process Supplementary works report REP4-043 goes some way to addressing our concerns as the assessment follows a receptor led approach. However, not all marine process receptors are covered within the report and not all aspects of the proposal are fully assessed. It is possible that this would result in a material difference to the conclusions within the ES. |  | At this stage of the Examination we consider that an update to the ES chapter and revised assessments are unlikely to be forthcoming. Therefore NE's advice now focusses on reducing the level of risk to designated sites and associated receptors, through identifying design changes and advising on the monitoring required to detect change and trigger counter measures.
EIA - CEA | Natural England considers that there is a potential risk of cumulative impacts as a result Hornsea Four and Northern Endurance Partnership, Scotland to England Green Link 2 and Dogger Bank South constructing and operating within similar timeframes. Therefore should these projects make an application prior to the determination of this case, Natural England advise that the cumulative impacts will need to be assessed, including within the HRA.
EIA conclusions | Given our concerns relating to the identification of receptors, data gaps and incomplete assessments, we are unable to agree with the conclusions of the ES at this time. Whilst we welcome the additional work undertaken by the Applicant , we recognise that considerable uncertainty remains in relation to the baseline characterisation, and are unable to agree with the conclusions drawn by the applicant in a number of areas.
HRA screening | Natural England notes that only Flamborough Head SAC has been screened in for further assessment of changes to physical processes during operation and increased levels of suspended sediment during construction, operation and decommissioning. Based on the information currently available, we consider that Flamborough Head SAC should also be screened in for further assessment of changes to physical processes during construction and decommissioning, as well as beyond the operational lifetime of the project, as well as for potential changes to the hydrodynamic regime (arising as a result of potential impacts to the Flamborough Front). Flamborough and Filey Coast SPA should also be screened in for the same impacts. We also consider that the Humber Estuary SAC/SPA/Ramsar should also be screened in for further assessment of changes to physical processes throughout all stages of the project, and that the Southern North Sea SAC should be screened in for changes to hydrodynamic regime (Flamborough Front) and sediment transport regime.
HRA Assessment conclusions | As a result of Natural England’s concerns relating to the LSE Screening and evidence gaps within the Environmental Statement, we are currently unable to exclude beyond reasonable scientific doubt the potential for impacts to Flamborough Head SAC, Flamborough and Filey Coast SPA, Humber Estuary SAC/SPA/Ramsar and Southern North Sea SAC. Additional measures to avoid/reduce/mitigate potential impacts may need to be explored.
MCZ Screening | Natural England note that the applicant has screened in Holderness Inshore MCZ and Holderness Offshore MCZ into assessment due to the potential for impacts from increased suspended sediment. In light of our comments on the ES chapter, we advise that potential impacts to physical process attributes are also assessed. For habitat features this includes: Supporting processes –energy exposure, supporting processes –sediment movement and hydrodynamic regime. For the Spurn Head Geological feature of Holderness Inshore, this includes: Extent of supporting geomorphological processes and associated sediments, Sediment transport pathways and connectivity to wider environment, and Extent and distribution.
MCZ Assessment Conclusions | As a result of Natural England’s concerns relating to the screening of potential impact pathways, and the evidence gaps within the ES, we are currently unable to exclude beyond reasonable scientific doubt, the potential for significant impacts to Holderness Inshore MCZ and Holderness Offshore MCZ. Additional measures to avoid/reduce/mitigate potential impacts may need to be explored.
Benthic & Intertidal (Appendix F)
Project Description | The project parameters are clearly defined
Worst Case Scenario (WCS) and Maximum Design Scenario (MDS) | Although we welcome the elements of further refinement within REP4-043, Natural England's broad concerns relating to the precautionary nature of some of the MDS, and the difficulties this then poses in ensuring a realisitic worst case scenario for benthic receptors is assessed, remain unchanged. This approach conflicts with the principles of the ‘mitigation hierarchy’ and the emphasis within it on avoiding and reducing impacts. |  | At this stage in the Examination we consider it unlikely that the applicant will provide further evidence or further refine their assessments. Therefore Natural England's advice now focusses on reducing the level of risk to designated sites and associated receptors through identifying potential design changes and/or advising on monitoring required
Baseline characterisation | Natural England is broadly content with the baseline characterisation. We have highlighted limitations with the assessment of priority habitat but are satisfied that this can be addressed post consent.
Data Gaps | Other than the limitations mentioned above there are no data gaps within the Benthic and Intertidal Ecology Chapter.
EIA - Identified impacts | Natural England are now satisfied that impacts have been considered. Our preference would have been for these assessments to be captured within the ES rather than additional documents to allow a clear audit trail. However, we are satisfied that this would not make a material difference to the outcome of these assessments on this occasion.
EIA - Methodology | We do not agree with the definitions used within the assessments of magnitude for permanent and temporary habitat loss |  | At this stage of the Examination we consider that revised assessments are unlikely to be forthcoming. Therefore NE's advice now focusses on reducing the level of risk to designated sites and associated receptors, through identifying design changes and advising on the monitoring required to detect change and trigger counter measures.
EIA - CEA | Natural England considers that there is a potential risk of cumulative impacts as a result Hornsea Four and Northern Endurance Partnership constructing and operating within similar timeframes. Therefore should NEP make an application prior to the determination of this case, Natural England advise that the cumulative impacts will need to be assessed, including within the HRA.
EIA conclusions | We are unable to agree with the assessment conclusions related to permanent and temporary habitat loss due to the issue raised above in relation to the methodology and definitions around different levels of magnitude. There are also a number of issues within the Marine Geology, Oceanography and Physical Processes chapter which could have implications on benthic aspects. |  | At this stage of the Examination we consider that revised assessments are unlikely to be forthcoming. Therefore NE's advice now focusses on reducing the level of risk to designated sites and associated receptors, through identifying design changes and advising on the monitoring required to detect change and trigger counter measures.
HRA screening | There are a number of indirect impact pathways described in Appendix E (Marine geology, oceanography and physical processes) of our response which require further consideration within the HRA/RIAA
HRA Assessment conclusion | Natural England notes that there is no information provided in relation to the likely disposal locations of sandwave material removed during site preparation works and would welcome clarification on this point to support the assumptions made within the assessment.
MCZ screening | There are a number of indirect impact pathways described in Appendix E (Marine geology, oceanography and physical processes) of our response which require further consideration.
MCZ Assessment conclusion | Natural England notes that there is no information provided in relation to the likely disposal locations of sandwave material removed during site preparation works and would welcome clarification on this point to support the assumptions made within the assessment.
Fish & Shellfish (Appendix G)
Project Description | Natural England is generally satisfied with the project description
Worst Case Scenario (WCS) and Maximum Design Scenario (MDS) | Natural England note that there are a number of instances whereby the MDS is based on conservative assumptions rather than being underpinned by survey data. For example, sandwave clearance and boulder clearance are based on clearance across the full length of the cable corridor, despite the baseline characterisation indicating that this will not be required. This approach conflicts with the principles of the ‘mitigation hierarchy’ and the emphasis within it on avoiding and reducing impacts.
Baseline characterisation | Natural England is broadly satisfied with data collected and baseline characterisation, although note that some of the data are old (overall 10 years). Overall, we would defer to Cefas regarding the suitability of data.
Data Gaps | It was not possible to fully assess the behavioural responses in herring in relation to piling noise. Additional information is required to establish a more accurate peak herring spawning timeframe. |  | At this stage of the Examination we consider that revised assessments are unlikely to be forthcoming. Therefore NE's advice now focusses on reducing the level of risk to designated sites and associated receptors, through identifying design changes and advising on the monitoring required to detect change and trigger counter measures. In relation to the outstanding piling issue, given the limited amount of time remaining within the Examination, and recognising that the MMO as advised by Cefas are also looking for the pilling restriction period to be extended; we defer to Cefas’ expertise in determining a more suitable period.
EIA - Identified impacts | With the addition of REP5-083 G5.5 Clarification Note on Drill Arisings and Deposited Sediments and REP3-035 & REP5-074 clarifing levels of EMF Natural England are satified that all impacts have been identified.
EIA - Methodology | It is stated that ‘where a range of significance of effect is presented, the final assessment for each effect is based upon expert judgement’. In all cases within this report the significance is scaled down to ‘slight’ which concerns Natural England.
EIA - CEA | Natural England still considers there to be an environmental risk around Hornsea Four and Northern Endurance Project occuring within the same geographical area and having construction / opperational periods overlapping. |  | As no futher information is available at this time to make a more detailed assesment, this is now a matter for the Examining Authority/Secretary of State to consider.
EIA conclusions | Piling & Herring: We are not convinced with the conclusion that there are no significant effects on herring spawning grounds as the period within which Commitment 190 restricts piling isn't precautionary enough to avoid impact. EMF: We are content with the assessment but would like to the assumptions validated post construction. |  | Piling & Herring: We defer to Cefas’ expertise in agreeing a more suitable period. EMF: We would like EMF readings to be taken over the cables once in situ and operational, to validate the assumptions made in the assessment.
HRA - Screening | Natural England would have expected to see the lamprey features of the Humber Estuary and, Tweed Estuary, River Derwent SACs considered in the AA.
HRA - Assessment & Conclusion | Natural England does not consider it possibly to carry out a meaningful assessment of impacts to migrating lamprey at this time. Given the distance between the designated sites and the project we consider the risk to these species to be low.
Onshore Ecology (Appendix H)
Project Description | Natural England is generally satisfied with the project description
Worst Case Scenario | Natural England are generally satisfied that the worst case scenario has been presented correctly with clear rationale.
Data suitability & baseline characterisation | Generally, surveys and investigation are adequate in identifying risks and mitigation to prevent harm to designated sites.
Data Gaps | No surveys have been carried out for Best and Most Versatile (BMV) soils. However, the additional data required has been identified as part of the DCO, mitigation, CoCP and EMP. Whilst this was not best practice it has no material impact as data is identified through other means. Natural England consider this issue closed.
EIA - Identified impacts | All potential pressures have been identified.
EIA - Methodology | Natural England broadly agree with the EIA Methodology
EIA - CEA | All relevant projects and pressures have been screened into the CEA at the point of submitting the EIA.
EIA - Conclusions | Natural England broadly agree with the conclusions reached within the EIA.
HRA - Screening | Natural England are generally satisfied that HRA screening has been completed to a satisfactory standard.
HRA - Assessment & Conclusions | Natural England broadly agree with the assessment conclusions and mitigation proposed is suitable.
Assessment of impacts to SSSIs | In the crossing schedule table the ‘Related Co Number’ only mentions Co1 for the SSSI crossing points. It does not mention Co18, Co124, & Co168 which contain specific measures for the SSSI and is an important part of the mitigation for crossings within the SSSI. The Applicant acknowledges that commitments 18, 124 and 168 are relevant to River Hull SSSI and will be secured via relevant DCO requirements and associated plans. Natural England are content that this is sufficent to mitigate impacts to the River Hull SSSI.
Landscape & Seascape (Appendix H)
Seascape | As with our previous responses, Natural England will limit our comments to those aspects of the scheme which have the potential to affect the special character of the Flamborough Head Heritage Coast (FHHC) and its seascape setting.
Seascape - Visual Impact | At minimum distances in excess of 68km from the coastline of East Riding, Natural England is confident that the turbines of Hornsea 4 will not be visible, when viewed with the naked eye, from onshore locations.
Seascape - Lighting | Following earlier discussions with the Applicant we no longer have concerns about the effects of the lighting proposed for the HVAC Booster Stations on the special character of the Flamborough Head Heritage Coast. See Document F2.17 for details.
Landscape | Natural England is currently assessing the Yorkshire Wolds against the criteria for designation as an Area of Outstanding Natural Beauty (AONB). The proposed development is located within the Yorkshire Wolds. Whilst initial assessment phase does not confer any additional planning protection, it is possible that this could become a material consideration in planning decisions during the determination period. Natural England would be pleased to provide further information in relation to this matter as it becomes available. The main relevant dates are for the potential designation of the Yorkshire Wolds are: Natural Beauty Assessment and identification of Candidate Area which has sufficient natural beauty for designation: by end July 2022 Consideration of the desirability of designation and selection of a proposed Boundary by end Jan 2023 Statutory and public consultation: July 2023 Statutory Notice Period: March 2024 Designation Order made and submitted to Secretary of State by end July 2024. AONBs are formally designated once a designation Order, made by Natural England, is confirmed by the Defra Secretary of State. Following the issue of the designation Order by Natural England, but prior to confirmation by the Secretary of State, any area that is subject to a designation Order would carry great weight in decisions on planning and infrastructure proposals. |  | In light of these timescales and the likely timescales for Hornsea 4's onshore construction, we would recommned that the Applicant undertakes a high level assessment based on the information available. This assessment could then be updated as appropriate as part of the discharge of DCO conditions and associated plans, taking account of any updated information. Further information can be found at: [Redacted]
Compensation (Appendix C)
Artificial Nest Structures (offshore)
Evidence gaps | Whilst nest availability is likely to be more limited offshore than onshore, uncolonised structures are available offshore. An understanding of why these structures are uncolonised will be necessary to demonstrate that nest availability is a limiting factor on the population.
Scale: Impact calculated | Natural England now considers the ornithology baseline agreed and has provided impact values in line with our advised approach. Given the late stage of Examination where this has been possible, the values have not been agreed with the Applicant.
Scale: Provision | We maintain our concerns regarding the level of risk and lack long-term resilience of provision of a single structure, however we consider that provision of ~750 nests offshore offers a reasonable prospect of delivering adequate compensation for kittiwake.
Implementation: Mechanism | A new or repurposed offshore structure will be delivered. Final designs will be decided in the post-consent steering group but we are confident in the Applicant's ability to design/adapt/build a structure.
Implementation: Deliverable before impact | Natural England welcome the increase lead in time to three breeding seasons prior to operation, however as kittiwake do not breed until they are 4+ years old breeding recruits will not enter the biogeographic population until that point. Justification is needed on the deviation from 4 breeding seasons consented for Hornsea Project Three, Norfolk Boreas and Norfolk Vanguard, demonstrating that the required colony size/growth is achievable prior to wind farm operation for the reduced lead in time.
Location: Identified | The preferred offshore structure to repurpose as an ANS has been identified (Wenlock platform). The structure is within the North Norfolk Sandbanks and Saturn Reef SAC, which is designated for features that are currently in unfavourable condition and have restore conservation objectives. |  | We would welcome further assessment by the Applicant on the implications of the proposals for the site.
Location: Secured | The Applicant is in discussion with owners/operators of platforms in NNSSR SAC.
Additionality/success criteria | As nest availability has not been proven to be a limiting factor there remains a high level of uncertainty regarding additionality. It will also depend on whether an existing colony is retained or a new colony is produced. Moving birds and/or consolidating smaller colonies would not be considered compensation. Productivity will need to be higher at the compensation colony.
Long term resilience | We are concerned that the provision of a single structure does not build in resilience over the lifetime of the project.
Adaptive management | Options for adaptive management should be included in the relevant compensaiton documents.
Monitoring | Monitoring efforts are likely to need to be wider in scope than just the artificial structure, and the current understanding of existing offshore colonies and their productivity will need to be built on to fully evidence the additional benefit of a new or repurposed structure. We acknowledge that final details such as timing/number of surveys will be decided post consent but we consider a more detailed monitoring plan (e.g. aims, objectives) should be included in the relevant compensation documents.
Bycatch reduction
Evidence gaps | The LEB trial has been restricted by confidentiality agreements and therefore has not delivered useful baseline data on bycatch in the target fishery for review. The Applicant has demonstrated that there is some level of connectivity and that the measure could benefit the National Site Network and to a lesser extent, the specifically impacted populations. However, the evidence relating to connectivity is insufficient to make any inferences on scale (e.g. quantify the proportion of breeding birds from FFC SPA that might be expected to winter in the English Channel, or indeed birds from outwith the National Site Network). Therefore, the challenge relating to the compensation measure is accounting for the uncertainty around the degree of connectivity by scaling it appropriately. This has not been considered within the Applicant's submissions.
Scale: Impact calculated | Natural England now considers the ornithology baseline agreed and has provided impact values in line with our advised approach. Given the late stage of Examination where this has been possible, the values have not been agreed with the Applicant.
Scale: Provision | A proportional reduction in bycatch is reported from vessels where the technology was deployed compared to those where it was not. We do not consider this sufficient to form a view on the likely effectiveness or scalability of the measure.
Implementation: Mechanism | A proportional reduction in bycatch is reported from vessels where the technology was deployed compared to those where it was not. We do not consider this sufficient to form a view on the likely effectiveness or scalability of the measure. The Applicant has committed to extending the LEB trial over the 2022/23 non-breeding period. Natural England welcomes this but highlights that until the results of the full trial are provided, which will be outwith the Examination, the measure will not be adequately assessed.
Implementation: Timeline | If a successful method was identified reduction could be achieved quickly, and implementation one year prior to impacts occuring would be appropriate. However, our concerns will remain unchanged until the a method is proven effective.
Location: Identified | Natural England agree with the reasoning for the identified locations for auks. We note that the Applicant now reports that a 25% reduction in bycatch of guillemots has been achieved by the application of the LEB in the target fishery. This is encouraging, but Natural England retain serious concerns relating to the reporting of the propotional reduction only. It remains unclear if the reduction in bycatch observed can be considered significant.
Location: Secured | Natural England will comment at Deadline 7.
Additionality/success criteria | If bycatch reduction can be achieved, then success criteria are relatively straightforward to define. However, the question of additionality may become pertinent if other bycatch reduction initiatives are rolled out at the industry level.
Long term resilience | Fisheries are highly dynamic in terms of gear use/focal species. This could alter bycatch levels, require new fisheries to be identified and/or require new reduction methods to be developed. The Applicant has acknowledged that trials of additional measures will be conducted if needed and that vessels the LEB are deployed on can change from year to year.
Adaptive management | Bycatch levels could be altered by fisheries being dynamic, and therefore require new fisheries and reduction methods to be identified and developed. This will need to be considered in adaptive management. |  | We consider adaptive management options should be outlined at this stage and included in the relevant compensation documents.
Monitoring | Monitoring requirements will depend on the method implemented, but will likely be straightforward as noted under Additionality. |  | We consider that the monitoring approach (aims and objectives) should be outlined now rather than in the post-consent steering group.
Predator eradication
Evidence gaps | Natural England welcome the updates on further work that has been undertaken by the Applicant to refine site selection and evidence the suitability of those sites for predator eradication. We note that work is ongoing, and should deliver a final report in autumn to "aid the final decision of location" for the predator eradication measure. We remain concerned that a fully justified location may not be identified within the examination period.
Scale: Impact calculated | Natural England now considers the ornithology baseline agreed and has provided impact values in line with our advised approach. Given the late stage of Examination where this has been possible, the values have not been agreed with the Applicant.
Scale: Provision | Natural England acknowledge the significant amount of work undertaken by the Applicant to date to identify potential sites to implement predator eradication. Table 6 in document G5.13 appears to summarise much of this work. It is suggested that this table should clarify how many of the potential (currently unutilised) nest sites identified on islands with rats present would be accesible to those rats. Although the Applicant has demonstrated that guillemots are present in areas that rats can access, it will be important to consider the degree of overlap between potential guillemot and rat habitat. Crucially, if un-utilised guillemot habitat is identified at candidate sites that is not accessible to mammalian predators it is logical to assume that some other factor is the cause of non-occupancy.
Implementation: Method | Proven techniques exist for the eradication of rats on islands, and ongoing biosecurity measures can maintain rat free status. However, eradication programs are challenging and can be prone to delays and other issues arising from unforeseen circumstances.
Implementation: Timeline | Natural England remain concerned by the proposed timeline for implementation of compensatory measures in relation to the windfarm becoming operational. Predator eradication is to be initiated 2 years prior to operation. As previously noted, the predator eradication measure must account for the lag in delivering adult birds into the breeding population. The high level of difficulty in eradicating mammalian predators should also be considered, it is highly uncertain that eradication will be achieved within the proposed timeframe.
Location: Identified | Natural England welcome the updates on further work that has been undertaken by the Applicant to refine site selection and evidence the suitability of those sites for predator eradication. We note that work is ongoing, and should deliver a final report in autumn to "aid the final decision of location" for the predator eradication measure. We remain concerned that a fully justified location may not be identified within the examination period.
Location: Secured | Letters of comfort have been provided by the Alderney Wildlife Trust and the States of Guernsey. This will need revisiting after the feasibility study has concluded and the final plans can be developed.
Additionality/success criteria | Increased productivity of the target colonies will be an essential measure of success. Proving additionality raises similar questions as have been considered for kittiwake ANS. It will be difficult to ascertain if any breeding birds are additional or have simply moved. Wider monitoring may provide some insight.
Long term resilience | Biosecurity plans have been included and are acknowledged as being essential to the measure’s long-term success. We welcome the Applicant's commitment to undertaking further eradication in the case of re-invasion.
Adaptive management | We note that adaptive management focusses on eradication failure rather than the colony(ies) subsequently not reaching required growth levels. It must be considered that even if eradication is successful, adaptive management may still be required if compensation is not delivered. |  | We consider adaptive management options should be outlined at this stage and included in the relevant compensation documents.
Monitoring | See additionality/success criteria. We welcome that productivity monitoring for guillemot and/ or razorbill would be evaluated over a number of breeding seasons. |  | We consider that the monitoring approach should be outlined now for inclusion in the relevant compensation documents.

## B - Ornithology
Point | [RR - 029] Appendix B point number | Taken from Natural England’s Relevant and Written Representations Hornsea 4 Appendix B - Offshore Ornithology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Risk Status at Deadline 2 | Consultation, actions, progression | RAG Risk Status Deadline 3 | Consultation, actions, progression | RAG Risk Status Deadline 4 | Consultation, actions, progression | RAG Risk Status Deadline 5 | Consultation, actions, progression | RAG Risk Status Deadline 6 | Consultation, actions, progression | RAG Risk Status Deadline 7 | Consultation, actions, progression | RAG Risk Status Deadline 8 | Issue Resolved
Baseline characterisation Documents Used: A2.5 Offshore and Intertidal Ornithology, A5.5.1 Offshore and Intertidal Ornithology Baseline Characterisation Report, A5.5.6 Offshore Ornithology MRSea Report |  |  |  | Documents reviewed: G1.9 Applicant’s comments on Relevant Representations Revision: 01 [REP1-038], attended a workshop with the Applicant on 17th February 2022. |  | Documents reviewed: A5.5.2 Offshore Ornithology Displacement Analysis (tracked), G2.9 Gannet Displacement and Mortality Evidence Review, G2.10 MRSea Baseline Sensitivity Report (Gannet), G2.11 Razorbill Assessment Alone and Incombination Farne Islands SPA, G2.13 Assessment of Common Scoter and Red Throated Diver within the ECC. |  | Documents reviewed: G2.10 MRSea Baseline Sensitivity Report (Gannet) - Revision: 02 [REP3-029] |  | Documents reviewed: G4.15 Applicants Response to Rule 17 Deadline 4A. |  | Documents reviewed: G5.9 Revised Ornithological Baseline (tracked); G5.40 Clarification note Revised Ornithology Baseline; G5.2 Ornithology EIA and HRA Annex (tracked); G4.7 Ornithological Assessment Sensitivity Report [G4.7]; G5.34 Applicant’s response to Natural England’s additional guidance on apportioning of seabirds to FFC SPA for Hornsea Project Four; G5.7 Indirect Effects of Forage Fish and Ornithology [G5.7] |  | Documents reviewed: G5.25 Ornithology EIA and HRA Annex (tracked)
B1 | 1, 34,41, 63,64, 70 | Model-based methods (MRSea) have been used in preference to design-based methods to generate abundance and density estimates for several species (fulmar, gannet, kittiwake, great black-backed gull, guillemot, razorbill and puffin). Due to concerns with the implementation of the modelling approach, Natural England cannot currently agree with the baseline estimates produced for the selected species and any subsequent conclusions drawn from assessments where they have been used. No comparison has been presented between either the raw data, design-based estimates and the MRSea modelled estimates and associated estimates of precision (coefficients of variation (CV)). To provide the requisite confidence in the outputs, the use of MRSea needs to be justified and validated through these comparisons. An overview of the model approach, particularly inclusion of temporal trends and flexibility in relation to distributions, is also not provided. |  | Following a meeting on 17th February 2022, we are expecting an updated analysis addressing Natural England concerns to be provided at Deadline 3 for gannet as an example species. The Applicant is intending to provide a Baseline Sensitivity Report at Deadline 2 and an updated MRSea Report including design-based estimates and monthly dot-density maps to compare with model-based estimates and distributions. Further comment will be provided at these deadlines. Please also see response to ExQ HRA.1.10. |  | The Applicant has provided the first part of three components that will make up a Baseline Sensitivity Report. This report will aim to address concerns and requests for clarification submitted by Natural England (NE) in relation to the methods used to derive abundance estimates that underpin the impact assessments. REP2-046 formally addresses NE comments [RR-029] and sets out the Applicant's approach to addressing these. Critically, the Applicant has acknowledged that they will need to re-analyse the data, initially for gannet, to determine the significance of any change in estimates to address NE concerns. It is suggested that if changes are judged to be insignificant then additional modelling would not be undertaken for other species following agreement with NE. It is worth highlighting at this point that we currently consider it highly unlikely that the modelling will not need to be rerun for the remaining species. NE appreciate that the Applicant has consulted with CREEM on methods and presentation and the example outputs generally appear to be in line with expectations. However, NE note that the Applicant appears to have switched to the use of month, rather than survey, in the model framework. As a result, NE will need to give consideration to the implications of this on further assessments. We also note the Applicant's frustration that this issue was not addressed within the Evidence Plan Process (EPP). Whilst NE agreed in principle with the Applicant pursuing the MRSea approach during the Evidence Plan process, it was only when the full Application was submitted that it became apparent that repeated advice to provide model validation to support the use of this novel approach had not been followed. Natural England's advice throughout the EPP was to provide design based estimates alongside the MRSea output to mitigate the risks of potential issues arising with the novel approach. Again, the Applicant chose not to follow Natural England's advice regarding this matter. |  |  |  | Natural England welcomes the scope of works provided by the Applicant at Deadline 4a [REP4a-001] and the presentation of its contents to NE at at meeting on 25th May 2022. We will provide full comment on the revised baseline when it is submitted at Deadline 5, but in principle we agree with the Applicant's outlined approach to use the following in all updated assessments: Kittiwake: MRSea_V2 (collision) Gannet: MRSea_V2 (collision); design-based (displacement) Guillemot: MRsea_V2 (displacement) Razorbill: Design-based (displacement) All other species: (design- based) This approach is in accordance with NE's advice provided at Deadline 4 [REP4-055] and we welcome the Applicant's endeavours in addressing this issue. |  | Following further clarifications from the Applicant, Natural England agrees that the baseline data using the agreed updated approach and modelling is fit for purpose. The Applicant has supplied design-based data for all relevant species and has revised their modelling in line with advice from NE and CREEM. We acknowledge that the Applicant will not be able to provide confidence intervals around the final abundance estimates where corrections or adjustments have been applied to the data (see B2). |  |  |  | Following further clarifications from the Applicant, Natural England agrees that the baseline data using the agreed updated approach and modelling is fit for purpose. The Applicant has supplied design-based data for all relevant species and has revised their modelling in line with advice from NE and CREEM. We acknowledge that the Applicant will not be able to provide confidence intervals around the final abundance estimates where corrections or adjustments have been applied to the data (see B2). |  | Yes
B2 | 42 | The corrected abundance and density estimates do not include confidence intervals (CI) in these tables and therefore the level of uncertainty associated with these estimates is not available for consideration. Please provide CIs for the estimates in Appendix B and include a description of how they were derived. |  | No change. |  | Natural England anticipate that all revised abundance estimates, associated upper and lower confidence limits, and methods used to calculate these will be provided in the final MRSea Baseline Sensitivity Report and associated data tables at Deadline 3. |  | The Applicant has provided the completed Baseline Sensitivity Report containing the re-analysis of the baseline data for gannet. Natural England have provided an executive summary alongside detailed comments on this report in submission EN010098 H4 Appendix B4 - NE comments on G2.10 MRSea Baseline Sensitivity Report. |  | A revised baseline is due to be submitted at Deadline 5 |  | Following further discussions with the Applicant, they have confirmed that, due to their methods for estimating abundance, they will not be able to provide accurate confidence intervals for corrected estimates. We note confidence intervals are presented for uncorrected estimates. |  |  |  | Following further discussions with the Applicant, they have confirmed that, due to their methods for estimating abundance, they will not be able to provide accurate confidence intervals for corrected estimates. We note confidence intervals are presented for uncorrected estimates. |  | No
B3 | 44 | No details are provided in relation to potential issues with ageing different species. Natural England highlights the importance of site-specific ageing data in relation to apportioning for HRA and request a full breakdown of relevant data for the project area, including any relevant boat-based survey data which may have higher proportions of aged individuals, for use in SPA apportioning. Details on the limitations of the age classification approach and the percentages of all birds of each species that were aged should also be provided. No details are provided here or in Appendix D in relation to potential issues with ageing different species. NE advise that where good quality site-specific ageing data is not available, the precautionary approach is to assume that all ‘adult type’ birds (i.e. birds that cannot be distinguished from adults, and hence might be adults) are apportioned as adults. We also suggest that the apportioning of adult birds should be season-specific to account for any seasonal variations in the use of the site. |  | RR-029-APDX:B-44 suggests that sufficient breakdown of site-specific aged data is provided in APP-074. However, this does not indicate the proportions aged and the proportions of adult-type birds. We further note that gannet site-specific age data was made available and used in apportioning prior to the submission and this appears to have been retracted without reason. |  | No change. |  | The Applicant has provided the completed Baseline Sensitivity Report containing the re-analysis of the baseline data for gannet. Natural England have provided an executive summary alongside detailed comments on this report in submission EN010098 H4 Appendix B4 - NE comments on G2.10 MRSea Baseline Sensitivity Report. |  | We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. Further advice was provided by NE to the Applicant on 27th May 2022 to feed into these assessments. We have also submitted this advice into the Examination at Deadline 5. |  | The Applicant has provided further information on ageing data from the area for lease + 4km buffer, which NE have advised should be used to estimate the proportions of adult gannet or adult-type kittiwake present in the breeding season for the purposes of apportioning (provided in Ornithology EIA and HRA Annex (tracked) [G5.2]). However, Natural England disagrees with the Applicant's approach to using all data across the entire year to inform their values. Natural England have therefore used the data provided to refine the apportioning values to be used by Natural England when forming our position. We also note that the Applicant has provided a lengthy critique of this approach and Natural England's assumption regarding the precautionary approach to definining adult proportions for other species in the breeding and, in the case of guillemot and razorbill, chick rearing/moult (Ornithological EIA and HRA Annex [G5.2], Ornithological Assessment Sensitivity Report [G4.7] & Applicant’s response to Natural England’s additional guidance on apportioning of seabirds to FFC SPA for Hornsea Project Four [G5.34]). We maintain that where there is insuffienct site- and species-specific evidence, the precautionary approach to adult apportioning should be adopted. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No change |  | The Applicant has provided further information on ageing data from the area for lease + 4km buffer, which NE have advised should be used to estimate the proportions of adult gannet or adult-type kittiwake present in the breeding season for the purposes of apportioning (provided in Ornithology EIA and HRA Annex (tracked) [G5.2]). However, Natural England disagrees with the Applicant's approach to using all data across the entire year to inform their values. Natural England have therefore used the data provided to refine the apportioning values to be used by Natural England when forming our position. We also note that the Applicant has provided a lengthy critique of this approach and Natural England's assumption regarding the precautionary approach to definining adult proportions for other species in the breeding and, in the case of guillemot and razorbill, chick rearing/moult (Ornithological EIA and HRA Annex [G5.2], Ornithological Assessment Sensitivity Report [G4.7] & Applicant’s response to Natural England’s additional guidance on apportioning of seabirds to FFC SPA for Hornsea Project Four [G5.34]). We maintain that where there is insuffienct site- and species-specific evidence, the precautionary approach to adult apportioning should be adopted. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No
B4 | 45 | Bar graphs do not provide CIs associated with the abundance estimates. CIs in relation to all abundance or density estimates should be provided. |  | CIs are provided numerically in APP-074. RR-029-APDX:B-45 | [11 empty] | CIs are provided numerically in APP-074. RR-029-APDX:B-45 |  | No
B5 | 45 | It is suggested that abundance estimates without any corrections are suitable for assessing displacement. NE disagree with this and advise that corrected data should be used for the assessment. Clarification is needed on whether data from Appendix A (uncorrected) or B (corrected) was used for the assessment of displacement for these species. |  | The Applicant has confirmed that only corrected data has been used. RR-029-APDX:B-45. | [11 empty] | The Applicant has confirmed that only corrected data has been used. RR-029-APDX:B-45. |  | Yes
B6 | 46 | All seasonal maps provide identical distributions (scaled by changes in abundance) for each species. This suggests that the underlying distributions of birds do not change across seasons, which is implausible. NE considers that it would be more appropriate to provide modelled spatial distribution surfaces for the Afl, and include either plots of coefficients of variation of percentile-based confidence intervals generated from bootstrap samples to characterise spatial uncertainty. The Applicant should provide maps including the entire Afl and showing CIs associated with predicted spatial distributions for each species overlaid with raw data observations. |  | To be addressed in forthcoming submissions at Deadlines 2 and 3. RR-029-APDX:B-46 and RR-029-5.1. |  | Natural England's position remains unchanged, however, we are hoping that this will be fully addressed in the final MRSea Baseline Sensitivity Report. We note that the example map outputs provided in the Deadline 2 submission (G2.10 MRSea Baseline Sensitivity Report (Gannet)) appear to fulfil Natural Englands requirements in this regard. |  | The Applicant has provided the completed Baseline Sensitivity Report containing the re-analysis of the baseline data for gannet. Natural England have provided an executive summary alongside detailed comments on this report in submission EN010098 H4 Appendix B4 - NE comments on G2.10 MRSea Baseline Sensitivity Report. |  | A revised baseline is due to be submitted at Deadline 5 |  | The agreed revised baseline modelling approach has addressed this issue by including a temporal interaction within the modelling framework. Maps provided in the Ornithology EIA and HRA Annex (tracked) [G5.2] illustrate changes in spatial distributions. |  |  |  | The agreed revised baseline modelling approach has addressed this issue by including a temporal interaction within the modelling framework. Maps provided in the Ornithology EIA and HRA Annex (tracked) [G5.2] illustrate changes in spatial distributions. |  | Yes
B7 | 48,49 | NE note that CIs should be provided for density estimates that are derived from the density surfaces using a different method to the abundance estimates.NE also note that coefficients of variation (CVs) are provided for design-based estimates but not for the model-based estimates. Both issues should be rectified. |  | No change. RR-029-APDX:B-48, RR-029-APDX:B-49, and RR-029-APDX:B-103. |  | Natural England's position remains unchanged, however, are hopeful that all revised abundance estimates, associated upper and lower confidence limits, coefficients of variation, and methods used to calculate these will be provided in the final MRSea Baseline Sensitivity Report and associated data tables at Deadline 3. |  | The Applicant has provided the completed Baseline Sensitivity Report containing the re-analysis of the baseline data for gannet. Natural England have provided an executive summary alongside detailed comments on this report in submission EN010098 H4 Appendix B4 - NE comments on G2.10 MRSea Baseline Sensitivity Report. |  | A revised baseline is due to be submitted at Deadline 5 |  | The Applicant has now provided CVs for the model-based estimates and included CIs when displaying the modelled abundance surfaces. |  |  |  | The Applicant has now provided CVs for the model-based estimates and included CIs when displaying the modelled abundance surfaces. |  | Yes
B8 | 65 | This suggests 95% CIs were produced for each grid cell, but maps illustrating these are not presented within the report. Please provide maps with associated 95% CIs for reference. |  | To be addressed in forthcoming submissions at Deadlines 2 and 3. RR-029-APDX:B-65 and RR-029-5.1 |  | Natural England's position remains unchanged, however, we are hopeful that this will be fully addressed in the final MRSea Baseline Sensitivity Report to be submitted at Deadline 3. We note that the example map outputs provided in the Deadline 2 submission (G2.10 MRSea Baseline Sensitivity Report (Gannet)) appear to fulfil Natural Englands requirements in this regard. |  | The Applicant has provided the completed Baseline Sensitivity Report containing the re-analysis of the baseline data for gannet. Natural England have provided an executive summary alongside detailed comments on this report in submission EN010098 H4 Appendix B4 - NE comments on G2.10 MRSea Baseline Sensitivity Report. |  | A revised baseline is due to be submitted at Deadline 5 |  | The Applicant has provided CIs when displaying the modelled abundance surfaces. |  |  |  | The Applicant has provided CIs when displaying the modelled abundance surfaces. |  | Yes
B9 | 66 | Based on the described approach, survey number, or bio-season, is being included within models as a factor. Examining the maps of spatial distributions produced, the models therefore appear to be describing a single ‘global’ spatial density distribution, based on relationships with the included covariates across the entire 24 surveys, which is scaled according to survey or bio-season. The pooling of all data across all years and bio-seasons appears inappropriate, as currently there is the assumption that the underlying form of the relationships with the available covariates remain consistent over time and space. |  | To be addressed in forthcoming submissions at Deadlines 2 and 3. RR-029-APDX:B-66 and RR-029-5.1. |  | Natural England note that the Applicant now appears to be using "month" rather than "survey" in their example provided in the report submitted at Deadline 2 (G2.10 MRSea Baseline Sensitivity Report (Gannet)). If this is maintained, it is unclear how individual survey estimates will be derived from the model which will preclude the use of the standard displacement assessment method advised by Natural England. Natural England will consider this matter further on receipt of the proposed Deadline 3 submission. The Applicant has agreed to include a temporal-spatial interaction term in the model framework to allow flexibility in the spatial surfaces. The final results of the re-analysis will provide more information on what different models were trialled and which was ultimately selected as the 'best'. Natural England cannot comment further prior to inspection of the analysis results. |  | The Applicant has provided the completed Baseline Sensitivity Report containing the re-analysis of the baseline data for gannet. Natural England have provided an executive summary alongside detailed comments on this report in submission EN010098 H4 Appendix B4 - NE comments on G2.10 MRSea Baseline Sensitivity Report. |  | A revised baseline is due to be submitted at Deadline 5 |  | The agreed revised baseline modelling approach has addressed this issue by including a temporal interaction within the modelling framework. Maps provided in the Ornithology EIA and HRA Annex (tracked) [G5.2] illustrate changes in spatial distributions. |  |  |  | The agreed revised baseline modelling approach has addressed this issue by including a temporal interaction within the modelling framework. Maps provided in the Ornithology EIA and HRA Annex (tracked) [G5.2] illustrate changes in spatial distributions. |  | Yes
B10 | 67 | It remains unclear how density and abundance estimates were derived for different behaviours (sitting/flying) and only total density and abundance estimates are presented within this report. Based on discussion with the Applicant during the Evidence Plan Process, it would appear the results for all birds were apportioned according to the raw count data for each behaviour. However, it remains unclear whether apportioning ratios were determined from individual surveys or across the whole survey programme. If this is the case, clarity is needed on how the CIs associated with the estimates for different behaviours were derived. Detailed clarification should be provided on the methods undertaken here. This should include a table providing the apportioning values used for each behaviour and a description of how the data were treated to derive appropriate CIs. |  | To be addressed in forthcoming submissions at Deadlines 2 and 3. RR-029-APDX:B-67 and RR-029-5.1. |  | The Applicant has provided some details in their response to Natural England's comments in regards to this in REP2-046. However, it does not address the lack of CIs around density estimates provided in the original MRSea report that appear to not be directly related to the total abundance estimates and associated Confidence Limits. Further, the explanation provided is somewhat contradictory as it implies that CIs could not be calculated for apportioned birds in flight used for collision risk assessment, yet CIs around flying bird estimates were relied upon to derive SDs for collision risk modelling. Clarity is therefore needed on how these CIs were derived. Natural England hope to see all revised abundance estimates, associated upper and lower confidence limits, coefficients of variation, and methods used to calculate these will be provided in the final MRSea Baseline Sensitivity Report and associated data tables at Deadline 3 in order for this issue to progress. Where it is not possible to provide CIs, this should be clearly sign-posted and explained. |  | The Applicant has provided the completed Baseline Sensitivity Report containing the re-analysis of the baseline data for gannet. Natural England have provided an executive summary alongside detailed comments on this report in submission EN010098 H4 Appendix B4 - NE comments on G2.10 MRSea Baseline Sensitivity Report. |  | A revised baseline is due to be submitted at Deadline 5 |  | The Applicant has provided clarification on how abundance and density estimates have been derived. Following further discussions with the Applicant, they have confirmed that, due to their methods for estimating abundance, they will not be able to provide accurate confidence intervals for corrected estimates. We note confidence intervals are presented for uncorrected estimates. |  |  |  | The Applicant has provided clarification on how abundance and density estimates have been derived. Following further discussions with the Applicant, they have confirmed that, due to their methods for estimating abundance, they will not be able to provide accurate confidence intervals for corrected estimates. We note confidence intervals are presented for uncorrected estimates. |  | No
B11 | 68 | Density is calculated as a mean from all the cells within a specific area, but that the population was derived by summing the predicted numbers of birds in the relevant cells. It appears that upper and lower confidence intervals (CIs) for the population estimates were derived from the CIs for individual cells based on the bootstrap approach, whilst it is unclear how CIs for the densities have been derived. Confirmation is needed on whether they are based on the distribution of mean density values from the mean density surface. It is also unclear how part cells (where clipped) were considered. For example, were part cells assumed to be in the area of interest or not, or was an adjustment made based on the proportion of the cell included? Further, we note that these two approaches do not produce interchangeable metrics of abundance. Thus, the mean density multiplied by the relevant area would not produce the same population estimate as derived from summing the numbers in each cell. We request that clarification is provided over how part cells were treated in relation to density and abundance estimates. Further detail on how estimates and associated CIs were derived is also needed. |  | To be addressed in forthcoming submissions at Deadlines 2 and 3. RR-029-APDX:B-68 and RR-029-5.1. |  | Whilst the Applicant has provided some details in their response to Natural England's comments regarding the treatment of part cells, it remains unclear why the density values multiplied by the relevant area do not result in the reported population estimates as may be expected. For example, in Volume A5, Annex 5.6: Offshore Ornithology MRSea Annex, Table 6, simply multiplying the density estimates by the area of the array and 4 km buffer (883 km2) to produce a population estimate results in some population estimates that differ to those presented by up 16% (February 2017 survey). The average difference in this case is 6.5%. Natural England maintain that it is important that we understand why there is this discrepency between the two metrics. This will be checked again when the final MRSea Baseline Sensitivity Report and associated data tables are provided at Deadline 3. |  | The Applicant has provided the completed Baseline Sensitivity Report containing the re-analysis of the baseline data for gannet. Natural England have provided an executive summary alongside detailed comments on this report in submission EN010098 H4 Appendix B4 - NE comments on G2.10 MRSea Baseline Sensitivity Report. |  | A revised baseline is due to be submitted at Deadline 5 |  | The Applicant has provided clarification on how abundance and density estimates have been derived. Following further discussions with the Applicant, they have confirmed that, due to their methods for estimating abundance, they will not be able to provide accurate confidence intervals for corrected estimates. We note confidence intervals are presented for uncorrected estimates. |  |  |  | The Applicant has provided clarification on how abundance and density estimates have been derived. Following further discussions with the Applicant, they have confirmed that, due to their methods for estimating abundance, they will not be able to provide accurate confidence intervals for corrected estimates. We note confidence intervals are presented for uncorrected estimates. |  | No
B12 | 69 | No CVs are provided alongside model estimates and CIs are not included for density estimates. Please provide CVs alongside all estimates to provide an indication of relative precision and CIs associated with all density estimates. |  | To be addressed in forthcoming submissions at Deadlines 2 and 3. RR-029-APDX:B-69 and RR-029-5.1. |  | Natural England anticipate that all revised abundance estimates, associated upper and lower confidence limits, coefficients of variation, and methods used to calculate these will be provided in the final MRSea Baseline Sensitivity Report and associated data tables at Deadline 3. |  | The Applicant has provided the completed Baseline Sensitivity Report containing the re-analysis of the baseline data for gannet. Natural England have provided an executive summary alongside detailed comments on this report in submission EN010098 H4 Appendix B4 - NE comments on G2.10 MRSea Baseline Sensitivity Report. |  | A revised baseline is due to be submitted at Deadline 5 |  | The Applicant has provided CVs for the revised model estimate. Following further discussions with the Applicant, they have confirmed that, due to their methods for estimating abundance, they will not be able to provide accurate confidence intervals for corrected estimates. We note confidence intervals are presented for uncorrected estimate. |  |  |  | The Applicant has provided CVs for the revised model estimate. Following further discussions with the Applicant, they have confirmed that, due to their methods for estimating abundance, they will not be able to provide accurate confidence intervals for corrected estimates. We note confidence intervals are presented for uncorrected estimate. |  | No
Displacement and barrier assessment Documents Used: A2.5 Offshore and Intertidal Ornithology, A5.5.2 Offshore Ornithology Displacement Analysis, B2.2 Report to Inform Appropriate Assessment Part 1 | [9 empty] | G4.14 Further Consideration of Lighting Requirements
B13 | 2,30,47,52,75 | NE do not agree with the seasonal definitions used for gannet and kittiwake based around the migration-free breeding season. NE advised during the Evidence Plan process that for species where breeding birds are predicted to be present in the project area, that the breeding season months follow those presented in Furness (2015) under ‘breeding season’ and not the ‘migration-free breeding season’, except where local colony or site-specific information suggests that a different set of months is appropriate for defining colony attendance. No evidence has been provided to support the use of the migration-free breeding seasons and given the proximity of the project area to FFC SPA, we consider that using the migration-free breeding season could lead to collision and displacement impacts being underestimated. We recommend that the Applicant provide all relevant values for the assessment based on the recommended seasonal definitions for gannet and kittiwake . These seasons should be carried through the entire EIA and HRA process. |  | Natural England agrees that values in line with the NE approach have been provided for gannet in (APP-177). However, for kittiwake it is suggested that the full breeding season is April to August for the NE scenario. Natural England advise that March to August is used for Kittiwake. This should be addressed. We highlight these values will need to be updated in line with any assessments that are redone owing to baseline concerns. |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | Natural England note that the Applicant has undertaken assessments using the SNCB recommended seasonal definitions. However, the Applicant continues to support the use of the core breeding season definition whilst Natural England maintains our position. We note that ultimately, the difference is only likely to affect gannet displacement numbers and is unlikely to make a material difference to our conclusions. We note the Applicant has provided further discussion around this point in Ornithological Assessment Sensitivity Report [G4.7] which we have commented on separately. |  |  |  | Natural England note that the Applicant has undertaken assessments using the SNCB recommended seasonal definitions. However, the Applicant continues to support the use of the core breeding season definition whilst Natural England maintains our position. We note that ultimately, the difference is only likely to affect gannet displacement numbers and is unlikely to make a material difference to our conclusions. We note the Applicant has provided further discussion around this point in Ornithological Assessment Sensitivity Report [G4.7] which we have commented on separately. |  | No
B14 | 7,9,12,31,84,87,90,99, 119 | The Applicant has only considered a 1% mortality rate for displacement assessments, contrary to SNCB advice that a range of mortality rates between 1 and 10% are considered. We request that the seasonal and annual estimated mortality calculated using NE’s recommended approach (60-80% displacement rate for gannet, 30-70% for auks and a range of 1-10% mortality rate) is provided. |  | The Applicant provided G1.47 Auk Displacement and Mortality Evidence Review Revision: 01 [REP1-069] at Deadline 1 in support of their approach. Natural England does not consider that the information provided in the report provides justification for the use of single displacement (50%) and mortality (1%) rate values for the auks at Hornsea 4, and we advise that these values could underrepresent impacts on these species. Full comments on this document are provided in REP2-085. Natural England's position is unchanged. (RR-029-APDX:B-7). A similar report for gannet is due to be submitted at Deadline 2 (RR-029-APDX:B-12). A full auk displacement assessment will be submitted at Deadline 5. |  | The Applicant's document G2.9 Gannet Displacement and Mortality Evidence Review, submitted at Deadline 2, results in a conclusion that 40-60% displacement should be considered for gannet during the breeding season and 60-75% would be more appropriate during the non-breeding season. The Applicant also provides further defence of the use of a single mortlaity rate (1%) at the bottom end of the suggested NE range. Whilst Natural England welcome the review, we do not consider that the report provides sufficient justification for the use of different displacement and mortality rates to those advised by NE, based on the available evidence. We maintain our position that our advised displacement range (60-80%) is consistent with the evidence and we note that that, of the seven studies reported suggesting displacement rates of <60%, the Applicant places low confidence in the survey methods and/or data collected for five of these in the report. Natural England also note that there is currently no empirical evidence for displacement consequent mortality of gannet and the quoted studies have significant limitations and numerous underlying assumptions limiting confidence in their conclusions. Thus, NE consider a range of 1-10% should continue to be considered during the assessment. Natural England and the Applicant maintain their respective positions. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | Natural England note that the Applicant has provided displacement assessments for key species considering the full range of displacement and mortality rates specified respectively. We would like to clarify that Natural England adopts this range-based approach to allow consideration of sources of uncertainty and other factors within and outwith the displacement assessment when considering our position. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural Enlgand do not require any further action from the Applicant. |  | No change |  | Natural England note that the Applicant has provided displacement assessments for key species considering the full range of displacement and mortality rates specified respectively. We would like to clarify that Natural England adopts this range-based approach to allow consideration of sources of uncertainty and other factors within and outwith the displacement assessment when considering our position. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural Enlgand do not require any further action from the Applicant. |  | No
B15 | 13 | In line with the other species assessed, please provide the full annual displacement matrix for gannet within the array area + 2 km buffer. |  | Not addressed (RR-029-APDX:B-13). |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | The Applicant has provided relevant information in Ornithology EIA and HRA Annex (tracked) [G5.2] . |  |  |  | The Applicant has provided relevant information in Ornithology EIA and HRA Annex (tracked) [G5.2] . |  | Yes
B17 | 10 | Tables have not been provided detailing the construction displacement estimates for gannet or puffin impacts as for the other species (e.g. guillemot). These tables should be provided as per the other species. |  | Natural England maintains that it would be beneficial for the tables to be provided, but acknowledges that it does not have a material impact on our ability to draw conclusions (RR-029-APDX:B-10) | [7 empty] | The Applicant has provided relevant information in Ornithology EIA and HRA Annex (tracked) [G5.2] . |  |  |  | The Applicant has provided relevant information in Ornithology EIA and HRA Annex (tracked) [G5.2] . |  | Yes
B18 | 14 | The Applicant refers to a comprehensive review of post-construction monitoring studies they have undertaken to inform auk displacement and presents a summary of that review. Until such time as Natural England have been provided with the full review and been able to comment on the evidence provided, we cannot agree with conclusions presented that are based on its contents. Please present the full review for comment by Natural England: APEM (2021, In prep). Review of Auk Disturbance & Displacement, Habituation and potential Mortality Rates to inform Offshore Wind Farm EIAs. APEM Note in preparation. |  | This report [REP1-069] was submitted at Deadline 1. Having reviewed it, Natural England does not agree with the conclusions based on its contents. Please see our additional Deadline 2 submission for our full comments on the report [REP2-085]. (RR-029-APDX:B-14) |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | No change, Natural England consider the preferred displacement and mortality rates adopted by the Applicant are not sufficiently precautionary and do not agree that the provided review provides adequate justification. Natural England continue to advocate our advised approach to the assessment parameters. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural Enlgand do not require any further action from the Applicant. |  | No change |  | No change, Natural England consider the preferred displacement and mortality rates adopted by the Applicant are not sufficiently precautionary and do not agree that the provided review provides adequate justification. Natural England continue to advocate our advised approach to the assessment parameters. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural Enlgand do not require any further action from the Applicant. |  | No
B19 | 15, 33,35, 50,51,92,97,98 | Natural England notes that there has been no assessment of the extent and suitability of habitat for guillemot outside the array plus buffer area, nor of the potential effects of increased densities in this area. Furthermore, additional evidence previously requested by NE during the Evidence Plan Process to address questions regarding the impacts of displacement on guillemot and razorbill in the Hornsea 4 array area has not been presented. This included a request for information about the potential specific importance of the Hornsea 4 array area to guillemot and razorbill compared to the wider surrounding area. Natural England request that further consideration is given now to drivers of seasonal variations in the wider spatial distributions of auks, particularly during August and September, to determine the potential importance of this area. |  | Please see Point 18 (RR-029-APDX:B-15). The Applicant appears to have interpreted this point as focusing only on the breeding season. We do not consider that the wider context for the importance of the area to auks, particularly during August and September has, been provided. Further, whilst the Applicant has highlighted several times that the array area and buffer are not the ‘most important’ areas for auks, this does not detract from the fact that they remain important. The Applicant is currently considering what further evidence may be required to be submitted in response to Natural England’s indication of areas of the North Sea that may have functional linkages or be supporting habitats to the FFC SPA. This will be submitted at Deadline 5. RR-029-APDX:B-92 |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | Natural England acknowledge that the Applicant has looked to address this issue through the provision of an Indirect Effects of Forage Fish and Ornithology [G5.7] report at Deadline 5. We note that the report concludes that the most productive areas in the sea areas adjacent to the site are likely to be driven by bathymetry, prey and the Flamborough Front, fishing pressure and seabird hotspots appear linked to key areas. The DAA has mitigated the potential loss of what appear to be the most important sea areas within the survey area, but seasonal and annual variability in the location of the Flamborough Front and prey resources cannot be ruled out and may mean that the array areas is more important in specific years, particularly in relation to guillemot and razorbill during the chick rearing/moult period. Further, based on the available evidence Natural England cannot rule out the potential for indirect effects to alter the ecology of this important area with ramifications for the huge numbers of birds that utilise it at a very vulnerable and important stage in their lives. We will be providing an additional written response to the Indirect Effects of Forage Fish and Ornithology [G5.7] report and further justication of our advice relating to the need for a bespoke approach to assessment for guillemot and razrobill in our Deadline 6 submissions. |  | No change |  | Natural England acknowledge that the Applicant has looked to address this issue through the provision of an Indirect Effects of Forage Fish and Ornithology [G5.7] report at Deadline 5. We note that the report concludes that the most productive areas in the sea areas adjacent to the site are likely to be driven by bathymetry, prey and the Flamborough Front, fishing pressure and seabird hotspots appear linked to key areas. The DAA has mitigated the potential loss of what appear to be the most important sea areas within the survey area, but seasonal and annual variability in the location of the Flamborough Front and prey resources cannot be ruled out and may mean that the array areas is more important in specific years, particularly in relation to guillemot and razorbill during the chick rearing/moult period. Further, based on the available evidence Natural England cannot rule out the potential for indirect effects to alter the ecology of this important area with ramifications for the huge numbers of birds that utilise it at a very vulnerable and important stage in their lives. We will be providing an additional written response to the Indirect Effects of Forage Fish and Ornithology [G5.7] report and further justication of our advice relating to the need for a bespoke approach to assessment for guillemot and razrobill in our Deadline 6 submissions. |  | No
B20 | 16,19,34,53 | The abundance estimates for the Applicant's approach to the displacement assessment for guillemot, razorbill and puffin have not included birds in flight. SNCB advice is clear that both birds in flight and birds on the water need to be included in abundance estimates. Figures should be recalculated following NE guidance. |  | Flying birds are to be included in a reanalysis that will be submitted at Deadline 5. It is noted that this material changes to the estimated impacts are likely to occur as a result of this (RR-029-5.9B) |  | Natural England note that the Applicant's revised document submitted at Deadline 2, A5.5.2 Offshore Ornithology Displacement Analysis (tracked), has been altered to include updated peak-mean abundance estimates based on the existing data for all behaviours for the auks. This results in substantial increases to some of the predicted impacts in some seasons and no change in others depending on the species. Whilst this is a useful exercise, NE's concerns with the baseline data are in the process of being addressed and it is unclear whether this data will underpin the final assessment. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | The Applicant has provided an updated assessment addressing this in Ornithology EIA and HRA Annex (tracked) [G5.2] . |  |  |  | The Applicant has provided an updated assessment addressing this in Ornithology EIA and HRA Annex (tracked) [G5.2] . |  | Yes
B21 | 17 | “During the non-breeding bio-season, the weighted mean peak abundance for guillemot is 34,095 individuals within the array area and 2km buffer.” This appears to be incorrect. The weighted mean is 17,062 according to Table 5.29 and according to our calculations using the Applicant’s approach this should be 14,575. These values should be checked and recalculated, incorporating NE comments on the displacement methodology as a whole. |  | The Applicant has confirmed that there was an error in the text (RR-029-APDX:B-17). | [11 empty] | The Applicant has confirmed that there was an error in the text (RR-029-APDX:B-17). |  | Yes
B22 | 20 | NE welcome the Applicant also providing estimates for a range of displacement and mortality rates following SNCB advice, however due to concerns with the abundance estimates they are based on we cannot agree with the values produced. |  | No change, we expect these values to be updated pending the outcome of baseline data revisions (RR-029-APDX:B-20) |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | Having agreed the baseline, we consider the Applicant has provided relevant information in Ornithology EIA and HRA Annex (tracked) [G5.2] . |  |  |  | Having agreed the baseline, we consider the Applicant has provided relevant information in Ornithology EIA and HRA Annex (tracked) [G5.2] . |  | Yes
B23 | 25,76 | Hornsea 4 has included an assessment of barrier effects but only for fulmar, gannet and kittiwake. This is based on the assumption that only “fulmar, gannet and kittiwake may forage on a regular basis out to a distance as far as, or further than the Hornsea Four array area”. NE consider this assumption to be insufficiently evidenced and advise that either more evidence is provided to support the conclusions on the lack of barrier effects for auk species, or the Applicant should consider the potential for barrier effects on auks from Hornsea 4. |  | It is noted that there is currently no quantitative assessment method for barrier displacement effects and that the matrix approach should cover both birds in flight and on the water. A revised displacement analysis for auks will including flying birds will be submitted at Deadline 5. RR-029-APDX:B-76. |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | Natural England consider that given the Applicant has now included sitting and flying birds in the assessment of displacement, the potential for barrier effects is incorporated into the assessment for these species. |  |  |  | Natural England consider that given the Applicant has now included sitting and flying birds in the assessment of displacement, the potential for barrier effects is incorporated into the assessment for these species. |  | Yes
B24 | 25 | Currently puffin have been screened out of barrier effects based on the mean foraging range, whereas for the other auk species mean max foraging range was considered. It is not clear why only mean foraging range has been considered for puffin. NE consider that mean max foraging range plus 1SD should be used for all species. |  | Not addressed (RR-029-APDX:B-25) |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | Natural England consider that given the Applicant has now included sitting and flying birds in the assessment of displacement for auks, the potential for barrier effects is incorporated into the assessment for these species. |  |  |  | Natural England consider that given the Applicant has now included sitting and flying birds in the assessment of displacement for auks, the potential for barrier effects is incorporated into the assessment for these species. |  | Yes
B25 | 26 | For gannet, the Applicant assumes that no gannet would be foraging in the areas of Hornsea Projects 1-3 post construction so Hornsea 4 would not be acting as a barrier to access of these areas further east. |  | A displacement and mortality report for gannet will be submitted at Deadline 2 (RR-029-APDX:B-26). |  |  |  | No change. | [7 empty] | A displacement and mortality report for gannet will be submitted at Deadline 2 (RR-029-APDX:B-26). |  | Yes
B26 | 27 | We further note that in terms of in-combination impacts across the wider Hornsea zone, the Applicant states that the tracking data indicates that few gannet from FFC SPA commute beyond the four Hornsea projects. No quantitative data has been provided to support this statement. |  | No change (RR-029-APDX:B-27) |  |  |  | No change. | [7 empty] | No change (RR-029-APDX:B-27) |  | Yes
B27 | 28 | NE do not agree that that it can be concluded that meeting the minimum regulatory requirement for offshore lighting is the same as minimising impacts on ornithology receptors. We consider it would be appropriate to consider screening of key species that could be sensitive to impacts of lighting to provide context for this assessment. Further, mitigation measures outlined in the OSPAR guidance are not solely restricted to minimising the emission of light, but also include measures such as changing the spectrum of light emitted, shielding light, and use of intermittent light including switching lighting off at particular times. We would welcome these elements also being considered in Hornsea 4’s designs. |  | The Applicant is giving further consideration to lighting requirements and will submit further information at Deadline 3 (RR-029-APDX:B-28) |  |  |  | No change. |  | The Applicant submitted document G4.14 Further consideration of lighting requirements at Deadline 4. Natural England are grateful for the additional explanation of relevant lighting regulations, standards and guidelines which appear to suggest that there is currently very limited flexibility in lighting design and thus scope for mitigation. Whilst we consider it remains unclear what restrictions are in place within the relevant documents to prevent modification of lighting consistent with the OSPAR guidance, we do not consider this matter is of significant concern in relation to Hornsea 4, we therefore do not intend to make any further comment on this matter unless the ExA asks us for specific advice. | [5 empty] | The Applicant submitted document G4.14 Further consideration of lighting requirements at Deadline 4. Natural England are grateful for the additional explanation of relevant lighting regulations, standards and guidelines which appear to suggest that there is currently very limited flexibility in lighting design and thus scope for mitigation. Whilst we consider it remains unclear what restrictions are in place within the relevant documents to prevent modification of lighting consistent with the OSPAR guidance, we do not consider this matter is of significant concern in relation to Hornsea 4, we therefore do not intend to make any further comment on this matter unless the ExA asks us for specific advice. |  | No
B28 | 43,50,85,95 | NE considers that the weighted approach to calculating seasonal mean peak abundance for guillemot underestimates the potential impacts during a potential period of increased sensitivity, and does not account for the high numbers of guillemot present in the array area in August and September. |  | Natural England and the Applicant maintain their respective positions. RR-029-APDX:B-43, RR-029-APDX:B-50, and RR-029-APDX:B-16. |  | No change. |  | No change. |  | We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. Further advice was provided by NE to the Applicant on 27th May 2022 to feed into these assessments. We have also submitted this advice into the Examination at Deadline 5. |  | Natural England consider that the Applicant have followed our advice to provide values for our approach to the assessment for guillemot for HRA withing Ornithology EIA and HRA Annex (tracked) [G5.2], but not for the EIA. Natural England will consider impacts derived using our bespoke advice and for illustrative purposes the generic SNCB displacement assessment standard approach (including standard apportioning) when forming a position on the potential for significant adverse impact or Adverse Effects on Integrity of designated seabird features. We note that the Applicant has provided a response to Natural England's advice (Applicant’s response to Natural England’s additional guidance on apportioning of seabirds to FFC SPA for Hornsea Project Four [G5.34]) and we will be providing a separate statement in relation to this. The Applicant has further looked to justify their preferred approach to the assessment of displacement impacts on guillemot within Ornithology EIA and HRA Annex (tracked) [G5.2] and Indirect Effects of Forage Fish and Ornithology that we will be providing further comment on in our Deadline 6 submissions. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. On the basis that there is a significant difference between the Applicant's figures and those derived using Natural England's advice, we have increased the RAG status to red. |  | No change |  | Natural England consider that the Applicant have followed our advice to provide values for our approach to the assessment for guillemot for HRA withing Ornithology EIA and HRA Annex (tracked) [G5.2], but not for the EIA. Natural England will consider impacts derived using our bespoke advice and for illustrative purposes the generic SNCB displacement assessment standard approach (including standard apportioning) when forming a position on the potential for significant adverse impact or Adverse Effects on Integrity of designated seabird features. We note that the Applicant has provided a response to Natural England's advice (Applicant’s response to Natural England’s additional guidance on apportioning of seabirds to FFC SPA for Hornsea Project Four [G5.34]) and we will be providing a separate statement in relation to this. The Applicant has further looked to justify their preferred approach to the assessment of displacement impacts on guillemot within Ornithology EIA and HRA Annex (tracked) [G5.2] and Indirect Effects of Forage Fish and Ornithology that we will be providing further comment on in our Deadline 6 submissions. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. On the basis that there is a significant difference between the Applicant's figures and those derived using Natural England's advice, we have increased the RAG status to red. |  | No
B29 | 54 | We recommend that updated displacement matrices are provided in line with the SNCB advice detailed in these comments. Displacement matrices for annual impacts (all seasons summed) should also be presented, for all species. |  | No change. RR-029-APDX:B-54 and RR-029-APDX:B |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | The Applicant has provided an updated assessment providing relevant information in Ornithology EIA and HRA Annex (tracked) [G5.2] . |  |  |  | The Applicant has provided an updated assessment providing relevant information in Ornithology EIA and HRA Annex (tracked) [G5.2] . |  | Yes
B30 | 83 | The method used for assessing displacement impacts during the construction phase is unclear for all species. The methods state that, for construction, the displacement rate is halved, and displacement is calculated based on this lower range, along with a 1% mortality rate for all species. There are no displacement matrices or calculations presented for these. It was agreed during the Evidence Plan Process that for assessing the potential displacement impacts on gannets and auks during the construction phase of Hornsea 4, the impact level to be used would be half that of the operational phase assessments. The Applicant has set out an approach whereby the standard range of displacement rates appears to be halved and then a 1% mortality rate applied. This is not what was agreed. NE advise that the displacement impacts during construction are calculated as 50% of the operational impact level (which should include the full range of displacement rates (from 30 to 70% for auks and from 60 to 80% for gannet) and mortality rates (1 to 10% for all species). These values should then be presented as a range for the predicted impacts during the construction phase. Comments relating to concerns about displacement assessment during operation and original abundance estimates will need to be addressed before displacement impacts can be halved for construction. |  | No change. RR-029-APDX:B-83 |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | The Applicant has provided an updated assessment addressing this in Ornithology EIA and HRA Annex (tracked) [G5.2] . |  |  |  | The Applicant has provided an updated assessment addressing this in Ornithology EIA and HRA Annex (tracked) [G5.2] . |  | Yes
B31 | 86 | As definitive mortality rates for red-throated divers and common scoter are unknown, NE advise a range of figures for mortality rates of between 1% and 10% are considered for assessments (for impacts from array, construction and cable laying vessels). Assessing at 1% mortality is not sufficiently precautionary. |  | Further documenation to address this is due to be submitted at Deadline 2. RR-029-APDX:B-86 |  | The Applicant's document G2.13, Assessment of Common Scoter and Red-Throated Diver within the ECC, submitted at Deadline 2, include the potential impacts of the predicted project alone displacement on baseline mortality rates of red-throated diver and common scoter at 100% displacement and 10% mortality. The estimates did not exceed the 1% threshold for the Greater Wash SPA population. Therefore, we consider that an AEOI on Common Scoter and Red-Throated Diver can be ruled out for predicted displacement impacts from the Hornsea 4 project alone. | [9 empty] | The Applicant's document G2.13, Assessment of Common Scoter and Red-Throated Diver within the ECC, submitted at Deadline 2, include the potential impacts of the predicted project alone displacement on baseline mortality rates of red-throated diver and common scoter at 100% displacement and 10% mortality. The estimates did not exceed the 1% threshold for the Greater Wash SPA population. Therefore, we consider that an AEOI on Common Scoter and Red-Throated Diver can be ruled out for predicted displacement impacts from the Hornsea 4 project alone. |  | Yes
B32 | 88 | “On the basis of 56% of all the birds predicted to be displaced being breeding adult birds from the FFC SPA”. NE note that the proportion of adult guillemots and razorbills used in HRA apportioning (from Furness 2015) is 60% (Volume B2 Chapter 2 RIAA Part 11). |  | The Applicant is reviewing all apportioning assumptions and evidence in the Baseline Sensitivity report due to be submitted at Deadline 3. RR-029-APDX:B-88 |  |  |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | The Applicant has provided an updated assessment addressing this in Ornithology EIA and HRA Annex (tracked) [G5.2] . |  |  |  | The Applicant has provided an updated assessment addressing this in Ornithology EIA and HRA Annex (tracked) [G5.2] . |  | Yes
B33 | 89 | NE do not agree with the 13% weighted apportioning value used here or the current weighting approach assigned as the NE worst case scenario. NE advise that the merits of a bespoke approach to apportionment for guillemot to FFC SPA in August and September should be investigated. (See comments on Volume B2 Chapter 2 RIAA Part 11). |  | No change. RR-029-APDX:B-89 and RR-029-5.7 |  | No change. |  | No change. |  | We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. Further advice was provided by NE to the Applicant on 27th May 2022 to feed into these assessments. We have also submitted this advice into the Examination at Deadline 5. |  | As for B28 above. Natural England consider that the Applicant have followed our advice to provide values for our approach to the assessment for guillemot for HRA withing Ornithology EIA and HRA Annex (tracked) [G5.2], but not for the EIA. Natural England will consider impacts derived using our bespoke advice and for illustrative purposes the generic SNCB displacement assesment approach (including standard apportioning) when forming a position on the potential for significant adverse impact or Adverse Effects on Integrity of designated seabird features. We note that the Applicant has provided a response to Natural England's advice (Applicant’s response to Natural England’s additional guidance on apportioning of seabirds to FFC SPA for Hornsea Project Four [G5.34]) and we will be providing a separate statement in relation to this. The Applicant has further looked to justify their preferred approach to the assessment of displacement impacts on guillemot within Ornithology EIA and HRA Annex (tracked) [G5.2] and Indirect Effects of Forage Fish and Ornithology that we will be providing further comment on this in our Deadline 6 submissions. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. On the basis that there is a significant difference between the Applicant's figures and those derived using Natural England's advice, we have increased the RAG status to red. |  | No change |  | As for B28 above. Natural England consider that the Applicant have followed our advice to provide values for our approach to the assessment for guillemot for HRA withing Ornithology EIA and HRA Annex (tracked) [G5.2], but not for the EIA. Natural England will consider impacts derived using our bespoke advice and for illustrative purposes the generic SNCB displacement assesment approach (including standard apportioning) when forming a position on the potential for significant adverse impact or Adverse Effects on Integrity of designated seabird features. We note that the Applicant has provided a response to Natural England's advice (Applicant’s response to Natural England’s additional guidance on apportioning of seabirds to FFC SPA for Hornsea Project Four [G5.34]) and we will be providing a separate statement in relation to this. The Applicant has further looked to justify their preferred approach to the assessment of displacement impacts on guillemot within Ornithology EIA and HRA Annex (tracked) [G5.2] and Indirect Effects of Forage Fish and Ornithology that we will be providing further comment on this in our Deadline 6 submissions. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. On the basis that there is a significant difference between the Applicant's figures and those derived using Natural England's advice, we have increased the RAG status to red. |  | No
Collision risk Documents used: A5.5.3 Offshore Ornithology Collision Risk Modelling
B34 | 22, 55 | NE request that minimum and maximum collision estimates take into account the variability around flight heights (i.e. the upper and lower 95% confidence intervals around the flight height data) as this parameter can have a greater effect on collision range predictions compared to variability associated with density values. |  | This might be addressed in further submissions at Deadline 3 (RR-029-APDX:B-22) |  |  |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | Although maintaining their position on the inclusion of the 95% CIs for the flight height distributions, the Applicant has considered the influence of the confidence intervals around the flight height distributions on collision estimates for the Natural England Approach in Ornithology EIA and HRA Annex (tracked) [G5.2]. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | Natural England note that minimum and maximum collision risk estimates have been updated for gannet, kittiwake and great black-backed gull in Ornithology EIA and HRA Annex (tracked) [G5.25]. For clarity, the minimum estimates consider the highest ARs, lowest NAF, lower 95% CIs flight height distribution and the densities-SD. The maximum estimates consider the lowest ARs, highest NAF, upper 95% CI flight height distribuition and the densities+SD. |  | Natural England note that minimum and maximum collision risk estimates have been updated for gannet, kittiwake and great black-backed gull in Ornithology EIA and HRA Annex (tracked) [G5.25]. For clarity, the minimum estimates consider the highest ARs, lowest NAF, lower 95% CIs flight height distribution and the densities-SD. The maximum estimates consider the lowest ARs, highest NAF, upper 95% CI flight height distribuition and the densities+SD. |  | No
B36 | 36 | NE note some discrepancies between the Applicant’s impact values and those that NE advise: for EA3 the Applicant has given 41.8 whilst NE advise 4; for Moray West the Applicant has given 12 whilst NE advise 13 |  | Natural England considers the clarifications provided to address the concerns (41.8 was advised at Deadline 11 for EA3 whilst the 12 for Moray West was an error) (RR-029-APDX:B-36) | [11 empty] | Natural England considers the clarifications provided to address the concerns (41.8 was advised at Deadline 11 for EA3 whilst the 12 for Moray West was an error) (RR-029-APDX:B-36) |  | Yes
B37 | 37 | NE note some discrepancies between the Applicant’s impact values and those that NE advise: for Rampion the Applicant has used 0 whilst NE advise 121.5; for EA3 the Applicant has given 92.3 whilst NE advise 112.7. |  | It is argued that kittiwake from Rampion should not be included as they are in the Western Waters and English Channel BDMPS. Natural England will confirm our position on this at Deadline 3. (RR-029-APDX:B-37) |  | In line with other recent assessments (EA1/EA2, Vanguard and Boreas) Natural England request that the impacts on kittiwake from Rampion are included in the cumulative totals for Hornsea Project 4. Rampion is very close to the boundary between the UK North Sea waters region and UK Western Waters and English Channel and Furness (2015) notes that, although in the minority, some birds from UK North Sea colonies enter UK Western Waters and the English Channel. Thus, in line with the precautionary approach, we suggest that there is still potential for birds from the UK North Sea area to be subject to impacts from the Rampion Offshore Wind Farm. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | Natural England note the following in relation to the Applicant's cumulative and in-combination assessments presented in Ornithology EIA and HRA Annex (tracked) [G5.2]: *the Applicant has now introduced Rampion 2 (PEIR) predicted impacts into the assessments considering unconsented projects - impacts from Rampion and Rampion 2 are not considered for kittiwake for EIA as the project is not within the relevant BDMPS area. Natural England agree this approach. *for kittiwake, the Applicant has included impacts for unconsented projects in relevant EIA and HRA assessments. Given the current assumption that projects from Hornsea 3 onwards will fully compensate for impacts on kittiwake for HRA, we suggest the same assumption is applied for unconsented projects which are also likely to require compensation is secured for kittiwake. *there are summing errors in Table 51 (Ornithology EIA and HRA Annex (tracked) [G5.2]) where the Applicant appears to have not adjusted for their own values for Hornsea 3. We have calculated the NE total for consented projects should be 3979 and for all projects 4014. We have calculated the Applicant's total for consented projects to be 3864 and for all projects to be 3895. *we note there are summing errors in Table 110 (Ornithology EIA and HRA Annex (tracked) [G5.2]) where the Applicant appears to have not adjusted for their own values for Hornsea 3. We have calculated the NE total for consented projects should be 8735 and for all projects 9176. We have calculated the Applicant's total for consented projects to be 8145 and for all project to be 8586. Natural England are able to make these adjustments when forming our position based on the information provided by the Applicant, therefore Natural England do not require any further action from the Applicant. |  | No change |  | Natural England note the following in relation to the Applicant's cumulative and in-combination assessments presented in Ornithology EIA and HRA Annex (tracked) [G5.2]: *the Applicant has now introduced Rampion 2 (PEIR) predicted impacts into the assessments considering unconsented projects - impacts from Rampion and Rampion 2 are not considered for kittiwake for EIA as the project is not within the relevant BDMPS area. Natural England agree this approach. *for kittiwake, the Applicant has included impacts for unconsented projects in relevant EIA and HRA assessments. Given the current assumption that projects from Hornsea 3 onwards will fully compensate for impacts on kittiwake for HRA, we suggest the same assumption is applied for unconsented projects which are also likely to require compensation is secured for kittiwake. *there are summing errors in Table 51 (Ornithology EIA and HRA Annex (tracked) [G5.2]) where the Applicant appears to have not adjusted for their own values for Hornsea 3. We have calculated the NE total for consented projects should be 3979 and for all projects 4014. We have calculated the Applicant's total for consented projects to be 3864 and for all projects to be 3895. *we note there are summing errors in Table 110 (Ornithology EIA and HRA Annex (tracked) [G5.2]) where the Applicant appears to have not adjusted for their own values for Hornsea 3. We have calculated the NE total for consented projects should be 8735 and for all projects 9176. We have calculated the Applicant's total for consented projects to be 8145 and for all project to be 8586. Natural England are able to make these adjustments when forming our position based on the information provided by the Applicant, therefore Natural England do not require any further action from the Applicant. |  | No
B38 | 38 | NE note some discrepancies between the Applicant’s impact values and those that NE advise: for EA3 the Applicant has given 34.4 whilst NE advise 39. It appears that the Applicant has used the non-breeding collisions alone. |  | The correction has been agreed (RR-029-APDX:B-38) | [11 empty] | The correction has been agreed (RR-029-APDX:B-38) |  | Yes
B39 | 39 | As with the other assessments for gannet, a worst-case scenario including 10% mortality for 60% and 80% displacement has not been included. These scenarios should be provided. Counterfactuals of final population size are also not included in the table and should be provided. |  | Further submisions are expected at Deadlines 2 and 3. RR-029-APDX:B-39 |  |  |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | The Applicant has provided an updated assessment addressing this in Ornithology EIA and HRA Annex (tracked) [G5.2]. The Applicant still does not provide counterfactuals of final population size. We consider this to be unhelpful. Natural England are able to form an initial position based on the counterfactuals of growth rate but we maintain that these should be provided to allow a full and transparent assessment of the PVA metrics. |  | No change |  | The Applicant has provided an updated assessment addressing this in Ornithology EIA and HRA Annex (tracked) [G5.2]. The Applicant still does not provide counterfactuals of final population size. We consider this to be unhelpful. Natural England are able to form an initial position based on the counterfactuals of growth rate but we maintain that these should be provided to allow a full and transparent assessment of the PVA metrics. |  | No
B40 | 56 | Natural England question the approach for deriving mean densities, CIs and standard deviations (SDs) for used in the Band CRM or sCRM collision risk modelling. These parameters are fundamental to estimating potential collision impacts and potential variability or uncertainty. The Applicant should clarify how densities and associated CIs were estimated for birds in flight from modelled density surfaces based on all birds and following any apportioning of unidentified species. |  | Natural England accept the clarification provided but would like the data that went into calculations to be provided with any updated assessments before this issue can be closed out. RR-029-APDX:B-56 |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | Following further discussion with the Applicant it has become apparent that CIs associated with corrected estimates could not be derived. Based on our discussions, the Applicant has adopted a different approach to the estimation of SDs for sCRM in Ornithology EIA and HRA Annex (tracked) [G5.2] using the revised modelling data and bootstrap samples. |  |  |  | Following further discussion with the Applicant it has become apparent that CIs associated with corrected estimates could not be derived. Based on our discussions, the Applicant has adopted a different approach to the estimation of SDs for sCRM in Ornithology EIA and HRA Annex (tracked) [G5.2] using the revised modelling data and bootstrap samples. |  | Yes
B41 | 57 | Whilst NE appreciates alternate impact scenarios are presented by the Applicant, we advise that any further analysis and assessment includes the applied use of outputs presented and based on SNCB guidance and not exclusively only the Applicant’s modelled impacts. |  | Further submisions are expected at Deadline 3. RR-029-APDX:B-57. |  |  |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | The Applicant has provided an updated assessment addressing this in Ornithology EIA and HRA Annex (tracked) [G5.2] . |  |  |  | The Applicant has provided an updated assessment addressing this in Ornithology EIA and HRA Annex (tracked) [G5.2] . |  | Yes
[12 empty] | We noted an inconsistency in the density data presented in the Revised Ornithological Baseline (tracked) [G5.9] and the data apparently used for CRM (kittiwake and gannet) in the Ornithology EIA and HRA Annex (tracked). The Applicant has provided clarification on this and assurance that the central collision estimates are correct. However, this has led to them identifying an issue with the standard deviations used in the CRM and they have suggested they will provide updated figures at Deadline 6. Natural England do not consider that this issue will result in a material change to our position. We are still requesting the Applicant provides sCRM log files for our reference. |  | The Applicant has provided updated minimum and maximum collision estimates for gannet, kittiwake and great black-backed gull within G5.25 Ornithology EIA and HRA Annex (tracked). We have used these to inform our position at Deadline 7. Despite our requests, no sCRM log files have been provided by the Applicant. |  | The Applicant has provided updated minimum and maximum collision estimates for gannet, kittiwake and great black-backed gull within G5.25 Ornithology EIA and HRA Annex (tracked). We have used these to inform our position at Deadline 7. Despite our requests, no sCRM log files have been provided by the Applicant.
Population Viability Analysis Documents used: A2.5 Offshore and Intertidal Ornithology, A5.5.4 Ornithology Population Viability Analysis, B2.2 Report to Inform Appropriate Assessment Part 1, B2.2 Report to Inform Appropriate Assessment Part 11: Offshore Ornithology FFC SPA Population Viability Analysis
B42 | 18,60,96,114,117 | No values have been presented in line with the NE approach and the Counterfactuals of Final Population Size (CFPS) have not been provided, against NE advice. NE consider that these should be provided for all PVA results. |  | Natural England maintains that CFPS need to be provided (RR-029-APDX:B-18). |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | Natural England welcome that the Applicant has provided updated PVA's covering an array of impacts within Ornithological Assessment Sensitivity Report [G4.7]. NE will utilise these values when forming our position on the impacts of the project. However, we note that the Applicant continues to refuse to provide the counterfactuals of final population size as a standard output from the models. We consider this to be unhelpful. Natural England will be able to form an initial position based on the counterfactuals of growth rate but we maintain that the other counterfactuals should be provided to allow a full and transparent assessment of the PVA metrics. Further NE advised the Applicant at Deadline 5a [REP5a-029] that several of the PVAs are currently based on a Applicant modified BDMPS population that NE do not agree with (kittiwake, guillemot and puffin). NE also informed the Applicant of a new issue with the NE/JNNC PVA tool which may influence interpretation of outputs from the kittiwake model. We are awaiting a response from the Applicant on whether these issues will be addressed or not. |  | No change |  | Natural England welcome that the Applicant has provided updated PVA's covering an array of impacts within Ornithological Assessment Sensitivity Report [G4.7]. NE will utilise these values when forming our position on the impacts of the project. However, we note that the Applicant continues to refuse to provide the counterfactuals of final population size as a standard output from the models. We consider this to be unhelpful. Natural England will be able to form an initial position based on the counterfactuals of growth rate but we maintain that the other counterfactuals should be provided to allow a full and transparent assessment of the PVA metrics. Further NE advised the Applicant at Deadline 5a [REP5a-029] that several of the PVAs are currently based on a Applicant modified BDMPS population that NE do not agree with (kittiwake, guillemot and puffin). NE also informed the Applicant of a new issue with the NE/JNNC PVA tool which may influence interpretation of outputs from the kittiwake model. We are awaiting a response from the Applicant on whether these issues will be addressed or not. |  | Yes
B43 | 58115 | Lesser black-backed gull and herring gull have been excluded from full assessment using PVA for EIA impacts. Even if project alone predicted collisions for a species are small, these should still be added to the cumulative/in-combination total and an assessment made at this level. NE advise that PVA modelling is undertaken for species where the project alone or cumulative/in-combination level impact reaches 1% of baseline mortality for the population. |  | Natural England maintains it should be confirmed that 1% natural baseline mortality is not exceeded to enable the species to be fully ruled out. RR-029-APDX:B-58 and RR-029-APDX:B-6. |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | Natural England have progressed LBBG and herring gull through the EIA cumulative assessment to consider the very small predicted impacts at the BDMPS level. We note that LBBG cumulative impacts currently exceed the 1% increase in baseline mortality threshold which should trigger PVA. We will take this into consideration when forming our positions on the impacts of the project therefore we do not require anything further from the Applicant at this time. |  | No change |  | Natural England have progressed LBBG and herring gull through the EIA cumulative assessment to consider the very small predicted impacts at the BDMPS level. We note that LBBG cumulative impacts currently exceed the 1% increase in baseline mortality threshold which should trigger PVA. We will take this into consideration when forming our positions on the impacts of the project therefore we do not require anything further from the Applicant at this time. |  | No
B44 | 59116 | NE note there is no reference to the use of a ‘burn in’ period or justification for why one has not been included. NE consider that a ‘burn in’ period should be used, or a justification for why one has not been used provided. |  | The Applicant has tested burn-in values from 10-40 and will use 10 going forwards. This addresses Natural England's concern. | [11 empty] | The Applicant has tested burn-in values from 10-40 and will use 10 going forwards. This addresses Natural England's concern. |  | Yes
B45 | 61 | No data are included in the Survival rate column, rather the table indicates a “National pre-formulated” rate used. Clarity is needed on the specific survival rates used, including survival rates for the different age classes used. |  | We consider it would be beneficial for the values used to be provided. RR-029-APDX:B-61 |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | Natural England has utilised the PVA logs to check the survival rate values used by the Applicant. |  |  |  | Natural England has utilised the PVA logs to check the survival rate values used by the Applicant. |  | Yes
B46 | 61 | Productivity rates are presented, and NE agree with the values used for EIA, however we note that there is a discrepancy between the value presented in Table 2 for kittiwake and the value that appears in the equivalent logfile from the PVA run in Appendix A. Table 2 cites the east coast rate of 0.819 for kittiwake which we agree is the most appropriate rate for the cumulative BDMPS scale PVA. The matching logfile in Appendix A indicates that 0.69 (pg 57) was used which is the most appropriate rate for the biogeographic scale assessment. The productivity rate used should be checked and the PVA re-run as required. |  | It has been confirmed that the productivity rate used was an error. The Applicant will review and re-run the assessment if required. RR-029-APDX:B-61 |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | The Applicant has applied the correct value in the most recent PVA supplied in Ornithological Assessment Sensitivity Report [G4.7]. |  |  |  | The Applicant has applied the correct value in the most recent PVA supplied in Ornithological Assessment Sensitivity Report [G4.7]. |  | Yes
B47 | 62 | Following the displacement assessment, we note that the PVA was not carried out using a worst-case scenario of 80% displacement and 10% morality for gannet as per NE advice. We advise that this is provided, and the results considered in relation to combined collision and displacement impact scenarios. |  | Documents to be submitted at Deadline 2. RR-029-APDX:B-62 and RR-029-APDX:B-12. |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | The Applicant has followed Natural England's suggestion to examine a large range of impact scenarios (Ornithological Assessment Sensitivity Report [G4.7]). This has emcompased the full range of impacts based on Natural England's advised approach. |  |  |  | The Applicant has followed Natural England's suggestion to examine a large range of impact scenarios (Ornithological Assessment Sensitivity Report [G4.7]). This has emcompased the full range of impacts based on Natural England's advised approach. |  | Yes
B48 | 91121 | Due to the high degree of uncertainty surrounding sabbatical rates NE have not agreed to their use within impact assessments. If the Applicant can provide robust evidence for site-specific sabbatical rates, including seasonal variations then this could be considered when undertaking PVA modelling. However, where there is significant uncertainty around sabbatical rates the precautionary approach is to assume no adults within the site are on sabbaticals. NE suggest the Applicant should supply evidence demonstrating: a) the proportion of birds that take sabbaticals; b) whether the population estimates at an SPA exclude sabbaticals; and, c) whether sabbaticals return to the sea area around the colony. This should inform if/how sabbaticals are best incorporated in a PVA. |  | Further documents will be submitted at Deadline 3. We note that values excluding sabbatical rates have been provided. RR-029-APDX:B-91 | [5 empty] | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | The Applicant has not provided strong evidence for sabbatical rates and Natural England maintain our current position on sabbaticals during apportioning. The Applicant has followed our advice in providing assessments based on the Natural England approach. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No change |  | The Applicant has not provided strong evidence for sabbatical rates and Natural England maintain our current position on sabbaticals during apportioning. The Applicant has followed our advice in providing assessments based on the Natural England approach. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No
B49 | 118 | For kittiwake, Hornsea 4 has used a mean productivity value of 0.722 (SD 0.210). Natural England advise using a productivity rate of 0.580 (SD 0.096) for PVA models for the kittiwake population of FFC SPA. This represents the mean productivity across all plots in Flamborough/Bempton and Filey for the period 2012-2019 which represents the period when productivity plots were covered in both Flamborough/Bempton and Filey areas of the FFC SPA. The results of the current kittiwake PVA may present an optimistic picture of impact on colony growth rates, which would reinforce the conclusion of AEOI in-combination. Should the PVA modelling need to be rerun for kittiwake, Natural England advise using 0.580 (0.096) as the productivity value for kittiwake. |  | Natural England and the Applicant maintain their respective positions. We would expect our comments to be addressed in any re-runs of the PVA . RR-029-APDX:B-118 and RR-029-APDX:B-W. T |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | Natural England welcome that the Applicant has provided PVAs with a productivity rate of 0.58 (SD 0.096) for kittiwake at FFC SPA. We note that they have also undertaken a validation exercise which they suggest means a higher productivity rate should be adopted. However, Natural England note that the issue with the PVA tool (see B42) could influence interpretation of the validation and we are awaiting a response on this matter. |  | No change |  | Natural England welcome that the Applicant has provided PVAs with a productivity rate of 0.58 (SD 0.096) for kittiwake at FFC SPA. We note that they have also undertaken a validation exercise which they suggest means a higher productivity rate should be adopted. However, Natural England note that the issue with the PVA tool (see B42) could influence interpretation of the validation and we are awaiting a response on this matter. |  | No
B50 | 120123124 | NE strongly disagree with the use of adult apportioning based on stable age structure data. NE disagree with this approach as it is unlikely that a stable age structure, generalised across multiple years and sea areas, is likely to be representative of the Hornsea 4 area. Instead, we advise that where site-specific ageing data, for species that can be clearly aged as adults or sub-adults, such as gannet, is available from either relevant digital aerial survey (DAS) or boat-based surveys, these should be used. We note that this was the case for gannet in a previous iteration of this report that NE reviewed, but this information has now been excluded from the RIAA. |  | No change. RR-029-APDX:B-120 , RR-029-APDX:B-82 and RR-029-APDX:B-44. |  | No change. |  | No change. |  | We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. Further advice was provided by NE to the Applicant on 27th May 2022 to feed into these assessments. We have also submitted this advice into the Examination at Deadline 5. |  | We note the Applicant maintains their position on this matter and they have provided further discussion around the use of at-sea ageing data (Ornithological Assessment Sensitivity Report [G4.7] and Applicant’s response to Natural England’s additional guidance on apportioning of seabirds to FFC SPA for Hornsea Project Four [G5.34]). However, they have provided some additional data (in Ornithology EIA and HRA Annex (tracked) [G5.2]) following further advice from Natural England [REP5-116] in relation to gannet and kittiwake adult proportions derived from survey data to be used for apportioning impacts to FFC SPA. We do not agree that the Applicant has used all data across all seasons to estimate adult, or adult type, proportions and we have calculated the values based on the Natural England defined breeding season. We will consider these revised values when forming our position on the potential impacts of the project. |  | No change |  | We note the Applicant maintains their position on this matter and they have provided further discussion around the use of at-sea ageing data (Ornithological Assessment Sensitivity Report [G4.7] and Applicant’s response to Natural England’s additional guidance on apportioning of seabirds to FFC SPA for Hornsea Project Four [G5.34]). However, they have provided some additional data (in Ornithology EIA and HRA Annex (tracked) [G5.2]) following further advice from Natural England [REP5-116] in relation to gannet and kittiwake adult proportions derived from survey data to be used for apportioning impacts to FFC SPA. We do not agree that the Applicant has used all data across all seasons to estimate adult, or adult type, proportions and we have calculated the values based on the Natural England defined breeding season. We will consider these revised values when forming our position on the potential impacts of the project. |  | No
B51 | 125 | NE do not agree that the approach presented here should be called the “Natural England WCS method”, as we disagree with two crucial aspects of it: - NE do not support the use of the stable age structure approach and request site-specific ageing data is detailed and used to inform adult apportioning. In the absence of site-specific data, all adult-type birds should be assumed to be adults. -NE do not support the use of the weighted approach, which we believe will misrepresent impacts in August-September and October-February. |  | No change. RR-029-APDX:B-125, RR-029-5.7 and RR-029-APDX:B-44 |  | No change. |  | No change. |  | We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. Further advice was provided by NE to the Applicant on 27th May 2022 to feed into these assessments. We have also submitted this advice into the Examination at Deadline 5. |  | The Applicant has provided an updated assessment including our latest advice in Ornithology EIA and HRA Annex (tracked) [G5.2]. We disagree with the estimation of the proportions of adults based on all months of the year, rather than just the breeding season, for which it's being used. Due to this disagreement and time constraints, we have produced adjusted values based on the same dataset, limited to the Natural England defined breeding seasons, and have used these values in apportioning gannet and kittiwake to inform our position at Deadline 6. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No change |  | The Applicant has provided an updated assessment including our latest advice in Ornithology EIA and HRA Annex (tracked) [G5.2]. We disagree with the estimation of the proportions of adults based on all months of the year, rather than just the breeding season, for which it's being used. Due to this disagreement and time constraints, we have produced adjusted values based on the same dataset, limited to the Natural England defined breeding seasons, and have used these values in apportioning gannet and kittiwake to inform our position at Deadline 6. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No
B52 | 126 | We note that the Applicant includes a footnote to Table 7 which appears to suggest that the NE advised seasons for gannet were considered in relation to the project collision risk numbers based on the NE approach. This appears to be the first time it is mentioned in any of the submitted documents. Further, the Applicant appears to have only considered a single collision mortality estimate for the Applicant’s and the NE scenarios for the project, but it is not clear what these are based on in this section (e.g. Applicant’s approach central values and NE upper CIs). Clarification is needed on whether the numbers are based on the NE advised seasons and whether this was the case solely for CRM in this document. |  | Some clarification has been provided. We will provide further comment after reviewing updates in planned future submissions. RR-029-APDX:B-126 |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | The Applicant has provided an updated assessment in Ornithology EIA and HRA Annex (tracked) [G5.2] which has addressed these issues. |  |  |  | The Applicant has provided an updated assessment in Ornithology EIA and HRA Annex (tracked) [G5.2] which has addressed these issues. |  | Yes
B53 | 127 | NE note that values up to Hornsea 3 are not included in the table. It is also unclear what seasonal definitions have been adopted for the NE approach. Further, the Applicant appears to have only considered a single impact estimate for the Applicant’s and the NE scenarios for the project, but it is not clear what these are based on in this section (e.g. Applicant’s approach central values and NE upper CIs). NE advises that the upper and lower confidence intervals should be presented and considered in relation to the potential impacts modelled to illustrate the underlying uncertainty. |  | Some clarification has been provided. We will provide further comment after reviewing updates in planned future submissions. RR-029-APDX:B-127 |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | The Applicant has provided an updated assessment in Ornithology EIA and HRA Annex (tracked) [G5.2] which has addressed these issues. |  |  |  | The Applicant has provided an updated assessment in Ornithology EIA and HRA Annex (tracked) [G5.2] which has addressed these issues. |  | Yes
B54 | 128 | Table 12: NE cannot reproduce the in-combination estimates up to Hornsea Project Three based on the Applicant’s values provided in the RIAA chapter for each project. This indicates some checking is required. |  | The Applicant is currently reviewing a number of different elements used throughout the assessment process and should any material errors be identified, then PVAs can be re-run. RR-029-APDX:B-128 |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | Natural have checked the most recent cumulative and in-combination totals provided by the Applicant and provide comment on possible issues in B37 above. |  | No change |  | Natural have checked the most recent cumulative and in-combination totals provided by the Applicant and provide comment on possible issues in B37 above. |  | No
B55 | 129130 | NE again note that, despite a footnote appearing for Table 14, it has not been made clear what seasonal definitions have been used for gannet and kittiwake for the NE approach. Please clarify what seasonal definitions have been used for which assessment and ensure that NE advice is followed for the NE approach throughout the assessment process. |  | See Points 52 and 53.RR-029-APDX:B-129 | [11 empty] | See Points 52 and 53.RR-029-APDX:B-129 |  | Yes
Miscellaneous/Cumulative/EIA/RIAA Document Used: A2.5 Offshore and Intertidal Ornithology, B2.2 Report to Inform Appropriate Assessment Part 1
B56 | 3,32,61 | Natural England disagrees with the approach taken by the Applicant to calculate regional breeding season populations. For EIA assessments Natural England advise calculating the total annual impact for a species; then assessing this against the largest seasonal population (breeding or non-breeding) at the appropriate BDMPS population scale. We advise that values for herring gull and lesser black-backed gull should also be provided so they can be referred to in relation to cumulative assessment (see Point 4). NE advises the largest BDMPS values should be used which are in line with those advised for EA1N/EA2 (REP11-027) and Hornsea Project Two (REP6-017) (values given in table in Rel Reps comment). Changes made in response to this advice will need to be carried through to all assessments. |  | The Applicant has sought clarification on the method for calculating the breeding season BDMPS (RR-029-APDX:B-3). Natural England provided the following advice to the Applicant on 25th March 2022: In the case of guillemot and puffin the breeding season BDMPS populations are larger than the non-breeding season estimates presented in Furness (2015), and Natural England therefore advise that these are used in the EIA assessment. This was first raised with the Applicant during our written advice on the draft ES, associated annexes, and RIAA documents provided 21 June 2021. Natural England note that the values advised in the Relevant Reps have also previously been provided for the EA1N/EA2 (REP11-027) and Hornsea Project Two (REP6-017) projects. Natural England also note that these populations are larger than those proposed by the Applicant, resulting in a larger 1% natural mortality threshold for EIA. Natural England can confirm that the breeding season BDMPS populations were calculated using the data in Appendix A of Furness (2015). The numbers of breeding adults and immatures from each individual SPA populations or non-SPA colony with a foraging range within the respective BDMPS region were summed to generate a total breeding population. For guillemot the values presented in Appendix A: Table 62 were used to generate a population estimate of 2,045,078. For puffin the values from Appendix A: Table 68 were used to generate a population estimate of 868,689. Table 1 and 2 highlight the values which were summed in each case. |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | We note that the Applicant has sought to include our advice on this within their Ornithological Assessment Sensitivity Report [G4.7]. However, they have further adjusted our values to include overseas populations, based on the non-breeding season BDMPS values, for the breeding season. Natural England disagree with this approach as the non-breeding season population from overseas colonies is highly unlikley to be representative of the breeding season composition. This has resulted in the Applicant increasing the BDMPS values used in their assessment which will further dilute the potential impacts. Natural England have provided comment on this to the Applicant [REP5a-029] and suggest that the issue influences both the interpreation of the % increase in baseline mortality and PVA undertaken for kittiwake, guillemot and puffin within Ornithology EIA and HRA Annex (tracked) [G5.2] and Ornithological Assessment Sensitivity Report [G4.7]. |  | No change |  | We note that the Applicant has sought to include our advice on this within their Ornithological Assessment Sensitivity Report [G4.7]. However, they have further adjusted our values to include overseas populations, based on the non-breeding season BDMPS values, for the breeding season. Natural England disagree with this approach as the non-breeding season population from overseas colonies is highly unlikley to be representative of the breeding season composition. This has resulted in the Applicant increasing the BDMPS values used in their assessment which will further dilute the potential impacts. Natural England have provided comment on this to the Applicant [REP5a-029] and suggest that the issue influences both the interpreation of the % increase in baseline mortality and PVA undertaken for kittiwake, guillemot and puffin within Ornithology EIA and HRA Annex (tracked) [G5.2] and Ornithological Assessment Sensitivity Report [G4.7]. |  | No
B57 | 4,23 | Natural England do not agree with the exclusion of herring gull and lesser black-backed gull from full cumulative assessments. These should be included, considering annual impacts against the 1% baseline mortality rates for the largest BDMPS population. |  | See Point 43 (RR-029-APDX:B-4; RR-029-APDX:B-23) |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | Natural England have taken LBBG and herring gull through the cumulative assessment for EIA and note that, despite the very small numbers of predicted impacts, the cumulative total for LBBG would lead to an increase in baseline mortality of >1% based on the BDMPS population. We will take this into consideration when forming our positions on the impacts of the project therefore we do not require anything further from the Applicant at this time. |  | No change |  | Natural England have taken LBBG and herring gull through the cumulative assessment for EIA and note that, despite the very small numbers of predicted impacts, the cumulative total for LBBG would lead to an increase in baseline mortality of >1% based on the BDMPS population. We will take this into consideration when forming our positions on the impacts of the project therefore we do not require anything further from the Applicant at this time. |  | No
B58 | 6,78, 81 | The Applicant has not considered impacts from Hornsea 4 in the cumulative assessment if the project alone assessment was “negligible”. NE advise that even small, predicted impacts at the project alone level should still be considered in the context of a cumulative assessment with other plans and projects where there are concerns around cumulative impacts from multiple OWF. Cumulative annual impacts (including variability and uncertainty) should be assessed against the relevant largest BDMPS 1% baseline mortality threshold to clearly rule out the potential for any significant effects. |  | See Point 43 (RR-029-APDX:B-6). |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | See response to B57 above. |  | No change |  | See response to B57 above. |  | No
B59 | 11 | The Applicant concludes that if no significant impacts were identified on fish and benthic in their respective assessments, then there would be no significant impacts on ornithology receptors. Natural England disagrees with this assumption. Natural England advises that a summary of the outcomes of the relevant assessments on forage fish abundance and distribution in and around the project area should be included and discussed in relation to the implications for key seabird species. |  | Further information on indirect effects is due to be submitted at Deadline 3. | [5 empty] | Further information on indirect effects is due to be submitted at Deadline 5. |  | Natural England acknowledge that the Applicant has looked to address this issue through the provision of an Indirect Effects of Forage Fish and Ornithology [G5.7] report at Deadline 5. We will be providing an additional written response to this report in our Deadline 6 submissions. Natural England do not agree with the Applicant in relation to the importance of the area for key seabird species (namely guillemot and razorbill) during chick rearing and moult. We do not believe it is possible to rule out significance of the project on ecosytem functioning in and around the array. This has the potential to alter the abundance and distribtion of forage fish that are the likely drivers of the large numbers of guillemot and razorbill found in the array and adjacent area during August and September when birds are dispersing from the nearby FFC SPA colony. See also response to B19. |  | No change |  | Natural England acknowledge that the Applicant has looked to address this issue through the provision of an Indirect Effects of Forage Fish and Ornithology [G5.7] report at Deadline 5. We will be providing an additional written response to this report in our Deadline 6 submissions. Natural England do not agree with the Applicant in relation to the importance of the area for key seabird species (namely guillemot and razorbill) during chick rearing and moult. We do not believe it is possible to rule out significance of the project on ecosytem functioning in and around the array. This has the potential to alter the abundance and distribtion of forage fish that are the likely drivers of the large numbers of guillemot and razorbill found in the array and adjacent area during August and September when birds are dispersing from the nearby FFC SPA colony. See also response to B19. |  | No
B60 | 29 | NE agree that all relevant offshore wind farm projects have been considered in the cumulative assessment. However, we note that the range of predicted Hornsea 4 impacts are not considered in the cumulative assessments. Natural England request that the minimum and maximum cumulative predicted impacts (based on the central values for other projects and the range for Hornsea 4) are provided to allow consideration of uncertainty around estimates and confidence placed in conclusions. |  | No change. (RR-029-APDX:B-29) |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | We note that the variability in predicted impacts has not been taken through to the cumulative assessment. However, we note the main emphasis should be on central values for collision risk, and the impacts at the upper and lower displacement and mortality rates advised by Natural England for Displacement. Based on this we are happy that we have sufficient information to form a position on the potential cumulative impacts of the project. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No change |  | We note that the variability in predicted impacts has not been taken through to the cumulative assessment. However, we note the main emphasis should be on central values for collision risk, and the impacts at the upper and lower displacement and mortality rates advised by Natural England for Displacement. Based on this we are happy that we have sufficient information to form a position on the potential cumulative impacts of the project. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No
B61 | 30,31 | We note that the values in Table 5.48 do not sum to the total estimates in the ‘all projects’ total. Again, the assessment is also conducted for seasons defined around migration-free breeding rather than overall breeding season as requested by NE. Please ensure a version of the assessment is provided using the NE advised seasonal definitions. |  | The Applicant confirmed there was an error in the table which has been addressed. (RR-029-APDX:B-30) | [7 empty] | Note - Natural England have checked the most recent cumulative and in-combination totals provided by the Applicant and provide comment on possible issues in B37 above. We consider the Applicant has provided assessments broadly in line with our advice. We have flagged relevant summing errors and provided our position on several specific aspects of the in-combination assessment values (see B37, B81 and B85). In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No change |  | Natural England have checked the most recent cumulative and in-combination totals provided by the Applicant and provide comment on possible issues in B37 above. We consider the Applicant has provided assessments broadly in line with our advice. We have flagged relevant summing errors and provided our position on several specific aspects of the in-combination assessment values (see B37, B81 and B85). In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No
B62 | 71 | NE notes that sources of variability and uncertainty have not been considered in relation to any of the impacts carried through the HRA assessments. NE require this information on precision to allow judgement about what reliance can be placed on the estimates and to allow incorporation of variability into the range of impacts assessed. NE request that the Applicant includes predicted impacts with associated upper and lower estimates for consideration during the assessment and any associated PVA. |  | No change. Natural England maintains our position. RR-029-APDX:B-71 and RR-029-APDX:B-103 |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | We welcome the Applicant's Ornithological Assessment Sensitivity Report [G4.7] and Ornithology EIA and HRA Annex (tracked) [G5.2] that provide further information on the range of potential impacts based on Natural England's advised approach and that a range of PVA scenarios have been explored by the Applicant. |  | No change |  | We welcome the Applicant's Ornithological Assessment Sensitivity Report [G4.7] and Ornithology EIA and HRA Annex (tracked) [G5.2] that provide further information on the range of potential impacts based on Natural England's advised approach and that a range of PVA scenarios have been explored by the Applicant. |  | Yes
B63 | 72 | There is no clear presentation of the data used to derive the displacement impacts for the Appropriate Assessment (AA). For example, the Applicant has not presented information to show the peak abundance for each season, or the mean of the peak abundances across the survey years. Further, displacement matrices that use the upper and lower 95% confidence limits for the abundance estimates are not presented. These should be provided. |  | No change. Natural England maintains our position.RR-029-APDX:B-72 and RR-029-APDX:B-103 |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | We note that the Applicant has not not been able to provide confidence intervals associated with corrected and adjusted abundance estimates and maintain it is inappropriate to use these values in the assessment (Applicant’s response to Natural England’s additional guidance on apportioning of seabirds to FFC SPA for Hornsea Project Four [G5.34]). |  | No change |  | We note that the Applicant has not not been able to provide confidence intervals associated with corrected and adjusted abundance estimates and maintain it is inappropriate to use these values in the assessment (Applicant’s response to Natural England’s additional guidance on apportioning of seabirds to FFC SPA for Hornsea Project Four [G5.34]). |  | No
B64 | 73 | It is currently unclear what baseline mortality rates have been used in the RIAA. It is understood that these are based on adult rates rather than the weighted approach, but clarity should be provided on this. |  | It has been clarified that the adult survival rates are from Horswill & Robinson (2015). RR-029-APDX:B-73 | [11 empty] | It has been clarified that the adult survival rates are from Horswill & Robinson (2015). RR-029-APDX:B-73 |  | No
B65 | 75 | NE request that the ‘full’ breeding seasons are used for the assessment of impacts on gannet and kittiwake, rather than ‘migration-free breeding’ seasons. |  | Further comment will be provided when the Assessment Sensitivity Report is provided at Deadline 3. RR-029-APDX:B-75 |  |  |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | The Applicant has adopted our advice and provided assessment based on our seasonal definitions under the Natural England approach in Ornithology EIA and HRA Annex (tracked) [G5.2]. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No change |  | The Applicant has adopted our advice and provided assessment based on our seasonal definitions under the Natural England approach in Ornithology EIA and HRA Annex (tracked) [G5.2]. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No
B66 | 77 | NE note that model-based density data used in CRM are not provided with 95% CIs in Volume A5, Annex 5.1. Corrected and apportioned population data are also not provided with associated CIs despite these values underpinning displacement assessments. These should be provided in due course. |  | To be addressed in submissions at Deadline 2 and 3. RR-029-APDX:B-77 |  |  |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | We note that the Applicant has not not been able to provide confidence intervals associated with corrected and adjusted abundance estimates and maintain it is inappropriate to use these values in the assessment (Applicant’s response to Natural England’s additional guidance on apportioning of seabirds to FFC SPA for Hornsea Project Four [G5.34]). |  |  |  | We note that the Applicant has not not been able to provide confidence intervals associated with corrected and adjusted abundance estimates and maintain it is inappropriate to use these values in the assessment (Applicant’s response to Natural England’s additional guidance on apportioning of seabirds to FFC SPA for Hornsea Project Four [G5.34]). |  | No
B67 | 79,94,120,122 | NE disagree with apportioning based on the stable age structure (Furness 2015). NE have previously requested additional information on the age structure of the guillemot and razorbill using the site, which has not been provided. NE request further evidence be provided on the site-specific age structure of guillemot using the site. In the absence of this information and any evidence to suggest otherwise, NE advise that all adult-type birds are assumed to be adults. NE have not agreed the new approach provided for guillemot and, based on scrutiny of the methods used, advise that a more appropriate precautionary approach to apportioning impacts to FFC for guillemot in August and September will be required. Also, pending a review of the baseline characterisation data, in which we currently have very low confidence, it may also be necessary to apply a similar bespoke approach to apportioning razorbill in August and September. |  | Natural England and the Applicant maintain their respective positions. RR-029-APDX:B-79, RR-029-APDX:B-44 and RR-029-5.7 |  | No change. |  | No change. |  | Natural England provided further advice to the Applicant on the apportioning of auks on 27th May 2022. We have also submitted this advice into the Examination at Deadline 5. |  | The Applicant has not been able to provide any futher site-specific ageing data for the auks, but they have used SNCB advice in relation to apportioning during the breeding and post-breeding (razorbill) or chick rearing/moult periods in Ornithology EIA and HRA Annex (tracked) [G5.2]. Whilst the Applicant has provided their clear opinions (Applicant’s response to Natural England’s additional guidance on apportioning of seabirds to FFC SPA for Hornsea Project Four [G5.34]) regarding Natural England's advised approach to assessing displacement of guillemot and razorbill [REP5-115], they have used our advice and provided appropriate results for consideration Ornithology EIA and HRA Annex (tracked) [G5.2]. Natural England will be providing a response to Applicant’s response to Natural England’s additional guidance on apportioning of seabirds to FFC SPA for Hornsea Project Four [G5.34] at Deadline 6. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. On the basis that there is a significant difference between the Applicant's figures and those derived using Natural England's advice, we have increased the RAG status to red. |  | No change |  | The Applicant has not been able to provide any futher site-specific ageing data for the auks, but they have used SNCB advice in relation to apportioning during the breeding and post-breeding (razorbill) or chick rearing/moult periods in Ornithology EIA and HRA Annex (tracked) [G5.2]. Whilst the Applicant has provided their clear opinions (Applicant’s response to Natural England’s additional guidance on apportioning of seabirds to FFC SPA for Hornsea Project Four [G5.34]) regarding Natural England's advised approach to assessing displacement of guillemot and razorbill [REP5-115], they have used our advice and provided appropriate results for consideration Ornithology EIA and HRA Annex (tracked) [G5.2]. Natural England will be providing a response to Applicant’s response to Natural England’s additional guidance on apportioning of seabirds to FFC SPA for Hornsea Project Four [G5.34] at Deadline 6. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. On the basis that there is a significant difference between the Applicant's figures and those derived using Natural England's advice, we have increased the RAG status to red. |  | No
B68 | 80 | Razorbill is a component of the seabird assemblage feature of Farne Islands SPA. However, whilst the other auk species trigger an LSE in the breeding season, razorbill does not. This component of the assemblage should be screened in, or clarification should be provided regarding why razorbill (as a component of the seabird assemblage) has not triggered LSE. |  | The Applicant will provide clarification as to why razorbill from the Farne Islands SPA was not screened into assessment. RR-029-APDX:B-80 |  | The Applicant's document G2.11, Razorbill Assessment Alone and In-combination Farne Islands SPA, submitted at Deadline 2, is currently based on modelled abundance estimates for the Hornsea 4 project area that may be subject to revision. Natural England request that an updated version of the report is submitted alongside the revised Displacement Assessment for auks (including both sitting and flying birds) at Deadline 5. Should the impacts remain the same following revision, based on the predited impacts of less than 1 bird in the non-breeding season under Natural England's worst case scenario, we consider than an an AEoI could be ruled out for razorbill (as an unnamed component of the Farne Islands SPA seabird assemblage) and the seabird assemblage of the Farne Islands SPA arising from the operation and maintenance phase from Hornsea Four alone or in-combination. | [5 empty] | We request the Applicant confirms that the predicted levels of impact remain the same using the design-based abundance estimates. If so, based on the predited impacts of less than 1 bird in the non-breeding season under Natural England's worst case scenario, we consider than an AEoI could be ruled out for razorbill (as an unnamed component of the Farne Islands SPA seabird assemblage) and the seabird assemblage of the Farne Islands SPA arising from the operation and maintenance phase from Hornsea Four alone or in-combination. Once this is confimed we will consider this issue addressed. |  | No change |  | We request the Applicant confirms that the predicted levels of impact remain the same using the design-based abundance estimates. If so, based on the predited impacts of less than 1 bird in the non-breeding season under Natural England's worst case scenario, we consider than an AEoI could be ruled out for razorbill (as an unnamed component of the Farne Islands SPA seabird assemblage) and the seabird assemblage of the Farne Islands SPA arising from the operation and maintenance phase from Hornsea Four alone or in-combination. Once this is confimed we will consider this issue addressed. |  | No
B69 | 82 | It is unclear in this section what seasonal definitions have been employed for the assessment for gannet and kittiwake. However, based on the Applicant’s comments during consultation and the lack of consideration of the ‘full’ breeding seasons throughout the ES, it is concluded that the seasons for these two species revolve around the migration-free breeding periods presented by Furness (2015) and therefore do no follow NE advice. |  | The Applicant states outputs following Natural England advice were provided in APP-177, however we do not consider it is very clear in the report. This is likely to be further clarified in future submissions. RR-029-APDX:B-82 |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | The Applicant has used our advice and provided assessment based on our seasonal definitions under the Natural England approach in Ornithology EIA and HRA Annex (tracked) [G5.2]. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No change |  | The Applicant has used our advice and provided assessment based on our seasonal definitions under the Natural England approach in Ornithology EIA and HRA Annex (tracked) [G5.2]. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No
B70 | 93 | NE considers that the Applicant needs to provide further evidence to support their position of 25% of guillemot being from colonies other than FFC SPA. NE recognise that the Applicant has considered a case where 100% of birds are attributable to FFC SPA for the NE worst-case scenario, but we do not agree with other aspects of the ‘NE approach’ which have not been agreed with the Applicant. |  | Natural England do not agree with the Applicant's approach but acknowledge that values have been provided which mostly follow NE advice. RR-029-APDX:B-93 | [7 empty] | The Applicant has adopted our most recent advice on apportioning guillemot and razorbill under the Natural England approach in Ornithology EIA and HRA Annex (tracked) [G5.2]. We note that the Applicant has provided further context around potential connectivity to other colonies during the post-breeding (razorbill) or chick rearing/moult (guillemot) periods. However, Natural England maintain that, given the available evidence and proximity of the project to FFC SPA, the precautionary approach is to assume a larger proportion of birds are connected with that colony. In our additional advice on the bespoke assessment of guillemot and razorbill (provided to the Applicant 27th May 2022 and to Examination at Deadline 5), we have acknowledged that some birds may come from other colonies but have suggested a value of 90% of birds being connected to FFC SPA is more appropriate at this time of year. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. On the basis that there is a significant difference between the Applicant's figures and those derived using Natural England's advice, we have increased the RAG status to red. |  | No change |  | The Applicant has adopted our most recent advice on apportioning guillemot and razorbill under the Natural England approach in Ornithology EIA and HRA Annex (tracked) [G5.2]. We note that the Applicant has provided further context around potential connectivity to other colonies during the post-breeding (razorbill) or chick rearing/moult (guillemot) periods. However, Natural England maintain that, given the available evidence and proximity of the project to FFC SPA, the precautionary approach is to assume a larger proportion of birds are connected with that colony. In our additional advice on the bespoke assessment of guillemot and razorbill (provided to the Applicant 27th May 2022 and to Examination at Deadline 5), we have acknowledged that some birds may come from other colonies but have suggested a value of 90% of birds being connected to FFC SPA is more appropriate at this time of year. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. On the basis that there is a significant difference between the Applicant's figures and those derived using Natural England's advice, we have increased the RAG status to red. |  | No
B71 | 97 | NE require further evidence to be able to rule out the potential importance of both the Flamborough Front and wider prey availability issues in the immediate vicinity of the project on the success of birds at FFC SPA. |  | Natural England does not consider the most important areas being excluded to be sufficient justification for not considering the importance of the remaining Hornsea 4 array area. RR-029-APDX:B-97 and RR-029-APDX:B-92 |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | The Applicant has provided further information on this in the form of their Indirect Effects of Forage Fish and Ornithology [G5.7] submission. We do not consider the evidence provided is sufficient to rule out the importance of the Flamborogh Front and prey resources in the vicinity of the project. We consider that indirect effects, resulting in changes to ecosystem functioning, remain a significant risk associated with the project. Such effects could have a negative or postive impact on prey abundance and distibutions with associated impacts on seabirds and other top predators. This could affect condition and survival of individuals and could offset or compound other impact pathways for seabirds (i.e. displacement and collision risk). See also response to B19 and B59. Natural England will be providing a response to Applicant’s response to Natural England’s additional guidance on apportioning of seabirds to FFC SPA for Hornsea Project Four [G5.34] at Deadline 6. |  | No change |  | The Applicant has provided further information on this in the form of their Indirect Effects of Forage Fish and Ornithology [G5.7] submission. We do not consider the evidence provided is sufficient to rule out the importance of the Flamborogh Front and prey resources in the vicinity of the project. We consider that indirect effects, resulting in changes to ecosystem functioning, remain a significant risk associated with the project. Such effects could have a negative or postive impact on prey abundance and distibutions with associated impacts on seabirds and other top predators. This could affect condition and survival of individuals and could offset or compound other impact pathways for seabirds (i.e. displacement and collision risk). See also response to B19 and B59. Natural England will be providing a response to Applicant’s response to Natural England’s additional guidance on apportioning of seabirds to FFC SPA for Hornsea Project Four [G5.34] at Deadline 6. |  | No
B72 | 100 | It is unclear what breeding season is being assessed throughout but based on evidence elsewhere we assume that it is the non-migratory breeding season for which the results are reported rather than the ‘full’ breeding season. We request that results for both approaches are presented. Further, we note that the Applicant did submit age data for gannet previously, but this has now been removed without justification. |  | No change. Natural England maintains it's position. RR-029-APDX:B-100, RR-029-APDX:B-82 and RR-029-APDX:B-44. |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | The Applicant has adopted our advice and provided assessment based on our seasonal definitions under the Natural England approach in Ornithology EIA and HRA Annex (tracked) [G5.2]. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No change |  | The Applicant has adopted our advice and provided assessment based on our seasonal definitions under the Natural England approach in Ornithology EIA and HRA Annex (tracked) [G5.2]. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No
B73 | 101121 | NE do not agree that sabbaticals should be considered during apportioning of impacts to SPAs. We acknowledge that the Applicant has taken this into consideration for the NE approach to apportioning, however we do not agree with the adult apportioning rate applied on our behalf and consider that site-specific data should be used instead. Further, NE note that in a previous draft iteration of the document, the Applicant had provided site-specific information on the adult apportioning for gannet which suggested a much higher rate than that currently considered. Ageing data for gannet from relevant surveys should be used instead of the generalised stable age-structure throughout the apportioning. |  | Further documents will be submitted at Deadline 2 and 3. RR-029-APDX:B-101 and RR-029-APDX:B-91 . |  |  |  | No change. |  | We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. Further advice was provided by NE to the Applicant on 27th May 2022 to feed into these assessments. We have also submitted this advice into the Examination at Deadline 5. |  | The Applicant has used our advice and provided assessment excluding removal a sabbatical fraction and including our additional advice on apportioning of adults (provided to the Applicant on 27th May 2022 and submitted to Examination at Deadline 5) under the Natural England approach in Ornithology EIA and HRA Annex (tracked) [G5.2]. We note that the Applicant has revised our advised ageing data for gannet and kittiwake based on a more extensive dataset but we do not agree with the use of all months to derive an adult, or adult-type, proportion during the breeding season. Natural England have recalculated these proportions based on our defined breeding seasons and will consider these values when forming our position for these species. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No change |  | The Applicant has used our advice and provided assessment excluding removal a sabbatical fraction and including our additional advice on apportioning of adults (provided to the Applicant on 27th May 2022 and submitted to Examination at Deadline 5) under the Natural England approach in Ornithology EIA and HRA Annex (tracked) [G5.2]. We note that the Applicant has revised our advised ageing data for gannet and kittiwake based on a more extensive dataset but we do not agree with the use of all months to derive an adult, or adult-type, proportion during the breeding season. Natural England have recalculated these proportions based on our defined breeding seasons and will consider these values when forming our position for these species. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No
B74 | 102 | NE note that this suggests that barrier effects are only considered for operations and maintenance (O&M) whilst 10.4.4.377 suggests construction is considered. Further, NE note that barrier effects have only been considered for guillemot, razorbill and puffin – not for gannet, which are also assessed for displacement, or kittiwake. This is at odds with the EIA assessment which only examined barrier effects in relation to fulmar, gannet and kittiwake. NE notes that barrier effects could begin during construction, in line with displacement, and should therefore be considered. Include consideration of barrier effects for gannet and kittiwake or provide justification for how they have been screened out. |  | Natural England will confirm our position on this at Deadline 3. RR-029-APDX:B-102 |  | No change. Further information is due to be submitted at Deadline 5. | [5 empty] | Natural England note that the response of the Applicant to this issue in our relevant reps (RR-029-APDX:B-M) was that they had taken an appropriate and proportionate approach to scoping/screening of barrier effects. Whilst it is desirable that barrier effects receive a fuller assessment, we note the complications associated with quantifying impacts relating to barrier effects. Moreover, during the assessment of displacements, where birds on the water and in flight are considered, it is assumed that barrier effects are factored in to the potential impacts. In relation to kittiwake, not currently subject to displacement assessment in England, it remains difficult to quantify the impacts from barrier effects and how they may could ultimately impact a population through sub-lethal effects. We consider that barrier effects have been encompased in the relevant components of the updated assessment for key species and that, whilst the potential for barrier effects acting upon kittiwake cannot be ruled out, this will not make a material difference to our position. |  |  |  | Natural England note that the response of the Applicant to this issue in our relevant reps (RR-029-APDX:B-M) was that they had taken an appropriate and proportionate approach to scoping/screening of barrier effects. Whilst it is desirable that barrier effects receive a fuller assessment, we note the complications associated with quantifying impacts relating to barrier effects. Moreover, during the assessment of displacements, where birds on the water and in flight are considered, it is assumed that barrier effects are factored in to the potential impacts. In relation to kittiwake, not currently subject to displacement assessment in England, it remains difficult to quantify the impacts from barrier effects and how they may could ultimately impact a population through sub-lethal effects. We consider that barrier effects have been encompased in the relevant components of the updated assessment for key species and that, whilst the potential for barrier effects acting upon kittiwake cannot be ruled out, this will not make a material difference to our position. |  | Yes
B75 | 103 | NE agree that all relevant offshore wind farm projects have been considered for the in-combination assessment. However, we note that the range of predicted Hornsea 4 impacts are not considered in the assessments. Natural England request that the minimum and maximum in-combination predicted impacts (based on the central values for other projects and the range for Hornsea 4) are provided to allow consideration of uncertainty around estimates and confidence placed in conclusions. |  | No change. RR-029-APDX:B-103 |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | Natural England understands that the Applicant is only considering a single value in relation to in-combination assessments. However, we will base our conclusions on the range of values made available by the Applicant based on the Natural England Approach (e.g. for displacement the range of displacement and mortality rates advised by us). In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No change |  | Natural England understands that the Applicant is only considering a single value in relation to in-combination assessments. However, we will base our conclusions on the range of values made available by the Applicant based on the Natural England Approach (e.g. for displacement the range of displacement and mortality rates advised by us). In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No
B76 | 104 | NE consider than an in-combination assessment for red-throated diver and common scoter should be undertaken despite the alone assessment concluding the potential for no material contribution to baseline mortality. If the predicted impacts do not exceed 1% baseline mortality thresholds within the displacement mortality range considered by NE for the species, then they do not need to be considered further. |  | Further documents will be submitted at Deadline 2. RR-029-APDX:B-104 and RR-029-APDX:B-81 |  | The Applicant's document G2.13, Assessment of Common Scoter and Red-Throated Diver within the ECC, submitted at Deadline 2, reiterates their reasons for not providing an in-combination assessment for red-throated diver and common scoter as being project level impacts are trivial and inconsequential (<1 bird) and will not contribute to in-combination totals even at 100% displacement and 10% mortality. The Applicant also provides further information requested by NE prior to the DCO submission on the overlap of the Export Cable Corridor 2 km buffer overlap with the Greater Wash SPA. This suggested a maximum overlap of 0.4% of the entire SPA under the worst-case scenario and this was considered to not represent a significant threat to the distribution of the qualifying features within the site, due to the limited spatial and temporal nature of the potential distrubance. Natural England consider that this potential level of impact is unlikely to have a significant effect on the distribution of these species. Natural England agree that an AEOI from displacement due to cable laying vessels movements and activities in the ECC from Hornsea 4 alone or in-combination can be ruled out for the red-throated diver and common scoter features of the Greater Wash SPA. | [9 empty] | The Applicant's document G2.13, Assessment of Common Scoter and Red-Throated Diver within the ECC, submitted at Deadline 2, reiterates their reasons for not providing an in-combination assessment for red-throated diver and common scoter as being project level impacts are trivial and inconsequential (<1 bird) and will not contribute to in-combination totals even at 100% displacement and 10% mortality. The Applicant also provides further information requested by NE prior to the DCO submission on the overlap of the Export Cable Corridor 2 km buffer overlap with the Greater Wash SPA. This suggested a maximum overlap of 0.4% of the entire SPA under the worst-case scenario and this was considered to not represent a significant threat to the distribution of the qualifying features within the site, due to the limited spatial and temporal nature of the potential distrubance. Natural England consider that this potential level of impact is unlikely to have a significant effect on the distribution of these species. Natural England agree that an AEOI from displacement due to cable laying vessels movements and activities in the ECC from Hornsea 4 alone or in-combination can be ruled out for the red-throated diver and common scoter features of the Greater Wash SPA. |  | Yes
B77 | 107 | NE notes that only the Applicant’s ‘evidence-led’ approach to apportioning is applied to the NE range of displacement and mortality rates. This does not represent our advice for the assessment, and we note that NE disagree with the weighted approach to apportioning guillemot to FFC SPA. Furthermore, NE do not support the use of the stable age structure method for estimating adult proportions or the exclusion of sabbaticals (see Point 91). |  | No change. RR-029-APDX:B-107 |  | No change. |  | No change. |  | Natural England have provided further advice to the Applicant on the apportioning of auks on 27th May 2022. We have also submitted this advice into the Examination at Deadline 5. |  | The Applicant has adopted our updated advice and provided assessment under the Natural England approach in Ornithology EIA and HRA Annex (tracked) [G5.2]. The Applicant continues to defend their position in relation to displacement and apportioning of impacts to FFC SPA. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No change |  | The Applicant has adopted our updated advice and provided assessment under the Natural England approach in Ornithology EIA and HRA Annex (tracked) [G5.2]. The Applicant continues to defend their position in relation to displacement and apportioning of impacts to FFC SPA. In summary, we disagree with the Applicant's approach but are satisfied that they have provided sufficient information for us to be able to provide advice to the ExA regarding the potential impacts. Therefore, Natural England do not require any further action from the Applicant. |  | No
B78 | 109 | The estimates of the percentage of baseline mortality discussed in the text for puffin in-combination impacts at FFC appear to be incorrect in several places. These estimates need to be reviewed. |  | No change. RR-029-APDX:B-109 |  | No change. |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | Natural England agree the values presented by the Applicant in Ornithology EIA and HRA Annex (tracked) [G5.2]. |  |  |  | Natural England agree the values presented by the Applicant in Ornithology EIA and HRA Annex (tracked) [G5.2]. |  | Yes
B79 | 106,108,109,111 | NE note that some of the totals in Tables 4, 48, 52 and 56 appear to have small summing errors (presumably rounding related). |  | The Applicant has confirmed that the values are rounded. RR-029-APDX:B-106 | [11 empty] | The Applicant has confirmed that the values are rounded. RR-029-APDX:B-106 |  | Yes
B80 | 112 | NE cannot recreate the estimate of 1.11% baseline natural mortality given an impact of 289 birds relative to a baseline mortality of 15,048 for kittiwake. We have 1.92%. The calculations should be checked throughout this section. |  | The Applicant has confirmed confirm that the total number of collisions used in the calculation should be 227 and not 289. The Applicant intends to review all in-combination values, including those for Hornsea Four, included within the assessment and should any revisions be required then these will be considered and re-submitted to the ExA at the earliest point during the examination (currently anticipated to be Deadline 3). RR-029-APDX:B-112 |  |  |  | No change. |  | No change. We note that updated ornithological assessments are due to be submitted at Deadlines 5 and 6. |  | Natural England agree the values presented by the Applicant in Ornithology EIA and HRA Annex (tracked) [G5.2]. |  |  |  | Natural England agree the values presented by the Applicant in Ornithology EIA and HRA Annex (tracked) [G5.2]. |  | Yes
B82 | [11 empty] | NE have advised the Applicant of our disagreement with their method for adjusting the breeding season BDMPS values through the inclusion of a non-breeding season derived fraction of overseas birds. We note that this issue will have been carried throught the Applicant's assessments of change in baseline mortality rates and PVA for kittiwake, guillemot and puffin. We have requested that the Applicant reverts to our advised values in lieu of better evidence. |  | No change |  | NE have advised the Applicant of our disagreement with their method for adjusting the breeding season BDMPS values through the inclusion of a non-breeding season derived fraction of overseas birds. We note that this issue will have been carried throught the Applicant's assessments of change in baseline mortality rates and PVA for kittiwake, guillemot and puffin. We have requested that the Applicant reverts to our advised values in lieu of better evidence. |  | No
B83 | [11 empty] | Natural England note that the Applicant has introduced impact estimates from Rampion 2 (PEIR) to the cumulative an in-combination assessments. We agree the inclusion of these numbers as indicative of the potential impacts but note that there is uncertainty in any unconsented impact estimates which may limit our ability to draw robust conclusions regarding significant adverse impacts or AEoI when including these projects. |  | No change |  | Natural England note that the Applicant has introduced impact estimates from Rampion 2 (PEIR) to the cumulative an in-combination assessments. We agree the inclusion of these numbers as indicative of the potential impacts but note that there is uncertainty in any unconsented impact estimates which may limit our ability to draw robust conclusions regarding significant adverse impacts or AEoI when including these projects. |  | No
B84 | [11 empty] | We note that the Applicant has applied their breeding season apportioning to puffin in the NE approach presented in Table 105 of Ornithology EIA and HRA Annex (tracked) [G5.2]. Natural England will consider the correctly apportioned values when forming our postion on the impacts of the project. |  | No change |  | We note that the Applicant has applied their breeding season apportioning to puffin in the NE approach presented in Table 105 of Ornithology EIA and HRA Annex (tracked) [G5.2]. Natural England will consider the correctly apportioned values when forming our postion on the impacts of the project. |  | No
B85 | [11 empty] | We welcome that, following consultation with NE, the Applicant has included consideration of macro-avoidance on gannet collision estimates. However, we note that they have not applied corrections to cumulative or in-combination totals. Natural England will take this correction into consideration when forming our position in relation to gannet for EIA and HRA. |  | No change |  | We welcome that, following consultation with NE, the Applicant has included consideration of macro-avoidance on gannet collision estimates. However, we note that they have not applied corrections to cumulative or in-combination totals. Natural England will take this correction into consideration when forming our position in relation to gannet for EIA and HRA. |  | No
B86 | [11 empty] | We note that the values supplied in Table 6 of Indirect Effects of Forage Fish and Ornithology [G5.7] for Doggerbank Zone and Hornsea Zone are identical. Could the Applicant please check this. |  | No change |  | We note that the values supplied in Table 6 of Indirect Effects of Forage Fish and Ornithology [G5.7] for Doggerbank Zone and Hornsea Zone are identical. Could the Applicant please check this. |  | No

## C - Compensation
Point | [RR - 029] Appendix C point number | Taken from Natural England’s Relevant and Written Representations Hornsea 4 Appendix C - Derogations case | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Risk Status Deadline 2 | Consultation, actions, progression | RAG Risk Status Deadline 3 | Consultation, actions, progression | RAG Risk Status Deadline 4 | Consultation, actions, progression | RAG Risk Status Deadline 5 | Consultation, actions, progression | RAG Risk Status Deadline 6 | Consultation, actions, progression | RAG Risk Status Deadline 7 | Consultation, actions, progression | RAG Risk Status Deadline 8 | Issue Resolved
Offshore artificical nest structures Documents reviewed: A4.6.1: Compensation Project Description, B2.7 FFC SPA: Gannet and kittiwake compensation plan, B2.7.1 Compensation measures for FFC SPA Offshore Artifical Nesting Ecological Evidence, B2.7.2 Compensation measures for FFC SPA: Offshore Artifical Nesting Roadmap, 2.7.5: Compensation measures for FFC SPA: Artificial Nesting: Site Selection and Design |  |  |  | Documents reviewed: F3.4 Statement of Common Ground between Hornsea Project Four and Natural England: Derogation Matters Revision: 02 [REP1-036]; G1.9 Applicant’s comments on Relevant Representations Revision: 01 [REP1-038]; Attended workshops with Applicant on 3rd and 14th February 2022. Draft documents provided in support: APEM (2021), Calculation Methods of Hornsea Four’s Proposed Compensation Measures for Features of the FFC SPA. APEM Scientific Report P00007416. Orsted, Issued November 2021; Hornsea Four Offshore Artificial Nesting New Structure Site Selection Methodology 2nd Memo. |  | Documents reviewed: B2.7.2 Volume B2, Annex 7.2: Compensation measures for Flamborough and Filey Coast (FFC) Special Protection Area (SPA): Kittiwake Offshore Artificial Nesting Roadmap (Tracked) Revision 02; G1.50 Compensation measures for Flamborough and Filey Coast (FFC) Special Protection Area (SPA): Derogation and Compensation Update Position Statement Revision: 01 |  |  |  | No documents related to compensation were submitted at Deadline 4 |  | Documents reviewed: B2.7 Flamborough and Filey Coast (FFC) Special Protection Area (SPA): Kittiwake Compensation Plan (Tracked) - Revision: 02; B2.7.2 Volume B2, Annex 7.2: Compensation measures for Flamborough and Filey Coast (FFC) Special Protection Area (SPA): Kittiwake Offshore Artificial Nesting Roadmap (Tracked) - Revision 04; B2.7.4 Compensation measures for Flamborough and Filey Coast (FFC) Special Protection Area (SPA): Kittiwake Onshore Artificial Nesting Roadmap (Tracked) - Revision: 04; B2.7.6 Compensation measures for Flamborough and Filey Coast (FFC) Special Protection Area (SPA) Overview (Tracked) - Revision 02; B2.7.6 Outline Kittiwake Compensation Implementation and Monitoring Plan (Tracked) - Revision 02 |  | No new infomation was provided at Deadline 6 in relation to compensation, therefore none of these issues have moved forward. |  | Document's reviewed: G7.2 Applicant’s comments on other submissions received at Deadline 6 - Revision: 01
C1 | 1,12,38 | The timescale for implementation of the compensatory measure is very short, allowing only 1 or 2 breeding seasons for structure colonisation prior to wind farm operation. We do not believe there is sufficient evidence to support this approach, noting that our advice on Hornsea 3 and Norfolk Boreas was that 3 to 5 years would be necessary, and this was accepted by the SoS. A fully evidenced justification needs to be provided to demonstrate that the required colony size/growth is achievable prior to wind farm operation for the reduced lead in time and/or an adaptive management plan to account for mortality debt needs to be presented. |  | Natural England welcome the increase lead in time to three breeding seasons prior to operation, however as kittiwake do not breed until they are 4+ years old breeding recruits will not enter the biogeographic population until that point. Justification is needed on the deviation from 4 breeding seasons consented for Hornsea Project Three, Norfolk Boreas and Norfolk Vanguard, demonstrating that the required colony size/growth is achievable prior to wind farm operation for the reduced lead in time. (OffN7; RR-029-APDX:C-1; RR-029-APDX:C-12) |  | No change. |  | No change. |  |  |  | No change. |  |  |  | Natural England welcome the increase lead in time to three breeding seasons prior to operation, however as kittiwake do not breed until they are 4+ years old breeding recruits will not enter the biogeographic population until that point. Justification is needed on the deviation from 4 breeding seasons consented for Hornsea Project Three, Norfolk Boreas and Norfolk Vanguard, demonstrating that the required colony size/growth is achievable prior to wind farm operation for the reduced lead in time. (OffN7; RR-029-APDX:C-1; RR-029-APDX:C-12) |  | No
C2 | 2,3,36 | The Applicant is aiming to maintain the coherence of the SPA network by recruiting kittiwake to the wider East Atlantic population rather than the FFC SPA population. However, the calculations for kittiwake needed relate only to the apportioned impact on breeding birds from FFC SPA. Natural England emphasises that the SPA network comprises of sites rather than a wider population, and notes that FFC is the only English site with kittiwake as a qualifying feature in its own right. It is NE’s view that this would increase the scale of compensation required, as to be confident of maintaining the number of breeding adults recruited to the FFC SPA population would require a larger number to be recruited to the wider East Atlantic population. The proportion of birds produced that are (all other things being equal) likely to be recruited into the FFC SPA from the wider East Atlantic population therefore needs to be factored into the calculations. The same considerations will also need to be given to the auk compensatory measures if evidence becomes available to calculate delivery levels, as these also do not aim to compensate at the site of impact. |  | We acknowledge the Applicant's response (RR-029-APDX:C-2) that it is not possible to quantify the proportion of new young produced by the structure(s) that will recruit to FFC SPA. However, we maintain that compensating to the wider population using a 1:2 ratio for the impact apportioned to FFC SPA may not be sufficient. Further discussion is needed on this matter. |  | No change. |  | No change. |  |  |  | No change. |  |  |  | We acknowledge the Applicant's response (RR-029-APDX:C-2) that it is not possible to quantify the proportion of new young produced by the structure(s) that will recruit to FFC SPA. However, we maintain that compensating to the wider population using a 1:2 ratio for the impact apportioned to FFC SPA may not be sufficient. See our final position provided at Deadline 7 for further consideration of this matter. |  | No
C3 | 10 | Natural England consider the provision of a single structure to be a high-risk approach, both in terms of initial failure and ongoing resilience over the lifetime of the project (~35 years). The risk of relying on a single structure is compounded by the proposed lead-in time of two full breeding seasons to achieve colonisation for new structures, and only one full breeding season for repurposed structures. We do not consider that it is currently possible to commit to a fixed number of structures that it will be necessary to provide, however we strongly advise that one will be insufficient. We advise that a commitment should therefore be made to provide more than one structure in more than one location, with the final number dependent on the scale of compensation required. |  | Whilst the lead in time has been increased, it is not currently possible to confirm whether a single structure is sufficient whilst the impact levels are unclear. The extent to which the measure accounts for the benefits accruing principally to the wider kittiwake population rather than the impacted site must also be considered (see point 2). However, we consider it unlikely that a single structure would be sufficient due to uncertainties with the measure. We are further concerned that the provision of a single structure does not build in resilience over the lifetime of the project. (OffN4; RR-029-APDX:C-10). |  | No change. |  | No change. |  |  |  | No change. |  |  |  | We acknowledge that the number of nest spaces being provided is broadly acceptable, but we remain concerned about the long-term resilience of single structure provision. |  | No
C4 | 13, 45 | The area of highest ecological opportunity that has been identified does not appear to have been defined, strictly, by the heatmapping process. Rather, an area of potentially better ecological opportunity has been disregarded for unconvincing reasons. It is not clear in B2.7.5 how has the black line boundary delineating the 140km x 70km area of highest ecological opportunity been defined. Figure 2 suggests that the most promising area (dark green squares) is to the immediate NW of Hornsea 4, however this has been ruled out for two reasons: 1. The position of the area in relation to the Hornsea 4 windfarm and FFC SPA (i.e., birds may have to transit through the windfarm) 2. Very few birds were shown to be nesting on platforms in this area With respect to point 1, we assume it is being suggested that Hornsea 4 would lie within the predicted flight path of foraging birds from an ANS in the dark green area. We note that potential transits through windfarms are presumably also a possible issue for an ANS sited within the black line boundary. Regarding the lack of breeding kittiwakes detected in the area, we note that there appear to be far fewer structures than within the black line boundary, thus reducing the chance that a structure suitable for colonisation is currently present. We recommend that further evidence gathering and analysis is required to confirm the suitability of structures (e.g., presence of suitable ledges, lack of deterrents or disturbance, etc) for breeding kittiwake before using this to discount the area. The presence of multiple pre-existing kittiwake colonies within the black line boundary (Figure 3) highlights the problem of proving additionality (i.e., it might be expected that a purpose-built structure could simply redistribute kittiwake to a more optimal structure, and this will not necessarily result in any overall increase in productivity). Clarity is needed on the selection criteria for the black line boundary and the discounting of the area that appears to be ‘most suitable’ according to the heat mapping exercise. |  | New structures Natural England agree that the search areas for new structures appear appropriate. We retain some concerns, however, that the large area of highest ecological suitability identified to the north of the array area has been dropped from consideration due to a lack of kittiwakes currently nesting on (surveyed) structures in the region (OffN8). We do not consider that this should necessarily be a barrier to the placement of a new structure. Repurposed structures The final location remains undetermined, however a comprehensive spatial mapping exercise considering agreed search criteria has been undertaken and revealed areas of high suitability. If existing colonies (i.e. decommissioned structures) are being maintained additionality must be carefully considered, as should possible consolidation of small colonies across numerous existing structures onto a new structure that may prove to be more attractive to nesting birds. Maintaining a colony with no productivity increase or relocating existing breeding birds would not deliver compensation. |  | No change. |  | No change. |  |  |  | No change. |  |  |  | New structures Natural England agree that the search areas for new structures appear appropriate. We retain some concerns, however, that the large area of highest ecological suitability identified to the north of the array area has been dropped from consideration due to a lack of kittiwakes currently nesting on (surveyed) structures in the region (OffN8). We do not consider that this should necessarily be a barrier to the placement of a new structure. Repurposed structures A comprehensive spatial mapping exercise considering agreed search criteria has been undertaken and revealed areas of high suitability. A structure for repurposing has been identified, however it is not yet secured and is located within the NNSSR SAC. Further discussion will be needed on the implications of the measure for the designated site. If existing colonies (i.e. decommissioned structures) are being maintained additionality must be carefully considered, as should possible consolidation of small colonies across numerous existing structures onto a new structure that may prove to be more attractive to nesting birds. Maintaining a colony with no productivity increase or relocating existing breeding birds would not deliver compensation. |  | No
C5 | 30 | Determining the reasons for existing structures being colonised versus not colonised may be key to ensuring the success or failure of the measure, and also improving our understanding of the extent to which offshore nest site availability is currently a limiting factor to kittiwake. We welcome the acknowledgement of this in Section 3.3.2 but are concerned that the Applicant has concluded that further investigations are beyond the scope and timescales of the project (3.3.2.2). We would welcome further discussion with the Applicant on this matter as it is not clear if all avenues of investigation detailed by the Applicant have been ruled out. |  | Natural England welcomes that the Applicant has been gathering additional evidence on this matter with an aim to submit futher information into examination as soon as possible. We also welcome that further suvey work is planned for Summer 2022. RR-029-APDX:C-30. |  | No change. |  | No change. |  |  |  | No change. |  |  |  | As nest availability has not been proven to be a limiting factor, new colonies will need to have increased productivity to deliver additionality. To account for this, monitoring efforts will need to be wider in scope than just the artificial structure, and the current understanding of existing offshore colonies and their productivity will need to be built on prior to implementation of the measure to fully evidence the additional benefit of a new or repurposed structure. |  | No
C6 | 32,33 | We note that Northern gannet have not maintained colonies at artificial structures. Evidence from Australasian gannet is encouraging but there may be unknown site- and species-specific factors. We consider that there is insufficient evidence to suggest that the creation of an artificial colony for Northern gannet would prove successful. |  | No change. |  | No change. |  | No change. |  |  |  | Documents relating to Northern gannet have not been reviewed for Deadline 6.
C7 | 35 | The analysis presented in ‘B2.7.1.1 Population modelling of black-legged kittiwake on the English east coast to identify the population of first-time breeders available to recruit to new colonies' is welcomed, but the limitations described therein must be fully acknowledged. We consider there to be limited evidence on the pool of available recruits in the relevant metapopulation and consider the analysis presented in this report to be speculative and uncertain. If nest limitation cannot be demonstrated, it will be essential to predict and subsequently to prove that ‘additional’ productivity compared to extant colonies has been achieved when assessing metrics of success for this measure. |  | No change. |  | No change. |  | No change. |  |  |  | No change. |  |  |  | As nest availability has not been proven to be a limiting factor, new colonies will need to have increased productivity to deliver additionality. To account for this, monitoring efforts will need to be wider in scope than just the artificial structure, and the current understanding of existing offshore colonies and their productivity will need to be built on prior to implementation of the measure to fully evidence the additional benefit of a new or repurposed structure. |  | No
C8 | 37,40 | We note the Applicant’s preference for a repurposed structure (with an exisiting colony due for decommissioning) and agree that repurposing an offshore structure or structures has some clear benefits over a new installation. However, it is important to consider the various possibilities in the context of compensation. If a structure currently holds a kittiwake colony and is scheduled for decommissioning, then it must be considered likely that those birds would be displaced to breed at another location rather than being lost from the breeding population altogether. This will particularly be the case if it cannot be determined why existing uncolonised offshore structures are uncolonised (i.e. that nest availability is a limiting factor, see Points 30&35). It is therefore difficult to envisage direct compensation being delivered simply by retaining a structure/colony: this is more akin to ‘avoided habitat loss’. However, if a repurposed structure could be significantly improved e.g. through installation of additional nesting ledges, leading to colony growth and/or increased productivity compared to the baseline, this could clearly be quantified and defined as compensation. This would require a robust population baseline for the colony using the existing structure(s). Further discussion and/or evidence is needed on the merits of a novel versus repurposed structure. |  | We welcome that a repurposed structure would be enhanced to offer improved nesting habitat but do not consider this point to have been fully addressed in RR-029-APDX:C-37. |  | No change. |  | No change. |  |  |  | No change. |  |  |  | We welcome that a repurposed structure would be enhanced to offer improved nesting habitat but do not consider this point to have been fully addressed in RR-029-APDX:C-37. |  | No
C9 | 39 | We note that a 5km buffer between the ANS and offshore wind farms has been proposed. We would welcome further discussion on the most appropriate buffer to use, and how the collision risk for the ANS would be affected by this. |  | No change. |  | No change. |  | No change. |  |  |  | No change. |  |  |  | We note that a 5km buffer between the ANS and offshore wind farms has been proposed. We would welcome further discussion on the most appropriate buffer to use, and how the collision risk for the ANS would be affected by this. |  | No
[12 empty] | We note that the preferred offshore structure to repurpose as an ANS has been identified (Wenlock platform). The structure is within the North Norfolk Sandbanks and Saturn Reef SAC, which is designated for features that are currently in unfavourable condition and have restore conservation objectives. We would welcome further assessment by the Applicant on the implications of the proposals for the site. |  |  |  | We note that the preferred offshore structure to repurpose as an ANS has been identified (Wenlock platform). The structure is within the North Norfolk Sandbanks and Saturn Reef SAC, which is designated for features that are currently in unfavourable condition and have restore conservation objectives. We would welcome further assessment by the Applicant on the implications of the proposals for the site. |  | No
Onshore artificial nest structures Documents reviewed: B2.7.3: Compensation measures for FFC SPA: Onshore Artifical Nesting: Ecological Evidence, B2.7.4: Compensation measures for FFC SPA: Onshore Artificial Nesting Roadmap | [5 empty] | Documents reviewed: B2.7.4 Volume B2, Annex 7.4: Compensation measures for Flamborough and Filey Coast (FFC) Special Protection Area (SPA): Kittiwake Onshore Artificial Nesting Roadmap (Tracked) Revision: 02; G1.50 Compensation measures for Flamborough and Filey Coast (FFC) Special Protection Area (SPA): Derogation and Compensation Update Position Statement Revision: 01
C10 | Summary table: Retention of onshore ANS as a backup, 11, 41,44 | Natural England is not persuaded that further onshore artificial nesting structures are likely to result in sufficient benefits to produce compensation, given the number and location of such structures already proposed by submitted OWF projects. Natural England cannot be confident that there is a sufficient pool of nest-limited kittiwake recruits, suitable locations and/or prey availability available to meet and sustain the existing high demand for this measure. We consider that further demand beyond that already submitted to BEIS could have a detrimental effect on the delivery of other compensation schemes of this nature. Further, our experience of the land identification and acquisition process for Hornsea 3 (which is still ongoing) suggests that suitable sites are rare. We strongly advise that the Applicant makes a clear commitment to the provision of offshore ANS for kittiwake. Furthermore, NE would not have confidence in a single structure onshore being adequate to provide compensation as the sole measure for kittiwake, not least because four structures were deemed necessary to provide appropriate resilience for HOW3. We are also concerned about the increasing concentration of developers attempting to compensate in the Lowestoft area. |  | The Applicant is retaining onshore ANS as a back up option in case it is deemed necessary by the Secretary of State. NE notes that if it is being retained as a measure in its own right rather than as a future adaptive management measure for offshore ANS, it must be considered in terms of its suitability as the sole measure of compensation for kittiwake. In this case, NE's concerns outlined in our Relevant Representation [RR-029], the SoCG [REP1-036; OnN1-OnN12] and our response to ExQ HRA.1.42 on this measure remain unchanged. Briefly, there is a lack of evidence to suggest that nest availability will continue to be a significant limiting factor onshore/coastal following the compensatory proposals already mandated, or that there are suitable locations and/or prey availability available to meet and sustain the existing high demand for this measure in onshore locations. It is improbable that evidence to address this could be provided during the timeframe of examination. We are not familiar with the strategic work to develop onshore site selection and design the Applicant refers to in RR-029-APDX:C-11 and would welcome further information on it. |  | No change. | [5 empty] | Natural England’s position on the provision of further onshore artificial nesting as a compensatory measure remains unchanged. We have no further comment to make. |  |  |  | Natural England’s position on the provision of further onshore artificial nesting as a compensatory measure remains unchanged. We have no further comment to make. |  | No
C11 | 43 | We note that at present there is no clear commitment to a timeframe for implementation and/or delivery of the compensation measure in relation to the operation of the windfarm. Clarity is needed on the Applicant’s intended timescale for implementation and delivery of the compensatory measures. An agreed timescale is essential to help determine the overall likelihood of success and ensure that uncertainty is accounted for by allowing time for adaptive management within reasonable timescales. |  | See Point 1. |  | No change. | [5 empty] | Natural England’s position on the provision of further onshore artificial nesting as a compensatory measure remains unchanged. We have no further comment to make. |  |  |  | Natural England’s position on the provision of further onshore artificial nesting as a compensatory measure remains unchanged. We have no further comment to make. |  | No
Auk Compensation Package Documents reviewed: B2.8 FFC SPA: Gannet, guillemot and razorbill compensation plan | [5 empty] | Documents reviewed: B2.8.2 Volume B2, Annex 8.2: Compensation measures for Flamborough and Filey Coast (FFC) Special Protection Area (SPA): Guillemot and Razorbill Bycatch Reduction: Roadmap (Tracked) Revision: 02; B2.8.4 Volume B2, Annex 8.4: Compensation measures for Flamborough and Filey Coast (FFC) Special Protection Area (SPA): Predator Eradication: Roadmap (Tracked) Revision: 03; G1.33 Predator eradication island suitability assessment: Bailiwick of Guernsey Revision: 1.1; G1.50 Compensation measures for Flamborough and Filey Coast (FFC) Special Protection Area (SPA): Derogation and Compensation Update Position Statement Revision: 01 | [5 empty] | Documents reviewed: B2.8 Flamborough and Filey Coast (FFC) Special Protection Area (SPA): Guillemot and Razorbill Compensation Plan (Tracked) - Revision: 02; B2.8.2 Compensation measures for Flamborough and Filey Coast (FFC) Special Protection Area (SPA): Guillemot and Razorbill Bycatch Reduction: Roadmap (Tracked) Revision: 04; B2.8.4 Compensation measures for Flamborough and Filey Coast (FFC) Special Protection Area (SPA): Predator Eradication: Roadmap (Tracked) Revision: 04; B2.8.7 Outline Gannet, Guillemot and Razorbill Compensation Implementation and Monitoring Plan (Tracked) - Revision 02; G1.33 Predator Eradication Island Suitability Assessment: Bailiwick of Guernsey (Tracked) Revision: 02; G5.13 Bycatch Reduction Technology Selection Phase Summary - Revision: 01; G5.4 Predator Eradication Implementation Study Update - Revision: 01
C12 | 47,49,52 | We disagree with the statement: “All compensation measures are feasible and can be secured while providing flexibility and scalability.” Whilst each measure is theoretically feasible, each has a critical uncertainty that could render the measure undeliverable. There is currently no proven method for reducing bycatch for the target species and it is not guaranteed that a suitable location for predator eradication will be identified. Until these uncertainties are resolved it will not be possible to determine what scale of compensation is achievable. |  | Natural England welcomes the preliminary progress made on these measures presented at Workshops in February. We will provide further comment when additional documentation is submitted at Deadline 5. RR-029-APDX:C-47 |  | No change. | [5 empty] | See comments under predator eradication and bycatch reduction headings below. |  |  |  | See comments under predator eradication and bycatch reduction headings below. |  | No
C13 | 48 | Natural England is concerned that measures might not be implemented until just one year prior to operation of any wind turbine generator. If compensation measures are implemented this close to operation it is highly likely that impact will occur prior to the measure delivering, resulting in the accumulation of mortality debt. This is exacerbated by the fact that displacement impacts may also occur for auks during the construction phase. Timelines for implementation should take full consideration of the uncertainty in the proposed measures and the risks to timely delivery of compensation. We note that eradication might take longer than the 2 years allocated and eradication is also not the measure of success. The compensation will not be delivering until the required number of chicks are being produced and have reached age of first breeding (i.e. recruited into the breeding population). We do not consider implementation before impact to be analogous to delivering compensation before impact. |  | Natural England agrees that bycatch reduction could be implemented on a shorter timescale prior to impacts occuring. Natural England remains concerned with the lead in time allocated for predator eradication. We highlight that it can take 5-6 years for razorbill and guillemot respectively to reach age of first breeding, and that the compensation will not be delivering until new adult birds are entering the population. We welcome the suggestion that the measures for guillemot and razorbill could be adjusted between the packages to ensure compensation is delivered, and consider that this should be reflected in adaptive management/monitoring proposals. |  | No change. |  | No change. |  |  |  | Natural England remain concerned by the proposed timeline for implementation of compensatory measures in relation to the windfarm becoming operational. Predator eradication is to be initiated 2 years prior to operation, and bycatch reduction just 1 year prior. As previously noted, the predator eradication measure must account for the lag in delivering adult birds into the breeding population. The high level of difficulty in eradicating mammalian predators should also be considered, it is highly uncertain that eradication will be achieved within the proposed timeframe. If the intention is to account for this by increasing the provision of bycatch reduction until the predator eradication is proven to be successful (in terms of additional auk productivity) it should be confirmed that the bycatch reduction measure can be successfully scaled accordingly. |  |  |  | Natural England remain concerned by the proposed timeline for implementation of compensatory measures in relation to the windfarm becoming operational. Predator eradication is to be initiated 2 years prior to operation, and bycatch reduction just 1 year prior. As previously noted, the predator eradication measure must account for the lag in delivering adult birds into the breeding population. The high level of difficulty in eradicating mammalian predators should also be considered, it is highly uncertain that eradication will be achieved within the proposed timeframe. If the intention is to account for this by increasing the provision of bycatch reduction until the predator eradication is proven to be successful (in terms of additional auk productivity) it should be confirmed that the bycatch reduction measure can be successfully scaled accordingly. |  | No
C14 | 49 | Natural England welcomes that a package of measures for auks has been developed, however we are concerned that it is suggested that only one measure might be progressed and that “The Applicant is confident that each of the measures on their own is robust and deliverable”. Whilst both measures have theoretical merit, there remains significant uncertainty in terms of their deliverability and quantifiable benefits and based on the evidence available at this time, Natural England do not have confidence that either measure would be able to deliver compensation individually. We therefore consider that the Applicant should commit to progressing both of the main compensatory measures for auks. |  | Natural England welcomes the commitment from the Project to deliver both the predator eradication and bycatch measures as a package. (PE3; RR-029-APDX:C-CC; RR-029-APDX:C-49) We consider this should be secured in the draft DCO to enable this matter to be closed out. |  | No change. |  | No change. |  |  |  | NE welcomes that the implementation of both predator eradication and bycatch reduction is secured in the draft DCO. Please see Tab I for our outstanding concerns regarding compensation DCO conditions. |  |  |  | NE welcomes that the implementation of both predator eradication and bycatch reduction is secured in the draft DCO. The Applicant has also amended the DCO wording to include approval by the Secretary of State in consultation with the H4 OOEG should a change be made to deliver strategic compensation instead. The wording 'at the sole discretion of the undertaker' has also been removed. |  | Yes
C15 | 51 | We welcome that all measures will be progressed through feasibility (2022-2023) and early phase implementation (2024-2025; noting that we would usually expect feasibility to have been determined pre-submission) but are concerned that this will be “prior to a project decision on the required compensation option(s) to be taken forward to development (2025+)”. We do not consider it appropriate for the Project to decide post-consent which compensation measures to take forward as this would risk compensation delivery not being fully secured within the DCO. It is our view that a commitment to deliver the package of measures should be secured within the DCO, with a requirement for the Applicant to submit further evidence to SoS should they wish to only pursue one measure (i.e. via a license variation or non-material change). As a minimum we would expect this to be a decision requiring the agreement of the established steering group. |  | Natural England welcomes the commitment from the Project to deliver both the predator eradication and bycatch measures as a package (PE3; RR-029-APDX:C-51). We consider this should be secured in the draft DCO to enable this matter to be closed out. |  | No change. |  | No change. |  |  |  | NE welcomes that the implementation of both predator eradication and bycatch reduction is secured in the draft DCO. However, a new condition has been added to the draft DCO indicating that a change from delivering project-level to strategic consultation could be made 'at the sole discretion of the undertaker'. Again, we would expect this to be a decision requiring the agreement of the established steering group and approval by SoS. See also point I36. |  |  |  | NE welcomes that the implementation of both predator eradication and bycatch reduction is secured in the draft DCO. The Applicant has also amended the DCO wording to include approval by the Secretary of State in consultation with the H4 OOEG should a change be made to deliver strategic compensation instead. The wording 'at the sole discretion of the undertaker' has also been removed. |  | Yes
C16 | 55,58 | The same metrics of success cannot be applied to predator eradication and the bycatch reduction method. Bycatch reduction can quantifiably reduce the mortality of adult birds, and thereby directly compensate for annual losses. It should be noted that it would still be necessary to apply a ratio (multiplier) to the predicted impact to account for uncertainty. The colonisation of a site, or improved productivity of an existing site due to predator eradication, can also deliver adult guillemots to the breeding population. However, this must be calculated from the observed productivity of the colony. A number of factors must be considered (productivity, recruitment, survival rates, philopatry, etc), and quantifying the (estimated) required colony size for this measure is more closely aligned with the provision of artificial nesting sites (ANS) for kittiwake. The presence of a colony of 70 breeding adults will not necessarily compensate for the estimated mortality of 35 birds per year. In order to calculate the colony size that will be required to compensate for the loss of 35 breeding adult guillemot similar calculations will be required as for the provision of kittiwakes from ANS. |  | Due to concerns with the baseline characterisation, it is not currently possible to agree impact levels and therefore compensation levels. The extent to which the measure accounts for the benefits accruing principally to the wider auk populations rather than the impacted site must also be considered. However, we agree with the calculation methodology provided by the Applicant in document G1.41 Calculation Methods of Hornsea Four’s Proposed Compensation Measures for Features of the FFC SPA. |  | No change. | [5 empty] | No change. |  |  |  | The potential scale and extent of the measures remain uncertain. However, we agree with the calculation methodology provided by the Applicant in document G1.41 Calculation Methods of Hornsea Four’s Proposed Compensation Measures for Features of the FFC SPA. |  | No
C17 | 59 | The project impact includes displacement from the operational phase only. The Applicant has assessed displacement during the construction period as occurring at 50% of the level expected during operation. The total predicted impacts from displacement need to be considered in the implementation timeline. |  | NE will comment at Deadline 3. |  | Natural England are satisfied that the applicant understands the requirement to compensate for the total displacement impact, i.e., including displacement occuring in the construction phase and decommisioning phase as well as that arising from the operation of the wind farm (RR-029-APDX:C-59) | [9 empty] | Natural England are satisfied that the applicant understands the requirement to compensate for the total displacement impact, i.e., including displacement occuring in the construction phase and decommisioning phase as well as that arising from the operation of the wind farm (RR-029-APDX:C-59) |  | Yes
[12 empty] | We note the emerging evidence for auks breeding on offshore structures (B2.7.2, Figure 2). Given the uncertainties relating to both measures within the proposed auk compensation package it may be worthwhile considering the provision of specifically designed habitat for auks on an offshore ANS, alongside kittwake. These species tend to breed in mixed colonies at natural sites. It seems likely that it is the kittiwakes ability to build a nest structure that has enabled their colonisation of a range of structures. Auks do not build nests, and are therefore more restricted in their site selection for egg laying. However, if structures were designed with the requirements of auks in mind (ledge slope, depth, orientation, provision of 'crevices' for razorbill etc.) it is possible that a mixed seabird colony could be established at the ANS. |  |  |  | We note the emerging evidence for auks breeding on offshore structures (B2.7.2, Figure 2). Given the uncertainties relating to both measures within the proposed auk compensation package it may be worthwhile considering the provision of specifically designed habitat for auks on an offshore ANS, alongside kittwake. These species tend to breed in mixed colonies at natural sites. It seems likely that it is the kittiwakes ability to build a nest structure that has enabled their colonisation of a range of structures. Auks do not build nests, and are therefore more restricted in their site selection for egg laying. However, if structures were designed with the requirements of auks in mind (ledge slope, depth, orientation, provision of 'crevices' for razorbill etc.) it is possible that a mixed seabird colony could be established at the ANS.
Predator eradication Documents reviewed: B2.8 FFC SPA: Gannet, guillemot and razorbill compensation plan, B2.8.3: Compensation measures for FFC SPA: Predator Eradication: Ecological Evidence, B2.8.4: Compensation measures for FFC SPA: Predator eradication: Roadmap | [5 empty] | Documents reviewed: B2.8.4 Volume B2, Annex 8.4: Compensation measures for Flamborough and Filey Coast (FFC) Special Protection Area (SPA): Predator Eradication: Roadmap (Tracked) Revision: 03; G1.33 Predator eradication island suitability assessment: Bailiwick of Guernsey Revision: 1.1; G1.50 Compensation measures for Flamborough and Filey Coast (FFC) Special Protection Area (SPA): Derogation and Compensation Update Position Statement Revision: 01 |  | Documents reviewed: G3.4.1 Compensation measures for FFC SPA: Ecological Connectivity of Compensation Measures Annex 1 - Revision: 01; G3.17 Applicant's comments on Natural England's Comments received at Deadline 2 - Revision: 01 [REP-046] |  |  |  | Documents reviewed: G1.33 Predator Eradication Island Suitability Assessment: Bailiwick of Guernsey (Tracked) Revision: 02; G5.4 Predator Eradication Implementation Study Update - Revision: 01; G5.35 Predator eradication and control opportunities within the Bailiwick of Guernsey - Revision: 02
C18 | 50,54,56,88,90 | Natural England considers predator control much less likely to be successful than predator eradication, as the main target species of the measure (guillemot) usually nests on inaccessible ledges. We consider that either further evidence needs to be provided supporting the use of predator control as a viable method for the target species, or sites where predator eradication is not possible should be removed from the shortlist. |  | Natural England welcomes that following the refinement of the short list, areas where only ‘control’ is an option are no longer being further considered (PE11; RR-029-APDX:C-50). | [13 empty] | Yes
C19 | 57 | If the shortlisted sites prove unsuitable following ground-truthing and feasibility assessment, we consider it highly unlikely that sites previously longlisted but disregarded will offer any further opportunities for predator eradication. There is therefore a risk that a suitable site will not be identified making the compensation undeliverable. |  | Preliminary evidence seen by Natural England indicates that potentially feasible sites have been identified. The results of the process will be needed to confirm suitability (PE9). According to REP1-065 these will be submitted at Deadline 5. We will provide formal comments on REP1-061 (G1.33 Predator eradication island suitability assessment: Bailiwick of Guernsey Revision: 1.1) at Deadline 3. |  | Natural England have reviewed REP1-061 (G1.33 Predator eradication island suitability assessment: Bailiwick of Guernsey Revision: 1.1) and welcome the further refinement of identified sites for predator eradication. Natural England agree that although subject to a number of limitations and assumptions, the methods presented therein would allow at least a comparative assessment of nesting potential between sites, and an estimate of a sites breeding population potential to inform calculations on the required scale of the measure. We note that colonisation potential could also be influenced by factors such as prey availability that will be difficult to account for. However, we must reinforce our significant concern that specific sites have not yet been identified. Full feasibility studies are required to identify sites and ensure they meet a range of established criteria, set out in the Manual of the UK Rodent Eradication Best Practice Toolkit (2018), as acknowledged by the applicant in REP1-061. It is not clear if this will be achievable within the examination period, and if it is not, the measure can not be considered to be secured. Natural England are in broad agreement with the conclusions presented by the RSPB in REP2-093, particularly the assertion that, "the results of any detailed feasibility study and associated implementation plans must be presented to the examination for scrutiny by the Examining Authority and interested parties as soon as practicable". Until this information has been gathered and submitted Natural England can not have any confidence in the ability of the Applicant to initiate a predator eradication scheme that will adequately compensate for any predicted impacts on razorbill or guillemot. Furthermore, there remains a significant risk that feasibility studies fail to identify a suitable site. | [5 empty] | Natural England welcome the updates on further work that has been undertaken by the Applicant to refine site selection and evidence the suitability of those sites for predator eradication. We note that work is ongoing, and should deliver a final report in autumn to "aid the final decision of location" for the predator eradication measure. We remain concerned that a fully justified location may not be identified within the examination period. We note that there are now three documents relating to the implementation of predator eradication at the Baliwick of Guernsey. Effective review of the measure across a number of technical documents is becoming increasingly difficult. It is suggested that the information presented could be refined into a single document allowing a clearer understanding of the relative merits of the locations proposed and an outline strategy setting out where eradication/control is being proposed. |  |  |  | Natural England welcome the updates on further work that has been undertaken by the Applicant to refine site selection and evidence the suitability of those sites for predator eradication. We note that work is ongoing, and should deliver a final report in autumn to "aid the final decision of location" for the predator eradication measure. We remain concerned that a fully justified location may not be identified within the examination period. We note that there are now three documents relating to the implementation of predator eradication at the Baliwick of Guernsey. Effective review of the measure across a number of technical documents is becoming increasingly difficult. It is suggested that the information presented could be refined into a single document allowing a clearer understanding of the relative merits of the locations proposed and an outline strategy setting out where eradication/control is being proposed. |  | No
C20 | 84 | We consider it an oversimplification to define brown rat as the main predator of razorbill and guillemot in the UK, as many populations are not exposed to brown rat predation. The predation of auks by rats should be put into context with pressure from other predators. |  | Natural England welcomes that evidence on the abundance and species of predators present at potential sites is being collected (RR-029-APDX:C-84). | [11 empty] | Natural England welcomes that evidence on the abundance and species of predators present at potential sites is being collected (RR-029-APDX:C-84). |  | No
C21 | 85 | We note that following successful eradication, if biosecurity measures fail and re-invasion occurs, ongoing predator control will not seek to eradicate the predator population. It is concerning that this strategy does not take account of ongoing monitoring. A reduced population of predators could still prevent nesting auks, or significantly reduce their population and/or productivity. In this case, simply controlling the predator population may not be sufficient to deliver the compensatory requirement. Adaptive management should take account of ongoing monitoring, and (potential) steps taken following re-invasion should include complete eradication if required to deliver the compensatory measure. |  | We note the Applicants response that monitoring for reinfestation will be ongoing during the operational phase of the Project, but remain concerned that biosecurity measures will involve predator control rather than re-eradication (RR-029-APDX:C-85). |  | No change |  | C21-85 of the Applicant's response to the Risk and Issues Log [REP-046] states: "If a re-invasion was to occur, the Applicant would undertake a further eradication programme to remove the target invasive species from the location. To be clear, the Applicant does not intend to control invasive predators, rather eradicate them and maintain the successful eradication status." Natural England welcome this clarification and request that the associated Predator Eradication Roadmap and/or Compensation Plan is updated to reflect this, at which point we will consider this concern addressed. |  |  |  | Natural England note the Applicant's commitment to undertaking further eradication in the case of re-invasion in Document B2.8.4 and consider this matter closed. |  |  |  | Natural England note the Applicant's commitment to undertaking further eradication in the case of re-invasion in Document B2.8.4 and consider this matter closed. |  | Yes
C22 | 86 | It is our understanding that a major non-native predator eradication project at Rathlin Island has already received funding. Therefore, this location will not be available and should be removed from the potential locations. |  | We welcome that Raithlin Island has been removed from the shortlist (PE8; RR-029-APDX:C-86). | [11 empty] | We welcome that Raithlin Island has been removed from the shortlist (PE8; RR-029-APDX:C-86). |  | Yes
C23 | 91 | There is some discrepancy across the documentation. It is suggested here that a suite of measures will be implemented, while in the bycatch documents it is also proposed that one method or another might prove sufficient in isolation. We note that again it is suggested that the suite of measures could provide compensation at a ratio of 1:2 but there is no quantification of the likely benefit of any compensatory measure (alone or cumulatively) to support this statement. We reiterate our view that committing to a suite of measures will be essential to provide confidence that compensation for auks can be delivered. The efficacy and deliverability of the proposed compensatory methods remains highly uncertain. We accept that the measures will interact in terms of delivery, which might allow some flexibility of required outputs. |  | The Applicant has committed to progress both measures as a package which is welcomed. We understand that this is on the basis of each measure delivering at a 1:1 level, providing 2:1 compensation overall. As detailed in Point 16, we do not consider that it is currently possible to quantify either the level of compensation required or deliverable, which will be needed to determine if this approach is appropriate. Resolving this will require the baseline data issues to be addressed, and the results of the predator eradication and bycatch reduction feasibility studies to be provided (expected at Deadline 5). | [11 empty] | The Applicant has committed to progress both measures as a package which is welcomed. We understand that this is on the basis of each measure delivering at a 1:1 level, providing 2:1 compensation overall. Natural England have concerns about each measure's ability to deliver this. We do not consider that it is currently possible to quantify the level of compensation deliverable, which will be needed to determine if this approach is appropriate. |  | No
C24 | 92 | It is not clear what “precautionary assessment” is referred to that informed the decision to undertake predator eradication at 1-3 locations. We are not aware of any quantification of potential benefits arising for the target species as a result of any proposed compensatory measure. Please clarify the assessment that is referred to in the text. |  | Whilst Natural England agrees with the calculation approach for predator eradication detailed in REP1-063, we maintain that due to outstanding uncertainies with the measure and baseline data, the amount of compensation deliverable is not currently possible to quantify. This will be reviewed at Deadline 5 when the results of the feasibility study are submitted (RR-029-APDX:C-92). Formal comment on REP1-061 will be provided at Deadline 3. |  | Natural England have reviewed REP1-061 (G1.33 Predator eradication island suitability assessment: Bailiwick of Guernsey Revision: 1.1). As acknowledged in that document, any asssessment of potential nest sites and breeding population potential at a site following predator eradication will be subject to numerous limitations and assumptions. Any colonisation potential, or increase of an existing population or its productivity remains highly speculative. We suggest that it may prove useful to ground truth the nest site identification process detailed in REP1-061 to give a greater level of confidence in its utility. This could be readily achieved by applying it to discrete areas within existing colonies (photographed occupied, and unoccupied, preferably in winter with minimal guano staining). We maintain that due to outstanding uncertainies with the measure and baseline data, the amount of compensation deliverable is not currently possible to quantify. This will be reviewed at Deadline 5 when the results of the feasibility study are submitted (RR-029-APDX:C-92). | [5 empty] | Natural England acknowledge the significant amount of work undertaken by the Applicant to date to identify potential sites to implement predator eradication. Table 6 in document G5.13 appears to summarise much of this work. It is suggested that this table should clarify how many of the potential (currently unutilised) nest sites identified on islands with rats present would be accesible to those rats. Guillemot tend to breed on inaccesible ledges and thus are generally less susceptible to mammalian predators. Although the Applicant has demonstrated that guillemots are present in areas that rats can access, it will be important to consider the degree of overlap between potential guillemot and rat habitat. Crucially, if un-utilised guillemot habitat is identified at candidate sites that is not accessible to mammalian predators it is logical to assume that some other factor is the cause of non-occupancy. We note that sites for predator eradication have not be finalised at this point, so we can not advise further. |  |  |  | Natural England acknowledge the significant amount of work undertaken by the Applicant to date to identify potential sites to implement predator eradication. Table 6 in document G5.13 appears to summarise much of this work. It is suggested that this table should clarify how many of the potential (currently unutilised) nest sites identified on islands with rats present would be accesible to those rats. Guillemot tend to breed on inaccesible ledges and thus are generally less susceptible to mammalian predators. Although the Applicant has demonstrated that guillemots are present in areas that rats can access, it will be important to consider the degree of overlap between potential guillemot and rat habitat. Crucially, if un-utilised guillemot habitat is identified at candidate sites that is not accessible to mammalian predators it is logical to assume that some other factor is the cause of non-occupancy. We note that sites for predator eradication have not be finalised at this point, so we can not advise further. |  | No
C25 | 93 | We note that the Letters of Comfort from the Alderney Wildlife Trust and Agriculture, Countryside and Land Management Services indicates that the States of Guernsey and Alderney are committed to Ramsar management plans which include mammal eradication. This raises the question of whether the Applicant can offer any additionality at these locations. The Applicant would need to show that their proposals are above and beyond the management plans, and/or that the current management planswould not be implemented without their input. We further note that these areas lie outside UK law which could present complications. We also highlight that the Ramsar site falls outside the UK national site network, so the benefits here would be indirect, i.e. to the wider biogeographic populations. |  | Natural England welcomes initial clarifications provided but considers that this will likely need revisiting after the feasibility study has concluded and the final plans can be developed (RR-029-APDX:C-93). | [11 empty] | Natural England welcomes initial clarifications provided but considers that this will likely need revisiting after the feasibility study has concluded and the final plans can be developed (RR-029-APDX:C-93). |  | No
[8 empty] | Natural England have reviewed REP3-034. A clear representation is made of the evidence relating to connectivity of guillemot and razorbill from FFC SPA and the wider National Site Network, and the proposed area for delivery of compensation for those species through predator eradication. Natural England agree with the conclusion that there is likely to be some level of connectivity with the National Site Network. However, Natural England believe the evidence suggests that this level of connectivity with the National Site Network is likely to be limited, and especially with the impacted FFC SPA colony. Furthermore, the evidence relating to philopatry and dispersal is insufficient to make any inferences on scale (e.g. quantify the proportion of birds that may ultimately recruit back into the network from the compensation colony). Therefore, the challenge relating to the compensation measure is accounting for the uncertainty around the degree of connectivity by scaling the target appropriately. This has not been considered within this document, and the evidence presented has not been assessed in that context. Please also see EN010098 H4 Appendix C4-NE comments on G3.4 Compensation measures for FFC SPA Compensation Connectivity Note for detailed comments on REP-032 where this is discussed further. | [7 empty] | Natural England have reviewed REP3-034. A clear representation is made of the evidence relating to connectivity of guillemot and razorbill from FFC SPA and the wider National Site Network, and the proposed area for delivery of compensation for those species through predator eradication. Natural England agree with the conclusion that there is likely to be some level of connectivity with the National Site Network. However, Natural England believe the evidence suggests that this level of connectivity with the National Site Network is likely to be limited, and especially with the impacted FFC SPA colony. Furthermore, the evidence relating to philopatry and dispersal is insufficient to make any inferences on scale (e.g. quantify the proportion of birds that may ultimately recruit back into the network from the compensation colony). Therefore, the challenge relating to the compensation measure is accounting for the uncertainty around the degree of connectivity by scaling the target appropriately. This has not been considered within this document, and the evidence presented has not been assessed in that context. Please also see EN010098 H4 Appendix C4-NE comments on G3.4 Compensation measures for FFC SPA Compensation Connectivity Note for detailed comments on REP-032 where this is discussed further. |  | No
[12 empty] | Natural England have reviewed REP5a-019. Natural England continue to advise that predator eradication, rather than control, will be required. It is accepted that, following eradication, ongoing control may be required (as part of ongoing biosecurity measures) in those locations where natural re-incursion of rats by swimming is possible. The case study examples given show positive responses of seabirds to control. However, it must be acknowledged that in some instances these control measures refer to a wide range of predators. Further, the control measures described tend to be highly intensive, requiring ongoing monthly servicing of bait stations and traps. In all case studies, improvements in productivity of extant seabird populations are noted, although some studies highlight that control is inherently inferior to eradication. Crucially, it is not clear that controlling rats at currently unutilised habitat will be sufficient to enable breeding auks to colonise that habitat. In the absence of any evidence, it should be assumed that only predator eradication would be sufficient in this case. Nevertheless, we do acknowledge that predator control could benefit existing breeding populations of auks, if it is proven that there is nesting habitat overlap and predation pressure from rats. Ultimately, it appears inevitable that some ongoing predator control effort may be required as part of the compensatory measure. Natural England continue to advise that full eradication is likely to be required to facilitate any new or recolonisation of suitable habitat that is currently unutilised by breeding auks due to the presence of rats. |  |  |  | Natural England have reviewed REP5a-019. Natural England continue to advise that predator eradication, rather than control, will be required. It is accepted that, following eradication, ongoing control may be required (as part of ongoing biosecurity measures) in those locations where natural re-incursion of rats by swimming is possible. The case study examples given show positive responses of seabirds to control. However, it must be acknowledged that in some instances these control measures refer to a wide range of predators. Further, the control measures described tend to be highly intensive, requiring ongoing monthly servicing of bait stations and traps. In all case studies, improvements in productivity of extant seabird populations are noted, although some studies highlight that control is inherently inferior to eradication. Crucially, it is not clear that controlling rats at currently unutilised habitat will be sufficient to enable breeding auks to colonise that habitat. In the absence of any evidence, it should be assumed that only predator eradication would be sufficient in this case. Nevertheless, we do acknowledge that predator control could benefit existing breeding populations of auks, if it is proven that there is nesting habitat overlap and predation pressure from rats. Ultimately, it appears inevitable that some ongoing predator control effort may be required as part of the compensatory measure. Natural England continue to advise that full eradication is likely to be required to facilitate any new or recolonisation of suitable habitat that is currently unutilised by breeding auks due to the presence of rats.
Bycatch reduction Documents reviewed: B2.8 FFC SPA: Gannet, guillemot and razorbill compensation plan, B2.8.1: Compensation measures for FFC SPA: Bycatch Reduction: Ecological Evidence, B2.8.2: Compensation measures for FFC SPA: Bycatch resuction: Roadmap | [5 empty] | Documents reviewed: G1.42 Compensation measures for Flamborough and Filey Coast (FFC) Special Protection Area (SPA): Gannet Bycatch Reduction: Ecological Evidence Revision: 1, B2.8.2 Volume B2, Annex 8.2: Compensation measures for Flamborough and Filey Coast (FFC) Special Protection Area (SPA): Guillemot and Razorbill Bycatch Reduction: Roadmap (Tracked) Revision: 02, G1.41 Calculation Methods of Hornsea Fours Proposed Compensation Measures for Features of the Flamborough and Filey Coast (FFC) Special Protection Area (SPA |  | Documents reviewed: G3.4.1 Compensation measures for FFC SPA: Ecological Connectivity of Compensation Measures Annex 1 - Revision: 01 |  |  |  | Documents reviewed: G5.13 Bycatch Reduction Technology Selection Phase Summary - Revision: 01 | [5 empty] | NA
C26 | Summary table: Target fishery | We agree with the current selection but note that the existing levels of bycatch will need to be fully quantified, with consideration given to interannual variation. Crucially, a bycatch reduction mechanism needs to prove effective within the identified fishery and sufficient fishers will need to implement the measure over a long-term period. |  | Natural England agree with the reasoning for the identified locations for auks. Certainty will be given if a bycatch reduction method is proved effective for fishery in that location (BR6). We acknowledge that bycatch reduction trials are ongoing and that results are pending (Deadline 5). We note that one trial might not provide sufficient evidence of effectiveness and/or scale and welcome that there is scope for an additional trial to be conducted in 2022-2023. However, we note that this will fall outside of the Examination period. |  | Natural England are concerned that the Applicant is not clearly committing to a second year of trials for the LEB (REP1-021). We consider that the LEB remains unproven in a fishery setting or for the species of concern, and its effectiveness must be proven through a robust trial. A single year (in fact, only a winter 'season') of data collection is not sufficient as interannual variation cannot be considered. Further, the raw data must be available in order for us to fully review such a trial, and we understand that only proportional reductions in bycatch will be reported. We appreciate this is a request of the fishery and recognise the sensitivity of the data in question, but therefore must highlight the lack of co-operation and transparency that this suggests, as well as the inherent risk to the perceived legitimacy of the trial results. | [5 empty] | No change. Natural England retains previously raised concerns regarding our ability to properly review the results of the bycatch reduction technology trial. A proportional reduction in bycatch is reported from vessels where the technology was deployed compared to those where it was not. We do not consider this sufficient to form a view on the likely effectiveness or scalability of the measure. |  |  |  | Natural England retains previously raised concerns regarding our ability to properly review the results of the bycatch reduction technology trial. A proportional reduction in bycatch is reported from vessels where the technology was deployed compared to those where it was not. We do not consider this sufficient to form a view on the likely effectiveness or scalability of the measure. |  | No
C27 | 46 | It is stated [in B2.8] that, “the bycatch measure can be scaled from the compensation of 70 breeding individuals to ~267 breeding individuals by increasing the number of vessels from 7-30 respectively.” While it is accepted that methods are scalable, it is not clear from this or Volume B2, Annex 8.1: Compensation measures for FFC SPA: Bycatch Reduction: Ecological Evidence how this precise calculation has been derived. We request that full details of this calculation are provided. Further, as there is no proven method of reducing bycatch of auks in gillnet fisheries, we consider that any quantification or even estimation of bycatch reduction is necessarily highly speculative. |  | Natural England are concerned that averaging bycatch rates across fishermen could result in important context being lost from the data, which could result in inaccurate bycatch rates being applied (RR-029-APDX:C-46). We highlight that RR-029-APDX:C-73 indicates that bycatch rates differ between fishers/vessels. |  | No change. See response to point C29 below. | [5 empty] | No change. Bycatch rates are not reported in document G5.13 due to confidentiality agreements with fishers. Understanding how bycatch varies across vessels is essential when considering uncertainty in delivery and scalability of the measure. It is possible that the study could identify predictive variables within the fishery that could be used to target vessels most likely to experience seabird bycatch. We note that application of reduction technology would be most effective if implemented on these vessels. |  |  |  | Bycatch rates are not reported in document G5.13 due to confidentiality agreements with fishers. Understanding how bycatch varies across vessels is essential when considering uncertainty in delivery and scalability of the measure. It is possible that the study could identify predictive variables within the fishery that could be used to target vessels most likely to experience seabird bycatch. We note that application of reduction technology would be most effective if implemented on these vessels. |  | No
C28 | 49,60 | Impact values are yet to be agreed and we are unclear how bycatch reduction has been quantified (i.e., the “maximum potential delivery threshold” reduction of 9 auks bycaught per boat with technology deployed). We do not deem this calculation to be possible due to a lack of relevant evidence, and even an estimate would be highly speculative at this time. |  | Further information to be submitted at Deadline 5. Natural England will provide formal commet on the gannet bycatch reduction evidence review [REP1-064] at Deadline 3.
C29 | 61,81 | It is unclear how (or why, at this stage) the bycatch reduction measure is proposed for implementation across “approximately 7 vessels”. Is this the number of vessels that the Applicant believes will be amenable to the project from their initial engagement with fishers? Further clarification is needed on what this approach is based on. Please provide (and reference) the “precautionary assessment” that has been undertaken to inform the decision to implement bycatch reduction on 7 vessels. |  | Natural England welcomes the clarification provided by the Applicant on this point (RR-029-APDX:C-61). As noted in point 30, Natural England has concerns regarding averaging used in the bycatch calculations, but will provide further comment when calculations are updated in due course. |  | Natural England have reviewed the calculation methods supplied in REP1-063, and are in broad agreement that they are fundamentally sound and fit for purpose. However, we do not agree that an appropriate approximation of baseline bycatch is being generated in the first step of the compensation calculation for quantifying the scale of bycatch reduction. Therefore, we would also disagree with any subsequent calculation of bycatch reduction. The method detailed relies on questionnaire responses from fishers. An average number of auks bycaught per annum has been provided from those fishers that responded. This is not species-specific, and it is not clear if fishers have compentent bird identification skills, so even assignment to this group could be erroneous. Without access to the raw data, and with no further statistics provided, we can not assess how representative the mean value is, or consider variance around it. Interannual variation has also not been accounted for, and it is unclear how many years fishers considered when providing their estimates. It is likely that bycatch varies significantly across vessels, temporally, and spatially. Applying an anecdotal, unsubstantiated average bycatch rate across a number of vessels is not an appropriate baseline to calculate a potential reduction from. A far greater understanding of the bycatch within the target fishery, including spatial and temporal variation as well as between vessels (and their individual practices, gear types, etc) will be essential before we can have any confidence in an estimate of potential reductions arising from the implementation of any bycatch reduction technology. Natural England anticipate that progress has been made by the Applicant in this respect during trials of the Looming Eye Buoy. | [5 empty] | No change. It is assumed that bycatch reduction calculations now take account of actual bycatch rates. However, this data has been gathered from a limited number of vessels over a single non-breeding season and does not account for inter-annual variation. Further, these rates are not reported by the Applicant due to confidentiality agreements with fisheres engaged on the trial. The results of the Applicant's investigations into the significance of the observed reduction in bycatch by the application of LEBs have not been reported on. Therefore, Natural England cannot currently adopt an informed position on the likely success of the bycatch reduction technology. |  |  |  | It is assumed that bycatch reduction calculations now take account of actual bycatch rates. However, this data has been gathered from a limited number of vessels over a single non-breeding season and does not account for inter-annual variation. Further, these rates are not reported by the Applicant due to confidentiality agreements with fisheres engaged on the trial. The results of the Applicant's investigations into the significance of the observed reduction in bycatch by the application of LEBs have not been reported on. Therefore, Natural England cannot currently adopt an informed position on the likely success of the bycatch reduction technology. |  | No
C30 | 62,73 | It is noted that 80% of fishers (that responded to consultation) indicated that they might be willing to take part in a pilot study for the bycatch reduction technique. However, the number of fishers that were consulted, responded to the consultation and the proportion of fishers in the fishery that they represent has not been provided. No conclusion can therefore be made on the sentiment of the fishery from the data provided. This additional information should be provided to put the fishery response into context. Furthermore, it is likely that those that responded are more likely to be amenable to this request. There is a potential bias toward, a) sympathetic fishers and b) fishers who generally experience lower rates of bycatch (possibly due to, e.g., favoured locations, gear type/set up, or fishing intensity). |  | Natural England welcomes the confirmation that 52 responses were received of which 42 were positive. However, the 81% response rate only relates to these two values, the number of fishers consulted (of which 52 responded) has not been provided (RR-029-APDX:C-62; RR-029-APDX:C-73). It would be instructive to understand what level of engagement with the survey there was to gauge the overall sentiment of the fishery and likely resilience of the measure. | [11 empty] | Natural England welcomes the confirmation that 52 responses were received of which 42 were positive. However, the 81% response rate only relates to these two values, the number of fishers consulted (of which 52 responded) has not been provided (RR-029-APDX:C-62; RR-029-APDX:C-73). It would be instructive to understand what level of engagement with the survey there was to gauge the overall sentiment of the fishery and likely resilience of the measure. |  | No
C31 | 63 | It should be noted that the measure can only be “implemented relatively quickly” if a proven method has been identified. If further trials, development, or testing of other methods are required then implementation could be seriously delayed. |  | If a successful method was identified reduction could be achieved quickly, and implementation one year prior to impacts occuring would be appropriate. However, our concerns will remain unchanged until the trial results are available. We welcome that there is scope for a second year of data gathering to be collected in 2022/2023 but note that this will be beyond the end of examination. | [11 empty] | If a successful method was identified reduction could be achieved quickly, and implementation one year prior to impacts occuring would be appropriate. However, our concerns will remain unchanged until the trial results are available. We welcome that there is scope for a second year of data gathering to be collected in 2022/2023 but note that this will be beyond the end of examination. |  | No
C32 | 64 | It will be essential that any trial of bycatch reduction techniques also quantifies levels of bycatch in the fishery. |  | We welcome that the LEB trail is being conducted with a control net employed on each vessel to allow for more precise estimates of bycatch within the target fishery (RR-029-APDX:C-64). | [11 empty] | We welcome that the LEB trail is being conducted with a control net employed on each vessel to allow for more precise estimates of bycatch within the target fishery (RR-029-APDX:C-64). |  | Yes
C33 | 66,75,77 | In previous engagement with the Applicant, Fishtek, Birdlife and RSPB on bycatch trials (28 July 2021), net illumination, net visibility and acoustic deterrents were all dismissed as unsuitable. We consider that this advice has been taken onboard by the Applicant as only the Looming Eyes Buoy (LEB) has been taken forward for trial, but we note that the other methods have been retained in all documents. We consider it unlikely that these offer a fall-back option should the LEB trial fail. |  | The Applicant has acknowledged that further research would be required for these measures to be implemented for bycatch reduction of guillemot and razorbill (RR-029-APDX:C-75) | [11 empty] | The Applicant has acknowledged that further research would be required for these measures to be implemented for bycatch reduction of guillemot and razorbill (RR-029-APDX:C-75) |  | No
C34 | 67 | To Natural England’s knowledge, the LEB has so far only been tested and found to be somewhat effective on sea duck. The trial in the Baltic Sea described by Rouxel et al (2021) focused on the response of long-tailed ducks to the LEB only as it was not conducted in a fishery. In this case a 20-30% reduction in abundance was found within 50m of the LEB. The possibility of habituation was also noted. Until a specific trial has been carried out for this method there is no convincing evidence that the LEB can reduce bycatch of guillemot or razorbill in the target fisheries. |  | We understand results of a targeted LEB trail are to be submitted at Deadline 5. | [7 empty] | We note that the Applicant now reports that a 25% reduction in bycatch of guillemots has been achieved by the application of the LEB in the target fishery. This is encouraging, but Natural England retain serious concerns relating to the reporting of the propotional reduction only, with no supporting raw data, and the fact that this trial represents a single non-breeding season and does not account for inter-annual variation. Further, document G5.13 details a statistical analysis of the data in the methods, but no results or discussion of that analysis are presented. It remains unclear if the reduction in bycatch observed can be considered significant. |  |  |  | We note that the Applicant now reports that a 25% reduction in bycatch of guillemots has been achieved by the application of the LEB in the target fishery. This is encouraging, but Natural England retain serious concerns relating to the reporting of the propotional reduction only, with no supporting raw data, and the fact that this trial represents a single non-breeding season and does not account for inter-annual variation. Further, document G5.13 details a statistical analysis of the data in the methods, but no results or discussion of that analysis are presented. It remains unclear if the reduction in bycatch observed can be considered significant. |  | No
C35 | 68,69,72 | Interviews of fishers alone is not considered a suitable approach to determine the prevalence of bycatch by region as it relies solely on anecdotal evidence. We consider the relevance and significance of the evidence has been overstated and should be verified through other data sources. |  | We welcome that the LEB trial will enable more accurate recordings of bycatch levels. We will comment further when results are presented at Deadline 5. | [7 empty] | The LEB trial has been restricted by confidentiality agreements and therefore has not delivered useful baseline data on bycatch in the target fishery for review. |  |  |  | The LEB trial has been restricted by confidentiality agreements and therefore has not delivered useful baseline data on bycatch in the target fishery for review. |  | No
C36 | 71 | We agree with the conclusion to focus bycatch reduction efforts (for auks) within the English Channel given the predicted levels of bycatch and the absence of more impactful fisheries closer to FFC SPA. However, it will be important to consider the possibility of changing the area of focus depending on the efficacy of the project, as well as potential changes in fisheries, distribution of auks and/or high risk areas. Adaptive management will also need to consider the dynamic nature of fisheries. |  | The Applicant considers the measure flexible as vessels the LEB are deployed on can change from year to year. Adaptive management will be discussed within the OOEG (RR-029-APDX:C-71). Natural England agree that a suite of measures gives increased resilience, however, we note that the compensation ratio would be reduced by half if one measure was not delivering. This would need to be accounted for by adaptive management. If bycatch reduction proves a viable method over the short term it may prove prudent to over-deliver to buffer against any future issues. | [11 empty] | The Applicant considers the measure flexible as vessels the LEB are deployed on can change from year to year. Adaptive management will be discussed within the OOEG (RR-029-APDX:C-71). Natural England agree that a suite of measures gives increased resilience, however, we note that the compensation ratio would be reduced by half if one measure was not delivering. This would need to be accounted for by adaptive management. If bycatch reduction proves a viable method over the short term it may prove prudent to over-deliver to buffer against any future issues. |  | No
C37 | 78 | It is highly unlikely that Natural England would deem compensation at a 1:1 ratio to be appropriate, given the high levels of uncertainty in the efficacy of the measure, the likely difficulties in quantifying actual bycatch reduction on an annual basis and compensation not being delivered at the site of impact. |  | The Applicant is offering compensation at a 1:2 ratio, with bycatch and predator eradication each being implemented at a 1:1 level (RR-029-APDX:C-78). Further discussion will be needed on this point. |  | No change. |  | No change. |  |  |  | No change. |  |  |  | The Applicant is offering compensation at a 1:2 ratio, with bycatch and predator eradication each being implemented at a 1:1 level (RR-029-APDX:C-78). Further discussion will be needed on this point. |  | No
C38 | 79 | It is noted that a bycatch “technology selection phase” is planned for 2021-23. However, it is our understanding that this phase is in fact the trialling of a single technique (LEB), and possibly another above-water deterrent (predator kites). If this technology is not taken forward, there is currently insufficient evidence to simply select another technology (e.g., net illumination or modification, acoustic deterrents). Therefore, another trial phase would be required. The aims, objectives, risks, and possible outcomes of the ‘selection phase’, including implications for implementation timelines, should be presented. |  | Natural England welcomes that initial results of the LEB trial are promising, and that there is scope for further testing of this and/or for an additional method to be trialled in 2022/2023 (RR-029-APDX:C-79). |  | Natural England are concerned that the Applicant is not clearly committing to a second year of trials for the LEB (REP1-021). We consider that the LEB remains unproven in a fishery setting, and its effectiveness must be proven through a robust trial. A single year (season) of data collection is not sufficient as interannual variation can not be considered. Further, the raw data must be available in order for us to fully review such a trial, and we understand that only proportional reductions in bycatch will be reported on. We appreciate this is a request of the fishery, but therefore must highlight the lack of co-operation and transparency that this suggests. We draw attention to the fact that in order to collect sufficient data, the LEB trial will not complete within the timescale of the examination. | [5 empty] | No change. |  |  |  | We consider that the LEB remains unproven in a fishery setting, and its effectiveness must be proven through a robust trial. A single year (season) of data collection is not sufficient as interannual variation can not be considered. Further, the raw data must be available in order for us to fully review such a trial, and we understand that only proportional reductions in bycatch will be reported on. We appreciate this is a request of the fishery, but therefore must highlight the lack of co-operation and transparency that this suggests. We draw attention to the fact that in order to collect sufficient data, the LEB trial will not complete within the timescale of the examination. |  | No
C39 | 80 | Early consideration of scaling up compensation is welcomed. However, at this stage it is unclear how much confidence can be placed in the suite of compensation methods proposed being able to deliver any level of compensation. Proof of concept trials are still required to prove bycatch reduction method efficacy before longer term trials can quantify the potential delivery of compensation. Furthermore, levels of impact and compensation ratios are yet to be agreed and will depend on several factors. |  | Results of the trial phase will be submitted at Deadline 5. | [11 empty] | We consider that the LEB remains unproven in a fishery setting, and its effectiveness must be proven through a robust trial. A single year (season) of data collection is not sufficient as interannual variation can not be considered. Further, the raw data must be available in order for us to fully review such a trial, and we understand that only proportional reductions in bycatch will be reported on. We appreciate this is a request of the fishery, but therefore must highlight the lack of co-operation and transparency that this suggests. We draw attention to the fact that in order to collect sufficient data, the LEB trial will not complete within the timescale of the examination. |  | No
C40 | 82 | We assume the bycatch technology selection phase (trial) will run for three years. This will generate useful data and allow for consideration of interannual variation. However, it is implied that the outcome of this trial will inform whether predator eradication will be implemented. The wording of the document elsewhere implies only that the scale of the measures will be subject to change. It has been Natural England’s understanding that a suite of measures will be taken forward and we believe that committing to the full suite of measures will be essential to ensure confidence that adequate compensation can be delivered over the lifetime of the project. |  | Natural England welcomes the commitment from the Project to deliver both the predator eradication and bycatch measures as a package. We consider running the trial for more than one year will be essential to gain a measure of interannual variation (PE3;RR-029-APDX:C-82). |  | No change. Natural England note that edits to document B2.8.2 Volume B2, Annex 8.2 (REP1-021) appear to indicate that the LEB trial may not be extended to a second year, in which case interannual variation could not be considered. It would be useful for the Applicant's intention to be clarified. | [5 empty] | The Applicant has committed to extending the LEB trial over the 2022/23 non-breeding period. Natural England welcomes this but highlights that until the results of the full trial are provided, which will be outwith the Examination, the measure will not be adequately assessed. |  |  |  | The Applicant has committed to extending the LEB trial over the 2022/23 non-breeding period. Natural England welcomes this but highlights that until the results of the full trial are provided, which will be outwith the Examination, the measure will not be adequately assessed. |  | No
[6 empty] | Gannet bycatch reduction. Natural England have reviewed REP1-064. A significant amount of useful information is presented, however, due to the provision of this document part way through examination, we will focus on our key concerns to justify Natural England's overarching position. We highlight that there is no proven method of reducing Northern gannet bycatch specifically. It will not be possible to trial a bycatch reduction method within the timescales of examination. Even if an immediate start was possible, any such trial would be unable to deliver conclusive results until 2024 at the very earliest. The level of Northern gannet bycatch in UK fisheries remains highly uncertain, and would need to be properly understood and quantified in a target fishery before any bycatch reduction could be quantified. Scottish longline fisheries are identified as being most likely to have significant levels of gannet bycatch. These fisheries are unlikely to be available to English projects hoping to deliver compensation. In summary, Natural England agree that it is likely that Northern gannet are subject to bycatch in UK fisheries, and that reducing this bycatch is theoretically possible with an existing technology (or possibly, by adapting an exisitng technology). However, Natural England do not believe that reducing the bycatch of Northen gannet is a currently viable compensatory measure. Further, we consider the process required to develop and secure the measure to be unachievable with respect to the project timelines. |  | No change.
[8 empty] | Natural England have reviewed REP3-034. A clear representation is made of the evidence relating to connectivity of guillemot and razorbill from FFC SPA and the proposed area for delivery of compensation for those species through bycatch reduction. Natural England agree with the conclusion that there is some level of connectivity, and that the measure could benefit the National Site Network and to a lesser extent, the specifically impacted populations. However, the evidence relating to connectivity is insufficient to make any inferences on scale (e.g. quantify the proportion of breeding birds from FFC SPA that might be expected to winter in the English Channel, or indeed birds from outwith the National Site Network). Therefore, the challenge relating to the compensation measure is accounting for the uncertainty around the degree of connectivity by scaling it appropriately. This has not been considered within this document. Please also see EN010098 H4 Appendix C4-NE comments on G3.4 Compensation measures for FFC SPA Compensation Connectivity Note for detailed comments on REP-032 where the question on scale is discussed further. |  |  |  | No change. |  |  |  | Natural England have reviewed REP3-034. A clear representation is made of the evidence relating to connectivity of guillemot and razorbill from FFC SPA and the proposed area for delivery of compensation for those species through bycatch reduction. Natural England agree with the conclusion that there is some level of connectivity, and that the measure could benefit the National Site Network and to a lesser extent, the specifically impacted populations. However, the evidence relating to connectivity is insufficient to make any inferences on scale (e.g. quantify the proportion of breeding birds from FFC SPA that might be expected to winter in the English Channel, or indeed birds from outwith the National Site Network). Therefore, the challenge relating to the compensation measure is accounting for the uncertainty around the degree of connectivity by scaling it appropriately. This has not been considered within this document. Please also see EN010098 H4 Appendix C4-NE comments on G3.4 Compensation measures for FFC SPA Compensation Connectivity Note for detailed comments on REP-032 where the question on scale is discussed further. |  | No
Fish habitat enhancement Document Used:
C41 | General | Natural England is of the view that fish habitat (seagrass) restoration cannot be considered compensation, as a link between seagrass restoration and the productivity of the impacted species cannot currently be demonstrated or quantified. We also consider that it cannot be treated as a back-up to account for the high levels of uncertainty in other measures. This is also due to the likely timeframes to implementation, and uncertainty regarding the level of impact on target species. Nevertheless, we welcome and support the measure being retained for resilience/ecosystem enhancement and commend the general approach being taken. As we do not consider the measure to be compensation, we have not commented on the documents further, however we would be happy to engage with the Applicant on their methods at a later stage. |  | Natural England welcomes that the Applicant aims to conduct targeted research to fill some of the evidence gaps associated with this resilience measure and that a pilot projec t is already underway. We not that further documentation is to be submitted at Deadline 6 (RR-029-APDX:C-RRR). | [7 empty] | Natural England reiterates our support of the Applicant pursuing an ecosystem enhancement resilience measure. However, as the provision of resilience measures has no legal basis under the Habitats Regulations (2017), we have focussed our efforts on reviewing the main compensation measures. |  |  |  | Natural England reiterates our support of the Applicant pursuing an ecosystem enhancement resilience measure. However, as the provision of resilience measures has no legal basis under the Habitats Regulations (2017), we have focussed our efforts on reviewing the main compensation measures.
Prey availability Documents reviewed: B2.6.2 Compensation mreasures for FFC SPA: Prey Resource Evidence | [11 empty] | Document reviewed: G5.8 Orsted's approach to strategic ecological compensation - Revision: 01
C42 | 5 | The report questions whether the science-led approach could be secured within the relevant timeframes as it is likely to take between 3-5 years to have full traction. We consider that this should be compared with the timeframe that may be required to achieve sufficient colonisation of offshore nest structures, which is likely to also be 3-5 years. |  | Further context has been provided by the Applicant on the delivery process for this research (RR-029-APDX:C-5). We consider this point resolved. | [11 empty] | Further context has been provided by the Applicant on the delivery process for this research (RR-029-APDX:C-5). We consider this point resolved. |  | Yes
C43 | 6 | We welcome the Applicant’s commitment to fund research into a science-led, ecosystem-based assessment to inform fisheries management and quota allocation, though we query whether this should be secured within the DCO. |  | RR-029-APDX:C-6: The Applicant is willing to make a legal commitment outside of the DCO to manage, fund and deliver the research projects identified. A commitment to fund research would be flexible to the route chosen by UK government to manage the fishery and would also provide valuable information in relation to understanding the status of the related species and what may change under different future climate scenarios. However, this approach suggests that there is no guarantee of this specific research happening, as it will be dependent on the Government's chosen course of action. We continue to recommend that this is secured through the DCO or relevant certified documents. |  | No change |  | No change |  |  |  | The recently published British Energy Security Strategy (BESS) commits to speeding up the deployment of offshore wind and Natural England welcome the measures proposed in the Offshore Wind Environmental Improvement Package policy paper, including strategic compensatory measures and a centralised Marine Recovery Fund (MRF) to help facilitate delivery of those measures. We acknowledge the new information and suggested commitments made by the Applicant in relation to this, however we consider it unlikely that this system will be in place in time for contributions to the MRF to be considered as an appropriately secured measure for Hornsea 4 at the point of the consent decision. In this context, anticipated use of the MRF might be best presented solely as an adaptive management measure at this time. See also I36. |  |  |  | The recently published British Energy Security Strategy (BESS) commits to speeding up the deployment of offshore wind and Natural England welcome the measures proposed in the Offshore Wind Environmental Improvement Package policy paper, including strategic compensatory measures and a centralised Marine Recovery Fund (MRF) to help facilitate delivery of those measures. We acknowledge the new information and suggested commitments made by the Applicant in relation to this, however we consider it unlikely that this system will be in place in time for contributions to the MRF to be considered as an appropriately secured measure for Hornsea 4 at the point of the consent decision. In this context, anticipated use of the MRF might be best presented solely as an adaptive management measure at this time. See also I36. |  | No
General Documents reviewed: A4.6.1 Compensation Project Description, B2.6 Compensation measures for FFC SPA: Overview | [5 empty] | Documents reviewed: G1.41 Calculation Methods of Hornsea Fours Proposed Compensation Measures for Features of the Flamborough and Filey Coast (FFC) Special Protection Area (SPA | [5 empty] | Document reviewed: B2.7.6 Compensation measures for Flamborough and Filey Coast (FFC) Special Protection Area (SPA) Overview (Tracked) - Revision 02
C44 | 3 | Due to concerns with the baseline characterisation modelling used for these species and them being based on the Applicant’s approach rather than SNCB parameters, Natural England cannot agree with the predicted impact levels presented. |  | Concerns relating to this are addressed in 'B - Ornithology'. Based on the indicated timelines for submission of additional material on this topic, impact levels for compensation are unlikely to be progressed before Deadline 5. This represents a significant risk to the examination process. | [7 empty] | As noted in B1 of the Ornithology tab, Natural England now considers the ornithology baseline agreed. Natural England will comment on the implications for compensation impacts at Deadline 7. |  |  |  | As noted in B1 of the Ornithology tab, Natural England now considers the ornithology baseline agreed. Natural England has commented on the implications for compensation impacts in our Deadline 7 compensation position.
C45 | 3 | We do not consider that it is currently possible to determine the scale of compensation required. The current evidence base is insufficient to have confidence in values presented as potential reductions remain theoretical. Irrespective of this, calculations have not been provided to support the Applicant’s values. For agreement on compensation levels to be reached, a quantified assessment of the level of compensation required to meet the predicted impact will need to be presented for each measure, demonstrating that all demographic parameters and associated uncertainties have been accounted for. It is important to highlight that the delivery requirement of any compensation measure is to provide X additional breeding adult birds per annum and not X chicks per annum. Calculations therefore need to determine how many breeding pairs and/or what increase in productivity is necessary to produce enough chicks per annum to result in X additional adult kittiwake recruiting to the East Atlantic population per annum. |  | Whilst it is still not possible to quantify compensation requirements due to outstanding baseline uncertainties and feasibility trials still being ongoing, it is possible to agree the calculation approach for when all the required data is available. Natural England will provide formal comment on G1.41 Calculation Methods of Hornsea Four’s Proposed Compensation Measures for Features of the FFC SPA [REP1-063] at Deadline 3. However, having reviewed a draft version for Workshops held on 3rd and 14th February, we provisionally agree with the calculation approach for kittiwake nest structures and predator eradication, but have some outstanding concerns regarding averaging in the bycatch reduction calculations. |  | Natural England have reviewed the calculation methods presented in REP1-063. Natural England consider the basic methodolgies presented to be sound and fit for purpose. However, we highlight the importance of reaching agreement on the data that will ultimately inform these calculations. Notably, Natural England have significant concerns regarding the quantification of a baseline level of bycatch (see our response to point C29 above). |  | No change. |  |  |  | No change. |  |  |  | Natural England have reviewed the calculation methods presented in REP1-063. Natural England consider the basic methodolgies presented to be sound and fit for purpose. However, we highlight the importance of reaching agreement on the data that will ultimately inform these calculations. Notably, Natural England have significant concerns regarding the quantification of a baseline level of bycatch (see our response to point C29 above). |  | No
C46 | 3 | We welcome that the Applicant has suggested providing compensation at greater than a 1:1 ratio, however it is not clear how or why a compensation ratio of 1:2 has been selected. As we do not think it is currently possible to determine the scale of compensation achievable with the current measures due to outstanding uncertainties, further discussion will be needed on this topic. More generally, Natural England highlights that ratios are only one way of addressing the uncertainty associated with measuring success, and considers that well-designed and located measures based on agreed targets may be a surer way to achieve success than the application of crude ratios. |  | No change. | [11 empty] | We welcome that the Applicant has suggested providing compensation at greater than a 1:1 ratio, however it is not clear how or why a compensation ratio of 1:2 has been selected. As we do not think it is currently possible to determine the scale of compensation achievable with the current measures due to outstanding uncertainties, further discussion will be needed on this topic. More generally, Natural England highlights that ratios are only one way of addressing the uncertainty associated with measuring success, and considers that well-designed and located measures based on agreed targets may be a surer way to achieve success than the application of crude ratios. |  | No

## D - Marine Mammal
Point | [RR - 029] Appendix D point number | Taken from Natural England’s Relevant and Written Representations Hornsea 4 Appendix D - Marine Mammals | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Risk Status Deadline 2 | Consultation, actions, progression | RAG Risk Status Deadline 3 | Consultation, actions, progression | RAG Risk Status Deadline 4 | Consultation, actions, progression | RAG Risk Status Deadline 5 | Consultation, actions, progression | RAG Risk Status Deadline 6 | Consultation, actions, progression | RAG Risk Status Deadline 7 | Consultation, actions, progression | RAG Risk Status Deadline 8 | Issue Resolved
Document reviewed: A2.4 Marine Mammals |  |  |  | Document reviewed: G1.9 Applicant’s comments on Relevant Representations Revision: 01 [REP1-038]; B2.2: Report to Inform Appropriate Assessment Part 1 (Tracked) Revision: 02 [REP1-011]; B2.2.C Annex C of B2.2: Report to Inform Appropriate Assessment: Integrity Matrices (Tracked) Revision: 02 [REP1-013] | [5 empty] | G4.11 Clarification Note on Marine Mammals - Revision: 01 G3.17 Applicant's comments on Natural England's Comments received at Deadline 2 - Revision: 01 |  | Documents reviewed: G5.30 Applicant’s comments on other submissions received at Deadline 5 - Revision: 01; G5.36 Clarification Note on Seismic Surveys - Revision: 01 |  | Documents reviewed: REP6-012 F2.5 Outline Marine Mammal Mitigation Protocol (Tracked) – Revision: 02 |  | Documents reviewed: F2.11 Outline Southern North Sea Special Area of Conservation Site Integrity Plan (Tracked): Revision 02 [REP7-055]; G7.2 Applicant’s comments on other submissions received at Deadline 6 - Revision: 01
D1 | 1,9 | Natural England advised the Applicant during the Evidence Plan process to consider bottlenose dolphin in the project area as part of the Coastal East Scotland (CES) management unit (MU). The Applicant proposed to use the abundance estimates for the Greater North Sea (GNS) MU from the (then unpublished) IAMMWG (2021), noting that this was going to be the first abundance estimate for this population of bottlenose dolphin. The Applicant stated that both MU populations (GNS and CES) could be included in the report if that was more acceptable. In the Environmental Statement (ES) the Applicant has presented the combined GNS MU and the CES MU populations into a single reference population. With regards to the density estimate, the Applicant has assumed uniform distribution of the GNS MU population across the area. Natural England are concerned about the reference population and the density estimate being calculated at different scales (GNS+CES MU and GNS MU alone, respectively), as if applied to certain species and/or MU populations it could lead to a significant ‘dilution’ of the impacts. It therefore may not be appropriate to apply this approach in future impact assessments. However, in this case we acknowledge that the CES MU population is small and not likely to cause any discernible ‘dilution’. We do request however that the Applicant also present the density of the CES MU population based on uniform distribution (although it would be of interest to better understand any range in densities of this MU population e.g. in any ‘hotspots’). This will allow for comparison to the density estimate derived from the GNS MU. It may also be more representative of the coastal areas where impacts may occur (e.g. from UXO clearance, see Point 3). In the absence of known bottlenose dolphin density in the area of interest, we welcome the range of densities presented by the Applicant and the approach of taking the most precautionary density estimate. |  | The Applicant has requested clarification on what we mean by "present the density of the CES MU population based on uniform distribution." Essentially, we would like the applicant to present any available density estimates that could be representative of the Coastal East Scotland (CES) MU. The Applicant has considered both the CES MU and the Greater North Sea (GNS) MU as their reference population. At present, they have only presented a density estimate that is relevant to the GNS MU. Density estimates that are relevant to the CES MU should be presented for context, and to give us assurance that impacts are not being underestimated (through the use of a lower density estimate). The uniform density estimate is one type of approach to generating a density estimate for the CES MU, but if there are other approaches and/or figures in the literature these should be included. |  | No change. |  | No change. |  | The Applicant has provided examples of density estimates for the CES MU, which are an order of magnitude higher than the GNS MU. The Applicant maintains that there is no evidence to suggest that these density estimates are comparable to the areas of bottlenose dolphin presence along the northeast English coast. Whilst we understand that there is limited evidence, we are still concerned that the GNS MU density estimate is not suitably precautionary as it doesn't account for the known increased presence of bottlenose dolphin at the coast, which have been linked to the CES MU. We would be supportive of the Applicant using a higher density estimate for the portion of habitat along the northeast English coast that meets the typical usage patterns of bottlenose dolphin in the CES MU (i.e. within 2 km, 3 km, and 25 m depth contour). We understand that this assessment would be purely illustrative, and highly conservative, but it would give an indication of the worst-case number of animals impacted should density estimates be similar to the CES MU. |  | Natural England considers that the information provided by the Applicant is sufficient to address our concerns. |  |  |  | Natural England considers that the information provided by the Applicant is sufficient to address our concerns. |  | Yes
D2 | 2 | The Applicant should present the number of individuals within the area of Permanent Threshold Shift (PTS) from piling noise based on concurrent monopiles, which is within the Maximum Design Scenario (MDS). This should refer to the areas of impact detailed in the ES Volume A4 Annex 4.5 Subsea Noise Technical Report Part 2 (Section 5.3.2). |  | As requested, the Applicant has provided a table showing the number of animals that may experience PTS-onset based on concurrent piling. In this respect they have sufficiently addressed our original comment. However, from the new data we note that for harbour porpoise the number of individuals that may experience PTS from concurrent piling (of pin piles) is 1661-1792 (dependent on density estimate used). This represents a ~5-6-fold increase in the numbers, and so percentage of the MU (~0.5% compared to ~0.1%), exposed to PTS (when compared to single event piling). For minke whales, the number of animals potentially exposed to PTS has increased from <1 (single piling) to 9 (concurrent piling). In the MMMP the Applicant is proposing to only mitigate the instantaneous PTS zone (based on SPLpeak), which is <1000m. The Applicant has not committed to mitigation for the PTS zone based on SELcum, which is much larger than the one based on SPLpeak. The distances presented for this cumulative piling scenario is based on SELcum. Although the impact distances are not presented, it can be inferred from the area of impact (~1000 km2) that the mitigation proposed by the Applicant will not mitigate the full PTS zone. Therefore we do not agree that the risk from PTS will be minimised to negligible levels. We have provided more information on this point in our response the Examiner's Questions. Consideration should be given to implementing a maximum separation distance between two concurrent piling events, which limits how far apart the concurrent piling locations can be. A maximum separation distance would help to maximise the overlap of impact zones from piling, and therefore minimise the number of individuals potentially impacted. |  | No change. |  | No change. |  | The Applicant has provided further information in support of their position to not mitigate the full SELcum PTS zone and only mitigate the SPLpeak PTS zone. NE do not agree that the information provided by the Applicant is sufficient to justify their position, and maintain that the SELcum PTS zone must be taken into account when determining appropriate mitigation measures to reduce the risk of injury. We acknowledge that there are limitations to the assumptions used in modelling of SELcum PTS, however mitigation of solely the SPLpeak distance is insufficient as it will not account for exposure to sound over time which will certainly occur and could lead to PTS onset. At present, the best and most precautionary method available for calculating PTS from cumulative exposure is using the SELcum PTS thresholds and we advise that is what assessments and mitigation should be based on. We acknowledge that there is active research into the area of cumulative PTS. As such, better methods for estimating cumulative PTS distances may become available in the near future. We consider that any such new methods can be taken into account when finalising the mitigation measures in the MMMP post-consent. We understand that the Applicant is also of this position. If so, then this agreed position should be used to inform the principles of the draft MMMP, which need to be agreed at this stage. We advise that the draft MMMP is updated to clearly set out their position and Natural England's position on the use of SELcum or SPLpeak to determine PTS distances, the areas of ongoing research on this subject, and that the final mitigation will be based on the evidence available at the time (e.g. on modified SELcum PTS distances). Similarly, the ES assessment should also be updated to reflect this change. The assessment of residual risk of PTS, which takes into account mitigation, should clearly state that mitigation of the full PTS zone will be undertaken, noting that the definition of the full PTS zone will be agreed post-consent. |  | We welcome the Applicant's agreement to commit to mitigating cumulative PTS impact ranges that have been calculated using the latest research and methods available at the time of the final MMMP. However, it is imperative that this position is included in the Outline MMMP, as this document should outline the principles upon which mitigation is based, not solely the options for mitigation measures. To illustrate, the Co110 states that "a piling Marine Mammal Mitigation Protocol (MMMP), will be developed in accordance with the Oultine MMMP" - therefore the Outline MMMP must reflect the agreed position. |  | The Applicant has updated their MMMP in line with Natural England's advice. The update has addressed our concerns and so we consider the issue resolved. |  | The Applicant has updated their MMMP in line with Natural England's advice. The update has addressed our concerns and so we consider the issue resolved. |  | Yes
xq1 | 3 | With regards to the assessment of PTS from UXO on bottlenose dolphin, Natural England’s primary concern is UXO clearance in close proximity to the coast where bottlenose dolphin primarily from the CES MU may be present. We consider that it would be beneficial for the Applicant to provide an assessment specifically on this scenario. In the assessment we advise that the Applicant should use an appropriate density estimate and compare the number of individuals in the impact zone against the CES MU population in isolation. |  | We acknowledge that the assessment of UXO impacts is illustrative only at this stage. Therefore Natural England can consider the specific issue of UXO impacts to bottlenose dolphin resolved for the purposes of the DCO. We will provide comments on the assessment of bottlenose dolphin and Coastal East Scotland MU when we are consulted on the standalone Marine Licence for UXO clearance. On the more general subject of bottlenose density, please see response to Point 1. | [11 empty] | We acknowledge that the assessment of UXO impacts is illustrative only at this stage. Therefore Natural England can consider the specific issue of UXO impacts to bottlenose dolphin resolved for the purposes of the DCO. We will provide comments on the assessment of bottlenose dolphin and Coastal East Scotland MU when we are consulted on the standalone Marine Licence for UXO clearance. On the more general subject of bottlenose density, please see response to Point 1. |  | No
D4 | 4 | The Applicant is proposing to screen out the pathway of vessel collision risk from the CEA as “it is expected that all offshore energy projects will employ a vessel management plan.” We advise that not all projects screened into the CEA are offshore energy projects and therefore they may not all have a VMP e.g. seismic projects. Therefore, further justification is needed to demonstrate the appropriateness of screening out this pathway. We recommend the Applicant provide additional rationale on screening out vessel collision risk pathway from CEA for projects without VMPs. |  | The Applicant has provided written justification on the measures other developers may have in place (in addition to VMPs) and the nature of vessel movements for other developments. Although we consider that the applicant has still only provided an assumption about other industries, it is a reasonable assumption. Therefore the information provided by the applicant is sufficient to address our concerns. | [11 empty] | The Applicant has provided written justification on the measures other developers may have in place (in addition to VMPs) and the nature of vessel movements for other developments. Although we consider that the applicant has still only provided an assumption about other industries, it is a reasonable assumption. Therefore the information provided by the applicant is sufficient to address our concerns. |  | Yes
D5 | 5 | We note that the Applicant has not considered all offshore wind farm projects where the operation and maintenance (O&M) phase overlaps with the construction of Hornsea 4. To illustrate, there are many projects which are constructing/due to complete construction between 2021 and 2024 that have not been included in the CEA. We also note that no cable and pipeline projects have been screened into the CEA. The Applicant should consider whether all project types mentioned in 4.12.6.2 have been adequately included. |  | The Applicant's response has not addressed our concerns. In the response they have provided a different definition for the projects that have been considered in the CIA - stating that it's only projects with a construction window that overlaps or is +/- 1 year from the HOW04 construction window. This differs to the definition in 4.12.6.2 of the ES: "Offshore wind farms where construction and operational and maintenance phases overlap with the construction phase of Hornsea Four." By not including operational and maintenance phases, the Applicant is not fully assessing one of the impact pathways in the CIA "The potential for disturbance from vessel activity during construction, operation and maintenance and decommissioning of developments" (Paragraph 4.12.1.11, ES). The Applicant should explain why these changes have been made and address the inconsistencies. |  | No change. |  | No change. |  | The Applicant has stated that predicted impacts during the O&M phase will be disturbance and collision risk, which is assessed as negligible from the project. They assume all other projects will have a Vessel Management Plan. Whilst our original point re inconsistency stands, we do not consider this matter is of significant concern in relation to Hornsea 4, we therefore do not intend to make any further comment on this matter unless the ExA asks us for specific advice. | [5 empty] | The Applicant has stated that predicted impacts during the O&M phase will be disturbance and collision risk, which is assessed as negligible from the project. They assume all other projects will have a Vessel Management Plan. Whilst our original point re inconsistency stands, we do not consider this matter is of significant concern in relation to Hornsea 4, we therefore do not intend to make any further comment on this matter unless the ExA asks us for specific advice. |  | No
Document reviewed: A4.4.5 Subsea Technical Report (Part 2)
D6 | 6 | We welcome the inclusion of consecutive pin piling. However, information has not been provided on how the consecutive pin piling has been modelled. In particular, Natural England would like to understand: • If any break between pin piles has been assumed • Whether consideration has been given to the potential for marine animals to return within impact ranges during breaks between plies. • If there is no break between piles and the next pin pile starts at a lower energy, whether that sound would be sufficiently loud to maintain the fleeing response in marine mammals already displaced by previous piling. Further information on how the consecutive pin pile has been modelled and the underlying assumptions in the modelling should be provided. |  | The Applicant has provided further information on how the consecutive pin piling was modelled. We consider that the information provided addresses our concerns. | [11 empty] | The Applicant has provided further information on how the consecutive pin piling was modelled. We consider that the information provided addresses our concerns. |  | Yes
D7 | 7 | We welcome the inclusion of details on the source level noise of a WTG with a direct-drive gearbox, which is more representative of the systems proposed for Hornsea 4. However, we note that the direct drive WTG had a 150m diameter rotor, which is significantly smaller than that proposed for Hornsea 4 (305m). Therefore, we still consider there to be a significant gap in knowledge of the underwater noise levels of WTGs of this size. This knowledge gap could be the target of strategic post-construction monitoring undertaken by the project . |  | The Applicant has not provided any new information in their response. Please see our response to Examiner Questions on the subject of monitoring operational WTG noise. Please also see our response to Point 30 - we note that it is our concern with the overall lack of monitoring detail included in the OMMP that has raised this from yellow to amber. |  | No change. |  | No change. |  | No change. |  | No change/response from the Applicant on this point. We request that this knowledge gap is included in the OMMP. |  | No Change |  | The Applicant has confirmed that they will not update the OMMP with the requested monitoring objectives. |  | No
Document reviewed: A5.4.1 Marine Mammal Technical Report (Part 1); B2.2: Report to Inform Appropriate Assessment Part 12: Appendix I: Marine Mammals – Bottlenose dolphin RIAA information
D8 | 8 | The Applicant has presented information on bottlenose dolphin sightings in the northeast from 2018 and 2019. Of these years, sightings were only recorded in 2019, meaning that only 1 year of sightings is presented. If available, we consider it advisable to include data from 2020, to confirm the pattern of sightings or any changes. Data can be sought from the Sea Watch Foundation on bottlenose dolphin sightings from 2020 (and 2021, if available). |  | The Applicant considers that the additional data would not have any bearing on the outcome of the assessment and have provided justification for this. In view of this additional information Natural England is minded to agree that the information presented is sufficient. | [11 empty] | The Applicant considers that the additional data would not have any bearing on the outcome of the assessment and have provided justification for this. In view of this additional information Natural England is minded to agree that the information presented is sufficient. |  | Yes
D9 | 10,35 | We note that a key assumption in this assessment of apportioning is that bottlenose dolphin along the northeast coast of England show the same coastal distribution as when the species is present alongside the Tayside and Fife coast i.e. remain within waters 20m deep and within 2-3 km from the coast. Whilst we acknowledge that this is appropriate due to the lack of information from northeast England at the time of writing, this is a knowledge gap which should be addressed to better inform future apportioning assessments. This data gap could be investigated by the Applicant through their post-consent monitoring. Any such monitoring could also contribute to a more appropriate density estimate for bottlenose dolphin in the region. We request that this is included in the Project’s Outline Marine Monitoring Plan. |  | Please see response to Point 30. |  | No change. |  | No change. |  | No change. |  | No change/response from the Applicant on this point. We request that this knowledge gap is included in the OMMP. |  | No Change |  | The Applicant has confirmed that they will not update the OMMP with the requested monitoring objectives. |  | No
Document reviewed: B2.2 Report to Inform Appropriate Assessment Part 1 | [5 empty] | G2.14 Clarification Note on UnderwaterNoise Abatement Systems - Revision: 01 |  | G3.17 Applicant's comments on Natural England's Comments received at Deadline 2 - Revision: 01 [REP3-046]
D10 | 12,23 | Further information is required to demonstrate no likely significant effect (LSE) on the harbour seal feature of The Wash and North Norfolk Coast SAC as a result of vessel collision risk. We acknowledge that the area of construction itself has low numbers of harbour seals (although it is within the foraging range of the SAC). However, collision risk can also arise whilst vessels are in transit to/from ports, where densities may be higher. Information on vessel transit routes, ports for construction and operation and maintenance and anticipated densities (baseline and project addition) along these routes should be provided to support the conclusion of low risk to harbour seals. |  | The Applicant has not provided any new information in their response. In our response to Examiner Questions on the subject of further information needed from the Applicant in order to give us confidence in the assessment, we have requested the following: -Location of ports for construction, and operation and maintenance; -Anticipated vessel transit routes; -Baseline vessel density along these routes; -Vessel density taking into account the addition of project vessels; -Seal densities along the routes and an estimate of number of individuals that may be impacted |  | No change. |  | An illustrative assessment of vessel collision risk will be provided at Deadline 5. |  | The Applicant has provided an illustrative assessment of vessel collision risk. The Applicant has presented information on the potential ports for construction and O&M, anticipated vessel transit routes between these ports and the array area, and expected seal densities along these routes. They have also confirmed measures in the Vessel Management Plan "will serve to minimise the potential for collisions from smaller, faster vessels." This has resulted in the Applicant concluding no Adverse Effect on Site Integrity on the Wash and North Norfolk Coast SAC in relation to collision effects, which we are supportive of. However, for the avoidance of doubt, our initial request was for the Applicant to demonstrate no LSE to the Wash and North Norfolk Coast in relation to collision effects. The assessment and conclusion presented by the Applicant, alongside the use of mitigation in that conclusion, confirms to us that there is the potential for LSE and so a more detailed assessment (which can take into account mitigation) was required. This should therefore be reflected in the RIAA/HRA. In addition, the assessment presented by the Applicant was illustrative because the port(s) for construction and O&M are not yet known. Once the port(s) have been identified, we advise that the assessment should be revisited to ensure that the conclusions are still valid. The need for this updated assessment prior to the discharge of the O&M plan should therefore be secured. |  | The note provided by the Applicant at Deadline 4 (G4.11) demonstrated no AEOI rather than no LSE, therefore for completeness the RIAA should be updated to reflect that LSE cannot be excluded for this pathway. Nevertheless, we agree with the conclusions of no AEoI and acknowledge that the Applicant has presented an assessment that can be utilised by the Examining Authority in its RIES and by the SoS in their HRA. The Applicant has not agreed to revisiting the assessment once the ports for construction and operation/maintenance are known. We maintain our advice that the assessment should be revisited to ensure that the conclusions are still valid. Nevertheless, we do agree that the illustrative assessment is likely to be the worst-case, that the relevant mitigation measures have been secured, and therefore the revised assessment is unlikely to have an effect on the conclusions of our assessment. |  |  |  | The note provided by the Applicant at Deadline 4 (G4.11) demonstrated no AEOI rather than no LSE, therefore for completeness the RIAA should be updated to reflect that LSE cannot be excluded for this pathway. Nevertheless, we agree with the conclusions of no AEoI and acknowledge that the Applicant has presented an assessment that can be utilised by the Examining Authority in its RIES and by the SoS in their HRA. The Applicant has not agreed to revisiting the assessment once the ports for construction and operation/maintenance are known. We maintain our advice that the assessment should be revisited to ensure that the conclusions are still valid. Nevertheless, we do agree that the illustrative assessment is likely to be the worst-case, that the relevant mitigation measures have been secured, and therefore the revised assessment is unlikely to have an effect on the conclusions of our assessment. |  | No
D11 | 13 | We note that the tiers used for the RiAA differ from those used in the cumulative environmental assessment (CEA) in the marine mammal environmental statement (MM ES) chapter. Justification should be provided as to why two different tier systems have been used, as well as a clear comparison of the two systems and any implications for the assessments. |  | As referenced in their comment, the Applicant has provided a Revision 02 of the RiAA where they provide more information on the tiering structure. The information provided partially addresses our concerns. We note that, under Tier 5 in the CEA, the applicant has included projects such as decommissioning projects, CCS projects, and “seismic surveys across various oil and gas development blocks in the North Sea.” Given that such seismic surveys have not been included in Tier 3a in the RIAA, we do not consider these tiers equivalent. The tiering structure should therefore be amended to reflect this. We also still consider that further justification on why different tiers have been used is needed. |  | No change. |  | No change. |  | The Applicant has clarified that the previous side-by-side compraison of tiers provided at Deadline 1 was incorrect. They have provided an updated side-by-side comparison, for illustrative purposes, in the response. Whilst we maintain that consistent tiering structure would have been clearer, we are content with the comparison provided (except for seismic surveys - see below). The response by the Applicant and the updated side-by-side comparison does not address our concern over the disparity between including seismic surveys in the CEA, but not in the in-combination assessment in the RIAA. Natural England has recently provided clarifcation to the Applicant over the inclusion of seismic surveys. |  | The Applicant has provided a note with an illustrative assessment of the in-combination assessment including a nominal high order UXO clearance and a nominal seismic survey. The approach taken to calculating the contribution of a nominal high order UXO clearance is as requested. We welcome the Applicant's inclusion of a nominal seismic survey in principle. However, the Applicant has not taken on board our suggestions for determining a realistic assessment scenario, as they have treated the seismic survey as a static source. Nevertheless, we agree that assessing the seismic survey as a mobile source would not change the assessment conclusions as the risk of AEoI to the Southern North Sea SAC has already been identified. However, it does further highlight the risk of significant exceedance of the thresholds should all identified projects and plans go ahead at the same time, further emphasising the need for effective mitigation of cumulative underwater noise disturbance. |  |  |  | The Applicant has provided a note with an illustrative assessment of the in-combination assessment including a nominal high order UXO clearance and a nominal seismic survey. The approach taken to calculating the contribution of a nominal high order UXO clearance is as requested. We welcome the Applicant's inclusion of a nominal seismic survey in principle. However, the Applicant has not taken on board our suggestions for determining a realistic assessment scenario, as they have treated the seismic survey as a static source. Nevertheless, we agree that assessing the seismic survey as a mobile source would not change the assessment conclusions as the risk of AEoI to the Southern North Sea SAC has already been identified. However, it does further highlight the risk of significant exceedance of the thresholds should all identified projects and plans go ahead at the same time, further emphasising the need for effective mitigation of cumulative underwater noise disturbance. |  | No
D12 | 14 | We further note that the different definitions of tiers and/or approaches between the MM ES chapter and the RiAA has led to different types of projects being scoped in/out between these two chapters. The most notable change is with respect to seismic surveys, which have been omitted from the RiAA but included in the CEA in the MM ES chapter. We highlight that this is a deviation from the approach taken by previous offshore wind projects including Hornsea 3, which is acknowledged in the text. Whilst we understand the rationale, we cannot consider that the incombination assessment presented in this RiAA is the worst-case scenario. We understand that the Applicant is proposing to capture any future seismic surveys in the SIP; however, Natural England has concerns about the current implementation of SIPs (see Relevant Representations, Paragraphs 5.30- 5.32). Because of the short lead-in times for seismic surveys, it is paramount that the SIP is not undertaken/finalised too far in advance of construction as this could mean that potentially concurrent seismic activities are not captured; this should be secured in a DCO condition. The approach taken by the Applicant relies heavily on the SIP for mitigation of adverse effect as, at this stage, the project has not committed to undertaking any mitigation measures. That the in-combination assessment does not present the worst-case scenario, yet the thresholds for significant disturbance are already exceeded, further highlights that noise abatement at source should be being considered strategically across the offshore wind industry at earlier stages than the SIP. Therefore, we cannot currently rule out an adverse effect on integrity for the SNS SAC in combination. We strongly recommend that the Applicant commit to mitigation measures at this stage, rather than at the SIP, to reduce potential impacts from the project alone. We consider the mitigation should be included to minimise impacts as far as possible on principle, with the later SIP consultation determining if they can be removed. |  | Section 8.2 does not fully address our concerns in this comment. We have provided clarification to the Applicant on the inclusion of seismic surveys in the RIAA and anticipate further information at Deadline 2 on this. We do not expect the Applicant to address our overarching concerns regarding the use of SIPs as this is a matter for the Decision Makers, however we do consider that the Applicant should address our concern regarding mitigation being committed to at this stage. We have also provided various comments about at-source mitigation in this response, that we await a response on. |  | No change. |  | The Applicant has requested an updated position from Natural England on the inclusion of seismic surveys in the RIAA, owing to concerns that the methodological options available would present unreasonable results. Natural England maintains that a nominal seismic survey should be included in the RIAA in-combination assessment to ensure that this potential avenue for impact is accounted for. Whilst the Applicant has confirmed that airgun seismic surveys will not occur, surveys using sub-bottom profilers may be required. In addition, the oil and gas industry may carry out seismic surveys in or around the area and these typically have a very short lead in time. We therefore consider it reasonable to expect there to be at least one seismic survey that overlaps with Hornsea Four, and this should be accounted for in the assessment. The Applicant has currently investigated the use of two examples of seismic survey inclusion, which we agree would provide an unreasonable prediction of impact. However, this is due to the examples selected to be extreme. We suggest the Applicant could look at the JNCC Marine Noise Registry records for the previous 12 months for an indication of average noise levels to include. Alternatively, HRAs conducted by BEIS for seismic surveys for the oil and gas industry could also provide a representative value to use. We highlight that the inclusion of a nominal seismic survey is not without precedent. The cumulative impact assessment for EA1N and EA2 included a worst case scenario of two seismic surveys (based on two locations, one in each seasonal area and maximum overlap with the seasonal area) using a distance of 10km. We do not consider it appropriate for this to only be considered in the SIP due to our previously outlined concerns. In addition, there is precedent for SIPs not being subject to Appropriate Assessment and it therefore cannot be guaranteed that an updated in-combination assessment will be performed. |  | No change. |  | The Applicant has provided a note with an illustrative assessment of the in-combination assessment including a nominal high order UXO clearance and a nominal seismic survey. The approach taken to calculating the contribution of a nominal high order UXO clearance is as requested. We welcome the Applicant's inclusion of a nominal seismic survey in principle. However, the Applicant has not taken on board our suggestions for determining a realistic assessment scenario, as they have treated the seismic survey as a static source. Nevertheless, we agree that assessing the seismic survey as a mobile source would not change the assessment conclusions as the risk of AEoI to the Southern North Sea SAC has already been identified. However, it does further highlight the risk of significant exceedance of the thresholds should all identified projects and plans go ahead at the same time, further emphasising the need for effective mitigation of cumulative underwater noise disturbance. Note that we maintain our recommendation that the Applicant commit to mitigation measures, however this is covered in our response to other comments (e.g. D21). |  |  |  | The Applicant has provided a note with an illustrative assessment of the in-combination assessment including a nominal high order UXO clearance and a nominal seismic survey. The approach taken to calculating the contribution of a nominal high order UXO clearance is as requested. We welcome the Applicant's inclusion of a nominal seismic survey in principle. However, the Applicant has not taken on board our suggestions for determining a realistic assessment scenario, as they have treated the seismic survey as a static source. Nevertheless, we agree that assessing the seismic survey as a mobile source would not change the assessment conclusions as the risk of AEoI to the Southern North Sea SAC has already been identified. However, it does further highlight the risk of significant exceedance of the thresholds should all identified projects and plans go ahead at the same time, further emphasising the need for effective mitigation of cumulative underwater noise disturbance. Note that we maintain our recommendation that the Applicant commit to mitigation measures, however this is covered in our response to other comments (e.g. D21). |  | No
D13 | 15, 20,22 | The Applicant has listed the sources of underwater noise from the project and has included geophysical and seismic surveys. However, no information on the surveys themselves (noise sources, duration) have been provided. It is of particular importance that the noise sources are listed, as Natural England’s main concern with regards to underwater noise production and impacts on marine mammals relates to sub-bottom profilers (SBPs) and airguns. Can the Applicant please confirm if there is potential for seismic surveys to be undertaken as part of this project? Underwater noise from such surveys have not been assessed in Annex 4.5 Subsea Technical Noise Report, and the pathway of underwater noise from these surveys as part of the project are not assessed in the MM ES chapter. Any such project activities should be included consistently across the marine mammal assessments. We request clarification as to whether these surveys are to be included as part of the DCO, or whether they will be undertaken under a separate licence? If they are to be included in the licence more detail will be needed on the activities and an assessment of impacts in the ES Chapter carried out to determine if these could lead to thresholds being exceeded if done on the same day as piling. At present, geophysical surveys undertaken by the offshore wind industry are exempt from obtaining a Marine Licence (ML) and have historically not been captured in in-combination assessments. We therefore do not have confidence that any geophysical surveys undertaken (by both this project and the offshore wind industry generally) will be included in the SIP under the current approach. We request that the Applicant commits to providing details of their geophysical surveys at the time the SIPs (for both piling and UXO clearance) are written to allow the Regulators to undertake a fully informed in-combination assessment of the works. OR We recommend the Applicant commit to providing information/requesting sign off on the surveys so that the Regulators (in consultation with Natural England) can undertake an appropriate in-combination assessment. |  | The applicant has confirmed that they will not be undertaking geophysical surveys as part of the activities under the Hornsea Four DCO. Natural England would defer to the MMO as to whether or not this is appropriate noting their representations on this matter. However, as they are a known activity directly connected to the contruction (and in some cases, operation) of wind farm development they should be fully considered and assessed within the ES and RIAA. |  | No change. |  | See response to D12. |  | No change. |  | No change/response from the Applicant on this point. Natural England request that the Applicant provide information on the geophysical survey equipment likely to be used, and commit to mitigation and/or the inclusion of text in relation to the mitigation process for geophysical surveys. As stated at Deadline 2, Natural England defer to the MMO as to whether it is appropriate for geophysical surveys to not be covered in the DCO. However, as they are a known activity directly connected to the construction (and in some cases, operation) of wind farm development they should be given a high-level assessment within the ES and RIAA, even if they are then going to be undertaken under a separate licence (similar to UXO clearance operations). |  | No Change |  | No change/response from the Applicant on this point. Natural England request that the Applicant provide information on the geophysical survey equipment likely to be used, and commit to mitigation and/or the inclusion of text in relation to the mitigation process for geophysical surveys. As stated at Deadline 2, Natural England defer to the MMO as to whether it is appropriate for geophysical surveys to not be covered in the DCO. However, as they are a known activity directly connected to the construction (and in some cases, operation) of wind farm development they should be given a high-level assessment within the ES and RIAA, even if they are then going to be undertaken under a separate licence (similar to UXO clearance operations). |  | Yes
D14 | 17,18,24,39 | Natural England’s understanding from the Project Description ES chapter (A1.4; 4.4.8.4.35) is that there will be no concurrent piling between the Hornsea 4 array area and the HVAC booster station search area; only that there may be simultaneous piling, undertaken by two vessels, within one of these areas at any one time. We advise that this commitment to not undertake concurrent piling between HVAC and array areas should be secured as a licence condition as it is a fundamental part of the assessment of underwater noise impacts for the project alone. Alternatively, a condition could be secured allowing either concurrent or simultaneous piling to occur. We highlight that Table 3 (Co85) includes the worst-case scenario as simultaneous piling (assumed to be two locations piled at the same time). Clarification is needed on whether there is the potential for both concurrent and simultaneous piling to occur within a 24-hour period (i.e. up to 4 locations in a 24-hour period). If so, this scenario (and associated disturbance impacts) must be assessed as it would comprise the worst-case for number of piling locations in a 24-hour period. If it is not the intention of the Applicant to include this in the WCS, then this should be conditioned in the DCO. |  | In their revised version of the draft DCO, the Applicant has clarified in licence condition 13 (2) (5) that only 2 pile locations will be piled within a 24 hour period. This explicitly addresses our second point. We infer that the revised licence condition does not allow for the possibility of concurrent piling at the HVAC search area and the array, addressing our first point also. | [11 empty] | In their revised version of the draft DCO, the Applicant has clarified in licence condition 13 (2) (5) that only 2 pile locations will be piled within a 24 hour period. This explicitly addresses our second point. We infer that the revised licence condition does not allow for the possibility of concurrent piling at the HVAC search area and the array, addressing our first point also. |  | Yes
D15 | 21 | We consider that the types of geophysical surveys undertaken by the offshore wind industry (including those using sub-bottom profilers (SBPs)) have the potential to result in PTS in marine mammals. Furthermore, such geophysical surveys typically go through the ML exemption route, through which there is no legally-binding condition to undertake marine mammal mitigation to reduce the risk of injury (and disturbance). We advise that the Applicant commit to mitigation for geophysical surveys. |  | The applicant has confirmed that they will not be undertaking geophysical surveys as part of the activities under the Hornsea Four DCO. However, we do not consider that removes the need for these activities to be fully considered within the ES and RIAA. (See Point 13). |  | No change |  | See response to D12. |  | No change. |  | No change/response from the Applicant on this point. Natural England request that the Applicant provide information on the geophysical survey equipment likely to be used and commit to mitigation and/or the inlcusion of text in relation to the mitigation process for geophysical surveys. As stated at Deadline 2, Natural England defer to the MMO as to whether or not it is appropriate for geophysical surveys to not be covered in the DCO. However, as they are a known activity directly connected to the construction (and in some cases, operation) of wind farm development they should be given a high-level assessment within the ES and RIAA, even if they are then going to be undertaken under a separate licence (similar to UXO clearance operations). |  | No Change |  | No change/response from the Applicant on this point. Natural England request that the Applicant provide information on the geophysical survey equipment likely to be used and commit to mitigation and/or the inlcusion of text in relation to the mitigation process for geophysical surveys. As stated at Deadline 2, Natural England defer to the MMO as to whether or not it is appropriate for geophysical surveys to not be covered in the DCO. However, as they are a known activity directly connected to the construction (and in some cases, operation) of wind farm development they should be given a high-level assessment within the ES and RIAA, even if they are then going to be undertaken under a separate licence (similar to UXO clearance operations). |  | Yes
D16 | 25 | If there is the potential for a seismic survey to occur, then the effective deterrent range (EDR) to be used should be 12 km not 5 km, as this would be the worst-case scenario. However, we note that seismic surveys are not explicitly included in the Project Description ES Chapter (only geophysical surveys are), and more generally seismic surveys are not undertaken for offshore wind projects. We therefore advise the Applicant to consider whether reference to seismic surveys can be removed from the assessment. |  | The Applicant has confirmed that seismic surveys may be required. The Applicant's response on the JNCC (2020) guidelines is incorrect. The JNCC (2020) guidelines only propose a single EDR for seismic surveys, which is 12 km; all seismic surveys using airguns need to use this EDR. The 5 km EDR is applicable only to non-airgun geophysical sources e.g. sub-bottom profilers. Therefore, a 12 km must be used in the assessment of disturbance impacts to harbour porpoise. We therefore request that the assessment is updated using the 12 km EDR. |  | No change |  | We welcome the Applicant's confirmation that seismic airgun surveys will not be used on the Project, making use of the 5km EDR approriate. We request that the Project description is updated to reflect that whilst seismic surveys (e.g. sub-bottom profilers) may be required, seismic airgun suveys will not be required. This is to make it clear what has been assessed. We will then consider this concern addressed. |  | No change. |  | The Project Description has been updated to reflect that seismic airgun surveys will not be required. We consider this point addressed. |  |  |  | The Project Description has been updated to reflect that seismic airgun surveys will not be required. We consider this point addressed. |  | Yes
D17 | 26 | In relation to Hornsea 4 pre-construction works: We understand that the value of 3,683 km2 has been calculated for the maximum area of disturbance around simultaneous/concurrent piling (in Section 10.3.3.38), not pre-construction works, therefore we anticipate that this number is not correct for pre-construction works and should be recalculated. Revise the maximum area of disturbance for the pre-construction surveys. |  | We have provided clarification to the Applicant on the inclusion of geophysical surveys in the RIAA and anticipate further information at Deadline 2 on this. |  | No change |  | No change |  | No change |  | No change. |  | No Change |  | We have provided clarification to the Applicant on the inclusion of geophysical surveys in the RIAA and anticipate further information at Deadline 2 on this. |  | No
D18 | 27 | We advise that a figure should be presented to accompany Table 32, showing how overlap between projects can be taken into account in the in-combination assessment and offer a reduction in spatial area by 15-25% (as stated in Section 11.3.2.23). This is important as the Applicant considers this approach provides certainty that primary mitigation will be sufficient. |  | The Applicant has provided a figure to accompany Table 32, as requested. We understand that the figure presents all projects in Tiers 1-2 in Table 32 that could contribute to in-combination disturbance on the SNS SAC. There are parts of this figure which could be clearer (e.g. the caption, and which year each panel in the figure is relating to). There are two inconsistencies between the Figure 23 and the numbers presented in Table 32: • In the winter min/max figures there is no contribution from Hornsea 4 presented. Whereas, in Table 32, the min/max overlap between Hornsea 4 and the winter area is 352 and 277 km2 respectively. The figure must be updated to show the contribution of Hornsea 4 to in-combination disturbance in the winter area of the SNS SAC. • Based on Table 32, Dogger Bank C does contribute to the in-combination disturbance in the summer max scenario. This should be reflected in Figure 23. These clarifications and inconsistencies should be addressed before we can consider whether our concern has been addressed. |  | No change |  | An updated figure and/or information will be provided at Deadline 5. |  |  |  | No change/response from the Applicant on this point. We request that an updated figure is provided to include: -the contribution of Hornsea 4 to winter area min/max figures - the contribution of Dogger Bank C to in-combination disturbance in the summer max scenario. |  | No Change |  | The Applicant has provided the updated figure with the requested changes. |  | Yes
D19 | 28 | We consider that the values presented in Table 32 are suitably precautionary, rather than excessively so. Of particular note is that Table 32 only considers a single activity, whereas several of the projects in the in-combination assessment have concurrent piling within their MDS, including Hornsea 4. If Hornsea 4 undertook concurrent piling with the worst-case geographical spread, resulting in 3,683 km2, the remaining capacity (‘headroom’) in the threshold would be insufficient to allow even one other project to undertake piling fully within the SNS SAC (i.e. one from Dogger Bank A, B, Norfolk Vanguard and Norfolk Boreas). We understand that this is based on the worst-case scenario for concurrent piling at Hornsea 4, however we do not have any information on the average amount of overlap between two piling locations for example. Nevertheless, this illustrates our concern that it is not an unrealistic scenario that, without mitigation, the thresholds could be exceeded. We also note that these assessments do not take into account other well-established sources of noise such as seismic surveys, which may further contribute to the thresholds in the seasons assessed. |  | We have provided clarification to the Applicant on the inclusion of geophysical surveys in the RIAA and anticipate further information at Deadline 2 on this. |  | No change |  | No change |  | No change |  | The Applicant has provided a note with an illustrative assessment of the in-combination assessment including a nominal high order UXO clearance and a nominal seismic survey. The approach taken to calculating the contribution of a nominal high order UXO clearance is as requested. We welcome the Applicant's inclusion of a nominal seismic survey in principle. However, the Applicant has not taken on board our suggestions for determining a realistic assessment scenario, as they have treated the seismic survey as a static source. Nevertheless, we agree that assessing the seismic survey as a mobile source would not change the assessment conclusions as the risk of AEoI to the Southern North Sea SAC has already been identified. However, it does further highlight the risk of significant exceedance of the thresholds should all identified projects and plans go ahead at the same time, further emphasising the need for effective mitigation of cumulative underwater noise disturbance. |  |  |  | The Applicant has provided a note with an illustrative assessment of the in-combination assessment including a nominal high order UXO clearance and a nominal seismic survey. The approach taken to calculating the contribution of a nominal high order UXO clearance is as requested. We welcome the Applicant's inclusion of a nominal seismic survey in principle. However, the Applicant has not taken on board our suggestions for determining a realistic assessment scenario, as they have treated the seismic survey as a static source. Nevertheless, we agree that assessing the seismic survey as a mobile source would not change the assessment conclusions as the risk of AEoI to the Southern North Sea SAC has already been identified. However, it does further highlight the risk of significant exceedance of the thresholds should all identified projects and plans go ahead at the same time, further emphasising the need for effective mitigation of cumulative underwater noise disturbance. |  | No
D20 | 29 | Natural England considers that mitigation of the noise at source is also an extremely beneficial type of mitigation and should not be disregarded in favour of the primary mitigation listed, as the inclusion of noise abatement systems (NAS) could be secured and put in place now, rather than the primary mitigation which will only be finalised once construction timetables are known (in a narrow window prior to construction). It also limits the contribution of the project alone to the disturbance thresholds and therefore reduces the overall impact to the SNS SAC. We further note that, by the time the project has progressed to the stage of producing the SIP, many of the financial decisions have been made and it is less likely that funds will be available to undertake noise abatement at source. |  | The Applicant has not provided any new information or confirmed that they will be using at-source noise mitigation; they continue to rely on the SIP process to secure mitigation. However, we note that a Clarification note on underwater noise abatement systems will be provided at Deadline 2. As it is mentioned by the Applicant in their response, we request that the Applicant provide justification as to why committing to mitigation is "not possible" at this stage. |  | The Applicant has provided a document [REP2-050] that details the environmental conditions of the site, in relation to the environmental limitations of noise abatement systems (NAS). The document demonstrates that the conditions on the site are within the known limits of NAS for wind speed and current state; the theoretical limits for water depth; and potentially approaching the limits of wave height in the winter months. This document therefore confirms that this site is suitable for NAS and addresses our query in this respect. We maintain that mitigation should be committed to at this stage and that it would be appropriate for NAS to be considered within this. |  | No change. |  | No change. |  | Natural England's position is that a commitment should be made to deliver mitigation, with the option to demonstrate that it is not needed post-consent. We acknowledge Hornsea 4's position of not commiting to specific mitigation measures due to potential advances in technology and welcome that the need for mitigation has been budgeted for (pers comm). We would therefore welcome the inclusion of text outlining the process for mitigation to demonstrate that the requirement for mitigation has been factored into the Project's plans. |  | No Change |  | The Applicant has included text detailing the process for determining mitigation in the Outline SIP. Natural England maintain that committing to mitigation at this stage and minimising impacts as far as possible would be preferable, but acknowledge that in this instance this is an acceptable compromise. |  | No
D21 | 30 | Natural England cannot agree with the conclusion of no AEOI for in-combination disturbance impacts to the SNS SAC due to lack of confidence in the SIP process (see Relevant Representations, Paragraphs 5.30-5.32). We consider that mitigation should be committed to at this stage for future review under the SIP process. |  | Natural England maintains that mitigation should be committed to at this stage. This concern has not been resolved. |  | No change |  | No change |  | No change |  | Natural England's position is that a commitment should be made to deliver mitigation, with the option to demonstrate that it is not needed post-consent. We acknowledge Hornsea 4's position of not commiting to specific mitigation measures due to potential advances in technology and welcome that the need for mitigation has been budgeted for (pers comm). We would therefore welcome the inclusion of text outlining the process for mitigation to demonstrate that the requirement for mitigation has been factored into the Project's plans. |  | No Change |  | The Applicant has included text detailing the process for determining mitigation in the Outline SIP. Natural England maintain that committing to mitigation at this stage and minimising impacts as far as possible would be preferable, but acknowledge that in this instance this is an acceptable compromise. We note that it will not be possible to rule out AEoI in-combination until the post-consent SIP is provided for assessment. |  | No
D22 | 31 | We do not agree that, at this stage, UXO clearance and geophysical/seismic surveys can be considered ‘additive’. Given the lack of information on requirements for geophysical/seismic surveys and UXO clearance works, and that these two activities will be undertaken under different licences with different controls/mitigation measures, these two activities should be considered separately. To illustrate, we do not have confidence that the geophysical/seismic surveys would occur on the same days as the UXO clearance in the winter period, which are assumed to be on a maximum of 20 days in the SNS SAC (Section 11.3.2.30). There is a risk that impacts (from a seasonal disturbance perspective) will be greater than what has been presented because of the assumed additive nature. The geophysical/seismic survey works should be treated as separate to the UXO clearance. |  | We have provided clarification to the Applicant on the inclusion of geophysical surveys in the RIAA and anticipate further information at Deadline 2 on this. Please also see Points 13 and 15 regarding the inclusion of geophysical surveys in assessments. |  | No change |  | See response to D12. We consider that the advice provided in D12 in relation to seismic surveys also applies to UXO clearance. We request that 1 nominal high-order detonation is included in the RIAA in-combination assessent. We acknowledge that there is a move towards low-order methods of UXO clearance, however we consider it likely that high order clearance would be retained as a contingency option and should therefore be assessed. |  | No change. |  | The Applicant has provided a note with an illustrative assessment of the in-combination assessment including a nominal high order UXO clearance and a nominal seismic survey. The approach taken to calculating the contribution of a nominal high order UXO clearance is as requested. We welcome the Applicant's inclusion of a nominal seismic survey in principle. However, the Applicant has not taken on board our suggestions for determining a realistic assessment scenario, as they have treated the seismic survey as a static source. Nevertheless, we agree that assessing the seismic survey as a mobile source would not change the assessment conclusions as the risk of AEoI to the Southern North Sea SAC has already been identified. However, it does further highlight the risk of significant exceedance of the thresholds should all identified projects and plans go ahead at the same time, further emphasising the need for effective mitigation of cumulative underwater noise disturbance. With regards to geophysical surveys undertaken for the Hornsea 4 project, we request that the Applicant provide details on geophysical projects at the time of licence application to demonstrate that all projects and plans that could act in-combination have been taken into account. |  | No Change |  | The Applicant has provided a note with an illustrative assessment of the in-combination assessment including a nominal high order UXO clearance and a nominal seismic survey. The approach taken to calculating the contribution of a nominal high order UXO clearance is as requested. We welcome the Applicant's inclusion of a nominal seismic survey in principle. However, the Applicant has not taken on board our suggestions for determining a realistic assessment scenario, as they have treated the seismic survey as a static source. Nevertheless, we agree that assessing the seismic survey as a mobile source would not change the assessment conclusions as the risk of AEoI to the Southern North Sea SAC has already been identified. However, it does further highlight the risk of significant exceedance of the thresholds should all identified projects and plans go ahead at the same time, further emphasising the need for effective mitigation of cumulative underwater noise disturbance. With regards to geophysical surveys undertaken for the Hornsea 4 project, we request that the Applicant provide details on geophysical projects at the time of licence application to demonstrate that all projects and plans that could act in-combination have been taken into account. |  | No
Document reviewed: B2.2: Report to Inform Appropriate Assessment Part 10: Appendix G: Marine Mammals – Grey seal RIAA information | [7 empty] | G3.17 Applicant's comments on Natural England's Comments received at Deadline 2 - Revision: 01 [REP3-046]
D23 | 33 | A figure of the movements of the 9 tagged pups and juveniles should be presented, in order to better understand the movements of these life stages and the difference in movements compared to adult seals. Pups and juveniles are part of the protected feature of the site as well as adults. |  | The Applicant notes that a figure will be added to the document. A revised document has not been provided yet, therefore our concerns have not yet been addressed. |  | No change |  | We note that a Figure has now been provided. We will provide further comment at Deadline 5. |  | The Applicant has provided a figure showing the movements of juvenile and pup grey seals along the east coast of England. It is interesting to note that these pups/juveniles show higher association with the more distant Berwickshire and North Northumberland Coast SAC than the Humber Estuary SAC. The data on the figure supports that Applicant's statement that "seals in the Project boundary area showed associations with both the Berwickshire and North Northumberland Coast SAC and the Humber Estuary SAC, and therefore it is not appropriate to attribute all impacts from Hornsea Four to the Humber Estuary SAC alone." We are therefore content that the figure addresses our concern. | [5 empty] | The Applicant has provided a figure showing the movements of juvenile and pup grey seals along the east coast of England. It is interesting to note that these pups/juveniles show higher association with the more distant Berwickshire and North Northumberland Coast SAC than the Humber Estuary SAC. The data on the figure supports that Applicant's statement that "seals in the Project boundary area showed associations with both the Berwickshire and North Northumberland Coast SAC and the Humber Estuary SAC, and therefore it is not appropriate to attribute all impacts from Hornsea Four to the Humber Estuary SAC alone." We are therefore content that the figure addresses our concern. |  | Yes
Document reviewed: F2.11: Outline Southern North Sea Special Area of Conservation Site Integrity Plan | [5 empty] | G2.14 Clarification Note on UnderwaterNoise Abatement Systems - Revision: 01
D24 | 37 | We note that the Applicant has stated that the review of the SNS SAC SIP will occur six to nine months prior to the start of construction. We strongly advise that this timeframe (or similar) is included in the SIP consent condition. This is to ensure that the SIP is undertaken when the final details of projects that may act in-combination, as well as Hornsea 4, are known. |  | The Applicant has not addressed our concerns. We maintain that the timeframe of the SIP needs to be secured in the DCO. |  | No change |  | No change |  | No change |  | We maintain that the submission of the SIP 6-9 months prior to construction should be secured in the DCO. |  | No Change |  | The Applicant has revised their outline SIP to state that the SIP will be submitted at 12 and 4 months prior to construction. This is welcome but we continue to advise that the timeframe for SIP submission is secured as a condition in the DCO. |  | No
D25 | 40 | We consider that both primary and secondary mitigation need to be considered by the Applicant when determining how to provide certainty of no AEoI |  | The Applicant has not addressed our concerns. |  | No change |  | No change |  | No change |  | Natural England's position is that a commitment should be made to deliver mitigation, with the option to demonstrate that it is not needed post-consent. We acknowledge Hornsea 4's position of not commiting to specific mitigation measures due to potential advances in technology and welcome that the need for mitigation has been budgeted for (pers comm). We would therefore welcome the inclusion of text outlining the process for mitigation to demonstrate that the requirement for mitigation has been factored into the Project's plans. |  | No Change |  | The Applicant has included text detailing the process for determining mitigation in the Outline SIP. Natural England maintain that committing to mitigation at this stage and minimising impacts as far as possible would be preferable, but acknowledge that in this instance this is an acceptable compromise. We note that it will not be possible to rule out AEoI in-combination until the post-consent SIP is provided for assessment. |  | No
D26 | 43 | We request that the Applicant provide more information on the likelihood of NAS being suitable for the Hornsea 4 project. Several factors are listed as affecting the suitability of NAS, however these are factors that we would anticipate to be mostly already understood about the site, or possible to make generalisations on based on existing data. We wish to understand the likelihood of NAS being feasible as early as possible, given the Applicant’s inclusion of this measure in both the OMMMP and the Outline SIP. |  | The Applicant is considering this comment and will potentially provide more information at Deadline 2 on this subject. The comment has not yet been addressed. |  | The Applicant has provided a document [REP2-050] that details the environmental conditions of the site, in relation to the environmental limitations of noise abatement systems (NAS). The document demonstrates that the conditions on the site are within the known limits of NAS for wind speed and current state; the theoretical limits for water depth; and potentially approaching the limits of wave height in the winter months. This document clarifies that the site is suitable for NAS. |  | The Applicant has provided a document [REP2-050] that details the environmental conditions of the site, in relation to the environmental limitations of noise abatement systems (NAS). The document demonstrates that the conditions on the site are within the known limits of NAS for wind speed and current state; the theoretical limits for water depth; and potentially approaching the limits of wave height in the winter months. This document clarifies that the site is suitable for NAS. |  | The Applicant has provided a document [REP2-050] that details the environmental conditions of the site, in relation to the environmental limitations of noise abatement systems (NAS). The document demonstrates that the conditions on the site are within the known limits of NAS for wind speed and current state; the theoretical limits for water depth; and potentially approaching the limits of wave height in the winter months. This document clarifies that the site is suitable for NAS. | [5 empty] | The Applicant has provided a document [REP2-050] that details the environmental conditions of the site, in relation to the environmental limitations of noise abatement systems (NAS). The document demonstrates that the conditions on the site are within the known limits of NAS for wind speed and current state; the theoretical limits for water depth; and potentially approaching the limits of wave height in the winter months. This document clarifies that the site is suitable for NAS. |  | Yes
D27 | 45 | We advise that the Applicant should also consider the use of Passive Acoustic Monitoring (PAM) as a monitoring method for pre-piling searches during the hours of darkness or poor weather. |  | The Applicant maintains that they do not need PAM. We disagree with this and do not consider that they have addressed our concerns. They state that the full mitigation zone (based on instantaneous PTS) is 2.9 km for harbour porpoise and that PAM does not cover that distance; we would advise that this issue is not only applicable to PAM as MMOs would also be unlikely to detect harbour porpoise over the this 2.9 km mitigation zone. As per the SNCB statement on ADDs (2016), we note that the Lofitech ADD can elicit behavioural response from harbour porpoise and harbour seal, and potentially for grey seals. We note that since the 2017 statement there has been evidence to demonstrate that the Lofitech ADD is also effective at deterring minke whales (McGarry et al., 2017). However, there is limited evidence that Lofitech ADDs are effective at deterring dolphin species, including bottlenose dolphin which may be present in impact zones. We therefore advise that a combination of methods including MMOs, PAM and ADDs would provide a level of protection to all marine mammal species likely to occur. |  | No change |  | No change |  | No change |  | No change There is limited evidence that ADDs are effective for deterring dolphin species. Natural England recommend that Hornsea 4 commits to using PAM as well as MMObs and ADD for pre-piling searches. |  | The Applicant has updated their MMMP in line with Natural England's advice (inclusion of Passive Acoustic Monitoring as a potential mitigation method). The update has addressed our concerns and so we consider the issue resolved. |  | The Applicant has updated their MMMP in line with Natural England's advice (inclusion of Passive Acoustic Monitoring as a potential mitigation method). The update has addressed our concerns and so we consider the issue resolved. |  | Yes
D28 | 46 | Based on the information provided in the OMMMP, further discussion is needed during Examination between Natural England and the Applicant as to the most appropriate duration of ADD activation. |  | The Applicant agrees that further discussion is needed. It can be inferred from their response that they would intend to have this discussion post-consent. The exact timings of the ADD duration could be finalised post-consent (after further modelling is undertaken). However, the principles which determine ADD duration should be discussed at this stage (i.e. whether ADD duration corresponds to the instantaneous PTS zone or the cumulative PTS zone). Agreement is needed on this point. Note that this discussion is related to our concerns over no commitment to mitigate the full cumulative PTS zone as per our previous comments. |  | No change |  | No change |  | No change |  | See response to comment D2. |  | The Applicant has updated their MMMP in line with Natural England's advice. The update has addressed our concerns and so we consider the issue resolved. |  | The Applicant has updated their MMMP in line with Natural England's advice. The update has addressed our concerns and so we consider the issue resolved. |  | Yes
D29 | 47 | The Applicant notes that previously bubble curtains have been used in waters up to 45m in depth. Further information is needed on whether it is feasible to use bubble curtains in the deeper waters of the site that are >45m, possibly even >60m. We request that more information is provided on the likelihood of bubble curtains and NAS being suitable for the Hornsea 4 project (specifically in regard to deeper waters). |  | The Applicant is considering this comment and will potentially provide more information at Deadline 2 on this subject. The comment has not yet been addressed. |  | The Applicant has provided a document [REP2-050] that details the environmental conditions of the site, in relation to the environmental limitations of noise abatement systems (NAS). The document demonstrates that the conditions on the site are within the known limits of NAS for wind speed and current state; the theoretical limits for water depth; and potentially approaching the limits of wave height in the winter months. This document clarifies that the site is suitable for NAS. | [9 empty] | The Applicant has provided a document [REP2-050] that details the environmental conditions of the site, in relation to the environmental limitations of noise abatement systems (NAS). The document demonstrates that the conditions on the site are within the known limits of NAS for wind speed and current state; the theoretical limits for water depth; and potentially approaching the limits of wave height in the winter months. This document clarifies that the site is suitable for NAS. |  | Yes
Document reviewed: F2.7: Outline Marine Monitoring Plan
D30 | 48, 51, 52 | This section of the OMMP remains extremely short and lacking on detail. There has been no consideration of the areas of the assessment where assumptions have been made and where the project could contribute to filling knowledge gaps (for example, with regards to operational WTG noise levels (Point 7), or the assumed distribution of bottlenose dolphin close to the coast (Point 9)). Many of our comments and proposals for additional monitoring for marine mammals made during the Evidence Plan process have not been sufficiently addressed by the consultation response and new version of the OMMP. We note that monitoring is not only required where an adverse effect is predicted; it should address assumptions in the ES and confirm the ES assessments. We do not consider that the conclusions of the SIP will have bearing on the requirements for monitoring. Further, the pre- and post-construction digital aerial surveys are not carried out at a scale that is conducive to understanding impact at the population scales of marine mammals. Natural England advise that the Applicant undertakes strategic monitoring to understand these population level impacts. We recommend that the OMMP is kept live during examination so an updated, final version can be provided capturing the results of further discussion. |  | The Outline Marine Monitoring Plan needs to clearly reflect the options for monitoring at this stage, as it is this document that provides the guiding principles for the monitoring that is agreed post-consent. It is therefore imperative that this document is thorough and covers the monitoring options that address our concerns and/or the assumptions in the ES. |  | No change |  | No change |  | No change |  | We request that the OMMP is updated with the suggested monitoring objectives. |  | No Change |  | The Applicant has confirmed that they will not update the OMMP with the requested monitoring objectives. |  | No
D31 | 49 | The Applicant has included monitoring undertaken under the MMMP as a monitoring commitment. However, we consider that this monitoring is undertaken for the purposes of mitigation only i.e. it is a pre-piling search. If the data collected are not being used to confirm the results of the ES assessment, then we cannot consider it as EIA-related monitoring. |  | The Applicant will remove this monitoring from the OMMP. This addresses our concern. | [11 empty] | The Applicant will remove this monitoring from the OMMP. This addresses our concern. |  | Yes
D32 | 50 | We are disappointed to see that the Applicant has reduced the number of monitored piling locations from 6 to 4, in comparison to an earlier version of the OMMP. We request that a justification is provided for the reduction. |  | The Applicant states that the 6 monitoring locations in the draft OMMP was in error. Natural England consider the first four piles to represent the absolute minimum requirement, and consider that monitoring the most resistant piles would be beneficial as they are likely to represent the largest noise impacts and could be further used to validate the noise impact predictions of the ES. |  | No change |  | No change |  | No change | [5 empty] | The Applicant states that the 6 monitoring locations in the draft OMMP was in error. Natural England consider the first four piles to represent the absolute minimum requirement, and consider that monitoring the most resistant piles would be beneficial as they are likely to represent the largest noise impacts and could be further used to validate the noise impact predictions of the ES. |  | No
D33 | RR-029-5.30-32 | Use of Site Integrity Plans Whist Natural England are in agreement that the project alone will not result in an Adverse Effect on Integrity (AEoI) on the Southern North Sea SAC (SNS SAC), there are various scenarios whereby the underwater noise thresholds for the site would be exceeded on an in-combination basis, and therefore the potential for adverse effect incombination cannot be excluded due to the uncertainty over concurrent works. This issue is not unique to Hornsea 4 and there is a broad acceptance that in many instances it will be possible to mitigate or manage noise levels to avoid AEoI closer to the time of construction. However, it is usually not possible to demonstrate this through assessment given the vast number of potential scenarios that would need to be accounted for. The submission of an In-Principle Site Integrity Plan (SIP) offers the opportunity for developers to demonstrate to the ExA/Competent Authority that avoiding AEoI will indeed be possible through appropriate management and mitigation but deferring the ultimate determination to the MMO in the pre-construction phase of the project. It is then anticipated that the SIP will be updated/finalised close to the time of construction when the extent of noisy activities within the designated site in any given season is better known and therefore able to be assessed, to enable the MMO to assess the impact of a much-refined worst case scenario and confirm that the applied for works will not result in an AEoI on the SNS SAC in-combination with other plans and projects. Whilst this approach carries risk and uncertainty for all parties, it has been accepted as the most pragmatic way forward at this time. Natural England have previously advised that a mechanism to manage multiple SIPs over varying timescales needs to be developed and put in place by the Regulators to ensure that the noise thresholds are not exceeded. Whilst we recognise steps have been taken to achieve this with the creation of the Activity Tracker, the current “case by case” approach is not fit for purpose and has already resulted in the in-combination noise levels coming close to exceeding the site thresholds. This is likely to result in difficulties across all industries further down the line, as the next round of offshore windfarms come forward in the southern North Sea. Should potential exceedance of the thresholds occur, a process for dealing with this issue needs to be in place. Until the mechanism by which the SIPs will be managed, monitored and reviewed is further developed, Natural England are unable to advise that this approach is sufficient to address the in-combination impacts described in this Application and therefore it is not possible to be certain that there will be no AEoI on the SNS SAC. |  | We do not consider that our overarching concerns with the SIP process are for the Applicant to address, with the exception of committing to mitigation at this stage. We have included this point from our Relevant Representations to track any progress made on the issue by Decsion Makers during the Examination. |  | No change |  | No change |  | No change |  | No change |  | No Change |  | We do not consider that our overarching concerns with the SIP process are for the Applicant to address, with the exception of committing to mitigation at this stage. We have included this point from our Relevant Representations to track any progress made on the issue by Decsion Makers during the Examination. |  | No
D34 | RR-029-5.35 | Inclusion of Unexploded Ordnance (UXO) Within the Report to Inform Appropriate Assessment (RiAA) the Applicant has undertaken assessments of the potential impacts to designated sites for marine mammals from unexploded ordnance (UXO) clearance activities. While we welcome the work undertaken, we cannot comment on this section or the AEoI conclusions as we do not have the information to underpin the assessment scenario, nor have we seen any of the proposed mitigation documents. We consider it would be more appropriate for this level of detail to be provided as part of the standalone UXO Marine Licence application. We consider it worth noting however that the Applicant’s proposed worst case scenario of 5 UXO detonations in a 24 hour period is of major concern for the future UXO marine licence as the threshold would likely be exceeded. |  | The applicant has confirmed that they will not be undertaking UXO clearance as part of the activities under the Hornsea Four DCO; these will be undertaken under a separate Marine Licence. This approach approach has become standard across the industry. The assessment of impacts from UXO clearance provided by the applicant was more detailed than anticipated and came to a conclusion of no AEoI (despite significant uncertainty in the assessment). Natural England will provide comments on the detailed assessment and assessment conclusions when we are consulted on the standalone Marine Licence for UXO clearance. We consider that this matter has been addressed for the purpose of the DCO. | [11 empty] | The applicant has confirmed that they will not be undertaking UXO clearance as part of the activities under the Hornsea Four DCO; these will be undertaken under a separate Marine Licence. This approach approach has become standard across the industry. The assessment of impacts from UXO clearance provided by the applicant was more detailed than anticipated and came to a conclusion of no AEoI (despite significant uncertainty in the assessment). Natural England will provide comments on the detailed assessment and assessment conclusions when we are consulted on the standalone Marine Licence for UXO clearance. We consider that this matter has been addressed for the purpose of the DCO. |  | Yes

## F - Benthic Intertidal
Point | [RR - 029] Appendix F point number | Taken from Natural England’s Relevant and Written Representations Hornsea 4 Appendix F Benthic and Intertidal | RAG Status Rel and WR Rep | Response from Applicant on RR | Consultation, actions, progression | RAG Risk Status Deadline 2 | Consultation, actions, progression | RAG Risk Status Deadline 3 | Consultation, actions, progression | RAG Risk Status Deadline 4 | Consultation, actions, progression | RAG Risk Status Deadline 5 | Consultation, actions, progression | RAG Risk Status Deadline 6 | Consultation, actions, progression | RAG Risk Status Deadline 7 | Consultation, actions, progression | RAG Risk Status Deadline 8 | Issue Resolved
Document used: Volume A2.2 Environmental Statement Volume A2 Chapter 2 Benthic and Intertidal Ecology [APP-014] & Volume A5.2.1 Benthic and intertidal ecology technical report [APP-068] |  |  |  |  | Document reviewed: G1.9 Applicant’s comments on Relevant Representations Revision: 01 [REP1-038] & G1.44 Clarification Note on Marine Sediment Contaminants [REP1-066] |  | Document reviewed: REP2-038 Applicant’s Responses to the ExA’s First Written Questions (ExQ1) & |  | Document Reviewed: G3.6 Clarification Note: Justification of Offshore Maximum Design Scenarios - Revision: 01 [REP3-035]; G3.17 Applicant's comments on Natural England's Comments received at Deadline 2 - Revision: 01 [REP3-046] |  | Document Reviewed: REP4-031 G1.44 Clarification Note on Marine Sediment Contaminants (Tracked) - Revision: 02 REP4-044 G4.10 Applicant’s comments on other submissions received at Deadline 3 - Revision: 01 (No comments made on benthic issues) |  | Documents Reviewed: REP5-074 G5.2 Applicant’s Responses to the Examining Authority's Second Written Questions (ExQ2); REP5-081 G5.3 Applicant’s comments on other submissions received at Deadline 4; REP5-083 G5.5 Clarification Note on Drill Arisings and Deposited Sediments - Revision: 01; REP5a-016 G5.32 Endurance No Overlap Environmental Impact Assessment and Habitats Regulations Assessment Review - Revision: 01; REP5a-014 G5.30 Applicant’s comments on other submissions received at Deadline 5 - Revision: 01 |  | None of the documents reviewed at Deadline 7 addressed any of the outstanding issues within Benthic Ecology. Documents Reviewed: REP6-003 A1.4 Chapter 4 Project Description (Tracked) - Revision: 06; REP6-005 - A4.4.4 Dredging and Disposal Site Characterisation (Tracked) - Revision: 02 REP6-014 F2.15 Outline Cable Specification and Installation Plan (Tracked) - Revision: 03 REP6-007 A4.4.8 Pro rata Annex (Tracked) - Revision: 04 |  | Documents Reviewed: Deadline 7 Submission - C.1.1 Draft Development Consent Order (DCO) (Tracked); G7.2 Applicant’s comments on other submissions received at Deadline 6 - Revision: 01
F1 | 1, 2 & 20 | Natural England noted at RR that different threshold standards were used for different contaminants and not all data included in the technical report was copied into the ES. We seek further clarification on the use of different thresholds and more detail in the ES when stations exceeded thresholds. Neither the ES or technical report explores the potential source for the regionally elevated contaminants (particularly arsenic) and it would be useful to understand whether this is considered to be natural or anthropogenic in origin. |  |  | Natural England welcome the additional document provided by the Applicant (G1.44 Clarification note on marine sediment contaminants revision 1 [REP1-066] which helps clarify all contaminant levels and highlight where thresholds (CEFAS Action Levels and Canadian Marine Sediment Quality Guidelines) have been exceeded. It removes any concerns around inconsistencies in interpretation of the data tables and between the benthic ES chapter [APP-014] and the technical Annex [APP-068]. One example of exceedance which we were concerned about (PAH) appears to have been a typographic error. We welcome the additional information around source of Arsenic within the sediments and note that the levels are considered normal within the region. We do wish to seek clarification from the Applicant or Cefas on why the CAL1 thresholds haven't been used for PAH (limit of 0.1mg/kg). | [11 empty] | Natural England welcome the additional document provided by the Applicant (G1.44 Clarification note on marine sediment contaminants revision 1 [REP1-066] which helps clarify all contaminant levels and highlight where thresholds (CEFAS Action Levels and Canadian Marine Sediment Quality Guidelines) have been exceeded. It removes any concerns around inconsistencies in interpretation of the data tables and between the benthic ES chapter [APP-014] and the technical Annex [APP-068]. One example of exceedance which we were concerned about (PAH) appears to have been a typographic error. We welcome the additional information around source of Arsenic within the sediments and note that the levels are considered normal within the region. We do wish to seek clarification from the Applicant or Cefas on why the CAL1 thresholds haven't been used for PAH (limit of 0.1mg/kg). |  | No
F2 | 3, 12 & 20 | The ES does not provide an assessment as to whether there was any evidence the elevated contaminants (Arsenic & PAH & THC) were having an adverse effect on the baseline benthic community composition and structure, particularly within the ECC. In addition, more discussion is required to help fully assess the impact these contaminated sediments might have to the faunal community when disturbed as a result of construction activities given that a number of them exceed the Cefas Action Level 1 threshold or Canadian Marine Sediment Quality Guidelines. Natural England recommends this aspect is clarified by the Applicant. This will help to further inform whether the contaminants would be a cause for concern (or not) due to sediment disturbance and re-suspension impacts from construction activities. |  |  | Issue not addressed - Given the number of samples which exceed the recognised thresholds particularly within the ECC Natural England cannot agree with the generalisation (made in G1.44 Section 4.1.1.2) that the chemical composition of all the material being disturbed are typical of wider regional background. Natural England advises further review and expansion of data interpretation by the Applicant is needed to provide suitable evidence that despite the threshold exceedances, the chemical constituents within the ECC were not adversely affecting the faunal community at the time of the survey. For example linking the chemical and benthic fauna composition through description and expansion of the statistical analysis described in Paras 5.5.2.22 to 5.5.2.24 of the technical appendix [APP-068] or a check of the species recorded at stations with CEFAS exceedances against published sensitivities such reported as part of the MarsSEA MarLIN - The Marine Life Information Network - Species (A-Z), We note the latter was undertaken within the technical Annex for the Array area [APP-068], but not for the export cable corridor. A similar comment was made by the Applicants in response to our Relevant Representations RR-029- APDX:F-31 “Furthermore, the biotopes present within the array area and ECC are considered to be tolerant of chemical pressures, as presented within the MarESA assessment“. This may provide some level of reassurance that could be used as part of expert judgement in determining the likelihood that sediment disposal will result in adverse effects as concluded in Section 4.1.2.4 of the contaminant clarification note. |  | Natural England request additional evidence from the Applicant on the impact those sediments which exceed contamination thresholds have had on the baseline benthic communities to date. We are also seeking guidance from Cefas / MMO and what impact disturbing these contaminated sediments may have. We will update the Examining Authority at the next deadline. |  | The applicant has stated an update will be made to G1.44 Clarification Note on Marine Sediment Contaminants following Natural England’s contaminants comments and this will be submitted at Deadline 4. Natural England will review this in due course. Natural England agree with the approach proposed to look at published sensitivities from MarsSEA MarLIN against species recorded at stations. |  | Natural England acknowledges that a check against the Marlin MarSEA for species sensitivities at stations within the export cable corridor where contaminants exceeded the CEFAS action levels and Canadian ISQG's did not provide further supportive evidence. We welcome the further statistical analysis of the survey data for any trends in the faunal community assemblage linked with the elevated contaminants and the conclusion no apparent link is evident and therefore we are content that our original concern is addressed. However, we note that Action Level 1 is exceeded in a number of instances and defer to CEFAS/ MMO for any further comment on these exceedances in relation to disturbance and/or disposal of sediments as a result of construction activities. | [5 empty] | Natural England acknowledges that a check against the Marlin MarSEA for species sensitivities at stations within the export cable corridor where contaminants exceeded the CEFAS action levels and Canadian ISQG's did not provide further supportive evidence. We welcome the further statistical analysis of the survey data for any trends in the faunal community assemblage linked with the elevated contaminants and the conclusion no apparent link is evident and therefore we are content that our original concern is addressed. However, we note that Action Level 1 is exceeded in a number of instances and defer to CEFAS/ MMO for any further comment on these exceedances in relation to disturbance and/or disposal of sediments as a result of construction activities. |  | No
F3 | 13 | There is little evidence provided of the impact of direct and indirect seabed disturbances leading to the release of sediment contaminants (BIE-C-6) but the magnitude is concluded to be negligible which rules out the need to consider sensitivity. Addressing point 13 above will improve evidence of the impact. Natural England would encourage the ExA to seek advice from Cefas on possible impacts and significant of disturbing contaminated sediments as they have more expertise in this area. |  | Further clarification relating to the potential impacts of disturbing sediment bound contaminants is provided in G1.44 Hornsea Four Contaminated Sediments Clarification Note | We welcome the clarification note [REP1-066 ] Natural England would encourage the ExA to seek advice from Cefas on possible impacts and significance of disturbing contaminated sediments as they have more expertise in this area. | [7 empty] | Natural England’s only remaining concern relating to contamination is in relation to those where the level is between Cefas Action Level 1 & 2. Cefas have provided us with the following advice, which the ExA may wish to consider: ‘Results that fall between current UK AL1 and AL2 require further assessment for which we apply a weight of evidence approach. This includes looking at things such as regional differences), using the result in the context of the area to be dredged (are the results considered within range/similar to previous results found in the area), results of any monitoring from disposal sites and other non-chemical contamination considerations such as physical size distribution, final end use of the material, level of risk based on volume etc.’ |  | No change |  | Natural England’s only remaining concern relating to contamination is in relation to those where the level is between Cefas Action Level 1 & 2. Cefas have provided us with the following advice, which the ExA may wish to consider: ‘Results that fall between current UK AL1 and AL2 require further assessment for which we apply a weight of evidence approach. This includes looking at things such as regional differences), using the result in the context of the area to be dredged (are the results considered within range/similar to previous results found in the area), results of any monitoring from disposal sites and other non-chemical contamination considerations such as physical size distribution, final end use of the material, level of risk based on volume etc.’
F4 | n/a | Natural England queries the highlighted CEFAS Action level organotin exceedances (including two stations within the ECC above CEFAS Action Level 2) as these organotin exceedances were not previously reported in the technical annex [APP-068]. We recommend this is checked against the raw data by the Applicant as the data within the table suggests the measurement unit is mg/kg (ppm). The array report highlights that all concentrations were ≤1ng g (equivalent to µg/kg or ppb) at all stations. In contrast the CEFAS Action levels are reported in units of mg/kg (ppm). If the organotin concentrations reported within this clarification note are correct and CEFAS AL1 and AL2 are exceeded, Natural England would have concerns about environmental impacts during construction. This should be of note by the MMO in determining the suitability of sediments for disposal as this would not have been considered following their review of the benthic ES chapter and technical Annex. |  |  | This issue was new at deadline 2 after reviewing G1.44 Clarification Note on Marine Sediment Contaminants [REP1-066] |  | Natural England are seeking guidance from Cefas / MMO on this point as it was new information at Deadline 2. We will update the Examining Authority at the next deadline. |  | We note that the Applicant has committed to provide a revised version of G1.44 Clarification Note on Marine Sediment Contaminants at Deadline 4. We have highlighted a potential error in the labelling of Orgotins within Table 4 REP1-065 (G1.44 Clarification Note on Marine Sediment Contaminants Revision: 1) to the Applicant directly. |  | The Applicant has updated the Contaminant clarification note at Deadline 4. The organotin data is amended to below the Limit of Detection (LoD) at all stations. There are no concerns regarding organotins. This matter is now resolved. | [5 empty] | The Applicant has updated the Contaminant clarification note at Deadline 4. The organotin data is amended to below the Limit of Detection (LoD) at all stations. There are no concerns regarding organotins. This matter is now resolved. |  | Yes
F5 | 4 | It is noted that the geophysical data and DDV did not reveal the presence of Sabellaria aggregations (Annex I reef). However, as Sabellaria spinulosa individuals were the dominant taxon in grab samples at ECC Stations 17 to 21, the suitability of this substrate for the potential colonisation of Sabellaria should be considered for assessment as part of pre-construction surveys. If Sabellaria reef is encountered Natural England would wish to see the developer commit to micrositing around any patches of reef during both the construction and O&M phase as stated by Co48 and Co84. Consequently, this condition should be secured in the draft DCO/dML |  | The Applicant notes that the presence and dominance of S. spinulosa at these stations is recorded with Volume A5, Annex 2.1: Benthic and Intertidal Ecology Technical Report (APP- 068). Furthermore, according to Gubbay (2007), the numbers of S. spinulosa identified within the surveys is not considered high enough to quantify as an Annex I reef habitat or a Sabellaria reef biotope. Moreover, as detailed in Section 1.2 of Appendix A, Volume A5, Annex 2.1: Benthic and Intertidal Ecology Technical Report (APP-068), grab samples targeted the range of different sediments and depths observed in the geophysical study. The Applicant will conduct biogenic and geogenic reef surveys as part of pre-construction survey efforts, to identify any biogenic reef features and to enable micrositing around such features, if present. | Issue not addressed - Natural England wish to see Sabellaria reef considered for assessment due to Sabellaria spinulosa individuals being the dominant taxon in grab samples at ECC Stations 17 to 21, therefore the suitability of this substrate for the colonisation of Sabellaria reef is good and potential of the habitat high. |  | No Change - Natural England wish to see Sabellaria reef considered for assessment due to Sabellaria spinulosa individuals being the dominant taxon in grab samples at ECC Stations 17 to 21, therefore the suitability of this substrate for the colonisation of Sabellaria reef is good and potential of the habitat high. |  | No change |  | No change |  | Natural England believe that Sabellaria reef should have been considered within the ES assessment as the potential for this habitat to occur in the future at stations 17-21 is high (owing to the ephemeral nature of this habitat, individual species being present in samples and suitable substate type). Natural England note that the DCO overall makes provision to ensure that impacts to habitats of principal importance can be avoided during construction "where possible". In instances where micrositing to avoid the impact cannot be achieved, Natural England would like to see a commitment to explore further options to reduce or mitigate impacts and potentially monitoring as required. This could be secured by expanding condition 13 (1) (c) (ix) of Schedules 11 and 12 to include habitats of principal importance (as well as national sites i.e. MCZs, SSSIs and HPMAs). Natural England note that potential impacts to Priority Habitats during operation and maintenance activities has not been addressed. We would like to see a commitment to avoid/reduce/mitigate impacts to priority habitat as far as possible during the O&M phase, and a reference to this within the outline O&M plan. |  | No Change |  | Natural England welcomes the amendments to Condition 13 (1) c ix - provide 'means to address impacts on European sites , habitats of principal importance and any international or nationally designated sites, where relevant'. This addresses our concerns in realtion to impacts on protected species during construction. However potential impacts to Priority Habitats during operation and maintenance activities has not been addressed. We suggest a commitment to avoid/reduce/mitigate impacts to priority habitat as far as possible during the O&M phase, and a reference to this within the outline O&M plan. |  | No
F6 | 5 | The ES and Benthic Technical report should be expanded to further clarify the overall justification of ‘low’ grade Annex I stony reef against the Irving (2009) criteria. Stony reef does not have to be unbroken as stated in paragraph 2.7.1.36; a mosaic of stony reef and sediment also qualifies if the percentage of cover of cobbles and boulders is great enough to meet the criteria set by Irving (2009). There is evolving guidance on the justification of ‘low’ resemblance to stony reef topic and this should be kept under review for pre-construction surveys (Refining the criteria for defining areas with a ‘low resemblance’ to Annex I stony reef (JNCC Report No. 656)). The 2020 Stony Reef assessment revealed a range of stony reef classifications (from low to medium) at Stations ECC_22 and ECC_23. On a precautionary basis we query why this range was not cited rather than using the majority, particularly as a low confidence score was assigned to the acoustic data due to its quality. We note the approach of stating a classification range was used for the classification of Sea Pen and Burrowing megafauna community within the array report (see Section 2.2.1). Natural England also query why Annex I stony reef habitat was not carried forward as a Valued Ecological Receptor (VER) on a precautionary basis, as was undertaken for the sea-pen and burrowing megafauna habitat. For consistency we recommend Annex 1 stony reef habitat is included within the impact assessment. Natural England would also like commitments Co48 and Co84 expanded to include Annex I habitat (outside designated sites) with the potential to include stony reef, if qualifying examples were found in pre-construction surveys. These commitments should be secured in the draft DCO/dML. |  | The Applicant notes that the quality of the data from the dropdown video is not low. Moreover, this recorded data demonstrates that the stony substrata had a low resemblance to cobble reef in most instances. As a result, the assessment was therefore based on this data. 'Coarse and mixed sediments with moderate to high infaunal diversity and scour tolerant epibenthic communities' was carried through into the assessment, therefore, low grade stony reef is assessed ecologically. Annex I reef was not assessed based on the conclusions of the survey report. The Applicant can confirm that the foundations and cables will be micro-sited around habitats of principal importance wherever reasonably practicable and will be subject to agreement with the MMO. As per commitment Co84, benthic monitoring will be undertaken at pre-construction phases of the proposed development in order to determine the location, extent and composition of any habitats of principal importance (Section 41 of the 2006 Natural Environmental and Rural Communities (NERC) Act). In the event that habitats of principal importance are identified in the pre-construction survey; post-construction monitoring will also be carried out with a focus on these identified habitats. The Applicant will be undertaking a pre-construction survey to identify any areas of potential reef, and whilst this assessment is based on low grade reef The Applicant believes that it is proportionate based on the results of the Ocean Ecology survey which revealed that the majority of sites across each transect were low quality reef. However, a thorough review of stony reef habitat will be reassessed at pre-construction. | We have an outstanding concern relating to how examples of stony reef (outside a designated site) would be categorised in relation to 'habitats of principle importance' and at what 'grade' examples of stony reef would be micro sited around in relation to Co48 & Co84. We still query why stony reef data points were not cited as a range (low to medium) where datapoints within a polygon found both low and medium reef examples. The applicant has also not answered our query with regards to stony reef being carried forward as a Valued Ecological Receptor (VER). We would also welcome clarity as to the status of the Commitments Register and if and how commitments may be enforced post consent. |  | No Change - We have an outstanding concern relating to how examples of stony reef (outside a designated site) would be categorised in relation to 'habitats of principle importance' and at what 'grade' examples of stony reef would be micro sited around in relation to Co48 & Co84. |  | The applicant has confirmed that examples of medium or high stony reef will be micro-sited around as per Co48 & Co84. To alleviate Natural England's concerns moving forward with regards to our confidence in the classification of stony reef, we request that Natural England be consulted on survey design of pre construction benthic surveys to ensure most up to date guidance is being followed when identifying examples of stony reef and that this specific point is captured appropriately within the DCO/dML and/or relevant certified documents. |  | Whilst there is no change with regard to the proposal Natural England put forward at deadline 4, we wish to provide this additional statement. With regard to our comment at deadline 4 Re 'ensure up to date guidance is being followed when identifying examples of stony reef' Natural England would like to highlight the 2022 JNCC paper on 'Refining the criteria for defining areas with a ‘low resemblance’ to Annex I stony reef' in particular section 8 (refinement of guidance) which should be considered alongside Irvine 2009 paper. The work includes biota as an important characteristic to be assessed in any stony reef surveys. This paper also states 'if the majority of the four criteria exceed ‘low’, then this strong justification could result in classifying the area as having a ‘medium resemblance’ to Annex I stony reef'. |  | The Applicant has confirmed that the pre-construction monitoring plan (secured under Condition 17 of Schedules 11 and 12 of the DCO (REP5-088)) will consider the latest guidance in relation to the identification of stony reef and that Natural England will be consulted on that plan prior to the pre-construction surveys. Natural England welcome the commitment to microsite around habitats of principal importance (as identified under NERC 2006) wherever possible during the construction phase, whilst highlighting that this commitment will only reduce the risk of impacts to these features rather than remove it completely. In instances where micrositing to avoid the impact cannot be achieved, Natural England would like to see a commitment to explore further options to reduce or mitigate impacts and potentially monitoring as required. This could be secured by expanding condition 13 (1) (c) (ix) of Schedules 11 and 12 to include habitats of principal importance (as well as national sites i.e. MCZs, SSSIs and HPMAs). Natural England note that potential impacts to Habitats of Principal Importance during operation and maintenance activities have not been addressed. We would like to see a commitment to avoid/reduce/mitigate impacts to priority habitat as far as possible during the O&M phase, and a reference to this within the outline O&M plan. |  | No Change |  | See F5 above. |  | No
F7 | 21 | Natural England request to see the raw data behind the stony reef assessment and each score given to the 4 categories of reefiness to fully understand the justification of low grade reef being assigned. The technical report shows that within the area delineated at Station ECC_23, ‘medium’ resemblance to stony reef was classified for two of the four fixes, and the area classified overall as ‘low’ resemblance to stony reef. At Station ECC_22 for one of the areas assessed overall as ‘low’ resemblance Annex I stony reef there were two fixes recording ‘medium’ resemblance to stony reef separated by approximately 10m. |  | The Applicant notes that Appendix D8 of Volume A5, Annex 2.1: Benthic and Intertidal Ecology Technical Report (APP-068)) provides a detailed review of the raw data which provides evidence for the classification process. This guidance also suggests “When determining whether an area of seabed should be considered as Annex I stony reef, it a ‘low’ is scored in any of the four characteristics (composition, elevation, extent or biota), then a strong justification would be required for this area to be considered as contributing to the Marine Natura Site Network of qualifying reefs in terms of the EU Habitats Directive.” This suggests that the patches identified during this survey would not necessarily be considered to be contributing to the Marine Natura Site Network unless there is strong justification. it is unlikely that any impacts associated with the installation of the proposed Hornsea Project Four export cable route will be of any significance in the context of the Marine Natura Site Network. | Natural England have been given access to the raw data behind the Stony reef assessment and will interrogate it further to provide confidence the data has been classified correctly |  | Natural England have been given access to the raw data behind the Stony reef assessment and will interrogate it further to provide confidence the data has been classified correctly |  | Natural England have concerns with regards to our confidence in the classification of stony reef by the applicant. To alleviate Natural England's concerns moving forward with regards to our confidence in the classification of stony reef, we request that Natural England be consulted on survey design of pre construction benthic surveys to ensure most up to date guidance is being followed when identifying examples of stony reef and that this specific point is captured appropriately within the DCO/dML and/or relevant certified documents. Goulding et al, 2020, Refining the criteria for defining areas with a ‘low resemblance’ to Annex I stony reef, JNCC Report 656 |  | Natural England have been given access to the Raw data and reviewed this. We made comment at deadline 4 with regard to a way forward with regards to our concerns with reef classification i.e. that we wish to be consulted on pre-construction survey design to ensure that appropriate guidance is being followed in order to avoid any unnecessary delays in the discharge of conditions. There is no further comment from the applicant yet. See F6 |  | Natural England have now been given access to the Raw data. As per F6 above, The Applicant has confirm that the pre-construction monitoring plan (secured under Condition 17 of Schedules 11 and 12 of the DCO (REP5-088)) will consider the latest guidance in relation to the identification of stony reef and that Natural England will be consulted on that plan prior to the pre-construction surveys. Natural England are therefore content to close out this issue, noting that the issue above (F5) relating to commitments around habitats of principle importance may apply if examples of medium / high stony reef are found to be present. |  |  |  | Natural England have now been given access to the Raw data. As per F6 above, The Applicant has confirm that the pre-construction monitoring plan (secured under Condition 17 of Schedules 11 and 12 of the DCO (REP5-088)) will consider the latest guidance in relation to the identification of stony reef and that Natural England will be consulted on that plan prior to the pre-construction surveys. Natural England are therefore content to close out this issue, noting that the issue above (F5) relating to commitments around habitats of principle importance may apply if examples of medium / high stony reef are found to be present. |  | Yes
F8 | 6 | The jack up vessel (JUV) footprint is on all occasions twice the value presented in the Volume 4, Annex 4.9: Pro-rata Annex. However, from descriptions in the text it appears to be correct in Table 2.12 and probably incorrect in Pro-Rata Annex. This was raised in our comments on the draft ES in November 2020 |  |  | Applicant has clarified that the values in Pro Rata Annex (APP-047) is per foundation type and the installation of foundation only whereas the figure in ES benthic chapter (APP-014) is footprint for entire WTG. | [11 empty] | Applicant has clarified that the values in Pro Rata Annex (APP-047) is per foundation type and the installation of foundation only whereas the figure in ES benthic chapter (APP-014) is footprint for entire WTG. |  | Yes
F9 | 7 | As raised on previous draft versions of the ES the highest proportion of temporary habitat disturbance in the Hornsea 4 array area and offshore ECC comes from boulder and sandwave clearance, which correspond to almost 80% of total temporary disturbance. In light of Paragraph 2.6.196 of NPS EN-3, which states that “The methods of construction, including use of materials should be such as to reasonably minimise the potential for impact on the physical environment”, it seems appropriate to reduce the MDS and provide a more accurate estimate of sandwave and boulder clearance. Geophysical data – either project specific or otherwise - should be used to refine this assessment to a more realistic area. Natural England note that the Applicant has undertaken geophysical survey work in 2021. These data should be used to update the assessment and refine the DCO parameters. |  |  | Natural England notes that the Applicant is preparing a Clarification Note on the Justification of Offshore Maximum Design Scenarios will be submitted at Deadline 3. |  | We are awaiting the outcome of the review of the Maximum Design Scenario Note expected at Deadline 3. |  | No Change - Natural England welcome the submission of paper G3.6 Justification of Maximum Design Scenarios. However, we note the area subject to bedform clearance (sandwaves and boulders) remains unchanged. This means there has been no change in the extent of temporary habitat disturbance which Natural England do not agree can be defined as 'minor'. |  | No change |  | Natural England remain concerned that the MDS includes provision for sandwave clearance along the full length of the cable corridor. This results in a MDS of a large area subject to temporary habitat disturbance. We understand the applicant's reluctance to specify precise locations for sandwave clearance given the inherent variability of the marine environment, and the mobile nature of these bedforms. However, similar projects have been able to refine their MDS based on the proportion of the cable corridor that is likely to require sandwave clearance rather than basing the MDS on the overly precautionary /unrealistic assumption that the entire cable corridor will require sandwave clearance. The applicant has made it clear that they do not intend to make any further revisions within the examination timescales. We therefore refer this matter to the Examining Authority for further consideration in the context of paragraph 2.6.196 of NPS EN-3 (see column C). Natural England note that the commitment to exclude sandwave levelling from the Smithic Bank area should reduce the risk of impact to nearby benthic receptors (i.e. Holderness Inshore MCZ, Flamborough Head SAC/SSSI). However, the same cannot be said to be true for Holderness Offshore MCZ and the potential for impacts to priority habitat identified under NERC 2006. Therefore as per F5 and F6 above, we would like to see consideration of the potential impacts of all site preparation works on European Sites, National Sites and Priority Habitats included within the DCO/dML. |  | No Change |  | The Applicant has followed our suggestion and included consideration of habitats of principal importance and any international or nationally designated sites sites within Consition 13 1 c ix of sechedule 11 & 12 providing some mitigation to impacts on nationally designated sites. Natural England remain concerned that the MDS includes provision for sandwave clearance along the full length of the cable corridor. This results in a MDS of a large area subject to temporary habitat disturbance. We understand the applicant's reluctance to specify precise locations for sandwave clearance given the inherent variability of the marine environment, and the mobile nature of these bedforms. However, similar projects have been able to refine their MDS based on the proportion of the cable corridor that is likely to require sandwave clearance rather than basing the MDS on the overly precautionary /unrealistic assumption that the entire cable corridor will require sandwave clearance. The applicant has made it clear that they do not intend to make any further revisions within the examination timescales. We therefore refer this matter to the Examining Authority for further consideration in the context of paragraph 2.6.196 of NPS EN-3 (see column C).
F10 | 8 | The total maximum area of temporary loss/disturbance of subtidal habitat due to construction activities is predicted to be up to approximately 75.9 km2 (16% of the total seabed area). Natural England feel that the definition of magnitude does not align with the levels of disturbance being described here. The impact in this case is temporary ( as evidence suggests recovery), but Natural England would argue that 75km2 can’t be considered a minority of the receptor and with this in mind magnitude should be higher, which would in turn impact the significance of the effect. However, we acknowledge that these figures are based on MDS and a precautionary approach has been taken when calculating these, therefore impacted area should be smaller. Natural England recommend refining the MDS as the project develops (as mentioned above in point 7) to ensure impacts to the benthic environment are recorded as accurately as possible. This will help assess future projects fairly when cumulative assessments are conducted. |  | It should be noted that this is the greatest spatial area which may be impacted in accordance with the Rochdale Envelope approach. The Applicant maintains that the temporary habitat disturbance will represent a local spatial extent, short term intermittent impact, affecting a relatively small portion of the benthic subtidal habitats in the Hornsea Four Order Limits. As a result, the Applicant maintains that an assessment of minor magnitude is valid. | Natural England notes that the Applicant is preparing a Clarification Note on the Justification of Offshore Maximum Design Scenarios will be submitted at Deadline 3. |  | We are awaiting the outcome of the review of the Maximum Design Scenario Note expected at Deadline 3. |  | No Change - The review of MDS has not resulted in a reduction to sandwave clearance area and therefore the total maximum area of temporary loss / disturbance remains unchanged. Natural England do not believe 75km2 can be considered a minority of the receptor. |  | No change |  | In the ES the Applicant has submitted a large area to be subject to temporary habitat disturbance (MDS) and assessed this as being minor in magnitude. Natural England do not feel this impact fits into either minor or moderate magnitude definition. The implication of this is that the significance of overall impacts may be under or overestimated. Natural England have not previously agreed these definition on other projects but rather have disputed individual impacts where we disagreed with overall assessment conclusions. Natural England do not believe this issue can be resolved within the remaining examination timelines as adjusting magnitude would require new impact assessments across the chapter. We also aknowledge that our concerns related to this approach have applicability beyond Hornsea Four. We wish to highlight this point for consideration by the ExA and the Secretary of State when making a final decision. |  | No change |  | In the ES the Applicant has submitted a large area to be subject to temporary habitat disturbance (MDS) and assessed this as being minor in magnitude. Natural England do not feel this impact fits into either minor or moderate magnitude definition. The implication of this is that the significance of overall impacts may be under or overestimated. Natural England have not previously agreed these definition on other projects but rather have disputed individual impacts where we disagreed with overall assessment conclusions. Natural England do not believe this issue can be resolved within the remaining examination timelines as adjusting magnitude would require new impact assessments across the chapter. We also aknowledge that our concerns related to this approach have applicability beyond Hornsea Four. We wish to highlight this point for consideration by the ExA and the Secretary of State when making a final decision.
F11 | 9 | It is not clear how all the habitats within 14km of the order limits are considered in the assessment of significance of impact, as data and biotope information has not been collected within this area. There may be habitat within 14km that differ from those presented in this report in relation to habitats found in ECC and array area and therefore sensitivities may be different. The developer should make it clear what evidence has been used for assessments of impacts outside the order limits, whether this be modelled habitat maps or expert judgement, in order to help give the reader confidence in any assessments of impacts being made. |  | As presented in Section 1.2 of Volume A5, Annex 2.1: Benthic and Intertidal Ecology Technical Report (APP-068), using existing data, including benthic subtidal grab data from former Hornsea Zone, other Hornsea projects and Dogger Bank A and B Offshore Wind Farms (Dogger Bank A & B), together with publicly available information, new data collected specifically for Hornsea Four and benthic habitat modelling, the objective was to develop a robust baseline description of the subtidal benthic and intertidal resources within the Hornsea Four Order Limits and surrounding area. In addition to this, the habitat model (Figure 2.4 to Figure 2.7 of Volume A2, Chapter 2: Benthic and Intertidal Ecology (APP-014)) revealed the biotopes across the site, particularly in the offshore section of Hornsea Four benthic subtidal ecology study area. Therefore, it is the Applicant’s position that there is adequate information for the purposes of baseline characterisation for benthic ecology | We note the applicant's position that there is adequate information for the purposes of baseline characterisation of benthic ecology, however our question was in relation to the assessment of significance in the area outside the order limits and what this was based on, which we do not feel has been addressed. | [11 empty] | We note the applicant's position that there is adequate information for the purposes of baseline characterisation of benthic ecology, however our question was in relation to the assessment of significance in the area outside the order limits and what this was based on, which we do not feel has been addressed. |  | No
F12 | 10 | Flamborough SAC and Holderness Offshore MCZ are close to the cable route and therefore could be affected by higher levels of SSC and deposition. Natural England recommend referring to the assessment carried out in B2.2: Report to Inform Appropriate Assessment Part 1 (10.2.3.8) and A5.2.3 Marine Conservation Zone Assessment (Section 7) when describing the effect of increased suspended sediment and deposition from the ECC on the nearby protected sites, rather than dismissing the impacts as minor. |  | This is noted by the Applicant. | This issue has been noted by the applicant but it is not clear if/how it will be addressed. |  | No change. |  | No Change - Natural England is expecting additional information to be submitted by the applicant during the examination to support this issue however, a timeline for this has not been provided. |  | No Change - Natural England is expecting additional information to be submitted by the applicant during the examination to support this issue however, a timeline for this has not been provided. |  | In G3.17 the Applicant stated it would provide additional information and contextualisation within A2.2 Benthic and Intertidal Ecology (APP-014) with references to information in B2.2 & A5.2.3, as per Natural England's advice. However this has not been submitted into examination as of D5a. Natural England have reviewed the relevant sections of B2.2 & A5.2.3 and do not feel any information here will make a material difference to the outcomes of the impact assessments therefore we will be content to close out this issue, assuming the relevant updated will be submitted into Examination at D6. |  |  |  | In G3.17 the Applicant stated it would provide additional information and contextualisation within A2.2 Benthic and Intertidal Ecology (APP-014) with references to information in B2.2 & A5.2.3, as per Natural England's advice. However this has not been submitted into examination as of D5a. Natural England have reviewed the relevant sections of B2.2 & A5.2.3 and do not feel any information here will make a material difference to the outcomes of the impact assessments therefore we will be content to close out this issue, assuming the relevant updated will be submitted into Examination at D6. |  | No
F13 | 11 | Here it is stated that ‘The communities associated with subtidal chalk reef habitat, which is a protected feature of the Flamborough Head SAC are expected to have some tolerance to increases in SSC (De-Bastos and Hill 2016c; Tillin and Hill 2016), particularly as these habitats are near the coast, where background SSC levels are highest. Sensitivity of many animals associated with soft rock habitats to light sediment deposition would also be expected to be limited, due to the resilience of some characterising species (De-Bastos and Hill 2016c) and the natural sediment mobility in these areas.’ Natural England advises that the sensitivity of designated features within MPAs should be taken from the relevant conservation advice package and associated advice on operations, rather than wider references. |  | It is the Applicant’s position that it is appropriate to cite and base assessment on relevant peer-reviewed literature. The Applicants notes that the conservation advice package by Natural England on Flamborough Head SAC noted moderate sensitivity to smothering from the disposal of dredged soils and a moderate–high sensitivity to siltation from dredging. However, due to the location of Hornsea Four ECC (1.2 km away), it is not anticipated to result in a significant impact on Flamborough Head SAC. In addition, indirect impacts using a 10 km tidal excursion have been screened into the assessment on a precautionary basis (Table 2.9 of Volume A2, Chapter 2, Benthic and Intertidal Ecology (APP-014)) and a moderate sensitivity was used in the assessment, based on peer-reviewed literature and the MarESA assessment. | Natural England notes the Applicant's response, however, whilst we welcome the use of supplementary evidence we continue to maintain that assessment of impacts to features within MPAs should refer to the conservation advice and associated advice on operations for that feature. |  |  |  | The Applicant will provide additional information and contextualisation within A2.2 Benthic and Intertidal Ecology (APP-014) referring to the conservation advice and associated advice on operations for the feature of the Flamborough Head SAC. The update will be submitted during examination. | [7 empty] | The Applicant will provide additional information and contextualisation within A2.2 Benthic and Intertidal Ecology (APP-014) referring to the conservation advice and associated advice on operations for the feature of the Flamborough Head SAC. The update will be submitted during examination. |  | No
F14 | 14 | Natural England have previously commented on a draft version of this ES chapter in November 2020 and did not agree with the assessment of magnitude for ‘long-term habitat loss/ change’ due to the use of the term ‘high reversibility’ concluding negligible magnitude. The magnitude has been re-assessed as minor and acknowledgment made that some infrastructure will be permanent. However Natural England still question if this is the most appropriate term given than the definition for minor is ‘discernible, temporary change’. We appreciate that the definition ‘moderate’ magnitude (Considerable, permanent / irreversible changes, over the majority of the receptor) is also not appropriate for this scenario as it is not affecting the majority of the receptor. Therefore, it seems to fit neither category well. Natural England wish to have more discussion with the developer on this issue and request further scientific justification or refinement of the magnitude of impact. |  | This is noted and the Applicant will continue to actively engage with Natural England through the SoCG process in relation to the issues raised in the representation | The Applicant has stated that they will continue to actively engage with Natural England through the SoCG process in relation to the issues raised in the representation. An updated SoCG is due to be submitted at Deadline 3. |  | No progress has been made on this issue yet. |  | No Change |  | No change |  | Natural England feel that the definitions of magnitude used in the ES are too broad and without a suitable incremental step between minor and moderate. For example, an impact of permanent nature but over a minority of the site/receptor doesn’t fit into either category well. There is also no incremental step between minority or majority of receptor. The implication of this is that the significance of impacts may be over or under estimated. Natural England have not previously agreed these definition on other projects but rather have disputed individual impacts where we disagreed. Natural England do not believe this issues can be resolved within the remaining examination timelines as adjusting magnitude would require new impact assessments across the chapter. We also acknowledge that our concerns related to this approach have applicability beyond Hornsea Four. We wish to highlight these points for consideration by the ExA and Secretary of State when making a final decision. |  | No change |  | Natural England feel that the definitions of magnitude used in the ES are too broad and without a suitable incremental step between minor and moderate. For example, an impact of permanent nature but over a minority of the site/receptor doesn’t fit into either category well. There is also no incremental step between minority or majority of receptor. The implication of this is that the significance of impacts may be over or under estimated. Natural England have not previously agreed these definition on other projects but rather have disputed individual impacts where we disagreed. Natural England do not believe this issues can be resolved within the remaining examination timelines as adjusting magnitude would require new impact assessments across the chapter. We also acknowledge that our concerns related to this approach have applicability beyond Hornsea Four. We wish to highlight these points for consideration by the ExA and Secretary of State when making a final decision.
F15 | 15 | Natural England advise that the following two impacts should not have been excluded from the CEA based on Hornsea 4 alone not leading to significant impacts. These two impacts have been assessed as ‘negligible’ where the methodology states they could be excluded from the CEA. Natural England believe a CEA should be carried out for these two impacts (appreciating it will probably conclude ‘not significant’),or provide further detail to justify the exclusion of these potential cumulative impacts • Construction phase: - Direct and indirect seabed disturbances leading to the release of sediment contaminants: the potential significance of the impact from Hornsea 4 alone has been assessed as not significant. • Operation and maintenance phase - Increased risk of introduction or spread of MINNS due to presence of subsea infrastructure and vessel movements (e.g., ballast water) may affect benthic ecology and biodiversity: the potential significance of the impact from Hornsea 4 alone has been assessed as not significant |  | It is the Applicant’s position that the assessments for both the project alone and the CEA remain valid. Those impacts for the project alone which have concluded negligible magnitudes, and so no significant effects in EIA terms, it was not considered proportionate to assess cumulative effects. | Issue not addressed - We do not agree with the methodology that impacts assessed as negligible alone do not need to be considered in an 'in-combination' assessment. Natural England still believe further justification for excluding these impacts should be provided or they should be carried forward to CEA assessment as it is important that the combined effects are fully explored. |  | Issue not addressed - We do not agree with the methodology that impacts assessed as negligible alone do not need to be considered in an 'in-combination' assessment. Natural England still believe further justification for excluding these impacts should be provided or they should be carried forward to CEA assessment as it is important that the combined effects are fully explored. Also see issue F2 requiring further certainty that contaminated sediments will not have an effect on Benthic communities. |  | No Change |  | No change |  | Strategically, we believe a better approach to assessing cumulative affects needs to be considered for impacts which might be considered negligible under the current definition. There is an increasing number of large OWF projects proposed across the North Sea and negligible impacts will start to add up. We wish to highlight these points for consideration by the ExA and Secretary of State. |  | No change |  | Strategically, we believe a better approach to assessing cumulative affects needs to be considered for impacts which might be considered negligible under the current definition. There is an increasing number of large OWF projects proposed across the North Sea and negligible impacts will start to add up. We wish to highlight these points for consideration by the ExA and Secretary of State.
F16 | 16 | Natural England does not believe there is sufficient information or evidence available on the Endurance Carbon Capture project to reach the anticipated conclusion that there would be no significant impact. The Applicant admits there is limited detail on the project at this time, and it is not possible to make a detailed assessment. Natural England would like the assessment to acknowledge that there may be overlap with the construction phase of the Endurance Carbon Capture project and Hornsea 4 as the timelines provided are very tight in relation to consent and start of construction. There is also no acknowledgment (in this report or the Annex 3.5 Offshore cumulative effects) that the two projects overlap in spatial extent, which can only magnify the impacts. Natural England require the assessments of impacts in combination with the Endurance Carbon Capture project to be reviewed at a later date when more information is available. The same concerns are also relevant to section 2.13.2.22 relating to cumulative impacts of suspended sediment and 2.14.1.14 with respect to long term habitat loss. |  | The Applicant highlights that no planning application has been submitted in relation to the offshore elements of the Endurance Carbon Capture and Storage (CCS) project and as such, there is limited information available to base assessment on, and this project should remain in Tier 3 of cumulative assessment. The Applicant considers that the assessment on Endurance CCS has followed the guidance set out in PINS Advice Note 17 (Cumulative effects assessment relevant to nationally significant infrastructure projects) which states “For ‘other existing development and/or approved development’ falling into Tier 3, the applicant should aim to undertake an assessment where possible, although this may be qualitative and at a very high level.” The Applicant acknowledges that cumulative assessments may need to be updated if further details on the Endurance CCS are submitted to planning authorities. | Natural England welcomes the applicants commitment to update the cumulative assessment if and when new information comes forward on this project to the planning inspector. The Endurance Carbon Capture project has submitted an EIA scoping document to the MMO in September 2021 for the project therefore it should now be considered a Tier 2. It is unclear if the information from the scoping document has been captured in the assessment. |  | We would appreciate it if the Applicant could confirm what information has been used to assess the cumulative impacts from the Endurance Carbon capture project. |  | Natural England welcome that the Applicant is reviewing details from the Northern Endurance Partnership project offshore EIA Scoping Report and that consideration is being given to the update of cumulative assessments within a future Examination submission. We will review when provided. |  | No update from the applicant available yet |  | The Applicant has reviewed the information presented within the NEP Scoping Report. They have confirmed that it contains no details over and above what was available at the time of writing the ES (ExQ ES.2.2). Therefore the Applicant’s position is that it is not possible to undertake more detailed cumulative effects assessments (CEA). Natural England welcome this confirmation. However, Natural England considers that there is a potential risk of cumulative impacts as a result of these projects constructing and operating within similar timeframes. Therefore should NEP make an application prior to the determination of this case, Natural England advise that the cumulative impacts will need to be assessed, including within the HRA. |  | No change |  | The Applicant has reviewed the information presented within the NEP Scoping Report. They have confirmed that it contains no details over and above what was available at the time of writing the ES (ExQ ES.2.2). Therefore the Applicant’s position is that it is not possible to undertake more detailed cumulative effects assessments (CEA). Natural England welcome this confirmation. However, Natural England considers that there is a potential risk of cumulative impacts as a result of these projects constructing and operating within similar timeframes. Therefore should NEP make an application prior to the determination of this case, Natural England advise that the cumulative impacts will need to be assessed, including within the HRA.
F17 | 17 | The nearshore ECC area is busy with Bridlington A disposal site (2.7km away) and construction and operation of Dogger A&B export cable leading to high levels of suspended sediments in the water column. Natural England query if cumulative effects of suspended sediment from these 3 projects in the ECC areas can still be quantified as minor in magnitude |  | It is the Applicant’s position that the findings of the assessment remain valid and there would not be any significant cumulative effects in EIA terms. This position is owing to the planned construction for Dogger Bank A and B cables between 2021 and 2024. The earliest possible date for the start of the construction of Hornsea Four is early 2024. It is therefore likely that the installation of Hornsea Four’s export cable will be following the completion of Dogger Bank A and B export cables. Moreover, only a small portion (approximately 4%) of the Dogger Bank A and B export cables intersects with the Hornsea Four benthic subtidal ecology study area, and therefore the maximum amount of sediment released cumulatively with Hornsea Four will be considerably less. It should also be noted that the worst-case scenario for the projects (Hornsea Four, Dogger Bank A and B) assumes that the whole volume of sediment from the excavated trenches for the export cables is released for dispersion regardless of the extraction method used and therefore the amount that is released is likely to be of a lower volume. As such, The Applicant considers that a minor magnitude is appropriate. | Natural England welcomes the additional context provided by the Applicant. |  | No further comments | [9 empty] | Natural England welcomes the additional context provided by the Applicant. |  | No
F18 | 18 | As per point F14 above Natural England has concerns over the term ‘minor’ being used to assess magnitude of the long-term habitat loss/change alone and in-combination with other projects. The term ‘minor’ does not account for the permanent nature of these effects and in turn a ‘slight’ effect (not significant in EIA terms) is very subjective. The area affected within the CEA is 15.36km2 (5 times that of Hornsea Project Four in isolation). The same can be said for impacts associated with colonisation of WTG (2.14.1.19) Natural England wish to have more discussion with the developer on this issue and request further scientific justification or refinement of the magnitude of impact |  | This is noted and the Applicant will continue to actively engage with Natural England through the SoCG process to seek to resolve the issues raised in the representation. | The Applicant has stated that they will continue to actively engage with Natural England through the SoCG process in relation to the issues raised in the representation. An updated SoCG is due to be submitted at Deadline 3. |  | No progress has been made on this issue yet. |  | No Change |  | No change |  | As with F14, Natural England feel that the definitions of magnitude used in the ES are too broad and without a suitable incremental step between minor and moderate. For example, an impact of permanent nature but over a minority of the site/receptor doesn’t fit into either category well. There is also no incremental step between minority or majority of receptor. Again, we highlight the implication of this is that the overall impact may be over or underestimated. Natural England have not previously agreed these definition on other projects but rather have disputed individual impacts where we disagreed. Natural England do not believe this issue can be resolved within the remaining examination timelines as adjusting magnitude would require new impact assessments across the chapter. We also acknowledge that these concerns with this approach have applicability beyond Hornsea Four. We wish to highlight these points for consideration by the ExA and Secretary of State when making a final decision. |  | No change |  | As with F14, Natural England feel that the definitions of magnitude used in the ES are too broad and without a suitable incremental step between minor and moderate. For example, an impact of permanent nature but over a minority of the site/receptor doesn’t fit into either category well. There is also no incremental step between minority or majority of receptor. Again, we highlight the implication of this is that the overall impact may be over or underestimated. Natural England have not previously agreed these definition on other projects but rather have disputed individual impacts where we disagreed. Natural England do not believe this issue can be resolved within the remaining examination timelines as adjusting magnitude would require new impact assessments across the chapter. We also acknowledge that these concerns with this approach have applicability beyond Hornsea Four. We wish to highlight these points for consideration by the ExA and Secretary of State when making a final decision.
F19 | 19 | There is a typo in Table 2.24 under Long-term habitat loss/ change from the presence of foundations, scour protection and cable protection (BIE-O-8) where residue impact is assigned ‘Not significant’, however in the main body of the report (2.11.2.9) it is assigned slight significance, |  | It is understood that the residual impact cited by Natural England for BIE-O-8 is a typographic error and should be ‘Slight significance (not significant in EIA terms)’. | The applicant has clarified that this is a typographic error. | [11 empty] | The applicant has clarified that this is a typographic error. |  | Yes
F20 | 22 | Natural England wish to highlight the subjective nature of habitat classification. The biotopes mapped (Figure 11) at the boundary of the ECC and Array area reveal two distinct biotopes A5.242 & A5.261. These differences could be related to data being collected during different surveys and analyses undertaken by separate contractors. The geophysical sediment delineation and PSA data are essentially similar. Had the two survey data sets been considered as a whole, classification may have been different. |  | The Applicant notes that paragraph 2.7.5.3 of Volume A2, Chapter 2, Benthic and Intertidal Ecology (APP-014) has stated that biotopes presented “should not be considered as definitive”. The habitats presented, however, “represent a robust characterisation of the receiving environment”. In addition, the data collected and collated by the contractors was thoroughly assessed prior to inclusion in the ES. | We note the Applicant's position. |  | No further comments. | [5 empty] | Position unchanged from Relevant Reps and remains for the ExA's consideration. |  | No change |  | Position unchanged from Relevant Reps and remains for the ExA's consideration.
Document used: F2.15: Outline Offshore Cable Installation Plan
F21 | 23 | Within the Sandwave clearance plan, location information should include area of impact and volume of sandwave clearance at clearance and disposal locations. Information should also be clearly provided on habitats impacted and comparison of plans to ES predictions. |  | The Applicant notes that the Outline Cable Installation Plan states that the following details will be considered: · Details of locations where sandwave clearance is required to install cable below reference seabed level; · Expected volumes of sediment to be dredged and disposed, if relevant; · Proposed locations for disposal, if relevant, including: o Consideration of Habitats of principal importance (Section 41 of the 2006 Natural Environment and Rural Communities (NERC) Act; o Consideration of Archaeological Exclusion Zones (AEZ); and o Proximity to dredge location. The Applicant notes that the Cable Specification and Installation Plan is conditioned in the DML and will be submitted to and approved in writing by the MMO and as such, should provide comfort that the details requested will be included. | The information highlighted by the Applicant is in relation to things to 'consider within the consultation' of the cable installation plan document rather than stating they will be in included in the plan itself. Natural England does not see where the requested details relating to sandwave clearance extent and location information are included within the DML. If it can be demonstrated that this information is captured within the DML or associated document then Natural England would be content to close out this issue. |  | No change - The information highlighted by the Applicant is in relation to things to 'consider within the consultation' of the cable installation plan document rather than stating they will be in included in the plan itself. Natural England does not see where the requested details relating to sandwave clearance extent and location information are included within the DML. If it can be demonstrated that this information is captured within the DML or associated document then Natural England would be content to close out this issue. |  | The Applicant has confirmed that the Construction Method Statement (secured by Condition 13(c) of Schedules 11 and 12 of C1.1: Draft DCO including draft DMLs (REP2-061)) must provide details on ‘foundation installation methodology, including drilling methods and disposal of drill arisings and material extracted during seabed preparation for foundation and cable installation works’. As such the Applicant considers that Natural England’s request for sandwave clearance information is appropriately captured within the DML. However, this document will be submitted post consent and therefore does not aid the assessment of these impacts pre application. Consequently we do not consider this sufficient to address our concerns. |  | No change |  | Natural England still have concerns and have been unable to fully assess the impact of sandwave clearance, as information on the area impacted by this activity will not be available until the post-consent phase within the Offshore Cable Installation Plan. See F6 for further details. |  | No change |  | Natural England still have concerns and have been unable to fully assess the impact of sandwave clearance, as information on the area impacted by this activity will not be available until the post-consent phase within the Offshore Cable Installation Plan. See F6 for further details. |  | No
Document Used: Volume A4.4.4: Dredging and Disposal (Site Characterisation)
F22 | 24 | Huge volumes of spoil requiring disposal are predicted to be produced across the array area and ECC from seabed preparation, drilling and cabling. However, there is no MDS calculation of area which will be affected by disposal of this material, either in terms of temporary habitat loss from smothering or change in substrate type (should particle size be significantly different). We request the Applicant provide this to allow impacts to be fully assessed. |  | The Applicant notes that Section 7.1.3 of Volume A4.4.4: Dredging and Disposal Site Characterisation (APP-042) provides an assessment of the dispersal of drilled and dredged material and the impact of the disposal of this material. | Issue not addressed - The Applicant has suggested that an assessment is provided in Section 7.1.3 of Volume A4.4.4 (APP-042) however this refers to effects of sediment plumes with no references to impacts once sediment settles. Natural England would like to see extent figures estimating the area affected by the settlement of sediment plumes. |  | No change - Natural England would like to see extent figures estimating the area affected by the settlement of sediment plumes. |  | The Applicant has confirm that further consideration is being given to the impact of drill arisings and settled sediment plumes with a clarification note due to be submitted into Examination at Deadline 5. Natural England will review this in due course. |  | Natural England are waiting for documentation to be submitted at deadline 5 to progress this issue |  | G5.5 Clarification Note on drill arising and deposition of sediments (REP5-083) provides a figure for the footprint which will be affected by light smothering (<5cm) as a result of sediment disposal activities. This is predicted to be 26 km2 in the export cable and 48 km2 in the array area (10% & 9% of Array and ECC). Heavy smothering (5-30 cm as defined by the Marlin MarESA assessment) will occur over a total maximum footprint of 4 km2 in the export cable and 8 km2 in the array area (1% & 2%). The report goes on to conclude that based on the available evidence, the predicted MDS for sediment deposited is consistent with the evidence present within the relevant ES assessments and the magnitude of the impact on all VERs is therefore assessed as being minor. Natural England disagree with the conclusion that the impact is minor, noting that the area impacted by smothering is of similar scale to that of temporary disturbance impact which we have also rasied concerns about (F10). This relates directly to the concerns we have raised (e.g. F10) regarding the defintions of magnitude and sensitivity, and how this has the potential to result in an over or under estimation of impact. As stated, we do not consider there to be sufficient time remaining within the Examination to address these concerns, and we recognise that these matters have applicability beyond Hornsea Four. We therefore highlight this matter for the ExA and Secretary of State to consider. |  | No change |  | G5.5 Clarification Note on drill arising and deposition of sediments (REP5-083) provides a figure for the footprint which will be affected by light smothering (<5cm) as a result of sediment disposal activities. This is predicted to be 26 km2 in the export cable and 48 km2 in the array area (10% & 9% of Array and ECC). Heavy smothering (5-30 cm as defined by the Marlin MarESA assessment) will occur over a total maximum footprint of 4 km2 in the export cable and 8 km2 in the array area (1% & 2%). The report goes on to conclude that based on the available evidence, the predicted MDS for sediment deposited is consistent with the evidence present within the relevant ES assessments and the magnitude of the impact on all VERs is therefore assessed as being minor. Natural England disagree with the conclusion that the impact is minor, noting that the area impacted by smothering is of similar scale to that of temporary disturbance impact which we have also rasied concerns about (F10). This relates directly to the concerns we have raised (e.g. F10) regarding the defintions of magnitude and sensitivity, and how this has the potential to result in an over or under estimation of impact. As stated, we do not consider there to be sufficient time remaining within the Examination to address these concerns, and we recognise that these matters have applicability beyond Hornsea Four. We therefore highlight this matter for the ExA and Secretary of State to consider.
F23 | 25 | This paragraph in relation to HDD exit pits is not clear as to if there will be any impact on the intertidal area. It is stated that ‘8 exit pits will be excavated in the shallow subtidal area’. However, it then goes on to say, ‘The HDD exit pit may be located above mean high water (MHW), within the Hornsea Four intertidal area (intertidal punch out) or below mean low water (MLW)’. The location of the exit pits will cause different impacts depending if it is intertidal or subtidal. The benthic chapter states no temporary habitat disturbance will occur within the intertidal, which would not be the case should HDD exit pits emerge above MHW. Can the Applicant please clarify the position of HDD exit pits, and if there is a possibility they will be above MHW, amend the benthic and intertidal ecology report, MDS in relation to intertidal habitat loss and incorporate additional impacts. |  | As noted in Volume A1, Chapter 4: Project Description (APP-010), the HDD exit pits will be located at a minimum of 400 m and a maximum of up to 1,500 m from the TJB (Transition Joint Bays), though the final locations will be confirmed post-consent. | Issue not addressed - The Applicant has provided no additional evidence to provide confidence that the exit pits will not be within the intertidal area. If the applicant is unable to provide accurate locations at this time then the worst case scenario should be considered up front and prior to consent. If the intertidal area is located within the proposed range from the TJB (HDD exit pits will be 400m - 1,500m from TJB) then impacts on the intertidal habitat need to be included as part of the assessment. Natural England request the applicant confirms where the exit pits will be in relation to the intertidal area. |  | No Change - Natural England request the applicant confirms where the exit pits will be in relation to the intertidal area. |  | The applicant has confirmed that the reference in paragraph 4.9.2.9 of A1.4: Project Description (REP1-004) is not correct. The wording relating to the location of HHD exit pits should read “The exit pits will be below Mean Low Water (MLW)”. This will be updated in A1.4: Project Description (REP1-004) and submitted at deadline 6. This will resolve Natural England's concerns in relation to intertidal impacts from the HHD exit pits and we will review the Project Description at Deadline 6 to ensure this has been corrected. |  | REP4-004 A1.4 Project Description (Tracked) - Revision: 4 has amended references to the HDD exit pits having the potential to be within the intertidal area. Therefore Natural England are content that the HDD exit pits will not be placed within the intertidal and the impact assessment is therefore complete. | [5 empty] | REP4-004 A1.4 Project Description (Tracked) - Revision: 4 has amended references to the HDD exit pits having the potential to be within the intertidal area. Therefore Natural England are content that the HDD exit pits will not be placed within the intertidal and the impact assessment is therefore complete. |  | Yes
F24 | 26 | It is not clear where the volumes of material for disposal associated with trenching come from and this is not made clear in the project description. Natural England would welcome clarification on whether this material is actively collected and disposed of, or if not the volume of material which will be likely be suspended in the water column as a result of displacement from the cable trenching activity. |  | The Applicant can confirm that the volumes of material associated with trenching, as set out in Table 2 and 3 of Volume A4, Annex 4.4: Dredging and Disposal (Site CharacterisationAPP-042) relate to material that will be suspended in the water column as a result of cable trenching activity. Therefore, this is a precautionary assessment of material to be disposed of. | Whilst the Applicant's response to our relevant reps answers this concern (RR-029-APDX:F-26), this now links to issue F22 (line 26 of this issues log) where we request information on the extent that sediment will settle out of the water column and impact the benthos. | [11 empty] | Whilst the Applicant's response to our relevant reps answers this concern (RR-029-APDX:F-26), this now links to issue F22 (line 26 of this issues log) where we request information on the extent that sediment will settle out of the water column and impact the benthos. |  | Yes
F25 | 27 | Options should be kept open should a project come along in relevant timescales that could effectively use the spoil material. Consideration of disposal at this stage should not preclude beneficial or other use if it becomes viable. Natural England suggest this option remains under consideration. We recognise that there are vessel movements associated with transport of the spoil – however any project that needed the spoil would also likely have vessel movements associated with it, which would be reduced or eliminated by use of spoil from this project. This is therefore not a reason not to consider re-use as the overall impacts would be the same or less |  | Noted. | The applicant has noted our comment with regards to re-use of sediment spoil. We would welcome the inclusion of a commitment to give ongoing consideration to this matter within the Commitments Register to prompt further consideration. (N.B. Natural England has changed the RAG status to Amber to reflect that we would like this point addressed). |  | No further comments - The applicant has noted our comment with regards to re-use of sediment spoil. We would welcome the inclusion of a commitment to give ongoing consideration to this matter within the Commitments Register to prompt further consideration. (N.B. Natural England has changed the RAG status to Amber to reflect that we would like this point addressed). |  | No Change. The Applicant has suggested that they will provide further comment on this matter at Deadline 5. |  | Natural England are waiting for documentation to be submitted at deadline 5 to progress this issue |  | The applicant has stated it will follow best practice guidance on spoil disposal and keep options open to consider alternatives uses of spoil material at the point of construction as per the Dredging and Disposal site characterisation paper. Following discussion with the applicant (as part of updating SoCG) we understand that the use of a trailing suction hopper dredge or similar methods that extract and store sediment which needs to be disposed, are only likely to be used in discrete areas, and that the majority of material will be sidecast (trenching) or "liquified" (CFE) and that there may therefore be very little spoil material extracted for disposal. Given this context, we are content on this occasion to close out this issue. However, we would welcome further discussion with the applicant as to how the provision for the use of methods that are only likely to be employed in discrete locations can be better reflected future projects to ensure that the MDS is not overly precautionary/an unrealistic reflection of what is likley to occur. |  |  |  | The applicant has stated it will follow best practice guidance on spoil disposal and keep options open to consider alternatives uses of spoil material at the point of construction as per the Dredging and Disposal site characterisation paper. Following discussion with the applicant (as part of updating SoCG) we understand that the use of a trailing suction hopper dredge or similar methods that extract and store sediment which needs to be disposed, are only likely to be used in discrete areas, and that the majority of material will be sidecast (trenching) or "liquified" (CFE) and that there may therefore be very little spoil material extracted for disposal. Given this context, we are content on this occasion to close out this issue. However, we would welcome further discussion with the applicant as to how the provision for the use of methods that are only likely to be employed in discrete locations can be better reflected future projects to ensure that the MDS is not overly precautionary/an unrealistic reflection of what is likley to occur. |  | No
F26 | 28, 32 & 34 | Where there is near surface chalk and drilling is required for foundation installation, then drill arisings will be composed of chalk and may differ significantly in composition from the surface sediments (as acknowledged in 6.1.1.1) Monitoring of chalk drill arisings at Lynn and Inner Dowsing and Lincs OWF has shown these mounds to persist in the environment rather than be winnowed away. This has potential to change the biotopes locally and should be considered in this context in this report and the ES. Where the composition of the drill arising is different to that of the surface sediment, mitigation measures should be included within the DCO to reduce the impact on the benthic environment. It would be preferable to dispose of the material (which are a waste product of construction operations and are not integral to the project) at a licensed marine disposal /landfill site, as per standard best practise undertaken by other marine users. If removal is not possible then long term monitoring would be required of mounds post construction and may result in additional mitigation or decommissioning requirements if they are found to persist long term. |  | The Applicant notes that the form of chalk arisings depend on the form of the chalk layer, the size and type of the drill, and the pressure of the drill. Lynn and Inner Dowsing drilled for smaller diameter piles into a dense (hard) chalk layer (around 3 to 12 m below the surface (to reach a layer of Upper Cretaceous Chalk). Larger diameter clasts (20 to 100 mm) remained close to the pile. The original concern for Lynn and Inner Dowsing was in regard to chalk plumes of the finer silt sized fraction, however monitoring did not detect any such chalk plumes (COWRIE ScourSed-09, 2010). Section 4.4.6.5 of Volume A5, Annex 1.1: Marine Processes Technical Report (APP-067) notes that Sheringham Shoal Offshore Wind Farm (90 km to the south of Hornsea Four) also encountered Cretaceous Chalk but was still able to drive all piles into the seabed without the need of drilling (Carotenuto et al. 2018). This project is closer to Hornsea Four in terms of geology and is likely to be more representative of the chalk likely to be encountered. Table 6 of Volume A4 Annex 4.4 Dredging and Disposal Site Characterisation (APP-042) presents a summary of impacts from disposal of material from seabed preparation, sandwave clearance, pile drilling and cable trenching within the Hornsea Four Order Limits including potential impacts on benthic ecology. No changes to biotopes are predicted locally within the Applicant’s Environmental Statement. | Natural England notes the Applicant's response to this issue RR-029-APDX:F-28 & RR-029-APDX:F-32] however, we do not consider that the additional narrative they have provided addresses this particular concern. Natural England appreciate it is difficult to predict where drilling may be required and what the material deposited as a result will be like as a number of factors will affect this. However chalk mounds could still form in the environment as a result of disposal of drill material, as they have done in other locations and the impact of this should be assessed. Mitigation, or post construction monitoring to inform the need for mitigation should also be considered to avoid or reduce impacts. |  | Natural England still feel the issue of Drill Arisings needs to be fully assessed within the ES and monitoring or mitigation proposed should it be required post-construction. |  | The Applicant has stated in REP3-046 (page 30) that further consideration is being given to the impact of drill arisings and a clarification note is due to be submitted into Examination at Deadline 5. Natural England will review this when available. |  | Natural England are waiting for documentation to be submitted at deadline 5 to progress this issue |  | Natural England welcome the additional information supplied by the applicant to address this matter. We would welcome clarification as to how the figure of 0.027km2 has been calculated to confirm this is a true reflection of the worst-case scenario. However Natural England agree that the scale presented is not significant in a benthic context provided the assumptions made within the assessment hold true. Ideally we would have liked to have seen this incorporated into the assessment as opposed to being presented as a standalone figure, however given the stage of the examination we are content to close out this issue. |  |  |  | Natural England welcome the additional information supplied by the applicant to address this matter. We would welcome clarification as to how the figure of 0.027km2 has been calculated to confirm this is a true reflection of the worst-case scenario. However Natural England agree that the scale presented is not significant in a benthic context provided the assumptions made within the assessment hold true. Ideally we would have liked to have seen this incorporated into the assessment as opposed to being presented as a standalone figure, however given the stage of the examination we are content to close out this issue. |  | No
F27 | 29 | Whilst areas may have low resemblance to stony reef, it would still be beneficial to this habitat to avoid deposition of sediment in these areas. Please see comments above in point 6 on assessment of stony reef and use caution with regards to depositing material in the vicinity of any potential examples of this habitat |  | The Applicant notes that micrositing mitigation would be agreed through consultation with the MMO and Natural England on the identified sensitive features which are required to be avoided (e.g. biogenic and geogenic reef) including avoidance of interaction with spoil material. Pre-construction surveys required for micrositing are described within F2.7: Outline Marine Monitoring Plan (APP-242). These surveys will then inform the layout which will be agreed post consent through the Design Plan (submission of which is conditioned in the DML) which will be submitted to and approved in writing by the MMO. | Natural England acknowledged the Applicant's position that micrositing and mitigation will be agreed prior to construction, however we would welcome a commitment to avoid sensitive features including low resemblance stony reef when it comes to the identification of disposal sites in particular. This would avoid pushing this matter to the post consent phase to be resolved. (N.B. Natural England has changed this RAG status to Amber to highlight that this is something we would ideally like to be addressed). |  | Natural England would welcome a commitment to avoid sensitive features including low resemblance stony reef when it comes to the identification of disposal sites in particular. This would avoid pushing this matter to the post consent phase to be resolved. |  | Natural England have concerns with regards to our confidence in the classification of stony reef by the applicant. To alleviate Natural England's concerns moving forward with regards to our confidence in the classification of stony reef, we request that Natural England be consulted on survey design of pre construction benthic surveys to ensure most up to date guidance is being followed when identifying examples of stony reef and that this specific point is captured appropriately within the DCO/dML and/or relevant certified documents. |  | No change. |  | The Applicant has confirmed the existing Commitment wording (Co48 & Co84) includes all construction related activities, including disposal of sediment. Therefore this issue has been closed. |  |  |  | The Applicant has confirmed the existing Commitment wording (Co48 & Co84) includes all construction related activities, including disposal of sediment. Therefore this issue has been closed. |  | Yes
F28 | 30 | Natural England welcome the Applicant’s plan to deposit spoil material close to the site of production as it is best practice to try and ensure sediment composition is unchanged. This is particularly important in the case of larger particles, which should not be deposited on finer sediments as they are likely to persist and change the habitat composition. However, Natural England would like the Applicant to commit to this best practice either through a formal commitment or within a mitigation agreement. |  | As confirmed in paragraph 4.3.1.6 of Volume A4, Annex 4.4: Dredging and Disposal (Site Characterisation) (APP-042), the spoil material will be retained in the local sedimentary system, as far as reasonably practicable. | We are yet to receive comment from the Applicant as to whether they will commit to best practice through a formal commitment. |  | No change - We are yet to receive comment from the Applicant as to whether they will commit to best practice through a formal commitment. |  | No change, the applicants view is a formal commitment is not required. |  | No change. |  | Following discussion with the Applicant as part of updating SoCG, we understand that the use of a trailing suction hopper dredge (or similar methods that extract and store sediment which needs to be disposed) is only likely to be in discrete areas and more likely to be used in the array than along the cable corridor. Therefore the majority of material will be sidecast (trenching) or "liquified" (Controlled Flow Excavator) and that there may therefore be very little spoil material extracted for disposal. Given this context, we are content on this occasion to close out this issue. However, we would welcome future discussions with the applicant as to how the provision for the use of methods that are only likely to be employed in discrete locations can be better reflected in subsequenr projects to ensure that the MDS is not overly precautionary/an unrealistic reflection of what is likely to occur, whilst still allowing the applicant sufficient flexibility. |  |  |  | Following discussion with the Applicant as part of updating SoCG, we understand that the use of a trailing suction hopper dredge (or similar methods that extract and store sediment which needs to be disposed) is only likely to be in discrete areas and more likely to be used in the array than along the cable corridor. Therefore the majority of material will be sidecast (trenching) or "liquified" (Controlled Flow Excavator) and that there may therefore be very little spoil material extracted for disposal. Given this context, we are content on this occasion to close out this issue. However, we would welcome future discussions with the applicant as to how the provision for the use of methods that are only likely to be employed in discrete locations can be better reflected in subsequenr projects to ensure that the MDS is not overly precautionary/an unrealistic reflection of what is likely to occur, whilst still allowing the applicant sufficient flexibility. |  | No
F29 | 31 | As in point F2 above, high levels of contaminants have been found in some sediment samples as described in the ‘benthic and intertidal ecology’ chapter and ‘Technical report’. Should evidence arise that the dredging and disposal of these sediments could have environmental impacts due to the high contaminant levels they contain, Natural England wants to see measures in place to minimising this effect. |  | An assessment of the potential effects associated with the accidental release of pollutants on benthic receptors was scoped out of the assessment. Given the designed-in mitigation measures (see Table 2.11 of Volume A2, Chapter 2: Benthic and Intertidal Ecology (APP- 014)) which are proposed (i.e., the implementation of a Construction Project Environmental Management and Mitigation Plan (CPEMMP), it is considered that the likelihood of accidental release is extremely low. Furthermore, the biotopes present within the array area and ECC are considered to be tolerant of chemical pressures, as presented within the MarESA assessment. As such, this impact has therefore been scoped out of the assessment. | Natural England are less concerned with the accidental release of pollutants from human sources, rather this point was referring to the high levels of contaminants found in the benthic sediments themselves and what might happen when these are disturbed during dredging and disposal. We welcome the statement about biotopes being tolerant to chemical pressures within the order limits and this will to some extent relieve our concerns. However we seek guidance from Cefas and the MMO on the suitability of those sediments which exceed contamination thresholds CAL 1 & ISQG TEL (as identified in RREP1-066 Clarification Note on Marine Sediment Contaminants Revision: 1) for dredging and disposal activities associated with construction. |  | Natural England are seeking guidance from Cefas / MMO on the suitability of those sediments which exceed contamination thresholds for disposal at sea. We will update the Examining Authority at the next deadline. |  | No Change: We note the Applicant will provide a revised version of G1.44 Clarification Note on Marine Sediment Contaminants at Deadline 4 which may address our concerns. |  | See Natural England's response to F2 at deadline 5 above. The Applicant has further reviewed the data and suggests there is little evidence from statistical analyses of any impact to the faunal community at the export cable corridor stations where hydrocarbons including PAHs and the metals (arsenic, nickel and lead) exceed CEFAS ALs and/or the Canadian ISQGs. However, Natural England notes that these conclusions relate only to the impact on the faunal assemblage where the contaminants are currently located and does not account for the potential impacts to different faunal assemblages should the sediment be deposited in alternate locations. We acknowledge F28 above that the Applicant is proposing best practice to deposit spoil material as close to the site of production. This will clearly minimise the potential for faunal impacts as a result of the presence of elevated contaminants. We therefore suggest that this best practice be secured in the DCO. |  | See row F3 above. |  | No change |  | See F3.
F30 | 33 | In table 6 Broadscale habitat features of the Holderness Offshore and Inshore MCZs are given a sensitivity of the receptor as Low, when it should be medium to light smothering. This is recorded correctly in the MCZ assessment document. |  | The Applicant will correct the sensitivity of the receptor for the Holderness Offshore and Inshore MCZs in Volume A4, 4.4: Dredging and Disposal Site Characterisation (APP-042). | In RR-029-APDX:F-33 the Applicant has confirmed they will correct the sensitivity of the receptor for the Holderness Offshore and Inshore MCZs in Volume A4, 4.4: Dredging and Disposal Site Characterisation (APP-042) | [11 empty] | In RR-029-APDX:F-33 the Applicant has confirmed they will correct the sensitivity of the receptor for the Holderness Offshore and Inshore MCZs in Volume A4, 4.4: Dredging and Disposal Site Characterisation (APP-042) |  | Yes
F31 | 35 | Natural England welcome the PSA monitoring along the cable route pre and post construction. There is only good evidence on impacts and recovery from sandwave clearance at one site (Race Bank). Therefore, there would be benefit in building up a comprehensive understanding of impacts from sandwave clearance by monitoring at more locations |  | Agreement on PSA monitoring is welcomed by the Applicant. | [12 empty] | Natural England welcome the PSA monitoring along the cable route pre and post construction. There is only good evidence on impacts and recovery from sandwave clearance at one site (Race Bank). Therefore, there would be benefit in building up a comprehensive understanding of impacts from sandwave clearance by monitoring at more locations |  | Yes
Document used: Volume A4.5.3 Offshore Cumulative Effects Appendix A Screening Matrix
F32 | 36 | It is not clear how ongoing effects of projects already operational are taken into account when assigned category a (included as part of the topic baseline and hence not considered within the cumulative impact assessment) within the screening matrix. This is the case for many cables, pipelines & oil and gas plans or projects as well as shipping activity. For example all existing oil and gas infrastructure in the vicinity are already changing the habitat and therefore the ability to withstand further pressures and justify the use of non significant or minor judgements in EIA terms. In the long term the issue is that there will be multiple projects affecting the same widespread habitats with low sensitivity. If all of these are assessed as negligible and the baseline doesn’t change, then it is hard for the reader to understand if and at what point the level of construction/ infrastructure starts to be an issue. |  | It is noted in PINS Advice Note Seventeen (PINS 2019) that where other projects are expected to be completed before the construction of the proposed NSIP and the effects of those projects are fully determined, effects arising from them should be considered as part of the baseline and may be considered as part of assessment in the construction and operational phase (noting that the assessment should clearly distinguish between projects forming part of the baseline and those in the CEA). Table 3 of Volume A4, Annex 5.3: Offshore Cumulative Effects presents the CEA long list screening criteria which differentiates between ‘Project, plan or activity is considered as part of the baseline environment but has ongoing effects’ which are screened in, and ‘Project, plan or activity included as part of the baseline environment (therefore not a consideration in the CEA)’ which are screened out. | Natural England's position on this matter remains unchanged. | [11 empty] | Natural England's position on this matter remains unchanged. |  | No

## E - Marine Processes
Point | [RR - 029] Appendix E point number | Taken from Natural England’s Relevant and Written Representations Hornsea 4 Appendix E - Marine Geology, Oceanography and Physical processes | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Risk Status Deadline 2 | Consultation, actions, progression | RAG Risk Status Deadline 3 | Consultation, actions, progression | RAG Risk Status Deadline 4 | Consultation, actions, progression | RAG Risk Status Deadline 5 | Consultation, actions, progression | RAG Risk Status Deadline 6 | Consultation, actions, progression | RAG Risk Status Deadline 7 | Consultation, actions, progression | RAG Risk Status Deadline 8 | Issue Resolved
Document Used: Volume A2.1 Marine Geology Oceanography and Physical Processes [App-13] A5.1.1 Marine Processes Technical Report [APP-067] |  |  |  | Document reviewed: G1.9 Applicant’s comments on Relevant Representations Revision: 01 [REP1-038] & G1.46 Clarification Note on Marine Processes Supplementary Work Scope of Works Revision: 01 [REP1-068] |  | Document reviewed: REP2-038 Applicant’s Responses to the ExA’s First Written Questions (ExQ1) |  | Document Reviewed: G3.6 Clarification Note: Justification of Offshore Maximum Design Scenarios - Revision: 01 [REP3-035}; G3.8 Chart depicting the Dogger Bank A and B export cable crossing rock protection - Revision: 01 [REP3-037]; G3.9 Clarification Note: Marine Processes Supplementary Work Update - Revision: 01 [REP3-038]; G3.17 Applicant's comments on Natural England's Comments received at Deadline 2 - Revision: 01 [REP3-046] |  | Document Reviewed: REP4-043 G4.9 Marine Processes Supplementary Report - Revision: 01 REP4-044 G4.10 Applicant’s comments on other submissions received at Deadline 3 - Revision: 01 REP4-038 G4.4 Written Summary of the Applicant’s Oral Case at Issue Specific Hearing 4 (ISH4) - Revision: 01 |  | Documents reviewed: REP5-074 G5.2 Applicant’s Responses to the Examining Authority's Second Written Questions (ExQ2); REP5-081 G5.3 Applicant’s comments on other submissions received at Deadline 4; REP5a-017 G5.33 Clarification Note on Marine Processes Mitigation and Monitoring - Revision: 01; REP5-083 G5.5 Clarification Note on Drill Arisings and Deposited Sediments - Revision: 01 |  | Documents Reviewed: REP6-003 A1.4 Chapter 4 Project Description (Tracked) - Revision: 06 REP6-005 - A4.4.4 Dredging and Disposal Site Characterisation (Tracked) - Revision: 02 REP6-014 F2.15 Outline Cable Specification and Installation Plan (Tracked) - Revision: 03 REP6-007 A4.4.8 Pro rata Annex (Tracked) - Revision: 04 |  | Documents reviewed: F2.7 Outline Marine Monitoring Plan (Tracked): Revision 02; G7.2 Applicant’s comments on other submissions received at Deadline 6 - Revision: 01
E1 | 1 | Paragraph 5.5.9 of NPS EN-1 states that “The applicant should be particularly careful to identify any effects of physical changes on the integrity and special features of Marine Conservation Zones (MCZs), candidate marine Special Areas of Conservation (cSACs), coastal SACs and candidate Coastal SACs, coastal Special Protection Areas (SPAs) and potential Sites of Community Importance (SCIs) and Sites of Special Scientific Interest (SSSI). We highlight that neither Holderness Inshore MCZ nor Holderness Offshore MCZ have been considered in this chapter, yet they remain marine processes receptors. Given their proximity, in places, to the offshore export cable corridor, there is a need to consider the potential environment impacts of the project on these designated sites. It should also be noted that the project has the potential to impact on sites much further afield such as the Humber Estuary SAC and SSSI, and well as the supporting habitat of sites such as the Southern North Sea SAC and Humber Estuary SPA. Natural England’s view is that in order to establish the regional significance of the project’s impacts in EIA terms, it is important the EIA incorporates these designated sites as receptors. Natural England notes and welcomes the applicant’s commitments to avoid direct overlap of the permanent project footprint with MCZs and SSSIs. However, it should be noted that indirect impacts to these sites could potentially be just as significant. |  | Natural England's position on this matter remains unchanged. |  | Natural England's position on this matter remains unchanged. |  | No change |  | Please see our comment in E6. |  | We maintain our advice that all marine process receptors should be identified and assessed within the Environmental Statement. We ideally have liked to have seen this addressed through an update to the Marine Processes chapter of the ES to ensure full consideration and a clear audit trail, however we do not believe there is sufficient time remaining within the Examination for this to be addressed. Please see E17, E22, E49 and E50 for specific comments in relation to receptors for the landfall, ECC and Array. |  | No change |  | We maintain our advice that all marine process receptors should be identified and assessed within the Environmental Statement. We would ideally have liked to have seen this addressed through an update to the Marine Processes chapter of the ES to ensure full consideration and a clear audit trail, however we do not believe there is sufficient time remaining within the Examination for this to be addressed. Please see E17, E22, E49 and E50 for specific comments in relation to receptors for the landfall, ECC and Array. |  | No
E2 | 18, 21 | Maximum Design Scenarios Although we acknowledge that there have been efforts made to refine the Maximum Design Scenarios (MDS) in some cases, Natural England remains concerned that a number of maximum design scenarios are unnecessarily precautionary. Of particular concern to Natural England are the volumes of sandwave levelling and boulder clearance outlined in the draft DCO/dML, which are based on clearance across the full length of the cable corridor, particularly given that there are geophysical data available from a 2021 campaign that should allow these figures to be refined. An additional concern is the proposal to defer a large proportion of the detailed assessment to the post consent phase, notably the Cable Burial Risk Assessment and Scour Assessment. Consequently, the volumes of rock protection outlined in the draft DCO/dML are conservative and estimated based on experience at other projects rather than being informed by the ground conditions within the developable area. From a marine processes perspective, this makes WCS for each receptor difficult to define as a wide range of potential scenarios are possible. |  | Natural England's position remains unchanged. However, we welcome the Applicant’s intention to provide a review of the Maximum Design Scenario (RR-029-5.40), which they plan to subit at Deadline 3. |  | We are awaiting the outcome of the review of MDS expected at Deadline 3. |  | We welcome the Applicant's efforts to reduce volumes of bedform clearance (for cable installation) within the array (REP3-035), however, our position remains unchanged since sandwave clearance is still proposed for the entire length of the Export Cable Corridor, (ECC) despite the recent gathering of high-res geophysical data in 2021. We would welcome further justification on the rationale for not reducing sandwave clearance along the ECC. |  | Whilst Natural England welcome the changes made to the MDS in relation to bedform clearance volume we had hoped the survey data would allow the bedform clearance area to be reduced in areas where there are no bedforms present. The requirement to clear an area of 40m along the full length of the cable corridor (for bedforms) leads to a huge area of temporary disturbance which we believe is not standard practice amongst windfarm developments (Rampion & EA1&EA2 only carry out bedform clearance where bedforms are known to be present). Natural England advise that as a minimum the MDSs are further refined in relation to sensitive receptors such as Smithic Bank, Flamborough Front and the Holderness Coast. |  | Although we welcome the elements of further refinement within REP4-043, Natural England's broad concerns relating to the precautionary nature of some of the MDS, and the difficulties this then poses in ensuring a realisitic worst case scenario for marine process receptors is assessed, remain unchanged. At this stage in the Examination we consider it unlikely that the Applicant will provide further evidence or further refine their assessments. Therefore Natural England's advice now focusses on reducing the level of risk to designated sites and associated receptors through identifying potential design changes and/or advising on monitoring required to detect changes and trigger counter measures. |  | No change |  | Although we welcome the elements of further refinement within REP4-043, Natural England's broad concerns relating to the precautionary nature of some of the MDS, and the difficulties this then poses in ensuring a realisitic worst case scenario for marine process receptors is assessed, remain unchanged. At this stage in the Examination we consider it unlikely that the Applicant will provide further evidence or further refine their assessments. Therefore Natural England's advice now focusses on reducing the level of risk to designated sites and associated receptors through identifying potential design changes and/or advising on monitoring required to detect changes and trigger counter measures. |  | No
E3 | 10 21 & 40 | Maximum Design Scenario In light of Paragraph 2.6.196 of NPS EN-3, which states that “ Methods of construction, including use of materials should be such as to reasonably minimise the potential for impact on the physical environment”, further justification should be provided to support the following maximum design parameters and provide an understanding of how these figures has been calculated: • The requirement for up to 8 HDD exit pits for a maximum of 6 cables. • An MDS for sand wave clearance based on clearance along the full length of each of the 6 cables, despite geophysical data being available. • Cable protection based on a percentage of the total cable route rather than available geophysical data (10% of route). • Drilling will only be required for up to 10% of all pile installations (or up to 10% of the depth across all installations) |  | Natural England's position remains unchanged. However, we welcome the Applicant’s intention to provide a review of the Maximum Design Scenario (RR-029-5.40), which they plan to submit at Deadline 3. |  | We are awaiting the outcome of the review of MDS expected at Deadline 3. |  | Natural England welcomes the explanation provided by the Applicant (REP3-035) regarding the requirement for up to 8 HDD Exit Pits. However, we are unclear why such a high failiure rate is anticipated and would welcome further discussion as to whether this can be better managed through more detailed site investigtions prior to consturction. We welcome the justification to support the MDS for up to 10% of Hornsea Four cables requiring protection, however, we remained concerned that some, or all of the 10%, may be located within nearshore shallow areas as this could lead to morphological change. We welcome the detailed explanation for a MDS for drilling up to 10% of all pile installations. Whilst we welcome the reduction in MDS bedform clearance volume for array and interconnector cables, the area remains unchanged. Moreover, there has been no reduction in the MDS for bedform clearance along the export cable corridor. If full survey coverage of the Hornsea Four Offshore Order Limits is available, can it be explained why the MDS for bedform clearance along the ECC is not possible? |  | Rock protection on Smithic bank was reduced down to 5% within the REP3-035, however, Natural England still wish to see this reduced to zero, in order to exclude the potential for significant impacts arising both alone and cumulatively/in combination with other plans/projects. Similarly we would wecome consideration of further measures to reduce the over all impact of the proposal, particularly in the nearshore area, for example, the bundling of cables to reduce the number of installations through smithic bank and the number of cable crossings required. The Marine Process Supplementary works report REP4-043 suggests that bedform clearance for sandwaves will not occur across Smithic Bank (2.4.1.2) but this was not discussed in the MDS paper. Natural England would welcome clarification on this point and further information as to how this is secured within the DCO. (See ExQ2, PDS2.2) |  | Please note our advice in E2 above and throughout. |  | No change |  | Please note our advice in E2 above and throughout. |  | No
E4 | 3 | Maximum Design Scenario - Introduction of Gravity Base Structures It should be noted that the use of Gravity Base Structures (GBS) as a maximum design scenario was introduced following the Section 42 consultation on the PEIR. Consequently, rather than seeing a refinement of the MDS between PEIR and application, we have seen a significant increase in scope which has substantially increased the significance of impacts for marine geology, oceanography and physical process receptors and therefore introduced an additional element of risk associated with this project. Although a follow up consultation took place in Q3/4 of 2020/21, several of the key areas of concern that were raised by NE and the MMO (Cefas) at this time (and indeed at PEIR) have not been addressed within the final application. |  | Whilst we note that the Applicant has limited the number of GBS to 110, the introduction of GBSs in the MDS has substantially increased the significance of impacts and, thus, the risk associated with this project. However, our original comment to the ExA was intended to highlight that these changes to the MDS at a relatively late stage in the evidence plan process, and the lack of resolution prior to application have left us with substantial issues to resolve during this examination. |  | No Change |  | No change |  | After reviewing the Marine Process Supplementary works report REP4-043, Natural England consider that the potential for significent effects to Flamborough Front as a result of the project at an alone or cumulative/incombination level cannot be ruled out. Consequently we advise that steps are taken to avoid or reduce the potential impacts as far as possible and that this should include the removal of GBS as the maximum design scenario (noting that they have not been required for Offshore Windfarm developments in English waters to date) or that the maximum number is significantly reduced. |  | In G5.33, the Applicant has stated that the Maximum Design Scenario has been reviewed for Gravity Base Structures (GBSs) and confirms GBS foundations (WTG type) will be utilised at a maximum of 80 of the 180 WTG foundation locations. This refinement of the MDS is very welcome. However, we remain concerned that the Hornsea Four array, alone/in-combination, has the potential to lead to increased vertical mixing and have an adverse effect on the Flamborough Front. Due to the variable nature and uncertanties associated with Flamborough Front, and the wide range of scenarios potentially available under the MDS, it is difficult to identify and model a realistic worst case for each relevant marine process receptor in order to exclude the potential for signficant impacts and the potential for an Adverse Effect on Integrity on a number of desginated sites. Whilst these concerns remain for all foundation types, GBS have the potential to give rise to signficantly greater impacts and therefore their inclusion within the MDS substantially increases the risk of significant impacts occuring. As further detail on on the foundation type and layout will be available at the post consent phase, should the ExA and SoS be minded to proceed on the basis of the information available, Natural England advise that a clear requirement is included within the DCO/dML conditions to fully assess the proposed layout plan prior to discharge, with the option to include further measures to avoid, reduce or mitigate impacts until it can be demonstrated that signficant impacts can be ruled out. This approach of "deferred assessment" is not without its own challenges and risks. Therefore we would advise that this is only considered where the ExA/SoS are satisfied that significant impacts can be avoided and that all steps have been taken by the Applicant to reduce the risks as much as possible prior to consent. Therefore, we continue to advise that GBS foundations be removed as a design option. |  | No change |  | In G5.33, the Applicant has stated that the Maximum Design Scenario has been reviewed for Gravity Base Structures (GBSs) and confirms GBS foundations (WTG type) will be utilised at a maximum of 80 of the 180 WTG foundation locations. This refinement of the MDS is very welcome. However, we remain concerned that the Hornsea Four array, alone/in-combination, has the potential to lead to increased vertical mixing and have an adverse effect on the Flamborough Front. Due to the variable nature and uncertanties associated with Flamborough Front, and the wide range of scenarios potentially available under the MDS, it is difficult to identify and model a realistic worst case for each relevant marine process receptor in order to exclude the potential for signficant impacts and the potential for an Adverse Effect on Integrity on a number of desginated sites. Whilst these concerns remain for all foundation types, GBS have the potential to give rise to signficantly greater impacts and therefore their inclusion within the MDS substantially increases the risk of significant impacts occuring. As further detail on on the foundation type and layout will be available at the post consent phase, should the ExA and SoS be minded to proceed on the basis of the information available, Natural England advise that a clear requirement is included within the DCO/dML conditions to fully assess the proposed layout plan prior to discharge, with the option to include further measures to avoid, reduce or mitigate impacts until it can be demonstrated that signficant impacts can be ruled out. This approach of "deferred assessment" is not without its own challenges and risks. Therefore we would advise that this is only considered where the ExA/SoS are satisfied that significant impacts can be avoided and that all steps have been taken by the Applicant to reduce the risks as much as possible prior to consent. Therefore, we continue to advise that GBS foundations be removed as a design option. |  | No
E5 | 18 | Maximum Design Scenario - GBS Natural England notes and welcomes the applicant’s efforts to refine the maximum design scenario for the use of GBSs down to 110 foundations. However, there is limited context provided (i.e. the likely location of these 110) and therefore it is difficult to refine down the worst-case scenario for the impact assessments. |  | No Change. |  | No Change |  | No change |  | No change |  | We welcome the reduction of the MDS for GBS foundations from 110 down to 80. However, in order to reduce the risk of turbulence induced vertical mixing and impacts to stratification, we would advise that GBS foundations be removed as a design option. (See E4 above) |  | No change |  | We welcome the reduction of the MDS for GBS foundations from 110 down to 80. However, in order to reduce the risk of turbulence induced vertical mixing and impacts to stratification, we would advise that GBS foundations be removed as a design option. (See E4 above) |  | No
E6 |  | Receptors Natural England does not agree that appropriate marine process receptors have been identified for assessment and considers that the “study areas” are too narrow in scope. Consequently, we are unable to agree with a large number of impact assessment conclusions. Although the impacts to designated sites may be subject to separate assessments (i.e. RIAA and MCZ Assessments), they remain marine process receptors and therefore should also be fully considered within the Environmental Statement. |  | Natural England does not disagree with the source-pathway-receptor approach described by the Applicant. Rather, we disagree with the identification of all sensitive marine process receptors within the marine process study area. In our Scoping Opinion (2018), we expressed concern with the validity of the chosen physical process features considered as potential receptors. Similarly, in our Section 42 response (2019), we expressed concern again that not all receptors had been identified. Furthermore, in our Scoping Opinion (2018) we advised that all impacts on designated sites should be considered and addressed as far as possible. The Hornsea Four Marine Processes Study Area shown in Figure 1.1 (Volume A2, Chapter 1: Marine Geology, Oceanography and Physical Processes) encompasses a number of designated sites which have neither been identified nor considered within this chapter. We would, therefore, advise that all designated sites located within the Marine Processes Study Area should, firstly, be identified and, secondly, assessed in order to rule out any adverse effects on their integrity and special features due to the proposed development. RR-029-5.38 & 5.39 |  | No Change. |  | Natural England await the supplimentary Marine Processes paper from Orsted which was expected at Deadline 3 (now delayed until Deadline 4). |  | Our advice remains unchanged. Designated sites may indirectly be affected by changes to the hydrodynamic regime and, in turn, the coastal, physical and sedimentary processes, either in the near- or far-field. Consequently, it is important to include conservation-designated sites that sit within the anticipated maximum zone of influence of the proposed development in the list of sensitive receptors for the marine processes chapter. The assessment of impacts to conservation-designated sites may be considered elsewhere in the ES, however, if they are receptors to changes to marine and coastal physical processes, then we advise that they should first be identified, and secondly, given consideration in this chapter. This approach is line with Cefas guidelines (see Judd, 2012), and has been adopted by other recent development applications for example, EA1N and EA2, which included relevant SACs/SPAs and MCZs in their receptor groups for Marine Geology, Oceanography, and Physical Processes, whilst Norfolk Boreas and Vanguard included SACs and MCZs in their receptor groups for Marine Geology, Oceanography, and Physical Processes. |  | See E1 above |  | No change |  | See E1 above |  | No
E7 | 26 | There is a discrepancy between the volumes of sandwave clearance quoted here and throughout the ES documents. In 1.11.1.17 it is stated that sandwave clearance will be carried out along the offshore EEC for 6 cables with a sweeping width of 40m per cable 757,000m3. Within the Project Description (Volume 4. Chapter 4) the total volume cleared is given as 834,000m3 across six export cables and sweeping a width of 40 m per cable. Within the Pro Rata Annex (Vol 4 Annex 4.8) the volume of sandwave clearance is given as 834,00m3 across 6 cables with a clearance width of 30m. Similarly, there appears to be a discrepancy in relation to the array area. The volumes of sandwave clearance should be clarified to enable an accurate assessment and then captured within the DCO/dML. |  | Whilst we welcome clarification from the Applicant regarding the volume of sand cleared from the main ECC, we query why two different values for sandwave clearance widths are used. For example, the MDS for sandwave is a width of 40m, whilst calculations of sandwave clearance areas and volumes use an average corridor width of 30m. For consistency, and to assess the worst-case scenario for sandwave clearance, we advise that the MDS value should be adopted throughout. |  | No Change |  | In the recent Clarification Note: Justification of Offshore MDSs (REP3-035), Section 3.1.1.2 Table 1 presents the MDS for bedform clearance (at DCO application) as 834,000m^3. Table 3 states that the bedform clearance width is 40m. The discrepancy with these figures in the ES documents, as noted in our earlier comments, has not been addressed (Where sometimes for the calculations of sandwave clearance areas and volumes, an average corridor width of 30 m has been used.). We would welcome clarification from the Applicant that these latest figures are the correct MDS parameters going forward |  | No change |  | We are now content that the Applicant has now provided clarification (in the updated Project Description (G1.9) on this issue. |  |  |  | We are now content that the Applicant has now provided clarification (in the updated Project Description (G1.9) on this issue. |  | Yes
E8 | 14 | Evidence Gaps Natural England consider that there are a number of gaps in the evidence presented in support of this application. These include: • Adequate data/evidence on the underlying geology, seabed sediments and dominant morphological features in the vicinity of, and within, the proposed project area. • Sufficient baseline characterisation and understanding of the Flamborough Front through and/in the vicinity to the HP4 array, coupled with an adequate assessment of the effects of the array on tidal flows, turbulent wakes, and mixing within the water column. • Detailed investigation of the geomorphology of Smithic Bank, its evolution, and the impact of the proposed development on its form and function |  | Natural England notes and welcomes the Applicant's intention to undertake further work to validate the baseline characterisation. We note that this will not be provided until Deadline 3, therefore our advice at this time reamins unchanged. |  | We are awaiting the outcome of the Marine Processes Supplementary Works and Clarification Note at Deadline 3. |  | We are awaiting the outcome of the Marine Processes Supplementary Works and Clarification Note which is delayed until Deadline 4 |  | The Applicant provided a Supplementary Report (G4.9) which provided further information on Smithic Bank and the Flamborough Front. Whilst these extra data have addressed some of the gaps we previously highlighted in the baseline characterisation, significant uncertainty remains and that this uncertainty is unlikely to be addressed by the project. Given this, we would suggest that this uncertainty is aknowledged and accounted for in subsequent assessments, and that steps are taken to avoid/reduce/mitigate impacts to key receptors as far as possible in order to give the ExA and SoS confidence that the risk of significant impact on the key marine process receptors is reduced as far as possible. For further detail please see Annex E5 of our Deadline 5 response. |  | In G4.9, the Supplementary Report, the Applicant provided further information on the position and formation of the Flamborough Front relative to the Hornsea Four array, and some further information on the geomorphology of Smithic Bank. However, there are still considerable gaps in the evidence for both these features. Based on recent research, there is the potential for large-scale changes to annual primary productivity due to the Hornsea Four array, either alone or in-combination with a cluster of OWFs, due to impacts to the Flamborough Front. In regards to Smithic Bank, the Applicant has used partial bathymetric data to inform the geomorphological baseline from which only macro-scale changes to the sandbank can be inferred. There are also insufficient data to inform understanding of the southern part of South Smithic and sediment exchange between this part of the sandbank and the Holderness coastline. The Applicant has marshalled all of the evidence that we are aware of, nevertheless with the project as currently designed we are not able to exclude the risk of significant/adverse effects arising. NE's advice now focusses on reducing the level of risk to designated sites and associated receptors, through identifying design changes and advising on the monitoring required to detect change and trigger counter measures. Whilst we do not consider the evidence gaps to be addressed, we are changing the RAG status to yellow to reflect that - in terms of evidence provision - we do not consider there is any more the applicant can do at this stage. |  |  |  | In G4.9, the Supplementary Report, the Applicant provided further information on the position and formation of the Flamborough Front relative to the Hornsea Four array, and some further information on the geomorphology of Smithic Bank. However, there are still considerable gaps in the evidence for both these features. Based on recent research, there is the potential for large-scale changes to annual primary productivity due to the Hornsea Four array, either alone or in-combination with a cluster of OWFs, due to impacts to the Flamborough Front. In regards to Smithic Bank, the Applicant has used partial bathymetric data to inform the geomorphological baseline from which only macro-scale changes to the sandbank can be inferred. There are also insufficient data to inform understanding of the southern part of South Smithic and sediment exchange between this part of the sandbank and the Holderness coastline. The Applicant has marshalled all of the evidence that we are aware of, nevertheless with the project as currently designed we are not able to exclude the risk of significant/adverse effects arising. NE's advice now focusses on reducing the level of risk to designated sites and associated receptors, through identifying design changes and advising on the monitoring required to detect change and trigger counter measures. Whilst we do not consider the evidence gaps to be addressed, we are changing the RAG status to yellow to reflect that - in terms of evidence provision - we do not consider there is any more the applicant can do at this stage. |  | Yes
E9 | 2 | Data/Evidence The presentation of wave, tide and plume modelling in the Marine Processes chapter does not include the schematics of model output in the Technical Report which makes it difficult to gauge the magnitude of impacts. |  | The Applicant has not addressed the issue of model output schematics being presented in the Technical Report but not in the Marine Processes Chapter. This makes it difficult to fully assess and understand the magnitude of impacts. | [11 empty] | The Applicant has not addressed the issue of model output schematics being presented in the Technical Report but not in the Marine Processes Chapter. This makes it difficult to fully assess and understand the magnitude of impacts. |  | Yes
E10 | 58, 77 | Data/Evidence It is not clear what the legend means in Figure 46, for example, ‘E_50pct’, ‘E_50pct baseline’ etc. Consequently, we cannot interpret or draw any conclusions from this figure. |  | We welcome the Applicant's amendment to the figure legend. | [11 empty] | We welcome the Applicant's amendment to the figure legend. |  | Yes
E11 | 78 | Data/ Evidence Neither Chapter 1 nor the Annex 1.1 Technical Report provide a map of regional solid geology. This is an important part of the baseline characterisation and should be included. |  | Baseline characterisation should include a map of regional solid geology across the study area. This has not been provided, however, we are content with the Applicant's explanation regarding the geological information provided. | [11 empty] | Baseline characterisation should include a map of regional solid geology across the study area. This has not been provided, however, we are content with the Applicant's explanation regarding the geological information provided. |  | Yes
E12 | 60 & 72 | We are concerned that the wave shadow effect of the Hornsea4 GBS array (and cumulatively with Hornsea 2 and Hornsea 1 array) through the lifetime of the project has not been assessed. This is also the case for the HVAC Booster Station Search Area and the rock berm at the HP4/Dogger Bank A&B Cable Crossing. Therefore, we cannot rule out potential adverse effects to sensitive receptors and designated sites downwind of these areas (e.g. Holderness Offshore MCZ, Holderness Coast, Smithic Bank), until this has been assessed over the lifetime of the project. Moreover, Section 4.8.3.17 in the Technical Report estimates up to 10% wave height reduction effects on the leeward side of the array. Without a consideration of these effects over the lifetime of the project, we cannot understand the spatial extent and potential impacts of the wave shadow effect on downwind receptors. |  | Natural England notes the Applicant's explanation that the waves passing through the array do not interfere with sediment transport due to the water depth. However, our concern remains the modelling shows a 10% reduction in wave height on the leeward side of the array. Although the Applicant states that this dissipates with distance from the array and has no discernible effect at the coast, there is no assessment as to whether this 10% wave height reduction would have an impact over the lifetime of the project. We'd therefore welcome futher discussion with the Applicant on this matter. |  | No change |  | The Applicant’s rationale provided in REP3-046 is reasonable. However, we are not only concerned with impacts to distant receptors, we are also concerned with impacts to receptors further offshore and closer to the array, such as the Holderness Offshore MCZ, which have not been considered. Natural England wish to see some evidence to show how the potential reduction in wave height for the cumulative effect of Hornsea Four, Hornsea Two and Hornsea One over the lifetime of the project might relates to all sensitive receptors (i.e. including Holderness Offshore MCZ and Smithic Bank). |  | Our concerns regarding the hydrodynamic impacts due to the Dogger Bank A&B (formerly Creyke Beck) Cable Crossing remain unchange and have been presented in further detail in the joint Memo issues by NE/MMO/Cefas to the Applicant. Natural England would welcome further discussion with the Applicant around ways to reduce the risk of significant effects as far as possible. (N.B the Applicant has committed to seeking the most up to date information on the Dogger Bank A&B cable route in order to identify a more precise location for the cable crossing, ensuring that this is located as far away from Smithic Bank as possible within their red line boundary.) In regard to a 10% reduction in wave height downwind of the array and HVAC Booster Station, we remain concerned that this has not been assessed for the cluster of Hornsea OWFs (HP4 HP2 and HP1) over the lifetime of the project. Neither have the impacts on the Holderness Offshore MCZ been considered. Thus, our concerns remain. |  | We welcome the reduction in MDS for GBS WTG foundations within the array and are now content that the wave shadow effect of the Hornsea Four array will, therefore, be less than that predicted in the ES, and sufficiently distant from receptors so as not result in a signficant impact/ adverse effect on marine process receptors/ designated sites. The potential impact of the wave shadow effect on the Holderness Offshore MCZ due to the HVAC Booster Station has not been assessed by the Applicant, however, we are content that the MCZ is beyond the predicted wave shadow effect shown in the ES. We remain concerned that the MDS Dogger Bank A&B Cable Crossing rock berm could potentially interact with waves and currents to alter nearshore sediment transport processes over the lifetime of the project (and beyond). See E26 for further details. |  | No change |  | We welcome the reduction in MDS for GBS WTG foundations within the array and are now content that the wave shadow effect of the Hornsea Four array will, therefore, be less than that predicted in the ES, and sufficiently distant from receptors so as not result in a signficant impact/ adverse effect on marine process receptors/ designated sites. The potential impact of the wave shadow effect on the Holderness Offshore MCZ due to the HVAC Booster Station has not been assessed by the Applicant, however, we are content that the MCZ is beyond the predicted wave shadow effect shown in the ES. We remain concerned that the MDS Dogger Bank A&B Cable Crossing rock berm could potentially interact with waves and currents to alter nearshore sediment transport processes over the lifetime of the project (and beyond). See E26 for further details. |  | No
E13 | 35 | Although the use of a Controlled Flow Excavator has become standard within offshore windfarm applications, and assessments are made on the assumption that the seabed and associated habitats will recover in the short-term (up to 2 years), we highlight that there is very little evidence available to support this assumption. Natural England recommend that all available evidence is considered, and that there is a commitment to post-consent monitoring to test the assumptions made within this application. |  | Natural England does not consider that this point has been addressed and would welcome a commitment to post construction monitoring in order to verify the assumptions being made in relation to recovery. |  | No change - Natural England does not consider that this point has been addressed and would welcome a commitment to post construction monitoring in order to verify the assumptions being made in relation to recovery. |  | Whilst Natural England appreciate the justification provided by the applicant with regards to CFE they have not provided the evidence we have asked for with regards to impacts of CFE. As well as this Natural England request post-consent monitoring to be carried out to test the assumptions made in this application. |  | No change |  | We advise that all available evidence on the footprint of impact of using CFE should be considered, however at this stage in the Examination we are not anticipating further submissions from the Applicant. We would therefore wish to see post-consent monitoring in order to validate the assumptions made in the ES and other assessments. |  | No change |  | Natural England would like to see monitoring secured within the Outline Marine Monitoring Plan which will validate the assumptions made in the ES and other assessments. The Applicant has indicated that Project asset integrity surveys cover this scope and already committed to in F2.7 AAI Volume F2.7 Outline Marine Monitoring Plan. Whilst we are pleased to note that our request would not require additional monitoring commitments, the survey scope as set out would not necessarily result in a report that would validate the assumptions made in realtion to the use of CFE. We would therefore welcome a commitment to specifically reporting on this matter. |  | No
E14 | 27 | It is stated that if Trailing Suction Hopper Dredging is carried out to achieve sandwave clearance, spoil disposal will be at a site elsewhere. Locations of spoil disposal need to be identified so that their impact can be assessed. |  | Natural England does not consider that this point has been addressed. Our understanding is that the Trailing Suction Hopper Dredging would mean that once removed, the sediment would be reained with the hopper and once full, transported to a disposal location. The two dredge disposal locations are currently identified "the array" and "the ECC". Our concern is that this is not specific enought to allow an assessment. |  | No change - Natural England would like to see potential disposal locations identified within the order limits. |  | No change |  | Natural England has further concerns with regards to disposal locations now being limited by the Dogger Bank A&B project boundary preventing sediment disposal in this area [REP4-035]. It is important that any sediment collected during cable installation, is retained within the Smithic Bank system. The assumption that sediment will be retained in the sandbank system is fundamental to the applicant's conclusions regarding the significance of impacts. Consequently, Natural England wish to see reasurance from the Applicant that they can achieve this, by confirming their planned disposal locations within the much smaller areas now available to them. |  | The applicant has not identified potential spoil disposal sites so we are unable to understand the potential impacts on marine process receptors, noting that the WCS for each receptor permitted under this proposed MDS would be completely unrealistic. Based on our discussions with the Applicant, we understand that the preferred method for sandwave clearance would result in the side casting or material or liquification of sediment using CFE, therefore the use of Trailing Suction Hopper Dredging (TSHD) and the storage and subsequent disposal of material is expected to be limited and more likely within the array than the cable corridor. Although this gives some reassurance that the risks associated with this method are lower than the current WCS would imply, without more specific information, or a refinement of the use of TSHD reflected in the MDS, we reamin unable to demonstrate this through assessment based on the information provided. In regard to Smithic Bank, in G5.33, the applicant has indicated that sediment will be retained within the system and will not be stored and disposed of. This gives some reassurance that the risk of impact impact of sediment disposal on nearshore receptors is reduced, however this does not give the same reassurance for offshore receptors such as Holderness Offshore MCZ (and priority habitat - see Benthic comments). Beyond this examination we would welcome further discussion with the Applicant as to how these "contingency" activites can be better reflected within the MDS to avoid overly precautionary/unrealistic worst case scenarios. |  | Natural England notes the revision to the project to the project description confirming that TSHD will not be used within Smithic Bank, however our overarching concern remains. |  | Natural England notes the revision to the project description confirming that TSHD will not be used within Smithic Bank, however our overarching concern remains. |  | No
E15 | 23 | The potential impacts of vessels and equipment in the construction/decommissioning and operational phases of the project should also be considered. For example, there is potential for jack-up vessels or vessels with several anchors to hold station to cause indentations on the seabed. |  | We maintain that all impacts associated with the proposal that have the potential to be significant either alone or on a cumulative basis should be considered. Consequently the impact of jack-up legs and anchor placements on the seabed, waves, currents, and sediment regime should have been included in the assessment. Ideally, the worst-case scenario for these effects should be assessed for the different phases of the project. However, it should be noted that in this instance Natural England have given this comment a yellow RAG status on the basis that the inclusion of such an assessment is unlikely to make a significant material difference in this instance. | [11 empty] | We maintain that all impacts associated with the proposal that have the potential to be significant either alone or on a cumulative basis should be considered. Consequently the impact of jack-up legs and anchor placements on the seabed, waves, currents, and sediment regime should have been included in the assessment. Ideally, the worst-case scenario for these effects should be assessed for the different phases of the project. However, it should be noted that in this instance Natural England have given this comment a yellow RAG status on the basis that the inclusion of such an assessment is unlikely to make a significant material difference in this instance. |  | Yes
E16 | 5, 12, 13 & 5-61 | Climate Change “Assuming the SMP policy of NAI remains unchanged in the future, the best estimates of retreat distance for the short term (0 to 20 years) and medium term (20 to 50 years) would be around 33 m and 82 m, respectively (Environment Agency 2020), based on present conditions.” This does not take into account of the influence of climate change impacts (e.g. sea level rise) as required within paragraph 5.5.7 of NPS EN-1. These predictions are key to understanding the potential for infrastructure to become exposed throughout the project lifetime and the subsequent requirement for remedial works. In addition, giving the dynamic nature of this coastline it is imperative that the ongoing need for remedial works beyond the life span of the project are fully considered. Given the sensitivity of the Holderness Coastline, potential scenarios should be modelled to allow assessment of the potential impacts again taking account of the potential impact of climate change such as vertical lowering of Smithic bank due to sea level rise causing partial reduction in wave sheltering poteritally impacting cliff erosion rates. Cliff erosion rates should be provided that take into consideration increased rates of sea level rise. Moreover, estimated cliff erosion rates should be provided for the entire lifespan of the project, incorporating increased rates of sea level rise. Although climate change effects are explored within section 1.7.11 of the ES chapter, the modelling presented within the chapter is based on present conditions and does not take account of the potential impacts of climate change. As highlighted within the Environmental Statement itself, climate change and more specifically sea level rise, has the potential to impact on marine process receptors, particularly in the nearshore area. For example, an increase in sea level rise could place vertical profile of Smithic Bank lower in the tidal frame which may lead to a reduction in wave sheltering effects, which may in turn lead to increase cliff erosion along the Holderness Coast. Natural England advise that to ensure the assessment incorporates the predicted impacts of climate change, modelled predictions should incorporate potential climate change scenarios. |  | Whilst the Applicant has considered long-term average cliff recession rates in the planning of the HDD TJB locations inland, they have not included estimates of changes to the intertidal area due to climate change/sea level rise, or through the project lifetime. Similarly, there is no consideration of changes to the Holderness Cliff due to the coastal access ramp, changes to the coastline linked to lowering of Smithic Bank due to the proposed development and climate change/sea level rise. We would also wish to seek clarification of the anticipated need for remedial works for landfall infrastructure beyond the lifetime of the project, as we note it is the Applicant’s position that there is no requirement for remediation plans. Therefore, we would advise that annual monitoring of cliff retreat and beach lowering rates over the lifetime of the project should be carried out in order to assess cliff/beach stability and cable exposure. |  | No change |  | Natural England is waiting for the Marine Processes supplimanty reports before commenting on other Marine Process issues. |  | Natural England's concerns remain regarding: (a) the anticipated requirement for any remedial works to infrastructure at Landfall beyond the lifetime of the project and any associated climate change impacts, and (b) increased lowering of, or morphological change to, Smithic Bank due to remedial works, cable protection/crossings at or near the sandbank, and additional impacts due to climate change. We are currently awaiting further information from the Applicant on the beach access ramp, and more detailed information regarding the Dogger Bank A & B Cable Crossing and its location relative to the eastern flank of Smithic Bank. |  | Our concerns remain regarding management of the export cable through the lifetime of the project, with particular regard to climate change effects, sea level rise, lowering of Smithic Bank etc. Limited information has been provided on the anticipated requirement for remedial works to infrastructure at landfall or in the nearshore over the lifetime of the project (and beyond should infrastructure remain in situ following decommissioning). This should be borne in mind by the ExA when considering the potential long-term impacts of landfall infrastructure. We also consider that the implications of leaving landfall infrastructure in situ needs to be considered in the context of future climate change-driven coastal change as part of the decommissioning plan. |  | No change |  | Our concerns remain regarding management of the export cable through the lifetime of the project, with particular regard to climate change effects, sea level rise, lowering of Smithic Bank etc. Limited information has been provided on the anticipated requirement for remedial works to infrastructure at landfall or in the nearshore over the lifetime of the project (and beyond should infrastructure remain in situ following decommissioning). This should be borne in mind by the ExA when considering the potential long-term impacts of landfall infrastructure. We also consider that the implications of leaving landfall infrastructure in situ needs to be considered in the context of future climate change-driven coastal change as part of the decommissioning plan. |  | No
Landfall
E17 | 4 & 70 | Identification of key receptors of the landfall Natural England do not agree that all the landfall receptors have been fully identified and assessed. As indicated in Point 1 above, several receptors that may potentially be influenced by impacts in the landfall area have not been included in Table 1.6. These include the following designated sites: • Holderness Inshore MCZ (including Spurn Head Geological Feature) • Humber Estuary SAC, SPA (supporting habitat), Ramsar, SSSI. • Dimlington Cliffs SSSI In addition, in section 1.7.6.7, Smithic Bank is identified as a local sediment store for material supplied through cliff erosion. Consequently, Smithic Bank should be considered a receptor of the landfall works. It will be important to consider potential impacts to longshore transport within the MCZ where the erosion of the Holderness cliffs and beaches provide a source of coarse and fine sediment that are transported south to Spurn Head and offshore sandbanks by waves and currents. Fine and medium sands can be transported south to the Lincolnshire coast which may bring other designated sites into scope. Therefore, any changes to this longshore drift resulting from this project could cause erosion or accretion of intertidal habitat and influence the morphology of the spit. Given the sparsity of baseline characterisation surveys of the Holderness coastal zone and Smithic Bank, significant environmental effects on the Holderness MCZ and other designated features cannot be ruled out at this stage. |  | Natural England position remains unchanged. |  | Natural England position remains unchanged. |  | Natural England position remains unchanged. |  | We are awaiting further information on the location of the beach access ramp. The Holderness Inshore MCZ has not been identified as a receptor within the Marine Processes chapter, nor have further afield receptors such as the Humber Estuary SAC, SPA, Ramsar, SSSI or the Dimlington Cliffs SSSI. In turn, potential impacts to these sensitive receptors due to the Landfall works. Therefore, Natural England's position remains unchanged. In addition, there is evidence to suggest that there is sediment exchange between the Holderness Coast and Smithic Bank, so we cannot rule out potential adverse effects to the sandbank structure and function due to the Landfall works. Moderate changes to the sandbank elevation or morphology could provide significant variations in wave power at the shoreline which could, in turn, modify the shoreline response to individual storms and substantially change shoreline morphology over the long-term. This has not yet been sufficiently assessed in terms of the requirement and impacts of any cable protection on Smithic Bank, cable remediation/replacement, the location of the Dogger Bank A & B Cable Crossing (we have advised that the applicant seeks the most up to date information on the Dogger Bank A&B layout given that their lanfall works have commenced). Therefore, at this stage we cannot rule out significant effects to the Holderness Coast, Holderness MCZ and other designated features along this coastline. |  | As highlighted in E1 above, we maintain our advice that all marine process receptors should be identified and assessed within the Environmental Statement. We ideally would have liked to have seen this addressed through an update to the Marine Processes chapter of the ES to ensure full consideration and a clear audit trail, however we do not believe there is sufficient time remaining within the examination for this to be addressed. Consequently we now offer revised advice based on whether we consider the receptors to have been adequately identified within the Applicant's additional submissions: Holderness Inshore MCZ - Whilst not considered within the ES or supplementary material, we are content that impacts to this receptor can be addressed through the MCZ assessment. Humber Estuary SAC, SPA, Ramsar, SSSI - Whilst not considered as a receptor in the ES or supplementary material, we are content that the impacts to this receptor can be addressed within the HRA with the exception of the SSSI. However, although the SSSI includes features that lie outwith the SAC/SPA/Ramsar, it is not expected that the conclusions relating to the SSSI would be materially different to those for the N2K sites. Dimlington Cliffs SSSI - This site is not considered as a receptor in the ES or supplementary material. As SSSI impacts are usually considered within the ES, and this SSSI does not underpin another designation, it will not be captured in other assessments. |  | No change |  | As highlighted in E1 above, we maintain our advice that all marine process receptors should be identified and assessed within the Environmental Statement. We ideally would have liked to have seen this addressed through an update to the Marine Processes chapter of the ES to ensure full consideration and a clear audit trail, however we do not believe there is sufficient time remaining within the examination for this to be addressed. Consequently we now offer revised advice based on whether we consider the receptors to have been adequately identified within the Applicant's additional submissions: Holderness Inshore MCZ - Whilst not considered within the ES or supplementary material, we are content that impacts to this receptor can be addressed through the MCZ assessment. Humber Estuary SAC, SPA, Ramsar, SSSI - Whilst not considered as a receptor in the ES or supplementary material, we are content that the impacts to this receptor can be addressed within the HRA with the exception of the SSSI. However, although the SSSI includes features that lie outwith the SAC/SPA/Ramsar, it is not expected that the conclusions relating to the SSSI would be materially different to those for the N2K sites. Dimlington Cliffs SSSI - This site is not considered as a receptor in the ES or supplementary material. As SSSI impacts are usually considered within the ES, and this SSSI does not underpin another designation, it will not be captured in other assessments. |  | No
E18 | 6 & 15 & 19 | Intertidal Access Ramp Insufficient detail is provided in relation to the intertidal access ramp to allow assessment of potential impacts on receptors (including the Holderness Cliffs and foreshore). Although it is the intention that the ramp only be in place for the installation phase (36 months) structure, it needs to be demonstrated that its installation will not result in long-lasting impacts on the Holderness Cliffs or beach at the landfall location, which may in turn give rise to impacts to other sensitive receptors. We would wish to see an assessment of the potential impacts of this beach access ramp to cliff stability. Consequently, until addtional information is provided Natural England is unable to exclude the potential for significant impacts to a number of receptors, including designated sites such as Flamborough Head SAC, Humber Estuary SAC, SPA, Ramsar and SSSI, Holderness Inshore MCZ and Dimlington Cliffs SSSI. To address this, we wish to see a full and detailed assessment of: the potential impacts of the access ramp on coastal processes and geomorphology and consideration of how any impacts will be managed; assessment of the implications for the Shoreline Management Plan (noting the policy for this area is No Active Intervention), and the effects on marine ecology and protected sites. It should be noted that the requirement for a beach access ramp has not been included in previous iterations of this ES chapter and has therefore not been considered throughout the evidence plan process (EPP). |  | Whilst we are reassured that the temporary access ramp only partially encroaches on the very upper intertidal zone, and is unlikely to interfere with beach processes (RR-029-5.36; RR-029-5.37), there still remains the concern that the ramp will be installed at a low point of a rapidly eroding cliff. Any works that result in the lowering of the cliff will need to consider the impact on flood risk from wave action and spray. The impact of the beach access ramp on cliff stability and cliff erosion has not been fully considered. Similarly the potential impact of accelerated cliff erosion needs to be considered. Natural England would welcome further discussion with the applicant on this issue. |  | No change |  | No Change |  | At ISH4, it was agreed that the Applicant would give further consideration to the definition and mapping of the eastern boundary of Works Area 9d (temporary ramp to beach) on the Works Plans as the geographical position of Mean High Water Springs varies according to beach level, and if it moved westward the base of the ramp could intrude into the intertidal zone. Therefore, we await further information from the Applicant on the location of the temporary access ramp relative to MHWS. This will allow us to assess whether there might potentially be any impacts to the coast, coastal processes, and designated sites. |  | Natural England have reviewed the location of the intertidal access ramp provided following ISH4 (REP4--038). We also note the Applicants comments in G5.33 (REP5a-017) with regard to ERYC not having any additional requiirements but defering any intertidal impacts to MMO. Natural England's concerns were/are relating to changes in erosion downstream of the ramp, in terms of beach and cliff profile changes owing to the ramp acting as a groyne. However, if the ERYC is satisfied with the information presented by the Applicant, then Natural England will close this issue out. (The issue remains yellow because the Applicant did not provide an adequate assessment of the beach access ramp in its submission and the ramp was not considered throughout the Evience Plan Process). |  |  |  | Natural England have reviewed the location of the intertidal access ramp provided following ISH4 (REP4--038). We also note the Applicants comments in G5.33 (REP5a-017) with regard to ERYC not having any additional requiirements but defering any intertidal impacts to MMO. Natural England's concerns were/are relating to changes in erosion downstream of the ramp, in terms of beach and cliff profile changes owing to the ramp acting as a groyne. However, if the ERYC is satisfied with the information presented by the Applicant, then Natural England will close this issue out. (The issue remains yellow because the Applicant did not provide an adequate assessment of the beach access ramp in its submission and the ramp was not considered throughout the Evience Plan Process). |  | Yes
E19 | 24 & 25 | HDD exit pits It is vital that the seabed profile is restored following the excavation of exit pits (particularly given the sensitivities of this area). Material from elsewhere should not be brought in for reinstatement. There should be an element of sorting of sediment to enable the sediment structure to be reinstated. The appropriate storage of material should be secured in the DCO/dML as mitigation. Furthermore, there is no mention of the reinstatement of the seabed profile following backfilling of the exit pits. It would be useful to provide an assessment of the potential range of change in intertidal/subtidal elevation and coastal retreat over the lifetime of the project following reinstatement. Natural England, therefore, cannot agree with the assessment of significance of this impact pathway. |  | We welcome the Applicant’s commitment to include these details in the Cable Specification and Installation Plan. If this can be conditioned in the dML or outlined in a certified document then we would be content to close this matter. |  | No change - We welcome the Applicant’s commitment to include these details in the Cable Specification and Installation Plan. If this can be conditioned in the dML or outlined in a certified document then we would be content to close out this matter. |  | The Applicant has provided reasurance that details requested by Natural England in relation to the restoration of profile of the excavated HDD exit pits will be provided with the Cable Specification and Installation Plan which is conditioned in the DML (condition 13). As of deadline 4 Natural England have been unable to review these documents in full and will provide an update at deadline 5. We note that it is a last resort to use matterial from elsewhere in the backfill of these exit pits, Natural England would continue to advise against this when the cable specification and installation plan is submitted to the MMO for sign off. |  | Natural England's comments remain unchanged. |  | The current version of the outlined Cable Specification and Installation plan does not mention HDD exit pits. Natural England would need to see this document updated to include our advice on restoring the seabed profile following excavation of exit pits before the issue can be resolved. |  | Natural England welcomes the updates to the cable specification plan which highlight the locations that additional sediment will be extracted from as a contingency measure in order to allow full reinstatement of the HDD exit pits should the excavated material winnow away. Whilst this is useful additional clairty, we would also like to see information presented in relation to the storage of material and the steps that will be taken to reduce the risk of material being lost, to therefore limit the need for this contingency. |  | Natural England welcomes the updates to the cable specification plan which which make it clearer that the intetnion is to reinstate with the excavated sediment and that extraction from elsewhere would be a contingency measure. |  | Yes
E20 | 49 | Construction Impacts The use of jack up barges should also be included in the assessment of turbulent wakes and scour in the nearshore if applicable. |  | We advise that it is standard practice for many offshore wind farm applications to consider the impact of jack-up legs and anchor placements on the seabed. We would have liked to have seen these impacts incorporated into the assessments. However, on this occasion we are satisfied that this wouldn't materially affect the outcome of the overall assessment. | [11 empty] | We advise that it is standard practice for many offshore wind farm applications to consider the impact of jack-up legs and anchor placements on the seabed. We would have liked to have seen these impacts incorporated into the assessments. However, on this occasion we are satisfied that this wouldn't materially affect the outcome of the overall assessment. |  | Yes
E21 | 50 | Cofferdams It is unclear if the three-month period of cofferdam placement is the total amount of time cofferdams will be in situ, or if each cofferdam could be in place for a maximum of 3 months (with no more than 3 in situ at any one time). This should be clarified in order for Natural England to consider the conclusions of this section. Once clarified, this timeframe should be secured within the DCO/dML conditions. |  | We welcome clarification of the duration for cofferdam placement in the nearshore. The Applicant has suggested that as the DML will be limited to what has been assessed, a condition securing these parameters is not required as it is inherently secured. The However, Section 1.11.1.118 of the ES is misleading as its states that the cofferdams will be in place for a three-month period, yet the Applicant has now clarified that cofferdams could be in place for three periods of three months to account for up to eight HDD exit pits. We advise that the MDS for cofferdam placement duration should be secured within the dMLs to ensure clarity on this issue post consent. |  | No change - We advise that the MDS for cofferdam placement duration should be secured within the dMLs to ensure clarity on this issue post consent. |  | No Change |  | In ISH4 the Applicant has now clarified that the three-month period refers to each individual cofferdam and in theory there could be three sets of three-month construction periods to account for all the exit pits. We also note that the Applicant believes a DML condition is not required to control this. We would advise that this timeframe, now clarified, should be clearly secured within the DCO/dML conditions for the avoidance of doubt. |  | Please see our previous comment. |  | No change |  | In ISH4 the Applicant has now clarified that the three-month period refers to each individual cofferdam and in theory there could be three sets of three-month construction periods to account for all the exit pits. We also note that the Applicant believes a DML condition is not required to control this. We would advise that this timeframe, now clarified, should be clearly secured within the DCO/dML conditions to ensure that there is calrity over what is consented as well as what has been assessed in the ES. |  | No
Export cable corridor
E22 | 7 & 15 | Identification of key receptors of the ECC Natural England does not agree that all the receptors of the ECC have been identified and assessed. As indicated in Point 1 above, there are a number of designated site receptors which may be influenced by impacts in the Export Cable Corridor (ECC) either directly or indirectly as a result of impacts to other marine process receptors. These therefore need to be considered. These include: • Holderness Inshore MCZ • Holderness Offshore MCZ • Flamborough and Filey Coast SPA • Flamborough SSSI • Humber Estuary SAC, SPA, SSSI and Ramsar • Greater Wash SPA • Southern North Sea SAC The potential for indirect impacts to the Holderness Coast from the ECC should also be explored. We are concerned that moderate elevation changes to the sandbank through construction/decommissioning (and maintenance) activities, and alterations to the sediment transport processes nearby due to the presence of the Dogger Bank A&B Cable Crossing, might modify the Holderness shoreline response to storm waves, and the Holderness shoreline morphology over the lifetime of the project/installed infrastructure. Consequently, direct and indirect effects on nearby designated sites and those further afield need to be carefully considered. |  | We look forward to receiving the Applicant’s proposed Source-Pathway-Receptor model for Smithic Bank. However, given the current uncertainty regarding the MDS for sandwave levelling and cable protection, we cannot rule impacts to other marine process receptors such as the MCZ and other designated areas. Our position remains unchanged. |  | We are awaiting the outcome of the Marine Processes Supplementary Works and Clarification Note at Deadline 3. |  | We are awaiting the outcome of the Marine Processes Supplementary Works and Clarification Note which is delayed until Deadline 4. |  | Natural England's concerns remain regarding potential alterations to Smithic Bank and, in turn, the Holderness Coast due to the presence of the Dogger Bank A & B Cable Crossing, in addition to the presence of any cable protection on the sandbank, and any cable remediation or replacements works over the lifetime of the project. We have provided our detailed comments on this matter in a joint memo with the MMO and Cefas to the Applicant. We aknowlege that due to the complexities of the marine environment it would be unlikely that the risks could be removed entirely, but we consider that they can and should be further mitigated and reduced. Whilst we cannot yet rule out impacts, direct or indirect, to nearby designated sites or sensitive receptors, we are keen to work with the applicant to further explore measures that will reduce the risk as far as possible. Please also see our earlier comments regarding the inclusion of the Holderness MCZ within the Marine Process receptors list for this chapter. |  | As highlighted in E1 above, we maintain our advice that all marine process receptors should be identified and assessed within the environmental statement. We ideally would have liked to have seen this addressed through an update to the Marine Processes chapter of the ES to ensure full consideration and a clear audit trail, however we do not believe there is sufficient time remaining within the Examination for this to be addressed. Consequently we now offer revised advice based on whether we consider the receptors to have been adequately identified within the Applicant's additional submissions: Holderness Inshore MCZ and Holderness Offshore MCZ - Whilst not considered withing the ES or supplementary material, we are content that impacts to these receptors can be addressed through the MCZ assessment. Humber Estuary SAC, SPA, Ramsar, SSSI - Whilst not considered as a receptor in the ES or supplementary material, we are content that the impacts to this receptor can be addressed within the HRA with the exception of the SSSI. Although the SSSI includes features that lie outwith the SAC/SPA/Ramsar, it is not expected that the conclusions relating to the SSSI would be materially differnt to those for the N2K sites. Greater Wash SPA and Southern North Sea SAC - Although not considered as a receptor within the ES, we are content that impacts to these receptors can be addressed through the HRA. We are content that the Holderness Coast was identified as a potential receptor of the array within Marine Processes Supplementary Works and Clarification Note, although we do not support some of the conclusions drawn. On the basis that all of these receptors have either been considered within supplementary submissions, or have the potential to be appropriately considered within MCZ assessments and HRA we will amend the RAG status to yellow on the basis that we do not expect further action from the applicant on this matter. |  |  |  | As highlighted in E1 above, we maintain our advice that all marine process receptors should be identified and assessed within the environmental statement. We ideally would have liked to have seen this addressed through an update to the Marine Processes chapter of the ES to ensure full consideration and a clear audit trail, however we do not believe there is sufficient time remaining within the Examination for this to be addressed. Consequently we now offer revised advice based on whether we consider the receptors to have been adequately identified within the Applicant's additional submissions: Holderness Inshore MCZ and Holderness Offshore MCZ - Whilst not considered withing the ES or supplementary material, we are content that impacts to these receptors can be addressed through the MCZ assessment. Humber Estuary SAC, SPA, Ramsar, SSSI - Whilst not considered as a receptor in the ES or supplementary material, we are content that the impacts to this receptor can be addressed within the HRA with the exception of the SSSI. Although the SSSI includes features that lie outwith the SAC/SPA/Ramsar, it is not expected that the conclusions relating to the SSSI would be materially differnt to those for the N2K sites. Greater Wash SPA and Southern North Sea SAC - Although not considered as a receptor within the ES, we are content that impacts to these receptors can be addressed through the HRA. We are content that the Holderness Coast was identified as a potential receptor of the array within Marine Processes Supplementary Works and Clarification Note, although we do not support some of the conclusions drawn. On the basis that all of these receptors have either been considered within supplementary submissions, or have the potential to be appropriately considered within MCZ assessments and HRA we will amend the RAG status to yellow on the basis that we do not expect further action from the applicant on this matter. |  | Yes
E23 | 59 & 66 | Environmental value of key receptors The form and function of Smithic Bank are equally important (to cliff erosion and longshore drift of Holderness coast) since the sandbank protects the coastal hinterland, including the town of Bridlington. Moreover, lowering of Smithic Bank due to HP4 related project impacts could have a significant impact on longshore sediment transport. Therefore, we would advise that both Smithic bank and Holderness Coast have high environmental value. (Section 1.11.2.41) |  | We maintain our position that both the Holderness Coast and Smithic Bank are receptors of high environmental value. |  | No change - We maintain our position that both the Holderness Coast and Smithic Bank are receptors of high environmental value. |  | No change |  | Our comments remain unchanged. |  | We maintain our earlier position, that Smithic Bank and the Holderness Coastline should be considered of high environmental value, for the reaons previously stated. Professor Mike Elliot covers this point, agreeing that Smithic bank is of high environmental value in REP5-010 Section 2.3.1.3. At this stage in the Examination we do not expect that the Applicant will make further revisions to their assessments, therefore we would advise that the ExA and SoS should have regard to the high value of this receptor by ensuring that the risk of potential impacts are managed as far as possible, and that approprate monitoring to detect changes and trigger any necessary counter measures is secured. |  | No change |  | We maintain our earlier position, that Smithic Bank and the Holderness Coastline should be considered of high environmental value, for the reaons previously stated. Professor Mike Elliot covers this point, agreeing that Smithic bank is of high environmental value in REP5-010 Section 2.3.1.3. At this stage in the Examination we do not expect that the Applicant will make further revisions to their assessments, therefore we would advise that the ExA and SoS should have regard to the high value of this receptor by ensuring that the risk of potential impacts are managed as far as possible, and that approprate monitoring to detect changes and trigger any necessary counter measures is secured. |  | No
E24 | 11 & 81 | Cable Crossings The figure throughout both the ES and Technical report describe different numbers of cable crossings with Dogger Bank A&B (12/24), This should be consistent and accurately represented in the draft DCO/dML. The MDS cable crossing footprint area needs also to be consistent. |  | We welcome clarification from the Applicant that two pairs of Dogger Bank A&B cables (i.e. four cables) will cross six Hornsea 4 export cables. However, we would advise that for consistency the same definition/quantity should be used throughout reporting. | [11 empty] | We welcome clarification from the Applicant that two pairs of Dogger Bank A&B cables (i.e. four cables) will cross six Hornsea 4 export cables. However, we would advise that for consistency the same definition/quantity should be used throughout reporting. |  | Yes
E25 | 7 | Smithic Bank Smithic Bank is a headland-associated banner type bank which extends south from Flamborough Head by over 12km. Smithic Bank provides shelter for the Holderness coast from wave exposure and acts as a sediment store that feeds the Holderness Coast, Holderness Inshore MCZ and the wider regional sediment transport pathways to areas further afield such as the Humber Estuary. Accordingly, Natural England considers Smithic Bank to be of high environmental value. |  | The Applicant states that Smithic Bank provides partial shelter from waves to a small section of the Holderness Coast (which in turn is rapidly eroding) RR-029-5.42. We concur that Smithic Bank plays a vital role within the Holderness coastal system not only providing a buffer between the shoreline and approaching waves, but also influencing longshore sediment transport, and shoreline morphology. Therefore, we consider Smithic Bank to be of high environmental value. |  | We are awaiting the outcome of the Marine Processes Supplementary Works and Clarification Note at Deadline 3. |  | No change |  | Natural England's comment remains unchanged. Smithic Bank acts as an effective offshore wavebreak, along with Flamborough Head, it shelters the northern quarter of the Holderness Coastline and the town of Bridlington. It is also a potential nursery and feeding ground for several fish species, which could in turn support the birds nesting and roosting on Flamborough Head. (Boyes et al. 2017) Therefore, we continue to consider Smithic Bank to be of high environmental value. Boyes, S.; Barnard, S. and Elliott, M. (2017). The East Riding Coastline: Past, Present and Future. Institute of Estuarine and Coastal Studies. (IECS). The University of Hull. April 2017, 53pp. |  | See E23 above. See also E26, E28 |  | No change |  | See E23 above. See also E26, E28 |  | No
E26 | 17 & 62 | Dogger Bank A&B Cable Crossings Natural England notes and welcomes that the Dogger Bank cable crossing will be positioned east of Smithic Bank and seaward of the 20m depth contour. However we remain concerned that the Dogger Bank A&B Crossing (and associated cable protection) is still sufficiently close to Smithic Bank, and in sufficiently shallow water, as to potentially affect the nearshore wave-current and sediment transport regimes. This, in turn could affect the integrity and morphology of Smithic Bank. Therefore, we advise that further assessment be carried out to provide a better understanding of the impact of the Dogger Bank A&B cable crossing on Smithic Bank and the nearshore zone. The cumulative impacts of the Hornsea Four Dogger Bank A&B, and Scotland to England Green Link 2 cables (and their protection) should be considered over the long-term (i.e. lifespan of the crossing). |  | The Applicant states that the figures presented in Volume A2, Chapter 1 and Volume A5, Annex 1.1, provide a representation only of the Hornsea Four/Dogger Bank A&B Cable Crossing footprint area (approx.1000m by 2000m), rather than the specific location of the much smaller crossing. The cable crossing footprint area adopted in the hydrodynamic modelling in Volume A5, Annex 1.1 measured 500m by 770m. In order to understand the scale and magnitude of the impacts of the Dogger Bank Cable Crossing on nearshore sediment transport pathways and long-term erosion/accretion, it is important that a realistic worst-case cable crossing footprint area be presented. Furthermore, the hydrodynamic modelling was not extended to include sediment transport and long-term erosion/accretion. Therefore, we advise that adverse effects on nearshore sediment transport cannot be ruled out at this stage. Whilst the Applicant has modelled changes to the hydrodynamic regime due to the Dogger Bank Cable Crossing, there is no assessment of changes to the nearshore sediment transport regime, or long-term erosion or accretion trends. Therefore, we cannot rule out adverse environmental impacts, until this has been assessed. |  | We are awaiting the outcome of the Marine Processes Supplementary Works and Clarification Note at Deadline 3. |  | Natural England have reviewed G3.8 Chart depicting the Dogger Bank A and B export cable crossing rock protection. We note that the MMO have discharged Dogger Bank A export cable documents and therefore a more precise location for Dogger Bank A export cables is available through the MMO public register and this chart could be refined further. Equally further assessments or evidence should be provided to provide better understanding of cable protection at crossings on smithic bank and the nearshore zone. |  | We have provided a joint memo (NE/MMO/Cefas) to the Applicant in which we have reiterated our concerns regarding the location of the Dogger Bank Cable Crossing relative to Smithic Bank. The Applicant has agreed to provide a more up-to-date map showing the location of the Dogger Bank Cable Crossing relaive to the eastern flank of Smithic Bank and to investigate siting the corssing as far away from Smithic Bank as possible within their order limits. We will review this information when we receive it, and update our comments in this Log if appropriate. |  | Natural England notes the response to our deadline 5 advice. The Applicant has marshalled all of the evidence that we are aware of, nevertheless with the project as currently designed we are not able to exclude the risk of significant/adverse effects arising. NE's advice now focusses on reducing the level of risk to designated sites and associated receptors, through identifying design changes and advising on the monitoring required to detect change and trigger counter measures. Based on the proposed cable crossing location and the MDS for the rock berm height 3m (maximum design for anchor strick protection) we would be unable to rule out the potential for significant impacts to Smithic Bank. However, we note that a typical design rock berm of 1.8m could offer sufficient protection from fishing gear. Should the MDS for the berm height be set at 1.8m we would have confidence that the risk of impact was reduced to a more acceptable level. We also advise that appropriate monitoring of the order limits between the Holderness Coast and 1km seawards of the Cable Crossing is secured in the DCO/dML, and that additional mitigation/remediation can be triggered through an appropriate mechanism if the impacts are greater than anticipated. We would also like to see options to move the crossing further seaward explored as part of the layout plan, to ensure that the mitigation hierarchy (avoid/reduce/mitigate) continues to be followed in the post consent phase of the project. We would welcome the inclusion of this as a commitment and would like to see this appropriately secured within the DCO/dML. |  | No change |  | Natural England notes the response to our deadline 5 advice. The Applicant has marshalled all of the evidence that we are aware of, nevertheless with the project as currently designed we are not able to exclude the risk of significant/adverse effects arising. NE's advice now focusses on reducing the level of risk to designated sites and associated receptors, through identifying design changes and advising on the monitoring required to detect change and trigger counter measures. Based on the proposed cable crossing location and the MDS for the rock berm height 3m (maximum design for anchor strick protection) we would be unable to rule out the potential for significant impacts to Smithic Bank. However, we note that a typical design rock berm of 1.8m could offer sufficient protection from fishing gear. Should the MDS for the berm height be set at 1.8m we would have confidence that the risk of impact was reduced to a more acceptable level. We also advise that appropriate monitoring of the order limits between the Holderness Coast and 1km seawards of the Cable Crossing is secured in the DCO/dML, and that additional mitigation/remediation can be triggered through an appropriate mechanism if the impacts are greater than anticipated. We would also like to see options to move the crossing further seaward explored as part of the layout plan, to ensure that the mitigation hierarchy (avoid/reduce/mitigate) continues to be followed in the post consent phase of the project. We would welcome the inclusion of this as a commitment and would like to see this appropriately secured within the DCO/dML. |  | No
E27 | 52, 53, 61 & 64 | Dogger Bank A&B Cable Crossings Section 1.11.2.12 describes modelling of a MDS case for the combined rock berm occupying an area of 500m by 1000m and up to 3m high. The wave and tidal modelling in the Technical Report have adopted a cable crossing footprint area of 500m by 770m (by 3m high), yet in Figure 1.2 in the Marine Processes Chapter and Figure 5 in the Technical Report etc, this cable crossing area would appear to be significantly greater approximately 1000m x 2000m (2-2.5 times) than that used in modelling. The MDS for this cable crossing footprint should be stated in order to assess the worst-case scenario for marine processes. Therefore, we are concerned that the extent of scouring around the HP4/Dogger Bank A&B Cable Crossing could actually be 2 to 2.5 times greater than estimated. Given our comment above, and the uncertainty regarding the mobility of sediments at the Hornsea 4/Dogger Bank A&B Cable Crossing, we cannot agree that scouring at this cable crossing will have a negligible magnitude. Furthermore, there is the additional concern that the Hornsea 4/Dogger Bank A&B Cable Crossing is still not situated in sufficiently deep water as to avoid significantly reducing water depths and, dissipating storm wave energy, at a location just seaward of Smithic Bank. No impact assessment has been offered here for marine processes; therefore, we would wish to see this assessment carried out. We also cannot agree with the conclusions that the magnitude of impacts will be negligible to minor, nor that the significance of the effects on Smithic Bank, the Holderness Coast, and other sensitive receptors, will be slight for the project alone, and in-combination. |  | The Applicant states that the figures presented in Volume A2, Chapter 1 and Volume A5, Annex 1.1, provide a representation only of the Hornsea Four/Dogger Bank A&B Cable Crossing footprint area (approx.1000m by 2000m), rather than the specific location of the much smaller crossing. The cable crossing footprint area adopted in the hydrodynamic modelling in Volume A5, Annex 1.1 measured 500m by 770m. Our concern remains that there is sufficient uncertainty regarding the anticipated Dogger Bank cable crossing footprint area and thus, the scale and magnitude of its impacts on nearshore sediment transport pathways and long-term erosion/accretion. We advise that a realistic worst-case cable crossing footprint area needs to be presented. |  | No change - We advise that a realistic worst-case cable crossing footprint area needs to be presented. |  | No change |  | The Applicant has provided further clarification regarding the anticipated MDS for the Dogger Bank Cable Crossing, which we welcome. However, until we receive the updated information regarding the location of the cable crossing relative to the most up to date data showing Smithic Bank we cannot yet agree with the Applicant's conclusions that the magnitude of impacts will be negligible to minor, nor that the significance of effects on Smithic Bank, Holderness Coast, and other sensitive receptors will be slight for the project alone, and in-combination. |  | Please see our comments in E26 above. |  | No change |  | Please see our comments in E26 above. |  | No
E28 | 22, 51 & 63 | Cable Installation and use of cable protection at Smithic Bank We would be concerned if a 2km length of cable re-burial/de-burial occurred across Smithic Bank, potentially up to 7 times through the lifetime of the project, as is stated here. This highlights the need to fully assess the potential impacts of the cable installation across the project lifetime and to bring forward mitigation where needed. We remain concerned about the potential placement of any cable protection across Smithic Bank as this could lead to a reduction in water depth within the water column, and potentially lead to local scour and the formation of a barrier to sediment transport. Significantly altering the profile of the sandbank could have a significant impact on longshore drift, and in turn, could result in impacts to features much further afield. We advise that cable protection on or in close proximity of the Bank needs to be avoided, with evidence brought forward to demonstrate any separation distance is sufficient. It should be noted that as things stand, the Maximum Design Scenario would allow for an eventuality whereby rock protection was placed along the full length of the cables across Smithic Bank. |  | Whilst the Applicant advises that it is highly improbable that 2km length of cable will be re-buried seven times through the lifetime of the project on Smithic Bank, this MDS would still need to be assessed. Given that this is a highly improbably scenario we would welcome further refinement of the MDS. We look forward to reviewing the Applicant’s Clarification Note on the MDS which the plan to submit at Deadline 3. |  | No change - We look forward to reviewing the Applicant’s Clarification Note on the MDS which the plan to submit at Deadline 3. |  | We welcome the Applicant's commitment to reducing the requirement for cable protection across Smithic Bank to 5% of all cables across the sandbank, however based on the evidence currently available we can not support the use of any cable protection across Smithic Bank. Therefore, our position remains unchanged until we have reviewed the outcome of the Supplementary Works and Clarification Note for Marine Processes. Furthermore, we would wish to see how the Applicant responds to our concerns regarding cable re-burial/de-burial through the lifetime of the project. |  | We welcome the Applicant's commitment to reducing the requirement for cable protection across Smithic Bank to 5% of all cables across the sandbank, however based on the evidence currently available we can not support the use of any cable protection across Smithic Bank. In our joint NE/MMO/Cefas memo (14 June 2022) to the Applicant, we advised that we remain concerned with the installation of cables (and any associated cable protection) across or near Smithic Bank when considered in-combination with multiple developments (e.g. Dogger Bank A & B, SEGL2 etc). Successive cable installations and repair (and associated cable protection) could act cumulatively to increase morpholpgical alteration of the sandbank through the combined influence of sediment removal through dredging, and potential changes to sediment transport pathways arising from the presence of cable protection. Therefore, we would advise that a detailed assessment of the cumulative impacts of multiple developments on Smithic Bank be carried out. Similarly, the potential impact of cable reburial/replacement/remediation through the lifetime of the project (including climate change impacts) need to be adequately assessed. Given the complexity and unpredictable nature of the marine environment we acknowledge that it is likely to be difficult to remove the risk entirely. However, we consider that further options could be explored reduce the associated risk as far as possible. For example, avoiding cable protection on Smithic Bank completely, the bundling of cables through the nearshore area to reduce the number of instalations across Smithic Bank, the location of appropriate sediment disposal lcations to ensure that excavated sediment is retained within the Smithic Bank system. |  | Moderate elevation changes to the sandbank and significant changes to sandbank morphology through cable installation activities, associated cable protection, and remedial works by Hornsea Four alone, or in-combination with other developments, could alter the nearshore hydrodynamic regime, sediment transport (including longshore flux), shoreline response to storms, and alter shoreline morphology over the long-term. Please see AS-048 and our joint memo with MMO/Cefas for our advice on proposed mitigation and monitoring for Smithic Bank. Placement of cable protection on Smithic Bank: We seek a commitment to have no cable protection inshore of the 20m depth contour in order to avoid impacts to sediment transport, and we would wish to see this secured in the dML/DCO in order to reduce the potential for significant impacts/adverse effects. Should the ExA/SoS take an alternative view and consider that a 5% requirement can remain, it remains the case that a more detailed assessment would be required to understand the potential impacts of rock placement on Smithic Bank, both alone and cumulatively/in combination. As the detail of the likely scale and location of the rock placement will not be understood until post consent survey work has been undertaken to inform a cable burial risk assessment, we would advise that the DCO/dML should require that a plan is produced prior to construction that quantifies a more precise requirement (i.e. location and extent) within and around Smithic Bank and then revisits the findings of the Environmental Statement and subsequent updates. This plan would then need to be be subject to Assessment/HRA prior to discharge by the MMO. If electing to pursue this option, the ExA/SoS may wish to seek assurance from the Applicant that suitable alternatives/mitigation/remediation would be available should significant impacts be determined at this stage. |  | No change |  | Moderate elevation changes to the sandbank and significant changes to sandbank morphology through cable installation activities, associated cable protection, and remedial works by Hornsea Four alone, or in-combination with other developments, could alter the nearshore hydrodynamic regime, sediment transport (including longshore flux), shoreline response to storms, and alter shoreline morphology over the long-term. Please see AS-048 and our joint memo with MMO/Cefas for our advice on proposed mitigation and monitoring for Smithic Bank. Placement of cable protection on Smithic Bank: We seek a commitment to have no cable protection inshore of the 20m depth contour in order to avoid impacts to sediment transport, and we would wish to see this secured in the dML/DCO in order to reduce the potential for significant impacts/adverse effects. Should the ExA/SoS take an alternative view and consider that a 5% requirement can remain, it remains the case that a more detailed assessment would be required to understand the potential impacts of rock placement on Smithic Bank, both alone and cumulatively/in combination. As the detail of the likely scale and location of the rock placement will not be understood until post consent survey work has been undertaken to inform a cable burial risk assessment, we would advise that the DCO/dML should require that a plan is produced prior to construction that quantifies a more precise requirement (i.e. location and extent) within and around Smithic Bank and then revisits the findings of the Environmental Statement and subsequent updates. This plan would then need to be be subject to Assessment/HRA prior to discharge by the MMO. If electing to pursue this option, the ExA/SoS may wish to seek assurance from the Applicant that suitable alternatives/mitigation/remediation would be available should significant impacts be determined at this stage. Natural England note that the Applicant has provided an updated OMMP which includes monitoring at Smitic bank which broadly aligns with our advice, subject to revision and clarifications (See NE's D8 comments on the OMMP for full details). However we reiterate that this monitoring needs to inform the ned for additional mitigation or remediation if the impacts are greater than anticipated. |  | No
E29 | 43 | The Hornsea 4 export cable route crosses the southern part of Smithic Bank. The installation of cables and rock protection (and replenishment) in this area could result in the lowering of Smithic Bank or the alteration of its morphology. Additionally, Dogger Bank A& B export cables, necessitates the placement of a substantial amount of rock protection at each of the 24 cable crossing points, seawards of Smithic Bank. Moreover, the Scotland to England Green Link 2 project has indicated a similar landfall to Hornsea 4 and will potentially cross Smithic Bank. We are concerned that a significant area of cable installation activities and the addition of any cable protection may alter the elevation/profile of the sandbank. Moderate elevation changes to the sandbank could produce significant variations in wave power at the shoreline which will, in turn, modify the shoreline response to storms, and substantially change shoreline morphology. |  | It has been shown that moderate elevation changes to sandbanks like Smithic Bank could translate to an alteration in wave power at the shoreline and, in turn, a modification of the shoreline response to storms. Whilst we note that the Applicant considers that ‘cable installation is unlikely to lead to lowering of the bank profile’, there is insufficient evidence to rule out the adverse impacts described above. We also remain concerned that the cumulative impacts of a number of cable installations (i.e. HP4, Dogger Bank A&B, SEGL2) and any cable protection across Smithic Bank may affect the form and function of the sandbank. Moreover, we advise that the impacts of the HP4/Dogger Bank A&B cable crossing (with up to 3m of cable protection) within 20m water depth offshore of Smithic Bank have not been adequately assessed since the wave and tidal modelling was based on a significantly smaller cable crossing footprint area than the one identified in the Environmental Statement. We advise that an additional review is required for the Hornsea Four/Dogger Bank A&B cable crossing, based on the anticipated cable crossing footprint area, to assess changes to nearshore sediment transport processes and morphology over the lifetime of the project (and beyond).. We would also wish to see more robust evidence presented on the adverse effects on Smithic Bank, nearshore sediment transport processes, the Holderness coast, and nearby designated sites. We note that the Applicant is carrying out a Technical Review of the MDS in relation to cable protection across Smithic Bank, and we look forward to the Clarification Note regarding MDS justification. |  | No change |  | No change - Natural England await the Marine Processes Supplementary Reports at Deadline 4. |  | Please see our comments in E26-E28. |  | See comment in E28 above. |  | No change |  | See comment in E28 above. |  | No
E30 |  | Natural England is concerned that the Hornsea 4 development (alone and in-combination) might adversely affect the form and function of Smithic Bank, and, in turn, affect that of other marine process receptors such as the Holderness Coast, Holderness Inshore MCZ, Dimlington Cliffs SSSI, Humber Estuary SAC/SPA/Ramsar/SSSI, Flamborough Head SAC/SSSI. Consequently, we advise that the long-term impacts of (a) cable installation and cable protection across Smithic Bank (including the proposed 25% rock replenishment during the operational phase), and (b) the presence of the HP4/Dogger Bank A&B cable crossing, need to be addressed in terms of the risk of lowering of the sandbank and affecting its associated sediment transport processes. We would also advise that these impacts be considered over the lifetime of the project, also taking into consideration the impacts of climate change. |  | Natural England's position remains unchanged. |  | We are awaiting the outcome of the Marine Processes Supplementary Works and Clarification Note at Deadline 3. |  | No change - Natural England await the Marine Processes Supplementary Reports at Deadline 4. |  | Please see our comments in E26-E28. |  | We remain concerned with the potential impacts to the form and function of Smithic Bank, alone and in-combination, from the impacts cable protection, cable repair and replacement and cable remedial burial. We have suggested ways forward to reduce the impact of cable protection in cell E28 and monitoring of the cable corridor in E26 across smithic bank and in relation to the Dogger Bank cable crossing zone. This would be to confirm modelling predictions and assessments within the ES and inform the requirement for remedial measures. The Marine Processes Supplementary report REP4-043 confirms that bedform clearance for sandwaves will not occur across Smithic Bank (2.4.1.2), and clarifiation note on marine processes mitigation and monitoring (REP5a-017) states that sediment will be retained within the system. However neither of these points are secured in the DCO. |  | No change overall, however, Natural England notes and welcomes the revision to the project to the project description confirming that TSHD will not be used within Smithic Bank. |  | No change overall, however, Natural England notes and welcomes the revision to the project description confirming that TSHD will not be used within Smithic Bank. |  | No
E31 | 28 | Sandwave clearance It is stated that “There is expected to be a low sensitivity of these receptors to sandwave clearance, not least because of the expected absence of such features in this area.” However, if sandwave clearance is found to be required in the nearshore zone and, as stated in Section 1.11.1.23, the ‘scale of tidal advection is around 10km’, then this could affect sensitive coastal receptors. Therefore, the worst-case scenario should be considered here and assessed accordingly. The assessment of sensitivity only considers the fate of the sediment that is removed and does not address the potential impact of the removal on relevant receptors. Furthermore, sediment disposal locations have not been identified, and there is no evidence to support the assumption that “Once deposited, the sand removed from sandwaves is likely to re-join the same bedload transport environment that originally created and moved the bedforms.” (Para 1.11.1.26). Consequently, the impacts to receptors cannot be presumed to be of short-term duration. Based on the applicant’s rationale of focussing on nearshore receptors to the north of the sediment separation Zone, it is unclear why Smithic Bank has not been included in the assessment. However, it should also be noted that whilst the landfall location lies to the north of the longshore sediment transport path divide, this zone is only apparent when sediment movement is averaged over several years. At any given time, sediment transport could be predominantly to the north or south. Therefore, the impact to receptors to the south should also be considered (including the Holderness Inshore MCZ and the Holderness Coast). Again, Natural England highlight that the assessment should consider all sensitive receptors potentially impacted by sediment clearance along the full extent of cable corridor. To address this, the WCS should be considered and presented for plume spreading due to sandwave clearance in the nearshore. A schematic/map(s) should be provided showing the maximum sediment plume concentration, extent, persistence and any associated bed level changes within the array and along the export cable corridor. Marine Process receptors should be clearly identified on the map/schematic. |  | We remain concerned that a number of sensitive receptors (such as the MCZ and Smithic Bank) have been omitted from this assessment despite their proximity to the proposed sandwave excavation activities. |  | No change - We remain concerned that a number of sensitive receptors (such as the MCZ and Smithic Bank) have been omitted from this assessment despite their proximity to the proposed sandwave excavation activities. |  | No change |  | The Marine Processes Supplementary report REP4-043 suggests that bedform clearance for sandwaves will not occur across Smithic Bank (2.4.1.2), which we welcome. However, this was not discussed in the MDS paper and it is not yet secured in the DCO. As noted in E2, we welcome the changes made to the MDS in relation to bedform clearance volume, however, there has been no reduction in sandwave clearance area. We reiterate our earlier advice, for bedform clearance to be reduced and carried out only where bedforms are found to be present. |  | We remain concerned that a number of sensitive receptors (such as the MCZ and Smithic Bank) have been omitted from this assessment despite their proximity to the proposed sandwave excavation activities and associated sediment disposal. Uncertainty also remains regarding whether Smithic Bank is a closed sedimentary system, or 'leaky' and thus, whether any sediment removed and then re-deposited will be retained within this system. As noted in E2, we welcome the changes made to the MDS in relation to bedform clearance volume, however, there has been no reduction in sandwave clearance area. We reiterate our earlier advice, for bedform clearance to be reduced and carried out only where bedforms are found to be present and that the MDS should be refined accoridingly. The Marine Processes Supplementary report REP4-043 confirms that bedform clearance for sandwaves will not occur across Smithic Bank (2.4.1.2), and clarifiation on marine processes mitigation and monitoring (REP5a-017) states that sediment will be retained within the system. However neither of these points are secured in the DCO. Noting that this issue as originally raised within our Relevant Reps Related to the nearshore area, we would be content to close out this matter should the mitigation for Smithic Bank be secured within the DCO. |  | Natural England notes the revision to the project description confirming that TSHD will not be used within Smithic Bank. This along with the confirmation that bedform clearance will not occur across smithic bank resduces the risk from smothering and increase in suspended sediment concentration to nearby receptors however until this mitigation is secured within the DCO we can't close out this issue. |  | Natural England notes the revision to the project description confirming that TSHD will not be used within Smithic Bank. This along with the confirmation that bedform clearance will not occur across smithic bank resduces the risk from smothering and increase in suspended sediment concentration to nearby receptors however until this mitigation is secured within the DCO we can't close out this issue. The Applicant does not consider it necessary to secure these points within the DCO. Natural England therefore derf this matter to the ExA/SoS for further consideration. |  | No
E32 | 36, 37, 38 & 39 | Cable Trenching Given the proximity of the ECC to the Holderness Inshore and Holderness Offshore MCZs, an assessment of the impact of sediment plumes due to cable trenching needs to be carried out here. The maximum spatial extent of the plumes, their persistence, and concentrations should be fully discussed and consideration given to all sensitive receptors and/or designated sites within the zone of influence. We are concerned that the impact assessment for cable trenching in the nearshore in particular, does not consider all sensitive receptors. This assessment should include Holderness Inshore MCZ, Flamborough Head SAC/SSSI and Smithic Bank, both alone and cumulatively with other projects (e.g. Dogger Bank A&B). Consequently, Natural England does not agree with the assessment of magnitude and sensitivity with regards to cable trenching as not all sensitive receptors have been considered. We advise that further mitigation may be required. |  | We remain concerned that a number of sensitive receptors (such as the MCZ and Smithic Bank) have been omitted from this assessment despite their proximity to the proposed activities. |  | No change - We remain concerned that a number of sensitive receptors (such as the MCZ and Smithic Bank) have been omitted from this assessment despite their proximity to the proposed sandwave excavation activities. |  | No Change |  | We appreciate that cable installation is a short-term activity leading to temporary disturbance of the sediment and benthic habitats, however, given the proximity of the ECC to to Holderness Inshore and Offshore MCZ, they should be included in the cable trenching impact assessments and their conservation objectives be considered. It is, therefore, important that all sensitive marine processes receptors be considered here. |  | As highlighted in E1 above, we maintain our advice that all marine process receptors should be identified and assessed within the environmental statement. We ideally would have liked to have seen this addressed through an update to the Marine Processes chapter of the ES to ensure full consideration and a clear audit trail, however we do not believe there is sufficient time remaining within the Examination for this to be addressed. Consequently we now offer revised advice based on whether the impacts to these receptors have been considered in assessments elsewhere. See E17 and E22 for further details. |  | No change |  | As highlighted in E1 above, we maintain our advice that all marine process receptors should be identified and assessed within the environmental statement. We ideally would have liked to have seen this addressed through an update to the Marine Processes chapter of the ES to ensure full consideration and a clear audit trail, however we do not believe there is sufficient time remaining within the Examination for this to be addressed. Consequently we now offer revised advice based on whether the impacts to these receptors have been considered in assessments elsewhere. See E17 and E22 for further details. |  | No
E33 | 41 & 42 | Drilling at the HVAC booster station The conclusion of the assessment of the impact of drilling at the HVAC booster station discusses sediment plumes, and associated deposition, in the offshore array area (1.11.1.85). This should be corrected and the impacts of drilling at the HVAC Booster Stations should be assessed (for example, for the Holderness Offshore MCZ). Sediment plumes, and associated deposition, due to drilling at the HVAC Booster Station Search Area have not been considered. No impact assessment has been provided. An impact assessment should consider the WCS for up to two drilling rigs operating simultaneously. The potential impact of this WCS on sensitive receptors and/or designated sites (e.g. Holderness Offshore MCZ) needs to be considered. |  | Natural England notes the applicants response, but would like to see evidence of the plume extent, concentration and persistence for the HVAC drilling before this issue can be closed out. We'd welcome further discussion with the Applicant on this point. |  | No change - Natural England would like to see evidence of the plume extent, concentration and persistence for the HVAC drilling before this issue can be closed out |  | No change |  | Natural England would like to see evidence of the plume extent, concentration and persistence for the HVAC drilling, with particiular consideration of the Holderness Offshore MCZ, before this issue can be closed out. |  | We would like to see evidence of the plume extent, concentration and persistence for WCS two drilling rigs operating simultaneously at the HVAC Booster Search Area. Given that the Holderness Offshore MCZ sits within a tidal excursion of the HVAC Booster Station a pathway exists for plume dispersion and associated deposition of sediment and this would be assessed before we can close this issue out. However, at this stage in examination we do not expect any further assessments to be carried out to provide evidence on the impact of sediment plumes. Therefore we present this as an outstanding issue for the Examiner to consider. However, we have looked again at this issue and can advise that given the distance, the risk of significant impact is likely to be low. |  | No change |  | We would like to see evidence of the plume extent, concentration and persistence for WCS two drilling rigs operating simultaneously at the HVAC Booster Search Area. Given that the Holderness Offshore MCZ sits within a tidal excursion of the HVAC Booster Station a pathway exists for plume dispersion and associated deposition of sediment and this would be assessed before we can close this issue out. However, at this stage in examination we do not expect any further assessments to be carried out to provide evidence on the impact of sediment plumes. Therefore we present this as an outstanding issue for the Examiner to consider. However, we have looked again at this issue and can advise that given the distance, the risk of significant impact is likely to be low. |  | No
E34 | 30 & 32 | Seabed Levelling within the HVAC Booster Station No impact assessment is offered within the Marine Geology, Oceanography and Marine Processes for HVAC Booster Station Search Area seabed levelling as they are considered in other chapters. However, relevant marine processes receptors that are sensitive to sediment plumes caused by seabed preparation for HVAC Booster Stations should be included here (i.e. Holderness Offshore MCZ). A schematic showing the plume model results on a map of the study area along with the location of sensitive receptors and nearby designated sites would be extremely helpful in assessing any potential impacts to the Holderness Offshore MCZ. |  | We remain concerned that the Applicant has omitted the MCZs from the Marine Process impact assessment, despite being located within the Marine Process Study Area. We advise that the MCZs should be considered here. However, we are content with the Applicant's response regarding the likely suspended sediment concentrations at the Holderness Offshore MCZ. | [11 empty] | We remain concerned that the Applicant has omitted the MCZs from the Marine Process impact assessment, despite being located within the Marine Process Study Area. We advise that the MCZs should be considered here. However, we are content with the Applicant's response regarding the likely suspended sediment concentrations at the Holderness Offshore MCZ. |  | Yes
E35 | 75 | Boulder Clearance Provisions exist for boulder clearance along the offshore ECC and within the offshore array area as well as within the HVAC booster station search area., yet it is not stated where these boulders will be removed to and therefore the potential impact of this cannot be considered. Further clarification should be provided and the potential impacts to marine process receptors should be assessed. |  | We welcome the clarification regarding the methods for boulder clearance and assurance that the boulders removed will not form an artificial reef. | [11 empty] | We welcome the clarification regarding the methods for boulder clearance and assurance that the boulders removed will not form an artificial reef. |  | Yes
E36 | 29 | This assessment of Magnitude and Impact appears to relate to the excavation of exit pits and not sandwave clearance. Natural England does not agree with this assessment of magnitude (as negligible) and impact (as not significant) as not all receptors have been adequately considered (e.g. Holderness Offshore MCZ). We advise that further mitigation may be required. |  | The Applicant has now provided the correct paragraph. However, we remained concerned that until the MDS for sandwave clearance is refined, the impacts to designated areas cannot be fully assessed. The Applicant thanks Natural England for this observation. The paragraph should read: “1.11.1.30 Sandwave clearance is a contingency provision to remove mobile seabed features which could inhibit cable laying. If sandwave clearance occurred in the nearshore (up to HDD exit pits) then effects on local receptors would be negligible. Irrespective of the sensitivity of the receptor, the significance of the impact is not significant as defined in the assessment of significance matrix (Table 1.16) and is therefore not considered further in this assessment.” Impacts on Holderness Inshore and Holderness Offshore MCZs from sandwave clearance are provided in Sections 7.1.2 and 7.2.2 Volume A5, Annex 2.3: Marine Conservation Zone Assessment (APP-070). |  | We are awaiting the outcome of the MDS Clarification Note at Deadline 3. |  | The MDS Document REP3-035 indicates that the MDS for sandwave clearance across the entire ECC remains unchanged. Therefore, our concerns regarding assessment of impacts to designated areas still needs to be considered. |  | As we have noted earlier, the Marine Processes Supplementary report REP4-043 suggests that bedform clearance for sandwaves will not occur across Smithic Bank (2.4.1.2). (Although the Applicant needs to confirm this, and explain how it can be secured.) As noted in E2, we welcome the changes made to the MDS in relation to bedform clearance volume, however, there has been no reduction in clearance area. We advise that the MDS bedform clearance should be limited to those areas where bedforms are found to be present, and not the entire ECC (excluding Smithic Bank). Furthermore, without considering all marine processes receptors (i.e. the MCZs), we cannot agree with the conclusions that the magnitude is negligible, and the impact not significant. |  | Although Natural England's position has not changed on this matter, we recognise that at this stage in the examination, further assessment is unlikely to be forthcoming. Therefore Natural England's advice now focusses on reducing the level of risk to designated sites and associated receptors through identifying potential design changes and/or advising on monitoring required to detect changes and trigger counter measures. Please see E31 for further details. |  | No change |  | Although Natural England's position has not changed on this matter, we recognise that at this stage in the examination, further assessment is unlikely to be forthcoming. Therefore Natural England's advice now focusses on reducing the level of risk to designated sites and associated receptors through identifying potential design changes and/or advising on monitoring required to detect changes and trigger counter measures. Please see E31 for further details. |  | No
Array
E37 | 40 | It is anticipated that up to 10% of all pile installations will require drilling (or up to 10% of the depth across all installations). Given that the underlying geology is not known, it is unclear what the 10% is based on, and consequently we are unable to confirm if this is a realistic worst-case scenario |  | The Applicant is currently reviewing the MDS and a workstream is underway. We will provide further comments on this issue once further information is available. |  | We are awaiting the outcome of the MDS Clarification Note at Deadline 3. |  | Based on the information provided by the Applicant in Document REP3-035, we are content that 10% drilling requirements is a realistic worst-case scenario. | [7 empty] | Based on the information provided by the Applicant in Document REP3-035, we are content that 10% drilling requirements is a realistic worst-case scenario. |  | Yes
E39 | 43 | Nine seismic units have been described, based on sub-bottom profiles of stratigraphy across the offshore array area. It is unclear what these seismic units are and how they relate spatially to the project. Further detail should be provided (i.e. a map). |  | We would advise that all nine seismic units should be presented, not just the one presented by the Applicant. |  | No change to position. |  | No change |  | No change |  | Although Natural England's position has not changed on this matter, we recognise that at this stage in the examination, further assessment is unlikely to be forthcoming. Therefore Natural England's advice now focusses on reducing the level of risk to designated sites and associated receptors through identifying potential design changes and/or advising on monitoring required to detect changes and trigger counter measures. |  | No change |  | Although Natural England's position has not changed on this matter, we recognise that at this stage in the examination, further assessment is unlikely to be forthcoming. Therefore Natural England's advice now focusses on reducing the level of risk to designated sites and associated receptors through identifying potential design changes and/or advising on monitoring required to detect changes and trigger counter measures. |  | No
E40 | 56 | Flamborough Front The Flamborough Front is formed where the stratified water from the northern North Sea meets the mixed water from the southern North Sea. The mixing of these two waterbodies leads to an upwelling of nutrients, which in turn leads to increased plankton growth and associated productivity, giving rise to concentrations of forage fish which in turn provide a feeding ground for other species. It is therefore perhaps of no surprise that areas around the front support high densities of seabirds and marine mammals. Consequently, it is vital that the potential impacts of the project alone and incombination with other plans and projects be adequately assessed. Natural England, therefore, considers this receptor to have high environmental value and not medium as indicated in the ES. |  | The Applicant states that no measurable indirect impacts on ecology are anticipated (RR-029-5.56). However, no parameterisation has been provided of water column stratification, biogeochemical fluxes, and primary production within and adjacent to the Hornsea Four array area to support this statement. Therefore, a conclusion of no indirect impacts on ecology cannot be made. The lifespan of the project also needs to be considered when assessing the potential effects of the Hornsea Four infrastructure on mixing of stratified waters and alteration of primary production. This would require accurate forecasting of the interaction between tidal flows, the array infrastructure, biogeochemical fluxes and primary production (see Dorrell et al., 2021 and Christiansen et al., 2022). The Flamborough Front gives rise to nutrient-rich waters which create a biodiversity hotspot attracting seabirds and marine mammals to the area each year. Therefore, the Flamborough Front plays a key role in primary production, marine ecosystem and biogeochemical cycles and, consequently, we consider it to have high environmental value. The Applicant suggests that the location of the Flamborough Front is typically south of Hornsea Four. Yet, in Figure 37 of Volume A5, Annex 1.1: Marine Processes Technical Report, Hornsea Four clearly overlaps (sits within) an area of high frequency (%) occurrence of the Flamborough Front. The Applicant is currently carrying out a marine process analysis to provide assurance to the position of the Flamborough Front and the potential impacts of Hornsea Four on the front, both alone and in-combination. We welcome and look forward to seeing this analysis. |  | We are awaiting the outcome of the Marine Processes Supplementary Works and Clarification Note at Deadline 3. |  | We are awaiting the outcome of the Marine Processes Supplementary Works and Clarification Note at Deadline 4. |  | The Flamborough Front gives rise to nutrient-ruch waters which create a biodiversity hotspot. It plays a key role in primary production, the marine ecosystem and biogeochemical cycles. Therefore, we maintain that the Flamborough Front is of high environmental value. Please see our joint memo (with MMO and Cefas) on this matter. |  | Natural England's position that the Flamborough Front is of high ecological value remains unchanged. Its role in the marine ecosystem bringing nutrient-rich water to Flamborough Head, concentrating food for fish, seabirds, seals and cetaceans is well documented. At this stage in the Examination we do not expect that the Applicant will make further revisions to their assessments, therefore we would advise that the ExA and SoS should have regard to the high value of this receptor by ensuring that the risk of potential impacts are managed as far as possible and that approprate monitoring to detect changes and trigger any necessary counter measures is secured. (See E42 below). |  | No change |  | Natural England's position that the Flamborough Front is of high ecological value remains unchanged. Its role in the marine ecosystem bringing nutrient-rich water to Flamborough Head, concentrating food for fish, seabirds, seals and cetaceans is well documented. At this stage in the Examination we do not expect that the Applicant will make further revisions to their assessments, therefore we would advise that the ExA and SoS should have regard to the high value of this receptor by ensuring that the risk of potential impacts are managed as far as possible and that approprate monitoring to detect changes and trigger any necessary counter measures is secured. (See E42 below). |  | No
E41 | 57 | Flamborough Front The foundation structures of the Hornsea 4 array area have the potential to generate turbulent wakes that will contribute to a mixing of the stratified water column. Mixing generated in this way could have a significant impact on the large-scale stratification of the North Sea off the coast of Flamborough Head. The presence of the Hornsea 4 array area, combined with those of Hornsea 2 and Hornsea 1, would occupy a considerable area, hence the potential large-scale impact on the Flamborough Front. Furthermore, the inclusion of Gravity Base Structures, as the MDS for turbine foundation design at Hornsea 4, significantly increases the potential for turbulence effects. Gravity bases of the size and scale proposed have not previously been deployed in the English waters, therefore, we have no evidence base on which to base understanding of their impact on marine processes and their receptors. Natural England therefore advises that the sensitivity of the Flamborough Front should be considered high, until further evidence to the contrary can be provided. |  | Clusters of offshore wind farms such as Hornsea Four, Hornsea Two and Hornsea One, could potentially lead to large-scale structural changes in stratification and, in turn, alter biogeochemical cycles (either positively or negatively) and marine ecosystem functioning. Therefore, we advise that the Flamborough Front should be considered of high sensitivity, until evidence is provided to support this conclusion. |  | We are awaiting the outcome of the Marine Processes Supplementary Works and Clarification Note at Deadline 3. |  | We are awaiting the outcome of the Marine Processes Supplementary Works and Clarification Note at Deadline 4 |  | Please see our joint (NE/MMO/Cefas) memo response (Annex E5 of our Deadline 5 response). Natural England recognise that the potential impacts on the Flamborough Front resulting from this project alone and cumulatively with other plans/projects is difficult to predict with certainty. To that end, we are keen to work with the applicant to reduce the risk of impact as far as possible. Natural England would therefore welcome further consideration of the need for the inclusion of gravity base structures as the maximum design scenario for the project, noting that they have not previously needed to be deployed by projects in English waters (including Hornsea 1 and 2). |  | We advise that the sensitivity of the Flamborough Front should be considered high, until further evidence is provided to the contrary. At this stage in the Examination we do not expect that the Applicant will make further revisions to their assessments, therefore we would advise that the ExA and SoS should have regard to the high value of this receptor by ensuring that the risk of potential impacts are managed as far as possible and that approprate monitoring to detect changes and trigger any necessary counter measures is secured. (See E42 below). |  | No change |  | We advise that the sensitivity of the Flamborough Front should be considered high, until further evidence is provided to the contrary. At this stage in the Examination we do not expect that the Applicant will make further revisions to their assessments, therefore we would advise that the ExA and SoS should have regard to the high value of this receptor by ensuring that the risk of potential impacts are managed as far as possible and that approprate monitoring to detect changes and trigger any necessary counter measures is secured. (See E42 below). |  | No
E42 | 8, 55, 56 | Flamborough Front Based on data within Volume A5, Annex 1.1: Marine Processes Technical Report, the Hornsea Four array area appears to be located within a zone of 90-100% occurrence of the Flamborough Front, which would suggest that statements from Section 1.7.9.3 contradicts this evidence. The waters around Flamborough Head are particularly rich in marine life because of its proximity to an upwelling of nutrients and plankton caused by the Flamborough Front. Given the importance of this frontal system to primary productivity in the North Sea, it is vital to understand the potential impacts of the HP4 alone, and in-combination with other plans and projects. “Turbulent wakes are not expected to interact with the Flamborough Front.” The magnitude of impact has been assessed as ‘negligible’ for this effect.” The Flamborough Front is located close to/overlaps the HP4 array (and HP2 and HP1)/ Given the importance of the Front to primary productivity (and in turn secondary productivity), a better understanding of the potential impacts of the project alone (and in-combination) is required. |  | See our comments on RR-029-5.56, RR-029-5.57 & RR-029-5.58. We would advise that the sensitivity of the Flamborough Front should be considered high, until further evidence is provided to the contrary. |  | We are awaiting the outcome of the Marine Processes Supplementary Works and Clarification Note at Deadline 3. |  | We are awaiting the outcome of the Marine Processes Supplementary Works and Clarification Note at Deadline 4 |  | Please see our joint (NE/MMO/Cefas) memo response. (Annex E5 of our Deadline 5 response). |  | We remain concerned that the cluster of offshore wind farms within the Hornsea Zone could have a cumulative impact on seasonal stratification through increased vertical transport which induces greater mixing and leads to a decrease in stratification. The cumulative impact of multiple OWF installations in a region critical to wildlife populations and the shelf ecosystem, may have impacts on resources within this region (e.g. fisheries, bird habitats). The addition of a cluster of OWFs in the Hornsea zone, could alter the structure of the Flamborough Front over the long-term, and impact not only the lower trophic levels (via stratification mixing and nutrient cycling) but all the way up to large marine vertebrates. The Applicant has marshalled all of the evidence that we are aware of, nevertheless with the project as currently designed we are not able to exlclude the risk of significant/adverse effects arising. NE's advice now focusses on reducing the level of risk to designated sites and associated receptors, through identifying design changes and advising on the monitoring required to detect change and trigger counter measures. Measures to reduce risk: As highlighted in E4 above, whilst our concerns relate to the potential impact of all foundation types, the risk is significantly greater with the use of Gravity Base type foundations. Given this, our advice remains that GBS should be removed as the MDS for turbine foundations. As further detail on on the foundation type and layout will be available at the post consent phase, should the ExA and SoS be minded to proceed on the basis of the information available, Natural England advise that a clear requirement is included within the DCO/dML conditions to fully assess the the proposed layout plan prior to discharge, with the option to include further measures to avoid, reduce or mitigate impacts until it can be demonstrated that signficant impacts can be ruled out. This approach of "deferred assessment" is not without its own challenges and risks. Therefore we would advise that this is only considered where the ExA/SoS are satisfied that significant impacts can be avoided and that all steps have been taken by the Applicant to reduce the risks as much as possible prior to consent (i.e. through the removal of GBS). Monitoring: We propose a robust monitoring stratory for the lifetime of the project is required to provide evidence to suport the assumptions made in the ES is secured post construction. The initial step to monitoring proposed in G5.33, aims to assess changes to stratification at three locations within the array this is useful in terms of understanding small-scale physical processes, but it would be difficult to identify three locations that are representative of the whole array based on this plan. Therefore, we advise that the first step should be to use high-resolution satellite imagery to examine wakes, sediment plumes, and chlorophyll concentrations across the array and the wider zone of impact beyond the array. We recommend this monitoring should cover a temporal period to include the build-up of seasonal stratification through to breakdown of seasonal stratification. Secondly, the array-scale monitoring should be used to identify representative locations for the near-field monitoring of changes to stratification. Further consideration is also needed of the sub-surface/mid water chlorophyll concentrations. Over the long-term, there is a need to carefully consider monitoring changes to stratification, currents, suspended sediment concentrations, pH, turbulence, light, and chlorophyll. |  | No change |  | We remain concerned that the cluster of offshore wind farms within the Hornsea Zone could have a cumulative impact on seasonal stratification through increased vertical transport which induces greater mixing and leads to a decrease in stratification. The cumulative impact of multiple OWF installations in a region critical to wildlife populations and the shelf ecosystem, may have impacts on resources within this region (e.g. fisheries, bird habitats). The addition of a cluster of OWFs in the Hornsea zone, could alter the structure of the Flamborough Front over the long-term, and impact not only the lower trophic levels (via stratification mixing and nutrient cycling) but all the way up to large marine vertebrates. The Applicant has marshalled all of the evidence that we are aware of, nevertheless with the project as currently designed we are not able to exlclude the risk of significant/adverse effects arising. NE's advice now focusses on reducing the level of risk to designated sites and associated receptors, through identifying design changes and advising on the monitoring required to detect change and trigger counter measures. Measures to reduce risk: As highlighted in E4 above, whilst our concerns relate to the potential impact of all foundation types, the risk is significantly greater with the use of Gravity Base type foundations. Given this, our advice remains that GBS should be removed as the MDS for turbine foundations. As further detail on on the foundation type and layout will be available at the post consent phase, should the ExA and SoS be minded to proceed on the basis of the information available, Natural England advise that a clear requirement is included within the DCO/dML conditions to fully assess the the proposed layout plan prior to discharge, with the option to include further measures to avoid, reduce or mitigate impacts until it can be demonstrated that signficant impacts can be ruled out. Natural England's comments on the monitoring set out in the OOMP ate provided at D8. This approach of "deferred assessment" is not without its own challenges and risks. Therefore we would advise that this is only considered where the ExA/SoS are satisfied that significant impacts can be avoided and that all steps have been taken by the Applicant to reduce the risks as much as possible prior to consent (i.e. through the removal of GBS). Monitoring: We propose a robust monitoring stratory for the lifetime of the project is required to provide evidence to suport the assumptions made in the ES is secured post construction. The initial step to monitoring proposed in G5.33, aims to assess changes to stratification at three locations within the array this is useful in terms of understanding small-scale physical processes, but it would be difficult to identify three locations that are representative of the whole array based on this plan. Therefore, we advise that the first step should be to use high-resolution satellite imagery to examine wakes, sediment plumes, and chlorophyll concentrations across the array and the wider zone of impact beyond the array. We recommend this monitoring should cover a temporal period to include the build-up of seasonal stratification through to breakdown of seasonal stratification. Secondly, the array-scale monitoring should be used to identify representative locations for the near-field monitoring of changes to stratification. Further consideration is also needed of the sub-surface/mid water chlorophyll concentrations. Over the long-term, there is a need to carefully consider monitoring changes to stratification, currents, suspended sediment concentrations, pH, turbulence, light, and chlorophyll. |  | No
E43 | 74 | Flamborough Front Figure 37 & 3.4.3.11: Figure 37 (Volume A5, Annex.1.1: Marine Processes Technical Report (APP-067) presents seasonal front maps for the frequency of occurrence across the study area and also the position of the Flamborough Front from the 3-D baroclinic model for July 2018. The latter is a snapshot from one year, and not representative of the average position of the front over a number of years. Furthermore, the Summer front map shows 90-100% occurrence of the front both south and north of the Hornsea Four array area (based on cloud-free satellite images over a 10-year period). Based on this latter data, the Hornsea Four array area would appear to be located within a zone of 90-100% occurrence of the Flamborough Front. This appears to contradict the last sentence in Section 3.4.3.11 “…Hornsea Four also occupies a location where there is an apparent reduced frequency of occurrence for the front.”. Therefore, we do not agree with the quoted statement. The potential extent of overlap with the Flamborough Front needs to be clarified. |  | The Applicant’s response states that ‘the front is mainly located either south or north of Hornsea Four’. Moreover, the Summer seasonal front map in Figure 37 (of the Technical Report) shows that Hornsea Four (and Hornsea Two and Hornsea One) sit within an area where the probability of occurrence of the Flamborough Front is 80-100%. This would suggest that the Hornsea Four array overlaps the Flamborough Front. |  | We are awaiting the outcome of the Marine Processes Supplementary Works and Clarification Note at Deadline 3. |  | We are awaiting the outcome of the Marine Processes Supplementary Works and Clarification Note at Deadline 4. |  | Natural England welcome the publication of the G4.9 Marine Process Supplimentary Report [REP4-043] which confirms that the Flamborough Front does overlap the array area of Hornsea 4, (as well as other OWF in the area of the North Sea). With this acknowledgment we would like to work with The Applicant to dicuss ways to avoid, reduce or mitigate the impacts on the Flamborough Front from the Array (which are covered by other lines in this log). We have agreement that the Flamborough front does overlap with the array area therefore can close this line specifically. | [5 empty] | Natural England welcome the publication of the G4.9 Marine Process Supplimentary Report [REP4-043] which confirms that the Flamborough Front does overlap the array area of Hornsea 4, (as well as other OWF in the area of the North Sea). With this acknowledgment we would like to work with The Applicant to dicuss ways to avoid, reduce or mitigate the impacts on the Flamborough Front from the Array (which are covered by other lines in this log). We have agreement that the Flamborough front does overlap with the array area therefore can close this line specifically. |  | Yes
E44 | 57, 73 | Flamborough Front We would advise that the sensitivity of the Flamborough Front should be considered High until further evidence to the contrary has been provided. Given the uncertainties discussed above, we cannot agree at this stage with the assessment of the magnitude of impact on the Flamborough Front, nor the significance of the effect. Therefore, we do not agree the impact assessment. We advise that mitigation will be required. |  | We note that the Applicant has commissioned further studies and that an update will be provided at Deadline 3. |  | We are awaiting the outcome of the Marine Processes Supplementary Works and Clarification Note at Deadline 3. |  | We are awaiting the outcome of the Marine Processes Supplementary Works and Clarification Note at Deadline 4. |  | Natural England note that the Applicant will be submitting a report on "Indirect-effects: Forage fish and seabirds" at deadline 5. We will comment on this in due course with regard to sensitivity of Flamborough front. |  | Natural England continue to advise that the sensitivity of the Flamborough Front should be considered to be high. At this stage in the Examination we do not expect that the Applicant will make further revisions to their assessments, therefore we would advise that the ExA and SoS should have regard to the high sensitivity of this receptor by ensuring that the risk of potential impacts are managed as far as possible and that approprate monitoring to detect changes and trigger any necessary counter measures is secured. (See E42 above ). |  | No change |  | Natural England continue to advise that the sensitivity of the Flamborough Front should be considered to be high. At this stage in the Examination we do not expect that the Applicant will make further revisions to their assessments, therefore we would advise that the ExA and SoS should have regard to the high sensitivity of this receptor by ensuring that the risk of potential impacts are managed as far as possible and that approprate monitoring to detect changes and trigger any necessary counter measures is secured. (See E42 above ). |  | No
E45 | 58 | Flamborough Front and Assessment of Impacts to Designated Sites Based on the high levels of uncertainty described, Natural England is unable to rule out the potential for significant impacts to the Flamborough Front. Given the front’s influence on the wider ecology of the area, potential for significant impacts on the benthic environment, birds, mammals and fish also cannot be excluded and the potential for adverse effect on designated sites such as Flamborough Head SAC Flamborough and Filey Coast SPA, the Southern North Sea SAC cannot be ruled out until further evidence can be provided. |  | Recent studies (e.g. Dorrell et al, 2021 and Christiansen et al., 2022) suggest that offshore wind farms can cause far-reaching changes to stratification which are likely to affect plankton production and the food web structure. Consequently, this may influence the function of protected areas such as the Flamborough Head SAC, Flamborough and Filey Coast SPA, and Southern North Sea SAC. Therefore, potential adverse effects cannot be ruled out at present due to the lack of robust scientific evidence to the contrary. However, we look forward to the Applicant’s marine process analysis and any new supporting evidence which enables such adverse effects to be discounted (for Hornsea Four alone and/or in-combination with other plans or projects). |  | We are awaiting the outcome of the Marine Processes Supplementary Works and Clarification Note at Deadline 3. |  | We are awaiting the outcome of the Marine Processes Supplementary Works and Clarification Note at Deadline 4. |  | Natural England note that the Applicant will be submitting a report on "Indirect-effects: Forage fish and seabirds" at deadline 5. We will comment on this in due course with regard to sensitivity of Flamborough front. |  | Natural England have reviewed REP5-085 G5.7 Indirect Effects of Forage Fish and Ornithology and do not believe there is sufficently robust data available to support the Applicant's conclusion that the area of the array is less productive that the surounding areas. The Applicant has not yet provided any evidence of Hornsea Four array-specific annual chlorophyll concentration variations. Enhanced mixing rates due to the Hornsea Four infrastructure alone and in-combination may lead to not only temporal and spatial variations in vertical density structure, but also impact biogeochemical function at a fundamental level that could cascade up the ecosystem (i.e. from phytoplankton to fish, seabirds, seals, cetaceans etc). In order to understand the potential impacts of the Hornsea Four development, alone and in-combination, on the seasonally stratified sea will require a robust monitoring strategy for the lifetime of the project. (See E42 for further details). |  | No change |  | Natural England have reviewed REP5-085 G5.7 Indirect Effects of Forage Fish and Ornithology and do not believe there is sufficently robust data available to support the Applicant's conclusion that the area of the array is less productive that the surounding areas. The Applicant has not yet provided any evidence of Hornsea Four array-specific annual chlorophyll concentration variations. Enhanced mixing rates due to the Hornsea Four infrastructure alone and in-combination may lead to not only temporal and spatial variations in vertical density structure, but also impact biogeochemical function at a fundamental level that could cascade up the ecosystem (i.e. from phytoplankton to fish, seabirds, seals, cetaceans etc). In order to understand the potential impacts of the Hornsea Four development, alone and in-combination, on the seasonally stratified sea will require a robust monitoring strategy for the lifetime of the project. (See E42 for further details). |  | No
E46 | 54 | Wake to Wake Interactions Section 1.11.2.27: It is stated that “The inclusion of 10 GBS box-type foundations in the array with greater widths (75m and 150m), and also non-cylindrical shapes, increases the potential for wake-to-wake interactions across parts of the array which are in the leeward path of the larger foundations.” Whilst it is suggested that the area affected by these wake-to-wake interactions will be limited, this has not been demonstrated or qualified. Evidence should be provided to show the spatial extent of these wake-towake interactions. |  | Further evidence should be provided by the Applicant to support their conclusion here. |  | No Change |  | Natural England notes the Applicant has drawn our attention to Section 4.7 of Marine Processes Technical Report (APP-067) for further information. Natural England reviewed this document at Relevant Representation and did not consider the information sufficient on wake-to-wake interaction with regards to the 10 larger GBS box type foundations (75m & 150m width) and hence raised this issue. We have reviewed section 4.7 again and still request further evidence to demonstrate and qualify the wake-to-wake interactions expected (with regard to the large GBS box type foundations) as the examples given within the technical report are for smaller gravity base structures at wider spacings. |  | No change |  | There is considerable evidence that suggests that wakes could extend > 1km leading to wake-to-wake merging (see Foster, 2018). Therefore, the horizontal extent of the increased mixing of the water column and therefore the decrease in stratification could well extend beyond the footprint of the array. We advise that there is a need to more accurately quantify the spatial extent of foundation structure wakes and plumes. Understanding the nature of these wakes is important in assessing whether they pose a disturbance to the marine environment through enhanced levels of turbulence, increased sediment erosion, turbidity in the water column, disrupting light availability, or alteration of vertical density stratification. The Applicant has marshalled all of the evidence that we are aware of, nevertheless with the project as currently designed we are not able to exlclude the risk of significant/adverse effects arising. NE's advice now focusses on reducing the level of risk to designated sites and associated receptors, through identifying design changes and advising on the monitoring required to detect change and trigger counter measures. Further details can be found in E42 above. |  | No change |  | There is considerable evidence that suggests that wakes could extend > 1km leading to wake-to-wake merging (see Foster, 2018). Therefore, the horizontal extent of the increased mixing of the water column and therefore the decrease in stratification could well extend beyond the footprint of the array. We advise that there is a need to more accurately quantify the spatial extent of foundation structure wakes and plumes. Understanding the nature of these wakes is important in assessing whether they pose a disturbance to the marine environment through enhanced levels of turbulence, increased sediment erosion, turbidity in the water column, disrupting light availability, or alteration of vertical density stratification. The Applicant has marshalled all of the evidence that we are aware of, nevertheless with the project as currently designed we are not able to exlclude the risk of significant/adverse effects arising. NE's advice now focusses on reducing the level of risk to designated sites and associated receptors, through identifying design changes and advising on the monitoring required to detect change and trigger counter measures. Further details can be found in E42 above. |  | No
E47 | 76 | Modelling of an indicative sediment plume and spoil deposition event from seabed levelling within the array is based on one site located central to the array. However, this does not consider any overlapping impacts from concurrent seabed preparation activities, therefore the cumulative impact cannot be assessed. We would, therefore, advise considering carrying out the modelling for two neighbouring sites within the centre of the array |  | Given the distance from the array to sensitive receptors, we are content with the information provided by the Applicant. | [11 empty] | Given the distance from the array to sensitive receptors, we are content with the information provided by the Applicant. |  | Yes
E48 | 33 | In order to determine the WCS impacts due to GBS foundation preparation in the offshore array area, overlapping/concurrent seabed preparation activities should be assessed. We would advise that the fate of dredged material from two neighbouring sites in the centre of the array should be modelled. This should also take account of the overlapping/concurrent seabed preparation activities in the offshore area. |  | Given the distance from the array to sensitive receptors, we are content with the information provided by the Applicant. | [11 empty] | Given the distance from the array to sensitive receptors, we are content with the information provided by the Applicant. |  | Yes
E49 | 9, 47 & 48 | Within paragraph 1.7.8.3, it is noted that there is a sand ridge in the north western part of the array which is associated with a larger area of sand ridges and sandbanks known as ‘The Hills’. These are sufficiently close to the array as to be impacted by changes to hydrodynamics and sediment transport. The impact of scouring around foundations should be considered for marine processes receptors such as 'The Hills' over the medium to long term. Natural England is concerned with the potential impact of the MDS foundation type, GBS structures, on the physical environment in particular the adjacent sandbank systems (i.e. The Hills). Given the uncertainties stated here regarding large box-type GBS foundations, we would suggest the WCS should be adapted in terms of their potential effect on scour development and, thus, scour protection requirements. Additionally, within paragraph 1.7.8.2 the Outer Silver pit geological feature (which lies directly adjacent to the array) is referenced, and yet it hasn’t been considered a potential receptor. Further justification should be provided to support its exclusion from further consideration. |  | Further evidence should be provided by the Applicant to support their conclusion here. |  | No change on position - Further evidence should be provided by the Applicant to support their conclusion here. |  | Natural England request further evidence to show the impact that large GBS structures might have on nearby receptors such as The Hills or Outer Silver pit. This could be in the form of modelling or examples from other windfarms but should include impact of scouring around foundations and changes to hydrodynamics and sediment transport in the vicinity of the array. If either of these features are not considered receptors, then justification should be provided to support the exclusion from further consideration. |  | The Applicant provided verbal clarification at ISH4 that there is no pathway to the Hills which has subsequently been captured within REP4 038. We welcome the further clarification regarding Hills and consider that this can now be closed out. In relation to Outer Silver Pit, whilst we acknowlege it is parallel to the main tidal flow axis, and in parts in deep water (i.e. 60-70m) and should not be affected by waves, its location is very close to the array (1km or slightly less in places). We would therefore welcome modelling of one of the turbines located closest to the Outer Silver Pit Receptor to give us confidence that this matter can be closed out. |  | Outer Silver Pit is located very close to the Hornsea Four array (1km or slightly less in places). It is an important fish spawning and nursery area and is, therefore, a potential receptor that could be affected by sediment settlement due to HP4 construction activities. However, the orientation of Outer Silver Pit is parallel to the main tidal axis and the depth across most of Outer Silver Pit suggests that it is unlikely to be affected by the influence of surface waves. Therefore, we are content now that sediment transfer between the array and Outer Silver Pit is unlikely to be significant and this issue can now be closed out. We closed out impacts on The Hills at Deadline 5. |  |  |  | Outer Silver Pit is located very close to the Hornsea Four array (1km or slightly less in places). It is an important fish spawning and nursery area and is, therefore, a potential receptor that could be affected by sediment settlement due to HP4 construction activities. However, the orientation of Outer Silver Pit is parallel to the main tidal axis and the depth across most of Outer Silver Pit suggests that it is unlikely to be affected by the influence of surface waves. Therefore, we are content now that sediment transfer between the array and Outer Silver Pit is unlikely to be significant and this issue can now be closed out. We closed out impacts on The Hills at Deadline 5. |  | Yes
E50 | 34 | Seabed levelling in the offshore array area has not been assessed for its impact on marine process receptors. Consequently, the Applicant has not considered potential adverse impacts due to the modification or removal of sandwaves on nearby or adjacent prominent sand ridge and sandbank systems (e.g. The Hills). This is particularly relevant to the northern part of the offshore array area and should be assessed. |  | Further evidence should be provided by the Applicant to support their conclusion here. |  | No change on position - Further evidence should be provided by the Applicant to support their conclusion here. |  | No Change. Natural England does not consider the Applicants response to this issue in REP3-046 to provide sufficient explanation or evidence to rule out impacts from seabed levelling within the array area or out to The Hills. |  | The Applicant provided verbal clarification at ISH4 that there is no pathway to the Hills which has subsequently been captured within REP4 038. We welcome the further clarification regarding Hills and consider that this can now be closed out. In relation to Outer Silver Pit, whilst we acknowlege it is parallel to the main tidal flow axis, and in parts in deep water (i.e. 60-70m) and should not be affected by waves, its location is very close to the array (1km or slightly less in places). We would therefore welcome modelling of one of the turbines located closest to the Outer Silver Pit Receptor to give us confidence that this matter can be closed out. |  | There remains uncertainty as to whether Outer Silver Pit is a depositional environment. It is an important fish spawning and nursery area so it should have been identified and evaluated as a receptor. However, given that Outer Silver Pit sits in deep water it is unikely to be affected by surface waves. Furthermore, its orientation is parallel to the tidal axis so whilst there may be some east-west sediment transfer, we are content that this is not likely to be significant. Therefore, we are content for this matter to be closed out (it will remain yellow as the approach to identify and evaluate Outer Silver Pit as a receptor was not inlcuded in the ES). |  |  |  | There remains uncertainty as to whether Outer Silver Pit is a depositional environment. It is an important fish spawning and nursery area so it should have been identified and evaluated as a receptor. However, given that Outer Silver Pit sits in deep water it is unikely to be affected by surface waves. Furthermore, its orientation is parallel to the tidal axis so whilst there may be some east-west sediment transfer, we are content that this is not likely to be significant. Therefore, we are content for this matter to be closed out (it will remain yellow as the approach to identify and evaluate Outer Silver Pit as a receptor was not inlcuded in the ES). |  | Yes
E51 | 46 | It is stated that “All foundations are considered sufficiently separated to mitigate the chance of group scour.” Group scour is known to extend beyond the influence of the foundation with large diameter structures such as GBS or jacket structures and, therefore, has a large cumulative environmental effect when taking into the whole Hornsea 4 array. Therefore, further information should be provided to support this assertion and the separation distance should be stated. |  | We advise that evidence should be provided by the Applicant to support this conclusion. |  | No change on position - Further evidence should be provided by the Applicant to support their conclusion here. |  | Natural England wish to see evidence of predicted scour extent of all GBS and foundations (but particularly the larger GBS which have not been used before in UK waters) and calculations to show the separation distance is sufficient to avoid any group scour impacts. |  | No change |  | Natural England welcomes the Applicant's comment that pre and post construction surveys will be used to collect data on changes in seabed topography. However we require that this is adequately captured in the OMMP so it is clear that these post construction geophysical surveys are being used to validate assessments made within the Environmental Statement. This is important information for when the MMO is signing these documents off. However, it should be noted that post construction monitoring does not negate the need for detailed assessment within the application and our advice in this regard remains unchanged and we do not consider that the potential for group scour can be excluded on the basis of the information currently available. At this stage in the Examination we do not expect that the Applicant will make further revisions to their assessments, therefore we would advise that the ExA and SoS should have regard to the high value of this receptor by ensuring that the risk of potential impacts are managed as far as possible and that approprate monitoring to detect changes and trigger any necessary counter measures is secured. whilst our concerns relate to the potential impact of all foundation types, the risk is significantly greater with the use of Gravity Base type foundations. Given this, our advice remains that GBS should be removed as the MDS for turbine foundations. As further detail on on the foundation type and layout will be available at the post consent phase, should the ExA and SoS be minded to proceed on the basis of the information available, Natural England advise that a clear requirement is included within the DCO/dML conditions to fully assess the the proposed layout plan prior to discharge, with the option to include further measures to avoid, reduce or mitigate impacts until it can be demonstrated that signficant impacts can be ruled out. This approach of "deferred assessment" is not without its own challenges and risks. Therefore we would advise that this is only considered where the ExA/SoS are satisfied that significant impacts can be avoided and that all steps have been taken by the Applicant to reduce the risks as much as possible prior to consent (i.e. through the removal of GBS). |  | No change |  | Natural England welcomes the Applicant's comment that pre and post construction surveys will be used to collect data on changes in seabed topography. However we require that this is adequately captured in the OMMP so it is clear that these post construction geophysical surveys are being used to validate assessments made within the Environmental Statement. This is important information for when the MMO is signing these documents off. However, it should be noted that post construction monitoring does not negate the need for detailed assessment within the application and our advice in this regard remains unchanged and we do not consider that the potential for group scour can be excluded on the basis of the information currently available. At this stage in the Examination we do not expect that the Applicant will make further revisions to their assessments, therefore we would advise that the ExA and SoS should have regard to the high value of this receptor by ensuring that the risk of potential impacts are managed as far as possible and that approprate monitoring to detect changes and trigger any necessary counter measures is secured. whilst our concerns relate to the potential impact of all foundation types, the risk is significantly greater with the use of Gravity Base type foundations. Given this, our advice remains that GBS should be removed as the MDS for turbine foundations. As further detail on on the foundation type and layout will be available at the post consent phase, should the ExA and SoS be minded to proceed on the basis of the information available, Natural England advise that a clear requirement is included within the DCO/dML conditions to fully assess the the proposed layout plan prior to discharge, with the option to include further measures to avoid, reduce or mitigate impacts until it can be demonstrated that signficant impacts can be ruled out. This approach of "deferred assessment" is not without its own challenges and risks. Therefore we would advise that this is only considered where the ExA/SoS are satisfied that significant impacts can be avoided and that all steps have been taken by the Applicant to reduce the risks as much as possible prior to consent (i.e. through the removal of GBS). |  | No
E52 | 45 | The anticipated maximum scour footprint around each foundation option should be provided. We also advise monitoring scour development around a number of WTGs (GBS and monopile) and OSS in order to validate scour predictions in the ES. |  | Whilst we welcome clarification from the Applicant on anticipated maximum scour footprints around WTGs and OSSs, it is unclear if the applicant has carried out any monitoring of secondary scour. Our position remains that post construction monitoring should test the assumptions made within the ES. |  | Our position remains that post construction monitoring should test the assumptions made within the ES. |  | Natural England welcomes the Applicants comments that pre and post construction surveys will be used to collect data on changes in seabed topography. However we require that this is adequately captured in the OMMP so it is clear that these post construction geophysical surveys are being used to validate assessments made within the Environmental Statement. This is important when the MMO is signing these documents off. Natural England also wish to see predicted maximum scour footprints for each foundation type. |  | No change |  | See E51 above. |  | No change |  | See E51 above. |  | No
E59 | [11 empty] | Drill arisings - Following review of REP5-083 G5.5 Clarification Note on Drill Arisings and Deposited Sediments Natural England would have concerns if the drilling mounds were as high as the MDS (10m), particularly if they did not winnow away as quickly as anticipated. Natural England therefore request the applicant confirms the number/location height of mounds post construction and that should any mounds stand at a height greater than 3m (i.e. the maximum height of the scour protection), we would expect further monitoring to determine if the material is winnowing away as expected, with the option for intervention to remove some of the material if it persists. If this can be appropriately secured within the DCO/DML or relevant certified document, Natural England would consider this issue resolved (subject to the clarification highlighted above). |  | Natural England have corrected an error in the RAG status of this issue at deadline 6. |  | The project has included a commitment to monitoring mounds over 3m as requested. However, we would like to see a mechanism whereby intervention can be made (i.e. removal) if the mounds are not winnowing as expected. |  | Yes
Decommissioning and Post Operational Impacts
E53 | 41 | It should also be noted that the project is not intending to decommission rock protection at the end of the operational lifetime of the project. Consequently, the placement of rock protection represents a permanent change to the seabed and the impact of this beyond the operational lifetime of the project should be considered. |  | We remain concerned that any rock protection placed onshore of the depth of closure and/or across Smithic Bank represents a permanent change to the seabed and an obstacle to sediment transport processes, not only during, but also beyond, the lifespan of the project. These long-term alterations to the nearshore seabed morphology and sediment transport processes should be adequately assessed. |  | No change |  | No change |  | No change. |  | We remain concerned that any rock protection placed represents a permanent change to the seabed and an obstacle to sediment transport processes, not only during, but also beyond, the lifespan of the project. These long-term alterations to the nearshore seabed morphology and sediment transport processes should be adequately assessed. However, with limited time remaining within the examination, we recognise that such an assessment may not be forthcoming. Therefore we would urge the ExA/ SoS to be mindful of the long term persistence of rock protection beyond the operational lifetime of the windfarm when determining this case. We also reiterate our advice in relation to the avoidance of rock protection in the nearshore area - See E26 and E28 and the increased emphasis this long term/permanent persistence of impacts should add. |  | No change |  | We remain concerned that any rock protection placed represents a permanent change to the seabed and an obstacle to sediment transport processes, not only during, but also beyond, the lifespan of the project. These long-term alterations to the nearshore seabed morphology and sediment transport processes should be adequately assessed. Therefore we would urge the ExA/ SoS to be mindful of the long term persistence of rock protection beyond the operational lifetime of the windfarm when determining this case. We also reiterate our advice in relation to the avoidance of rock protection in the nearshore area - See E26 and E28 and the increased emphasis this long term/permanent persistence of impacts should add. The Applicant has highlighted that the decommissioning programme is subject to a separate regulatory regime, and that the matters Natural England has highlighted should be addressed through through this regime. Natural England therefore defer this matter to the ExA/SoS for consideration. |  | No
E54 | 60 | Impacts beyond the operation and decommissioning of the project Within the project description it is indicated that only areas of cable that have become exposed at the time of decommissioning will be removed, and that the majority of cable will remain in situ. Similarly, it is anticipated that joining bays, both onshore (coastal) and offshore will remain in situ and there are no plans for the removal of cable/scour protection. In view of this, Natural England considers that the assessment of impacts on marine processes should extend beyond the operational lifetime of the project in order to determine if and when this infrastructure may become exposed to allow options for long term management and mitigation to be considered. Of particular concern would be the potential impact that may arise in the coastal and nearshore zone. Given the highly dynamic nature of the Holderness coastline it is imperative that the ongoing need for remedial works beyond the lifespan of the project are considered. |  | It remains unclear how the ongoing need for remedial works (i.e. removal of exposed infrastructure) will be addressed beyond the decommissioning phase. |  | No change - It remains unclear how the ongoing need for remedial works (i.e. removal of exposed infrastructure) will be addressed beyond the decommissioning phase. |  | No change |  | No change |  | We advise that the Applicant / examiner gives full consideration to the management of the export cables and other infrastructure in the nearshore zone and landfall both through the lifetime of the project, and beyond. The impacts of infrastructure left in situ beyond the lifetime of the project needs to be assessed in terms of impacts on marine processes. Similarly, the benefits and impacts of infrastructure removal at decommissioning needs to be evaluated in terms of marine processes. However, as this is unlikely to be addressed within the remaining examination period, we advise that this assessment is undertaken prior to the submission of the draft decommissioning plan and that this requirement is secured within the DCO. This assessment should consider the potential impacts of climate change (see E16 above) |  | No change |  | We advise that the Applicant / examiner gives full consideration to the management of the export cables and other infrastructure in the nearshore zone and landfall both through the lifetime of the project, and beyond. The impacts of infrastructure left in situ beyond the lifetime of the project needs to be assessed in terms of impacts on marine processes. Similarly, the benefits and impacts of infrastructure removal at decommissioning needs to be evaluated in terms of marine processes. We advise that this assessment is undertaken prior to the submission of the draft decommissioning plan and that this requirement is secured within the DCO. This assessment should consider the potential impacts of climate change (see E16 above) The Applicant has highlighted that the decommissioning programme is subject to a separate regulatory regime, and that the matters Natural England has highlighted should be addressed through through this regime. Natural England therefore defer this matter to the ExA/SoS for consideration. |  | No
E55 | 20 & 65 | Section 4.13 states large amount of sub surface infrastructure will remain in situ, unless it poses a hazard to sea users at the time of decommissioning. Further consideration should be given to the potential for infrastructure remaining in situ following decommissioning to become exposed over time, and the resulting impacts on marine processes and coastal morphology in the context of climate change. The project description also indicates that scour and cable protection (including cable crossings &rock berms) will remain in situ. The long-term implications of this beyond the operational lifetime of the project also need to be explored. |  | Our concerns over the risk of buried infrastructure becoming exposed, and impacts to marine process have not been addressed. We remain concerned that assets situated within the nearshore zone could become exposed due to the highly dynamic conditions acting on the seabed over time. Beyond the operational lifetime of the project, this could lead to scour (or secondary scour) and therefore, loss of seabed sediments which could result in morphological change. Therefore, we would wish to see this assessed more fully. |  | No change - Our concerns over the risk of buried infrastructure becoming exposed, and impacts to marine processes have not been addressed. We would wish to see this assessed more fully. |  | No change |  | No change |  | Please see our comment in E54 above. |  | No change |  | Please see our comment in E54 above. |  | No
Cumulative Impacts
E56 | 67 | We would advise that the Viking Link interconnector cable should be screened into the marine processes cumulative assessment and thus included in this table. It should be noted that Eastern Green Link and the Northern Endurance Partnership should now be considered in Tier 2. Dogger Bank South Offshore Windfarm is also at scoping stage and should therefore be considered as Tier 2. |  | The Applicant applied a cut-off date (May 2021) for projects/plans to be included in the CEA. The Applicant's response is, therefore, accurate based on this cut-off date, but should be reviewed when further details are available. |  | N.B. Natural England would expect the CEA to be updated once the outstanding issues relating to the "alone" assessment have been resolved. Additional plans/projects that have arisen beyond the May 2021 cut off can be incorporated at this stage. | [9 empty] | N.B. Natural England would expect the CEA to be updated once the outstanding issues relating to the "alone" assessment have been resolved. Additional plans/projects that have arisen beyond the May 2021 cut off can be incorporated at this stage. |  | Yes
E57 | 68 | Given that the proposed Endurance storage facility overlaps the northern part of the HP4 array, and the pipeline will need to be crossed by the HP4 offshore ECC, there may be cumulative impacts which should be considered. This should include the cumulative impact of O&M activities as well as additional wake effects if infrastructure is placed within or adjacent to the Hornsea Four array. |  | Natural England requires the Applicant to acknowledge that cumulative assessments may need to be updated if further details on the Endurance CCS are submitted to the planning authorities. This will also require the assessment of impacts in combination with the Endurance Carbon Capture project to be reviewed at a later date when more information is available. |  | N.B. Natural England would expect the CEA to be updated once the outstanding issues relating to the "alone" assessment have been resolved. Additional plans/projects that have arisen beyond the May 2021 cut off can be incorporated at this stage. | [9 empty] | N.B. Natural England would expect the CEA to be updated once the outstanding issues relating to the "alone" assessment have been resolved. Additional plans/projects that have arisen beyond the May 2021 cut off can be incorporated at this stage. |  | Yes
E58 | 69 | The SEGL2 landfall site ‘may potentially be to the North of the Hornsea 4 landfall with a cable which would pass across Smithic Bank to the north of the OECC. Potential cumulative effects with HP4 relate to construction-related sediment plumes should both projects be installed around the same period. SEGL2 cable installation and protection requirements across Smithic Bank when coupled with the Dogger Bank A&B export cables, and HP4 export cables all passing across the sandbank will need to be considered cumulatively in terms of potential impacts to the form and function of the sandbank. |  | We also remain concerned that the cumulative impacts of a number of cable installations (i.e. HP4, Dogger Bank A&B, SEGL2) and any cable protection across Smithic Bank may affect the form and function of the sandbank. Therefore, our concerns remain. We note, however, that the Applicant is carrying out a Technical Review of the MDS in relation to cable protection across Smithic Bank, and we look forward to the Clarification Note regarding MDS justification. |  | We are awaiting the outcome of the MDS Clarification Note at Deadline 3. This risk of cumulative impacts with SEGL2 should remain a key concern and more detail be presented as and when it becomes available. |  | No Change - Natural England expect to be consulted on the SEGL2 project in July via the MMO MSMC portal. |  | No change. The concerns around cumulative impacts of cable installation, cable protection, cable remediation/replacement across Smithic Bank still remain. Although a commitment to avoid cable protection across the entire bank could help reduce the cumulative impacts. |  | No change. The concerns around cumulative impacts of cable installation, cable protection, cable remediation/replacement across Smithic Bank still remain. Although a commitment to secure the measures outlined in E26, E28 and E31 would reduce the risk of significant cumulative impacts. |  | No change |  | No change. The concerns around cumulative impacts of cable installation, cable protection, cable remediation/replacement across Smithic Bank still remain. Although a commitment to secure the measures outlined in E26, E28 and E31 would reduce the risk of significant cumulative impacts. |  | No
REPORT TO INFORM HABITATS REGULATIONS ASSESSMENT
RR-029-APDX:E-I |  | LSE SCREENING - Natural England notes that only Flamborough Head SAC has been screened in for further assessment of changes to physical processes during operation and increased levels of suspended sediment during construction, operation and decommissioning. Based on the information currently available, we consider that Flamborough Head SAC should also be screened in for further assessment of changes to physical processes during construction and decommissioning, as well as beyond the operational lifetime of the project, as well as for potential changes to the hydrodynamic regime (arising as a result of potential impacts to the Flamborough Front). Flamborough and Filey Coast SPA should also be screened in for the same impacts. We also consider that the Humber Estuary SAC/SPA/Ramsar should also be screened in for further assessment of changes to physical processes throughout all stages of the project, and that the Southern North Sea SAC should be screened in for changes to hydrodynamic regime (Flamborough Front) and sediment transport regime. |  | In regard to the Flamborough Front, we refer to our earlier comment to RR-029-5.58, whereby potential adverse effects cannot be ruled out for the function of Flamborough Head SAC, Flamborough and Filey Coast SPA, and Southern North Sea SAC due to enhanced mixing of the stratified layer by the Hornsea Four array (alone and in-combination with Hornsea Two and Hornsea One). Therefore, we consider that the aforementioned designated sites should be screened in. |  | No change |  | No change |  | No change |  | No change |  | No change |  | In regard to the Flamborough Front, we refer to our earlier comment to RR-029-5.58, whereby potential adverse effects cannot be ruled out for the function of Flamborough Head SAC, Flamborough and Filey Coast SPA, and Southern North Sea SAC due to enhanced mixing of the stratified layer by the Hornsea Four array (alone and in-combination with Hornsea Two and Hornsea One). Therefore, we consider that the aforementioned designated sites should be screened in. |  | No
Marine Conservation Zones Assessment
RR-029-APDX:E-K |  | MCZ Screening |  | The Holderness Offshore MCZ lies < 1km from the proposed Hornsea Four/Dogger Bank A&B Crossing area. Given the uncertainty regarding the anticipated cable crossing footprint area, we advise that potential impacts to supporting processes (sediment transport and hydrodynamic regime) require further consideration. We also remain concerned that cable installation/protection across Smithic Bank could alter its form and function and, in turn, modify approaching waves, coastal morphology and the longshore transport of sediment. Thus, we advise consideration should be given to these impacts with regard to the Holderness Inshore MCZ. |  | No change |  | No change |  | No change |  | No change |  | No change |  | The Holderness Offshore MCZ lies < 1km from the proposed Hornsea Four/Dogger Bank A&B Crossing area. Given the uncertainty regarding the anticipated cable crossing footprint area, we advise that potential impacts to supporting processes (sediment transport and hydrodynamic regime) require further consideration. We also remain concerned that cable installation/protection across Smithic Bank could alter its form and function and, in turn, modify approaching waves, coastal morphology and the longshore transport of sediment. Thus, we advise consideration should be given to these impacts with regard to the Holderness Inshore MCZ. |  | No

## G - Fish & Shellfish
Point | [RR - 029] Appendix G point number | Taken from Natural England’s Relevant and Written Representations Hornsea [4 RR - 029 Appendix G - Fish and Shellfish] | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Risk Status Deadline 2 | Consultation, actions, progression | RAG Risk Status Deadline 3 | Consultation, actions, progression | RAG Risk Status Deadline 4 | Consultation, actions, progression | RAG Risk Status Deadline 5 | Consultation, actions, progression | RAG Risk Status Deadline 6 | Consultation, actions, progression | RAG Risk Status Deadline 7 | Consultation, actions, progression | RAG Risk Status Deadline 8 | Issue Resolved
Document used: Volume A2.3 Fish and Shellfish Ecology & Volume A5.3 Fish and Shellfish Ecology Technical Report |  |  |  | Document reviewed: [REP1-038] G1.9 Applicant’s comments on Relevant Representations Revision: 01 [REP1-039 ] G1.10 Clarification Note on Peak Herring Spawning Period and Seasonal Piling Restriction |  | Document reviewed: REP2-038 Applicant’s Responses to the ExA’s First Written Questions (ExQ1) & REP2-077 MMO Deadline 2 submissions & REP2-032 G1.10 Clarification Note on Peak Herring Spawning Period and Seasonal Piling Restriction (Tracked) - Revision: 02 |  | Document Reviewed: G3.6 Clarification Note: Justification of Offshore Maximum Design Scenarios - Revision: 01 [REP3-035]; G3.17 Applicant's comments on Natural England's Comments received at Deadline 2 - Revision: 01 [REP3-046] |  | Document Reviewed: REP4-044 G4.10 Applicant’s comments on other submissions received at Deadline 3 - Revision: 01 |  | REP5-049 G1.10 Hornsea Four Clarification Note on Peak Herring Spawning Period and Seasonal Piling Restriction (Tracked) Revision: 03; REP5-074 G5.2 Applicant’s Responses to the Examining Authority's Second Written Questions (ExQ2); REP5-083 G5.5 Clarification Note on Drill Arisings and Deposited Sediments - Revision: 01 |  | No new infomation was provided at Deadline 6 in relation to Fish and Shellfish therefore none of these issues have moved forward. |  | Documents reviewed: G1.10 Hornsea Four Clarification Note on Peak Herring Spawning Period and Seasonal Piling Restriction (Tracked) - Revision 04
G1 | 1 | A new paper has recently been published which provides new evidence of impacts of EMF on shellfish. Natural England advise that the Applicant reviews Scott et al (2021) and reconsiders the scoping out of EMF impacts on fish and Shellfish. |  | Natural England note the Applicant's response to the issue raised. However, they have not provided EMF values for their cables to allow us to compare their project with those considered within the study. We have highlighted this to the Applicant and are awaiting this information from them in order to determine if there assessment of No LSE and keeping the impact scoped out is correct. |  | Natural England are awaiting data from the Applicant on Hornsea 4 EMF predictions along the cable route in order to assess significants of impact. |  | Natural England have reviewed the projects predicted EMF levels and note that the levels appear lower than those within Scott et al (2021) where impacts were reported however it is unclear why these levels are so different to those considered representative of Offshore Windfarms in the study. Notwithstanding this, as a pathway has been identified the impact should be fully assessed and evidence provided within the Environmental Statement chapter for fish and shellfish to confirm no significant effect alone or on a cumulative basis. In this assessment it should be demonstrated why EMF levels for Hornsea 4 cables are predicted to be so much lower than those in Scott et al (2021) report, and we recommend monitoring this to validate predictions following construction. |  | No change - Natural England welcome the Examiners Question (NVL.2.2) directed at the applicant and will review the response in due course |  | Natural England have reviewed the Applicants answer to ExQ NVL.2.2 and welcome the additional explaination as to why the EMF would be lower than levels suggested elsewhere. We would continue to advocate for a proper assessment of all information relating to this issue, but are generally satisfied that the information provide during examination provides sufficent justification. We recommend a reading of EMF levels over the cables is done once opperational to provide some real life data to validate the specification levels and provide additional evidence to support industry and research moving forward. Adaptive risk management style approach might be required if the recorded levels are higher than predicted. |  |  |  | Natural England have reviewed the Applicants answer to ExQ NVL.2.2 and welcome the additional explaination as to why the EMF would be lower than levels suggested elsewhere. We would continue to advocate for a proper assessment of all information relating to this issue, but are generally satisfied that the information provide during examination provides sufficent justification. We recommend a reading of EMF levels over the cables is done once opperational to provide some real life data to validate the specification levels and provide additional evidence to support industry and research moving forward. Adaptive risk management style approach might be required if the recorded levels are higher than predicted. |  | No
G2 | 2 & 6 | Whilst Natural England welcome the commitment to avoid piling during the period 1st September to the 16th October within the HVAC search area (Co190), we do not believe the evidence presented is strong enough to limit this measure to that 6-week period. The spawning season for Herring is 1st August – 31st October. The 6-week period proposed here is based on a piling restriction used for Triton Knoll OWF. The Applicant is asked to provide site specific evidence to support a ‘peak’ Herring spawning season for the Hornsea 4 area or is advised to follow a precautionary approach and halt piling from 1st August - 31st October. This issue was raised previously in our advice on the draft ES in November 2020. Whilst the implementation of a seasonal piling restriction goes some way to minimum risk to the herring spawning ground in the vicinity of HVAC, Natural England do not consider that sufficient evidence has been presented to limit this ‘peak’ spawning period to just 6 weeks. As per our comments on the draft Environmental Statement in November 2020 and above in point 2 we wish to see additional evidence provided to support this ‘peak’ spawning period of The Banks herring spawning ground, or an expansion in the ‘peak’ period to cover the full spawning season in order to reduce the effect on herring. Until this is addressed, we can’t agree with the magnitude of effect on herring from piling being assessed as ‘minor’ at this time. |  | Natural England notes that the MMO (as advised by Cefas) have responded to the Applicant's 'Clarification note on peak herring spawning period' (G1.10) at Deadline 1. Natural England would like to see the Applicant's Response to this submission before making further comment on this point. |  | Natural England cannot support the Applicants position on 'peak herring spawning' G1.10 as there are limitations with the use of IHLS survey data underpinning the calculation of 'peak' herring spawning. The IHLS surveys are conducted during a narrow window each year with the aim of showing herring active spawning grounds and is not intended to be used for determining peak periods of spawning. By using these survey dates as the start point for this calculation bias is introduced, as no larva hatched after this date can be considered and any larva hatched early may have had opportunity to move out of area. With this in mind Natural England’s position remains unchanged. We consider that more precaution needs to be included within the ‘peak herring spawning’ calculation and / or agreement to expand the no piling period of Co190 beyond the current 6 weeks. This is due to concerns Natural England have about the potential impacts of piling on herring stocks as it would result in less food for protected bird and marine mammal species off Flamborough and within the North Sea. |  | No change |  | No change |  | Natural England do not support the current piling restriction period for the reasons previously outlined. Given the limited amount of time remaining within the Examination, and recognising that the MMO as advised by Cefas are also looking for the pilling restriction period to be extended; we defer to Cefas’ expertise in determining a more suitable period. |  |  |  | We note the Applicant has increased their piling restriction period to 21st August - 23rd October. As before, we defer to Cefas’ expertise in determining whether this is sufficient to resolve concerns. |  | No
G3 | 3, 5 & 10 | The technical report shows the International Herring Larvae Survey (IHLS) larval densities to vary from year to year. This makes it difficult to say with certainly that there is no overlap between the ECC area and high-density spawning areas. Therefore, Natural England believe the magnitude of impact of direct disturbance on herring spawning grounds (FSE-C-1), and temporary localised increases in SSC and smothering (FSE-C-2) should be higher than 'minor' on a precautionary basis as there is the potential for impacts to become more significant in EIA terms and/or lead to ‘loss of resource’ where overlap occurs. Natural England welcome the adjustment of sensitivity of spawning herring to SSC from medium to high. |  | Natural England does not feel the description of the peak herring spawning area and the ECC is accurate in the ES as there are instances when the peak area does overlap directly. The mobile and annual variation in peak spawning areas make determining overlap and therefore likely effect difficult. However following the Applicants response to our relevant reps, we do appreciate that the spawning area is large and even in years when peak spawning does overlap with the ECC this is only a minor overlap in relation to the size of the spawning area. Therefore we accept that minor magnitude has been correctly assigned in this instance. | [11 empty] | Natural England does not feel the description of the peak herring spawning area and the ECC is accurate in the ES as there are instances when the peak area does overlap directly. The mobile and annual variation in peak spawning areas make determining overlap and therefore likely effect difficult. However following the Applicants response to our relevant reps, we do appreciate that the spawning area is large and even in years when peak spawning does overlap with the ECC this is only a minor overlap in relation to the size of the spawning area. Therefore we accept that minor magnitude has been correctly assigned in this instance. |  | Yes
G4 | 4 | Natural England do not feel the impacts associated with drilling foundations, in particular the mounds formed following disposal of drill material, have been considered in the impact assessment (as raised previously in Nov 2020). This also applies to the benthic chapter. Whilst the impacts from increased suspended sediment are considered, there is no mention of temporary or long-term habitat loss/change in habitat as a result of drill arisings forming persistent mounds or changing surface substrate type. Whilst the area affected might be less than the presence of the infrastructure itself, the area impacted by disposal will be in addition to the infrastructure itself and therefore needs to be considered in the impact assessment. |  | Natural England note the applicants comment that any area impacted by drill arising will be within the footprint of seabed preparation works, however the impacts from drill arisings are likely to be different to those arising from the use of GBS. Therefore it is still Natural England's position that impacts associated will drill arisings should be assessed in the context of Fish and Shellfish as well as other receptors within the ES. (N.B We have changed the RAG status from yellow to align with similar comments made in relation to benthic ecology and that we would like this issue to be considered further). |  | No change - It is Natural England's position that impacts associated with drill arisings should be assessed in the context of Fish and Shellfish as well as other receptors within the ES. |  | The Applicant has stated in REP3-046 (page 59) that further consideration is being given to the impact of drill arisings and a clarification note due to be submitted into Examination at Deadline 5. |  | No update |  | Natural England welcome the additional information supplied by the applicant to address this matter. We would welcome clarification as to how the figure of 0.027km2 has calculated to confirm this is a true reflection of the worst-case scenario. However Natural England agree that the scale presented is not significant in a fish/shellfish context provided the assumptions made within the assessment hold true. Ideally we would have liked to have seen this incorporated into the assessment as opposed to being presented as a standalone figure, however given the stage of the examination we are content to close out this issue. |  |  |  | Natural England welcome the additional information supplied by the applicant to address this matter. We would welcome clarification as to how the figure of 0.027km2 has calculated to confirm this is a true reflection of the worst-case scenario. However Natural England agree that the scale presented is not significant in a fish/shellfish context provided the assumptions made within the assessment hold true. Ideally we would have liked to have seen this incorporated into the assessment as opposed to being presented as a standalone figure, however given the stage of the examination we are content to close out this issue. |  | No
G5 | 7 | Natural England suggests the calculated combined suspended sediment levels is reduced in line with the area of overlap between the Dogger Bank A & B export cables and the fish and shellfish study area. This will allow a more accurate cumulative impact to be assessed. |  | Natural England notes the Applicant's response to this point. We appreciate that taking a precautionary approach to setting MDS has become industry standard, however we also note that presenting a "realistic scenario" alongside the "worst case" is used elsewhere in the Application and that this could have been useful here. | [11 empty] | Natural England notes the Applicant's response to this point. We appreciate that taking a precautionary approach to setting MDS has become industry standard, however we also note that presenting a "realistic scenario" alongside the "worst case" is used elsewhere in the Application and that this could have been useful here. |  | No
G6 | 8 | Natural England does not believe there is sufficient information or evidence available on the Endurance Carbon Capture project to reach the anticipated conclusion that there would be no significant impact. The Applicant recognises there is limited detail on the project at this time, and it is not possible to make a detailed assessment Natural England would like the Applicant to acknowledge that there may be overlap with the construction phase of the Endurance project and Hornsea 4 as the timelines provided are very tight in relation to consent and start of construction. There is also no acknowledgment (in this report or the Annex 3.5 Offshore cumulative effects) that the two projects overlap in spatial extent, which can only magnify the impacts. Natural England require the assessments of impacts in combination with the Endurance Carbon Capture project to be reviewed at a later date when more information is available. This is the case for all impact receptor pathways for which the Endurance Carbon Capture project is currently assessed against. |  | Natural England welcomes the applicant's commitment to update the cumulative assessment if and when new information comes forward on this project to the planning inspector. The Endurance Carbon Capture project has submitted an EIA scoping document to BEIS in September 2021 for the project therefore it should now be considered a Tier 2. It is unclear if the information from this consultation has been included in the assessment. |  | Could the Applicant confirm what information has been used to assess the cumulative impacts from Endurance Carbon capture project. |  | Natural England welcome the Applicant's commitment to review the Northern Endurance Partnership project offshore EIA Scoping Report and that consideration is being given to the update of cumulative assessments within a future Examination submission. We will review this again when updated. |  | No Update |  | The Applicant has reviewed the information presented within the NEP Scoping Report. They have confirmed that it contains no details over and above what was available at the time of writing the ES. Therefore the Applicant’s position is that it is not possible to undertake more detailed cumulative effects assessments (CEA). Natural England welcome this confirmation. However, Natural England considers that there is a potential risk of cumulative impacts as a result of these projects constructing and operating within similar timeframes. Therefore should NEP make an application prior to the determination of this case, Natural England advise that the cumulative impacts will need to be assessed, including within the HRA. |  |  |  | The Applicant has reviewed the information presented within the NEP Scoping Report. They have confirmed that it contains no details over and above what was available at the time of writing the ES. Therefore the Applicant’s position is that it is not possible to undertake more detailed cumulative effects assessments (CEA). Natural England welcome this confirmation. However, Natural England considers that there is a potential risk of cumulative impacts as a result of these projects constructing and operating within similar timeframes. Therefore should NEP make an application prior to the determination of this case, Natural England advise that the cumulative impacts will need to be assessed, including within the HRA.
G7 | 9 | We note that some of the data sets used within the technical report are quite old (circa 10 years). We would defer to Cefas (MMO) on the appropriateness of this. |  | The age of the data is still of concern to Natural England but will not make a material difference in the case of this project. | [11 empty] | The age of the data is still of concern to Natural England but will not make a material difference in the case of this project. |  | No

## H-Onshore ecology, Landscape (hidden)
Point | [RR - 029] Appendix H point number | Taken from Natural England’s Relevant and Written Representations Hornsea 4 Appendix H to the Relevant Representations of Natural England Onshore Ecology & Landscape, Seascape and Visual Effects [RR-029] | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Risk Status Deadline 2 | Consultation, actions, progression | RAG Risk Status Deadline 3 | Consultation, actions, progression | RAG Risk Status Deadline 4 | Consultation, actions, progression | RAG Risk Status Deadline 5 | Consultation, actions, progression | RAG Risk Status Deadline 6 | Consultation, actions, progression | RAG Risk Status Deadline 7 | Consultation, actions, progression | RAG Risk Status Deadline 8 | Issue Resolved
Document Used: A3.6 Land Use and Agriculture
H1 |  | Natural England would have preferred BMV surveys to have been completed prior to application. But commitment to surveys and mitigation is adequate to prevent significant harm to BMV soils. |  | Natural England will review The Applicants comments on Onshore matters for deadline 5. |  | Natural England will review The Applicants comments on Onshore matters for deadline 5. |  |  |  | This issue has been noted by the Applicant. As per the RAG status (in 'how to read this log') this issue is assigned yellow as whilst the approach is inconsistent with Natural England's advice, we consider that in this particular case it is unlikely to make a material difference. Consequently, Natural England have no further comments on the issue unless otherwise directed by the ExA.
Document Used: A4.3 Selection and Refinement of the Onshore Infrastructure
H2 |  | Natural England found some errors in the selection criteria e.g. Table 10 states that black should be used for routes intersecting SSSIs. But in table 11 both routes intersect a SSSI but they are in amber. Also, there was no assessment of BMV soils in the route selection. From the information provided it is difficult to ascertain whether it is the most sustainable route. However, the mitigation and surveys for onshore issues from the other parts of the document are adequate to prevent impacts. |  | Natural England will review The Applicants comments on Onshore matters for deadline 3. |  | Natural England will review The Applicants comments on Onshore matters for deadline 5. |  |  |  | The Applicant acknowledges that there are inconsistencies however these would not alter site selection or the route planning process. Also acknowledged that NE's assistance and input that significant effects are expected to be prevented at the crossing locations associated with River Hull SSSI. As per the RAG status (in 'how to read this log') this issue is assigned yellow as whilst the approach is inconsistent with Natural England's advice, we consider that in this particular case it is unlikely to make a material difference. Consequently, Natural England have no further comments on the issue unless otherwise directed by the ExA.
Document Used: A4.4.2 Onshore Crossing Schedule
H3 |  | In the crossing schedule table the ‘Related Co Number’ only mentions Co1 for the SSSI crossing points. It does not mention Co18, Co124, & Co168 which contain specific measures for the SSSI and is an important part of the mitigation for crossing. If this document is a working document for keeping track of mitigation measures at each crossing point, Natural England suggest this is addressed. The correct mitigation is identified in the commitments Co18, Co124 & Co168, provided these are secured for all relevant crossings with SSSI this should be acceptable. |  | Natural England will review The Applicants comments on Onshore matters for deadline 3. |  | Natural England will review The Applicants comments on Onshore matters for deadline 5. |  |  |  | The Applicant acknowledges that commitments 18, 124 and 168 are relevant to River Hull SSSI and will be secured via relevant DCO requirements and associated plans. Natural England are content that this is sufficent to mitigate impacts to the River Hull SSSI.
Document Used: A4.5.6 Location of Onshore Cumulative Schemes
H4 |  | To the best of Natural England’s knowledge, this appears accurate. However, we would defer to the Local Planning Authority on this matter. |  | Natural England will review The Applicants comments on Onshore matters for deadline 3. |  | Natural England will review The Applicants comments on Onshore matters for deadline 5. |  |  |  | This issue has been noted by the Applicant. As per the RAG status (in 'how to read this log') this issue is assigned yellow as whilst the approach is inconsistent with Natural England's advice, we consider that in this particular case it is unlikely to make a material difference. Consequently, Natural England have no further comments on the issue unless otherwise directed by the ExA.
Document Used: A6.3.2 Extended Phase 1 Target Note Tables
H5 |  | The document doesn’t reference the River Hull Headwaters SSSI, where Natural England believe it should, however it doesn’t affect the outcome of the application. |  | Natural England will review The Applicants comments on Onshore matters for deadline 3. |  | Natural England will review The Applicants comments on Onshore matters for deadline 5. |  |  |  | This issue has been noted by the Applicant. As per the RAG status (in 'how to read this log') this issue is assigned yellow as whilst the approach is inconsistent with Natural England's advice, we consider that in this particular case it is unlikely to make a material difference. Consequently, Natural England have no further comments on the issue unless otherwise directed by the ExA.
Document Used: A6.3.4 Breeding Bird Survey Report
H6 |  | The document doesn’t reference the River Hull Headwaters SSSI, but it doesn’t affect the overall outcome of the application. |  | Natural England will review The Applicants comments on Onshore matters for deadline 3. |  | Natural England will review The Applicants comments on Onshore matters for deadline 5. |  |  |  | This issue has been noted by the Applicant. As per the RAG status (in 'how to read this log') this issue is assigned yellow as whilst the approach is inconsistent with Natural England's advice, we consider that in this particular case it is unlikely to make a material difference. Consequently, Natural England have no further comments on the issue unless otherwise directed by the ExA.
Document Used: F2.6 Outline Onshore Infrastructure Drainage Strategy
H7 |  | There is no mention of SSSI or the need to consult NE within this document. Although not mentioned, this is in the Code of Construction Practice so Natural England consider this acceptable. |  | Natural England will review The Applicants comments on Onshore matters for deadline 3. |  | Natural England will review The Applicants comments on Onshore matters for deadline 5. |  |  |  | This issue has been noted by the Applicant. As per the RAG status (in 'how to read this log') this issue is assigned yellow as whilst the approach is inconsistent with Natural England's advice, we consider that in this particular case it is unlikely to make a material difference. Consequently, Natural England have no further comments on the issue unless otherwise directed by the ExA.

## I - DCO
Point | Rel rep Reference | Taken from Natural England’s Relevant and Written Representations Horsnea 4 Appedix A - Development Consent Order, Deemed Marine License and related certified documentation | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Risk Status Deadline 5a | Consultation, actions, progression | RAG Risk Status Deadline 6 | Consultation, actions, progression | RAG Risk Status Deadline 7 | Consultation, actions, progression | RAG Risk Status Deadline 8 | Issue Resolved
Document reviewed: C1.1 Draft DCO including Draft DML |  |  |  | Documents reviewed: G1.9 Applicant's comments on Relevant Representations Revision: 01 [REP1-038] |  | Documents reviewed: REP5-036 C1.1.1 Schedule of Changes to the draft Development Consent Order (DCO) and Deemed Marine Licences (DML); REP5-089 Updated draft Development Consent Order (dDCO) (Tracked) ; REP5a-003 C.1.1 Draft Development Consent Order (Tracked); AS-036 G6.5 Applicants Comments on Natural England's DCO Submissions received at Deadline 5a |  | An updated DCO was not submitted at Deadline 6, therefore none of the issues below have been moved forward. |  | Documents reviewed: G7.2 Applicant’s comments on other submissions received at Deadline 6 - Revision: 01; B2.7 Flamborough and Filey Coast (FFC) Special Protection Area (SPA) Kittiwake Compensation Plan (Tracked): Revision 03
I1 | 1 | Part 1 Article 2 Natural England does not agree with the definition of Environmental Statement (ES) as it does not allow for any additional evidence to be submitted later and be considered part of this statement. This is important as decisions will take into account not just evidence supplied during the application, but further evidence supplied during the examination. This subsequent information will likely be the information that the Examining Authority (ExA) makes their recommendation on and the Secretary of State makes their determination on. Therefore, when looking at items such as maximum extents, volumes etc these later documents may be the correct ones to use for certain conditions/plans and thus should be reflected in the interpretations. The interpretation should be updated. |  | Natural England notes the Applicant’s response [REP1-038]. Our position remains unchanged, we note that the recent Boston Alternative Energy project DCO has included an updated definition of Environmental Statement that allows for documents submitted after application to be included. If this is not addressed in the DCO, updated ES chapters would need to be provided accounting for any new information provided during Examination. |  | Natural England notes the Applicant's response to our comments dated 8 July, and the addition of a part 2 in schedule 10 to cover documents submitted during Examination as certified documents and therefore part of the Environmental Statement (ES). Subject to this list being accurate Natural England agrees this resolves the concerns we had raised with the definition of Environmental Statement. Whilst this is acceptable in terms of the definition of the ES, for clarity - both for this Project in its post consent phase and for other Projects undertaking cumulative assessments - we consider it important that the ES itself reflects the corrected values from updated assessments prodvided during Examination. See action ISH11-3 in our DL6 cover letter. |  |  |  | Natural England notes the Applicant's response to our comments dated 8 July, and the addition of a part 2 in schedule 10 to cover documents submitted during Examination as certified documents and therefore part of the Environmental Statement (ES). Subject to this list being accurate Natural England agrees this resolves the concerns we had raised with the definition of Environmental Statement. Whilst this is acceptable in terms of the definition of the ES, for clarity - both for this Project in its post consent phase and for other Projects undertaking cumulative assessments - we consider it important that the ES itself reflects the corrected values from updated assessments prodvided during Examination. See action ISH11-3 in our DL6 cover letter. |  | Yes
I2 | 2 | Part 1 Article 2 The definition of maintain does not link to an Outline Operations and Maintenance (O&M) plan. The definition and interpretation of what is permitted under maintain is linked to the ES. We acknowledge that Tables 4.43-4.45 in Volume A4, Chapter 4 Project Description are excellent and do give detailed information on what maintenance is expected, however we consider that the standard approach of using an O&M plan to detail what is licenced and may be undertaken without permission, what needs further permission and what is not licenced and will need further consent significantly reduces the risks of misunderstanding during operation and is an essential point of reference for approvals and consenting during the lifetime of the project. We suggest that the tables used in the Project Description could be turned into the outline O&M plan, or the interpretation could be amended to refer to these tables for offshore to avoid ambiguity (subject to our concerns regarding cable protection over the lifetime of the project, see Point 34). Updates should be reflected in both the interpretations and the deemed Marine License (dML) conditions. |  | Natural England welcomes the submission of the Outline Operations and Maintenance Plan (OOMP) at Deadline 2. Our request to have the definition of maintain link to the OOMP remains, however, we note the inclusion of the definition of the OOMP within the deemed Marine License schedules and support the inclusion. |  | No change. |  |  |  | Natural England welcomes the submission of the Outline Operations and Maintenance Plan (OOMP) at Deadline 2. Our request to have the definition of maintain link to the OOMP remains, however, we note the inclusion of the definition of the OOMP within the deemed Marine License schedules and support the inclusion. |  | No
I3 | 3 | Schedule 1 Part 3 Requirements The maximum volumes of dredge works, such as sandwave clearance, are not provided here. We note that they are given in Schedule 1 Part 1, however, as this section details the maximum design parameters and as dredging is a significant impact and an important parameter to enforce, we would have expected it to be provided here. As the figures are provided in the DMLs and the maximums would be enforced by the MMO we do not think this is a major issue in and of itself. |  | No further comment. | [5 empty] | No further comment. |  | No
I4 | 4 | Schedule 1 Part 3 Requirement 2(2)(c) This requirement gives the minimum blade distance to sea as 42.43m. However, this is based on LAT (lowest astronomical tide). We note that it is normally given as HAT (highest astronomical tide). Using LAT implies a much higher distance between turbine blade and the sea. While in theory neither is incorrect, we consider it important to note that simply changing the metric would not provide any enhanced mitigation. We request that the value in HAT is provided to allow comparison with the gap for other developments. |  | The applicant has provided the requested information. We have no further comment to make at this juncture. | [5 empty] | The applicant has provided the requested information. We have no further comment to make at this juncture. |  | Yes
I5 | 5 | Schedule 1 Part 3 Requirement 2(6) This requirement gives the maximum footprint for all turbines. However, there is no limitation on the maximum scope per individual foundation. We would note the same issue with regard to the substation foundations at requirement 3(11) and (12). This issue is repeated in the Deemed Marine licences. We request that the maximum footprint for individual turbine foundations and other marine structures is provided within the DCO and the dMLs. |  | No change. |  | No change. |  |  |  | No change. |  | No
I6 | 6 | Schedule 1 Part 3 Requirement 24 The relevant SNCB should be consulted upon any decommissioning plan and that consultation should be secured within this requirement. We request this requirement is updated to reflect this. |  | Natural England notes the Applicant’s response [REP1-038]. Our position remains unchanged, however, we note the SoS may make a determination on the drafting. |  | No change. |  |  |  | Natural England notes the Applicant’s response [REP1-038]. Our position remains unchanged, however, we note the SoS may make a determination on the drafting. |  | No
I7 | 7 | Schedule 11 Part 2 Condition 4 Natural England have concerns regarding the granting of a licence for cable protection deployment across the lifetime of the development. (See also rel rep point 34) |  | The Applicant proposes limiting the cable repair deployment licensed under the DCO to 15 years and has updated the DCO accordingly. This is in line with the approach agreed between the SNCBs and MMO. |  | Natural England notes that our agreement with this provision was made in error. We apologise for our mistake. Our current position is that cable protection should only be licensed for a maximum period of 10 years after construction outside of marine designated sites. Please see our draft paper as submitted to the Boreas examination at deadline 3: https://infrastructure.planninginspectorate.gov.uk/wp-content/ipc/uploads/projects/EN010087/EN010087-001527-DL3%20-%20Natural%20England%20-%20Draft%20Position%20Paper.pdf |  |  |  | Natural England notes that our agreement with this provision was made in error. We apologise for our mistake. Our current position is that cable protection should only be licensed for a maximum period of 10 years after construction outside of marine designated sites. Please see our draft paper as submitted to the Boreas examination at deadline 3: https://infrastructure.planninginspectorate.gov.uk/wp-content/ipc/uploads/projects/EN010087/EN010087-001527-DL3%20-%20Natural%20England%20-%20Draft%20Position%20Paper.pdf |  | No
I8 | 8 | Schedule 11 Part 2 Condition 13(1)(j) This condition secures the use of a Site Integrity Plan so that in combination projects and the project alone do not have an adverse effect on the integrity of the Southern North Sea Special Area of Conservation (SNS SAC). However, recent decisions have reduced our certainty that this condition will adequately address the issues of in combination impacts. This condition is linked to condition 14 which requires the document to be produced no later than 4 months prior to commencement. However, we consider that it should also be restricted to a requirement of no sooner than 6 months prior to commencement. |  | Following further consideration and experience with regard to a Site Integrity Plan sign off process Natural England’s position has changed slightly. We note that the condition as currently drafted also allows for the plan to be submitted far in advance which could lead to issues if the details of construction are not fully available. Therefore, we consider that the condition should state the plans should be submitted no sooner than 9 months and no later than 6 months prior to works. We note that whilst the Applicant has included this timeframe within the Outline SNS SAC SIP, they do not consider the timing requirement should be included in the DCO. Natural England maintains that the timeframe of the SIP needs to be secured in the DCO. |  | Natual England maintains our position that it is important to secure the timings for this important document. We do not consider the securing of a minimum timing is likely to prevent early discussion as we frequently have engagement with a wide range of developers in advance of statutory submission deadlines. |  |  |  | Natual England maintains our position that it is important to secure the timings for this important document. We do not consider the securing of a minimum timing is likely to prevent early discussion as we frequently have engagement with a wide range of developers in advance of statutory submission deadlines. |  | No
I9 | 9 | Schedule 11 Part 2 Condition 13 (5) and (6) These conditions allow for simultaneous piling of 2 piles to occur, either within the same licensed area or across the array (Schedule 11) and HVAC booster station (Schedule 12) areas. However, there is no restriction on the of number of piles that can be installed in a day. We further note that the Applicant refers to concurrent piling (defined as “two separate foundation locations per 24 hours”; B2.2 RIAA Part 1, 10.3.3.37) in two locations in their RIAA. We are concerned that whilst these conditions restrict the level of simultaneous piling (i.e. no more than 2 piles at the same time), there are no restrictions on the number of piles that can be installed in a day and no restrictions on conducting simultaneous and concurrent piling. This could allow up to 4 piling locations in a 24-hour period which would exceed the maximum design scenario. We request that these conditions are amended to restrict all activities to within a calendar day and that condition 6 is also amended to allow only simultaneous or concurrent piling of 2 piles to occur. |  | Natural England notes the changes and welcomes that the Applicant has made it clear that only 2 piles may be piled in a 24-hour period and has updated the DCO accordingly . | [5 empty] | Natural England notes the changes and welcomes that the Applicant has made it clear that only 2 piles may be piled in a 24-hour period and has updated the DCO accordingly . |  | Yes
I10 | 10 | Schedule 11 Part 2 Condition 14 This condition ensures that for most documentation, plans need to be submitted 4 months in advance to the MMO. Given the significant increase in the size, scope and potential for in combination impacts of offshore windfarm projects we consider that 4 months is now insufficient time, and a 6-month requirement would be more appropriate. We highlight that a 6-month condition was recently agreed for EA1N and EA2. We request the condition be amended to reflect a 6-month requirement for pre-construction. However, we would be willing to discuss a more detailed condition that looked to remove the ‘one size fits all’ approach, allowing for most documents to be 4 months, but key documents to be 6 months. |  | Natural England notes and welcomes the change for some of the documents. However, our concerns still remain and we would like further dialogue on adding further documents to the list proposed by the Applicant. Such as the updated SIP document, for example (see Point 8 above). |  | See Point 8. |  |  |  | See Point 8. |  | No
I11 | 11 | Schedule 11 Part 2 Condition 18 This condition does not allow for a stop should the noise of the piling be significantly in excess of the predicted noise levels. Given concerns related to in-combination noise, especially in relation to Marine mammals and the SNS SAC, it is essential that appropriate controls are provided. We request that the following conditions agreed on EA1N and EA2 are included here: Draft DCO Schedule 13 Part 2, condition 2: (2) The undertaker must carry out the surveys approved under sub-paragraph (1), including any further noise monitoring required in writing by the MMO, and provide the agreed reports in the agreed format in accordance with the agreed timetable, unless otherwise agreed in writing with the MMO in consultation with the relevant statutory nature conservation bodies. (3) The results of the initial noise measurements monitored in accordance with sub-paragraph (1) must be provided to the MMO within six weeks of the installation of the first four piled foundations of each piled foundation type. The assessment of this report by the MMO will determine whether any further noise monitoring is required. If, in the opinion of the MMO in consultation with the statutory nature conservation body, the assessment shows statistically significantly different impacts to those assessed in the environmental statement or failures in mitigation, all piling activity must cease until an update to the marine mammal mitigation protocol and further monitoring requirements have been agreed. |  | No change. |  | Natural England notes and welcomes the changes to the condition at Deadline 5a and consider these amendments are sufficient to address our concerns. |  |  |  | Natural England notes and welcomes the changes to the condition at Deadline 5a and consider these amendments are sufficient to address our concerns. |  | Yes
I12 | 12 | Schedule 11 Part 2 Condition 18(2)(a) Natural England notes that this condition includes a requirement to monitor the noise generated by the first four piles installed. This requirement is in line with previous requirements for similar projects. However, Natural England would consider the first four piles to represent the minimum requirement and would welcome discussion on expanding this proposed monitoring to include an agreed selection of the most resistant piles. The most resistant piles are likely to represent the largest noise impacts and could be further used to validate the noise impact predictions of the ES. |  | The Applicant has indicated their position and drafting will not change. Natural England’s position remains unchanged. |  | No change. |  |  |  | The Applicant has indicated their position and drafting will not change. Natural England’s position remains unchanged. |  | No
I13 | 13 | Schedule 11 Part 2 conditions 17-19 No monitoring conditions include the requirement to follow the Marine Mammal Monitoring Plan. We consider that adherence to the plan should be secured within the dMLs. |  | The Applicant has advised that conditions 17(3), 18(4) and 19 (3) of schedules 11 and 12 secure the marine mammal monitoring plan as they require the Applicant to carry out surveys in line with the outline Marine Mammal Monitoring Plan. Natural England questions this assertion as the Outline Marine Mammal Monitoring Plan is not referenced anywhere in the DCO/DML and the conditions themselves do not refer to marine mammals at all. We would welcome a legal opinion from the MMO on this point. |  | No change. |  |  |  | The Applicant has advised that conditions 17(3), 18(4) and 19 (3) of schedules 11 and 12 secure the marine mammal monitoring plan as they require the Applicant to carry out surveys in line with the outline Marine Mammal Monitoring Plan. Natural England questions this assertion as the Outline Marine Mammal Monitoring Plan is not referenced anywhere in the DCO/DML and the conditions themselves do not refer to marine mammals at all. We would welcome a legal opinion from the MMO on this point. |  | No
I14 | 14 | Schedule 11 Part 2 condition 24 Natural England welcome in principle the inclusion of a completion of construction condition, however we note that we may wish to raise issues at a later date following discussion with the MMO to agree industry wide standardisation of the condition.
I15 | 15 | Schedule 12 All issues raised under Schedule 11 also apply to Schedule 12 where similar conditions exist.
I16 | 16 | Schedule 12 Part 2 There are no conditions in this Schedule limiting the maximum hammer energy to be used during piling. Schedule 11 Condition 13(4) should be in repeated in Schedule 12 to restrict the maximum hammer energy to 5,000kJ. |  | Natural England welcomes the amendments the applicant has made to add a condition and consider the proposed changes address these concerns. | [5 empty] | Natural England welcomes the amendments the applicant has made to add a condition and consider the proposed changes address these concerns. |  | Yes
I17 | 17 | Schedule 12 Part 2 Condition 26(1)(a) This condition refers to the final number of installed turbines. This licence does not cover turbine installation and the condition should therefore refer to the number of substations. |  | Natural England notes that the requirement for a close out report has been entirely removed. We would note that our comment was not asking for the removal of the close out report, and we still consider there is a need for a close out report for the transmission assets to confirm the end of construction of the transmission works and to provide the final details on the deployment of cable, cable protection and the installation of the substations. |  | We note the Applicant's response. However, we maintain our position that a close out report for transmission assets would be valuble to confirm the end of construction, and provide final details of cable and cable protection. However, we are content for the SoS to determine if there is a need for this requirement. |  |  |  | We note the Applicant's response. However, we maintain our position that a close out report for transmission assets would be valuble to confirm the end of construction, and provide final details of cable and cable protection. However, we are content for the SoS to determine if there is a need for this requirement. |  | No
I18 |  |  |  | Although we haven’t raised this previously within this Examination, we have suggested to both the Applicant and the MMO that there may be merit in including the landfall activities within a separate schedule of the DCO/dML. Landfall works usually commence ahead of the other offshore transmission works and this results in developers seeking partial discharge of conditions and associated documents to enable these works to progress. We therefore query whether the inclusion of these works in a separate schedule would give greater clarity to all parties and allow more efficient discharge of conditions post consent. We would welcome feedback from the Applicant and the MMO on this suggestion. | [5 empty] | Although we haven’t raised this previously within this Examination, we have suggested to both the Applicant and the MMO that there may be merit in including the landfall activities within a separate schedule of the DCO/dML. Landfall works usually commence ahead of the other offshore transmission works and this results in developers seeking partial discharge of conditions and associated documents to enable these works to progress. We therefore query whether the inclusion of these works in a separate schedule would give greater clarity to all parties and allow more efficient discharge of conditions post consent. We would welcome feedback from the Applicant and the MMO on this suggestion. |  | No
I19 | NA |  |  |  |  | Natural England notes the changes at Schedule 1 Part 3 requirement 3(13) and the similar changes in schedule 11 with regard to the increase in the number of gravity base structures. We would note we have responded with regard to this in relation to the benthic and coastal processes impacts and that position is that no gravity bases should be used. |  |  |  | Natural England notes the changes at Schedule 1 Part 3 requirement 3(13) and the similar changes in schedule 11 with regard to the increase in the number of gravity base structures. We would note we have responded with regard to this in relation to the benthic and coastal processes impacts and that position is that no gravity bases should be used. |  | No
I20 | [5 empty] | Natural England notes the removal of provisions related to maintenance not considered within the environmental assessment in schedule 11 and 12 Part 2 Condition 4. It is our interpretation that this means any maintenance not covered in the Environmental Statement would require a separate Marine Licence. However, clarification of this point would be appreciated. |  |  |  | Natural England notes the removal of provisions related to maintenance not considered within the environmental assessment in schedule 11 and 12 Part 2 Condition 4. It is our interpretation that this means any maintenance not covered in the Environmental Statement would require a separate Marine Licence. However, clarification of this point would be appreciated. |  | No
I21 | [5 empty] | Natural England notes the changes proposed within schedule 12 Part 2 Condition 3 (2). We note this would limit the cable portection within Smithic Bank to 5% of the length of cable within the area. We accept the wording proposed, however, this is without prejudice to our conerns expressed elsewhere that the cable protection should not be used within this area. |  |  |  | Natural England notes the changes proposed within schedule 12 Part 2 Condition 3 (2). We note this would limit the cable portection within Smithic Bank to 5% of the length of cable within the area. We accept the wording proposed, however, this is without prejudice to our conerns expressed elsewhere that the cable protection should not be used within this area. |  | No
I22 | F6 - benthic chapter |  |  |  |  | Natural England welcome the commitment to microsite around habitats of principal importance (as identified under NERC 2006) wherever possible during the construction phase, whilst highligting that this commitment will only reduce the risk of impacts to these features rather than remove it completely. In instances where micrositing to avoid the impact cannot be acheived, Natural England would like to see commitment to explore further options to reduce or mitigate impacts and potentially monitoring as required. This could be secured by expanding condition 13 (1) (c) (ix) of Schedules 11 and 12 to include habitats of principal importance (as well as national sites i.e. MCZs, SSSIs and HPMAs). |  |  |  | The Applicant has followed our suggestion and included consideration of habitats of principal importance and any international or nationally designated sites sites within Consition 13 1 c ix of sechedule 11 & 12 providing some mitigation to impacts on nationally designated sites. |  | Yes
I23 | [5 empty] | Natural England note that potential impacts to Habitats of Principal Importance during operation and maintenance activities has not been addressed. We would like to see a commitment to avoid/reduce/mitigate impacts to priority habitat as far as possible during the O&M phase, and a reference to this within the outline O&M plan. |  |  |  | Natural England note that potential impacts to Habitats of Principal Importance during operation and maintenance activities has not been addressed. We would like to see a commitment to avoid/reduce/mitigate impacts to priority habitat as far as possible during the O&M phase, and a reference to this within the outline O&M plan. |  | No
Document reviewed: B2.7 FFC SPA: Gannet and Kittiwake Compensation Plan and B2.8 FFC SPA: Guillemot and Razorbill Compensation Plan |  |  |  | Document reviewed: B2.7 FFC SPA: Gannet and Kittiwake Compensation Plan and B2.8 FFC SPA: Guillemot and Razorbill Compensation Plan
I24 | 19 | Part 1 Condition 2 This condition needs to include a requirement to consult the relevant SNCB, as well as all other members of the Hornsea 4 (H4) Offshore Ornithology Engagement Group (OOEG). Please note this condition includes the terms of reference (TOR) that the H4 OOEG will adhere to, as well as details of the requirements upon the members in terms of timetables, meetings etc. Also, the details of the dispute mechanism and what the scope of the discussions of the H4 OOEG is to cover. It is essential that these factors are discussed and ideally agreed with all the members of the H4 OOEG and this is not currently secured within these draft conditions. |  | Natural England notes the response and that the Applicant considers consultation on the KCIMP elsewhere is sufficient. However, as noted in our original response the draft KCIMP document is produced after the OOEG Terms of reference, timetables, requirements, membership and dispute mechanism. All of which the membership of the OOEG should be consulted upon if they are to be bound by these documents. As currently drafted the membership of this group are going to be informed of the obligations on them with no formal option to respond. We note that Section 1.4.1.3 of the Kittiwake Compensation Plan [REP5-017] states that “Terms of Reference would be agreed between the parties”. We consider this should be secured in the DCO condition. |  | No change. |  |  |  | Natural England notes the response and that the Applicant considers consultation on the KCIMP elsewhere is sufficient. However, as noted in our original response the draft KCIMP document is produced after the OOEG Terms of reference, timetables, requirements, membership and dispute mechanism. All of which the membership of the OOEG should be consulted upon if they are to be bound by these documents. As currently drafted the membership of this group are going to be informed of the obligations on them with no formal option to respond. We note that Section 1.4.1.3 of the Kittiwake Compensation Plan [REP5-017] states that “Terms of Reference would be agreed between the parties”. We consider this should be secured in the DCO condition. |  | No
I25 | 20 | Part 1 Condition 2 (e) Natural England disagrees with the Applicant being the Chair of the Steering group. We note that an independent Chair has been appointed for the equivalent steering groups established to deliver Hornsea Three’s compensatory measures. Further, as noted above the details of this condition allow the applicant as chair to define the scope of discussions on several key aspects of mitigation, and this could take place without any requirement for discussion or agreement with the other members of the Hornsea 4 OOEG. |  | Whilst the Applicant being Chair has been removed from the DCO condition, it remains in the Kittiwake Compensation Plan [1.4.1.3; REP5-017]. We note that the Applicant does not consider any further change necessary, however Natural England’s position remains unchanged. |  | No change. |  |  |  | We welcome that the Applicant being Chair has been removed from both the DCO condition and associated compensation plan documents. |  | Yes
I26 | 21 | Part 2/3 Condition 3 and 8 If it is conditioned that the GKIMP and GGRIMP must be based on the strategies set out in the gannet and kittiwake compensation plan and the gannet, guillemot and razorbill compensation plans, we advise that a final version of the compensation plans would need to be provided to account for any changes made during the examination process. We note that a commitment is made to this effect in Volume B2, Annex 7.2: Compensation measures for FFC SPA: Offshore Artificial Nesting Roadmap, 4.1.1.1. Condition 3 has a typo in the last line - KGIMP instead of GKIMP. All refences to Natural England should be amended to the relevant Statutory Nature Conservation Body (SNCB), for consistency. |  | The Applicant has confirmed that final versions of the compensation plans will be submitted prior to the final deadline. Natural England will comment on all versions of the compensation plans at appropriate deadlines. Natural England notes the correction to refer to the statutory Nature Conservation Body and welcomes this change. |  | No change. |  |  |  | The Applicant has confirmed that final versions of the compensation plans will be submitted prior to the final deadline. Natural England will comment on all versions of the compensation plans at appropriate deadlines. Natural England notes the correction to refer to the statutory Nature Conservation Body and welcomes this change. |  | Yes
I27 | 22 | Part 2 Condition 3(c) Natural England is concerned with the significant reduction in lead in times proposed by the Applicant compared to those agreed for Hornsea 3. We further highlight that the Applicant defines the breeding season as running from 1 April- 31 August in each year. This is inconsistent with the breeding season accepted for Hornsea Three, which was defined as 1 March – 30 September. As with the reduced lead in time, the Applicant must provide evidence to justify this reduced breeding season. Furthermore, we consider that the compensation needs to be delivering and not just implemented prior to impact. Noting the wording for adaptive management at 3 (f) does not capture changes to timelines for the measures, or to the development should the monitoring highlight the measures are not delivering the required compensation. |  | Natural England welcomes the commitment to an increased lead in time to three full breeding seasons prior to operation, however as kittiwake do not breed until they are 4+ years old breeding recruits will not enter the biogeographic population until that point. Justification is needed on the deviation from 4 breeding seasons consented for Hornsea Project Three, Norfolk Boreas and Norfolk Vanguard, demonstrating that the required colony size/growth is achievable prior to wind farm operation for the reduced lead in time. We note that further information on this point was submitted at Deadline 5. We will provide further comment at Deadline 6. |  | No change. |  |  |  | Natural England welcomes the commitment to an increased lead in time to three full breeding seasons prior to operation, however as kittiwake do not breed until they are 4+ years old breeding recruits will not enter the biogeographic population until that point. We note the Applicant has also suggested that a timeframe might not need securing at all. Justification is needed on the deviation from 4 breeding seasons consented for Hornsea Project Three, Norfolk Boreas and Norfolk Vanguard, demonstrating that the required colony size/growth is achievable prior to wind farm operation for the reduced lead in time. |  | No
I28 | 23 | Part 2 Condition 3(d) We consider this should include monitoring and reporting on the effectiveness of the measures, as has been included for the guillemot and razorbill measures (8(a)(iv)). |  | We note that in the updated DCO this now relates to Part 2 Condition 1(e). Natural England welcomes that the Applicant has updated the condition to include a requirement to monitor. However, the new requirement does not include a requirement to report the results of the monitoring and the effectiveness of the compensation for either measure. |  | The Applicant has requested further clarification on this comment. An earlier version (Deadline 1) of this condition read as ‘the KIMP must include proposals for monitoring and reporting on the effectiveness of the measures, including x,y,z’. In more recent versions of the DCO the condition reads as ‘the KIMP must include details for the proposed ongoing monitoring of the measure including x,y,z’. Natural England request that ‘and reporting on the effectiveness of the measures’ is reinstated in the condition. |  |  |  | Natural England maintains its position. |  | No
I29 | 24, 30 | Part 2 Condition 3(e); Part 3 Condition 8 (a)(v) and (b)(iv) This condition should not just require a reporting of the consultation. It should require the applicant to detail how the consultation responses have been considered and give information explaining why any recommendations or advice has not been included. |  | We note that in the updated DCO this now relates to Part 2 Condition 1(f), Part 6 Condition 1(a)(x) and (b)(iv). No change. |  | No change. |  |  |  | We note that in the updated DCO this now relates to Part 2 Condition 1(f), Part 6 Condition 1(a)(x) and (b)(iv). No change. |  | No
I30 | 25, 29 | Part 2 Condition 3 (f); Part 3 Condition 8 (a)(vi) and (b)(v) As per point raised above on condition 3; captured within any adaptive measures should be any changes to timescales for both the project and for the compensation proposals. |  | We note that in the updated DCO this now relates to Part 2 Condition 1(g), Part 6 Condition 1(a)(xi) and (b)(v). The Applicant has requested clarification on this query. Natural England notes that the current drafting requires the applicant to submit any adaptive measures required should the monitoring highlight the compensation measures are not providing compensation. We consider that, should the compensation be found to be not or only partially functioning, a consideration needs to be provided on what the implications of this failure are for the timeline of providing fully functioning compensation and what this may mean for the feature of the site. Natural England is happy to engage further on this issue to ensure clarity. |  | The Applicant has requested further clarification on this comment. The current condition reads that the KIMP must include ‘details of any adaptive management measures, with details of the factors used to trigger any such measures’. The condition therefore just confirms that adaptive management measures need to be presented. We consider that adaptive management measures should be presented with the information needed to consider them, such as what knock on effects they may have on the timescales of the compensation delivery. Also, as implementation of adaptive management means the compensation is not performing as expected, what the impact might be from the failure on the designated feature being compensated for. Natural England would therefore like this condition to be expanded to include consideration of the implications of implementing adaptive management measures, such as on the timeframe for successfully delivering compensation. |  |  |  | The Applicant has requested further clarification on this comment. The current condition reads that the KIMP must include ‘details of any adaptive management measures, with details of the factors used to trigger any such measures’. The condition therefore just confirms that adaptive management measures need to be presented. We consider that adaptive management measures should be presented with the information needed to consider them, such as what knock on effects they may have on the timescales of the compensation delivery. Also, as implementation of adaptive management means the compensation is not performing as expected, what the impact might be from the failure on the designated feature being compensated for. Natural England would therefore like this condition to be expanded to include consideration of the implications of implementing adaptive management measures, such as on the timeframe for successfully delivering compensation. |  | No
I31 | 26 | Part 2 Condition 3(i) This condition says it links to 9 (b), but there is no 9 (b). We assume this refers to 8 (b), but it should be corrected and or clarified. |  | Natural England notes this has been corrected. |  | The |  |  |  | Natural England notes this has been corrected. |  | Yes
I32 | 27, 31 | Part 2 Condition 3(g); Part 3 Condition 8 (a)(vii) and (b)(vi) The reporting here should require the provision of this report to all members of the H4 OOEG. Or to the relevant statutory nature conservation body as a minimum. |  | We note that in the updated DCO this now relates to Part 2 Condition 1(h), Part 6 Condition 1(a)(xii) and (b)(vi). No change. |  | No change. |  |  |  | We note that in the updated DCO this now relates to Part 2 Condition 1(h), Part 6 Condition 1(a)(xii) and (b)(vi). No change. |  | No
I33 | 28 | Part 3 Condition 8(a)(iii) As with the lead in times for artificial nest structures, we are concerned that implementation of predator eradication and/or control two years prior to operation of the wind farm does not give sufficient time for the measure to be delivering prior to impact. |  | We note that in the updated DCO this now relates to Part 6 Condition 1(a)(iii) and (b)(ii). We note the Applicant has indicated they will work towards implementation and delivery four full breeding seasons prior to works. However, we also note no proposed change of wording to secure this. |  | No change. |  |  |  | We note that in the updated DCO this now relates to Part 6 Condition 1(a)(iii) and (b)(ii). We note the Applicant has indicated they will work towards implementation and delivery four full breeding seasons prior to works. However, we also note no proposed change of wording to secure this. |  | No
I34 | 32 | Part 4 Condition 12 The single condition for Fish Habitat Enhancement lacks the details as per the other compensatory measures. Key elements such as location, extent, timing, adaptive management, monitoring, reporting etc are not detailed to be included. This seems insufficient should this be required as part of compensatory measures. |  | The Applicant has suggested this wording may be updated as the discussions on compensation progress. Natural England acknowledges that less detail will be required of a resilience measure compared to a compensatory measure, however it would be welcomed if known parameters (e.g. extent) could be committed to in the final DCO. We will consider all changes as they are made. |  | No change. |  |  |  | The Applicant has suggested this wording may be updated as the discussions on compensation progress. Natural England acknowledges that less detail will be required of a resilience measure compared to a compensatory measure, however it would be welcomed if known parameters (e.g. extent) could be committed to in the final DCO. We will consider all changes as they are made.
I35 | 33 | We further note that none of the current conditions secure the need to produce the target level of compensation each year (on average). It should be noted the concerns regarding this are compounded further by our concerns on the adaptive management conditions and need to be addressed. |  | The Applicant’s response is noted. However, our concerns remain unchanged. |  | No change. |  |  |  | The Applicant’s response is noted. However, our concerns remain unchanged. |  | No
I36 | 34 |  |  | Part 1 Condition 1(a)(i); Part 6 Condition 1(a)(xiii) & 1(b)(vii) “provision for the option to be exercised at the sole discretion of the undertaker to pay a contribution (in addition to the sum stipulated in Part 3 of this Schedule) to the Marine Recovery Fund wholly or partly in substitution for the onshore compensation measure and/or the offshore compensation measure [predator eradication measures; bycatch eradication measures] or as an adaptive management measure for the purposes of paragraph 1.g. of this Part of this Schedule. The sum of the contribution to be agreed between the undertaker and Defra in consultation with the OOEG and included in the KCIMP [GRCIMP].” This is a new condition which Natural England will provide comment on at Deadline 6, upon consideration of new information submitted by the Applicant at Deadline 5 in relation to strategic compensation. |  | Natural England has provided a response regarding the use of the Marine Recovery Fund elsewhere (C43). However, if the ExA and SoS do approve of their use within this DCO we would recommend that the request to pay in to the fund should be at the discretion of the Applicant. However, the decision on if this is appropriate should be subject to the approval of the SoS with consultation of the relevant SNCB as a minimum, however, we would recommend consultation with the entire steering group. |  |  |  | The Applicant has amended the DCO wording to include approval by the Secretary of State in consultation with the H4 OOEG. The wording 'at the sole discretion of the undertaker' has also been removed. We welcome these changes.