## Title page
THE PLANNING ACT 2008
THE INFRASTRUCTURE PLANNING (EXAMINATION PROCEDURE) RULES
2010
Natural England's Risk and Issues Log - Deadine 1 Submission.
For:
The construction and operation of Five Estuaries Offshore Wind Farm, located approximately 57km from the Essex Coast in the Southern North Sea.
Planning Inspectorate Reference EN010115
03/10/2024

## How to read Risks and Issue Log
Natural England has created this Risk and Issues Log to track progress through the Five Estuaries examination process of risks and issues raised in our Relevant and Written Representations The Risks and Issues Log will be submitted at each deadline and mark issues with a colour from our RAG scale depending on the level of significance of the issue. It should be noted that the colour scale is likely to be different from that used in any Statement of Common Ground provided by The Applicant. The Risk and Issues Log is split into multiple tabs in line with the Appendices of our Relevant Representations submission. A - DCO B - Marine Processes C - Offshore Ornithology D - Ornithological Compensation E - Benthic Ecology F - Benthic Compensation G - Fish Ecology H - Marine Mammals I - Seascape J - Onshore Ecology K - Landscape VIA Each updated submission of the Risk and Issues Log will reflect our position following a review of documents that we have considered in forming our position at each deadline. Any issues added to the log due to additional submissions during Examination (not included in Relevant Reps) are highlighted in Red and then coded according to RAG status.
Purple Note for Examiners and/or competent authority. May relate to DCO/DML
Red Natural England considers that unless these issues are resolved it will have to advise that (in relation to any one of them, and as appropriate) it is not possible to ascertain beyond reasonable scientific doubt that the project will not affect the integrity of an SAC/SPA/Ramsar and/or significantly hinder the conservation objectives of an MCZ and/or damage or destroy the interest features of a SSSI and/or comply fully with the Environmental Impact Assessment requirements.
Addressing these concerns may require the following:
new baseline or survey data; and/or
significant revisions to baseline characterisation and/or impact modelling and/or
significant design changes; and/or
significant mitigation
In addition, Natural England may use this category to highlight where there is a significant risk that an issue will not be sufficiently addressed within the Examination timescales. Consequently, issues that start out as Amber may progress to Red in the latter stages of the examination.
Amber Natural England does not agree with the applicant’s position or approach and consider that this could make a material difference to the outcome of the decision-making process for this project.
Natural England considers that these matters may be resolved through:
provision of additional evidence or justification to support conclusions; and/or
revisions to impact assessment methodology and/or assessment conclusions; and/or
minor to moderate revisions to impact modelling; and/or
well-designed mitigation measures that are adequately secured through the draft DCO/dML and/or
amendments to draft plans
If these issues are not addressed or are unlikely to be resolved by the end of the Examination, then they may become a Red risk as set out above.
Yellow Natural England doesn’t agree with the Applicant’s position or approach. We would ideally have liked this to be addressed prior to the examination but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process and would not expect these matters to be an ongoing focus of the examination. However, we reserve the right to revise our opinion should further evidence be presented.
It should be noted by interested parties that just because these issues/comments are not raised as significant concerns in this instance, it should not be understood or inferred that Natural England would be of the same view in other cases or circumstances.
Once a Risk or Issue has been categorised as yellow, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be greyed out at subsequent deadlines in order to rationalise the risk and issues log.
Green Natural England is in broad agreement with the Applicant’s approach and has no significant outstanding concerns. As above, we reserve the right to revise our opinion should new evidence be presented. Once a Risk or Issue has been categorised as green, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be greyed out at subsequent deadlines in order to rationalise the risk and issues log.

## PADSS
Natural England will provide an update to the PADSS at Deadline 2.

## A - DCO
Point | Point Number(s) from Appendix A [PD2-003] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix A - DCO | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | A1, A11 | The during construction monitoring conditions within the deemed Marine Licences (dML) Schedules 10 and 11 do not secure that piling must cease in the event the monitoring highlights the noise impact is significantly in excess of the predicted impacts assessed, and the potential need for further monitoring.
2 | A2, A14 | The Margate and Long Sands Special Area of Conservation (SAC) Benthic Mitigation Plan is not secured through condition within the transmission dML, Schedule 11. This Plan details key mitigation for the SAC and should be secured through appropriate condition. It is important that the Margate and Long Sands Benthic Mitigation Plan be resubmitted for approval with detailed mitigation based on the final designs and up to date mitigation techniques.
3 | A3, A16 | NE cannot rule out an adverse effect on integrity (AEoI) on the Margate and Long Sands SAC (sandbanks) and the Flamborough and Filey Coast Special Protection Area (SPA) (kittiwake, guillemot, razorbill). Therefore provision for compensation should be included in the draft DCO on a without prejudice basis to provide the Secretary of State (SoS) with detailed and agreed provisions should he determine that compensation is required.
4 | A4 | The requirement for landscaping does not cover all required aspects e.g. survey methods, monitoring requirements and the requirement to maintain/replant. Further we would expect to be consulted on these plans prior to their approval by the relevant local planning authority.
5 | A5 | Requirement 8 (1) does not secure that the Code of Construction Practice (CoCP) must be submitted and approved prior to the commencement of works, nor includes a requirement to consult the relevant SNCB on the CoCP. The requirement should also note the final CoCP must accord with the outline CoCP. Further the requirement refers to sub paragraph (3) of the requirement which does not exist.
6 | A6 | This provision should be amended to state that no pre commencement clearance works should be undertaken until a written LEMP, as relevant to the stage of the works, has been submitted to, and approved by, the Local Planning Authority (LPA) following consultation with the relevant SNCB.
7 | A7 | Consideration should be given as to whether the requirement covering vehicle access and construction plans for the LBBG compensatory works sit better within the compensation schedule. This would ensure that the approval of compensatory works are considered holistically by a single decision maker and reduce the potential for conflicting decisions.
8 | A8 | The requirement securing the need for a Biodiversity Net Gain (BNG) strategy should be amended to require consultation with the relevant SNCB and to monitor, maintain and potentially employ adaptive management measures over thirty years, or for the lifetime of the development.
9 | A9 | The Site Integrity Plan (SIP) condition should require the SIP no sooner than 9 months and no later than 6 months prior to commencement of piling. to ensure the plan is not submitted too early to consider all relevant in combination issues.
10 | A10 | Natural England notes that the monitoring conditions only cover benthic monitoring. Ornithological and Marine Mammal monitoring should also be requirements due to the potential for impact.
11 | A12 | A condition requiring remediation or further mitigation works should monitoring show impacts are greater than predicted should be included within the dMLs. NE are advising this for all relevant dMLs.
12 | A15 | The cable protection condition should be amended to ensure that cable protection within the Margate and Long Sands Special Area of Conservation (SAC) is only deployed during the construction phase.
13 | A17 | All references to Natural England within this schedule should be amended to the SNCB to ensure consistency with the rest of the DCO.
14 | A18 | The condition relating to the Offshore Ornithology Engagement Group should be updated to include provision of terms of reference, a timetable for the preparation and delivery of the LBBG implementation and monitoring plan (LIMP), and a dispute resolution mechanism. These have been included in many compensation schedules for LBBG.
15 | A19 | Natural England notes that there is ongoing work on strategic compensation and would support the inclusion of appropriate provisions to allow use of agreed strategic compensation. However, the condition wording here is insufficient, if that is its purpose. Recommend amending this provision and consideration of how to appropriately implement a provision allowing strategic compensation options.
16 | A20 | The list of requirements to include in the LIMP is lacking in detail when compared to similar provisions used to secure compensation with respect to to see survey methodologies, timetables for the monitoring to be conducted and reports delivered and success criteria, and a detailed mechanism to determine the need for any alternative compensation or adaptive management measures, along with potential further monitoring and maintenance of such measures.
17 | A21 | This requirement ensures that LBBG compensation must be provided three full breeding seasons prior to operation. However, Natural England notes that on other developments a period of four full breeding seasons was deemed appropriate.
18 | A22 | The compensation may be required for longer than the lifetime of the project and therefore the provision should specify that the compensation should be maintained until the SoS approves its decommissioning in consultation with the relevant SNCB.
19 | A23 | Several activities within Appendix A will require a new marine licence, but are recorded as amber, whereas the coding provided within the plan indicates that these should be considered red e.g. foundation replacement. Appendix A should be amended to reflect the appropriate colour marking.
20 | A24 | It would have been useful for the table to have included a reference to the relevant section in the Environmental Statement (ES) to allow appropriate cross referencing.

## B - Marine Processes
Point | Point Number(s) from Appendix B [PD2-004] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix B - Marine Geology, Oceanography and Physical Processes | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | B1/B27 | There is insufficient evidence to support the impact assessment of cable protection on Annex I Sandbanks of Margate and Long Sands Special Area of Conservation (MLS SAC) from disruption of sediment transportation both alone and in-combination.
2 | B2/B11/B20/B25 | The cumulative impacts to MLS SAC require further consideration. In particular disruption from multiple cable crossings of the 2 VE cables with other plans and projects. And volumetric, extent and distribution changes when considered in-combination with other plans or projects. Noting that existing anthropogenic activities occurring with the SAC have already caused a significant alteration of the sandbanks and are hindering the conservation objectives for the designated site.
3 | B3 | The Maximum Design Scenario (MDS)/Worst-Case Scenario (WCS) for impacts to SPA and SAC supporting habitat, protected habitats and significant bedforms within the arrays has not been sufficiently considered. All aspects of construction such as drill arisings etc., impacts to sandbanks/sandwaves, seabed morphology and prey availability should be considered in more detail.
4 | B4/B9 | There is uncertainty regarding the MDS/WCS for volume of sediment disturbed due to cable trenching. Further evidence is required.
5 | B6 | From the coastal perspective, Scenario 3 (Five Estuaries completes works then North Falls completes works at a later time) should be used as the WCS.
6 | B7/B12/B22 | Further information is required to inform landfall MDS including (but not exclusively) anticipated length and location of trenching at landfall. Similarly, any sheet piling and/or an anchored or spud barge for Horizontal directional drilling works.
7 | B8 | Should a coordinated offshore connection with North Falls and Sea Link become a more mature option during examination, this will need to be assessed. Otherwise consideration should be given to how provision for this option at a later date can be included within the DCO to minimise the risk of a material change.
8 | B10 | WCS for potential morphological impacts to sandbanks and designated areas of seabed (e.g. MLS SAC) during construction should also consider boulder clearance, UXO clearance and pre-lay grapnel run activities as well as dredging.
9 | B13 | Are the number of array and export cable repairs/replacements over the project lifetime and total impact amounts in Table 1.31 realistic?
10 | B14 | The MDS for Array Area drill arising dimensions and distribution of grain sizes/sediment type should be provided and assessed accordingly.
11 | B15 | The seabed mobility and erosion potential should be assessed in the EIA.
12 | B16 | SEASTATES hindcast slightly overpredicts some of the significant wave height peaks, but the modelled peak wave period appears to underpredict measured peak wave period for approx. 25% of the time series shown.
13 | B17/B18 | Impacts to seabed morphology (i.e. sandwaves) related to changes to the tidal regime due to the presence of Wind Turbine Generator (WTG) and Offshore Platform (OSP) foundation structures should be assessed and significance determined.
14 | B19 | Further detail is required to inform the impact assessment for potential changes to Suspended Sediment Concentrations (SSCs), bed levels, and sediment type arising from construction related activities within the Array Areas.
15 | B21 | The present EIA may not be sufficient to determine decommissioning impacts at the end of the OWF lifespan.
16 | B23 | There remains a risk (e.g. climate change impacts) that buried infrastructure within the intertial may become exposed during the lifetime of the project.
17 | B24 | Given the large volumes of sediment that could be removed through levelling/bed preparation and detail included within the EIA, sufficient uncertainty remains regarding the recovery potential of sandwaves (and other similar bedforms) in the Array Areas.
18 | B26 | There are insufficient details regarding the location of the nearshore subtidal laydown areas and their potential impact on seabed morphology to agree with the effect significance conclusion. Furthermore, we do not agree that the coastline is of medium sensitivity/importance.

## C - Offshore Ornithology
Point | Point Number(s) from Appendix C [PD2-005] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix C - Offshore Ornithology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | C1, C30 | The estimated mortalities and compensation quantum derived for the derogation case for the Alde-Ore Estuary Special Protection Area (AOE SPA) lesser black-backed gull (LBBG) population, using the Natural England preferred approach, appear incorrect. If necessary an updated assessment (including updated PVA) should be conducted.
2 | C2, C13 | PVAs were run without a burn-in period of 5 years as per Natural England best practice advice.
3 | C3, C24 | An assessment of impacts on the Farnes SPA Razorbill population for the project alone during the Operations and Maintenance (O&M) phase and in-combination during all phases of the development should be provided.
4 | C4 | Other than for the AOE SPA LBBG population, the Applicant has apportioned adults subject to Habitats Regulations Assessment (HRA) during the breeding season using the generic data presented in Appendix A of Furness (2015), rather than using site-specific data to establish the number of adult- or adult-type birds present. Natural England do not accept the Applicant’s approach to apportioning adults based on theoretical generalised stable age structures.
5 | C5, C32 | The Applicant has applied their preferred displacement (50%) and mortality (1%) rates to the guillemot and razorbill populations at risk at each offshore wind farm (OWF) project included in the in-combination assessment for the Flamborough & Filey Coast Special Protection Area (FFC SPA). This departing from Natural England advice and the in-combination impact estimates used by the Secretary of State (SoS) for recently consented OWFs. We advise the project should simply add the VE project alone impact (at 70% displacement and 2% mortality) to the total in-combination impact agreed in the Sheringham and Dudgeon Extensions Project OWF (SADEP) Examination.
6 | C6, C31 | In the PVA for guillemot and razorbill, Natural England welcome the presentation of results for a range of project alone and project in-combination displacement and mortality scenarios, but we would like to see 2% rather than 10% mortality at 70% displacement as the worst-case scenario for these species.
7 | C9 | To mitigate the risk to red-throated diver (RTD), Natural England strongly recommends all vessel activity within the SPA +2km buffer be undertaken outside the seasonal restricted period during the Construction and Decommissioning (C&D) of the export cable (EC), and follow Natural England best practice guidelines on vessel movements during all other phases of the development for both the EC and array.
8 | C11 | For lesser black-backed gull the PVA analysis was run and presented for both VE and Natural England preferred scenarios, i.e. either using generic adult proportion data and discounting sabbaticals or using site-specific adult proportions and including sabbaticals, respectively. The Natural England preferred scenarios should be used as the basis of the impact assessment.
9 | C14 | The Cumulative Effects Assessment (CEA) considers an arbitrary 500km Zone of Influence (ZOI) to scope in other projects for consideration. For offshore ornithology, foraging range is an appropriate tool to screen for impacts to breeding birds, but not outside the breeding season. The approach for non-breeding birds is not given. However, all relevant wind-farms projects have been screened into the CEA.
10 | C15 | The values used in the in-combination assessment for other English North Sea projects entering the NSIP process in 2024 (Outer Dowsing, Dogger Bank South West and South East, North Falls) are likely to be subject to change through their respective Examinations. The Applicant should work collaboratively with these projects to share updated values in a streamlined way.
11 | C16 | CRM has been undertaken using the deterministic Band model. Uncertainty in flight density has been incorporated by estimating collisions using mean, Upper Confidence Interval (UCI) & Lower Confidence Interval (LCI) density estimates. However, other model parameters have not been varied e.g. flight height, except in the stochastic modelling that was undertaken for those species the Applicant considered at greater risk of collision.
12 | C17 | EIA CEA impacts on baseline mortality >1% are not modelled using PVA but considered against other OWF PVAs carried out in the southern North Sea e.g. Norfolk Boreas, East Anglia 3 and Hornsea 4. Cumulative impacts on baseline mortality >1% were found for gannet, great black-backed gull, lesser black-backed gull, herring gull, kittiwake, guillemot, and razorbill during the O&M phase as well as on red-throated diver during the C&D and O&M phases. However, the Applicant only reports comparative estimates of counter-factual population size or reduction in population size for gannet, kittiwake and LBBG. NE therefore recommends the cumulative impacts are assessed further using the PVA tool for these species.
13 | C18 | The impacts on red-throated diver (RTD) during construction of the EC are stated to be 15 birds per annum (at 100% displacement and 10% mortality) but the impacts from both the array and EC construction is stated as less at 14 birds. The combined impacts must be more or the same but not less than stated for one phase of the work.
14 | C19 | The draft DCO/dML includes a seasonal restriction, ‘Export cable installation will not be carried out within the Outer Thames Estuary SPA between 1st November to 31st March inclusive to mitigate disturbance impacts on red throated diver’. We welcome this but advice the seasonal restriction should be applied to the OTE SPA and a 2km buffer.
15 | C20 | Natural England has already identified significant adverse impacts at the EIA scale to gannet, kittiwake, great black-backed gull, guillemot, razorbill and red-throated diver from OWF in the North Sea, irrespective of whether the Five Estuaries is included in the cumulative totals. The project will therefore be making an additional contribution to those totals. We advise the Applicant review the EIA section of Natural England’s final offshore ornithology advice into the SADEP Examination for further information (REP8-102), and make updates to the CEA as necessary.
16 | C21 | The sensitivity of red-throated divers to disturbance effects from offshore developments are described in section 4.10.17 but using examples of research that do not illustrate the full scale of the impact, the Applicant’s own review of RTD sensitivity presented in doc. 6.2.4 secs. 4.11.25-4.11.34.
17 | C22 | The Applicant downplays the impact on auks caused by OWF induced displacement. There is an established evidence base in support of guillemot displacement from OWFs. While displacement effects on auks remain poorly understood and may prove to be variable, Natural England note a recent study has highlighted the potential for displacement to occur over much greater distances (up to ~20km) than are typically assessed or considered by baseline characterisation surveys (Peschko et al. 2024).
18 | C23 | Potential transboundary impacts on Alderney’s Ramsar site and the Cote de Granit Rose-Sept Isles have been omitted from the screening process, yet both contain important seabird populations, notably gannet.
19 | C25 | Impacts predicted during the C&D phase are not presented in matrices for guillemot (GU) and razorbill (RA) at the Farnes SPA, and for gannet (GX), GU and RA at the FFC SPA. As noted above, impacts predicted during the O&M phase are not presented in a matrix for RA at the Farnes SPA.
20 | C27 | Natural England does not agree with the Applicant’s process for adult apportioning subject to HRA, notably the breeding population of gannets at the FFC SPA.
21 | C28 | Natural England acknowledges that sabbaticals are an important consideration for improving impact estimates and represent a knowledge gap. However, at present we do not believe that simply removing them from assessments during apportioning is appropriate.
22 | C29 | Natural England are not persuaded that a sabbatical rate of 35% can be considered either relevant or precautionary, therefore the Applicant should cite the research used so it can be appraised.
23 | C33 | In the CRM for migratory waterbirds all species assessed were assumed to fly at rotor height at a precautionary 100% of the time except dark-bellied Brent goose. Brent geese were assessed instead at the less precautionary rate of 50% but a clear evidence-based reason was not given.
24 | C34 | In the RTD assessment, the Furness (2015) is migration free season used (i.e. impacts are only estimated for December and January), rather than October to May.
25 | C36 | The Applicant notes that some of the operating OWF were not built to full capacity and that their predicted impacts would be less in reality than stated, thereby providing some ‘headroom’ in the in-combination assessment. At present Natural England do not consider it appropriate to reduce impact estimates by considering as-built parameters unless those parameters are legally secured.
26 | C37 | The Applicant’s review points out that guillemot displacement rates may be reduced during the breeding bio-season by ~20% compared with the non-breeding bioseason. While Natural England do not disagree that auk displacement rates appear to be reduced for breeding birds in the breeding season, we note that the Applicant is only assessing displacement of auks in the non-breeding season.
27 | C38 | The RIAA reports that 40% of lesser black-backed gull were apportioned to the AOE SPA yet the Apportioning Note presents two different figures in the text e.g. sec. 2.2.23, 40%, and Table 2.5, 35.5%. This should be clarified.
28 | C39 | The Applicant states that for auk species “Potential LSE for migratory birds has been ruled out as they do not forage or roost in the array area and only transit through the area during migration” but does not evidence this statement.
29 | C40 | Post-consent monitoring is focused entirely on compensatory measures. Post-consent monitoring of the OWF could help clarify the key risks such as those posed to LBBG from collision, but no monitoring of this sort is proposed.
30 | C41 | We are unable to agree the effects of the project on some species subject to HRA. Clarification is required on the scale of impacts on the guillemot and razorbill populations breeding at the Farnes and FFC SPAs, the kittiwake and gannet populations at the FFC SPA and the lesser black-backed gull population at the AOE SPA. Until this is resolved we are unable to agree the scale of compensation required to off-set the losses predicted for these species.

## D - Ornithology Compensation
Point | Point Number(s) from Appendix D [PD2-006] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix D - Ornithology Compensation | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | D2 | We are broadly supportive of the proposal to provide compensation for impacts on guillemot and razorbill through reduction of disturbance at small colonies in south-west England, but highlight it will require significant amounts of on-site monitoring and engagement with local experts to establish a baseline for the current level of disturbance and potential impact on colony productivity at any given site, and to establish what measures might effectively mitigate any disturbance occurring.
2 | D3, D5 | Natural England consider the disturbance reduction measure to be technically feasible. However, the Applicant has not yet demonstrated whether sites can be easily observed or monitored in sufficient detail to establish annual counts and productivity estimates which can serve as a baseline for management interventions. Communication with landowners and stakeholders is still ongoing and it remains unclear how many sites will be able to participate.
3 | D4 | Impact levels are not yet agreed but are expected to result in a modest contribution to the in-combination total. For previous auk compensation cases Natural England has advised the use of 70% displacement and 2% mortality for establishing requirements, and advice these values be used for scaling requirements.
4 | D7 | Candidate locations have been identified but are not yet secured, though negotiations are under way. Without secured agreement with the relevant landowners and stakeholder willingness to participate, there remains the risk that the project will not deliver.
5 | D8, D9 | Monitoring will be required for all stages of the proposed management programme to identify trends accurately. Stakeholder engagement will also need to be upheld throughout the project to ensure all new participants are aware of the issues. The level of monitoring needed to identify suitable set-back distances and gather as much data as possible on nest failure will require suitably skilled observer(s).
6 | D10 | The proposal has potential as a sole measure given the likely scale of impact. The proposal would also benefit from the Applicant working alongside recreational stakeholders and the local authority . We also recommend, as a minimum, using signage in conjunction with public engagement to help deliver an effective code of conduct. We note and support the option of a collaborative approach between multiple developers.
7 | D11 | Adaptive management will not be adopted should other pressures such as impacts associated with climate change (e.g. extreme weather events) negatively impact the compensation delivery. However, adaptive management could be crucial to help restore and build resilience in the local auk population in the face of change.
8 | D12,D13, D17, D21, D22 | There is uncertainty regarding collaboration and agreement between VE and Dogger Bank South (DBS) OWF with regards to sharing the ANS. Further uncertainty exists as to whether sufficient numbers of birds (a) will occupy the RWE ANS and (b) depending on how the measure is allocated, whether sufficient birds can be allocated to VE. To safeguard delivery of the compensation, the alternative option to support Defra’s Marine Recovery Fund for an offshore ANS should be retained in the meantime.
9 | D15 | Natural England advise that the compensation requirement should be scaled up to the 95% UCI impact value and not be based on the central impact value.
10 | D25.0 | Adequate evidence has been provided to demonstrate technical feasibility for VE02, although without further data gathering and impact assessment as regards the impacts of the predator fence, we are not in a position to advise that impacts on the Orford Ness – Shingle Street SAC and Alde-Ore Estuary Ramsar site and SSSI will be adequately mitigated.
11 | D25.5 | As regards OTB, techniques for predator control and vegetation management are well established. However, OTB is a challenging site to access and sits in an area of high environmental sensitivity (The Wash SPA, SSSI and the Wash and North Norfolk Coast SAC). An appropriate access methodology and schedule for management has not been presented, and we consider an outline approach reflecting the above challenges should be submitted into the Examination in due course.
12 | D26 | The compensation level has not been agreed yet as per our Relevant Representations (Appendix C). Natural England is therefore unable to agree the number of additional breeding pairs required to achieve compensation. Furthermore, it is Natural England’s advice that for compensation the requirement should be scaled up to the 95% UCI and not the central impact value.
13 | D27 | Once the scale of impacts on the LBBG AOE SPA population have been agreed, the adequacy of the proposed level of compensation can be assessed. Proposals presented so far suggest this is likely to be the case should both the AOE SPA and OTB measures are progressed, once the number of predicted annual losses have been finalised and compensation is delivered at a ratio of 3:1.
14 | D28.0, D32 | The proposal to protect a site within the AOE SPA using predator proof fence will rely on the birds finding and occupying the site. There is a risk that the birds may be reluctant to nest on the ground such that the site remains unused or only occupied several years after the fence has been erected. The proposal may, therefore, rely heavily on the Outer Trial Bank site to deliver the additional compensation for the interim losses (at least until the fenced site becomes active). As such, Natural England recommends that both proposals are undertaken to reduce the risk – providing resilience should one site fail to deliver.
15 | D28.5 | We advise the fence be erected 4 years in advance of the operational phase to extend the lead in time as much as possible – noting this schedule was required and achieved by the Norfolk projects.
16 | D29 | As negotiations with landowners at both sites remain on-going, there is currently uncertainty whether or not either site can be secured for the lifetime of the project. Within the AOE SPA, the onshore ecology may also affect the location of the proposed predator-proof fencing.
17 | D30.0 | For the predator-proof fencing proposal in the AOE SPA, no schedule for fence maintenance and checks has been provided or details about how this will be done and by whom. Fence maintenance will be crucial to prevent predator incursions and a key component of on-going management throughout the year. Plans will also need to be in place to address fence breaches so these can be resolved quickly.
18 | D30.5 | For the proposal at Outer Trial Bank, workable plans for monitoring and biosecurity will need to be in place.

## E - Benthic Ecology
Point | Point Number(s) from Appendix E [PD2-007] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix E - Benthic and Intertidal Ecology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | E1/E7 | Further quantification of design parameters and impacts are required to address uncertainties with the Maximum Design Scenario (MDS) for cable protection within Margate and Long Sands Special Area of Conservation (MLS SAC) and inform compensatory requirements
2 | E2/E18 | Further assessment and justification re. pressures/impacts on supporting benthic habitats for Special Protection Area (SPA) features is required. In particular the Outer Thames Estuary SPA (OTE SPA) Red-throated diver populations which are present in the project red line boundary and vessel transit route from several local ports which may locate the projects O&M facility.
3 | E3/E6/E7/E24/E27 | The application documents, including the Report to Inform Appropriate Assessment (RIAA) provide contradictory information relating to the likely requirement for ‘additional’ scour and/or cable protection over and above that stipulated within the maximum design.
4 | E4/E20 | Natural England does not agree with the Applicant’s conclusion of No AEoI in relation to MLS SAC which has been designated for Annex I Sandbanks.
5 | E5/E37 | Mitigation measures for the potential presence of Section 41 Natural Environment and Rural Communities (NERC) Act 2006 Habitats are not sufficiently included. Including A4.231 Piddocks with a sparse associated fauna in sublittoral very soft chalk or clay.
6 | E8 | Further detail and updated assessments are required to determine if the WCS is realistic.
7 | E9/E11/E12 | Parameters to determine the dredge disposal criteria and/or mitigation for EIA and HRA issues, other than within the same sediment type have not been included.
8 | E10 | The evidence to support VE disposal activities includes those permitted and assessed in 2008 which can no longer be relied upon.
9 | E13/E30 | Further mitigation measures should be adopted to differentiate between areas inside and outside of designated sites unless a precautionary approach is taken to all installation and operation activities within the assessment.
10 | E17 | Natural England is concerned that there is a risk of impacting potential Annex I reef features located within MLS SAC and as a NERC (2006) Section 41 Priority Habitats.
11 | E19 | The Applicant has ruled out the option to adopt High Voltage Direct Current (HVDC) within the Export Cable Corridor (ECC) to mitigate impacts on sandbank features, which would reduce the number of cables
12 | E23 | The updated Renewable Energy National Policy Statement has not been taken into consideration and neither has the updated Defra Policy to support Best Practice Guidance for benthic compensation in MPAs
13 | E25 | Further details on Operation and Maintenance activities preferably included within an outline plan are required to inform the RIAA
14 | E26 | Within the RIAA there is limited linkage to the conservation objectives for MLS SAC.
15 | E28 | Benthic compensatory requirements for other projects should consider all projects including Dudgeon and Sheringham Extension Projects OWFs which have impacts similar to VE.
16 | E29 | The in-combinationTIERs do not align with best practice guidance and therefore do on take account of ongoing impacts from some projects.
17 | E31 | The following need further consideration in the table: UXO clearance impacts along cable route on benthic receptors. Potential need for cable protection at the HDD exit pits. Details of each cable repair rather than as a collective.
18 | E32 | MLS SAC sandbank feature extends beyond the site boundary and therefore impacts from outside the site might have indirect impacts to the SAC.
19 | E33 | The RIAA does not fully consider the sediment deposition from sandwave levelling to ensure that deposition is in the same sediment type.
20 | E34 | We disagree with RIAA where impacts are argued as small.
21 | E35/36 | It is not clear what ‘benchmarks’ the Applicant is referring to reached conclusions of no AEoI, or what evidence is being used to support the conclusions of insignificant effects. But any placement of cable protection and associated changes to physical processes and benthic communities could constitute a lasting impact over the lifetime of the project which is potentially irreversible. Natural England therefore disagrees with the Applicants conclusion and consider that an AEoI cannot be ruled out based on the evidence presented.
22 | E38 | The EIA fails to describe how elevation of Sabellaria spinulosa tube structures has been measured in order to inform the ‘reefiness’ assessment.
23 | E39 | The priority Habitats as listed under Section 41 of the NERC Act 2006 have not been appropriately considered within the EIA, or the Offshore In-Principle Monitoring Plan. This is particularly relevant for issue E37 regarding impact to piddocks, peat and clay.

## F - Benthic Compensation
Point | Point Number(s) from Appendix F [PD2-008] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix F - Benthic Compensation | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | F3/F13/F33 | The presented Worse Case Scenario (WCS) of lasting habitat loss/change of Annex I Sandbanks within Margate and Long Sands (MLS) SAC is not agreed. And is relevant to all compensation measures
2 | F3 | Due to potential uncertainties with the delivery mechanisms for strategic benthic compensation and timeframes for successful delivery of the measure, further discussions (outside of individual project examinations) are required to determine individual project contributions and compensatory ratios |  | We will provide no further comment in examination and all queries should be addressed to DEFRA.
3 | F4 | There are outstanding concerns in relation to the outcomes of the Impact Assessment and evidence used to support conclusions on scale and significance of potential impacts from cable installation activities and the placement of cable protection from Five Estuaries. Until these issues are resolved the scale and extent of the compensation measures required are not agreed. And this is relevant to all compensation measures
4 | F4 | As set out in the R4 plan level compensation document, the designation of a new site or existing site extension will be led on by a team in DEFRA in collaboration with interested parties therefore delivery mechanisms, costs and timeframes presented by the Applicant cannot and should not be relied upon |  | We will provide no further comment in examination and all queries should be addressed to DEFRA.
5 | F5 | There are likely to be time lags between impact occurring and strategic compensation achieving the desired outcomes. In this scenario, the project contribution to the measure should be such that it ensures an overall environmental net positive outcome for the impacted feature over the lifetime of the project.
6 | F6,F7,F8 | For strategic compensation the location, long term implementation and success criteria/ability to prove additionality will be determined by DEFRA, in consultation with Natural England and JNCC. This is still under consideration and nothing has been agreed and/or secured.
7 | F10 | Limited geotechnical and geophysical survey data has been presented with the Cable Burial Risk Assessment [APP-238] and the Cable Specification and Installation Plan [APP- 239] to have confidence that the cables can be buried to optimum cable burial depth. In addition, there is limited consideration of the highly dynamic sediment transport/marine processes within MLS SAC which may have implications for cable burial over the lifetime of the project. Therefore, the WCS presented for cable protection within MLS SAC may not be realistic.
8 | F11 | Under removal of redundant infrastructure Five Estuaries' focus is on the removal of disused telecommunications ‘telecom’ cables. But there is no evidence that redundant telecoms cables are causing a significant impact on the Annex I Sandbank feature of the MLS SAC or other benthic designated sites. Unless further supportive detailed evidence is provided, Natural England does not consider their removal to constitute suitable compensation as a sole benthic compensation measure.
9 | F12/F18/F20 | If further evidence is presented in support of telecoms removal as a compensation measure, and this is to be progressed, then commitments with the cable owners will need to be secured.
10 | F16 | The location of any redundant telecom cables to be removed has not been presented in detail and/or agreed with the SNCBs
11 | F17 | In order to provide the Secretary of State with the necessary comfort that removal of redundant infrastructure as a compensation measure is sufficiently progressed during the consenting phase, this should be set out in more detail. However, it is anticipated that as the examination progresses that this measure is either more thoroughly progressed or removed as an option if not.
12 | F19 | While removal of redundant infrastructure could be progressed as a sole measure it remains unclear if there are sufficient surface laid/exposed telecom cables on Annex I sandbanks to fully mitigate the potential project impacts. However, this proposal could be progressed as part of a package if not.
13 | F21 | Percentage buyout of aggregate licence(s) as a compensation measure for Annex I sandbank would reduce existing pressures on Annex I sandbanks. If this is progressed further detail should be provided of any agreements with Aggregates industry where this measure has potential.
14 | F22 | Whilst technically feasible as there are active Aggregate licences within the National Site Network which interact with Annex I sandbank, there is currently no certainty that this measure can be secured
15 | F24 | The location, long term implementation and success criteria/ability to prove additionality of percentage removal of aggregates extraction has not been presented in detail and/or agreed with the SNCBs
16 | F25,F26 | It is unclear if removal of aggregates can be delivered prior to the impacts occurring.
17 | F27 | In order to provide the Secretary of State with the necessary comfort that percentage removal of aggregates extraction as a compensation measure is sufficiently progressed during the consenting phase, this should be set out in more detail. It is anticipated that as the examination progresses that this measure is either more thoroughly progressed or removed as an option if not.
18 | F29 | While the buyout of Aggregate licences could be progressed, it remains unclear if there are any options open to the Applicant to deliver this measure either as a sole measure or as part of a package.
19 | F31 | Seagrass restoration is a lower preference measure compared to those supporting the same ecological function of the habitat being compensated for. Subtidal seagrass has not been found within MLS SAC.
20 | F32 | There have been no long term successes (even on a small scale) with seagrass restoration in the UK. Seagrass restoration is included as a potential measure only where it would be a minor part of a wider package in terms of the required compensation. Given the intention to compensate for Annex I sandbank habitat, which is, by definition, a subtidal habitat, seagrass restoration for the purpose of compensation shall be limited to subtidal seagrass. The measure could supplement other measures, or potentially as an adaptive management response.
21 | F35 | It is unclear if seagrass restoration can be delivered prior to the impacts occurring.
22 | F36 | The location, long term implementation and success criteria/ability to prove additionality of seagrass restoration has not been presented in detail and/or agreed with the SNCBs.
23 | F37-F40 | In order to provide the Secretary of State with the necessary comfort that seagrass restoration as a compensation measure is sufficiently progressed during the consenting phase, this should be set out in more detail. It is anticipated that as the examination progresses that this measure is either more thoroughly progressed addressing all information gaps or removed as an option if not
24 | F41 | More substantive consideration of ‘Alternatives’ is required to ensure that the Alternatives Test can be met.
25 | F42 | There needs to be more transparency over the project lifetime impacts and not just a focus on the Application and Examination.
26 | F43 | The conservation advice package for Margate and Long Sands SAC is in the process of being updated. With draft updates being published in Autumn 2024 and finalisation in March 2025. Within these updates there is relevant context on existing impacts to the site to help inform the in-combination assessments.
27 | F44 | It is unclear how the Applicant has determined that sandbank recovery will occur within a few months following sandwave levelling.
28 | F45 | Further geotechnical data is required pre-determination to inform the likelihood of cables being buried and thus the need for cable protection and therefore compensation.
29 | F46 | Cable Protection: Natural England advises across all documents that further detail is required on cable protection parameters during installation and project lifetime, before we can have any certainty on the proposed 5,400m2
30 | F47 | It is not agreed that compensation discussions should be deferred until it is determined post installation that it is definitely required
31 | F48 | Further consideration should be given to the implementation of mitigation hierarchy to reduce impacts as much as possible
32 | F49 | Information taken from other projects examination document often refers to mitigation not necessarily compensation. And does not align with final positions and therefore should not be relied upon. |  | We will not be providing further comments on this during Examination.
33 | F50 | APP-048 the Outline BIMP is presented as a skeleton document of what will be included post consent. Therefore, we are unable to provide comment at this time on its content. In addition it is not clear if the progression of a BIMP is the most appropriate approach if Strategic Compensation is taken forward.

## G - Fish Ecology
Point | Point Number(s) from Appendix G [PD2-009] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix G - Fish and Shellfish Ecology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | G1 | It is not clear whether conclusions of magnitude are based on the modelling of fish as either stationary or fleeing receptors.
2 | G2 | We welcome the implementation of additional mitigation measures, provided that these mitigations are secured through appropriate conditions on any consent issued. However, we defer to Cefas in regard to the appropriateness of these mitigation measures and associated buffers.
3 | G3 | In relation to spawning herring, we do not agree that the sensitivity of spawning herring to noise impacts would be medium during the construction phase of the Project.
4 | G4 | The potential for mortality does not equate to a low magnitude of impact, especially with regard to the current condition of the fishery.
5 | G6 | A seasonal piling restriction should be in place during the peak Downs herring spawning period. We defer to Cefas regarding the appropriateness of the proposed timing of the restriction and buffer required.
6 | G7 | We defer to Cefas on the matter of the suitability of the sediment disposal restriction as mitigation for the impacts of high levels of suspended sediment concentration (SSC) on herring (and sandeel).

## H - Marine Mammals
Point | Point Number(s) from Appendix H [PD2-010] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix H - Marine Mammal Ecology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | H1 | Population modelling should be conducted, for example Interim Population Consequences of Disturbance (iPCoD), to understand the impacts of the project alone and in-combination with other plans and projects at a population level and consequently inform the conclusions of the EIA and HRA.
2 | H2 | The Applicant has not committed to using Noise Abatement Systems (NAS) at this stage. The Applicant should commit to using noise abatement as mitigation now, should driven or part-driven piles be used during construction.
3 | H3 | The current approach to implementing Site Integrity Plans (SIPs) for piling impacts to the Southern North Sea SAC from offshore wind development does not allow sufficient time for mitigation methods, such as NAS, to be procured by the Applicant prior to construction, should they be required, therefore increasing the risk that an Adverse Effect on Site Integrity (AEoI) cannot be avoided.
4 | H4 | In relation to the Marine Mammal Baseline Characterisation the proposed densities to be used in the quantitative assessment should be an average monthly density estimate of 1.82 porpoise/km2 based on data obtained from the two-year baseline survey. Given that the project lies within the winter portion of the Southern North Sea SAC, where harbour porpoises are present in higher densities, low densities obtained by SCANS are not representative neither are they precautionary.
5 | H6 | A combination of medium sensitivity and medium magnitude should result in a non-significant effect. As such, the Cumulative Effects Assessment (CEA) for disturbance to harbour porpoise and harbour seals should result in moderate effect, which is significant in EIA terms opposed to the current conclusion of ‘minor.’
6 | H7 | SCANS III and IV densities should not be included in the quantitative assessment for PTS-onset, TTS- onset and behavioural disturbance from piling for harbour porpoise.
7 | H8 | Natural England is not confident in the level of commitment to using this mitigation method, nor does it support robust conclusions of the assessment that relies on this type of mitigation. Natural England strongly advises that the Applicant should commit to using NAS at this stage to ensure the conclusion that the significance of mitigated PTS from piling is Negligible.
8 | H9 | We defer to Cefas as the underwater noise specialists to comment on the Underwater Noise Technical Report.
9 | H10 | The Outline Marine Mammal Mitigation Plan (MMMP) provides a summary of potential mitigation measures. and is not intended to identify specific mitigation measures that will be implemented during pile-driving operations. However, Natural England strongly advises that the Applicant should commit to using noise abatement as mitigation now, should driven or part-driven piles be used during construction.
10 | H11 | In the Outline Marine Mammal Mitigation Protocol the Applicant proposes to start piling with a soft start at 15% (1050KJ) of the maximum hammer energy (7000KJ). We do not consider this to be adequately low energy for the commencement of piling and advise that the soft start is initiated with 10% of the maximum hammer energy i.e. 700KJ.
11 | H13 | If a marine mammal is not observed leaving the mitigation zone, a delay of 20 minutes from the last sighting should be implemented before commencement of soft start piling. This should be a commitment within the Outline Marine Mammal Mitigation Protocol.
12 | H14 | The Passive Acoustic Monitoring (PAM) guidance was updated in December 2023 (JNCC 2023). This updated version should be used to inform the final MMMP and the outline MMMP should be updated to note this expectation.
13 | H15 | We do not consider scare changes a suitable mitigation measure for UXO clearance, thus we advise that this measure is not considered in the outline MMMP.
14 | H16 | There is a misunderstanding around the concept of ‘breaks in UXO detonations’. Given the nature of detonations as an instantaneous activity, breaks in detonations are not possible. Time periods between subsequent detonations should not be considered as breaks and any time prior to a new detonation should be adequately monitored during the pre-denotation search. Post-detonation search is not considered as a ‘break,’ but it is a standard monitoring protocol following the detonation. This should be reflected in an updated Outline Marine Mammal Mitigation Protocol.
15 | H17 | It is stated in the MMMP for UXO and piling that “If UXO detonation [or piling] is delayed, there would be a risk of animals re-entering the mitigation zone when ADDs are switched off. However, turning on ADDs for extended periods may lead to habituation. Therefore, ADDs would be promptly turned off during delays and reactivated when detonation is ready to commence.” Protocol for delays should be carefully thought through taking into account maximum duration of the Acoustic Deterrent Device (ADD), time of the delay and expected time of the detonation. A break in ADD use should be more than 20 minutes to ensure a startle and flee response once reactivated in circumstances when the commencement of piling is delayed for a sufficient time to warrant the ADD being turned off.
16 | H18 | Visual marine mammal watches should commence at least 30 minutes before ADD activation. This might require the visual watch to be longer than 1 hour when the ADD activation time is longer than 30 minutes. This should be reflected in an updated Outline Marine Mammal Mitigation Protocol.
17 | H20 | Harbour porpoise has been screened out from sites that are more than 26 km from the project based on a lack of evidence to suggest connectivity. However, harbour porpoises within the North Sea Management Unit are considered to be a part of the continuous population. Thus, as wide-ranging animals, any designated site with harbour porpoise as a named feature within the North Sea Management Unit should be screened in.
18 | H21 | It is not clear if seismic surveys have been included in the in-combination assessment due to the contradicting text throughout the document. It is also not clear which tier they have been assigned to (tier 6 (Table 9.6) or tier 7 (Table 12.3, & 12.3.30)). Clarity should be provided on this.
19 | H22 | A high proportion of the Southern North Sea SAC is estimated to be disturbed by the project in-combination with other activities. This percentage is 86.47% at the highest and is far greater than the 20% daily noise threshold for the SAC. Consequently, we cannot agree to the conclusion of no AEoI for in-combination impacts of the project for disturbance of harbour porpoise in the SNS SAC unless the Applicant fully commits to NAS within the SIP.
20 | H23 | We do not agree with the conclusion of no AEoI for in-combination impacts of the project for disturbance of harbour porpoise in the SNS SAC across a season since the mitigation committed to in the MMMP is designed to reduce the likelihood of injury caused by underwater noise not to reduce disturbance, it cannot be used as a justification to support no AEoI. To reduce disturbance to harbour porpoise alone and in-combination, the Applicant needs to commit to NAS to significantly reduce the sound at source.

## I - Seascape
Point | Point Number(s) from Appendix I [PD2-011] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix I - Seascape Landscape and Visual | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | I1 | The Applicant has introduced a definition of what an “immediate setting” is (“the foreground seascape”), allowing them to assert that the project is a ‘horizon development’. However, the special qualities of the SCHAONB, particularly the wildness and tranquillity special qualities, are highly sensitive to changes in views out to sea. Further consideration is required.
2 | I2 | The apparent heights and lateral spread values of the Wind Turbine Generators (WTGs) across the perceived horizon should be used to inform judgements on the significance of effects, rather than a simple reliance on separation distance. The VE WTGs, especially the ~320m design option, will create a densification effect across the horizon when seen in conjunction with the Greater Gabbard and Galloper arrays. Further consideration is required.
3 | I3 | The WTG apparent height, turbine density, and turbine lateral spread are three separate parameters that may be used to inform judgements on the significance of effects to the SCHAONB and SHC. Evidence should be submitted to support the Applicant’s assessment that effects from an increase in WTG density is “considered preferable” to an increase in HFoV, and what this outcome means for the assessment of harm to the SCHAONB and SHC.
4 | I4 | Within the northern array area of VE, the most northerly 8 WTGs have the greatest potential to affect the special qualities of the SCHAONB and the special character of the SHC. This relates to their lateral spread, combined with their apparent height, which from some viewpoints will bridge the gap between Galloper OWF and the consented East Anglia TWO (EA2) array. While the remaining 8 WTGs are, from most views, partially masked by the Galloper WTGs, their sheer size will create a harsh juxtaposition on the horizon with the existing arrays. Further embedded mitigation is required.
5 | I5 | Natural England welcomes the reduction in the maximum blade tip height to 399m in the submitted proposal.
6 | I6 | The ~320m blade tip height design is more acceptable, although the apparent heights of the WTGs do not become completely insignificant. The greater northward lateral spread of WTGs combined the densification effects associated with the greater number of WTGs would also result in some significant effects. The ~320m turbines will still appear to be significantly taller than the existing turbines (Galloper and Greater Gabbard arrays), albeit partially obscured. Therefore, the need to consider Natural England’s Design Principles remains.
7 | I7 | Natural England's proposed Design Principles 1, 2 and 3 have not been adopted by the Applicant as embedded mitigation within the submission. We do not agree that the evolution of the project design is acceptable embedded mitigation, or that Design Principles 1, 2 and 3 have been fully considered within the project design. Further consideration of the Design Principles is needed.
8 | I8 | We do not agree with the description of the VE array as “relatively permeable”, nor that it “does not create enclosure”, or that “the apparent height of the VE WTGs is relatively small”. Further consideration of the Design Principles is needed.
9 | I9 | Page 71 of APP-079 states that “Visualisations of the ~320 m design scenario (79 turbines) are shown in Figure 10.47 – Figure 10.67.” Natural England has been unable to locate these visualisations within the submission material.
10 | I10 | The revised indicative Maximum Design Scenario (MDS) layout results in a distinct grouping of 8 WTGs in the remaining gap between the proposed VE array and the EA2 array. There remains disagreement with the statement that ‘VE will entirely occur in the context of the existing developments’ and that the VE WTGs can be considered as ‘generally in keeping’ with existing arrays given the starkly differing apparent heights between Galloper / Greater Gabbard arrays and VE. The SLVIA should be updated to consider the implications of removing the remaining gap between the existing/proposed OWF arrays in this area.
11 | I11 | There is disagreement with the assessment that the additional cluttering effects from the VE project have been appropriately mitigated. The potential effects on the SCHAONB and SHC from the distinct grouping of 8 WTGs in the remaining gap between the proposed VE array and the EA2 array have not been addressed. The assessment needs to be updated to assess what the additional impact of VE is in terms of the cluttering effect identified and apply mitigation based on the Natural England design principles.
12 | I12 | The most northerly 8 WTGs will create and draw focus to a new distinct object on the horizon, and that the resulting harm from this new object on the statutory purposes of the SCHAONB and the special character of the SHC has not been fully considered in the assessment.
13 | I13 | Natural England disagrees with the Applicant’s assessment on the “curtaining” effect. The assessment of the sense of openness and exposure special quality has not properly considered the effect of VE closing of gap between the existing Galloper and Greater Gabbard OWF arrays and the to be built EA2 array. There is a likelihood that VE would close the last ‘gap without turbines’ in direct views out to sea along a ~20km stretch of SCHAONB and SHC coastline (Orford Ness to Dunwich). This needs further consideration and mitigation.

## J - Onshore Ecology
Point | Point Number(s) from Appendix J [PD2-012] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix J - Onshore Ecology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | J1 | Confidence in mitigation proposals for protected species is reduced due to limitations of survey results caused by the timing of the surveys.
2 | J2/J32 | Use of an arbitrary time period for the definition of duration in relation to impact assessment for protected species doesn’t consider the life cycle of the species being assessed, including invertebrates of particular conservation concern.
3 | J3 | Depending on the opening of the King Charles III England Coast Path (ECP) there are likely to be receptor impacts
4 | J4 | There is potential for impacts to designated sites & features at the Lesser Black Backed Gull (LBBG) compensation site on Orford Ness
5 | J5/J14/ | Should this extension project utilise the same operational port facility as the constructed Galloper Offshore Wind Farm (OWF), within the Scour and Orwell Special Protection Area (SPA); an assessment of what the disturbance impacts of increased boat traffic and any expansion of the O&M facility is required.
6 | J7 | Habitat/botanical surveys undertaken in January 2024 were outside the optimal survey season limiting confidence in conclusions made regarding impacts to the proposed compensation site at Orford Ness. With the presence of uncommon species not being ruled out along the proposed fence line.
7 | J4/J8 | Coastal recession/advancement trends at the LBBG compensation site(s) have not been adequately assessed over the life time of the project using best available evidence.
8 | J10 | Following more robust site specific surveys further consideration is needed regarding appropriate mitigation measures for impacts on the Orford Ness – Shingle Street SAC from the LBBG compensation site(s).
9 | J11/J24 | Construction and management/monitoring/maintenance/ impacts to habitat within and adjacent to the fence line at the LBBG compensation site at Orford Ness is likely to have significant effects on perennial vegetation on coastal shingle, especially where the sediment structure is destabilised. This has the potential to cause a long-term, if not permanent, shift towards a secondary form of vegetation.
10 | J12/J24 | The EIA does not consider impacts to the shingle morphology and sediment structure and recoverability. Typically, shingle morphology landward of the seaward ridge never fully recovers. There is also the risk of further repeated damage occurring through regular maintenance/monitoring/ management of the fence line.
11 | J13/J25 | The EIA has not considered impacts to the saline lagoons at the Orford Ness compensation site from the presence of the fence through the lifetime of the project in terms of blockage to overtopping events and the transfer of new shingle to their eastern edge and subsequent implications to the lagoon biodiversity. Furthermore, the impacts of climate-related changes (including water levels and coastal stability) need to be further considered.
12 | J16/J17 | Key evidence to support the screening out of Marsh Harrier and Nightjar populations at the Alde Ore Estuary SPA and Minsmere-Walberswick SPA within the HRA is missing from the bibliography, namely an article by Wright (2012).
13 | J18 | Detail of all mitigation for Onshore Ecology and Biodiversity should be included in relevant sections of outline plans and documents e.g. Table 8.1
14 | J19 | What are the Applicant’s intended course of action should the agreed proposed buffer zones for Schedule 1 bird species and other breeding species be unsuccessful?
15 | J20 | Through use of the mitigation hierarchy every effort should be made to avoid, reduce and mitigate impacts including for black-tailed godwit, a designated feature of Hamford Water SPA & Ramsar; Stour and Orwell Estuaries SPA & Ramsar; and Blackwater Estuary SPA & Ramsar.
16 | J21 | Further clarification on the Applicant’s assessment of the cumulative effect of both disturbance and temporary habitat loss to dunlin, a designated feature of Stour and Orwell Estuaries SPA & Ramsar, and Blackwater Estuary SPA & Ramsar is required.
17 | J22 | Commitments to follow best practice should be made for maintaining vegetation community and diversity at the LBBG comepnsation area including (but not exclusively) the use of existing access trackways during construction and maintenance/ management.
18 | J23 | More than 'habitat management' in the form of mosaic cutting of vegetation and removal of arisings will be required to manage the increase in nutrients from the establishment of a gull colony at the Orford Ness compensation site.
19 | J26 | Compensatory measures for Lesser Black backed gull at Alde-Ore Estuary (AOE) SPA need to be agreed please see Ornithology compensation tab for further comments |  | We will not be providing further comments on this during Examination.
20 | J29 | While trenchless crossings of Holland Haven Marshes SSSI and the Frinton Golf Club are committed to in the Outline Landfall Methodology; mitigation measures within 9.21 Code of Construction Practice are included for all installation options to address potential impacts occur especially in relation to bentonite frac-out. All comments from NE and EA in relation to this location should be given due consideration
21 | J30 | Protected species licences and therefore Letters of No Impediment will not be required for this project. |  | We will not be providing further comments on this during Examination.
22 | J31 | Limitations of protected species surveys will need to be addressed pre-construction with all areas surveyed
23 | J33 | Pre construction surveys should follow standard methods, especially for badgers to ensure surveys are undertaken at the optimum time.
24 | J34 | Survey results lack information relating to badger main setts despite observations of numerous associated setts
25 | J35 | Trees within exclusion areas have only been subject to Ground Level Tree Assessment (GLTA) surveys and commitments to follow best practice at pre-construction are required
26 | J36 | The use of DLL prior to construction Is agreed to ensure compliance with the legal status of GCN and mitigate for potential impacts on this species. |  | We will not be providing further comments on this during Examination.
27 | J37 | The Applicant’s commitment to delivering a minimum of 10% BNG (section 1.2.2, pg.2) should be secured by requirement in the DCO.
28 | J38/J42 | BNG should reflect best practice or the approach used for TCPA development. The metric calculations will need updating over time to reflect updated guidance, design iterations and to maximise their potential biodiversity outcomes throughout the detailed design process.
29 | J39 | As per current government guidance, commitments are required to ensure mitigation or compensation for protected species or designated site impacts results in “no net loss”, with 10% BNG being additional.
30 | J40 | Assigning strategic significance was updated with the introduction of mandatory BNG in February 2024 (see Statutory Metric User Guide, pg.26). And this should be adhered to going forwards
31 | J41 | There is no irreplaceable or very high distinctiveness habitat on-site, although it does occur within the Order Limits (pg.11). |  | We will not be providing further comments on this during Examination.

## K - Landscape VIA
Point | Point Number(s) from Appendix K [PD2-013] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix K - Landscape and Visual Impact Assessment | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | K1 | Owing to insufficient evidence on the Norwich-Tilbury substation design/impacts at this stage, there is a potential for in-combination/cumulative impacts between this project, the Five Estuaries (VE), and North Falls substations.
2 | K3 | There is the potential for in-combination/cumulative landscape and visual impacts arising between VE, North Falls and Norwich-Tilbury NSIP substations.
3 | K5 | The setting of Dedham Vale National Landscape could be impacted prior to establishment of mitigation screening.