## Title page
THE PLANNING ACT 2008
THE INFRASTRUCTURE PLANNING (EXAMINATION PROCEDURE) RULES
2010
Natural England's Risk and Issues Log - Deadine 5 Submission.
For:
The construction and operation of Five Estuaries Offshore Wind Farm, located approximately 57km from the Essex Coast in the Southern North Sea.
Planning Inspectorate Reference EN010115
10/01/2025

## How to read Risks and Issue Log
Natural England has created this Risk and Issues Log to track progress through the Five Estuaries examination process of risks and issues raised in our Relevant and Written Representations The Risks and Issues Log will be submitted at each deadline and mark issues with a colour from our RAG scale depending on the level of significance of the issue. It should be noted that the colour scale is likely to be different from that used in any Statement of Common Ground provided by The Applicant. The Risk and Issues Log is split into multiple tabs in line with the Appendices of our Relevant Representations submission. A - DCO B - Marine Processes C - Offshore Ornithology D - Ornithological Compensation E - Benthic Ecology F - Benthic Compensation G - Fish Ecology H - Marine Mammals I - Seascape J - Onshore Ecology K - Landscape VIA Each updated submission of the Risk and Issues Log will reflect our position following a review of documents that we have considered in forming our position at each deadline. Any issues added to the log due to additional submissions during Examination (not included in Relevant Reps) are highlighted in Red and then coded according to RAG status.
Purple Note for Examiners and/or competent authority. May relate to DCO/DML
Red Natural England considers that unless these issues are resolved it will have to advise that (in relation to any one of them, and as appropriate) it is not possible to ascertain beyond reasonable scientific doubt that the project will not affect the integrity of an SAC/SPA/Ramsar and/or significantly hinder the conservation objectives of an MCZ and/or damage or destroy the interest features of a SSSI and/or comply fully with the Environmental Impact Assessment requirements.
Addressing these concerns may require the following:
new baseline or survey data; and/or
significant revisions to baseline characterisation and/or impact modelling and/or
significant design changes; and/or
significant mitigation
In addition, Natural England may use this category to highlight where there is a significant risk that an issue will not be sufficiently addressed within the Examination timescales. Consequently, issues that start out as Amber may progress to Red in the latter stages of the examination.
Amber Natural England does not agree with the applicant’s position or approach and consider that this could make a material difference to the outcome of the decision-making process for this project.
Natural England considers that these matters may be resolved through:
provision of additional evidence or justification to support conclusions; and/or
revisions to impact assessment methodology and/or assessment conclusions; and/or
minor to moderate revisions to impact modelling; and/or
well-designed mitigation measures that are adequately secured through the draft DCO/dML and/or
amendments to draft plans
If these issues are not addressed or are unlikely to be resolved by the end of the Examination, then they may become a Red risk as set out above.
Yellow Natural England doesn’t agree with the Applicant’s position or approach. We would ideally have liked this to be addressed prior to the examination but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process and would not expect these matters to be an ongoing focus of the examination. However, we reserve the right to revise our opinion should further evidence be presented.
It should be noted by interested parties that just because these issues/comments are not raised as significant concerns in this instance, it should not be understood or inferred that Natural England would be of the same view in other cases or circumstances.
Once a Risk or Issue has been categorised as yellow, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be greyed out at subsequent deadlines in order to rationalise the risk and issues log.
Green Natural England is in broad agreement with the Applicant’s approach and has no significant outstanding concerns. As above, we reserve the right to revise our opinion should new evidence be presented. Once a Risk or Issue has been categorised as green, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be greyed out at subsequent deadlines in order to rationalise the risk and issues log.

## PADSS
PRINCIPAL AREAS OF DISAGREEMENT SUMMARY STATEMENT (PADSS) - TAKEN FROM COVER LETTER TO NATURAL ENGLAND'S REL REPS [PD2-002]
NE Ref | The principal issue in question | The brief concern held by Natural England which will be reported on in full in WR / LIR | What needs to change, or be included, or amended so as to overcome the disagreement | Likelihood of the concern being addressed during Examination | RAG rating | What actions have been taken (if any), what still needs to change, or be included, or amended so as to overcome the disagreement | RAG rating at Deadline 3 | What actions have been taken (if any), what still needs to change, or be included, or amended so as to overcome the disagreement | RAG rating at Deadline 4 | What actions have been taken (if any), what still needs to change, or be included, or amended so as to overcome the disagreement | RAG rating at Deadline 5
Development Consent Order (DCO)
P1 | The during construction monitoring conditions within the deemed Marine Licences (dML) Schedules 10 and 11 do not secure that piling must cease in the event the monitoring highlights the noise impact is significantly in excess of the predicted impacts assessed. | This is a key mitigation for marine mammals and has been included in previous DCOs for various offshore wind farms, such as the recent East Anglia One North project or the Sheringham and Dudgeon Extension Project. | We recommend that the condition wording should be amended to include the requirement to stop should the noise impacts of the works be significantly in excess of those assessed. We also recommend that this wording is included in Schedules 10 and 11. | Potential resolution. |  | No change, no actions have been undertaken. |  | Natural England and the Applicant have a meeting scheduled for 9th December to discuss the outstanding DCO issues. An update on progress made will be provided at Deadline 5. |  | Natural England notes new wording has been included in the updated DCO submitted at Deadline 4 which partially addresses our concerns. We have oustanding conceerns relating to the timing of the reports and the wording used to trigger a stop of works.
P2 | Margate and Long Sands Special Area of Conservation (MLS SAC) Benthic Mitigation Plan is not secured within the transmission deemed Marine Licence (dML). | This plan includes key mitigation for the SAC which needs to be updated to include relevant up-to-date information on the final designs and up to date mitigation techniques. | Therefore, we consider that an updated plan should be secured through condition. | Potential resolution. |  | No change, no actions have been undertaken. |  | Natural England and the Applicant have a meeting scheduled for 9th December to discuss the outstanding DCO issues. An update on progress made will be provided at Deadline 5. |  | Natural England met with the Applicant on 9 December and has subsequently provided a written response to the Applicant's comments on the DCO, including this provision. We await any further update from the Applicant before providing further advice into examination..
P3 | Schedule 14 includes only impacts to Alde-Ore Estuary Special Protection Area (SPA) Lesser Black Backed Gull (LBBG), but not affected features of MLS SAC or Flamborough and Filey Coast (FFC) SPA. | We cannot rule out Adverse Effect on Integrity (AEoI) on MLS SAC and FFC SPA and advise that compensation may be required for these sites, if the Secretary of State (SoS) determines that it is required. | We, therefore, advise that provision for compensation for these features should be made in the draft DCO on a without prejudice basis. | Potential resolution. |  | No change, no actions have been undertaken. |  | Natural England and the Applicant have a meeting scheduled for 9th December to discuss the outstanding DCO issues. An update on progress made will be provided at Deadline 5. |  | Natural England met with the Applicant on 9 December and has subsequently provided a written response to the Applicant's comments on the DCO, including this provision. We await any further update from the Applicant before providing further advice into examination..
Marine Geology, Oceanography and Physical Processes
P4 | Disruption of sediment transport processes at MLS SAC due to the placement of cable protection | Insufficient information to assess the magnitude and significance of potential impacts to sediment transport processes within MLS SAC. | Further information is needed to demonstrate that the presence of cable protection within MLS SAC will not alter sediment transport processes and, morphology of Annex I sandbank features during the lifespan of the project. | Potential resolution. |  | No change, no actions have been undertaken. |  | The Applicant needs to provide more evidence to support their conclusions of 'only very minor changes' to the sediment transport regime, such as a more detailed sediment transport study/modelling of the proposed cable protection placement area at MLS SAC, based on the prevailing conditions to resolve this matter. |  | Currently, there is insufficient information to assess the impact of cable protection measures on the complex patterns of sediment circulation around the northern tip of MLS SAC and, in turn, seabed morphology and sediment composition.
P5 | Construction and Operation and Maintenance Impacts to SPA/SAC supporting habitats, and priority habitats | Incomplete consideration of potential impacts to seabed morphology and magnitude and significance of their effect. | An updated WCS/maximum design scenario (MDS) should be provided for construction-and operation and maintenance related impacts on seabed morphology and seabed mobility. | Potential Resolution. |  | Partially resolved. The Applicant needs to be provide a WCS/MDS for construction-related sediment deposition thickness within the Array Areas to inform the impact assessment for other ecological receptors (e.g. fish). With regards to changes to operational impacts to seabed morphology, we advise that further information is needed regarding seabed mobility/bedform migration and stability. |  | Our Deadline 3 advice remains unchanged. |  | No change.
Offshore Ornithology
P6 | Potential incorrect estimates for Alde-Ore Estuary (AOE) SPA lesser black backed gull (LBBG) mortalities. | At present, the estimates for mortalities due to collision at both the north and south VE arrays appear incorrect. | The total impact value should be clarified and, if necessary, the Population Viability Analysis (PVA) re-run (with burn-in) to indicate the project alone and in-combination effects on AOE SPA LBBG. | Uncertain. If the assessment is updated, as advised, this issue may be resolved. It will still be the case that an AEoI cannot be ruled out. |  | Uncertain. Whilst the mortality estimates have been clarified, the assessment still needs to be revised for the issue to be resolved. |  | No change. |  | Resolved. The Applicant has stated that PVA could not be run with burn-in for LBBG due to issues with the PVA tool and the available data. This is acceptable to NE [REP4-040].
P7 | Apportioning of adults (other than AOE SPA LBBG) during the breeding season based on generic data rather than site-specific data. | We advise that the evidence used to inform adult apportioning is not sufficient. The data on the number of adult- or adult-type birds present is generic. Seasonal variations should also be considered. | We continue to advise that for species that can be aged as adult or sub-adult from Digital Aerial Survey (DAS), site-specific data represents the best available evidence for apportioning. Where this is not possible, a precautionary approach should be adopted. An updated assessment based on Natural England’s advised approach should be submitted into the Examination in due course. | Potential resolution. If the Applicant updates the assessment in line with our recommendations, then this issue could be resolved. |  | Resolved adequately for the key species of concern. |  | Remains resolved. |  | This issue has been resolved.
P8 | In-combination impacts on the FFC SPA populations of guillemot and razorbill are at a level where adverse effects cannot be ruled out and VE will be adding to this. | The Applicant has applied their preferred displacement (50%) and mortality (1%) rates to the guillemot and razorbill populations at risk at each offshore wind farm (OWF) project included in the in-combination assessment for the FFC SPA. As well as departing from Natural England advice on this matter, in so doing the Applicant disregards the in-combination values that have been used by DESNZ for recent consents. | The Applicant should simply add the VE project alone impact (at 70% displacement and 2% mortality) to the total in-combination impact agreed in the Sheringham and Dudgeon Extensions Project OWF (SADEP) Examination. | Potential resolution. This should be submitted into the Examination to resolve this issue. |  | Progressed but not resolved - outputs for the VE project impact have now been presented at 70% displacement and 2% mortality, and some updates for other projects have been added, but the need to maintain and update the in-combination assessment in the light of additional information on other projects remains a live issue. |  | No change. |  | No change.
Ornithology Compensation
P9 | AOE SPA LBBG - concerns regarding the suitable level of compensation and the effectiveness of measures proposed at the two sites. | As well as the above issue regarding the impact calculation for AOE SPA LBBG, the compensation requirement is based on the mean number of mortalities rather than the 95% upper confidence interval (UCI) value. The proposed compensatory measures have potential merit, however further information is needed to provide sufficient confidence that the measures can be secured and will be effective. | The compensation quantum needs to be calculated in line with Natural England’s advice. Further information on the proposed compensation sites needs to be provided, particularly with respect to survey visits in summer 2024 as regards avoiding impacts on other designated sites (Orford Ness) and the likely drivers of population decline (Outer Trial Bank). | Uncertain. If the assessment is updated and the compensation based on the 95% UCI, the compensation requirements issue may be resolved. However, unless findings are presented promptly following the 2024 breeding season, the uncertainties around the proposed compensation are unlikely to be resolved during Examination. |  | No change. |  | No change. We note that landowner support for the proposed location on Orfordness is not available. |  | No change.
P10 | Uncertainty regarding adequacy of implementing disturbance management at southwest colonies for FFC SPA guillemot and razorbill. | Whilst we consider this measure to be technically feasible, candidate locations have been identified but not secured. Impact levels are also still to be agreed. | The Applicant needs to monitor the candidate sites to establish the current level of disturbance and identify measures needed to effectively mitigate it. | Uncertain Monitoring will take time so unless findings are presented promptly following the 2024 breeding season, this issue is unlikely to be resolved during Examination. |  | We welcome the provision of breeding season surveys, which indicate potential issues with recreational disturbance which could be addressed. However, several important elements still require further investigation or detail - please see Appendix M2 for more detail. |  | No change. |  | No change, recognising that some progress has been made by the Applicant.
P11 | FFC SPA kittiwake Artificial Nesting Structure (ANS). | As with LBBG above, the compensation requirements are to be calculated using the central impact value. There is also some uncertainty regarding the nature of the sharing agreement with DBS OWF for their ANS at Gateshead. | The compensation requirements need to be calculated using the 95% UCI. Further information is required on how the benefits of the Gateshead ANS will be divided amongst projects. | Potential to Resolve. If further details can be provided, then it is likely that this issue can be resolved. |  | No change. Compensation quantum still based on mean collision estimate (1.1 birds per annum) not the upper CI value (estimated 2.3 birds per annum). Also no further detail has been provided on arrangement with DBS OWF regards ANS nest space allocation. |  | Progressed but not resolved. Information on the sharing arrangement and apportioning of benefits for the Gateshead ANS has now been provided. However whilst the roadmap presents calculations regarding the 95% UCI, these relate to outputs using the lower of the two Nocturnal Activity Factors (NAF), whereas the higher one should be used. |  | Progressed but not resolved. We consider that the Applicant has addressed the 'division of benefits' approach, and they have presented the 95% UCI values which we welcome (albeit still arguing for use of the Central Impact Value and a 1:1 ration). However, the issue of using the lower of the two NAFs remains outstanding - NE considers the central impact value should be 1.1 not 0.82.
Benthic Ecology
P12 | AEoI on Annex I sandbank feature of Margate and Long Sands Special Area of Conservation (MLS SAC). | We disagree with the Applicant on the scale and significance of the impact. | Further reduction of impacts through adoption of robust mitigation measures. | Unlikely. |  | No change. |  | No change. |  | No change.
P13 | Mitigation measures fail to consider potential presence of Section 41 NERC Act habitats. | The Applicant has failed to consider Section 41 NERC Act habitats in their assessment. | The Applicant needs to consider and mitigate for potential impacts to Section 41 NERC Act habitats. | Potential Resolution. |  | Progressed but not resolved as there is no firm commitment to avoid and inclusion of a decision tree to minimise impacts where avoidance is not possible. |  | No change. |  | Whilst the Applicant has attempted to addess our concerns, without further commitments as per our response at Deadline 4 [REP4-059], our advice remains unchanged.
P14 | Methods and evidence used to determine MDS for cable protection within MLS SAC and WCS potentially not realistic. | Natural England is unable to advise on the scale and significance of the impacts and therefore compensatory requirements. | Natural England advises that further information is required to provide the necessary confidence in the MDS/Worst Case Scenario (WCS) for cable protection within the SAC. | Potential Resolution. |  | No change |  | No change (there remain inconsistencies in MDS between the [REP2-027] 10.20.1 Technical note - Methodology for Determining MDS (Offshore) and the [REP2-021] 9.13 Margate and Long Sands Special Area of Conservation Benthic Mitigation Plan - Revision B (Tracked) i.e. 900 m per cable vs 900 m in total) |  | No change. Whilst the Applicant has provided an updated Technical Note - Methodology for Determining MDS (Offshore) Rev B [REP4-034], the MDS/WCS for cable protection is still not clear. This should be clarified and all relevant documents updated.
Benthic Compensation
P15 | “Without Prejudice” Benthic Compensation | Further progress is required on each measure to have confidence that they are achievable and would deliver effective compensation for project impacts. | Natural England advises that further work on each measure will be required during examination before we can advise on the suitability. | Uncertain. Further review is likely to be undertaken during examination and with no guarantee this issue will be resolved within the examination timeframe. |  | No Change |  | Natural England advised in ExQ1 ME.1.10 [REP-059] that at this stage, we do not believe that there is merit in progressing and/or placing reliance upon project specific benthic compensation measures namely, Anthropogenic Pressure removal (Redundant infrastructure or aggregates) and Sea Grass Habitat Creation/Restoration. Therefore, we advise that once DEFRA's guidance on, and assurances in relation to the delivery of strategic benthic compensation (including timings etc.) become available, every effort is made by the Applicant to update the examination on Five Estuaries commitments to Strategic Benthic Compensation measures i.e. Marine Protected Area designation/extension |  | No change from our Deadline 4 advice
Marine Mammal Ecology
P16 | Southern North Sea Special Area of Conservation (SNS SAC) – harbour porpoise underwater noise impacts - Outline Site Integrity Plan (SIP) | Current approach to SIP implementation is unlikely to prevent impact thresholds from being exceeded in the SNS SAC. The Applicant has not committed to using Noise Abatement Systems (NAS) at this stage, increasing the risk that an adverse effect on site integrity (AEoI) cannot be avoided. | The Applicant should commit to specific mitigation measures at this stage, particularly Noise Abatement Systems (NAS), in the Outline/Draft Marine Mammal Mitigation Plan and submitted with the SIP at the DCO, which can be removed later if the revised SIP demonstrates they are not required. | Potential Resolution. If changes can be made to the Outline MMMP, it is likely this issue can be resolved. |  | The Applicant has not yet committed to NAS and updated MMMPs and SIP. We highlight that Defra and regulators have been actively considering updating current marine noise policy, and that an announcement regarding this may occur during the Examination period. Broadly speaking, the policy direction is towards an expectation that all offshore wind developers planning to carry out pile driving activity in English waters should in the first instance demonstrate that they have utilised best endeavours to deliver noise reductions through the use of primary and/or secondary noise mitigation methods. We will keep the Examination updated on any proposed policy changes. |  | No change. Natural England understands that the Defra Marine Noise Policy paper is currently due to be published in the next few weeks. See Appendix M4 for further information. |  | No change.
P17 | EIA/HRA Conclusions | Lack of robust evidence supporting the conclusions made. | Natural England recommends population modelling be conducted, for example, Interim Population Consequences of Disturbance (iPCoD), to inform the conclusions of the EIA and HRA. | Potential Resolution. If the Applicant carries out population modelling and updates their EIA/HRA assessment it may be possible to resolve this issue. |  | The Applicant carried out the iPCoD modelling for the project alone impacts. The modelling results showed that there is no change to the population size or trajectory, which supports the Applicant's assessment conclusions. However, Natural England has identified some concerns over the results presented. Natural England will respond to this in due course. |  | We welcome the iPCoD modelling carried out by the Applicant. However, we have concerns with the approach taken and results. Please refer to Appendix M3 of our Deadline 4 Examiners Question response. |  | No change.
Seascape, Landscape and Visual
P18 | Suffolk and Essex Coast & Heaths National Landscape/AONB and Suffolk Heritage Coast (SHC) – seascape impacts. | The special qualities of the National Landscape/AONB and the SHC will be affected by the proposed development. This is of particular concern at Orford Ness. We are concerned that the most northerly 8 WTGs will ‘close the gap’ and create a distinct grouping between the existing Galloper and Greater Gabbard OWF arrays, and the to be built EA2 array. In addition, the size difference between the VE and other WTGs in the area will result in a visually jarring ‘cluttering’ effect. | The SLVIA needs to be updated to properly assess the potential impacts on the AONB and SHC, particularly with respect to the most northerly WTG and the potential for the array to cause ‘curtaining’ and ‘cluttering’ effects. Once the assessment is updated, further consideration of NE advice on embedded mitigation is required, drawing on our three proposed design principles. | Uncertain. There is potential for the applicant to update the assessments during the examination. However, it is likely that the issues raised will not be resolved through. assessment alone and will require design changes in line with our proposed principles to be addressed. |  | No change. |  | No change. |  | No change.
Onshore Ecology
P19 | Potential impacts to designated sites and features at the proposed LBBG compensation site on Orford Ness. | Insufficient baseline data on the saline lagoon, shingle vegetation shingle sediment structure and morphology to advise on potential impacts. | An adequate baseline survey should be carried out pre-determination in the proposed compensation location in order to inform the impact assessment and avoidance/mitigation measures required. | Uncertain. If the Applicant can commit to carrying out pre-determination surveys and providing further information, as required, then this issue could be resolved during Examination. |  | Potential resolution. The Applicant has provided further information on the LBBG Orford Ness option including HRA, Flood Risk Assessment, EIA and updated plans. We will provide an update on this issue at Deadline 4. |  | Uncertainty now over acquisition of Cobra Mist land. Baseline survey data remains incomplete. Need to see appropriate survey data to support assessment conclusions, including to confirm current sensitivity of shingle morphology and habitats. |  | Whilst the Applicant has carried out invertebrate and vegetation surveys at Orford Ness [REP4-042], the surveyed area does not overlap the proposed compensation site. Therefore, our earlier concerns regarding an incomplete baseline remain.
P20 | Operational and maintenance facility impacts have not been considered. | No consideration has been given to the potential impacts from the operational port on the environment. | Natural England advises that impacts from the operation port should be assessed as part of the DCO at the consenting phase to ensure that a Holistic approach can be taken to the HRA. | Uncertain. The Applicant needs to include the O&M port in its EIA/HRA to resolve this issue during Examination. |  | No change. |  | No change. |  | No change.
Please note that this PADSS should be read in conjunction with our written representations Appendices, which provide further detail on the areas of disagreement as well as other areas of disagreement which require resolution. For ease of reference, we have added a RAG rating for each principal area. Please note that the PADSS is ordered by topic and not by priority.

## A - DCO
Point | Point Number(s) from Appendix A [PD2-003] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix A - DCO | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | A1, A11 | The during construction monitoring conditions within the deemed Marine Licences (dML) Schedules 10 and 11 do not secure that piling must cease in the event the monitoring highlights the noise impact is significantly in excess of the predicted impacts assessed, and the potential need for further monitoring. |  | No change |  | No change |  | Pending discussion at NE/Applicant meeting on 9 December. |  | Natural England provided comment on the new wording within the Deadline 5 cover letter. Outstanding issues remain with timing and some aspects of the wording, however, this issue has been partially resolved.
2 | A2, A14 | The Margate and Long Sands Special Area of Conservation (SAC) Benthic Mitigation Plan is not secured through condition within the transmission dML, Schedule 11. This Plan details key mitigation for the SAC and should be secured through appropriate condition. It is important that the Margate and Long Sands Benthic Mitigation Plan be resubmitted for approval with detailed mitigation based on the final designs and up to date mitigation techniques. |  | No change |  | No change |  | Pending discussion at NE/Applicant meeting on 9 December. |  | Natural England met with the Applicant on 9 December and has subsequently provided a written response to the Applicant's comments on the DCO, including this provision. We await any further update from the Applicant before providing further advice into examination.
3 | A3, A16 | NE cannot rule out an adverse effect on integrity (AEoI) on the Margate and Long Sands SAC (sandbanks) and the Flamborough and Filey Coast Special Protection Area (SPA) (kittiwake, guillemot, razorbill). Therefore provision for compensation should be included in the draft DCO on a without prejudice basis to provide the Secretary of State (SoS) with detailed and agreed provisions should he determine that compensation is required. |  | No change |  | No change |  | Pending discussion at NE/Applicant meeting on 9 December. |  | Natural England met with the Applicant on 9 December and has subsequently provided a written response to the Applicant's comments on the DCO, including this provision. We await any further update from the Applicant, before providing further advice into examination.
4 | A4 | The requirement for landscaping does not cover all required aspects e.g. survey methods, monitoring requirements and the requirement to maintain/replant. Further we would expect to be consulted on these plans prior to their approval by the relevant local planning authority. |  | No change |  | No change |  | Pending discussion at NE/Applicant meeting on 9 December. |  | Natural England met with the Applicant on 9 December and has subsequently provided a written response to the Applicant's comments on the DCO, including this provision. We await any further update from the Applicant before providing further advice into examination.
5 | A5 | Requirement 8 (1) does not secure that the Code of Construction Practice (CoCP) must be submitted and approved prior to the commencement of works, nor includes a requirement to consult the relevant SNCB on the CoCP. The requirement should also note the final CoCP must accord with the outline CoCP. Further the requirement refers to sub paragraph (3) of the requirement which does not exist. |  | No change |  | No change |  | Pending discussion at NE/Applicant meeting on 9 December. |  | Natural England met with the Applicant on 9 December and has subsequently provided a written response to the Applicant's comments on the DCO, including this provision. We await any further update from the Applicant before providing further advice into examination.
6 | A6 | This provision should be amended to state that no pre commencement clearance works should be undertaken until a written LEMP, as relevant to the stage of the works, has been submitted to, and approved by, the Local Planning Authority (LPA) following consultation with the relevant SNCB. |  | No change |  | No change |  | Pending discussion at NE/Applicant meeting on 9 December. |  | Natural England met with the Applicant on 9 December and has subsequently provided a written response to the Applicant's comments on the DCO, including this provision. We await any further update from the Applicant before providing further advice into examination.
7 | A7 | Consideration should be given as to whether the requirement covering vehicle access and construction plans for the LBBG compensatory works sit better within the compensation schedule. This would ensure that the approval of compensatory works are considered holistically by a single decision maker and reduce the potential for conflicting decisions. |  | No change |  | No change |  | No Change |  | No change.
8 | A8 | The requirement securing the need for a Biodiversity Net Gain (BNG) strategy should be amended to require consultation with the relevant SNCB and to monitor, maintain and potentially employ adaptive management measures over thirty years, or for the lifetime of the development. |  | No change |  | No change |  | Pending discussion at NE/Applicant meeting on 9 December. |  | Natural England met with the Applicant on 9 December and has subsequently provided a written response to the Applicant's comments on the DCO, including this provision. We await any further update from the Applicant before providing further advice into examination.
9 | A9 | The Site Integrity Plan (SIP) condition should require the SIP no sooner than 9 months and no later than 6 months prior to commencement of piling. to ensure the plan is not submitted too early to consider all relevant in combination issues. |  | No change |  | No change |  | Pending discussion at NE/Applicant meeting on 9 December. |  | Natural England met with the Applicant on 9 December and has subsequently provided a written response to the Applicant's comments on the DCO, including this provision. We await any further update from the Applicant before providing further advice into examination.
10 | A10 | Natural England notes that the monitoring conditions only cover benthic monitoring. Ornithological and Marine Mammal monitoring should also be requirements due to the potential for impact. |  | No change |  | No change |  | Pending discussion at NE/Applicant meeting on 9 December. |  | Natural England met with the Applicant on 9 December and has subsequently provided a written response to the Applicant's comments on the DCO, including this provision. We await any further update from the Applicant before providing further advice into examination.
11 | A12 | A condition requiring remediation or further mitigation works should monitoring show impacts are greater than predicted should be included within the dMLs. NE are advising this for all relevant dMLs. |  | No change |  | No change |  | Pending discussion at NE/Applicant meeting on 9 December. |  | Natural England met with the Applicant on 9 December and has subsequently provided a written response to the Applicant's comments on the DCO, including this provision. We await any further update from the Applicant before providing further advice into examination.
12 | A15 | The cable protection condition should be amended to ensure that cable protection within the Margate and Long Sands Special Area of Conservation (SAC) is only deployed during the construction phase. |  | No change |  | No change |  | Pending discussion at NE/Applicant meeting on 9 December. |  | Natural England met with the Applicant on 9 December and has subsequently provided a written response to the Applicant's comments on the DCO, including this provision. We await any further update from the Applicant before providing further advice into examination.
13 | A17 | All references to Natural England within this schedule should be amended to the SNCB to ensure consistency with the rest of the DCO. |  | No change |  | Resolved. Appropriate changes made in the DCO submitted at deadline 1.
14 | A18 | The condition relating to the Offshore Ornithology Engagement Group should be updated to include provision of terms of reference, a timetable for the preparation and delivery of the LBBG implementation and monitoring plan (LIMP), and a dispute resolution mechanism. These have been included in many compensation schedules for LBBG. |  | No change |  | No change |  | Pending discussion at NE/Applicant meeting on 9 December. |  | Natural England met with the Applicant on 9 December and has subsequently provided a written response to the Applicant's comments on the DCO, including this provision. We await any further update from the Applicant before providing further advice into examination.
15 | A19 | Natural England notes that there is ongoing work on strategic compensation and would support the inclusion of appropriate provisions to allow use of agreed strategic compensation. However, the condition wording here is insufficient, if that is its purpose. Recommend amending this provision and consideration of how to appropriately implement a provision allowing strategic compensation options. |  | No change |  | No change |  | Pending discussion at NE/Applicant meeting on 9 December. |  | Natural England met with the Applicant on 9 December and has subsequently provided a written response to the Applicant's comments on the DCO, including this provision. We await any further update from the Applicant before providing further advice into examination.
16 | A20 | The list of requirements to include in the LIMP is lacking in detail when compared to similar provisions used to secure compensation with respect to survey methodologies, timetables for the monitoring to be conducted and reports delivered and success criteria, and a detailed mechanism to determine the need for any alternative compensation or adaptive management measures, along with potential further monitoring and maintenance of such measures. |  | No change |  | No change |  | Pending discussion at NE/Applicant meeting on 9 December. |  | Natural England met with the Applicant on 9 December and has subsequently provided a written response to the Applicant's comments on the DCO, including this provision. We await any further update from the Applicant before providing further advice into examination.
17 | A21 | This requirement ensures that LBBG compensation must be provided three full breeding seasons prior to operation. However, Natural England notes that on other developments a period of four full breeding seasons was deemed appropriate. |  | No change |  | No change |  | Pending discussion at NE/Applicant meeting on 9 December. |  | Natural England met with the Applicant on 9 December and has subsequently provided a written response to the Applicant's comments on the DCO, including this provision. We await any further update from the Applicant before providing further advice into examination.
18 | A22 | The compensation may be required for longer than the lifetime of the project and therefore the provision should specify that the compensation should be maintained until the SoS approves its decommissioning in consultation with the relevant SNCB. |  | No change |  | No change |  | Pending discussion at NE/Applicant meeting on 9 December. |  | Natural England met with the Applicant on 9 December and has subsequently provided a written response to the Applicant's comments on the DCO, including this provision. We await any further update from the Applicant before providing further advice into examination.
19 | A23 | Several activities within Appendix A will require a new marine licence, but are recorded as amber, whereas the coding provided within the plan indicates that these should be considered red e.g. foundation replacement. Appendix A should be amended to reflect the appropriate colour marking. |  | No change |  | No change |  | Pending discussion at NE/Applicant meeting on 9 December. |  | No Change
20 | A24 | It would have been useful for the table to have included a reference to the relevant section in the Environmental Statement (ES) to allow appropriate cross referencing. |  | No change |  | No change |  | Pending discussion at NE/Applicant meeting on 9 December. |  | No Change

## B - Marine Processes
Point | Point Number(s) from Appendix B [PD2-004] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix B - Marine Geology, Oceanography and Physical Processes | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | B1/B27 | There is insufficient evidence to support the impact assessment of cable protection on Annex I Sandbanks of Margate and Long Sands Special Area of Conservation (MLS SAC) from disruption of sediment transport both alone and in-combination. |  | No change |  | Not progressed. |  | No change. Whilst we note in the MDS Technical Note [REP2-027] that "only very minor changes are expected to the sediment transport regime at MLS SAC due to the presence of cable protection", this conclusion needs to be backed up with more evidence, such as a detailed sediment transport modelling study, based on the prevailing conditions at the proposed cable protection site. |  | We welcome the Applicant's further consideration [REP4-035] of cable protection measure effects on the sediment transport regime at MLS SAC. However, further evidence is needed to support their conclusion that only very minor changes are expected to the sediment transport regime.
2 | B2/B11/B20/B25 | The cumulative impacts to MLS SAC require further consideration. In particular disruption from multiple cable crossings of the 2 VE cables with other plans and projects. And volumetric, extent and distribution changes when considered in-combination with other plans or projects. Noting that existing anthropogenic activities occurring with the SAC have already caused a significant alteration of the sandbanks and are hindering the conservation objectives for the designated site. |  | No change |  | No change. |  | No change. Further detail is needed to show the likely location/proximity and MDS parameters of any proposed VE cable crossings near the SAC. |  | The Applicant has provided additional information in [REP4-035] and [REP4-020] regarding the MDS for cable crossings and their potential locations. However, proximity of cable crossings to MLS SAC and Annex I sandbanks across the study area remains unclear.
3 | B3 | The Maximum Design Scenario (MDS)/Worst-Case Scenario (WCS) for impacts to SPA and SAC supporting habitat, protected habitats and significant bedforms within the arrays has not been sufficiently considered. All aspects of construction such as drill arisings etc., impacts to sandbanks/sandwaves, seabed morphology and prey availability should be considered in more detail. |  | No change |  | Not progressed. |  | Not progressed. |  | Not progressed.
4 | B4/B9 | There is uncertainty regarding the MDS/WCS for volume of sediment disturbed due to cable trenching. Further evidence is required. |  | No change |  | Resolved. The Applicant has confirmed [REP1-051] use of the assumption that up to 100% of material will be fluidised and displaced from the trench. |  | Not resolved. In the MDS Technical Note [REP2-027], Section 2.4.2, the Applicant states that a 50% sediment disturbance has been used for trial trenching (Table 1.6) which seems to contradict [REP1-051]. This needs to be clarified. |  | The Applicant has provided further information in [REP4-035] on the MDS volume of sediment disturbed during trenching. However, it remains unclear whether the MDS is based on the 50% or 100% assumption for material ejected during trenching. Further clarification is needed.
5 | B6 | From the coastal perspective, Scenario 3 (Five Estuaries completes works then North Falls completes works at a later time) should be used as the WCS. |  | No change |  | The Applicant has provided sediment plume modelling results [REP1-057] which coupled with a better understanding of the onshoring works overlap with North Falls has resolved this issue.
6 | B7/B12/B22 | Further information is required to inform landfall MDS including (but not exclusively) anticipated length and location of trenching at landfall. Similarly, any sheet piling and/or an anchored or spud barge for Horizontal directional drilling works. |  | No change |  | No change. Further clarification needed as to whether the sheet piled exit pits could remain open simultaneously for 2.5 years, or backfilled in between opening. |  | No change. Clarification still needed regarding sheet piled exit pits remaining open for 2.5 years. |  | No change.
7 | B8 | Should a coordinated offshore connection with North Falls and Sea Link become a more mature option during examination, this will need to be assessed. Otherwise consideration should be given to how provision for this option at a later date can be included within the DCO to minimise the risk of a material change. |  | No change |  | Not progressed. |  | No change. It is unclear if the coordinated offshore connection remains an option for the project. |  | The Applicant confirmed [REP1-050] that a coordinated offshore connection is no longer being progressed as an option. Therefore, this is no longer an issue.
8 | B10 | WCS for potential morphological impacts to sandbanks and designated areas of seabed (e.g. MLS SAC) during construction should also consider boulder clearance, UXO clearance and pre-lay grapnel run activities as well as dredging. |  | No change |  | Progressed. However, the WCS for seabed level impacts has not been provided. |  | Progressed. The Applicant has now provided the MDS for boulder clearance and pre-lay grapnel run seabed disturbance [REP2-027], which we welcome. However, the MDS overall change in bed level due to the different construction-related activities remains unclear. Seabed level change prediction, including MDS for overall changes, should be presented. |  | In [REP4-040] the Applicant has stated that there is a very low likelihood of a large total area of overlapping measurable local thicknesses of deposition resulting from overlapping plume effects, but it is not practicable to provide more detailed clarification. We advise that the WCS overlapping sediment deposition thickness and extent should be provided, if possible to better understand the scale and signifcance of impacts
9 | B13 | Are the number of array and export cable repairs/replacements over the project lifetime and total impact amounts in Table 1.31 realistic? |  | No change |  | Progressed. However, Applicant to confirm MDS for array and export cable repair seabed disturbance volumes. |  | Our advice at Deadline 3 remains unchanged. |  | The Applicant has provided further rationale [REP4-034] supporting their MDS for array and export cable repair/replacement outside of desingated sites which resolves this issue. However, we advise that if post consent it is identified that a MPA is likely to be affected by these activities, the WCS needs to be established, Affected features, pressures, and sensitivity will need to be identified. It is also important to consult the regulator to determine if a new marine licence will be required.
10 | B14 | The MDS for Array Area drill arising dimensions and distribution of grain sizes/sediment type should be provided and assessed accordingly. |  | No change |  | No change. |  | No change. |  | No change.
11 | B15 | The seabed mobility and erosion potential should be assessed in the EIA. |  | No change |  | No change. Potential changes to bed shear stresses, sediment erosion/deposition potential and site specific bedform mobility/stability have not been considered for the areas impacted by the proposed development. |  | No change. |  | No change.
12 | B16 | SEASTATES hindcast slightly overpredicts some of the significant wave height peaks, but the modelled peak wave period appears to underpredict measured peak wave period for approx. 25% of the time series shown. |  | No change |  | Unless there are significant changes to the project design and/or mitigation measures cannot be delivered, we will not comment again on this during Examination.as we do not believe that updating the modelling and/or assessment would make a material difference to the predicted project impacts at this time.
13 | B17/B18 | Impacts to seabed morphology (i.e. sandwaves) related to changes to the tidal regime due to the presence of Wind Turbine Generator (WTG) and Offshore Platform (OSP) foundation structures should be assessed and significance determined. |  | No change |  | No change – seabed morphology pre-/post construction monitoring should be carried out to ensure no unexpected changes occur. |  | No change. |  | No change.
14 | B19 | Further detail is required to inform the impact assessment for potential changes to Suspended Sediment Concentrations (SSCs), bed levels, and sediment type arising from construction related activities within the Array Areas. |  | No change |  | Progressed. We welcome the additional sediment plume modelling [REP1-057] provided by the Applicant. This has resolved our concerns regarding MDS sediment plume extent and concentrations. However, the MDS overall change in bed level due to the different construction-related activities remains unclear. |  | Our advice at Deadline 3 remains unchanged. |  | No change.
15 | B21 | The present EIA may not be sufficient to determine decommissioning impacts at the end of the OWF lifespan. |  | No change |  | No change. While we advise that this should be considered in the decommissioning programme and are therefore unlikely to provide further comment through examination; we draw your attention to other R&Is where we advise that every effort should be made at the consenting phase to ensure that decommissioning impacts will be minimised as much as possible through project commitments. For example use of appropriate cable protection that is readily removable. |  | We note that the Applicant has provided a technical note on offshore decommissioning [REP2-028], however, its focus is on noise impacts. Therefore, there is no change to our advice. Please see our Deadline 4 response Appendix O4. |  | No change.
16 | B23 | There remains a risk (e.g. climate change impacts) that buried infrastructure within the intertidal may become exposed during the lifetime of the project. |  | No change |  | Progressed. The Applicant [REP1-051] intends to use EA LiDAR data and Anglian Coastal Monitoring Programme data to monitor coastal change. However, this should be secured either in the IPMP or elsewhere. |  | No change. |  | No change.
17 | B24 | Given the large volumes of sediment that could be removed through levelling/bed preparation and detail included within the EIA, sufficient uncertainty remains regarding the recovery potential of sandwaves (and other similar bedforms) in the Array Areas. |  | No change |  | No change. We advise that the Applicant should provide an updated WCS seabed preparation sediment disturbance volume. We also advise monitoring pre- and post-construction to validate predictions of sandwave recovery. |  | No change. |  | No change.
18 | B26 | There are insufficient details regarding the location of the nearshore subtidal laydown areas and their potential impact on seabed morphology to agree with the effect significance conclusion. Furthermore, we do not agree that the coastline is of medium sensitivity/importance. |  | No change |  | Not progressed. Concerns remain regarding changing sediment character at laydown areas which could affect benthic ecology. |  | No change. |  | No change.

## C - Offshore Ornithology
Point | Point Number(s) from Appendix C [PD2-005] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix C - Offshore Ornithology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | C1, C30 | The estimated mortalities and compensation quantum derived for the derogation case for the Alde-Ore Estuary Special Protection Area (AOE SPA) lesser black-backed gull (LBBG) population, using the Natural England preferred approach, appear incorrect. If necessary an updated assessment (including updated PVA) should be conducted. |  | No change |  | Updated but not resolved, the impact assessment has been updated but until we review the documents submitted at Deadline 2 we cannot confirm that the compensation quantum has been correctly calculated. |  | Progressed. The Applicant has addressed some of the errors presented, but the PVAs need to be re-run with burn-in to inform an updated impact assessment. |  | Issue resolved following update to RIAA and PVA document [REP1-017] and [REP1-023].
2 | C2, C13 | PVAs were run without a burn-in period of 5 years as per Natural England best practice advice. |  | No change |  | No change. Please refer to Appendix M2 to our Deadline 3 cover letter. |  | No change. |  | Issue resolved apart from LBBG as issue with PVA tool and data available.
3 | C3, C24 | An assessment of impacts on the Farnes SPA Razorbill population for the project alone during the Operations and Maintenance (O&M) phase and in-combination during all phases of the development should be provided. |  | No change |  | No change. Please refer to Appendix M2 to our Deadline 3 cover letter. |  | No change. |  | Issue resolved as impacts on razorbill were found to be too small.
4 | C4 | Other than for the AOE SPA LBBG population, the Applicant has apportioned adults subject to Habitats Regulations Assessment (HRA) during the breeding season using the generic data presented in Appendix A of Furness (2015), rather than using site-specific data to establish the number of adult- or adult-type birds present. Natural England do not accept the Applicant’s approach to apportioning adults based on theoretical generalised stable age structures. |  | No change |  | No change. |  | No change in the Applicant's position. |  | Apportioning has been presented using our approach and that of the Applicant, although their position is still to use theirs in final analysis.
5 | C5, C32 | The Applicant has applied their preferred displacement (50%) and mortality (1%) rates to the guillemot and razorbill populations at risk at each offshore wind farm (OWF) project included in the in-combination assessment for the Flamborough & Filey Coast Special Protection Area (FFC SPA). This departs from Natural England advice and the in-combination impact estimates used by the Secretary of State (SoS) for recently consented OWFs. We advise the project should simply add the VE project alone impact (at 70% displacement and 2% mortality) to the total in-combination impact agreed in the Sheringham and Dudgeon Extensions Project OWF (SADEP) Examination. |  | No change |  | Progressed but not resolved - outputs for the VE project impact have now been presented at 70% displacement and 2% mortality, and some updates for other projects have been added, but the need to maintain and update the in-combination assessment in the light of additional information on other projects remains a live issue. |  | No change. |  | Issue partially resolved following RIAA [REP1-017]. The Applicant still advocates impacts based on their preferred approach, but has presented these impacts alongside those based on our preferred approach too. Resolution also pending resolution to C15.
6 | C6, C31 | In the PVA for guillemot and razorbill, Natural England welcome the presentation of results for a range of project alone and project in-combination displacement and mortality scenarios, but we would like to see 2% rather than 10% mortality at 70% displacement as the worst-case scenario for these species. |  | No change |  | Resolved. |  | This issue has been resolved so we will not provide further comment on this matter during Examination.
7 | C9 | To mitigate the risk to red-throated diver (RTD), Natural England strongly recommends all vessel activity within the SPA +2km buffer be undertaken outside the seasonal restricted period during the Construction and Decommissioning (C&D) of the export cable (EC), and follow Natural England best practice guidelines on vessel movements during all other phases of the development for both the EC and array. |  | No change |  | No change. |  | No change. |  | No change.
8 | C11 | For lesser black-backed gull the PVA analysis was run and presented for both VE and Natural England preferred scenarios, i.e. either using generic adult proportion data and discounting sabbaticals or using site-specific adult proportions and including sabbaticals, respectively. The Natural England preferred scenarios should be used as the basis of the impact assessment. |  | No change |  | No change. Please refer to Appendix M2 to our Deadline 3 cover letter. |  | No change. |  | No change.
9 | C14 | The Cumulative Effects Assessment (CEA) considers an arbitrary 500km Zone of Influence (ZOI) to scope in other projects for consideration. For offshore ornithology, foraging range is an appropriate tool to screen for impacts to breeding birds, but not outside the breeding season. The approach for non-breeding birds is not given. However, all relevant wind-farms projects have been screened into the CEA. |  | No change |  | Not resolved but changing the ZOI would not make a material difference. Therefore, we will not provide comment on this again through Examination.
10 | C15 | The values used in the in-combination assessment for other English North Sea projects entering the NSIP process in 2024 (Outer Dowsing, Dogger Bank South West and South East, North Falls) are likely to be subject to change through their respective Examinations. The Applicant should work collaboratively with these projects to share updated values in a streamlined way. |  | No change |  | Some updates for other projects currently in Examination have been added, but given the impacts of those projects remain in flux at this stage, the need to update the in-combination assessment remains a live issue. |  | No change - this is an ongoing requirement for the Applicant. |  | An update has been provided for guillemot impacts at Outer Dowsing OWF, but the need to update the in-combination assessment remains a live issue.
11 | C16 | CRM has been undertaken using the deterministic Band model. Uncertainty in flight density has been incorporated by estimating collisions using mean, Upper Confidence Interval (UCI) & Lower Confidence Interval (LCI) density estimates. However, other model parameters have not been varied e.g. flight height, except in the stochastic modelling that was undertaken for those species the Applicant considered at greater risk of collision. |  | No change |  | No change. |  | No change. |  | No change
12 | C17 | EIA CEA impacts on baseline mortality >1% are not modelled using PVA but considered against other OWF PVAs carried out in the southern North Sea e.g. Norfolk Boreas, East Anglia 3 and Hornsea 4. Cumulative impacts on baseline mortality >1% were found for gannet, great black-backed gull, lesser black-backed gull, herring gull, kittiwake, guillemot, and razorbill during the O&M phase as well as on red-throated diver during the C&D and O&M phases. However, the Applicant only reports comparative estimates of counter-factual population size or reduction in population size for gannet, kittiwake and LBBG. NE therefore recommends the cumulative impacts are assessed further using the PVA tool for these species. |  | No change |  | No change. |  | No change. |  | No change.
13 | C18 | The impacts on red-throated diver (RTD) during construction of the EC are stated to be 15 birds per annum (at 100% displacement and 10% mortality) but the impacts from both the array and EC construction is stated as less at 14 birds. The combined impacts must be more or the same but not less than stated for one phase of the work. |  | No change |  | No change |  | No change. |  | No change.
14 | C19 | The draft DCO/dML includes a seasonal restriction, ‘Export cable installation will not be carried out within the Outer Thames Estuary SPA between 1st November to 31st March inclusive to mitigate disturbance impacts on red throated diver’. We welcome this but advise the seasonal restriction should be applied to the OTE SPA and a 2km buffer. |  | No change |  | No Change |  | No Change |  | No change.
15 | C20 | Natural England has already identified significant adverse impacts at the EIA scale to gannet, kittiwake, great black-backed gull, guillemot, razorbill and red-throated diver from OWF in the North Sea, irrespective of whether the Five Estuaries is included in the cumulative totals. The project will therefore be making an additional contribution to those totals. We advise the Applicant review the EIA section of Natural England’s final offshore ornithology advice into the SADEP Examination for further information (REP8-102), and make updates to the CEA as necessary. |  | No change |  | No change. |  | No change. |  | No change
16 | C21 | The sensitivity of red-throated divers to disturbance effects from offshore developments are described in section 4.10.17 but using examples of research that do not illustrate the full scale of the impact, the Applicant’s own review of RTD sensitivity presented in doc. 6.2.4 secs. 4.11.25-4.11.34. |  | No change |  | No change. |  | No change. |  | No change.
17 | C22 | The Applicant downplays the impact on auks caused by OWF induced displacement. There is an established evidence base in support of guillemot displacement from OWFs. While displacement effects on auks remain poorly understood and may prove to be variable, Natural England note a recent study has highlighted the potential for displacement to occur over much greater distances (up to ~20km) than are typically assessed or considered by baseline characterisation surveys (Peschko et al. 2024). |  | No change |  | No change. NE's interpretation of the available evidence remains the same and does not support the applicant's stance. |  | No change. |  | No change.
18 | C23 | Potential transboundary impacts on Alderney’s Ramsar site and the Cote de Granit Rose-Sept Isles have been omitted from the screening process, yet both contain important seabird populations, notably gannet. |  | No change |  | No change. Please refer to Appendix M2 to our Deadline 3 cover letter. |  | No change. |  | No change.
19 | C25 | Impacts predicted during the C&D phase are not presented in matrices for guillemot (GU) and razorbill (RA) at the Farnes SPA, and for gannet (GX), GU and RA at the FFC SPA. As noted above, impacts predicted during the O&M phase are not presented in a matrix for RA at the Farnes SPA. |  | No change |  | Progressed - all requested matrices have been presented except those for razorbill at Farnes SPA during both C&D and O&M phases. See point 3 above for reason why NE request an impact assessment on razorbill at Farnes SPA. |  | No change. |  | Resolved. Although displacement data not presented, at the Farnes SPA the predicted impacts on razorbill from displacement were estimated to be 0% as per the revised RIAA, Table 6.1, pg.111.
20 | C27 | Natural England does not agree with the Applicant’s process for adult apportioning subject to HRA, notably the breeding population of gannets at the FFC SPA. |  | No change |  | Resolved. |  | This issue has been resolved so we will not provide further comment on this matter during Examination.
21 | C28 | Natural England acknowledges that sabbaticals are an important consideration for improving impact estimates and represent a knowledge gap. However, at present we do not believe that simply removing them from assessments during apportioning is appropriate. |  | No change |  | No change. Please refer to Appendix M2 to our Deadline 3 cover letter. |  | No change in the Applicant's position. |  | No change in the Applicant's position.
22 | C29 | Natural England are not persuaded that a sabbatical rate of 35% can be considered either relevant or precautionary, therefore the Applicant should cite the research used so it can be appraised. |  | No change |  | No change. Please refer to Appendix M2 to our Deadline 3 cover letter. |  | No change in the Applicant's position. |  | No change in the Applicant's position.
23 | C33 | In the CRM for migratory waterbirds all species assessed were assumed to fly at rotor height at a precautionary 100% of the time except dark-bellied Brent goose. Brent geese were assessed instead at the less precautionary rate of 50% but a clear evidence-based reason was not given. |  | No change |  | No change |  | No change. |  | No change.
24 | C34 | In the RTD assessment, the Furness (2015) migration free winter bio-season is used (i.e. impacts are only estimated for December and January), rather than October to May. |  | No change |  | No change but if the seasonal restriction can be secured then impacts will be mitigated adequately (albeit some residual disturbance could occur in the shoulder months of October and May) |  | No change. |  | No change.
25 | C36 | The Applicant notes that some of the operating OWF were not built to full capacity and that their predicted impacts would be less in reality than stated, thereby providing some ‘headroom’ in the in-combination assessment. At present Natural England do not consider it appropriate to reduce impact estimates by considering as-built parameters unless those parameters are legally secured. |  | No change |  | No change. |  | No change. |  | No change.
26 | C37 | The Applicant’s review points out that guillemot displacement rates may be reduced during the breeding bio-season by ~20% compared with the non-breeding bioseason. While Natural England do not disagree that auk displacement rates appear to be reduced for breeding birds in the breeding season, we note that the Applicant is only assessing displacement of auks in the non-breeding season. |  | No change |  | No change. |  | No change. |  | No change.
27 | C38 | The RIAA reports that 40% of lesser black-backed gull were apportioned to the AOE SPA yet the Apportioning Note presents two different figures in the text e.g. sec. 2.2.23, 40%, and Table 2.5, 35.5%. This should be clarified. |  | No change |  | Resolved. |  | This issue has been resolved so we will not provide further comment on this matter during Examination.
28 | C39 | The Applicant states that for auk species “Potential LSE for migratory birds has been ruled out as they do not forage or roost in the array area and only transit through the area during migration” but does not evidence this statement. |  | No change |  | No change |  | No change. |  | No change.
29 | C40 | Post-consent monitoring is focused entirely on compensatory measures. Post-consent monitoring of the OWF could help clarify the key risks such as those posed to LBBG from collision, but no monitoring of this sort is proposed. |  | No change |  | No change |  | No change. |  | No change.
30 | C41 | We are unable to agree the effects of the project on some species subject to HRA. Clarification is required on the scale of impacts on the guillemot and razorbill populations breeding at the Farnes and FFC SPAs, the kittiwake and gannet populations at the FFC SPA and the lesser black-backed gull population at the AOE SPA. Until this is resolved we are unable to agree the scale of compensation required to off-set the losses predicted for these species. |  | No change |  | No change. Impacts on razorbill at the Farnes SPA are not presented, whilst these and impacts on other key species need assessing via PVAs with burn in before we can agree likely outcomes and any compensation necessary. |  | No change in the Applicant's position. We highlight the need for the Applicant to present impact values (and a compensation quantum) based on the upper NAF value for FFC SPA kittiwake. |  | Progressed but not resolved. Impacts have been presented appropriately but the scale of compensation required needs to be agreed based on our preferred approach.

## D - Ornithology Compensation
Point | Point Number(s) from Appendix D [PD2-006] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix D - Ornithology Compensation | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | D2 | We are broadly supportive of the proposal to provide compensation for impacts on guillemot and razorbill through reduction of disturbance at small colonies in south-west England, but highlight it will require significant amounts of on-site monitoring and engagement with local experts to establish a baseline for the current level of disturbance and potential impact on colony productivity at any given site, and to establish what measures might effectively mitigate any disturbance occurring. |  | No change |  | No change but we will be responding to updated information at deadline 4. |  | No change. |  | No change - awaiting an updated Implementation and Monitoring Plan (IMP).
2 | D3, D5 | Natural England consider the disturbance reduction measure to be technically feasible. However, the Applicant has not yet demonstrated whether sites can be easily observed or monitored in sufficient detail to establish annual counts and productivity estimates which can serve as a baseline for management interventions. Communication with landowners and stakeholders is still ongoing and it remains unclear how many sites will be able to participate. |  | No change |  | Progressed but not resolved - please see Appendix M2 for more information. |  | Further progress made, but still not resolved. |  | No change awaiting an updated IMP and further information.
3 | D4 | Impact levels are not yet agreed but are expected to result in a modest contribution to the in-combination total. For previous auk compensation cases Natural England has advised the use of 70% displacement and 2% mortality for establishing requirements, and advise these values be used for scaling requirements. |  | No change |  | Progressed. Need to confirm that these values have been included in the compensation documents before this issue can be resolved. |  | Progressed but not resolved. The Applicant has presented displacement/mortality values according to our approach, but still continue to advocate their own displacement levels are used for scaling the compensation. |  | No change.
4 | D7 | Candidate locations have been identified but are not yet secured, though negotiations are under way. Without secured agreement with the relevant landowners and stakeholder willingness to participate, there remains the risk that the project will not deliver. |  | No change |  | No change but we will be responding to updated information at deadline 4. |  | No change. |  | No change - awaiting an updated IMP.
5 | D8, D9 | Monitoring will be required for all stages of the proposed management programme to identify trends accurately. Stakeholder engagement will also need to be upheld throughout the project to ensure all new participants are aware of the issues. The level of monitoring needed to identify suitable set-back distances and gather as much data as possible on nest failure will require suitably skilled observer(s). |  | No change |  | No change but we will be responding to updated information at deadline 4. |  | Progressed but not resolved. Whilst broad descriptions of monitoring methods have been given, further approaches to gathering data on populations and productivity need investigating. |  | No change - awaiting an updated IMP.
6 | D10 | The proposal has potential as a sole measure given the likely scale of impact. The proposal would also benefit from the Applicant working alongside recreational stakeholders and the local authority. We also recommend, as a minimum, using signage in conjunction with public engagement to help deliver an effective code of conduct. We note and support the option of a collaborative approach between multiple developers. |  | No change |  | No change but we will be responding to updated information at deadline 4. |  | No change. We need to see reassurance from stakeholders, landowners etc of their participation in the measure. |  | No change - awaiting an updated IMP.
7 | D11 | Adaptive management will not be adopted should other pressures such as impacts associated with climate change (e.g. extreme weather events) negatively impact the compensation delivery. However, adaptive management could be crucial to help restore and build resilience in the local auk population in the face of change. |  | No change |  | No change but we will be responding to updated information at deadline 4. |  | No change. |  | No change.
8 | D12,D13, D17, D21, D22 | There is uncertainty regarding collaboration and agreement between VE and Dogger Bank South (DBS) OWF with regards to sharing the ANS. Further uncertainty exists as to whether sufficient numbers of birds (a) will occupy the RWE ANS and (b) depending on how the measure is allocated, whether sufficient birds can be allocated to VE. To safeguard delivery of the compensation, the alternative option to support Defra’s Marine Recovery Fund for an offshore ANS should be retained in the meantime. |  | No change |  | No change but we will be responding to updated information at deadline 4. |  | Resolved.
9 | D15 | Natural England advise that the compensation requirement should be scaled up to the 95% UCI impact value and not be based on the central impact value. |  | No change |  | No change but we will be responding to updated information at deadline 4. |  | Progressed but not resolved. The Applicant has presented mortality estimates according to our approach, but still continue to advocate their own are appropriate and applied to compensation. |  | No change - awaiting an updated IMP.
10 | D25.0 | Adequate evidence has been provided to demonstrate technical feasibility for VE02, although without further data gathering and impact assessment as regards the impacts of the predator fence, we are not in a position to advise that impacts on the Orford Ness – Shingle Street SAC and Alde-Ore Estuary Ramsar site and SSSI will be adequately mitigated. |  | No change |  | No change but we will be responding to updated information at deadline 4. |  | No change. Requires robust appropriate baseline information to support assessment conclusions. See also our comments in Appendix J4 to this Deadline 4 submission. |  | No change. The Applicant has carried out vegetation and invertebrate surveys at Orford Ness [REP4-042], however, these do not overlap with the proposed compensation site. Therefore, the baseline remains incomplete. Please see also our comments in the Cover Letter to our Deadline 5 submission.
11 | D25.5 | As regards OTB, techniques for predator control and vegetation management are well established. However, OTB is a challenging site to access and sits in an area of high environmental sensitivity (The Wash SPA, SSSI and the Wash and North Norfolk Coast SAC). An appropriate access methodology and schedule for management has not been presented, and we consider an outline approach reflecting the above challenges should be submitted into the Examination in due course. |  | No change |  | No change but we will be responding to updated information at deadline 4. |  | Potential solutions are available, but have yet to be finalised and secured. |  | No change.
12 | D26 | The compensation level has not been agreed yet as per our Relevant Representations (Appendix C). Natural England is therefore unable to agree the number of additional breeding pairs required to achieve compensation. Furthermore, it is Natural England’s advice that for compensation the requirement should be scaled up to the 95% UCI and not the central impact value. |  | No change |  | No change but we will be responding to updated information at deadline 4. |  | Progressed but not resolved. The Applicant has presented mortality estimates according to our approach but still continue to advocate their own are appropriate and used to scale the compensation measure. |  | No change.
13 | D27 | Once the scale of impacts on the LBBG AOE SPA population have been agreed, the adequacy of the proposed level of compensation can be assessed. Proposals presented so far suggest this is likely to be the case should both the AOE SPA and OTB measures are progressed, once the number of predicted annual losses have been finalised and compensation is delivered at a ratio of 3:1. |  | No change |  | No change but we will be responding to updated information at deadline 4. |  | No change. |  | No change.
14 | D28.0, D32 | The proposal to protect a site within the AOE SPA using predator proof fence will rely on the birds finding and occupying the site. There is a risk that the birds may be reluctant to nest on the ground such that the site remains unused or only occupied several years after the fence has been erected. The proposal may, therefore, rely heavily on the Outer Trial Bank site to deliver the additional compensation for the interim losses (at least until the fenced site becomes active). As such, Natural England recommends that both proposals are undertaken to reduce the risk – providing resilience should one site fail to deliver. |  | No change |  | No change but we will be responding to updated information at deadline 4. |  | A two-site, two-project solution has been suggested but not yet agreed with the Applicant. |  | No change. Applicant is preferring one site solution.
15 | D28.5 | We advise the fence be erected 4 years in advance of the operational phase to extend the lead in time as much as possible – noting this schedule was required and achieved by the Norfolk projects. |  | No change |  | No change but we will be responding to updated information at deadline 4. |  | No change. |  | No change.
16 | D29 | As negotiations with landowners at both sites remain on-going, there is currently uncertainty whether or not either site can be secured for the lifetime of the project. Within the AOE SPA, the onshore ecology may also affect the location of the proposed predator-proof fencing. |  | No change |  | No change but we will be responding to updated information at deadline 4. |  | Recent landowner correspondence indicates significant concerns regarding the availabilty of the proposed compensation location at Orfordness. |  | No change. Awaiting updates.
17 | D30.0 | For the predator-proof fencing proposal in the AOE SPA, no schedule for fence maintenance and checks has been provided or details about how this will be done and by whom. Fence maintenance will be crucial to prevent predator incursions and a key component of on-going management throughout the year. Plans will also need to be in place to address fence breaches so these can be resolved quickly. |  | No change |  | No change but we will be responding to updated information at deadline 4. |  | No new information. No change. |  | No new information. No change.
18 | D30.5 | For the proposal at Outer Trial Bank, workable plans for monitoring and biosecurity will need to be in place. |  | No change |  | No change but we will be responding to updated information at deadline 4. |  | No change. |  | No change.

## E - Benthic Ecology
Point | Point Number(s) from Appendix E [PD2-007] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix E - Benthic and Intertidal Ecology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | E1/E7 | Further quantification of design parameters and impacts are required to address uncertainties with the Maximum Design Scenario (MDS) for cable protection within Margate and Long Sands Special Area of Conservation (MLS SAC) and inform compensatory requirements |  | No change |  | No change. |  | No change. Inconsistencies remain in the MDS between the [REP2-027] and [REP2-021]. |  | No change. Whilst the Applicant has provided an updated Technical Note - Methodology for Determining MDS (Offshore) Rev B [REP4-034], the MDS/WCS for cable protection is still not clear. This should be clarified and all relevant documents updated. Please also see our response to the ExA benthic ecology Rule 17 Letter submitted at Deadline 5.
2 | E2/E18 | Further assessment and justification re. pressures/impacts on supporting benthic habitats for Special Protection Area (SPA) features is required. In particular the Outer Thames Estuary SPA (OTE SPA) Red-throated diver populations which are present in the project red line boundary and vessel transit route from several local ports which may locate the projects O&M facility. |  | No change |  | No change |  | No change. No updates have been made to the RIAA in relation pressures/impacts on SPA feature supporting habitat |  | No change.
3 | E3/E6/E7/E24/E27 | The application documents, including the Report to Inform Appropriate Assessment (RIAA) provide contradictory information relating to the likely requirement for ‘additional’ scour and/or cable protection over and above that stipulated within the maximum design. |  | No change |  | No change |  | No change. No updates to the RIAA have been made in this respect. It is still not clear whether the potential for the addition of further rock protection due to secondary scour over the lifetime of the project has been considered and included within the calculations for the MDS/WCS for scour protection within the SAC. It is therefore still uncertain whether the RIAA appropriately considers the MDS/WCS. |  | No change.
4 | E4/E20 | Natural England does not agree with the Applicant’s conclusion of No AEoI in relation to MLS SAC which has been designated for Annex I Sandbanks. |  | No change |  | No change |  | No change. |  | No change.
5 | E5/E37 | Mitigation measures for the potential presence of Section 41 Natural Environment and Rural Communities (NERC) Act 2006 Habitats are not sufficiently included. Including A4.231 Piddocks with a sparse associated fauna in sublittoral very soft chalk or clay. |  | No change |  | In progress: We will provide further comments at D4 once the MLS SAC mitigation has been reviewed. |  | No Change: While consideration to priority habitats has been included in the MLS SAC mitigation measures [REP2-021]. This doesn't consider mitigation of Priority Habitats outside of the designated site and no commitments to avoid and/or minimise impacts are made and/or secured within MLS SAC. Please see our Deadline 4 response Appendix E4 |  | No change.
6 | E8 | Further detail and updated assessments are required to determine if the WCS is realistic. |  | No change |  | No change (there are inconsistencies in MDS between the [REP2-027] 10.20.1 Technical note - Methodology for Determining MDS (Offshore) and the [REP2-021] 9.13 Margate and Long Sands Special Area of Conservation Benthic Mitigation Plan - Revision B (Tracked) i.e. 900 m per cable vs 900 m in total) |  | No change. Multiple aspects of NE's Rel Reps advice have not been addressed. There are also inconsistencies in the MDS values - see comment above. |  | No change. Whilst the Applicant has provided an updated Technical Note - Methodology for Determining MDS (Offshore) Rev B [REP4-034], the MDS/WCS for cable protection is still not clear. This should be clarified and all relevant documents updated. Please also see our response to the ExA benthic ecology Rule 17 Letter submitted at Deadline 5.
7 | E9/E11/E12 | Parameters to determine the dredge disposal criteria and/or mitigation for EIA and HRA issues, other than within the same sediment type have not been included. |  | No change |  | No change. |  | No change. No further mitigation has been committed to in relation to dredge disposal criteria. |  | This will be updated at Deadline 6.
8 | E10 | The evidence to support VE disposal activities includes those permitted and assessed in 2008 which can no longer be relied upon. |  | No change |  | No change. |  | Progressed. The Sediment Plume Modelling results echo the earlier spreadsheet-based model results for disposal activities. However, we still need clarification regarding the overall MDS for sediment deposition due to multiple or overlapping construction activities. |  | This will be updated at Deadline 6.
9 | E13/E30 | Further mitigation measures should be adopted to differentiate between areas inside and outside of designated sites unless a precautionary approach is taken to all installation and operation activities within the assessment. |  | No change |  | In progress: We will provide further comments at Deadline 4 once the MLS SAC mitigation has been reviewed. |  | Not progressed. No additional detail has been included within the updated/new documents to have certainty that cables can be buried. |  | No change.
10 | E17 | Natural England is concerned that there is a risk of impacting potential Annex I reef features located within MLS SAC and as a NERC (2006) Section 41 Priority Habitats. |  | No change |  | Progressed - issues preventing resolution is that cable protection commitments remain limited to within fisheries byelaw areas, we would want these extended to entire SAC |  | No Change. |  | No change.
11 | E19 | The Applicant has ruled out the option to adopt High Voltage Direct Current (HVDC) within the Export Cable Corridor (ECC) to mitigate impacts on sandbank features, which would reduce the number of cables |  | No change |  | No change |  | No change. |  | No change.
12 | E23 | The updated Renewable Energy National Policy Statement has not been taken into consideration and neither has the updated Defra Policy to support Best Practice Guidance for benthic compensation in MPAs |  | No change |  | No Change |  | No change. |  | No change.
13 | E25 | Further details on Operation and Maintenance activities preferably included within an outline plan are required to inform the RIAA |  | No change |  | No change |  | No change. |  | No change.
14 | E26 | Within the RIAA there is limited linkage to the conservation objectives for MLS SAC. |  | No change |  | No change |  | No change. |  | No change.
15 | E28 | Benthic compensatory requirements for other projects should consider all projects including Dudgeon and Sheringham Extension Projects OWFs which have impacts similar to VE. |  | No change |  | No change |  | No change. SEPDEP is not mentioned in the RIAA. |  | No change.
16 | E29 | The in-combination TIERs do not align with best practice guidance and therefore do on take account of ongoing impacts from some projects. |  | No change |  | Progressed: Whilst Tier description updates have been provided, the projects considered in each tier don't appear to have changed. |  | No Change. |  | Our advice will be updated at Deadline 6.
17 | E31 | The following need further consideration in the table: UXO clearance impacts along cable route on benthic receptors. Potential need for cable protection at the HDD exit pits. Details of each cable repair rather than as a collective. |  | No change |  | No change |  | No change. The benthic chapter has not been updated. |  | No change.
18 | E32 | MLS SAC sandbank feature extends beyond the site boundary and therefore impacts from outside the site might have indirect impacts to the SAC. |  | No change |  | No change |  | No change. |  | No change.
19 | E33 | The RIAA does not fully consider the sediment deposition from sandwave levelling to ensure that deposition is in the same sediment type. |  | No change |  | No change |  | No change. |  | Our advice will be updated at Deadline 6.
20 | E34 | We disagree with RIAA where impacts are argued as small. |  | No change |  | No change |  | No change. |  | No change.
21 | E35/36 | It is not clear what ‘benchmarks’ the Applicant is referring to reached conclusions of no AEoI, or what evidence is being used to support the conclusions of insignificant effects. But any placement of cable protection and associated changes to physical processes and benthic communities could constitute a lasting impact over the lifetime of the project which is potentially irreversible. Natural England therefore disagrees with the Applicants conclusion and consider that an AEoI cannot be ruled out based on the evidence presented. |  | No change |  | Progressed: Natural England notes that the Applicant is referring to MarESA benchmarks. However, benchmarks refer to single discrete events, not repeated and/or ongoing events over the lifetime of the project. Therefore, there remains a requirement on the Applicant to clarify whether the impacts being assessed against the benchmarks are single discrete events, or otherwise and further justify their position. |  | No Change. |  | No change.
22 | E38 | The EIA fails to describe how elevation of Sabellaria spinulosa tube structures has been measured in order to inform the ‘reefiness’ assessment. |  | No change |  | No change |  | No change. |  | No change.
23 | E39 | The priority Habitats as listed under Section 41 of the NERC Act 2006 have not been appropriately considered within the EIA, or the Offshore In-Principle Monitoring Plan. This is particularly relevant for issue E37 regarding impact to piddocks, peat and clay. |  | No change |  | Progressed but not resolved as there is no firm commitment to avoid and inclusion of a decision tree to minimise impacts where avoidance is not possible |  | No change. All Section 41 Habitats should be included within the In-Principal Monitoring Plan so that impacts on these habitats, particularly those that are irreplaceable (i.e. Boring Piddock communities), can be avoided and reduced. |  | No change.

## F - Benthic Compensation
Point | Point Number(s) from Appendix F [PD2-008] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix F - Benthic Compensation | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | F3/F13/F33 | The presented Worse Case Scenario (WCS) of lasting habitat loss/change of Annex I Sandbanks within Margate and Long Sands (MLS) SAC is not agreed. And is relevant to all compensation measures. |  | No change |  | No change |  | No Change |  | No change.
2 | F3 | Due to potential uncertainties with the delivery mechanisms for strategic benthic compensation and timeframes for successful delivery of the measure, further discussions (outside of individual project examinations) are required to determine individual project contributions and compensatory ratios. |  | We will provide no further comment in examination and all queries should be addressed to DEFRA. Please see response on EXQ ME.1.10 in Appendix M1 of our Deadline 2 submission. |  | No change
3 | F4 | There are outstanding concerns in relation to the outcomes of the Impact Assessment and evidence used to support conclusions on scale and significance of potential impacts from cable installation activities and the placement of cable protection from Five Estuaries. Until these issues are resolved the scale and extent of the compensation measures required are not agreed. And this is relevant to all compensation measures. |  | No change |  | No change |  | In Progress: There has been further information provided by the Applicant but insufficient to agree the scale and signficance of the impacts to be compensated for. |  | No change.
4 | F4 | As set out in the R4 plan level compensation document, the designation of a new site or existing site extension will be led on by a team in DEFRA in collaboration with interested parties therefore delivery mechanisms, costs and timeframes presented by the Applicant cannot and should not be relied upon. |  | We will provide no further comment in examination and all queries should be addressed to DEFRA. Please see response on EXQ ME.1.10 in Appendix M1 of our Deadline 2 submission. |  | No change
5 | F5 | There are likely to be time lags between impact occurring and strategic compensation achieving the desired outcomes. In this scenario, the project contribution to the measure should be such that it ensures an overall environmental net positive outcome for the impacted feature over the lifetime of the project. |  | No change |  | No change |  | No Change: We advise that once DEFRA's guidance on, and assurances in relation to the delivery of strategic benthic compensation (including timings etc.) become available, every effort is made by the Applicant to update the examination on Five Estuaries commitments to Strategic Benthic Compensation measures i.e. Marine Protected Area designation/extension |  | No change.
6 | F6,F7,F8 | For strategic compensation the location, long term implementation and success criteria/ability to prove additionality will be determined by DEFRA, in consultation with Natural England and JNCC. This is still under consideration and nothing has been agreed and/or secured. |  | No change |  | No change
7 | F10 | Limited geotechnical and geophysical survey data has been presented with the Cable Burial Risk Assessment [APP-238] and the Cable Specification and Installation Plan [APP- 239] to have confidence that the cables can be buried to optimum cable burial depth. In addition, there is limited consideration of the highly dynamic sediment transport/marine processes within MLS SAC which may have implications for cable burial over the lifetime of the project. Therefore, the WCS presented for cable protection within MLS SAC may not be realistic. |  | No change |  | No change |  | No Change |  | No change.
8 | F11 | Under removal of redundant infrastructure Five Estuaries' focus is on the removal of disused telecommunications ‘telecom’ cables. But there is no evidence that redundant telecoms cables are causing a significant impact on the Annex I Sandbank feature of the MLS SAC or other benthic designated sites. Unless further supportive detailed evidence is provided, Natural England does not consider their removal to constitute suitable compensation as a sole benthic compensation measure. |  | No change |  | No change |  | Our advice provided at Relevant Representations remains unchanged. However, we do not believe that there is merit in progressing and/or placing reliance upon project specific benthic compensation measures, namely Anthropogenic Pressure removal (Redundant infrastructure or aggregates) and Sea Grass Habitat Creation/Restoration. |  | Please see our earlier advice which remains unchanged.
9 | F12/F18/F20 | If further evidence is presented in support of telecoms removal as a compensation measure, and this is to be progressed, then commitments with the cable owners will need to be secured. |  | No change |  | No change |  | Our advice provided at Relevant Representations remains unchanged. However, we do not believe that there is merit in progressing and/or placing reliance upon project specific benthic compensation measures, namely Anthropogenic Pressure removal (Redundant infrastructure or aggregates) and Sea Grass Habitat Creation/Restoration. |  | Please see our earlier advice which remains unchanged.
10 | F16 | The location of any redundant telecom cables to be removed has not been presented in detail and/or agreed with the SNCBs. |  | No change |  | No change |  | Our advice provided at Relevant Representations remains unchanged. However, we do not believe that there is merit in progressing and/or placing reliance upon project specific benthic compensation measures, namely Anthropogenic Pressure removal (Redundant infrastructure or aggregates) and Sea Grass Habitat Creation/Restoration. |  | Please see our earlier advice which remains unchanged.
11 | F17 | In order to provide the Secretary of State with the necessary comfort that removal of redundant infrastructure as a compensation measure is sufficiently progressed during the consenting phase, this should be set out in more detail. However, it is anticipated that as the examination progresses that this measure is either more thoroughly progressed or removed as an option if not. |  | No change |  | No change |  | Our advice provided at Relevant Representations remains unchanged. However, we do not believe that there is merit in progressing and/or placing reliance upon project specific benthic compensation measures, namely Anthropogenic Pressure removal (Redundant infrastructure or aggregates) and Sea Grass Habitat Creation/Restoration. |  | Please see our earlier advice which remains unchanged.
12 | F19 | While removal of redundant infrastructure could be progressed as a sole measure it remains unclear if there are sufficient surface laid/exposed telecom cables on Annex I sandbanks to fully mitigate the potential project impacts. However, this proposal could be progressed as part of a package if not. |  | No change |  | No change |  | Our advice provided at Relevant Representations remains unchanged. However, we do not believe that there is merit in progressing and/or placing reliance upon project specific benthic compensation measures, namely Anthropogenic Pressure removal (Redundant infrastructure or aggregates) and Sea Grass Habitat Creation/Restoration. |  | Please see our earlier advice which remains unchanged.
13 | F21 | Percentage buyout of aggregate licence(s) as a compensation measure for Annex I sandbank would reduce existing pressures on Annex I sandbanks. If this is progressed further detail should be provided of any agreements with Aggregates industry where this measure has potential. |  | No change |  | No change |  | Our advice provided at Relevant Representations remains unchanged. However, we do not believe that there is merit in progressing and/or placing reliance upon project specific benthic compensation measures, namely Anthropogenic Pressure removal (Redundant infrastructure or aggregates) and Sea Grass Habitat Creation/Restoration. |  | Please see our earlier advice which remains unchanged.
14 | F22 | Whilst technically feasible as there are active Aggregate licences within the National Site Network which interact with Annex I sandbank, there is currently no certainty that this measure can be secured. |  | No change |  | No change |  | Our advice provided at Relevant Representations remains unchanged. However, we do not believe that there is merit in progressing and/or placing reliance upon project specific benthic compensation measures, namely Anthropogenic Pressure removal (Redundant infrastructure or aggregates) and Sea Grass Habitat Creation/Restoration. |  | Please see our earlier advice which remains unchanged.
15 | F24 | The location, long term implementation and success criteria/ability to prove additionality of percentage removal of aggregates extraction has not been presented in detail and/or agreed with the SNCBs. |  | No change |  | No change |  | Our advice provided at Relevant Representations remains unchanged. However, we do not believe that there is merit in progressing and/or placing reliance upon project specific benthic compensation measures, namely Anthropogenic Pressure removal (Redundant infrastructure or aggregates) and Sea Grass Habitat Creation/Restoration. |  | Please see our earlier advice which remains unchanged.
16 | F25,F26 | It is unclear if removal of aggregates can be delivered prior to the impacts occurring. |  | No change |  | No change |  | Our advice provided at Relevant Representations remains unchanged. However, we do not believe that there is merit in progressing and/or placing reliance upon project specific benthic compensation measures, namely Anthropogenic Pressure removal (Redundant infrastructure or aggregates) and Sea Grass Habitat Creation/Restoration. |  | Please see our earlier advice which remains unchanged.
17 | F27 | In order to provide the Secretary of State with the necessary comfort that percentage removal of aggregates extraction as a compensation measure is sufficiently progressed during the consenting phase, this should be set out in more detail. It is anticipated that as the examination progresses that this measure is either more thoroughly progressed or removed as an option if not. |  | No change |  | No change |  | Our advice provided at Relevant Representations remains unchanged. However, we do not believe that there is merit in progressing and/or placing reliance upon project specific benthic compensation measures, namely Anthropogenic Pressure removal (Redundant infrastructure or aggregates) and Sea Grass Habitat Creation/Restoration. |  | Please see our earlier advice which remains unchanged.
18 | F29 | While the buyout of Aggregate licences could be progressed, it remains unclear if there are any options open to the Applicant to deliver this measure either as a sole measure or as part of a package. |  | No change |  | No change |  | Our advice provided at Relevant Representations remains unchanged. However, we do not believe that there is merit in progressing and/or placing reliance upon project specific benthic compensation measures, namely Anthropogenic Pressure removal (Redundant infrastructure or aggregates) and Sea Grass Habitat Creation/Restoration. |  | Please see our earlier advice which remains unchanged.
19 | F31 | Seagrass restoration is a lower preference measure compared to those supporting the same ecological function of the habitat being compensated for. Subtidal seagrass has not been found within MLS SAC. |  | No change |  | No change |  | Our advice provided at Relevant Representations remains unchanged. However, we do not believe that there is merit in progressing and/or placing reliance upon project specific benthic compensation measures, namely Anthropogenic Pressure removal (Redundant infrastructure or aggregates) and Sea Grass Habitat Creation/Restoration. |  | Please see our earlier advice which remains unchanged.
20 | F32 | There have been no long term successes (even on a small scale) with seagrass restoration in the UK. Seagrass restoration is included as a potential measure only where it would be a minor part of a wider package in terms of the required compensation. Given the intention to compensate for Annex I sandbank habitat, which is, by definition, a subtidal habitat, seagrass restoration for the purpose of compensation shall be limited to subtidal seagrass. The measure could supplement other measures, or potentially as an adaptive management response. |  | No change |  | No change |  | Our advice provided at Relevant Representations remains unchanged. However, we do not believe that there is merit in progressing and/or placing reliance upon project specific benthic compensation measures, namely Anthropogenic Pressure removal (Redundant infrastructure or aggregates) and Sea Grass Habitat Creation/Restoration. |  | Please see our earlier advice which remains unchanged.
21 | F35 | It is unclear if seagrass restoration can be delivered prior to the impacts occurring. |  | No change |  | No change |  | Our advice provided at Relevant Representations remains unchanged. However, we do not believe that there is merit in progressing and/or placing reliance upon project specific benthic compensation measures, namely Anthropogenic Pressure removal (Redundant infrastructure or aggregates) and Sea Grass Habitat Creation/Restoration. |  | Please see our earlier advice which remains unchanged.
22 | F36 | The location, long term implementation and success criteria/ability to prove additionality of seagrass restoration has not been presented in detail and/or agreed with the SNCBs. |  | No change |  | No change |  | Our advice provided at Relevant Representations remains unchanged. However, we do not believe that there is merit in progressing and/or placing reliance upon project specific benthic compensation measures, namely Anthropogenic Pressure removal (Redundant infrastructure or aggregates) and Sea Grass Habitat Creation/Restoration. |  | Please see our earlier advice which remains unchanged.
23 | F37-F40 | In order to provide the Secretary of State with the necessary comfort that seagrass restoration as a compensation measure is sufficiently progressed during the consenting phase, this should be set out in more detail. It is anticipated that as the examination progresses that this measure is either more thoroughly progressed addressing all information gaps or removed as an option if not. |  | No change |  | No change |  | Our advice provided at Relevant Representations remains unchanged. However, we do not believe that there is merit in progressing and/or placing reliance upon project specific benthic compensation measures, namely Anthropogenic Pressure removal (Redundant infrastructure or aggregates) and Sea Grass Habitat Creation/Restoration. |  | Please see our earlier advice which remains unchanged.
24 | F41 | More substantive consideration of ‘Alternatives’ is required to ensure that the Alternatives Test can be met. |  | No change |  | No change |  | No Change: Natural England is unsure if a coordinated transmission with North Falls is being progressed. |  | No change. However, we note that the Applicant has confirmed [REP1-050] that they are no longer pursuing a coordinated offshore connection with North Falls OWF and Sea Link interconnector as an option.
25 | F42 | There needs to be more transparency over the project lifetime impacts and not just a focus on the Application and Examination. |  | No change |  | No change |  | Our advice provided at Relevant Representations remains unchanged. However, this point becomes irrelevant if project specific benthic compensation is not progressed. |  | Please see our earlier advice which remains unchanged.
26 | F43 | The conservation advice package for Margate and Long Sands SAC is in the process of being updated. With draft updates being published in Autumn 2024 and finalisation in March 2025. Within these updates there is relevant context on existing impacts to the site to help inform the in-combination assessments. |  | No change |  | No change |  | Natural England will update at Deadline 5 on progress toward publication of an updated condition assessment for MLS SAC. However, it is now unlikely that conservation advice will be updated within the examination timeframes. |  | Natural England aims to update the condition assessment and having it publicly viewable on their Designated Sites system by the end of January 2025.
27 | F44 | It is unclear how the Applicant has determined that sandbank recovery will occur within a few months following sandwave levelling. |  | No change |  | No change |  | No Change |  | No change.
28 | F45 | Further geotechnical data is required pre-determination to inform the likelihood of cables being buried and thus the need for cable protection and therefore compensation. |  | No change |  | No change |  | No Change |  | No change.
29 | F46 | Cable Protection: Natural England advises across all documents that further detail is required on cable protection parameters during installation and project lifetime, before we can have any certainty on the proposed 5,400m2 |  | No change |  | No change |  | No change |  | No change.
30 | F47 | It is not agreed that compensation discussions should be deferred until it is determined post installation that it is definitely required. |  | No change |  | No change |  | No change |  | No change.
31 | F48 | Further consideration should be given to the implementation of mitigation hierarchy to reduce impacts as much as possible. |  | No change |  | No change |  | No Change |  | No change.
32 | F49 | Information taken from other projects examination document often refers to mitigation not necessarily compensation. And does not align with final positions and therefore should not be relied upon. |  | We will not be providing further comments on this during Examination.
33 | F50 | APP-048 the Outline BIMP is presented as a skeleton document of what will be included post consent. Therefore, we are unable to provide comment at this time on its content. In addition it is not clear if the progression of a BIMP is the most appropriate approach if Strategic Compensation is taken forward. |  | No change |  | No change |  | No change |  | No change.

## G - Fish Ecology
Point | Point Number(s) from Appendix G [PD2-009] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix G - Fish and Shellfish Ecology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | G1 | It is not clear whether conclusions of magnitude are based on the modelling of fish as either stationary or fleeing receptors. |  | No change |  | No change |  | Resolved. In [REP1-051], the Applicant has clarified that magnitude conclusions are based on a receptor-by-receptor basis. For spawning herring, sandeel, and seahorses, with regards to UWN impacts, they have been assessed as stationary.
2 | G2 | We welcome the implementation of additional mitigation measures, provided that these mitigations are secured through appropriate conditions on any consent issued. However, we defer to Cefas in regard to the appropriateness of these mitigation measures and associated buffers. |  | No change |  | No change |  | Discussions ongoing. |  | No change.
3 | G3 | In relation to spawning herring, we do not agree that the sensitivity of spawning herring to noise impacts would be medium during the construction phase of the Project. |  | No change |  | No change |  | No change. |  | No change.
4 | G4 | The potential for mortality does not equate to a low magnitude of impact, especially with regard to the current condition of the fishery. |  | No change |  | No change |  | No change. |  | No change.
5 | G6 | A seasonal piling restriction should be in place during the peak Downs herring spawning period. We defer to Cefas regarding the appropriateness of the proposed timing of the restriction and buffer required. |  | No change |  | No change |  | Discussions ongoing. |  | Discussions ongoing
6 | G7 | We defer to Cefas on the matter of the suitability of the sediment disposal restriction as mitigation for the impacts of high levels of suspended sediment concentration (SSC) on herring (and sandeel). |  | No change |  | No change |  | No change. However, we note that in [REP3-022] the Applicant states that sediment disposal would not be carried out in a manner which will impact herring spawning, and they are preparing a sediment disposal plan to set out how this is controlled. |  | No change, however, we note that the Applicant has now provided their [REP4-041] 10.30 Outline Sediment Disposal Management Plan. We, therefore, defer to Cefas on the suitability of the sediment disposal restrictions relating to important herring/other fish and shellfish spcies spawning/nursery areas.

## H - Marine Mammals
Point | Point Number(s) from Appendix H [PD2-010] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix H - Marine Mammal Ecology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | H1 | Population modelling should be conducted, for example Interim Population Consequences of Disturbance (iPCoD), to understand the impacts of the project alone and in-combination with other plans and projects at a population level and consequently inform the conclusions of the EIA and HRA. |  | No change |  | No change, though we welcome the provision of iPCoD modelling. We will provide an update at Deadline 4. |  | We welcome the iPCoD modelling carried out by the Applicant. However, we have concerns with the approach taken and results. Please refer to Appendix M3 of our Deadline 4 Cover Letter. |  | No change.
2 | H2 | The Applicant has not committed to using Noise Abatement Systems (NAS) at this stage. The Applicant should commit to using noise abatement as mitigation now, should driven or part-driven piles be used during construction. |  | No change |  | No change. We highlight that Defra and regulators have been actively considering updating current marine noise policy, and that an announcement regarding this may occur during the Examination period. Broadly speaking, the policy direction is towards an expectation that all offshore wind developers planning to carry out pile driving activity in English waters should in the first instance demonstrate that they have utilised best endeavours to deliver noise reductions through the use of primary and/or secondary noise mitigation methods. We will keep the Examination updated on any proposed policy changes. |  | No change. |  | No change.
3 | H3 | The current approach to implementing Site Integrity Plans (SIPs) for piling impacts to the Southern North Sea SAC from offshore wind development does not allow sufficient time for mitigation methods, such as NAS, to be procured by the Applicant prior to construction, should they be required, therefore increasing the risk that an Adverse Effect on Site Integrity (AEoI) cannot be avoided. |  | No change |  | No change. |  | No change. |  | No change.
4 | H4 | In relation to the Marine Mammal Baseline Characterisation the proposed densities to be used in the quantitative assessment should be an average monthly density estimate of 1.82 porpoise/km2 based on data obtained from the two-year baseline survey. Given that the project lies within the winter portion of the Southern North Sea SAC, where harbour porpoises are present in higher densities, low densities obtained by SCANS are not representative neither are they precautionary. |  | No change |  | No change. |  | Resolved. We welcome the response from the Applicant and the use of site-specific harbour porpoise density to inform the conlcusions of the assessment.
5 | H6 | A combination of medium sensitivity and medium magnitude should result in a non-significant effect. As such, the Cumulative Effects Assessment (CEA) for disturbance to harbour porpoise and harbour seals should result in moderate effect, which is significant in EIA terms opposed to the current conclusion of ‘minor.’ |  | No change |  | No change. |  | No change. |  | No change.
6 | H7 | SCANS III and IV densities should not be included in the quantitative assessment for PTS-onset, TTS- onset and behavioural disturbance from piling for harbour porpoise. |  | No change |  | No change. |  | No change. See also H4 above. |  | No change.
7 | H8 | Natural England is not confident in the level of commitment to using this mitigation method, nor does it support robust conclusions of the assessment that relies on this type of mitigation. Natural England strongly advises that the Applicant should commit to using NAS at this stage to ensure the conclusion that the significance of mitigated PTS from piling is Negligible. |  | No change |  | No change. |  | Resolved. We welcome the response from the Applicant and the use of site-specific harbour porpoise density to inform the conlcusions of the assessment.
8 | H9 | We defer to Cefas as the underwater noise specialists to comment on the Underwater Noise Technical Report. |  | No change |  | No change and we will not provide further comment on this during Examination.
9 | H10 | The Outline Marine Mammal Mitigation Plan (MMMP) provides a summary of potential mitigation measures. and is not intended to identify specific mitigation measures that will be implemented during pile-driving operations. However, Natural England strongly advises that the Applicant should commit to using noise abatement as mitigation now, should driven or part-driven piles be used during construction. |  | No change |  | No change. |  | No change. |  | No change.
10 | H11 | In the Outline Marine Mammal Mitigation Protocol the Applicant proposes to start piling with a soft start at 15% (1050KJ) of the maximum hammer energy (7000KJ). We do not consider this to be adequately low energy for the commencement of piling and advise that the soft start is initiated with 10% of the maximum hammer energy i.e. 700KJ. |  | No change |  | No change. |  | No change. |  | No change.
11 | H13 | If a marine mammal is not observed leaving the mitigation zone, a delay of 20 minutes from the last sighting should be implemented before commencement of soft start piling. This should be a commitment within the Outline Marine Mammal Mitigation Protocol. |  | No change |  | Resolved - this has been addressed in the updated MMMP. |  | No change and we will not provide further comment on this during Examination.
12 | H14 | The Passive Acoustic Monitoring (PAM) guidance was updated in December 2023 (JNCC 2023). This updated version should be used to inform the final MMMP and the outline MMMP should be updated to note this expectation. |  | No change |  | Resolved - this has been addressed in the updated MMMP. |  | No change and we will not provide further comment on this during Examination.
13 | H15 | We do not consider scare changes a suitable mitigation measure for UXO clearance, thus we advise that this measure is not considered in the outline MMMP. |  | No change |  | Resolved - this has been addressed in the updated MMMP. |  | No change and we will not provide further comment on this during Examination.
14 | H16 | There is a misunderstanding around the concept of ‘breaks in UXO detonations’. Given the nature of detonations as an instantaneous activity, breaks in detonations are not possible. Time periods between subsequent detonations should not be considered as breaks and any time prior to a new detonation should be adequately monitored during the pre-denotation search. Post-detonation search is not considered as a ‘break,’ but it is a standard monitoring protocol following the detonation. This should be reflected in an updated Outline Marine Mammal Mitigation Protocol. |  | No change |  | Resolved - this has been addressed in the updated MMMP. |  | No change and we will not provide further comment on this during Examination.
15 | H17 | It is stated in the MMMP for UXO and piling that “If UXO detonation [or piling] is delayed, there would be a risk of animals re-entering the mitigation zone when ADDs are switched off. However, turning on ADDs for extended periods may lead to habituation. Therefore, ADDs would be promptly turned off during delays and reactivated when detonation is ready to commence.” Protocol for delays should be carefully thought through taking into account maximum duration of the Acoustic Deterrent Device (ADD), time of the delay and expected time of the detonation. A break in ADD use should be more than 20 minutes to ensure a startle and flee response once reactivated in circumstances when the commencement of piling is delayed for a sufficient time to warrant the ADD being turned off. |  | No change |  | Resolved - this has been addressed in the updated MMMP. |  | No change and we will not provide further comment on this during Examination.
16 | H18 | Visual marine mammal watches should commence at least 30 minutes before ADD activation. This might require the visual watch to be longer than 1 hour when the ADD activation time is longer than 30 minutes. This should be reflected in an updated Outline Marine Mammal Mitigation Protocol. |  | No change |  | Resolved - this has been addressed in the updated MMMP. |  | No change and we will not provide further comment on this during Examination.
17 | H20 | Harbour porpoise has been screened out from sites that are more than 26 km from the project based on a lack of evidence to suggest connectivity. However, harbour porpoises within the North Sea Management Unit are considered to be a part of the continuous population. Thus, as wide-ranging animals, any designated site with harbour porpoise as a named feature within the North Sea Management Unit should be screened in. |  | No change |  | This has not been addressed therefore no change |  | No change. |  | No change.
18 | H21 | It is not clear if seismic surveys have been included in the in-combination assessment due to the contradicting text throughout the document. It is also not clear which tier they have been assigned to (tier 6 (Table 9.6) or tier 7 (Table 12.3, & 12.3.30)). Clarity should be provided on this. |  | No change |  | No change. |  | No change. |  | No change.
19 | H22 | A high proportion of the Southern North Sea SAC is estimated to be disturbed by the project in-combination with other activities. This percentage is 86.47% at the highest and is far greater than the 20% daily noise threshold for the SAC. Consequently, we cannot agree to the conclusion of no AEoI for in-combination impacts of the project for disturbance of harbour porpoise in the SNS SAC unless the Applicant fully commits to NAS within the SIP. |  | No change |  | No change. |  | No change. |  | No change.
20 | H23 | We do not agree with the conclusion of no AEoI for in-combination impacts of the project for disturbance of harbour porpoise in the SNS SAC across a season since the mitigation committed to in the MMMP is designed to reduce the likelihood of injury caused by underwater noise not to reduce disturbance, it cannot be used as a justification to support no AEoI. To reduce disturbance to harbour porpoise alone and in-combination, the Applicant needs to commit to NAS to significantly reduce the sound at source. |  | No change |  | No change. |  | No change. |  | No change.

## I - Seascape
Point | Point Number(s) from Appendix I [PD2-011] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix I - Seascape Landscape and Visual | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | I1 | The Applicant has introduced a definition of what an “immediate setting” is (“the foreground seascape”), allowing them to assert that the project is a ‘horizon development’. However, the special qualities of the SCHAONB, particularly the wildness and tranquillity special qualities, are highly sensitive to changes in views out to sea. Further consideration is required. |  | No change |  | No change. |  | No change. |  | No change.
2 | I2 | The apparent heights and lateral spread values of the Wind Turbine Generators (WTGs) across the perceived horizon should be used to inform judgements on the significance of effects, rather than a simple reliance on separation distance. The VE WTGs, especially the ~320m design option, will create a densification effect across the horizon when seen in conjunction with the Greater Gabbard and Galloper arrays. Further consideration is required. |  | No change |  | No change. |  | No change. |  | No change.
3 | I3 | The WTG apparent height, turbine density, and turbine lateral spread are three separate parameters that may be used to inform judgements on the significance of effects to the SCHAONB and SHC. Evidence should be submitted to support the Applicant’s assessment that effects from an increase in WTG density is “considered preferable” to an increase in HFoV, and what this outcome means for the assessment of harm to the SCHAONB and SHC. |  | No change |  | No change. |  | No change. |  | No change.
4 | I4 | Within the northern array area of VE, the most northerly 8 WTGs have the greatest potential to affect the special qualities of the SCHAONB and the special character of the SHC. This relates to their lateral spread, combined with their apparent height, which from some viewpoints will bridge the gap between Galloper OWF and the consented East Anglia TWO (EA2) array. While the remaining 8 WTGs are, from most views, partially masked by the Galloper WTGs, their sheer size will create a harsh juxtaposition on the horizon with the existing arrays. Further embedded mitigation is required. |  | No change |  | No change. |  | No change. |  | No change.
5 | I5 | Natural England welcomes the reduction in the maximum blade tip height to 399m in the submitted proposal. |  | No change |  | Natural England welcomes the reduction in the maximum blade tip height to 370m. |  | No change.
6 | I6 | The ~320m blade tip height design is more acceptable, although the apparent heights of the WTGs do not become completely insignificant. The greater northward lateral spread of WTGs combined the densification effects associated with the greater number of WTGs would also result in some significant effects. The ~320m turbines will still appear to be significantly taller than the existing turbines (Galloper and Greater Gabbard arrays), albeit partially obscured. Therefore, the need to consider Natural England’s Design Principles remains. |  | No change |  | No change. |  | No change.
7 | I7 | Natural England's proposed Design Principles 1, 2 and 3 have not been adopted by the Applicant as embedded mitigation within the submission. We do not agree that the evolution of the project design is acceptable embedded mitigation, or that Design Principles 1, 2 and 3 have been fully considered within the project design. Further consideration of the Design Principles is needed. |  | No change |  | No change. |  | No change. |  | No change.
8 | I8 | We do not agree with the description of the VE array as “relatively permeable”, nor that it “does not create enclosure”, or that “the apparent height of the VE WTGs is relatively small”. Further consideration of the Design Principles is needed. |  | No change |  | No change. |  | No change. |  | No change.
9 | I9 | Page 71 of APP-079 states that “Visualisations of the ~320 m design scenario (79 turbines) are shown in Figure 10.47 – Figure 10.67.” Natural England has been unable to locate these visualisations within the submission material. |  | No change |  | Resolved - the Applicant has now provided these. |  | Natural England considers this issue resolved and will provide no further comments on this matter.
10 | I10 | The revised indicative Maximum Design Scenario (MDS) layout results in a distinct grouping of 8 WTGs in the remaining gap between the proposed VE array and the EA2 array. There remains disagreement with the statement that ‘VE will entirely occur in the context of the existing developments’ and that the VE WTGs can be considered as ‘generally in keeping’ with existing arrays given the starkly differing apparent heights between Galloper / Greater Gabbard arrays and VE. The SLVIA should be updated to consider the implications of removing the remaining gap between the existing/proposed OWF arrays in this area. |  | No change |  | No change. |  | No change. |  | No change.
11 | I11 | There is disagreement with the assessment that the additional cluttering effects from the VE project have been appropriately mitigated. The potential effects on the SCHAONB and SHC from the distinct grouping of 8 WTGs in the remaining gap between the proposed VE array and the EA2 array have not been addressed. The assessment needs to be updated to assess what the additional impact of VE is in terms of the cluttering effect identified and apply mitigation based on the Natural England design principles. |  | No change |  | No change. |  | No change. |  | No change.
12 | I12 | The most northerly 8 WTGs will create and draw focus to a new distinct object on the horizon, and that the resulting harm from this new object on the statutory purposes of the SCHAONB and the special character of the SHC has not been fully considered in the assessment. |  | No change |  | No change. |  | No change. |  | No change.
13 | I13 | Natural England disagrees with the Applicant’s assessment on the “curtaining” effect. The assessment of the sense of openness and exposure special quality has not properly considered the effect of VE closing of gap between the existing Galloper and Greater Gabbard OWF arrays and the to be built EA2 array. There is a likelihood that VE would close the last ‘gap without turbines’ in direct views out to sea along a ~20km stretch of SCHAONB and SHC coastline (Orford Ness to Dunwich). This needs further consideration and mitigation. |  | No change |  | No change. |  | No change. |  | No change.

## J - Onshore Ecology
Point | Point Number(s) from Appendix J [PD2-012] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix J - Onshore Ecology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | J1 | Confidence in mitigation proposals for protected species is reduced due to limitations of survey results caused by the timing of the surveys. |  | No change |  | No change. |  | In progress. We welcome the Applicant's commitment to pre-construction surveys within the OLEM NE considers this matter resolved. However, there needs to be a commitment to ensure that the mitigation measures remain for purpose. |  | No change.
2 | J2/J32 | Use of an arbitrary time period for the definition of duration in relation to impact assessment for protected species doesn’t consider the life cycle of the species being assessed, including invertebrates of particular conservation concern. |  | No change |  | No change. |  | No change. |  | No change.
3 | J3 | Depending on the opening of the King Charles III England Coast Path (ECP) there are likely to be receptor impacts. |  | No change |  | No change, Natural England reviewing additional documentation. |  | Resolved. [REP1-051] has addressed this concern as it is highlighted that there will be a continuous route for the ECP during the proposed works.
4 | J4 | There is potential for impacts to designated sites & features at the Lesser Black Backed Gull (LBBG) compensation site on Orford Ness. |  | No change |  | No change. This will be updated at Deadline 4. |  | No change. We advise that baseline survey information is still needed to support the assessments, including for shingle morphology. We also note disagreement between the owners of the Cobra Mist land and VE [REP3-041] casting doubting over the feasibility of the LBBG compensation area at Orford Ness. Please refer to Appendix J4 to our Deadline 4 response. |  | The Applicant has provided invertebrate and vegetation surveys [REP4-042] and updated HRA, EIA and EcIA documents [REP4-008, REP4-014, and REP4-016, respectively] for the proposed Orford Ness compensation site. However, the survey area does not overlap with the proposed compensation site and the baseline remains incomplete. Both surveys were carried out at sub-optimal times. There is also no new information on the proposed ditch crossing. Please see our comments on these updated documents in the Cover Letter to our Deadline 5 submission.
5 | J5/J14 | Should this extension project utilise the same operational port facility as the constructed Galloper Offshore Wind Farm (OWF), within the Stour and Orwell Special Protection Area (SPA); an assessment of what the disturbance impacts of increased boat traffic and any expansion of the O&M facility is required. |  | No change |  | No change |  | No change. |  | No change.
6 | J7 | Habitat/botanical surveys undertaken in January 2024 were outside the optimal survey season limiting confidence in conclusions made regarding impacts to the proposed compensation site at Orford Ness. With the presence of uncommon species not being ruled out along the proposed fence line. |  | No change |  | No change. This will be updated at Deadline 4. |  | No change. The Applicant states that updated survey results/assessments will be included in a later iteration of the HRA. However, HRA conclusions are currently based on incomplete baseline information and are therefore not robust. Please also refer to Appendix J4 to our Deadline 4 response. |  | The Applicant has provided invertebrate and vegetation surveys [REP4-042] and updated HRA, EIA and EcIA documents [REP4-008, REP4-014, and REP4-016, respectively] for the proposed Orford Ness compensation site. However, the survey area does not overlap with the proposed compensation site and the baseline remains incomplete. Both surveys were carried out at sub-optimal times. There is also no new information on the proposed ditch crossing. Please see our comments on these updated documents in the Cover Letter to our Deadline 5 submission.
7 | J4/J8 | Coastal recession/advancement trends at the LBBG compensation site(s) have not been adequately assessed over the life time of the project using best available evidence. |  | No change |  | No change. This will be updated at Deadline 4. |  | In progress. The Applicant has assessed historical and contemporary trends in coastline change at the compensation area and found the area to be stable. However, there is still a need to commit prior to construction to checking the National Coastal Erosion Risk Mapping 2 (NCERM2) data, which will provide the 50 year erosion line (i.e. future coastal change). This is to ensure that the information remains fit for purpose and, if not, the Applicant should commit to making the necessary design changes. |  | No change. Our previous advice stands.
8 | J10 | Following more robust site specific surveys further consideration is needed regarding appropriate mitigation measures for impacts on the Orford Ness – Shingle Street SAC from the LBBG compensation site(s). |  | No change |  | No change. This will be updated at Deadline 4. |  | No Change. |  | No change. Please see our comments in the Cover Letter to our Deadline 5 submission.
9 | J11/J24 | Construction and management/monitoring/maintenance/ impacts to habitat within and adjacent to the fence line at the LBBG compensation site at Orford Ness is likely to have significant effects on perennial vegetation on coastal shingle, especially where the sediment structure is destabilised. This has the potential to cause a long-term, if not permanent, shift towards a secondary form of vegetation. |  | No change |  | No change. This will be updated at Deadline 4. |  | No change. The Applicant's conclusion of no LSE for fence installation is based on the assumption that the site has already been modified and the delicate matrix already impacted. However, this does not preclude the presence of rare and sensitive shingle flora and fauna, and new seasonally appropriate survey data should be acquired to support this conclusion. It is also important for determining site sensitivity and appropriate mitigation measures. Please also refer to Appendix J4 in our Deadline 4 response. |  | The Applicant has provided invertebrate and vegetation surveys [REP4-042] and updated HRA, EIA and EcIA documents [REP4-008, REP4-014, and REP4-016, respectively] for the proposed Orford Ness compensation site. However, the survey area does not overlap with the proposed compensation site and the baseline remains incomplete. Both surveys were carried out at sub-optimal times. There is also no new information on the proposed ditch crossing. Please see our comments on these updated documents in the Cover Letter to our Deadline 5 submission.
10 | J12/J24 | The EIA does not consider impacts to the shingle morphology and sediment structure and recoverability. Typically, shingle morphology landward of the seaward ridge never fully recovers. There is also the risk of further repeated damage occurring through regular maintenance/monitoring/ management of the fence line. |  | No change |  | No change. This will be updated at Deadline 4. |  | In Progress. The Applicant has now considered/assessed impacts, as requested, to the shingle morphology and sediment structure, and considers them to be already modified or disturbed. Moreover, mitigation measures will limit damage during construction and minimise disturbance during maintenance, management and monitoring [AS-040]. These will be included in the LBBG implementation and monitoring plan and submitted at a later deadline. However, we need to see baseline survey data before we can agree with the Applicant's conclusions and to confirm the current sensitivity of the shingle habitats. |  | No change.
11 | J13/J25 | The EIA has not considered impacts to the saline lagoons at the Orford Ness compensation site from the presence of the fence through the lifetime of the project in terms of blockage to overtopping events and the transfer of new shingle to their eastern edge and subsequent implications to the lagoon biodiversity. Furthermore, the impacts of climate-related changes (including water levels and coastal stability) need to be further considered. |  | No change |  | No change. This will be updated at Deadline 4. |  | Resolved. [AS-040] The Applicant states that the fence line of the LBBG compensation area has now been moved. Therefore, the fence line will avoid saline lagoons and therefore no direct impacts could occur. Climate change impacts have also been considered.
12 | J16/J17 | Key evidence to support the screening out of Marsh Harrier and Nightjar populations at the Alde Ore Estuary SPA and Minsmere-Walberswick SPA within the HRA is missing from the bibliography, namely an article by Wright (2012). |  | No change |  | Progressed: We welcome the references provided by the Applicant in REP1-051. However, the references are old and do not rule out the possibility of marsh harrier and nightjar migration across the proposed development area offshore. We refer the Applicant to the BTO website. |  | No change. |  | No change.
13 | J18 | Detail of all mitigation for Onshore Ecology and Biodiversity should be included in relevant sections of outline plans and documents e.g. Table 8.1 |  | No change |  | Resolved following review of Applicant's response to our relevant representations.
14 | J19 | What is the Applicant’s intended course of action should the agreed proposed buffer zones for Schedule 1 bird species and other breeding species be unsuccessful? |  | No change |  | No change. |  | No change. |  | No change.
15 | J20 | Through use of the mitigation hierarchy every effort should be made to avoid, reduce and mitigate impacts including for black-tailed godwit, a designated feature of Hamford Water SPA & Ramsar; Stour and Orwell Estuaries SPA & Ramsar; and Blackwater Estuary SPA & Ramsar. |  | No change |  | No change. This will be updated at Deadline 4. |  | No change. |  | No change.
16 | J21 | Further clarification on the Applicant’s assessment of the cumulative effect of both disturbance and temporary habitat loss to dunlin, a designated feature of Stour and Orwell Estuaries SPA & Ramsar, and Blackwater Estuary SPA & Ramsar is required. |  | No change |  | No change. This will be updated at Deadline 4. |  | No change. |  | No change.
17 | J22 | Commitments to follow best practice should be made for maintaining vegetation community and diversity at the LBBG compensation area including (but not exclusively) the use of existing access trackways during construction and maintenance/ management. |  | No change |  | No change. This will be updated at Deadline 4. |  | In progress. The Applicant has agreed to discuss maintenance and best practice options with Natural England. However, there is no agreement to commit to following best practice. |  | Our previous advice remains unchanged.
18 | J23 | More than 'habitat management' in the form of mosaic cutting of vegetation and removal of arisings will be required to manage the increase in nutrients from the establishment of a gull colony at the Orford Ness compensation site. |  | No change |  | No change. This will be updated at Deadline 4. |  | No change. Issue remains removal of vegetation arisings needs to be considered and actions secured should it be deemed necessary within the outline LBBG IMP. See also our advice in Appendix J4. |  | Our previous advice remains unchanged.
19 | J26 | Compensatory measures for Lesser Black backed gull at Alde-Ore Estuary (AOE) SPA need to be agreed - please see Ornithology compensation tab for further comments. |  | We will not be providing further comments on this during Examination. |  | Natural England notes the new evidence submitted into examination and therefore will provide further advice at Deadline 4 |  | No change - our original advice remains. However, please see our latest advice in Appendix C4 with our Deadline 4 cover letter. |  | No change. The scale of the compensation and how it is delivered has yet to be agreed.
20 | J29 | While trenchless crossings of Holland Haven Marshes SSSI and the Frinton Golf Club are committed to in the Outline Landfall Methodology; mitigation measures within 9.21 Code of Construction Practice are included for all installation options to address potential impacts occur especially in relation to bentonite frac-out. All comments from NE and EA in relation to this location should be given due consideration. |  | No change |  | No change. Further consideration is needed pre-determination of the impacts from bentonite frac-out, specifically at Holland Haven Marshes SSSI. |  | No change. |  | No change.
21 | J30 | Protected species licences and therefore Letters of No Impediment will not be required for this project. |  | We will not be providing further comments on this during Examination.
22 | J31 | Limitations of protected species surveys will need to be addressed pre-construction with all areas surveyed. |  | No change |  | No change |  | Resolved: Natural England notes the OLEM [REP2-023] includes details on conducting surveys for protected species prior to works.
23 | J33 | Pre construction surveys should follow standard methods, especially for badgers to ensure surveys are undertaken at the optimum time. |  | No change |  | No change. This will be updated at Deadline 4. |  | Resolved: Natural England is content that the OLEM [REP2-023] refers to the correct guidance for conducting badger surveys.
24 | J34 | Survey results lack information relating to badger main setts despite observations of numerous associated setts. |  | No change |  | No change. This will be updated at Deadline 4. |  | No Change. Natural England recommends that where practicable the pre-construction surveys should identify the main sett location. |  | No change. Please see our previous advice.
25 | J35 | Trees within exclusion areas have only been subject to Ground Level Tree Assessment (GLTA) surveys and commitments to follow best practice at pre-construction are required. |  | No change |  | No change. This will be updated at Deadline 4. |  | Natural England notes the OLEM states the pre-construction surveys will follow best practice for surveys.
26 | J36 | The use of DLL prior to construction Is agreed to ensure compliance with the legal status of GCN and mitigate for potential impacts on this species. |  | We will not be providing further comments on this during Examination.
27 | J37 | The Applicant’s commitment to delivering a minimum of 10% BNG (section 1.2.2, pg.2) should be secured by requirement in the DCO. |  | No change |  | Progressed: But our concerns are not fully addressed |  | No change. |  | No change.
28 | J38/J42 | BNG should reflect best practice or the approach used for TCPA development. The metric calculations will need updating over time to reflect updated guidance, design iterations and to maximise their potential biodiversity outcomes throughout the detailed design process. |  | No change |  | No change |  | No change. This will be updated at Deadline 5. |  | No change.
29 | J39 | As per current government guidance, commitments are required to ensure mitigation or compensation for protected species or designated site impacts results in “no net loss”, with 10% BNG being additional. |  | No change |  | No change |  | No change. This will be updated at Deadline 5. |  | No change.
30 | J40 | Assigning strategic significance was updated with the introduction of mandatory BNG in February 2024 (see Statutory Metric User Guide, pg.26). And this should be adhered to going forwards. |  | No change |  | No change |  | No change. This will be updated at Deadline 5. |  | No change.
31 | J41 | There is no irreplaceable or very high distinctiveness habitat on-site, although it does occur within the Order Limits (pg.11). |  | We will not be providing further comments on this during Examination.

## K - Landscape VIA
Point | Point Number(s) from Appendix K [PD2-013] | Taken from Natural England’s Relevant and Written Representations Five Estuaries OWF Project Appendix K - Landscape and Visual Impact Assessment | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | K1 | Owing to insufficient evidence on the Norwich-Tilbury substation design/impacts at this stage, there is a potential for in-combination/cumulative impacts between this project, the Five Estuaries (VE), and North Falls substations. |  | No change |  | No change. |  | No change. |  | No change.
2 | K3 | There is the potential for in-combination/cumulative landscape and visual impacts arising between VE, North Falls and Norwich-Tilbury NSIP substations. |  | No change |  | No change. |  | No change. |  | No change.
3 | K5 | The setting of Dedham Vale National Landscape could be impacted prior to establishment of mitigation screening. |  | No change |  | No change. Additional mitigation measures should be considered to address potential winter visibility whilst mitigation screening is established. |  | No change. |  | No change.