## Title page
THE PLANNING ACT 2008
THE INFRASTRUCTURE PLANNING (EXAMINATION PROCEDURE) RULES
2010
Natural England's Risk and Issues Log - Deadine 4 Submission.
For:
The construction and operation of the Rampion 2 Offshore Windfarm located approximately
13km off the Sussex coast in the English Channel.
Planning Inspectorate Reference EN010117
3rd June 2024

## How to Read Risks and Issue Log
Natural England has created this Risk and Issues Log to track progress through the Rampion 2 examination process. The Risks and Issues Log will be submitted at each deadline and mark issues with a colour from our RAG scale depending on the level of significance of the issue. It should be noted that the colour scale is different from that used in the Statement of Common Ground provided by The Applicant. The Risk and Issues Log is split into multiple tabs in line with the Appendices of our Relevant Representations submission. • Appendix A - Development Consent Order, Deemed Marine Licence • Appendix B - Offshore and Intertidal Ornithology • Appendix C - Marine Mammals • Appendix D - Coastal Processes • Appendix E - Fish and Shellfish Ecology • Appendix F - Benthic, Subtidal and Intertidal Ecology • Appendix G - Other Plans – Marine • Appendix H - Landscape and Visual Impact • Appendix I - Seascape, Landscape and Visual Impact • Appendix J - Terrestrial Ecology and Nature Conservation • Appendix K - Principal Areas of Disagreement Statements The Risk and Issues Log will be submitted alongside our written response at each deadline. This will reflect our position following a review of documents that we have considered in forming our position at each deadline. Any issues added to the log during Examination (not included in Relevant Reps) are highlighted in Red in column C and then coded according to RAG status. [New Text is in red] Risks and Issues have been presented on a document by document basis for all Annexes except Annexes G (Cromer MCZ) and H (SLVIA) which have been presented as a hybrid of broad themes, which may stretch across several documents, and a document by document basis depending on the point(s) being addressed. For all tabs except tabs G and H, the blue header row at the top of each section refers to the document that the comments are addressing. For Tabs G and H, the blue header row either addresses the broadscale theme that cover the comments below with relevant documents referenced within individual comments where appropriate or in the same document by document manner which has been adopted for all other tabs.
Purple Note for Examiners and/or competent authority. May relate to DCO/DML
Red Natural England considers that unless these issues are resolved it will have to advise that (in relation to any one of them, and as appropriate) it is not possible to ascertain beyond reasonable scientific doubt that the project will not affect the integrity of an SAC/SPA/Ramsar and/or significantly hinder the conservation objectives of an MCZ and/or damage or destroy the interest features of a SSSI and/or have significant adverse effects on landscape/seascape and/or comply fully with the Environmental Impact Assessment requirements.
Addressing these concerns may require the following:
new baseline or survey data; and/or
significant revisions to baseline characterisation and/or impact modelling and/or
significant design changes; and/or
significant mitigation
In addition, Natural England may use this category to highlight where there is a significant risk that an issue will not be sufficiently addressed within the Examination timescales. Consequently, issues that start out as Amber may progress to Red in the latter stages of the examination.
Amber Natural England does not agree with the applicant’s position or approach and consider that this could make a material difference to the outcome of the decision-making process for this project.
Natural England considers that these matters may be resolved through:
provision of additional evidence or justification to support conclusions; and/or
revisions to impact assessment methodology and/or assessment conclusions; and/or
minor to moderate revisions to impact modelling; and/or
well-designed mitigation measures that are adequately secured through the draft DCO/dML and/or
amendments to draft plans
If these issues are not addressed or are unlikely to be resolved by the end of the Examination, then they may become a Red risk as set out above.
Yellow Natural England doesn’t agree with the Applicant’s position or approach. We would ideally have liked this to be addressed prior to the examination but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process and would not expect these matters to be a ongoing focus of the examination. However, we reserve the right to revise our opinion should further evidence be presented.
It should be noted by interested parties that just because these issues/comments are not raised as significant concerns in this instance, it should not be understood or inferred that Natural England would be of the same view in other cases or circumstances.
Once a Risk or Issue has been categorised as yellow, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be greyed out at subsequent deadlines in order to rationalise the risk and issues log.
Green Natural England is in broad agreement with the Applicant’s approach and has no significant outstanding concerns. As above, we reserve the right to revise our opinion should new evidence be presented. Once a Risk or Issue has been categorised as green, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be shaded grey at subsequent deadlines in order to rationalise the risk and issues log.

## A - DCO DML
Point | Point Number(s) from Appendix A [RR-265] | Taken from Natural England’s Relevant and Written Representations Rampion 2 - Appendix A - Development Consent Order, Deemed Marine Licences [RR-265] | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Status at D1 | Consultation, actions, progression | RAG Status at D2 | Consultation, actions, progression | RAG Status at D3 | Consultation, actions, progression | RAG Status at D4
Document used: 3.1 Draft Development Consent Order [APP-019]
A1 | 1 | We note that no interpretation is provided to define the Relevant Statutory Nature Conservation Body. We advise that, for consistency with other Development Consent Orders (DCOs) and to future proof the DCO against any potential changes, a definition of Relevant Statutory Nature Conservation Body should be provided, and references to Natural England throughout the document replaced with Relevant Statutory Nature Conservation body. We advise that the DCO is amended to include the appropriate definition and wording. Natural England advise that similar wording that was used in the recent East Anglia 2 DCO. |  | Natural England accepts the definition as per the applicant's updated DCO.
A2 | 2 | We note that there is no definition here of the Outline Offshore Operations and Maintenance plans (OOOMP) (document 7.16). The document is also not listed under Schedule 16. The definition of ‘maintain’ should link not only to the Environmental Statement (ES) but also to the OOOMP. The OOOMP takes the detail from the ES to provide the clear scope for operations and maintenance activities considered under the Deemed Marine Licence (dMLs). Given the OOOMP defines the scope of operations and maintenance permitted under the DCO/dMLs, we advise this document is included within the definitions and the Schedule 16 list of documents. We advise that the definition of ‘maintain’ should also include the extent assessed in the environmental statement and defined in the OOOMP. This will make the extent of Operations and Maintenance clear and reduce the potential for misunderstanding during the long operations and maintenance period. Please note that, due to the length of this period, the individuals involved from all parties will change a number of times, and there is significant benefit to having a simple small defined document to cross reference ongoing operations and maintenance requests against. |  | No Change. |  | No Change |  | A definition of the OOOMP has been included and Natural England accepts this definition. However, notes the definition of maintain has not been updated so this issue in part remains. |  | No change
A3 | 3 | Natural England notes that the DCO only provides for a maximum volume of scour protection, while the ES parameters document provides both a maximum volume and area of scour protection. We advise that, given that the area of impact is one of the most important factors to be controlled, it should also be provided for here. Natural England notes that requirement 4 also only lists a maximum volume, and we advise this should also provide a maximum area of scour protection. We advise the Applicant updates these requirements to list the maximum extent of scour protection per turbine/substation and a maximum total. |  | The updated DCO now includes the area of scour protection.
A4 | 4 | This requirement relates to the approval of the Biodiversity Net Gain (BNG) strategy. The wording does not contain a requirement to consult the relevant statutory nature conservation body on this strategy. We advise the wording is updated to include a requirement to consult the relevant statutory nature conservation body prior to the approval of an BNG strategy. |  | The updated DCO includes a requirement to consult the SNCB.
A5 | 5 | Natural England notes that this condition relies on a requirement for a landscape and ecology management plan, based on the outline plan. Natural England advises that you refer to our terrestrial ecology and landscape advice in relation to our concerns regarding this outline plan. We advise that the outline plan is revised to account for terrestrial ecology and landscape advice provided. |  | No Change. |  | No change |  | No change |  | No change
A6 | 6 | Natural England notes there is no requirement providing for the surveying for European Protected Species onshore and preventing commencement of works until these surveys are completed. This is a standard DCO requirement and should be included to ensure protection of important species. We advise that the DCO is updated to include the appropriate requirement and recommend that the wording used in the most recent Dudgeon and Sheringham Extension Projects DCO is considered. |  | No Change. |  | No change |  | No change |  | No change
A7 | 7 | We advise that our comments provided above on interpretations (Part 1, Para 2 Interpretations) also apply to the interpretations provided within Schedule 11 and 12 of the deemed Marine Licences. We advise that the wording is amended as appropriate. |  | No Change. |  | No change |  | No change |  | No change
A8 | 8 | Natural England notes there is no condition limiting the maximum hammer energy. Given the environmental sensitivities of the area, particularly black bream, we advise that the upper limit of hammer energy for each foundation option is an important part of the projects Rochdale Envelope and should be defined to ensure it is not exceeded. This should be in line with the maximum hammer energies defined in the ES. We advise that the condition is amended to include a maximum hammer energy. Wording similar to that used on Dudgeon and Sheringham Extension DCO would be appropriate to include in this. |  | No Change. |  | No change |  | No change |  | No change
A9 | 9 | Natural England notes that the consent allows for deployment of cable protection up to 15 years from the date of the order. Our advice is this should be 10 years from the commencement of operations, as this is the maximum scope that we can support outside of designated sites. We also note that the wording used may give the Applicant less time to deploy cable protection if the project suffers a delay in the start of works or during construction. We advise that this wording is amended. |  | The amendments have been accepted, but a minor suggestion of changed wording is proposed.
A10 | 10 | Natural England notes that the wording here is to supply an operations and maintenance plan. However, it does not require that the plan submitted be in accordance with the OOOMP. Please see our above comments regarding the inclusion of the OOOMP within interpretations and definition of ‘maintain’. We advise the condition is amended to ensure the maintenance plan is in accordance with the OOOMP. |  | No Change. |  | No change |  | A definition of the OOOMP has been included and Natural England accepts this definition. However, notes the definition of maintain has not been updated so this issue in part remains. |  | No change
A11 | 11 | Natural England notes that the standard micro-siting requirement has been omitted. The requirement here refers to avoiding historic receptors only. While we note there is a specific requirement later to cover the avoidance of chalk, other features of ecological importance, such as Sabellaria reef features, should be provided for within the conditions. We advise this condition is amended. |  | Partially resolved, with some further amendments suggested.
A12 | 12 | Natural England notes that the wording here states ‘cable routing to ensure micrositing and where possible to avoid subtidal chalk features and areas which have potential to support black seabream nesting’. We advise that this commitment does not include all sensitive ecological features. We advise it should be amended in line with our advice on the benthic ecology chapter. We advise that key omissions are Sabellaria spinulosa reef, peat and clay exposures, and Stony/cobble reef. We advise this condition is amended in line with our comments on the benthic ecology chapter. |  | Partially resolved, with some further amendments suggested.
A13 | 13 | We advise that Schedule 11 Part 2 Condition 16 (2) (a) should specify side scan sonar. We advise this condition is amended. |  | Side Scan Sonar is now included. This issue is resolved.
A14 | 14 | We advise that Schedule 11 Part 2 Condition 16 (2) (b) should also include Peat and Clay exposures in line with our benthic comments. We advise this condition is amended. |  | Peat and clay exposures are now included. This issue is resolved.
A15 | Summary 1, 15 | We advise that there is a risk that the In Principle Sensitive Features Mitigation Plan (IPSFMP) may not deliver sufficient mitigation. In line with our comments on the ES and MCZ Assessment, we advise that a full piling exclusion March-July inclusive is included in relation to black seabream as a feature of Kingmere MCZ. Based on the evidence provided to date we advise that a full seasonal pilling restriction (March-July) is included in the DCO. |  | No Change. |  | No change |  | No change |  | No change
A16 | Summary 2, 16 | Given the increase in size and complexity of offshore wind farm construction, Natural England considers that a period of four months is insufficient for approval of some documentation. We request this is amended to a period of no less than 6 months. We advise the condition is amended to provide 6 months. Natural England notes that for the Dudgeon and Sheringham Extension Project, a 6-month period was agreed for some conditions. We would be willing to engage with the Applicant and the Marine Management Organisation (MMO) to potentially come to a similar agreement. |  | No Change. |  | No change |  | No change |  | Natural England notes that the timing requirement in Schedule 11 Part 2 Condition 11(1), Condition 12 (2) and (3) has been changed and extended to six months. Natural England welocmes this change as it partially addresses issues we have raised in our relevant representations. However, we note this does not fully address our concerns regarding the timing of other documents including the pre-construction documentation.
A17 | 17 | We note that no monitoring has been included in relation to marine mammals. We refer you to our comments on marine mammals where we have discussed monitoring and advise you to update accordingly. |  | No Change. |  | No change |  | No change |  | No change
A18 | Summary 4, 18 | Natural England notes the wording here does not cover the required during construction piling monitoring. Nor does it allow for a halt to works should the noise be significantly in excess of that predicted within the ES. Given the environmental sensitivities of the area, we request that this monitoring and the stop requirement be appropriately secured, as it has been in all previous Offshore Wind Farm DCOs. We advise that this is amended to include appropriate during construction monitoring requirements. Natural England suggests wording similar to the Dudgeon and Sheringham Extension Project DCO is used. |  | No Change. |  | No change |  | No change |  | No change
A19 | 19 | We advise that post consent monitoring is not limited to Sabellaria spinulosa reef and black seabream. This should be updated in line with our benthic and fish and shellfish comments. We also refer you to our comment on marine mammal monitoring. We advise this is amended in line with our advice on these topics. |  | No Change. |  | No change |  | No change |  | No change
A20 | 20 | We advise that all points raised above on Schedule 11 are applicable to Schedule 12 where similar provisions exist. To ensure brevity, Natural England will not repeat our comments. We advise points raised in Schedule 11 should also be addressed in Schedule 12. |  | No Change. |  | No change |  | No change |  | No change
A21 | 21 | We note that no compensation provisions or schedules are provided. We advise that, based on our comments on the ornithology thematic area, this is likely to be required. We refer you to our comments on ornithology and request this is updated accordingly. |  | A compensation schedule has been provided. See new comments below.
A22 | Summary 5, 22 | Natural England notes that an Outline Kittiwake Implementation and Monitoring Plan (KIMP) has been submitted to provide for compensation on a without prejudice basis. The outline KIMP should be updated to contain a draft compensation schedule to demonstrate how the compensation measures will be secured. |  | No Change |  | No change |  | No change |  | No change
A23 | Summary 6, 23 | In relation to impacts on seascape, there are a number of commitments and design principles. We advise that once agreed upon, we would expect to see these specifically secured in the DCO. We advise that agreed commitments and design principles are included in the DCO. |  | No Change |  | No change |  | No change |  | No change
Additional Comments Since Relevant Representations
Document used: Alternative Schedule 17 [PEPD-017] submitted prior to Deadline 1
A24 | 9 | Natural England notes the ongoing discussions regarding the kittiwake Compensation requirements and reserves the right to raise further comment on the draft text following these discussions | N/A |  |  | No change |  | No change |  | No change
A25 | 10 | Natural England notes the absence of provisions regarding the need for steering group. We recognise that the collaborative nature of the Applicant’s proposed compensatory measures may mean an alternative approach is necessary. At this stage, we wish to note that previous Steering group conditions did provide for some important aspects (such as a time table and provision of a dispute resolution mechanism) that should still be captured through condition, even if no steering group is required. | N/A |  |  | No change |  | No change |  | No change
A26 | 11 | Condition 4 of Schedule 17 - Natural England requests the timing of the compensation be stated as to be provided at least 4 full breeding seasons prior to operation, as per other similar projects. | N/A |  |  | No change |  | No change |  | No change
A27 | 12 | Natural England requests that end of life/decommissioning conditions be added similar to those on other projects. | N/A |  |  | No change |  | No change |  | No change
A28 | 13 | Natural England requests that a condition to notify the Secretary of State of the completion of compensatory measures be included, similar to those included in other projects compensation requirements. | N/A |  |  | No change |  | No change |  | No change

## B - Offshore Ornithology
Point | Point Number(s) from Appendix B [RR-265] | Taken from Natural England’s Relevant and Written Representations Rampion 2 Appendix B - Offshore and Intertidal Ornithology [RR-265] | RAG Status Rel and WR Rep, and D1 | Consultation, actions, progression | RAG Status at D2 | Consultation, actions, progression | RAG Status at D3 | Consultation, actions, progression | RAG Status at D4
Document used: [APP-053] 6.2.12 Rampion 2 ES Volume 2 Chapter 12 Offshore and intertidal ornithology
B1 | 1 | Natural England notes that breeding season Biologically Defined Minimum Population Scales (BDMPS) figures are presented using our approved method, alongside the alternative method proposed by the Applicant. In the case of great black-backed gull, guillemot, and razorbill, the Applicant’s method produces the greatest annual BDMPS figure, and the Applicant has chosen to take this forward to compare annual predicted mortalities against. Natural England does not support this and considers that either the breeding season figure using our approved method or the largest nonbreeding season BDMPS from Furness (2015) should be used as the reference population - whichever is greater. We note the differences are relatively minor and should not result in a material change to the impact totals.
B2 | 2 | The purpose of the PVA was to model the cumulative impacts for gannet, rather than project-alone impacts, so it is unclear why the results are presented in the project-alone section. The results of the PVA for gannet should be presented in paragraph 12.15.84, where the combined cumulative impacts for gannet on a BDMPS scale are given.
B3 | 3 | There appears to be a mistake in this section. The predicted annual number of collisions for herring gull due to the project alone is stated here to be 634, and the PVA has been carried out on that basis. Previously, in paragraph 12.13.122, it was given as 63. Natural England requires clarification on this.
B4 | Summary (1), 4 | In the cumulative impact assessment for gannet, guillemot, razorbill, kittiwake, great black-backed gull, and lesser black-backed gull, breeding season impacts appear to have been screened out for most other projects. This is presumably due to the breeding season reference population comprising adults within foraging range of Rampion 2, plus immatures from the preceding BDMPS season. Natural England does not agree with this method. It is not clear why this appears to have been done for the species mentioned above, but not herring gull. The Applicant should clearly explain their method for undertaking cumulative impact assessments and the rationale behind which figures are included. Natural England advises that the impacts for all projects within the relevant BDMPS for all seasons should be included in the cumulative impact assessment. This is particularly important for lesser black-backed gull and great black-backed gull, where the threshold of a 1% increase in mortality has been exceeded even without inclusion of these breeding season impact figures, and for gannet, guillemot, and razorbill, where Natural England already considers that there is a cumulative EIA level impact for the North Sea and Channel BDMPS.
B5 | 5 | The cumulative impact assessment for kittiwake contains numerous data gaps and cannot be considered comprehensive. However, given the total collision mortality estimates, as presented, amount only to a 0.27% increase in baseline mortality, and given the wind farm projects for which data are missing are generally small, we consider that the true cumulative impact is unlikely to exceed a 1% increase in baseline mortality across the UK Western waters and Channel BDMPS. No further action – Natural England simply wishes to state that the methodology used here would not be appropriate for other cases where impacts were more likely to arise on seabird receptors.
B6 | Summary (2), 6 | Natural England does not agree that the cumulative impact of Rampion 2 and other projects on great black-backed gull across the UK South-west & Channel BDMPS is not significant. A 1.99% increase on baseline mortality is significant in Environmental Impact Assessment (EIA) terms, and the PVA results show that this would severely impact the regional population, resulting in a population 19% smaller than the counterfactual after 30 years. The Applicant has not considered the magnitude of this result. The statement that while the national population is declining, the Isles of Scilly Special Protection Area (SPA) population is increasing, is inaccurate. The results of SPA surveys carried out in 2023 indicate that the Isles of Scilly SPA population has declined by 38% since 2015. While many of the figures presented by other wind farms may be precautionary, the Applicant has not taken into account the fact that the cumulative assessment contains numerous data gaps from older wind farms. We advise this is considered further. Natural England disagrees with the Applicant’s suggestion that the contribution of Rampion 2 to the cumulative total is small. Rampion 2 contributes 19.8 collisions out of a total of 90.5, and therefore, of the 20 projects listed in the cumulative assessment (of which only 8 have figures available – Table 12-50), Rampion 2 contributes 22%. |  | No change - additional material on this point was submitted at Deadline 1 which NE will respond to at Deadline 3. |  | The Applicant has provided further information, which we have provided comments on in Appendix B3. Natural England continues to advise that the impacts of Rampion 2 on great black-backed gull are likely to be significant at the EIA scale when considered cumulatively with other offshore windfarms. |  | No change
Document used: [APP-038] 5.9 Rampion 2 Report to Inform Appropriate Assessment
B7 | Summary (3), 7 | Natural England does not agree that the contribution of Rampion 2 to the in-combination assessment of collision risk to kittiwake, as a feature of Flamborough and Filey Coast SPA (FFC SPA), is so small that it is of no consequence. Prior to the Hornsea 3 OWF decision (which required compensatory measures), in-combination impacts had already reached a level where an AEOI could not be ruled out. As a result, particularly when considered with impacts from other soon-to-be submitted OWF proposals, additional impacts from Rampion 2 risk furthering the adverse effect. Natural England advises that further discussion with the Applicant is necessary to define and agree an appropriate compensation package for kittiwake in relation to the FFC SPA. See our comments on the derogation case below. |  | See comment on B13 below. |  | See comment on B13 below. |  | See comment on B13 below.
B8 | 8 | Natural England agrees with no AoEI in-combination for gannet in relation to FFC SPA (0.66-0.85 adult mortalities per annum).
B9 | 9 | Natural England agrees with no AoEI in-combination for Lesser black-backed gull (LBBG) in relation to Alde-Ore Estuary SPA, as it has been predicted that there would be less than one adult mortality across the entire lifetime of the project (predicted annual collision rate of 0.018 LBBG from the SPA per annum).
B10 | 10 | Natural England note that the Applicant has screen out great black-backed gull from the Habitats Regulations Assessment (HRA) in relation to Littoral Seino-Marin SPA, on the basis of perceived low collision risk with turbines. We advise that this species is at high risk of collision with turbines and therefore we advise that advice is sought from the French authorities in relation to the decision to screen this out.
B11 | Summary (4, 6) 11, 14 | Natural England does not agree with the Applicant that adverse effect on integrity can be ruled out for Flamborough and Filey Coast SPA due to impacts on guillemot and razorbill in-combination with other projects. We do not accept that the project-alone apportioned impacts are so low that there is not a detectable contribution to the in-combination effect. At the Hornsea 4 Examination, Natural England advised that AEoI could not be ruled out for these two species in-combination with other plans and projects, and there is the potential for effects from Rampion 2 to combine with those from projects likely to be submitted in the near future. Therefore, the effects of Rampion 2 in-combination with other projects should be properly considered, rather than assuming the contribution is not material. A full in-combination assessment of impacts should be presented for guillemot and razorbill for Flamborough and Filey Coast SPA. Natural England should be consulted on the results of this assessment, at which point we can advise on whether AEoI can be excluded. |  | No change - additional material on this point was submitted at Deadline 1 which NE will respond to at Deadline 3. |  | The Applicant has provided further information, which we have provided comments on in Appendix B3. As set out in our comments, AEOI cannot be ruled out in combination and therefore we advise that an in-principle compensation submission is made. Natural England met with RWE to discuss these comments on the 17/04/2024, we understand that they intend to submit an in-principal compensation proposal. |  | The Applicant has provided further information within a Guillemot and Razorbill Evidence and Roadmap, which we have provided comments on in Appendix B4. We broadly support the proposed approach and consider it proportionate to the level of risk. We advise that the next key step for the Applicant is to carry out a significant programme of monitoring at the shortlisted sites to establish the current level of disturbance each colony is subject to and to inform what compensation measures are likely to be effective. In terms of the compensation quanta, as with kittiwake we advise that the Plan presents these at ratios of 2:1 and 3:1 rather than just 1:1, and we also seek full detail regarding the calculations for the 'Hornsea 4 method'.
B12 | Summary (5, 6), 12, 14 | Natural England does not agree with the Applicant that adverse effect on integrity can be ruled out for the Farne Islands SPA due to impacts on guillemot in-combination with other projects. We do not accept that the project-alone apportioned impacts are so low that there is not a detectable contribution to the in-combination effect. Natural England advised Marine Scotland in relation to the Berwick Bank OWF that adverse effects on the Farne Islands SPA could not be ruled out due to impacts on guillemot from that project alone, and other consented /proposed projects could also impact the site. Therefore, there is the potential for effects from Rampion 2 to combine with those from Berwick Bank and other North Sea projects, and this should be properly considered by the Applicant, rather than assuming the contribution is not material. A full in-combination assessment of impacts should be presented for guillemot for the Farne Islands SPA. Natural England should be consulted on the results of this assessment, at which point we can advise on whether AEoI can be excluded. |  | No change - additional material on this point was submitted at Deadline 1 which NE will respond to at Deadline 3. |  | The Applicant has provided further information, which we have provided comments on in Appendix B3. As set out in our comment AEOI cannot be ruled out in combination and therefore we advise that an in-principle compensation submission is made. Natural England met with RWE to discuss these comments on the 17/04/2024, we understand that they intend to submit an updated document. |  | See comment on B11 above.
Document used: [APP-039] 5.10 Rampion 2 Habitats Regulations Assessment (Without Prejudice) Derogation Case
B13 | 13 | Natural England notes that the Applicant has presented a without-prejudice derogation case describing options for compensating for potential AEoI on kittiwake for Flamborough and Filey Coast. The most promising opportunity is the provision of additional nest spaces on an existing or proposed Artificial Nesting Structure (ANS) through a collaborative approach. This intervention is likely to be practicable and proportionate to the level of risk and given any AEOI will be in-combination with other projects, a collaborative approach is logical and appropriate. At present, insufficient details on the proposals are provided for the compensatory measures to be considered secured. We also consider that a Marine Recovery Fund (MRF) payment could provide an opportunity to contribute to strategic compensatory measures in the future but highlight that at present the MRF is not in place, and that limited information on the likely scope and delivery mechanism of the Fund is available. Therefore, it may be that at the point of decision-making, the Secretary of State may not have sufficient confidence in the MRF to mandate its use as a compensatory measure. The other measures set out in paragraph 6.2.27 of the derogations document are of uncertain merit and/or may be challenging to implement or effectively monitor, and therefore are not worth progressing further at this stage. We recommend that the Applicant develops the collaborative ANS option further, and that specific proposals (i.e. confirmed location of the ANS to be used, number of nest spaces to be provided etc.) are submitted into the Examination in due course through an updated Kittiwake Implementation and Monitoring Plan (KIMP). The Applicant should stay abreast of any progress with the MRF and update the Examination (and the derogations case) as required. |  | The Applicant has provided further details of the Kittiwake Implementation and Monitoring Plan at Deadline 1. We consider the proposal in relation to allocating nesting sites at an existing structure at Gateshead appropriate in relation to Rampion 2. We advise some further information is required as outlined in Appendix B2. |  | No change. |  | The Applicant has provided further details of the Kittiwake Implementation and Monitoring Plan at Deadline 3. We continue to advise that in relation to the scaling of compensatory requirements, the 95% Upper Confidence Interval impact is considered. These values have been provided in the updated Plan, which we welcome, though we note the Applicant does not support their use. We acknowledge that the Offshore Ornithology Engagement Group (OOEG) will now include multiple developers, and that further information has been provided on the sites to be monitored as part for the plan. Please see Appendix B4 for further detail.
B14 | 15 | Natural England does not generally support further deployment of onshore ANS, given the number of nest spaces that consented and submitted developments have already installed or are required to install in the future. As a result, we do not support the proposition that the recently installed onshore ANS on the River Tyne at Gateshead would provide appropriate compensation for the Dogger Bank South projects, noting that these 2 large Round 4 projects have not been tested through the Examination process. However, given the predicted level of contribution to in-combination effects, we do consider this ANS could provide compensatory benefits that would be proportionate to less impactful ‘extension’ projects such as Rampion 2.

## C - Marine Mammals
Point | Point Number (s) from Appendix C [RR-265] | Taken from Natural England’s Relevant and Written Representations Rampion 2 - Appendix C - Marine Mammals [RR-265] | RAG Status Rel and WR Rep, and D1 | Consultation, actions, progression | RAG Status at D2 | Consultation, actions, progression | RAG Status at D3 | Consultation, actions, progression | RAG Status at D4
Document Used: Chapter 12 Marine Mammals
C1 | Summary 6, Summary 11 | We have concerns over the definitions used for magnitude and sensitivity. The definitions of sensitivity and magnitude (throughout the Environmental Statement/within the Likely Significant Effect Matrix) could underestimate the likely impacts on marine mammals: a. The definitions of sensitivity have changed between the Preliminary Environmental Information Report (PEIR) and the application. Action: Define what a “significant level” of change is, in the context of the definitions of medium and low sensitivity. Review the sensitivity assigned in the individual impact assessments, and provide robust, transparent justification for the final sensitivity rating. b. There is little distinction between the definitions of low and medium magnitudes, leading to subjective conclusions. Action: The definitions of low and medium magnitude should be made clearer and/or the justification for one chosen magnitude over another should be made more robust in the species-specific assessments. c. Note that the defined terminology for magnitude should be used consistently throughout the document. The Applicant has not defined “negligible” magnitude and so this term should not be used in the assessment. |  | No change |  | No change |  | No change
C2 | 2 | Natural England have not had sight of the draft European Protected Species (EPS) licence application. The Applicant should consult Natural England on the draft EPS licence application (expected post consent). Natural England advise that this is considered sufficiently far in advance of the licence being required to ensure sufficient mitigation measures are in place, and for us to advise on any further measures that might be required. We would welcome sight of a draft as soon as possible.
C3 | 3 | There is a discrepancy in the number of pin pile foundations required for offshore substations; both 18 and 36 are listed in this table. The Applicant should clarify the correct maximum number of pin piles for the offshore substation.
C4 | 4 | Vessel disturbance may also occur when the vessels are in proximity to land during transit to/from ports. The Applicant should include information on known or likely ports and transit routes for the Rampion 2 project and should use this information to identify any seal haul out sites nearby that could be at risk of disturbance. The Applicant should detail known or likely port options, and proximity to known seal haul outs.
C5 | 5 | Whilst we welcome a commitment like C-275 regarding low order methods, we consider that the wording should be made stronger. This would align it with the imminent update to the joint position statement: https://www.gov.uk/government/publications/marine- environment-unexploded-ordnance-clearance-joint-interim- position-statement on Unexploded Ordnance (UXO) clearance. The statement will outline that low noise methods have to be the primary method of clearance. The statement will outline that low noise methods have to be the primary method of clearance. The Applicant should revise wording of commitment C-275.
C6 | 6 | The percentage of the Management Unit (MU) affected does not tally with the number of individuals affected for bottlenose dolphin and common dolphin. The Applicant should review the numbers in Table 11-31.
C7 | 7 and 8, Summary comments 12, 13 and 14 | The Applicant has not provided a Vessel Management Plan (VMP) but is relying on the VMP and mitigation measures therein in their assessment conclusions. Action: Provide an outline Vessel Management Plan. The VMP should include best practice measures to reduce the risk of seals flushing due to vessel disturbance. Disturbance to seal haul out sites and landfall can occur during the operation and maintenance (O&M) phase too. This should be acknowledged in the assessment, and the Applicant should clearly commit to following the VMP during the O&M phase to reduce this risk. |  | In lieu of a VMP, the Applicant has provided a “Proximity to Wildlife” document. The Applicant states that this document “will form part of the Vessel Management Plan”, which we infer will be produced post-consent, to comply with the DCO conditions. We advise it is not clear how this commitment (to develop parts of the VMP in line with the Proximity to Wildlife document) will be secured. Whilst the Proximity to Wildlife document includes some measures, it is stated that “A comprehensive code of conduct for vessel operators will be developed” (Section 3.2.3). We therefore infer that this document is an outline, and a further document will be created post-consent. We advise that it should be secured that Natural England will be consulted on the follow-on document that is produced post-consent. We advise that the measures listed in the outline document thus far are appropriate for an outline document. We note that a key measure (minimum distance) to reduce disturbance to seal haul outs is included. We note that the document lists relevant guidance (e.g. MWWC), and states that any new guidance will be incorporated to later revisions. It is also stated that the code of conduct will reduce risk “throughout all phases of the Project.” We have no further comments on the content of this document. |  | The DCO condition has been updated so that the Vessel Management Plan (VMP) will incorporate the Working in Proximity to Wildlife document, which Natural England welcome (Schedules 11 and 12 of the draft DCO, Condition 11(1)(f)). Natural England notes that the document states that is applicable to all phases of development, including construction, operation, maintenance and decommissioning. Natural England interprets this to mean that the VMP will be in place, applicable and enforced to all phases of development. This is due to the important ecological mitigations for marine mammal species within the protocol. We seek assurance that the Applicant and regulators also consider this to be the position with regard to this important mitigation document. Providing such assurance, would close out this issue. Natural England should be consulted on the VMP that is developed. |  | No change
C8 | 9 | The sensitivity of marine mammals to vessel disturbance should be the same irrespective of the phase of the Project. The Applicant should ensure sensitivity is the same across Project phase.
C9 | 10 | This table should present the relevant species-specific Management Units that each project is situated in. The Applicant include the relevant species specific MUs that each project in the cumulative effects assessment (CEA) lies in.
C10 | 11, Summary 7 | We are concerned that not all relevant projects have been included in the CEA for harbour porpoise disturbance. Table 11-37 presents less than half of the projects listed in Table 11- 35, and at a glance some of the omitted projects are in non-UK parts of the North Sea so should be in the relevant MU for harbour porpoise. The projects taken forward to the CEA should be reviewed to ensure it captures all the relevant ones, and that the impact presented (in terms of percentage of the MU affected) is correct. The Applicant should review the projects taken forward to the CEA for harbour porpoise and update the assessment if necessary We are unable to agree with the conclusions of the assessment at this stage. |  | We have reviewed the Applicant’s updated CEA for harbour porpoise (Table 11-37) and consider that the list of projects appears complete. The impact from the updated list has been revised; it is now 45,897 animals (13.2% of the MU), where previously it was 30,850. We advise that this number is higher than the number modelled by Booth et al. (2017) (34,396), which the Applicant uses as evidence of low likelihood of population-level effects (in paragraph 11.12.25). Therefore, we advise that the Applicant needs to provide further evidence that this higher number of animals impacted would not affect the overall harbour porpoise population trajectory. |  | No change |  | No change. Please also see our response to question Q3d-1 of [PD-011].
Document used: [APP-147] Volume 4, Appendix 11.1: Marine mammal baseline technical report
C11 | Summary 3 | Data Suitability and baseline characterisation - The survey data have not been used for the final baseline parameters (e.g. density, abundance) taken forward to the assessment; instead, the literature has been used.
C12 | 12 | The complete results of the site-specific digital aerial surveys have not been presented in the application. These should be presented for review. The Applicant should provide a separate document that has the complete results of the site-specific digital aerial surveys.
C13 | 13 | In the site-specific surveys there were many sightings of unidentified species (unidentified dolphin; unidentified dolphin/porpoise; unidentified seal etc.). These unidentified species have not been allocated to the identified species in the baseline characterisation. We advise that the worst-case scenario is to assume that all unidentified observations could be the specific constituent species. For example, all unidentified seals could be both harbour seals or grey seals, and so should be included in the density estimate for both harbour and grey seals. However, we are open to the Applicant proposing alternate ways to allocate unidentified species if preferred. The Applicant should allocate the unidentified species to specific species, then present the updated densities from the site-specific digital aerial surveys.
C14 | 14 and 15, Summary 4 | The Rampion 2 project now overlaps with the updated Coastal West Channel Management Unit (CWC MU) for bottlenose dolphin (see the March 2023 update to the MU document). The Applicant should update assessment of bottlenose dolphin so that it reflects the recent change in distribution of bottlenose dolphin that is reflected in the CWC MU boundary extension. Specifically, the Applicant should review and update the population abundance and density in the area. One approach to calculating density, which we suggest the Applicant presents, is to assume uniform density of bottlenose dolphin in the extended CWC MU. |  | No change |  | The Applicant has updated the baseline as requested. We do not have any further comments on the baseline. Following this the Applicant has revised their impact assessment using the updated baseline. However, Natural England do not currently agree with the assessment conclusions that the impacts on bottle-nosed dolphin will not be significant, and advise that further assessment and consideration of mitigation is needed. Please see our [Appendix C3] for further details. |  | No change
C15 | 16 | Natural England agrees that, based on the information presented, white-beaked dolphin can be scoped out of the assessment. Agreement.
C16 | 17 | The Applicant has stated that, for minke whale, they will use the Small Cetaceans in the European Atlantic and North Sea III (SCANS-III) data for the density estimate, even though this is not the highest estimate. We note the highest estimate is found in the Software Assurance Maturity Model (SAMM) survey; 0.012 whales/km2 in summer. It is unclear why the justification for using the SCANS-III data over the SAMM survey is applicable to minke whale but not other species e.g. common dolphin. The Applicant should clarify why the SAMM survey source/the most precautionary has not been used for minke whale density or use the most precautionary density estimate.
C17 | 18 | There appear to be 9 sightings on this figure, yet Table 8-1 only list a total count of 5. This difference should be clarified. The Applicant should clarify the difference in count between the figure and the table.
C18 | 19 | The Applicant has not presented the final density which they intend to use for harbour and grey seal. This should be specified here. It is noted that Table 10-1 states the density estimate will be grid cell specific. This information should be provided in Sections 8 and 9, and the approach clarified e.g. is the highest grid cell density in the 25 km radius of Rampion 2 being used, or the density within the zone of impacts? The Applicant should clarify in Sections 8 and 9 what density(s) will be used in the assessment.
C19 | 20 | The reference population for grey seals has been calculated based on the combined population of the South and Southeast England Seal MUs, rather than 50% of this combined total. This departs from Natural England’s advice in paragraph 8.3.1. The Applicant should update the grey seal reference population in accordance with Natural England’s previous advice.
Document used: Volume 4, Appendix 11.2 Marine mammal quantitative underwater noise impact assessment [APP-148]
C20 | 21 | This document does not appear to have been updated with the revised Maximum Design Scenario (MDS) e.g. it still refers to 116 turbines. All documents should reflect the submitted MDS. The Applicant should review and update document accordingly.
C21 | 22 | The first sentence states that most piling noise energy is between 30 – 500Hz, with some noise extending above 2kHz. The research quoted does not include any low frequency species, such as minke whale, and the summary of research by Finneran et al., 2015, only includes tests of noise above 1- 2kHz. We therefore consider that the Temporary Threshold Shift (TTS) notch at 2-10kHz is unlikely to be applicable to minke whales, as the tests used to ascertain this notch did not use the primary frequencies of piling noise that occur within the peak hearing range of minke whales (<1kHz). Review the sensitivity of minke whale to piling noise, particularly addressing the points made.
C22 | 23 | Natural England notes that The Wash harbour seal population has undergone a 20-30% decline in the last 5 years. Therefore, the Applicant’s justification that the sensitivity is low due to the increasing Wash harbour seal population despite offshore wind farm construction in the region should be reviewed. The Applicant should review the sensitivity of harbour seal to piling noise, particularly addressing the points made.
C23 | 24 | The Applicant has assumed that in the worst-case temporal impact is 1 day per location. We query whether this should be higher to accommodate the use of pin piles. How likely is it that 4 pin piles would be installed every day on which there was piling? Whilst not the worst-case scenario, we also query the temporal worst-case scenario for 2 monopiles being installed per day. The Applicant should review the worst-case number of pin piles (and monopiles) installed per day, potentially using other offshore wind farms as evidence.
Document Used: Volume 4, Appendix 11.3 Underwater noise assessment technical report
C24 | 25 and 26, Summary 1 and 2 | The number of piles and pile locations per day needs to be clarified. In the text the Applicant has stated that up to 2 monopiles and 4 pin piles may be installed in a 24-hour period (Section 3.2.2). However, the Applicant appears to have modelled simultaneous and sequential piling occurring within a 24-hour period (Tables 4-31 and 4-33). If both sequential and simultaneous piling is within the envelope, then theoretically up to 4 monopiles or 8 jacket pin piles could be installed in a 24- hour period (and indeed this is what is stated as the worst-case scenario in Appendix 11.2). The worst-case piling scenario in a 24-hour period must therefore be clarified, modelled and used consistently. It should also be clarified whether a maximum of 2 locations may be installed in a 24-hour period. In addition, the worst-case spatial extent of the noise impact (particularly for disturbance) requires review. We query whether the east and west locations are the worst-case in terms of spatial extent of underwater noise impact, given that the worst-case propagation occurs at the South and East locations (Section 4). Should this instead be South and East (or another location)? This may make a difference to the noise impacts that occur over larger spatial scales (e.g. disturbance assessment using noise contours). The Applicant should ensure that the worst-case spatial extent for noise impacts from simultaneous piling has been modelled, and update the assessments if necessary. |  | No change |  | No change |  | No change
C25 | 28 | Natural England notes that the underwater noise modelling has assumed a worst-case of a maximum 12 hours of operation in any 24-hour period. Evidence needs to be provided to support this assumption. The Applicant should provide evidence to confirm assumption that piling construction noise does not occur for more than 12 hours at a time.
C26 | 29 | Natural England expects that low order methods and/or noise abatement systems will be included in the suite of mitigation measures for UXO clearance. It would therefore be beneficial to model likely underwater noise impacts from these. The Applicant should model impact ranges from low order UXO clearance and abated UXO clearance.
C27 | 30 | The Applicant should use a maximum UXO weight of 750 kg in their modelling, as per Natural England’s best practice advice Environmental considerations for offshore wind and cable projects (this should also be updated in relation to fish). The Applicant should model the impact ranges from a 750 kg UXO as the worst-case scenario
Document used: [APP-038] Volume 5, 5.9 Report to Inform Appropriate Assessment
C28 | Summary 8 | Screening - We are satisfied that all sites/receptors have been identified.
C29 | Summary 9 | Methodology (impact assessment)- We are satisfied that all impacts have been identified.
C30 | Summary 10 | All marine mammal SACs have been screened out at Stage 1, no LSE.
C31 | 31 | Natural England agree that no English sites with marine mammal designated features are required to be taken to Stage 2 of the Habitats Regulations Assessment (HRA) i.e. Likely Significant Effect can be screened out. Agreement.
Document used: [APP-236] 7.14 Draft Piling Marine Mammal Mitigation Protocol
C32 | 34 | Recent evidence has shown an increased presence of bottlenose dolphins in the Rampion 2 area (see our comment on the ES) and so they could be present on-site during piling activities. This species should therefore be considered when selecting the final mitigation measures for piling. The Applicant should ensure that the final MMMP considers bottlenose dolphin.
C33 | 27, 32, 33, and 35, Summary 14 | We have several concerns regarding the MMMP: The acoustic deterrent device (ADD) duration is typically based on the permanent threshold shift (PTS) range. If the impact range is not presented for simultaneous piling, we query how an appropriate ADD duration can be calculated. The Applicant should consider this. The ADD is an important part of the mitigation measures and an appropriate duration is needed to demonstrate that its usage can reduce impacts to acceptable levels. The Applicant should present an approach to determining appropriate ADD duration for simultaneous piling. The MMMP should explicitly outline the soft start/ramp up procedure that has been modelled as the worst-case, and commit to not exceeding this soft start/ramp up profile. This will ensure that the worst-case impact ranges are not exceeded. Furthermore, the Joint Nature Conservation Committee (JNCC) guidelines for piling mitigation (https://data.jncc.gov.uk/data/31662b6a-19ed- 4918-9fab-8fbcff752046/JNCC-CNCB-Piling- protocol-August2010-Web.pdf) state that the soft start should be a minimum of 20 minutes. It is therefore not appropriate to have a soft start that is 7.5 minutes. The terminology used should match that in the guidelines and clearly demonstrate that the guidelines are being adhered to. We welcome the inclusion of at-source noise abatement methods in the draft MMMP, however, there is limited evidence on the noise reduction of various systems and their efficacy in the environmental characteristics of the site that may affect their deployment. We advise that the Applicant give due consideration to the uncertainties that exist regarding the levels of abatement that such measures might reach in the environmental conditions at the Rampion 2 site, such as the strength of the currents. |  | No change |  | No change |  | In reference to Document [REP3-051] 8.54 - Applicant's Responses to Examining Authority's First Written Questions (ExQ1), specifically Table 2-22 Marine Mammals, Ref MM 1.8, Paragraph 4 of the Applicant’s Response. For clarification, Natural England advises that the acoustic deterrent device (ADD) duration is based on the time needed for animals to flee the cumulative PTS zone, not the instantaneous PTS zone as stated by the Applicant in their response here. In their Marine Mammal Mitigation Plan (MMMP), the Applicant has presented the ADD durations needed for animals to flee the cumulative PTS zone (as well as instantaneous), therefore we inferred that the final duration of ADD activation had the option of being based on the cumulative PTS, which is what we would advise. We advise that we disagree that ADDs are not used to mitigate exposure to noise levels that could cause cumulative PTS. Therefore our point regarding appropriate ADD duration for simultaneous piling, based on cumulative PTS ranges, is outstanding.
Document used: [APP-237] 7.15 Draft Unexploded Ordnance Clearance Marine Mammal Mitigation Protocol
C34 | 36 | There are some details not presented in the UXO MMMP (but are presented in the piling MMMP). These include the outline ADD durations, and evidence on the reduction of noise from mitigation technologies. This information would be beneficial to present in the MMMP. The Applicant should consider this for the final UXO MMMP, to be developed at the post-consent stage.
C35 | 37 | We note that the maximum charge weight differs from Natural England’s best practice advice; 525kg rather than 750kg has been used. We advise that the measures in the draft UXO MMMP are sufficient up to the 525kg maximum charge weight that has been selected. If a UXO with a higher charge weight is found, the mitigation measures would likely need revising. The Applicant should consider this for the final UXO MMMP, to be developed at the post-consent stage.
C36 | 38 | For clarity, we do not consider that an application for an EPS licence contributes to the risk of PTS being negligible. Indeed, an EPS licence is only sought if there is still a residual risk of an offence occurring after the application of mitigation (in this case, PTS or an injury offence). By seeking an EPS licence the Applicant is acknowledging that there is still a risk of PTS occurring; therefore, the risk is not negligible. When applying for an EPS licence the Applicant will need to demonstrate that all satisfactory alternatives have been considered. The Applicant is already committing to the use of the low order clearance technique “deflagration” which we support. We advise that this technique (or a similar well- evidenced low order technique) is used as the preferred option for UXO clearance. Should high order clearance be needed, we advise that this is undertaken with noise abatement e.g. a bubble curtain. For the current position on UXO clearance please see https://www.gov.uk/government/publications/marine- environment-unexploded-ordnance-clearance-joint-interim- position-statement Note that this position statement is likely to be updated before the UXO MMMP is finalised. The latest position statement should be used to inform the final UXO MMMP. The Applicant should consider this for the final UXO MMMP, to be developed at the post-consent stage.
C37 | 39 | Natural England advise that UXO clearance is only undertaken during conditions that are conducive to visual monitoring (i.e. not during periods of fog, or high sea state (≥SS4). We do not recommend that PAM is solely relied on as mitigation for UXO clearance. For UXO clearance, PAM may be used to supplement visual observations only. The Applicant should include this clarification in the final UXO MMMP, to be developed at the post-consent stage.
C38 | 40 | Recent evidence has shown an increased presence of bottlenose dolphins in the Rampion 2 area (see our comment on the ES) and so they could be present on site during piling activities. This species should therefore be considered when selecting the final mitigation measures for UXO. The Applicant should consider this for the final UXO MMMP, to be developed at the post-consent stage.
C39 | 41 | The statement here by the Applicant does not mention the possibility of high order clearance without bubble curtains. We recommend that the Applicant consider committing to no unabated high order UXO clearance (should high order be required). As per our comment above the efficacy of noise abatement measures in the environmental conditions that exist at the Rampion 2 site should also be considered. The Applicant should consider this for the final UXO MMMP, to be developed at the post-consent stage.
Documents Used: 7.18 Offshore in Principle Monitoring Plan
C40 | Summary 14, Comment 42 | Currently the only post-consent monitoring that has been proposed is the industry-standard monitoring of underwater noise from the first 4 piles. Whilst the Applicant refers to the Marine Mammal Mitigation Plan (MMMP) there is no consideration of monitoring the effectiveness of the mitigation measures in reducing the impacts to acceptable levels. |  | No change |  | No change |  | No change
Mitigation Summary
C41 | Summary 13 | The embedded environmental measures outlined by the Applicant (in Table 11-14 in the ES Chapter 11 Marine Mammals) should be secured in the DCO/dML. Specifically: C-51 (Vessel Management Plan) – this should be secured for all phases of the project, C-52 (piling Marine Mammal Mitigation Plan), C-102 (UXO Clearance Marine Mammal Mitigation Protocol). We note that the Table 11-14 details that C-51 and C-52 will be secured in the DCO or dML conditions. C-102 will be secured through the application for UXO clearance works marine licence. Natural England query whether this secures that the final MMMP will be in accordance with the Draft MMMP submitted with this Application. There are also two other commitments Natural England strongly support in Table 11-14 and welcome the proposal to secure these in the dML: C-265 (piling noise mitigation technology), C-275 (low order detonations). |  | No change |  | The Applicant has responded on this point, clarifying where the measures are secured in the DCO/dML. Natural England has an outstanding concern noted in point C7 above. We note that, in the draft dMLs (Schedules 11 and 12 of the draft DCO, Condition 11(1)(m)), it is stated that the UXO MMMP will accord with the draft UXO MMMP, rather than the draft piling MMMP, which we agree with. We advise that this is consistently updated to close out this issue. |  | No change

## D - Coastal Processes
Point | Point Number(s) from Appendix D [RR-265] | Taken from Natural England’s Relevant and Written Representations Rampion 2 - Appendix D - Coastal Processes [RR-265] | RAG Status Rel and WR Rep, and D1 | Consultation, actions, progression | RAG Status at D2 | Consultation, actions, progression | RAG Status at D3 | Consultation, actions, progression | RAG Status at D4
Document Used: [APP-045] 6.2.4 Chapter 4 The Proposed Development
D1 | 1 | We note that Horizontal Directional Drilling (HDD) is to be used to install ducts that will house the cables under Climping Beach. Will any access be required to the beach? Furthermore, will cofferdams be required for the HDD exit pits? And have jointing bay depths taken into account potential changes in sea level and flood defence management over the lifetime of the project. Natural England advises that further information is required from the Applicant before we can fully advise on the potential impacts. This additional information and associated assessment should be provided within updated Application documents. |  | No change |  | No change |  | No change
D2 | 2 | Maximum sandwave clearance impact width, for the array and interconnector cables in the array area, is 10m and the maximum length of cables affected by sandwaves is anticipated to be 60km. Are these realistic? In terms of the length of cables likely to be affected by sandwaves, is there evidence from Rampion 1 that can be used to inform this maximum value? Furthermore, of the 60km quoted, what is the proportion of array vs interconnector cable length that is anticipated to be affected by sandwaves? Natural England advises that further evidence is required to support the realistic WCS parameters and Maximum Design Scenario (MDS) parameters as set out in the DCO/dML. Ideally, this would be included within an Outline Cable Specification and Installation Plan submitted to support the consenting phase |  | No change |  | No change |  | No change
Document used: [APP-046] 6.2.5 Chapter 5 Approach to the Environmental Impact Assessment
D3 | 3 | Graphic 5-4 sets out the general process of evaluating significance, incorporating magnitude of impact and value or sensitivity of receptor. The embedded matrix shows the categories for magnitude of change as: major, moderate, minor, and negligible. However, these do not agree with the definitions provided in Section 6.8 of [APP-047] Chapter 6 (Coastal Processes) which states that the categories for impact magnitudes are: high, medium, low, and very Low. Natural England requests that the Applicant provides further clarity on this matter and updates Application document s accordingly. Please note also that the Chartered Institute of Ecology and Environmental Management (CIEEM) do not advocate the use of a matrix approach to determining effect significance.
D4 | 4 | We note that Pre-Lay Grapnel Run (PLGR), Unexploded Ordnance (UXO) clearance and boulder clearance have not been considered for impacts on coastal processes. Yet they can lead to pressures such as abrasion/disturbance of the substrate on the surface of the seabed, changes in suspended solids, smothering etc. We advise that coastal process impacts due to PLGR, UXO clearance, and boulder clearance should be considered and assessed within updated Application documents. |  | No change |  | No change |  | No change
D5 | 5 | We note that jack-up vessels/anchoring may be used during construction. Have impacts to the seabed been assessed for spud leg/anchoring depressions? Natural England requests that if not already done so, these impacts are considered and assessed in an updated ES. |  | No change |  | No change |  | No change
D6 | 6 | The Executive Summary states that for the most part ‘coastal processes are not in themselves receptors…but are instead ‘pathways’ of effect. However, we highlight that there are a number of coastal processes receptors within the study area, including the coastline, sandbanks/sandwaves, and designated sites. Natural England requests that the applicant confirms that all coastal process receptors have been identified and therefore assessed. |  | No change |  | No change |  | No change
D7 | 7 | We note that the sandwave field within the array has not been included in the list of receptors. However, this is an important seabed morphological feature and potential supporting habitat which should be included in the assessment. Similarly, sandbanks (designated or otherwise) are important geomorphological features that may provide supporting habitat and should be identified as receptors and scoped into the assessment. Natural England advises that sandbanks/sandwaves are included within the list of receptors and the application documents are updated accordingly. |  | No change |  | No change |  | No change
D8 | 8 | Construction: Changes in Suspended Sediment Concentration (SSC) and deposition of disturbed sediments due to dredging, 3rd Column, Maximum Assessment Assumptions, Seabed Preparation Area. Total dredge/disposal volume of 19,500m3 is quoted for Offshore Substation (OSS) foundation, based on seabed preparation area of 100 x 60m x 1m x 3 OSS, but we query whether this should be 18,000m3 . Natural England requests that the Applicant checks these figures and ensures that correct volumes are included in any assessment and the DCO/DML.
D9 | 9 | Commitment C-283 – it does not state where the proposed gravel bags may be placed, or which areas of seabed may be affected. Natural England requests that the Applicant provides a map of gravel bag locations in order for us to agree with conclusions drawn on the significance of their use. Ideally, this would be included within an Outline Cable Specification and Installation Plan submitted to support the consenting phase. |  | Further information received in Doc. Ref. 8.25.13 and Offshore Works Plan regarding potential specifications and location of the gravel bag beds. However, we still have concerns regarding the significance of their potential impacts to the seabed and Climping Beach. |  | No change |  | No change
D10 | 10 | Methodology for ES Assessment – impact magnitude definitions and coastal process receptor sensitivity definitions have been provided, but no definitions are provided for the resulting significance of effects. Natural England requests that the Applicant includes the matrix, or other method used for determining significance of effect with an updated Application document. Without this, we are unable to agree with any conclusions drawn. |  | No change |  | No change |  | No change
D11 | 11 | We note that for the assessment of potential changes to the wave and hydrodynamic regimes, no coastal processes receptors have been identified. However, a reduction in significant wave heights on the downwind boundary could affect sensitive receptors that overlap with the wave shadow area (e.g. Kingmere MCZ). We advise that there are coastal process receptors which may be affected by changes to the wave and hydrodynamic regimes. These should be identified and assessed accordingly within updated Application documents. |  | No change |  | No change |  | No change
D12 | 12 | The minimum turbine spacing for the smaller and larger WTG options is 950m to 1130m, respectively. However, in the footnote, a minimum spacing of 830m for even smaller WTGs which could be employed, is provided. It also states that only relatively fine sediment is likely to be advected far enough to potentially cause overlapping effects of SSC. Natural England requests that the Applicant clarifies the separation distances for the proposed turbines and that plume dispersal range and settlement thickness are appropriately assessed within the application documents. If not, these would require updating.
D13 | 13 | We note that significance of residual effect has not been assessed for increases in SSC and deposition of disturbed sediments due to cable installation, on the basis that there are no coastal process receptors sensitive to the impact pathway. However, this impact has the potential to affect designated MCZ features which are identified as coastal processes receptors requiring assessment (see Table 6-6), We advise that significance of effect should be defined within the application documents. And where impacts on MCZ features are assessed in other documents, this should be signposted. |  | No change |  | No change |  | No change
D14 | 14 | We advise that cable protection measures installed at landfall represent a lasting rather than short-term/temporary change even if removed at the time of decommissioning. Consequently, we advise that the magnitude of change would be greater than low. We advise that the magnitude of change is greater than low for Climping Beach SSSI and the wider coastal morphology at the landfall. We advise that cable protection should be avoided within the depth of closure. An additional assessment should be carried out (e.g. wave modelling) based on the WCS for cable protection requirements. |  | No change |  | No change |  | No change
D15 | 15 | In 6.4.26.2, it states that the section of sea defence at the proposed landfall “is considered to be ‘very vulnerable,’ not just to overtopping, but also erosion and natural coastal realignment.” Natural England highlights that Climping Beach SSSI is a stretch of coast with a vegetated shingle beach, backed by a sand dune system, with the intertidal zone supporting important wintering birds. Vegetated shingle beaches are nationally uncommon and sand dune systems are fragile and susceptible to erosion. Thus, given that cable protection requirements are not presently known, we would advise that the sensitivity of the Climping Beach SSSI as well as the wider coastal morphology at landfall, is greater than medium. We note that the sea defences at Climping have failed in the recent storms, causing further coastal erosion and flooding. It is imperative that landfall HDD burial depths and cable protection options are adequately interrogated to future proof the asset integrity and prevent unnecessary coastal rock armouring. Especially as the shoreline management plan is to let the coast roll back, see: https://secoastalgroup.org.uk/media/2019/02/SelseyBill-to-Littlehampton-RBMP.pdf |  | The Applicant has provided further information, which we have provided comments on in Appendix DF 2. Our advice remains unchanged on this issue. |  | No change |  | Natural England note that the Applicant has stated in relation to the landfall location post consent 'The ground investigation will inform a coastal erosion and future beach profile estimation assessment which will advise regarding the need for and design of any further mitigation and adaptive measures to help minimise the vulnerability of these assets from future coastal erosion and tidal flooding.' Natural England advise that the consequence of these investigations being left to the post-consent phase is that the full significance of the issue and the likely effectiveness of the mitigation/adaptive measures are not adequately understood at the assessment stage due to the absence of this information.
D16 | 16 | Following on from our comments above, we advise that the significance of residual effect on morphology at landfall, including Climping SSSI, is greater than minor adverse and cable installation is an operation likely to damage the notified features of the SSSI. We advise that the residual effect on morphology at landfall, including Climping SSSI, is greater than minor adverse. Therefore, we advise that impact assessments are updated, and the mitigation hierarchy is adopted. |  | The Applicant has provided further information, which we have provided comments on in Appendix DF 2. Our comments remain unchanged on this issue. |  | No change |  | No change
D17 | 17 | Changes to the nearshore wave regime/longshore sediment transport due to the presence of cable protection measures have not been considered for the operational phase. Natural England advises that the Applicant needs to assess changes to the nearshore wave regime/longshore sediment transport due to the presence of cable protection measures during the operational phase. Ideally this would be included in an Outline Cable Specification and Installation Plan. |  | No change |  | No change |  | No change
D18 | 18 | Outer Owers Bank that overlaps, and sandwaves within the array, are coastal process receptors that may be affected by changes to the tidal regime. However, this has not been considered or assessed. Natural England advises that sandbanks/sandwaves that overlap/within the array areas are included within the list of receptors and assessed within updated application documents. |  | No change |  | No change |  | No change
D19 | 19 | It is stated that there is the potential for overlapping wake effects between Rampion 2 foundations and a small number of foundations in the adjacent Rampion 1 array. What is the extent and magnitude of these overlapping wake effects? Natural England advises that this should be considered and assessed, and any evidence from Rampion 1 included in updated application documents. |  | No change |  | No change |  | No change
D20 | 20 | Impacts to designated sites should also be included as receptors that could be affected by changes in the wave regime through the presence of the proposed development alone and in combination with Rampion 1. Natural England advised that this should be included by the Applicant in updated impact assessments. |  | No change |  | No change |  | No change
D21 | 21 | The use of cable protection measures within shallow, sandbank/sandwave, nearshore and intertidal areas have the potential to alter the sediment transport regime. However, this has not been included here. We advise that potential changes to the sediment transport regime due to the presence of cable protection within shallow, sandbank/sandwave, nearshore and intertidal areas need to be considered and assessed within updated application documents. |  | No change |  | No change |  | No change
D22 | 22 | With respect to changes at the coast, it is stated that “there will be no measurable reduction in wave height at adjacent coastlines…Accordingly, these changes are not predicted to have any measurable influence on alongshore and cross-shore sediment transport.” Is there any evidence from Rampion 1 regarding changes to the wave climate due its presence? Natural England advises that the Applicant includes/considers any relevant evidence from Rampion 1 regarding changes to the wave climate due to the presence of the wind farm within updated application documents. |  | No change |  | No change |  | No change
D23 | 23 | We note that the sensitivity of the sandwaves within the array has not been considered/assessed. In addition, the sensitivity and significance of effect have been evaluated for nationally and internationally designated sites, but not their magnitude of impact. Natural England advises that the Applicant assesses sensitivity of the sandwaves within the array. The magnitude of impact to designated sites also needs to be evaluated. Both of which should be included in updated Application documents. |  | No change |  | No change |  | No change
D24 | 24 | We advise, as with Rampion 1, that scouring around cable protection and cable crossings may occur in shallow water/nearshore. We advise that this needs to be considered and assessed by the Applicant and included in updated application documents. Noting that any remediation sound also be assessed. |  | No change |  | No change |  | No change
D25 | 25 | It is stated that there are no coastal processes receptors sensitive to the effects of scour. However, there are sandbanks/sandwaves overlapping/within the array areas. Therefore, the potential impact of scour to these seabed geomorphological features should be considered. We advise that the potential impact of scour needs to be considered and assessed within update application documents for sandbanks/sandwaves overlapping/within the array areas. |  | No change |  | No change |  | No change
D26 | 26 | The coastal stretch at landfall, including Climping Beach SSSI, is very vulnerable and the future of beach management works uncertain. Therefore, we advise that its sensitivity is likely to be greater than medium. We advise that the sensitivity of the coastal stretch at landfall, including Climping SSSI, is greater than medium. |  | No change |  | No change |  | No change
Document Used: [APP-129] 6.4.6.1 Appendix 6.1 Coastal Processes Technical Report Baseline Description
D27 | 27 | The Cefas suspended particulate matter (SPM) concentration are now quite old (1998-2015) and Rampion 1 is now part of the baseline. Are more up-to-date SPM data available? Natural England recommends that if available, the Applicant includes more up-to-date SPM data.
D28 | 28 | We note that there are a number of paleo-channels across the study area (export cable corridor and array areas) where the infill substrate maybe mobile or poorly consolidated. Are there any post-construction evidence/lessons from Rampion 1 regarding paleo-channel scour? We advise that scour monitoring may be necessary at these sites due to the unpredictable nature of the channel infill substrate and localised hydrodynamics. Include any evidence/lessons learned from Rampion 1. We advise that a Cable Burial Risk Assessment (including relevant geotechnical information) should be provided at the consenting stage to inform understanding of the potential for successful burial in paleo channels. |  | No change |  | No change |  | No change
D29 | 29 | We note that the model bathymetry was sourced from European Marine Observation and Data Network (EMODnet). Given that the bathymetry underpins the modelling, can the rationale be provided for not using up-to-date project-specific data? Natural England requests that the Applicant provides rationale for using EMODnet rather than up-to-date project-specific bathymetry data.
D30 | 30 | The Rampion 1 wave data used to locally validate the SEASTATES wave hindcast model were collected during November-December 2010. Similarly, the wave buoy data used to validate the model regionally are also old (2013), and pre-date the now built Rampion 1 array. Natural England advises that the Applicant must provide evidence-based justification as to how representative these data are of the present-day prevailing wave conditions across the study area. |  | No change |  | No change |  | No change
D31 | 31 | The SEASTATES wave hindcast model is shown to provide a close representation of wave conditions measured at wave buoys within and near the eastern Rampion 2 array. However, we note that none of the Rampion 1 wave buoys were located within the western array. How do the model data fit wave conditions at the western array? Natural England advises that best available evidence should be presented in updated application documents in order to support the current assessments. |  | No change |  | No change |  | No change
D32 | 32 | Were measurements of inshore wave conditions used to validate the model? Please can the Applicant clarify if/how present day inshore wave conditions informed the models used within the ES?
Document Used: [APP-131] 6.4.6.3 Appendix 6.3 Coastal Processes Technical Report Impact Assessment
D33 | 33 | The 2nd bullet point states that a representative current speed for the Rampion 2 offshore array area is 0.5m/s, which is representative of mid to higher tidal flow conditions, occurring on most flood and ebb cycles for a range of spring and neap conditions. However, we note that there is a marked variation in current speed across the array areas, from west to east, and north to south. Would it be more appropriate to use more than one current speed in the sediment plume modelling to represent these different conditions? We request that the Applicant provides evidence to demonstrate that this current speed is representative of flow conditions across the different arrays. This is important in terms of understanding whether a realistic worst-case scenario has been assessed. |  | No change |  | No change |  | No change
D34 | 34 | We note that there are no maps showing foundation/pin pile drilling plume maximum sediment plume concentration, spatial extent, and orientation, as well as associated deposition footprint. These are important for understanding potential impacts on sensitive receptors (e.g., benthic habitats, WFD water body status). We advise that maps should be provided by the Applicant to show anticipated maximum sediment plume concentration, spatial extent, and orientation, as well as associated deposition footprint. |  | No change |  | No change |  | No change
D35 | 35 | It is stated that there is limited field evidence of WTG installation into chalk using drill-drive methods, and the evidence provided is taken from Lynn and Inner Dowsing OWFs and environmental conditions may not be similar. Is there any evidence or lessons learned from Rampion 1 that can be drawn upon regarding the nature and evolution of drill arisings? Natural England advises that further assessment of drill arisings is required. |  | No change |  | No change |  | No change
D36 | 36 | The maximum Wind Turbine Generator (WTG) jacket dimensions at the seabed are 45 x 45m. Dredging to 70 x 70m. It is not clear why the dredged area will be 70 x 70m. Natural England requests that the Applicant provide further justification for the large dredge areas compared to foundation diameter.
D37 | 37 | As above. We note that there are no maps or schematics to show foundation and cable installation dredging plume model results. We advise that maps should be provided by the Applicant to show anticipated maximum sediment plume concentration, spatial extent, and orientation, as well as associated deposition footprint. |  | No change |  | No change |  | No change
D38 | 38 | We note that 1,375,000m3 could be dredged as part of the sandwave levelling/clearance in the Rampion 2 array area. Natural England advises the Applicant to provide further details including information on how sandwave recovery will be established following this activity, and how dredging could influence patterns of sediment transport and/or lead to morphological change should be included in updated Application documents. |  | No change |  | No change |  | No change
D39 | 39 | If the Trailing Suction Hopper Dredger (TSHD) operates in shallow water with small under keel clearance, there is the potential for the overspill plume to combine with a propeller wash plume due to scouring of the seabed. This propeller wash plume will release fines that are additional to those in the overspill plume and should be considered and assessed. Natural England advises the Applicant to consider and assess the relative contribution of fines to the passive/far-field plume due to propeller-induced bed erosion during dredging, where relevant. And update the Application where appropriate. |  | No change |  | No change |  | No change
D40 | 40 | We note that there are no maps or schematics to show cable burial plume model results. We advise that maps should be provided to show anticipated maximum sediment plume concentration, spatial extent, and orientation, as well as associated deposition footprint. |  | No change |  | No change |  | No change
D41 | 41 | We note that the recent Rampion 1 seabed analysis report (2023) identified exposure risk of short lengths of the export cables and array cables. The 2021 Rampion 1 seabed analysis report observed that all four export cables were experiencing an erosive trend, particularly towards onshore and near the offshore substation. Yet, the Rampion 1 Environmental Statement (ES) predicted that cable exposure would be unlikely due to their burial depth and the ability of the mobile sediments at the seabed to keep the cables buried. We advise that lessons learned and post-construction survey findings from Rampion 1 should be used to inform the cable burial depth assessment for Rampion 2. |  | No change |  | No change |  | No change
D42 | 42 | The assessment of changes to the wave regime due to Rampion 2 and the built Rampion 1 array has not considered impacts to the sandwave field in the eastern Rampion 2 array and Rampion 1 array. We advise that changes to the wave regime at the sandwave field should be considered and assessed by the Applicant in updated application documents. |  | No change |  | No change |  | No change
D43 | 43 | We note that the baseline tidal conditions have not been presented. Natural England advises that baseline tidal conditions (current and speed) for neap and spring tides should be presented in updated documents (i.e. maps) for the study area.
D44 | 44 | The assessment of change to tidal conditions due to the proposed scheme layouts has not been included. Natural England advises that an Assessment of change to tidal conditions due to the proposed scheme layouts should be provided (i.e. maps) to support Application documents. |  | No change |  | No change |  | No change
D45 | 45 | Cumulative changes to tidal conditions due to the presence of the proposed Rampion 2 scheme layout(s) and the built Rampion 1 have not been presented. Natural England advises that cumulative changes to tidal conditions due to the presence of the proposed Rampion 2 scheme layout(s) and built Rampion 1 array need to be presented by the Applicant to support their application. |  | No change |  | No change |  | No change
D46 | 46 | It is stated that during large storm events, ‘waves may stir the seabed within shallower parts of the offshore array areas, naturally causing an additional short-term contribution to SSC levels locally.’ It would be useful if these areas could be shown on a map.
D47 | 47 | We note that the assessment of predicted sediment transport regime changes has not been presented either for the proposed Rampion 2 scheme layout(s) alone or in combination with the built Rampion 1 OWF. Natural England advises that predicted sediment transport regime changes due to Rampion 2 alone and in combination with Rampion 1, should be presented. |  | No change |  | No change |  | No change
D48 | 48 | The evidence base for scour does not refer to Rampion 1 post-construction surveys. It is also stated that the erosion resistant (pre-Holocene) material is present at, or close, to the seabed in most parts of the western and northeast parts of the offshore array areas, which is likely to lead to a natural limitation of scour depth. Is there any supporting post-construction evidence from Rampion 1 that can be drawn on for the scour assessment? Natural England advises that best available evidence and/or lessons learned from Rampion 1 are submitted into examination within updated Application documents to support predictions of scour and scour protection requirement. |  | No change |  | No change |  | No change
Document Used: [APP-234] 7.12 Outline Scour Protection and Cable Protection Plan
D49 | 49 | We note that cable protection forms such as geotextile bags and polyethylene half shells are included as potential options. Natural England advises that where cable protection cannot be avoided, our preference is for the use of cable protection materials that match the receiving environment whilst also avoiding introducing plastics to the marine environment. Recoverability on decommissioning should also be considered.
D50 | 50 | We note that the Maximum Design Scenario (MDS) inter-array cable target burial depth is 1m, the proportion of array cable requiring protection is 20% and replenishment of cable protection during operations is 25% (of construction total). Have post-construction evidence or lessons learned from Rampion 1 been used to inform and validate these assumptions? Natural England advises that further information is required before we are able to provide further advice on the potential impacts. See also our related comments on Benthic Ecology. |  | No change |  | No change |  | No change
D51 | 51 | It is stated that in shallow water sections of the cable route, where ground conditions are not suitable to ‘ground out’ the export cable installation vessel on the seabed, the construction of temporary sand/gravel beds may be required. There are no details of these temporary sand/gravel beds or impact assessment. Furthermore, we note that the information provided here is not the same as presented in the benthic chapters. We request the Applicant provides further details of the temporary sand/gravel beds and assess their impact on the seabed/substratum. It is important that the proposed methodology for cable installation and its associated assessment of impact is consistent across all disciplines presented for review. |  | Further details on the placement and specification of the gravel bag beds have been provided, however our comments remain regarding their potential impacts. See also our comment D9 above. |  | No change |  | No change
D52 | 52 | We note that the target burial depth for export cables is 1-1.5m, and the proportion of export cable requiring protection is 20% and replenishment of protection during operations is 25% (% of construction total). Has evidence from Rampion 1 been drawn upon to inform the Rampion 2 export cable burial and protection requirement assessment? Natural England advises that further evidence is required to support the Application before we are able to provide further advice on the potential impacts. See also our related comments on Benthic Ecology. |  | No change |  | No change |  | No change

## E - Fish and Shellfish Ecology
Point | Point Number(s) from Appendix E [RR-265] | Taken from Natural England’s Relevant and Written Representations Rampion 2 Appendix E - Fish and Shellfish Ecology [RR-265] | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Status at D2 | Consultation, actions, progression | RAG Status at D3 | Consultation, actions, progression | RAG Status at D4
General Comments
E1 | 1 | We note that Natural England’s advice letter of the 14/07/2023, based on the Targeted meeting - Underwater Noise and Impacts on Fish Receptors, 30/03/2023, has been omitted. This letter contains key advice on outstanding issues and concerns in relation to black seabream as highlighted in the summary at the start of this section. We advise this document is updated to include consideration of our advice of the 14/07/2023. |  | No change |  | No change |  | No change
E2 | 2 | We note that the data sources used to inform the Environmental Statement (ES) Assessment appear to be up to 2020. We seek clarity that this has been updated since 2020, to ensure it includes current best available evidence in 2023? We advise this is reviewed and updated.
E3 | 3 | Natural England defer to Cefas on the assessment methodology and its conclusions in relation to herring and sandeel. We advise you refer to the comments of Cefas as advisors to the MMO on this matter.
E4 | 4 | We concur that sandeel are a key prey species in relation to tern species designated under the Solent and Dorset Coast Special Protection Area (SPA). We advise that tern species are also known to prey on herring. We advise that both species are considered as prey species for the tern features of the SPA throughout the assessment.
E5 | 5 | We note that the descriptions of significance in this matrix do not match the ones used in the text. We advise this is amended.
Worst Case Scenario
E6 | 6 | We note that there are inconsistencies between the worst-case scenario presented here in terms of piling and in Appendix 11.3, particularly in relation to the maximum duration of piling. These inconsistencies exist across all areas of the project and must be rectified. We advise that the assessment is updated to ensure the worst case is consistently presented across all the relevant documents. |  | No change |  | No change |  | No change
E7 | 7 | We note that for the interconnector cable the ‘maximum rock protection area for interconnector cables (based on 20% of 10km cable requiring protection) = 122,000m2’. However, we note in the project description chapter the length of cables is 40km rather than 10km. We advise this is corrected and the assessment updated as necessary. |  | No change |  | No change |  | No change
E8 | 8 | We advise that this table includes a line stating the figure number for the model of each of these scenarios. We advise all models need to include the boundaries of the MCZs for us to be able to understand the impacts on MCZ features. We note that Appendix 11.3 only models the following scenarios in relation to fish: Single location: • Worst-case monopile foundation – single pile • Worst-case monopile foundation – 2 sequentially installed piles Worst-case jacket foundation -single pile • Worst-case jacket foundation – 4 sequentially installed piles • Worst-case monopile/jacket foundation modelling using the Hawkins et al. (2014) Multiple Locations (2 locations): • Single monopile – installed simultaneously both E and W Locations • 2 sequentially installed monopiles – installed simultaneously at both E and W Locations • Single jacket pile – installed simultaneously at both E and W Locations • 2 sequentially installed jacket piles- installed simultaneously at both E and W Locations (noting the table refers to jacket piles, but the descriptions on figure 4.9 and table 4.37 refer to monopiles, one of which is incorrect) With regards to piling at multiple locations, only the impacts of 2 sequentially installed piles at two different locations at one time has been modelled. Therefore, it is unclear why Table 8.17 refers to more than four piles being installed simultaneously at the East and West locations. The spatial worst case appears to relate to Table 4.37 of Appendix 11.3. We advise explanation is provided on how 2 pin piles piled at the same time which require up to 2500kj hammer energy can create a greater worst-case scenario than 2 monopiles being piled at the same time with up to 4400kj hammer energy. We advise that clarity is provided on the worst-case scenario being presented and demonstration that this has been modelled. |  | No change |  | No change |  | No change
Mitigation
E9 | 9 | To avoid repetition between documents Natural England has included comments on commitments/mitigation once, but these comments should be referred to and considered wherever these are used to determine the assessment. To note.
Herring – Underwater Noise
E10 | 10 | Natural England defer to the advice of Cefas but based on the overlap with the Downs herring spawning ground (IHLS larval abundance data) shown in the Figures document, it seems unlikely to be appropriate that the magnitude of impact has been assessed as negligible for both TTS and behavioural impacts. We advise that you refer to the advice of Cefas on this matter, but Natural England highlight that the magnitude assign needs to be reviewed based on the IHLS data and that it is likely mitigation will be required. |  | Additional material pertaining to herring was submitted at Deadline 1 which NE will respond to at Deadline 3. |  | Natural England defers to MMO/Cefas with regards to the aspects of the new material that relate to herring. |  | No change
Black seabream (see also comments on the MCZ A [APP-040] relating to Kingmere)
E11 | 11 | We note that ‘A site-specific geophysical survey was undertaken between July and August 2020’. As Natural England have raised throughout the evidence plan process this only overlaps with the end of the spawning season for black seabream. Any data collected in August falls outside of the spawning season. The ‘Site-specific benthic grab and drop-down video (DDV) surveys were also undertaken between December 2020 and February 2021’, far outside of the black seabream season. Natural England therefore disagree that this information can be relied upon ‘to supplement existing data on likely black seabream nesting locations in areas relevant to the Proposed Development, but outside of areas previously subject targeted survey (principally within the Kingmere MCZ)’, given the timing of the surveys. Natural England disagree that the data sets referred to ‘allows a conclusion to be drawn that nests are likely to be present across a discrete area of the export cable corridor, and as such demonstrates the data to be representative and robust for the purposes of EIA’. We advise there is also no evidence presented to justify the statement ‘that the assessment takes a precautionary approach’. Natural England advises that the aggregates data is spatially discrete and therefore does not fill data gaps for areas outside of these boxes. We advise areas located outside of these survey boxes should not be considered to be absent of black seabream nests. Point 8.6.80 also suggests ‘Sussex IFCA data indicated that the majority of black seabream nest areas in 2014 fell outside of the repeat monitoring areas’. Whilst the assessment has some recognition of the limitations, we advise that these should be fully acknowledged, particularly in relation to the limited confidence they give to the baseline data, and the assessment revisited to account for the uncertainty introduced. Natural England advises that the aggregates data is useful in terms of avoidance of known nests, but should not be considered to suggest nesting does not occur outside of the survey boxes. In the absence of a robust dataset, we advise the assessment must therefore assume that nests could be present in the closest point of the MCZ to any activity. |  | No change |  | No change |  | No change
E12 | 12, summary 12, 94 | It is stated that ‘The post consent survey, undertaken as part of a suite of pre-construction surveys, will allow a determination to be made as to the extent of the nesting area, and specifically the key nesting areas, in order to identify the best cable route, minimising interaction with key sensitive features where practical, prior to offshore export cable installation’. Natural England advise that due to both seasonal variation and interannual variation with regards to nesting locations a single pre-construction survey should not be presumed as definitively and absolutely defining nesting locations. We advise that the focus should be on ensuring that that survey identifies potentially suitable habitat for nesting and avoids this. We advise that an appropriate methodology for pre-construction surveys has yet to be agreed and that this should be agreed with the MMO in consultation with Natural England. Whilst we understand that the final details of this are likely to be agreed post-consent, we advise that an outline plan should be included in the In Principle Monitoring Plan. The micro-siting should focus on avoiding the areas identified in these surveys and also known nesting locations. |  | No change |  | No change |  | No change
E13 | 13 | It is stated that ‘Historical analysis of black seabream monitoring data identified black seabream nesting areas tend to correspond to shallow waters (<10m) with thin layers of coarse sediments (10 to 30cm deep) overlying bedrock within the general vicinity of rocky outcrops (GoBe, 2015). BGS data identified areas of chalk beds within the intertidal area of the offshore export cable corridor and within the north-eastern tip of the array area (see Figure 8.13, Volume 3 of the ES (Document Reference 6.3.8))’. However, the data presented in 8.13 is broadscale. Additionally, no key is provided to explain what the area shaded in each colour signifies. Natural England advises consideration is given to what site-specific information could be gathered pre-consent to strengthen this information. We advise this information could be used to improve confidence in avoiding suitable black bream nesting habitat were possible within the cable corridor. |  | No change |  | No change |  | No change
E14 | 14 | We advise that it is important to distinguish bream as a feature of a designated site in a key nesting location (Kingmere MCZ), from the general population described over a wide area in this paragraph. We advise clarity is provided on this throughout the ES chapter and the MCZ assessment. |  | No change |  | No change |  | No change
E15 | 15 | The current licence conditions for Area 453 are incorrectly stated. We advise this is confirmed with the MMO and corrected in the text. Our understanding is that the relevant condition on the licence for 453 states ‘All licensed activities must not be undertaken in the Eastern Section of Area 453 (Zone B) between 1st April and 31st July inclusive, and in the Western Section of Area 453 (Zone A) between 1st April and 30th June’.
E16 | 16 | Natural England advise that the data presented here does not represent the full best available evidence base. This is because further surveys were conducted in 2022 and reported in March 2023. We advise that the ES is updated to reflect this data, particularly in relation to reproductive activities in July. We advise that the aggregates data supports reproductive activities occurring in July over multiple years of data. Natural England’s position is that the aggregates data supports our understanding that reproductive behaviour occurs in July, hence the inclusion of July in the sensitive season in line with the conservation advice. Therefore, we advise July should not be regarded as less important in relation to mitigation measures proposed.
E17 | 17 | It is stated ‘Site specific data indicate that the area surveyed as part of the aggregate extraction monitoring is likely to represent a discrete area of sediment veneer that does not extend across the full export cable corridor’. We advise a reference to this information is provided to support this statement. We agree that it should be considered that direct impacts on spawning areas are still possible.
E18 | 18 | It is stated that ‘there is a risk of direct disturbance to areas of nesting and / or nesting potential that may not be avoidable. Whilst a specific environmental measure has not been embedded within the design of the Proposed Development at this stage, there are a suite of measures available to reduce the magnitude, and therefore significance of direct disturbance (see RED, 2022)’. Natural England understood that the Applicant had committed to avoiding direct impacts on all known black seabream nesting areas in the first instance, where possible. Whilst we understand that mitigation measures have been proposed, greater confidence is required in the efficacy, as well as their potential to succeed, in the seabed conditions along the cable route. The Applicant needs to demonstrate that these measures will be effective or introduce additional mitigation. |  | No change |  | No change |  | No change
E19 | 20 | Natural England support black seabream (as well as herring, sandeel, and seahorses) being modelled as stationary receptors, we do not consider fleeing receptor models appropriate for these species. We therefore advise any reference or modelling of fleeing receptors should be disregarded in relation to these species. |  | No change |  | No change |  | Please refer to our appendix E4 comments reiterating this point in relation to information provided at deadline 3.
E20 | 21 | Natural England question why the south modelling location has been considered the worst case within the array area. We not this is not the closest modelling location to Kingmere MCZ or Beachy Head West MCZ. We advise that justification is provided in an updated assessment. |  | No change |  | No change |  | No change
Underwater Noise – Proposed Commitments
E21 | 22 | A piling Marine Mammal Mitigation Protocol (MMMP) will be implemented during construction. A Draft Piling Marine Mammal Protocol (Document Reference 7.14) has been submitted with this application, which includes soft start procedures. Natural England consider the MCZ features (particularly black seabream and seahorses) to be effectively static features, therefore mitigation measures that relate to fleeing features are not applicable. We therefore advise it is removed from the assessment in relation to these features, and more appropriate mitigation presented. |  | No change |  | No change |  | No change
E22 | 23, 73, 83, 90 | Commitment 274, 280,281: 'Commence piling at locations furthest from the MCZ the Kingmere MCZ during the black seabream breeding period (March-July)'. 'No piling will occur in the piling exclusion zones during the seabream breeding period (March-July) which will be defined by the modelling in the Final Sensitive Features Mitigation Plan'. 'No piling within the western part of the Rampion 2 offshore array closest to the Kingmere MCZ during the majority of the black seabream breeding period (March - June); and sequenced piling in the western part of the Offshore Array Area during July in accordance with the zoning plan to be set out in the Final Sensitive Features Mitigation Plan'. Based on the modelling for the worst-case scenarios provided, we consider that piling at locations further from Kingmere MCZ, could still result in TTS and behavioural impacts within Kingmere MCZ. Therefore, we are not persuaded that this mitigation would prevent the conservation objectives being hindered. We advise that based on the evidence presented to date, our outstanding concerns around the lack of a suitable threshold and the likely efficacy of mitigation measures in the specific environmental conditions of the development site, the exclusion should cover all piling works March to July inclusive, inclusive in line with the sensitive season for spawning/breeding black seabream in the conservation advice for Kingmere MCZ. We advise this is the appropriate length of the piling restriction needed to avoid hindering the conservation objectives of the MCZ. This is Natural England’s position. Our position that a full seasonal restriction is required has not changed from Rampion 1. We also question if the worst-case scenario including simultaneous and sequential pilling has been considered in the mitigation plan. If not, this should be reviewed. We highlight that there is a risk that delaying the production of a final mitigation plan to the post-consent phase will result in disagreement and delay, and urge the Applicant to bring something forward prior to consent that Natural England can agree. |  | No change |  | No change |  | This remains Natural England's advice. Please see our deadline 4 advice in Appendix E4 and N4.
E23 | 24, 102, 110 | Commitment 265: 'At least one offshore pilling noise mitigation technology will be utilised to deliver underwater noise attenuation in order to reduce predicted impacts to sensitive receptors at relevant Marine Conservation Zone (MCZ) sites and reduce the risk of significant residual effects on the designated features of these sites'. Notwithstanding Natural England’s current concerns regarding the efficacy of mitigation measures, we advise that instead of being one measure, this commitment should be to use the noise abatement combination that achieves the greatest amount of noise reduction year-round. It is stated that ‘Assumptions on attenuation performance of the noise mitigation techniques are based on demonstrable performance of the technology, to ensure confidence in delivering the required noise level reductions’. In relation to reducing impacts on MCZ features to an acceptable level, it needs to be demonstrated that the mitigation will be sufficient given the environmental conditions in the Rampion 2 array to reduce noise to an agreed level within the MCZ’s. Environmental conditions that could affect efficacy, include factors such as depth, the speed of local currents, wave height, wind speed and geology. We advise we are not aware that a full comparison between environmental conditions at test locations and those at Rampion 2 has been conducted. We understand that the Applicant to date has not had this information, and therefore we disagree that confidence in the noise attention to be achieved has been provided. We note that the Applicant has also proposed combining mitigation measures to achieve higher level of attenuation. We advise that no evidence is provided to support this being viable, or that it is possible to achieve these values through a combination of measures. We advise that full comparison of environmental conditions is undertaken, to aid in providing further confidence in the levels of abatement proposed. We advise this information needs to be submitted into the Examination. We advise further evidence is provided to have confidence that combing measures to achieve the values stated is viable. |  | No change |  | No change |  | This remains Natural England's advice. Please see our deadline 4 advice in Appendix E4 and N4.
Black seabream – Underwater Noise Assessment - Mortality and potential mortal injury, and Recoverable injury
E24 | 25 | It is stated that ‘Although it is likely that potential predators will also vacate the area during potential piling thus limiting this potential effect’. Natural England advise that no evidence has been presented to support this statement. We are aware that observation of nests in Dorset included predation by invertebrates such as whelks and urchins. We advise it should not be assumed that resident animals will have both the swimming capability and incentive to vacate the area, particularly if they are territorial/highly residential animals. Natural England advise that no evidence has been presented to support this statement, we advise this is provided or this assumption is removed from consideration in the assessment. |  | No change |  | No change |  | No change
E25 | 26 | We note that the 100km2 is stated as the underwater noise search area in the cumulative effects section. However, the distances stated for simultaneous piling are significantly greater than this. We advise the use of 100km2 to define the underwater noise study area across the documents, may not represent the worst-case scenario. We advise that the appropriateness of the 100km2 search area is re-considered, and further justification is provided. |  | No change |  | No change |  | No change
E26 | 27 | Natural England do not agree that the modelling locations used represent the worst-case scenario within Kingmere MCZ. We advise that modelling from the location within array area closest to the MCZ would appear to represent the greatest potential for overlap for a single pile. Visually it appears a location to the northeast of the current north-western modelling location could result in greater overlap with the MCZ in relation to 207dB, 203dB, and 186dB contours. Additionally, where piling is conducted simultaneously at two locations in terms of the MCZ we question what the closest distance between locations is likely to be, and how this is considered in terms of impacts on the MCZ. Currently the east and west locations appear to represent one of the better cases for the MCZ, as opposed to the closest together possible piling locations in closest proximity to the MCZ. We advise further explanation is required on this before Natural England can agree on there not being a significant impact in relation to mortality, potential mortal injury and recoverable injury of black seabream. We advise that further explanation and justification is provided to explain how this has been considered. |  | No change |  | No change |  | No change
E27 | 28 | Natural England advises that it is the interaction with the boundary of the MCZ that should be referred to here, and not the perceived highest density nesting locations within the MCZ. We advise this needs to be amended across the assessment. In relation to recoverable injury, we seek clarity that this contour does not overlap with the MCZ in any of the worst-case scenarios. We note that Figure 8.18 for example seems to show this contour on the boundary not going into the MCZ. We advise that should any of the worst-case scenarios involve the 203dB contour overlapping with the MCZ (even over a small area) this is likely to change our advice on this matter. We advise that clarity is provided here in relation to the interaction with the boundary of the MCZ. |  | Additional material was submitted at Deadline 1 which NE will respond to at Deadline 3. |  | Natural England have provided advice on the additional material submitted in Appendix E3. This information has not changed our position on this point. |  | No change
E28 | 29 | Black seabream are protected by Kingmere MCZ, and under the second conservation objective this specifically includes ‘the population (whether temporary of otherwise) of that species occurring in the zone be free of the disturbance of a kind likely to significantly affect the survival of its members or their ability to aggregate, nest, or lay, fertilise or guard eggs during breeding.’ Natural England advise that this protection is afforded as black seabream are considered to be highly vulnerable during the breeding season due to their specific nest locations and nest guarding behaviours, which mean expending more energy, reducing their feeding opportunities, and increasing their predation risk. Overall, these behaviours take an increased physiological toll compared to non-breeding behaviours, and impacts affect larger proportions of the local population, and so during the breeding season the black seabream have a heightened sensitivity to disruptive impacts. Therefore, we advise that they are treated as a receptor with high sensitivity to impacts from underwater noise throughout the noise assessment. The current sensitivity of medium only takes into account the hearing sensitivity of the species and not the ecological sensitivity, effectively treating its behaviour as simply normal shoaling activity as opposed to specific black seabream spawning behaviours. We advise that the sensitivity is amended to high. |  | No change |  | No change |  | No change
E29 | 30 | Natural England disagree with the downgrading of the magnitude of impact based on there being ‘limited interaction with the areas of primary importance’. We advise clarification is provided that the area of primary importance included the closest boundary of the MCZ. We advise this is clarified and if it is not MCZ boundary it is amended to this. |  | No change |  | No change |  | No change
Black seabream – Underwater Noise Assessment - Temporary Threshold Shift
E30 | 31 | Natural England note that there is an interaction between the TTS contours and Kingmere MCZ. Based on the information presented Natural England does not have confidence the mitigation presented in C-265, C-274, C-281 will be sufficiently effective. Therefore, we do not agree that the impact can be consider negligible for TTS. We advise that an assessment with and without mitigation is provided to present the worst-case scenario. We advise that based on our lack of confidence in the mitigation measures, we cannot conclude that the conservation objectives of Kingmere MCZ will not be hindered by this impact. We advise that information on the efficacy of the migration measures proposed in the same environmental conditions as are present at the Rampion 2 site is presented to demonstrate confidence that the noise levels would not exceed 186dB within the MCZ boundary. |  | No change |  | No change |  | No change
Black Seabream – Underwater Noise Assessment - Behavioural impacts
E31 | 32 | Breeding black seabream exhibit breeding behaviours that if subject to a behavioural response could even in the short-term lead to effects breeding success that could be significant. We strongly disagree that these effects can be considered to have no wider effect on the MCZ feature, considering the impacts of potentially failed breeding at Kingmere across the local population (given site fidelity) and in the light of the conservation objectives of the MCZ. We therefore advise that the application of the concept of acclimatisation to noise is inappropriate in this instance. This is because even if acclimatisation where to occur, the time frames over which it may occur would mean that it is likely this effect would have already had a significant impact on the breeding success of bream before this point, and that it is feasible breeding attempts could have failed for that year. We advise that this is Natural England’s position on this point and that habitation is not taken into account within the assessment. |  | No change |  | No change |  | No change
E32 | 33 | In relation to black seabream as a feature of Kingmere MCZ, Natural England does not support a behavioural threshold being derived for black seabream from studies that: • Are a proxy species for black seabream, as opposed to directly studying black seabream; • Are based on playback, particularly when this is in a tank and does not represent well the effects of particle motion that would be expected as a result of pile driving in the open ocean; • Are undertaken in captivity as opposed on receptors in the wild; • Use for example an air gun as opposed to a noise source akin to piling noise; • Are conducted within a quiet loch as opposed to the open sea. We advise that this is Natural England’s position on this point. |  | No change |  | No change |  | No change
E33 | 34 | Natural England disagrees with the addition of 30dB to the background noise levels based on the Radford et al. (2016) study, which was conducted on seabass, in a laboratory conditions and based on playback. We note Radford et al (2016) noted increases in ventilation rate (a secondary indicator of stress) due to noise increases which were less than 30dB above ambient levels. Therefore, we do not support the use of this study to justify a lack of behavioural disturbance for black seabream above ambient noise levels. We advise that Collett et al. (2012) included a temporally limited measure that is now 11 years out of date. Therefore, this cannot be relied upon as evidence. We also advise that consideration needs to be given to the fact that naturally occurring peaks are unlikely to represent a continuous noise source in the same way piling would. We understand Cefas have concerns with background noise being defined as peaks, as opposed to minimums. |  | No change |  | No change |  | No change
E34 | 35104 | Natural England does not support the use of 141dB re 1uPa SELss (taken from Kastelein et al. (2017), as a threshold for black seabream behavioural disturbance and we do not agree that the threshold is highly precautionary. Natural England advise that this study cannot be used to predict fish behavioural responses to pile driving in the natural environment because: • The experiment was conducted in a bare 7m x 4m container, in which seabass occupied 25% of the space. As recognised by the authors, this highly artificial environment permits only a narrow range of natural responses. • The noise stimuli was produced by playing recordings of piledriving through speakers. As recognised by the authors, this method is highly limited and does not replicate pile driving at sea (e.g. the playback range was inhibited by the capacity of the speaker). • Behavioural response was monitored by video from a distance, and response classifications were based on the collective behaviour of the school. Individual physiological responses were not recorded (such as ventilation rate, blood chemistry) and neither did the survey design permit investigation of natural behavioural changes or subpopulation level impacts. • The study tested only 7 pre-defined noise levels, not a continuous spectrum. The lowest level of noise tested was 122dB re 1 mPa2 s which did elicit some responses in the main study (i.e. it was perceived and reacted to by some of the seabass). Additionally, we advise that this study is not suitable to assess noise impacts to nesting black seabream in Kingmere MCZ for the following reasons: • The study was based on adult seabass, which do not exhibit demersal nest guarding or the breeding behaviours protected by Kingmere MCZ. • Natural England recognise that seabass and black bream are in the same hearing category, but note this is based solely on a grouping of physical characteristics and lacks any species-specific information or context. We advise that fish are extremely diverse and exhibit complex behaviours in response to a changeable environment. The authors of Kastelein also make this point: ‘Trying to predict behavioural responses simply by using energy in a model is not realistic, as responses to sound depend not only on the received level, but also on a large number of other sound parameters, the context, and parameters relating to the animal’.• The study found a 50% initial response threshold occurred at an SELss of 141 dB re 1 mPa2 s for 44cm sea bass. We note that 31cm seabass demonstrated a 50% initial response threshold occurring at 131 dB re 1 mPa2 s. Given Natural England’s conservation advice suggests that juveniles black seabream mature at around 20cm in length as females and are commonly 35cm in length, we advise the use of a threshold for a larger 44cm sea bass is clearly not appropriate. • Seabass are broadcast spawners with pelagic eggs, and therefore they do not exhibit the same spawning, nesting and nest guarding behaviours as black seabream. This crucial element of black seabream ecology, as specifically detailed in the conservation objectives for the MCZ, needs to be duly considered in the impact assessment. We highlight that Natural England’s has advised against this approach throughout the evidence plan process. We note that Figure 6 of Appendix 8.3 shows that even with using a 141dB re 1uPa SELss, this noise contour covers the entirety of Kingmere MCZ. This Appendix also references Kojima et al. (2010), which relates to red seabream, which is again inappropriate as this species does not have the same spawning behaviours as black seabream. Natural England advise that any behavioural threshold must be specific to the species (black seabream), the site (Kingmere MCZ) and the conservation objectives (breeding/spawning behaviours of black seabream) in order to successfully quantify and mitigate for the impacts. Currently Natural England’s advice is that we cannot conclude that the behavioural disturbance impacts of the project would not cause the conservation objectives of the MCZ to be hindered. We note in point 8.9.266 it is stated that ‘the use of the identified thresholds to inform the assessment of behavioural impacts on fish and shellfish is not supported by RED’ due to the lack of understanding of how a wild animal will respond and viability in existing noise studies. Natural England advise that when coupled with all the existing issues in this specific case, it does appear unlikely a suitable threshold can be agreed. We advise that this is Natural England’s position on this point. |  | No change |  | No change |  | No change
E35 | 36, 106 | Natural England support a further noise study being undertaken in 2023, given the temporal limitations of the previous 15-day study. Our understanding was that whilst this longer dataset would not be included with the ES, this would be available for the examination. Natural England advise that we are not content for this information to only be provided at the post-consent stage. We also advise that once this data is available there is still no certainty that a suitable behavioural threshold could be derived and agreed from this. We advise that this data is provided as soon as possible. |  | We provided comments on Appendix 8.4: Black Seabream Underwater Noise Technical Note and Survey Results - Revision A [PEPD-023] at deadline 1. Our comments on this can be found in Appendix E1. The information within this report does not change our position. |  | No change |  | No change. We advise that this study also needs to be acknowledged and considered within an updated IPSFMP.
E36 | 37 | We advise that the efficacy of the measures in the environmental conditions of the Rampion 2 location has not been satisfactorily demonstrated. Based on the lack of evidence to derive a suitable threshold, even if the mitigation measures could be proven to achieve the level proposed, we advise this would not be sufficient to justify a Negligible magnitude of impact. We advise that in the context of the MCZ this should be a Major impact (i.e. there is a significant risk of the activity hindering the MCZ conservation objectives). We advise that the magnitude of impact is revised. |  | No change |  | No change |  | No change
E37 | 38 | Given the proximity of Kingmere MCZ to both the cable corridor and the array, and the fact this is a designated feature of this protected site, their sensitivity to disturbance during the breading/spawning season, Natural England advise that the sensitivity of this feature should be high. We advise that the sensitivity is revised. |  | No change |  | No change |  | No change
E38 | 39 | Due to our disagreement with both the magnitude of impact assigned to this assessment and the sensitivity of the receptor, we do not agree that this impact can be considered not significant. We advise that this is revised in line with our comments above. |  | No change |  | No change |  | No change
Seahorses (see also comments on the MCZ Assessment for seahorses below)
E39 | 40 | We note that one short-snouted seahorse (Hippocampus hippocampus) was found in the October to November 2011 surveys and three in the February 2012 surveys. Two were found in the north-eastern part of the Rampion 1 array and two in the western part. We note that short-snouted seahorse were also found in three post- construction trawls conducted in the autumn. We note this is evidence of the potential for seahorse species to be present in the area, particularly overwinter (when they are understood to move offshore). We advise that the fact that they have been found on multiple occasions from surveys that only offer a short snapshot in time, indicates their consistent presence, but that conclusions should not be drawn on them only being found in low numbers throughout the assessment based on this. The assessment should be updated to reflect the this. |  | No change |  | No change |  | No change
Seahorse – Underwater Noise - Mortality and potential mortal injury, and recoverable injury
E40 | 41 | We seek clarification that that the locations modelled represent the closest location piling could occur in relation to each MCZ designated for seahorse. We advise clarity is provided and the assessment updated if needed. |  | No change |  | No change |  | No change
E41 | 42 | Given there are MCZs designated for seahorses surrounding the site, and seahorses were found during the Rampion 1 surveys, Natural England advise there does not appear to be any evidence to support the Applicant’s statement that they are ‘not present in significant numbers’. Additionally, it should be considered that a significant proportion of the local population may not have to be a large number. We advise that impacts on the scale of kilometres could span the entire range of local populations and so potentially pose a significant risk. We advise the assessment is amended in line with our advice. |  | No change |  | No change |  | No change
E42 | 43 | Natural England understand the Applicant has predicted no overlap (of the underwater noise contours relevant to this impact) with the MCZs designated for seahorses. Based on the reasoning in our comment to 8.9.74, we do not agree that the Applicant can determine the risk of impacts on seahorses outside of the MCZ’s is low when they could feasibly be present in the array area. Both species of the UK seahorses - spiny (Hippocampus guttulatus) and short-snouted - are protected under Section 9 of the Wildlife and Countryside Act 1981. We advise that the Applicant is aware that there is a possibility of seahorses being killed or injured, disturbed, or damage or destruction to their place of shelter or protection, all of which are offences under Section 9. We advise that it is therefore not appropriate to consider the magnitude of impact on seahorses to be negligible. We advise the assessment is amended in line with our advice. |  | No change |  | No change |  | No change
Seahorse – Underwater Noise - Temporary Threshold Shift
E43 | 44 | Natural England note that there is an interaction between the TTS contour and Beachy Head West MCZ. We note that the wording of commitment C-265 does not reflect the wording in the MCZ Assessment. Our understanding is the commitment is a minimum of one noise abatement measure, year-round. Please see our comment on 8.1.4 of the MCZ Assessment/the commitments on this. Based on this level of mitigation, we do not agree that the magnitude of impact can be consider negligible. We advise that an assessment with and without mitigation is provided to present the worst-case scenario. We advise that seahorses are a protected feature of the MCZ year-round, therefore any mitigation would also need to be proven to be below the threshold for TTS year-round within the MCZ. We advise the assessment is amended in line with our advice, and that the further information is provided. |  | Additional material was submitted at Deadline 1 which NE will respond to at Deadline 3. |  | Natural England have provided advice on the additional material submitted in Appendix E3. This information has not changed our position on this point. |  | No change
Seahorse – Underwater Noise - Behavioural impacts
E44 | 45 | We advise you refer to our comments on 3.1.1, 5.3.28 of the IPSFMP with regards to uncertainty over thresholds. Refer to IPSFMP comments. |  | No change |  | No change |  | No change
E45 | 46 | As noted above for Beachy Head West MCZ there is overlap with the TTS contour, given TTS thresholds are likely to be significantly larger than those for behavioural disturbance logically behavioural disturbance is highly likely to occur. We note that the 135dB contour mapped on figure 8.20 (which does not appear to consider all WCS) gives an indication that there is a clear overlap with Beachy Head West MCZ and possibly other MCZ’s. We advise that the WCS contour is mapped in relation to the lower figures quoted in the text for behavioural disturbance and the boundaries of the MCZ’s are included on this. We advise that a worst-case threshold is mapped and that the assessment is amended to account for the contours of this. We advise the mitigation measures would need to be proven to reduce this to a threshold level. |  | No change |  | No change - please see further advice on this matter in Appendix E3. |  | We understand that the Applicant intends to submit further information in relation to this point at deadline 4. Natural England will review this information when it is received and provide a response.
Other Impacts
E46 | 47 | Natural England advise there is an inconsistency with seahorses being treated a stationary receptor for underwater noise, but a fleeing report in terms of suspended sediment and smothering. We note that 8.9.398 suggest they would flee, whereas 8.9.415 suggest they have limited capacity to flee. We advise that they are considered as not having capacity to flee. We advise this is amended and that seahorses are treated as a stationary receptor throughout.
Underwater Noise - UXO clearance activities
E47 | 48 | When consulted on the separate marine licence for UXO clearance, it should be noted Natural England will advise that UXO detonation occurs outside of the sensitive season for black seabream (March July) given the close proximity of Kingmere MCZ to potential clearance locations. Therefore, we advise that the Project will need to consider this in their construction programme. Specific consideration also needs to be given to impacts on seahorses MCZ’s. We advise this will need to be considered.
E48 | 49 | A UXO Clearance Marine Mammal Mitigation Protocol (MMMP) will be developed. A Draft UXO Clearance MMMP (Document Reference 7.15) has been submitted with this application. The use of low order detonations to dispose of Offshore UXOs using the ‘deflagration method’ will be implemented, where practicable. We question how mitigation plans measures for marine mammals will specifically address impacts to black seabream and seahorse as MCZs features. Given it is stated that UXO clearance works have the potential to affect a similar area to that of piling, we advise that full consideration needs to be given to mitigation specifically aimed at the MCZ features.
Cable Corridor Works
E49 | 50 | Natural England advise that the impacts from direct disturbance from installation of the export cable and impacts from suspended sediment are dependent on Commitment 273. This is a seasonal restriction will be put in place to ensure offshore export cable corridor installation activities are undertaken outside the black seabream breeding period (March-July) to avoid any effects from installation works on black seabream nesting within or outside of the Kingmere MCZ. Natural England supports this measure. We advise that this should include all aspects of export cable installation, including but not limited to seabed preparation works, cable protection work, UXO works (which we understand would form part of a separate licence). We advise that should any activities not be included we would have concerns regarding the impacts of these. |  | No change |  | No change. We advise that any commitment regarding this matter should be secured in an updated mitigation plan, which we are yet to receive for review. |  | We note that there has been no change to commitment 273 within the updated In Principle Sensitive Features Mitigation Plan provided at deadline 3. Therefore, until this is updated, this point still remains outstanding.
E50 | 51 | Commitments 269 and 270 include: • ‘Cable routeing design will be developed to ensure micrositing where possible to identify the shortest feasible path avoiding areas considered to potentially support black seabream nesting’. • ‘A working separation distance (buffer) will be maintained wherever possible from sensitive features, notably black seabream nesting areas, as informed by the outputs of the physical processes assessment, to limit the potential for impacts to arise (direct or indirect)’. We advise that there needs to be clear prioritisation in this measure with micrositing (avoiding) being the preference in the first instance and if there is absolutely no way of avoiding black seabream nesting habitats, the shortest path should be taken as a mitigation measure. We advise this measure does not guarantee no direct impacts (as stated in the assessment), it only seeks to minimise them. We advise a robust pre-construction survey plan and a final micrositing plan are agreed with Natural England. Until this data is available the assessment should assume that it may not be possible to avoid potential black seabream nesting habitats. We advise this measure should apply to the placement of all infrastructure, construction equipment and include the operation and maintenance phase. We advise a commitment to the separation distance that will be employed should be made, and also a distance from the edge of the cable corridor where works will not occur. Should this not be possible in an area it should be highlighted in the final micrositing plan and discussed with Natural England. |  | No change |  | No change |  | No change
E51 | 52 | It is recognised that ‘Seabed disturbances resulting from construction activities such as cable trenching within The black seabream nesting area may damage nests and could potentially prevent future use of the seabed for nest building if a physical change in its character in discrete locations was to occur.. the cable installation may, in discrete locations, have a long-term negative effect on areas of high intensity black seabream nesting if the physical nature of the seabed habitat is altered’. Natural England also considers there may be long term habitat loss during operation and maintenance, as ‘it is recognised that some nesting habitat may potentially be lost through the introduction of cable protection’. Even with the mitigation proposed there is still a residual risk of unidentified nesting areas being impacted/ or not being avoidable/requiring cable protection, therefore we do not agree that there will be no long-term loss of habitat and that this can be assessed as Negligible. Additionally, there could be ongoing direct and indirect impacts from operations and maintenance (O&M) works on the export cable corridor. We advise that long term and ongoing loss of black seabream nesting habitat is recognised as potentially being unavoidable and having ongoing impacts through the lifetime of the project. In relation to Operation and Maintenance works we advise a Disturbance Management Plan (DMP) is produced. This should set out impacts from each aspect of these works and present measures (and supporting information of efficacy) to avoid/reduce/mitigate the disturbing effect arising from operations such as cable repair, replacement, reburial operations in or adjacent to sensitive features including Kingmere MCZ and locations suitable for black seabream nests. Adherence to the measures listed in the DMP could/should be a condition of the DCO/dML. |  | No change |  | No change |  | No change
E52 | 53 | Natural England question why there would be direct disturbance outside of the DCO boundary of the cable corridor (e.g., for anchor placement). We advise that activities are only permitted within the DCO boundary, and that anchor placement potentially in the MCZ outside of the DCO boundary has not been assessed. We advise this is clarified in the assessment. |  | No change |  | No change |  | Please see our response to point F24 of the benthic ecology tab.
E53 | 54 | ‘The offshore export cable routeing design will target areas of the seabed that enable maximising the potential for cables to be buried, thus providing for seabed habitat recovery in sediment areas and reducing the need for secondary protection and consequently minimising any potential for longer-term residual effects’. ‘Adoption of specialist offshore export cable laying and installation techniques will minimise the direct and indirect (secondary) seabed disturbance footprint to reduce impacts, which will provide mitigation of impacts to potential (unknown) black seabream nesting locations, where avoidance is not possible. The Applicant will seek to utilise the most appropriate technology available at the time of construction to reduce the direct footprint impact from cutting machinery.’ Whilst Natural England support cable burial as the most preferable form of cable protection and the potential for this to minimise the long-term effects. However, we understand that there are areas where the Applicant does not anticipate cable burial being possible and that up to 54% of the export cable corridor may require mechanical trenching, and that up to 20% of the corridor will need cable protection. We advise that it should be made clear across the documentation that there are clear limitations in the applicability of these measure across the whole cable corridor. Additionally, it should be recognised that methods such as mechanical trenching have the potential to reduce the likelihood of recovery of nesting habitats. Additionally, where cable protection is required this may represent a loss of suitable nesting habitat. Natural England advise that a cable burial risk assessment, which contains site specific geotechnical information, is provided during the Examination. Without this information, it would have to be assumed that the worst-case scenario would be realised. This includes cable protection and/or the most impactful trenching methodology being required in habitat suitable for black seabream nesting |  | No change |  | No change |  | No change
E54 | 55 | ‘An Outline Scour Protection and Cable Protection Plan (Document Reference 7.12)’. We advise that further detail is provided on how this plan will minimise long term loss of habitat in relation to black seabream and seahorses, and how this considers lessons learnt from Rampion 1. |  | No change |  | No change |  | No change
E55 | 56 | It is stated in relation to impacts from EMF that the cables will be buried at a target depth of ‘1.0 to 1.5m below the seabed surface for the majority of the route’. We understand that burial could be challenging in rock and that there are areas where cable protection will be required. Additionally, it is unclear why there is a range of 1m -1.5m, and so we advise that information is provided to evidence that burial 1m would still provide sufficient mitigation. We advise that a Cable Burial Risk Assessment is provided at the consenting stage. If this target depth cannot be met along the route then this could invalidate the ES conclusions. It is suggested that cable protection would provide the same mitigation as burial, but we advise no evidence has been provided here to support this statement. We advise that should installation methods such as pinning be used to minimise impacts on habitats such as chalk, this could invalidate EMF mitigation measures. We advise that further geotechnical information, including a Cable Burial Risk Assessment is provided. |  | No change |  | No change |  | No change
Decommissioning
E56 | 59 | It is suggested that the impacts due to decommissioning will have a magnitude no greater or less than the construction phase, but that a decommissioning programme will be developed. We advise that the magnitude of impacts is not reduced in this assessment from construction until the content of the Decommissioning Plan is known, and that Natural England should be consulted on this plan post consent. We advise that much of the mitigation proposed for construction is likely to be required for decommissioning. Where we have advised the sensitivity of features needs to be amended for the construction phase, this would also apply to decommissioning. We advise our comments above also apply to underwater noise from decommissioning. We advise that underwater noise impacts will need to be re-considered at the point where the full extent of these works and the machinery used is decided upon. We advise the decommissioning assessment is also updated.
E57 | 60 | Natural England advises that the default should be that cable protection should be removed, to avoid permanent loss of habitat that could support features naturally found in the area, such as black seabream nests. We advise this should be made a commitment, but that the worst case of not being able to remove cable protection is considered. |  | No change |  | No change |  | No change
E58 | 61 | We advise that Black seabream show interannual variation in their nesting locations. Therefore, it cannot be assumed that these locations would be the same, many years down the line at decommissioning. We advise this supports the need for ongoing data collection. |  | No change |  | No change |  | No change
E59 | 62 | We advise clarity is provided on the information used to generate the 100km noise buffer for cumulative effects. We advise you refer to our benthic comments in relation to possible cumulative effects with aggregates licences in relation to sedimentation. We advise evidence is provided to support this and that are benthic comments are referenced. |  | No change |  | No change |  | No change
Document used: [APP-040] 5.11 Rampion 2 Draft Marine Conservation Zone assessment (MCZ A)
E60 | 63 | Natural England seek clarification that the graphic demonstrates the absolute worst case in terms of spatial overlap with designated sites, as no explanation is provided as to what scenario this represents. Additionally, we note that the contours shown on this graphic do not consider behavioural impacts, and neither does the noise ZoI (Zone of Influence) that is used to screen impacts (Table 5.1). Given this is critical to the assessment of MCZ features, such as black seabream and seahorses, we advise this contour is included. We therefore advise the screening decisions should not rely on this ZoI as drawn. We advise that currently viewed in isolation this graphic does not provide a clear understanding of the issues to the reader. We advise all noise modelling/figures should include the boundary of the MCZ’s. We advise confirmation is provided in the report of what scenario this represents, and that it is the worst case. We advise that the noise ZoI is updated to include behavioural impacts in relation to specific species. We advise that behavioural thresholds are still a key area of disagreement between Natural England and the Applicant. |  | No change |  | No change |  | No change
E61 | 64 | Natural England advises that it is key all these measures are secured in any consent issued. We advise all embedded mitigation measures proposed are secured in the DCO/DML.
E62 | 65 | Natural England notes that agreement was not reached in the Expert Topic Groups (ETG’s) with regards to underwater noise impacts on black seabream. We advise that this is still a key area of disagreement between Natural England and the Applicant.
E63 | 66 | Natural England notes that EIA terminology and methodology to assess impacts are being applied throughout the MCZ Assessment. For clarity, the MCZ Assessment should seek to define and understand the potential of the conservation objectives being hindered by external activities/impacts. We advise that to avoid confusion the MCZ Assessment should not use EIA terminology. Additionally, we note that our comments within the thematic chapters regarding significance of effect and magnitude also apply to the MCZ assessment where the Applicant has brought forward these conclusions into it. We advise the MCZ Assessment is revised accordingly. |  | No change |  | No change |  | No change
E64 | 67 | We note that indirect impacts that were assigned a ‘negligible’ magnitude in the ES and have therefore been screened out and not taken to a stage 1 MCZ Assessment. We advise that our comments on the relevant chapters are taken into account and this screening is adjusted as necessary. Furthermore, the different impacts of the proposal on the MCZ features in question should be considered cumulatively rather than in isolation to avoid ‘salami-slicing’ the overall impact. We advise that our comments on the relevant thematic chapters are considered against any conclusions made in the MCZ Assessment. |  | No change |  | No change |  | No change
E65 | 68 | Natural England advises that cable repair, replacement and reburial as part of O&M activities in proximity to Kingmere MCZ have the potential to cause impacts that have not been included in the screening. Natural England advises that these impacts should be screened in. |  | No change |  | No change |  | No change
E66 | 69 | Natural England advises that where impacts have been screened out due to impacts on coastal and marine processes not being significant, Natural England’s comments on this chapter should be taken into account. Natural England advises our comments on coastal and marine processes are referred to and the assessment updated as necessary.
E67 | 70 | It is suggested that ‘The maximum design scenarios (spatial and temporal) with respect to underwater noise relates to the simultaneous and sequential piling of pin piles: - Spatial worst case - Simultaneous installation of jacket foundations. (Piling of 396 pin piles (4 pin piles piled simultaneously at both the East and West piling locations in the array area)), driven with a 2,500 kilojoule (kJ) hammer energy; - Temporal worst case - Sequential piling of 396 pin piles (pin piles piled sequentially at separate locations within a period of 24 hours), driven with a 2,500kJ hammer energy’. This is not the same as the Maximum Design Scenario (MDS) presented in the fish and shellfish chapters, which includes detailed parameters including, for example, number of piles per day. We advise clarity is provided on why this differs. We advise that you refer to our more detailed comments on the fish and shellfish chapter on this. We advise that a clear worst-case scenarios are presented across all documents, with any difference explained. We advise clarity is provided on the modelled scenario used to inform the assessment and included on the graphic. |  | No change |  | No change |  | No change
E68 | 71 | Notwithstanding our comments regarding the appropriateness of using of EIA terminology in the MCZ Assessment, we advise that clarity is provided where there are differences between the magnitude of impact and sensitivity applied between the two assessments. We advise any differences are recognised and clearly justified. Please refer to our chapter comments with regards to the magnitude of impact. We do not agree with the negligible magnitude of impact applied here. Please see comments on the chapter above. We advise any differences are recognised and clearly justified. Please refer to our chapter comments with regards to the magnitude of impact. |  | No change |  | No change |  | No change
E69 | 72 | Natural England agrees with the sensitivity assigned to the features of Kingmere MCZ in relation to increases in suspended sediment concentrations (SSC) and sediment deposition, as these are in line with our advice on operations. However, based on the fact the 500m buffer does overlap with an area of Kingmere MCZ, we do not agree with the assessment of a minor magnitude of impact. We advise that the magnitude of impact should be revised to consider the actual impact on the area of overlap, as opposed to contextualising this in relation to the site as a whole. |  | No change |  | No change |  | No change
E70 | 74 | Natural England advise that July should not be seen as less important in relation to the potential to hinder the conservation objectives of Kingmere MCZ. Whilst we agree that it appears from the aggregates data that the levels of spawning/nesting may be lower in July, this difference does not represent evidence that this period is not important to designated bream. It is thought possible that later spawning could be an important ‘last attempt’ if spawning has been unsuccessful earlier in the season. We advise that July should be consider equally important in line with the conservation advice. |  | No change |  | No change |  | We advise that as detailed in appendix E4 this remains Natural England's advice on this issue.
E71 | Summary 6 | We advise that it has not been demonstrated that the mitigation hierarchy has been followed in relation to underwater noise impacts from piling on black seabream. The Applicant should demonstrate how they have considered avoiding impacts in the first instance and, wherever possible, chosen options which reduce or eliminate such impacts. Where impacts are unavoidable, suitable/proven mitigation measures, accompanied by robust scientific evidence of their efficacy, should be proposed. However, the Applicant proposes piling during this period without the adoption of scientifically robust mitigation measures. |  | No change |  | No change |  | No change
E72 | 75 | It is stated that ‘Details of available mitigation technology have been presented to provide confidence that the required levels of noise attenuation can be delivered (either through one of the examples given, or through other future potential mitigation technology) and can therefore be relied upon to avoid potentially significant effects that may arise in the absence of mitigation’. Natural England advise that insufficient evidence has been presented to provided certainty that these measures can achieve the levels of attention proposed within the specific environmental conditions present at the construction site of Rampion 2. Natural England has concerns about the approach of effectively pushing this issue to post consent, given it may still not be possible to resolve at that stage. We advise that certainty of provision of the commitments is not the same thing as certainty that the commitments will be sufficient to prevent the conservation objectives of a designated site being hindered. The mitigation technology proposed has not been used in like for like conditions as Rampion 2. We encourage the Applicant to trial and monitor the noise attenuation achieved by the mitigation outside of the sensitive period for black seabream and present findings to the MMO and Natural England for review. Without such evidence we cannot agree that the conservation objectives of Kingmere MCZ will not be hindered. |  | No change |  | No change |  | We have provided comments on the updated information provided at deadline 3 within appendix E4. We understand the Applicant intends on submitting further information on this topic at deadline 4, which we will review and provide our advice on.
E73 | Summary 8 | Natural England advises that careful consideration is given as to whether a seasonal restriction is a means of proceeding with the proposal ‘in another manner’. Natural England advises that based on the information provided to date, the seasonal restriction stipulated above appears to be the only option that would avoid the need for the decision-maker to proceed to the subsequent steps of the MCZ assessment process i.e. a Stage 2 Assessment. Therefore, as the Applicant has not included the seasonal restriction in its entirety in the Rampion 2 application, we advise that they begin development of a Measures of Equivalent Environmental Benefit (MEEB) proposal, in the event of the Stage 2 Assessment reaching a negative conclusion. We note this has not been included in the submission. |  | Natural England had a meeting with the Applicant on the 8/04/2024. Within this meeting we reiterated our advice that as the Applicant has still not committed to a seasonal restriction in its entirety, we advise that they begin development of a Measures of Equivalent Environmental Benefit (MEEB) proposal, in the event of the Stage 2 Assessment reaching a negative conclusion. |  | We note that the Applicant is still proposing piling activities during the sensitive season for black seabream. In the absence of any further mitigation being proposed, we welcome the Examining Authority’s request (Question FS 1.1) for the Applicant to submit without prejudice options for Measures of Equivalent Environmental Benefit (MEEB) for consideration in the event of the Stage 2 MCZ Assessment reaching a negative conclusion. |  | We understand that the Applicant is hoping to submit without prejudice MEEB information at deadline 4, which we will review when it is available.
E74 | 76 | Based on the information presented to date Natural England does not have confidence that a ‘noise reduction is achievable to reduce the impact ranges of TTS and behavioural effects to outside of areas of primary importance for breeding black seabream’. Therefore, advise we do not agree with the conclusion that ‘there will be no impact from underwater noise on nesting black seabream within the Kingmere MCZ, and the magnitude of impact is considered to be negligible’. Additionally, we advise piling is not short-term and intermittent, particularly if it is conducted sequentially as stated in the WCS. We disagree that underwater noise will not hinder the conservation objectives of the site. |  | No change |  | No change |  | No change
E75 | 77 | In relation to decommissioning we understand that underwater noise from cutting has the potential to generate a lower level of underwater noise than pile driving. However, no reference is presented to demonstrate this and support the subsequent conclusion of no significant effect. We advise evidence is provided to support this conclusion.
E76 | 78 | The three main sources of SSC and sediment deposition may arise from Rampion 2 are listed as: drilling for foundations, trenching for cables, and seabed preparation activities (such as seabed levelling and sandwave clearance). We seek clarification that the seasonal restriction on cable installation activities in the export cable corridor during March-July includes the trenching activities and seabed preparation activities in this area. We advise the clarity is provided on the activities include in this restriction and any activities that would not be included before we can provide our final advice on this matter. |  | No change |  | No change. We advise that any commitment regarding this matter should be secured in an updated mitigation plan, which we are yet to receive to review. |  | We note that there has been no change to commitment 273 within the updated In Principle Sensitive Features Mitigation Plan provided at deadline 3. Therefore, until this is updated, this point still remains outstanding.
E77 | 79, 84, Summary 10 and 11 | Natural England also note that in relation to short snouted seahorse there is a potential for underwater noise impacts on the following MCZ’s: • Beachy Head West MCZ (TTS and behavioural) • Beachy Head East MCZ, Selsey Bill and the Hounds MCZ, Bembridge MCZ (behavioural). Natural England advises that Short-snouted seahorse are protected within these MCZs year-round. The Applicant has proposed the mitigation put forward will ensure these impacts are not realised within the MCZs, however, the assessment does not refer to evidence/modelling that demonstrates this, and no noise contour is displayed on graphic 1. We advise Graphic 1 is updated to include this contour. In relation to the mitigation measures themselves, Natural England has the same concerns around efficacy as raised above in relation to black seabream. Additionally, we have not agreed or discussed a suitable behavioural threshold with the Applicant for short-snouted seahorses. We advise that suitable evidence is provided to support this conclusion. |  | No change |  | No change |  | We understand the Applicant intends on submitting further information on this issues at deadline 4, which we will review when it is received.
E78 | 80 | It is stated that the ‘The implementation of embedded environmental measures to employ one or more noise abatement mitigations, during the summer breeding season of seahorse (C-265, C-274, C280, and C- 281, Table 3-1) will reduce the impact ranges of behavioural effects to outside of the MCZs.’ However, no evidence has been provided here to support this statement, and therefore the subsequent conclusion of not hindering the conservation objectives of the relevant MCZ’s. We also advise that we have not discussed an appropriate threshold for behavioural disturbance on seahorses with the Applicant. We advise that evidence is provided to demonstrate that the mitigation measures put forward have proven efficacy (in the same environmental conditions as are present at the Rampion 2 site) to reduce the noise levels to below an acceptable behavioural threshold level within Beachy Head West MCZ. We advise without this information we do not consider the magnitude to be negligible. |  | No change |  | No change |  | We understand the Applicant intends on submitting further information on this issues at deadline 4, which we will review when it is received.
E79 | 81 | As recognised in 7.5.3 Seahorses have been put into Group 4 ‘Fishes that have special structures mechanically linking the swim bladder to the ear’, which means they are a particularly sensitive receptor to underwater noise impacts. Natural England note that there is a potential for ‘TTS impacts on breeding seahorse’ as ‘there is an interaction of the impact ranges from piling in the array area, with Beachy Head West MCZ’. It is stated that ‘embedded mitigation to reduce impacts from underwater noise on sensitive receptors will reduce the impact ranges of TTS to outside of the MCZ’. However, no evidence has been provided here to support this statement, and therefore the subsequent conclusion of not hindering the conservation objectives of the relevant MCZ’s. We advise that evidence is provided to demonstrate that the mitigation measures put forward have proven efficacy (in the same environmental conditions as are present at the Rampion 2 site) to reduce the noise levels to below the TTS level within Beachy Head West MCZ. We advise without this information we do not consider the magnitude to be negligible. |  | No change |  | Natural England have provided advice on the additional material submitted in Appendix E3. This information has not changed our position on this point. |  | We understand the Applicant intends on submitting further information on this issues at deadline 4, which we will review when it is received.
E80 | 82 | We advise that short-snouted seahorse are treated as a stationary receptor in terms of increases in SSC and sediment deposition, in the same way they have been for noise. We advise the assessment is amended to reflect this. |  | No change |  | No change |  | No change
Document used: APP-039] 5.9 Rampion 2 Report to Inform Appropriate Assessment
E81 | 85 | Natural England are likely to agree with the conclusion of no AEoI in relation to the Atlantic salmon feature of The River Itchen SAC. However, we note that Table 7.1 includes figures for a fleeing receptor and Natural England advise that fish are not considered a fleeing receptor. Additionally, we advise that it would be more accurate to show the noise modelling location closest to the SAC on Figure 7.1 and for clarity to be provided on which of the WCS this figure is showing. We advise that the full range of stationary noise effects are shown in Figure 7.1 in order to support the conclusions drawn. We advise the Table is updated to the figures for a stationary receptor and that the full range of effects is modelled on Figure 7.1 to support the conclusions drawn.
Document used: [APP-239] 7.17 Rampion 2 In Principle Sensitive Features Mitigation Plan (IPSFMP)
E82 | 86 | Natural England has concerns regarding the IPSFMP not being finalised until the post-consent/pre-construction phase, and that it is stated the mitigation measures are not confirmed. We advise that where mitigation measures are essential to the assessment, we cannot agree the assessment conclusions without sufficient certainty in the measures being progressed and being able to achieve the levels of mitigation required. Natural England advise that further investigation and information is provided into the Examination to demonstrate the effectiveness of the measure. |  | No change |  | No change |  | No change
E83 | 87 | Natural England notes it appears to be implied here that if the worst-case scenario is not realised some of these measures may be reduced. Therefore, we advise that we do not have sufficient certainty of exactly what we might be agreeing to at this stage. We advise that this is clarified. |  | No change |  | No change |  | No change
E84 | 88, 91 | Natural England advise that post construction monitoring to verify the predicted effects will be required. Natural England would also expect that monitoring would be undertaken to demonstrate recovery, with further measures potentially being triggered if this was not shown. We advise that this clarified and included in an updated Plan. |  | No change |  | No change |  | No change
E85 | 89 | We advise this information from the Rampion 1 surveys is of limited relevance, given Rampion 1 had a piling restriction April-June, and the export cable was not located in an area of known bream nesting. We advise that the limitations of this are clearly recognised. We advise in the absence of further evidence being presented this will remain our advice. | [5 empty] | We note that point 2.5.5 has been updated.
E86 | 92 | It is stated that ‘Updates to the project design that could impact the conclusions of the assessment may be subject to further assessment if deemed appropriate in consultation with the relevant authority’. Natural England advises that we have concerns over assessments being changed post-consent and the process that would need to be followed to achieve this. We advise that updates to the underwater noise monitoring proposed also appear to be leaving handling the uncertainty to post consent. We advise that all reasonable efforts should be made to narrow down this uncertainty prior to consent being granted. |  | No change |  | No change |  | No change
E87 | 93 | We advise our benthic comments on the features to be included and comments above on the mitigation measures are considered here. Refer to our comments and amend. |  | No change |  | No change |  | See point F35. Our overarching concerns regarding mitigation measures relating to benthic habitats, including areas suitable for nesting bream remain.
E88 | 95, 98 | Natural England advise that we do not have confidence in the ability of the ‘spatial and temporal zoning plan’ to deliver effective mitigation to prevent the conservation objectives of Kingmere MCZ being hindered. As Cefas have raised, such plans rely on the modelling, which is not sufficiently reliable to make predictions to such specific boundaries. In addition, there is not sufficient information on the efficacy of mitigation measures in this environment and their ability to achieve thresholds to such defined boundaries. Finally, we advise that in the absence of an agreed threshold for behavioural disturbance to reduce the impact down to within the MCZ, mitigation cannot be agreed. Unless additional information is provided, it will remain our position that a pilling exclusion from March-July inclusive is the only measure we can have confidence will not hinder the conservation objectives of Kingmere MCZ. We advise that this information should be submitted into the Examination on this point. |  | No change |  | No change |  | See point E72.
E89 | 96 | We advise that the post-consent data collection will require an agreed plan to ensure that this will be sufficient to inform micrositing. We advise that an agreed monitoring plan, should be approved to the MMO in consultation with Natural England, well in advance of any surveys taking place to ensure survey can go ahead at the optimum time of year.
E90 | 97 | We advise that aiming for a 300m buffer from the edge of nesting areas is desirable. Any reduction in buffers would need to be clearly set out and agreed with MMO and Natural England. Please also refer to our detailed benthic comments. We advise that this is detailed in a final plan for micrositing to be agreed post-consent with the MMO in consultation with Natural England. Refer to our benthic comments.
E91 | 99 | We advise that clarity is provided here that this is relevant to Temporary Threshold Shift and behavioural disturbance. We advise clarity is provided. |  | No change |  | No change |  | We note that an updated In Principle Sensitive Feature Mitigation Plan has been submitted at deadline 3. Whilst 5.5.3 does now note that these measures are relevant to Temporary Threshold Shift and behavioural disturbance, we advise that based on the modelling that we commented on in our deadline 3 Appendix E3 there remains uncertainty over whether noise levels that could elicit recoverable injury could be experienced within Kingmere MCZ and therefore whether these measures may also be relevant to that affect as well.
E92 | 100 | This incorrectly refers to records of seahorses in the south-western region, whereas Rampion 2 is in the south-east. This should be amended in an updated assessment. | [5 empty] | We note that 5.3.3 has been updated to correct this error.
E93 | 101 | With regards to mitigation measures for Herring, Natural England defers to the advice of Cefas (see comments on the fish and shellfish chapter). To note.
E94 | 103 | We advise that the information shared confidentiality with Natural England is not sufficient to address our concerns. In relation to double big bubble curtains, we advise that other factors such as the strength of the current, depth of water and benthic substrate are critical to performance. These have not been compared. We advise that full comparison of environmental conditions is undertaken, to aid in providing further confidence in the levels of abatement proposed. |  | No change |  | No change |  | See point E72.
E95 | 105 | Please refer to our comments above in relation to the studies referenced here, and how they have been applied. We have concerns over the methodology used to determine a threshold from the ambient noise data collected. It is clear that the peak levels of noise have been referenced, but these are not the same as continuous noise from piling, and therefore it may be more appropriate to look toward the minimum levels of noise. However, we defer to Cefas on this matter. We advise that you refer to the more detailed advice of Cefas with regards to how the Applicant has proposed deriving a threshold ambient noise data. |  | No change |  | No change |  | No change
E96 | 107, 116 | Natural England advise that no detailed discussion regarding this mitigation being suitable for seahorses has been had as part of the evidence plan process. We advise that the maximum noise attenuation measures should be used year-round in all areas. We advise evidence is provided that this will sufficiently reduce the impacts within seahorse MCZ’s. No evidence has been provided to support 141dB re 1 μPa2s (SELss) being a suitable behavioural threshold for seahorses. We advise that seahorses are a ‘group 4’ receptor. Group 4 receptors are defined as having the highest sensitivity to noise and therefore we would expect to see evidence that this threshold was suitable for seahorses. We note that 8.9.259 of the Fish and Shellfish Chapter suggests lower thresholds. We advise that this advice is taken into consideration, the plan amended, and evidence provided. |  | No change |  | No change |  | We understand the Applicant intends on submitting further information on this issue at deadline 4, which we will review when it is received.
E97 | 108 | Natural England question whether this accounts for simultaneous piling at different locations, and the cumulative potential this has. We advise clarity is provided within the assessment. |  | No change |  | No change |  | No change
E98 | 109 | Notwithstanding our advice above on the uncertainty of what can be achieved with noise abatement, Natural England note that the footnote here states ‘ It should be noted that detailed octave or 1/3rd octave band attenuations for the PULSE (IQIP) and MNRU (MENCK) hammers were not supplied despite direct requests, and therefore these predictions are made with limited data and should be considered indicative for the equipment and conditions at Rampion 2’. We advise this further reduces the confidence that these measures will achieve the values of abatement stated. We advise that further effort to obtain this information is made. |  | No change |  | No change |  | We understand the Applicant intends on submitting further information on this issues at deadline 4, which we will review when it is received.
E99 | 111, 112,114 | Natural England support a piling exclusion in the western array (given we support this for the whole of the array March to July). We advise that the conservation advice notes the sensitive period is March to July inclusive (not March to June). There is evidence of active nests in July from the aggregates data, which informed the conservation advice for the site. We advise that July is included in any seasonal restriction. Natural England advises that insufficient evidence is available in relation to the efficacy of the mitigation measures and a suitable threshold to mitigate to in order to allow piling to proceed in the eastern array during March-July. We advise that currently there is insufficient evidence that a full seasonal restriction is not required in the eastern array. |  | No change |  | No change |  | Our postion has not changed on this point. See also See point E72.
E100 | 113 | We note the buffers on Figure 5.15 appear to relate to distances from the MCZ. It is not clear what sounds levels are expected within the MCZ at each of these distances. We note turbine locations have yet to be decided, therefore currently it is possible that even starting from the furthest piling location could result in piling significantly closer than band A in the eastern array or be significantly further east than the far western portion of the western array (band C).We advise that further information is provided. We advise that there are clear uncertainties in relation to where the furthest pile will be located and therefore the effectiveness of this element of the measure. Refer to comments above regarding the noise modelling specifically. |  | No change |  | No change |  | No change
E101 | 115 | In relation to piling noise mitigation between August to February, we advise that this period could offer an opportunity for the Applicant to test the efficacy of the mitigation measures outside of the sensitive period for spawning/breeding black seabream. However, considerations during this time would have to be given to other mitigation requirement e.g. for herring and seahorses. We advise that the Applicant considers trialling mitigation measures outside of sensitive seasons, to test their effectiveness in reducing noise levels.

## F - Benthic Ecology
Point | Point Number(s) Appendix F [RR-265] | Taken from Natural England’s Relevant and Written Representations Rampion 2 Appendix F - Benthic, Subtidal and Intertidal Ecology [RR-265] | RAG Status Rel and WR Rep D1 | Consultation, actions, progression | RAG Status at D2 | Consultation, actions, progression | RAG Status at D3 | Consultation, actions, progression | RAG Status at D4
Rampion 1 Lessons Learnt and Monitoring
F1 | Summary 1a | Natural England advises that a clear presentation and discussion of lessons learnt and monitoring from Rampion 1 is crucial to inform the basis of the current application. A better understanding of key limitations and constraints encountered for that project and how they, along with impacts to key species and habitats, were minimised where avoidance is not possible is critical to help support proposed design parameters, mitigation measures and conclusions drawn for this project. |  | No change |  | No change |  | No change
Benthic Characterisation and Predictive Habitat Mapping
F2 | 1 | It should be recognised that the Applicant failed to collect 7 of the 15 chemical samples, which almost halves the agreed sample size. Given the grab samples were conducted 4 months after the collection of geophysical data, we question why so many of these samples appear to still have been located within rock, as they were likely to fail. We note that all 7 stations record arsenic above the threshold effect level, and one station exceeded the probable effect level. We advise that the advice of CEFAS is sought in relation to this and appropriate management measures which may be required.
F3 | 2, Summary C | Natural England notes that, because of the delays to the programme, the site-specific survey data is already approximately 3 years old in certain areas. The limitations of the reliability of basing an ES Assessment on data that is outdated, particularly in relation to ephemeral species, such as Sabellaria spinulosa, should be recognised. The assessment should therefore assume that the habitats listed (comments 21, 67, and Summary J) are present and are unavoidable as a worst- case scenario and it will not be possible to avoid them. The Applicant should note that we expect micrositing to be conducted using up to date pre-construction data to avoid impacts where possible. NB: we advise that any data used to infer presence or absence of Sabellaria spinulosa is only valid for work within 2 years of the collection of the data. We advise that age of the data is acknowledged in the assessment and that the importance of the pre- construction surveys is noted. |  | No change |  | No change |  | No change
F4 | 3, Summary 1b, summary 1f, 73 | Natural England understands that the DDV survey occurred between December 2020 to February 2021. As per our advice to the Applicant (02/11/2020), this was not the optimum time for such surveys, and there was a risk the imagery would be poor quality and not fit for purpose. We note that Appendix 9.3 states that ‘The main assessment was conducted using the still images captured during the DDV transects and stations due to high turbidity levels, which reduces the resolution of analysis from the video imagery’. Sections 9.5.10-9.5.12 of the chapter allude to data limitations but does not explicitly acknowledge that some of these limitations stem from the lack of transect data. We advise this needs to be acknowledged in the main chapter. As turbidity affected the video quality, we question the quality of the stills for identifying habitats protected under Section 41 of the Natural Environment and Rural Communities Act (2006), as well as stoney reef features and potential black seabream nests. We note a further limitation with Ground Truthing surveys was that only 39 successful grabs were collected. Natural England queries if any further data has been collected by Applicant over the last two years to fill this known data gap and provide a more robust baseline for assessment. We advise this ES chapter should fully acknowledge the limitations of the site-specific data collected in providing a robust baseline. And advise the Applicant update the ES where possible with additional site- specific evidence. We advise that, based on the limitations of the characterisation data, collecting sufficient quality pre-construction data at a time of year where the turbidity is less likely to be high, will be key to informing the final mitigation strategy and to ensure the data collected is sufficient to inform micrositing. We advise that it should be a condition of the DCO/DML that a benthic survey plan is agreed with the MMO, in consultation with Natural England well in advance of any surveys taking place, to ensure surveys can go ahead at the optimum time of year. |  | No change |  | No change |  | No change
F5 | 4 | This section states, in relation to the Predictive Habitat Mapping, ‘Where site-specific data have been collected, this has been prioritised within the predictive habitat model and supersedes the historical data in the habitat map …..it has been retained to understand the occurrence of potential biotopes where ground-truth data weren’t collected to support the Application and the assessment of effects on the subtidal benthic ecology’. If data gaps have been identified, we advise that further information is provided regarding the risks to the reliability of the assessment due to such data gaps, and question why further data was not gathered to ensure a robust baseline. We advise that unless the Applicant can provide more site-specific data to update the ES a more precautionary approach is required due to the uncertainties with the current characterisation survey. This would include, but is not limited to, adoption of a suite of mitigation measures which would suitably avoid, reduce, mitigate impacts to any/all of the priority habitats. |  | No change |  | No change |  | No change
F6 | 5 | Section 9.6.13 suggests 15 biotopes were found in the site-specific survey, but table 9.11 lists 17 biotopes. We note that 5 of these biotopes are not included in the Key of Figure 9.4, which shows the spatial distribution of the biotopes (A4.131, A4.134, A4.214, A4.221, A5.611). We request clarification on which is these scenarios is correct, and that all documents are updated to reflect this. We advise that the Applicant provides an updated ES, with the correct figures throughout. |  | No change |  | No change |  | No change
F7 | 6, Summary L | Natural England’s best practice advice is to collect comprehensive/robust site-specific project data. However, Natural England notes that, outside of the site-specific project data, the Applicant has undertaken predictive modelling which relies heavily on data from literature and other surveys, which are dated and not specifically collected for this purpose. We understand these data have been used to substitute for the lack of site-specific data. But in using non site-specific project data the confidence in the modelling methodology can only be low. Therefore, Natural England does not support this approach. We advise that the conclusions drawn from the modelling are disregarded and instead greater emphasis is placed on avoiding, reducing and mitigating any potential impact pathway as much as possible. We also advise that a requirement is placed on the Applicant to undertake comprehensive pre-construction surveys which encompass sufficient data collection to inform micrositing and provide a robust baseline, that includes a rigorous power analysis. As well as informing the baseline, the addition of these data would help to provide greater confidence in the ES predictions. |  | No change |  | No change |  | No change
F8 | 7 | We advise that maximum likelihood estimates can be heavily biased for small samples. The optimality properties may not apply for small samples; therefore, the maximum likelihood can be sensitive to the choice of starting values. Depending on the setting of the bathymetry survey and the subsequent data collected, the underlying data being fed into the predictive model via the Maximum Likelihood Classification (MLC) methodology may not be as acute to have a level of sensitivity to pick up smaller/ low rugosity features. We advise that, as the MLC is trained via truthing and assumes that neighbouring cells correspond to higher likely hood of similarity, it is easy to underrepresent smaller or less distinguishable habitats (such as Sabellaria spinulosa). This under-representation is more likely to occur when the scale of the cells used are larger, as an overall assumption is derived for the most prevalent sediment or habitats found within that cell. Therefore, the MLC model may lack appropriate sensitivity. We advise that the conclusions drawn from the modelling are disregarded and instead greater emphasis is placed on avoiding, reducing and mitigating any potential impact pathway as much as possible. We also advise that a requirement is placed on the Applicant to undertake comprehensive pre-construction surveys which encompass sufficient data collection to inform micrositing and provide a robust baseline, that includes a rigorous power analysis. As well as informing the baseline, the addition of these data would help to provide greater confidence in the ES predictions. |  | No change |  | No change |  | No change
Environmental Impact Assessment
F9 | 8 | We note that the matrix now does not include the ‘very high’ category, in line with the MarLIN information that has been used to inform the assessment. However, it appears that a single consistent matrix has not been used across chapters. Whilst Natural England has raised issue across all projects with the use of matrices and potential for underestimating impacts; we advise that if the matrix approach remains acceptable to the regulator then a consistent matrix should be used by the Applicant across chapters. |  | No change |  | No change |  | No change
F10 | 9 | We note that the Applicant’s definitions, relating to the magnitude impact, suggests that ‘Major/Moderate’ includes permanent/irreversible change, whereas Minor is temporary change over a minority of the receptor, and Negligible means the receptor is not sensitive. There appears to be quite a leap between Moderate as a permanent change over the majority of the receptor, to Minor which is a temporary change over a minority of the receptor, with a wide range of magnitudes fitting between the two. Throughout the assessment, there are numerous incidences where the magnitude assigned does not match the definitions in this table, and a lower magnitude has been used against this guidance. Whilst Natural England has raised issue across all projects with the use of matrices and potential for underestimating impacts; we advise that if the matrix approach remains acceptable to the regulator then magnitudes used throughout the assessment are amended to reflect the definitions in this table. It is particularly key that permanent/irreversible changes are defined as Major or Moderate. |  | No change |  | No change |  | No change
Cable Burial and Scour Protection
F11 | 10, Summary I | Natural England has concerns over the long-term degradation of geotextile bags as cable protection and/or stabilisation for installation barges due to concerns over their removability and potential release of plastics, as well as the introduction of plastic to the marine environment generally. In relation to decommissioning scour protection, surface laid cables, external cable protection, and crossing protection, we advise that decommissioning should aim to remove infrastructure to reduce the potential for irreversible (permanent) habitat loss. We advise that the assessment should consider the worst-case scenario of irremovable cable protection, where doubt exists over the possibility of removal. We understand that the Applicant plans on producing a ‘decommissioning Programme which will be developed and updated throughout the lifetime of the Proposed Development to account for changing best practice’. It would be helpful if an Outline Decommissioning Plan was included at this stage, with the details agreed with stakeholders, including Natural England, based on best practice at the time of decommissioning. We advise that the Applicant produces a reburial hierarchy, which has external cable protection as a last resort. An outline of the process for reburial should be included with the Cable Specification and Installation Plan. We would welcome limits being placed on the Maximum Design Scenario to only use types of scour protection that have the greatest likelihood of being removed. We advise careful consideration should be given to the nature of the cable protection materials used as some may be damaging to the marine environment in their own right. We advise that an Outline Decommissioning Plan is provided by the Applicant that utilises lessons learnt from projects that are due to be decommissioned the near future. |  | The Applicant has provided further information, which we have provided comments on in Appendix DF 2. Our comments remain unchanged on these issues and we advise that the plans requested are provided. |  | No change |  | It remains Natural England's advice that an outline decommissioning plan should be submitted into the examination, as highlighted again in our response to BP 1.5 of the examiners questions first set of written questions. We understand that the Applicant intends on submitting further information relating to this point at deadline 4.
F12 | 11 | We note that mitigation measures that require burial and the potential need for scour prevention, and options for cable protection will be considered in a detailed Cable Burial Risk Assessment. We highlight the limitations in our confidence in the impact assessment, and the viability of mitigation measures presented prior to more detailed site-specific geotechnical data being gathered to inform this. It is stated that this report ‘will consider geological conditions in detail. RED will be using different burial equipment on Rampion 2 (compared to Rampion 1) and so the likelihood of exposure is considered much lower’. Natural England advises that it would be useful for a comparison on the equipment and methods to be clearly set out (including lessons learnt), given the Rampion 1 monitoring identified cable exposure, and there appears to still be a range of burial options under consideration for Rampion 2. We advise geotechnical information is provided within a Cable Burial Risk Assessment at the consenting phase. We request that a clear comparison between the burial equipment used for Rampion 1, and all options that might be used for Rampion 2, is provided to evidence this point. We advise that the Rampion 1 monitoring data are considered in any assessment. |  | No change |  | No change |  | No change
F13 | 12 | We note that there are areas where cable burial is not expected to be possible, and therefore scour may occur or scour prevention may be required, which could be in close proximity to Kingmere MCZ. Additionally, it is possible that turbines and associated scour prevention could be placed near to Offshore Overfalls MCZ. Therefore, we advise that further justification is required within this chapter in relation to the potential secondary impacts on designated benthic features within these sites. This should also be fully considered in the MCZ Assessment. We advise that further justification is provided, and the Applicant provides an up to date MCZ assessment. |  | No change |  | No change |  | No change
F14 | 13 | We advise that monitoring from Rampion 1 is used to inform predictions of impacts from scour prevention. We seek clarity regarding whether the figures stated for scour prevention are based on benthic survey information. Natural England should be consulted on the final Scour Prevention and Cable Protection Plan. Within updated ES documents the Applicant must demonstrate how Rampion 1 monitoring and the benthic survey data have been considered. As well as working with the Applicant on the revised Scour Prevention and Cable protection plan during the examination Natural England must be consulted on final plan as part of a DCO/dML conditioned. |  | No change |  | No change |  | No change
F15 | 14 | We note that Table 9.15 mentions burial of 1.5m with regards to reducing the effects of Electro Magnetic Fields (EMF). We note that a target burial depth of 1m is quoted for interconnector and array cables, which is less than 1.5m. Additionally, commitment C-41 states 1m. We advise that a consistent value is used, and evidence is referenced to support this. We question whether current information of benthic conditions has been used to inform the likelihood of achieving this across the various seabed conditions of the site. Has insight from success or failure of achieving burial depth at Rampion 1 in different sediment types been used to inform the assessment? If this target is not likely to be achievable based on the current information, the effectiveness of this mitigation measure for EMF pathways is reduced. The Applicant is to clarify what the burial depth commitment is, and how likely it is that the cable burial depth will provide the required mitigation. We advise that the viability of this should be informed by geotechnical data, lessons learnt for Rampion 1 and the Cable Burial Risk Assessment. |  | No change |  | No change |  | No change
F16 | 15 | Our comments in the coastal processes section regarding scour should be considered here, including consideration of scour monitoring in relation to Rampion 1. Based on our current understanding of the situation at Rampion 1, and the fact that it is suggested that there are likely to be issues burying the cable and scour around any scour protection, we advise that the magnitude of impact is not Negligible. We advise further consideration of this issue is required by the applicant in the cable specification and installation plan and/or the scour prevention and cable protection plan and the magnitude adjusted in the ES. |  | No change |  | No change |  | No change
F17 | 16 | Natural England advises that we do not regard a change to new hard sediment as a beneficial impact, as this is loss of what would naturally be present. Additionally, as this is a permanent change, the magnitude cannot be Minor based on the Applicants own definitions. We advise the Applicant updates the ES assessment accordingly. |  | No change |  | No change |  | No change
F18 | 17, 75 | It is stated that ‘the geological conditions are not entirely conducive to burial. Even so, many of the geological formations along the route are considered trenchable with mechanical cutting, although other formations that are strongly cemented are likely to pose an issue’ and that ‘In total, 2.35km of route length (per cable) may require a level of alternative protection, such as rock dumping. Overall, the engineering study has identified that a mechanical cutting trencher is necessary for up to 54% of the route length, of which 13% is considered likely to require further protection with rock placement. The remaining 46% is considered possible to achieve with jet trenching. This can be further clarified when route-specific geotechnical data is obtained at the pre-construction stage and the burial potential is confirmed (RED, 2022)’. Natural England requires clarity on where this information has been sourced, and whether this includes all aspects cabling, or just the export cable? We advise that consideration needs to be given to the impact this could have on the efficacy of the mitigation measures proposed generally, particularly ‘routeing design and micrositing’, and ‘use of specialist cable laying and installation techniques’ considering less than half the route appears to be suitable for jet installation. This may limit, or even prevent the recovery of sensitive features, where sufficient micrositing is not achievable. We advise there is the potential for permanent habitat loss/potentially significant habitat alteration if sensitive features cannot be avoided. We advise that the source of this information is provided, and that the impact of this on the mitigation measures is considered here and throughout the impact assessment. We agree that a hierarchy of jetting where possible first, before trenching is considered and minimising cable routing through harder strongly cemented formations is preferable. Pinning the of the cable and extending the HHD ducts should also be considered. Without the Cable Burial Risk Assessment and pre-construction information, we cannot fully understand the final constraints and therefore final impacts. We advise that, based on this situation a Cable Burial Risk Assessment, including route-specific geotechnical data is provided at the consenting stage. |  | No change |  | No change |  | No change
F19 | 18 | Natural England seeks clarity on whether any rock protection is likely to be required around the HDD exit pit, either temporarily or permanently. We advise information is provided on this and the ES chapter updated accordingly including any mitigation measures. |  | No change |  | No change |  | No change
F20 | 47 | We support the decommissioning phase being assessed as potentially the same significance as the construction phase at this stage. We advise that all scour and cable protection should be considered as needing to be removed. We advise this is considered by the Applicant during the consenting phase as part of an Outline Decommissioning Plan. |  | The Applicant has provided further information, which we have provided comments on in Appendix DF 2. Our comments remain unchanged on this issue and we advise that the plan requested is provided. |  | No change |  | No change. We understand that the Applicant intends on submitting further information regarding decomissioning at deadline 4.
F21 | 48 | While the intention may be to bury the cables, it is assumed that these cables require some cable protection allocation for where burial is not possible. This should be considered within this cumulative assessment. We advise that cable protection is included by the Applicant in an updated cumulative assessment. |  | No change |  | No change |  | No change
Nearshore grounding of vessels
F22 | 19 | It is stated in this section that ‘RED confirmed that floatation pits are no longer required for Rampion 2. RED will commit to using an alternative solution, such as rock filter bags (or similar) for seabed preparation purposes.’ Natural England supports the commitment to not use floatation pits, given the known impacts and loss of irreplaceable habitat incurred by this methodology for Rampion 1. It is stated in this section that ‘Gravel bags laid on the seabed to protect the cable barge during construction of Rampion 2, will be removed prior to the completion of construction, where practicable’. Natural England advises that this commitment is not sufficient in relation to mitigating impacts on priority habitats, Annex I habitat and potential habitats suitable for bream nests. If gravel bags are to be used, the Applicant needs to provide sufficient evidence that they can be removed and that the bags will not break down during use (particularly from abrasion with the barge). We note there is inconsistency throughout the application documents regarding the methodology to be employed, with some mention of loose material being used, which we are concerned is unlikely to be retrievable. We advise that any methodology selected should have demonstrable recoverability to pre installation state (OSPAR). We advise that the Applicant should provide a lessons learnt from Rampion 1 and a full appraisal of all possible options, with a commitment to using the methodology that minimises the environmental impacts the most. This should include the possibility of extending the HDD further out. The total impacts of the exit pit should be compared to the total impact of grounding out the vessel at several locations. Natural England advises that an appraisal of all possible options is provided, which includes consideration of lessons learnt from Rampion 1. This is required so that the full environmental impacts can be considered and assessed, and to evidence the achievability of mitigation. |  | The Applicant has provided further information, which we have provided comments on in Appendix DF 2. Our comments remain unchanged on this issue. We advise that the appraisal of all possible options we requested has not been provided. |  | No change |  | We note the new commitment C-297 , which states that the location of gravel beds will be microsited to avoid sensitive features, where practicable, which we support. We note that the Applicant states there would be abrasion of the underlying chalk from the use of gravel bags in 1.13. Natural England continue to advise that any loss of chalk should be considered a permanent loss of this Habitat of Principle Importance. Natural England maintains our advice that a full appraisal of all possible options should be provided. We note that commitment C-283 only commits to removing gravel bags prior to completion of construction, where possible. We advise that the gravel bags should be on the seabed for the minimum period required and that removal 'where possible' is not in line with the Applicants previous commitment to full remove the gravel bags. We note that the Applicant's response to deadline 2 submission document also appears to suggest 'If damage was to occur to the bags and some of the gravel material was left on the seabed, this is deemed to be of Minor significance on account of the natural presence of gravels across the offshore' . Natural England advises we disagree with this statement and suggest if the Applicant is not confident full removal is possible, it should be considered what measures may need to be put in place to mitigate the potential impacts on underlying habitats from loose gravel. We advise that the locations of the gravel bags should be monitored post consent.
F23 | 20 | Whilst we understand that the Applicant is committing to minimising the distance of the route through subtidal chalk, we advise that our previous advice regarding consideration of extending the HDD exit pit location further offshore to potentially further minimise impacts on chalk does not appear to have been considered. We advise this is considered as part of an appraisal of all potential options to minimise the damage to this irreplaceable habitat. |  | See F22 |  | No change |  | We note that point 2.1.11 of the Applicant's response to deadline 2 submissions, suggests that the 'detailed design of the landfall construction works will take place post-consent with the appointed contractor, taking account of survey information also gathered post consent. The principal means of determining the method used will be technical viability, withconsideration given to minimising environmental impact.' We note the options to be fed into this design included the location of the exit pit, potentential use of duct extensions, vessel grounding or the use of gravel bags. Natrual England's advice reamains that full consideration needs to be given to using the methodology that minmises the loss of irreplaceable chalk as far as possible.
Priority Habitats and Micrositing
F24 | 21, 67, Summary J | Natural England notes that following key Habitats of Principal Importance (Section 41 of the NERC Act (2006)) have been identified within the study area: •Sabellaria spinulosa •Littoral, sublittoral chalk, subtidal chalk •Fragile sponge and anthozoan communities on subtidal rocky habitats • Peat and clay exposures • Sublittoral sands and gravels, and sheltered muddy gravels. Additionally, the following Annex I features have been identified: • Annex I stony reef • Annex I Bedrock Reef. Black seabream (a feature of the adjacent MCZ) nests have also been known occur over the cable corridor. Natural England’s conservation advice suggests these are often found on near horizontal bedrock with a thin layer of sediment, and often track the moderate energy infralittoral rock and thin mixed sediments feature of the MCZ. Nests are often associated with rocky outcrops in shallow waters (<10 m) with thin sediment veneers. Natural England advises that these features should have their extent fully mapped as part of the pre-construction surveys, to inform avoidance via micrositing around them wherever possible. In addition to known black seabream nests sites, we advise that, as part of the pre-construction survey, suitable habitat for bream nesting is mapped. In relation to stony reef, we advise Golding (2020) is considered in addition to Irving (2009). We advise that the commitment to micrositing in relation to these features (C29) should also be applied to the siting of turbines, construction equipment (such as jack up barges and anchors), and all operations and maintenance works. This will require the Applicant to have data less than two years old to inform any ongoing operations and maintenance works that results in direct disturbance to areas where priority, Annex 1 biogenic reef habitats, areas of habitat suitable for bream nests could be present. This will likely require ongoing data collection throughout the project lifetime. We advise that the requirement to avoid priority habitats where possible is specified in the commitments, and that this should be a condition of the DCO/DML. The monitoring to inform micrositing should also be included within the IPMP. NB: Rampion 1 microsited around areas of stony reef in consultation with Natural England and the MMO so there is a similar expectation that Rampion 2 would instigate micrositing too. |  | No change |  | No change |  | We note that point 4.2.2 of the In Principle Sensitive Features Mitigation Plan has been updated to include 'Throughout export cable installation activities, there will be no anchoring of vessels within the MCZ or other designated site boundaries'. Whilst we support there being no achoring in designated sites, we advise that this does not address our concerns regarding the micrositing of anchoring around the senstive habitats listed in this point. Addtioanlly, this does not adress our advice in releation to avoding desingated sites, and micrositing around sentive features outside of sites in realtion to siting of turbines, construction equipment (paricualry jack up barges/rigs, which we assume may be used if anchours are not), and all operations and maintenance works. We note the addtion of peat and clay exposures to the export cable installation commitments, which we agree should be included. We note that this update does not always follow through into other parts of the text e.g point 5.2.4. We advise that the document is ammended to consitently refelct this udpate. All other points remain unaddressed.
F25 | 22 | Natural England requires clarification that both outcropping chalk and chalk with a thin sediment veneer, which would also be considered subtidal chalk, have been considered in the assessment. Natural England requests that the Applicant provides clarity on this and ensures that the ES has assessed outcropping chalk correctly. |  | No change |  | No change |  | No change
F26 | 23, 24 | It is stated in this section that ‘Observations of discrete Sabellaria spinulosa reef habitats were deemed to be of low ‘reefiness’ across the development site'. Natural England advises that Sabellaria spinulosa reef of all quality is protected under Section 40 and 41 of the Natural Environmental and Rural Communities (NERC) Act 2006. Therefore, due regard must be given to the conservation of this habitat. We advise these biotopes are given national importance. Natural England seeks clarity on whether all areas where potential reef was identified from the geophysical survey were investigated with DDV. We advise that this will be required for pre-construction surveys to ensure the full extent of all areas of reef is understood to inform micrositing. Natural England advises that all areas of Sabellaria spinulosa and stony reef are identified and mapped as part of the pre-construction survey to information micrositing and this should form part of the IPMP. We advise that this work is key to informing the micrositing of the cable route to avoid these features and is in line with what occurred for Rampion 1. |  | No change |  | No change |  | No change
F27 | 27 | Natural England advises that habitat loss or disturbance during construction should not be contextualised in relation to habitat availability in the wider area, particularly where it is protected under Section 41. Where the cable is installed through chalk, this represents a permanent loss of irreplaceable habitat listed as a Habitat of Principle Importance as under section 41 of the Natural Environmental and Rural Communities (NERC) Act 2006, which both the developer as a statutory undertaker and the regulator have a duty to protect. We understand that it is currently thought a mechanical trencher may be required over 54% if the route, which has the potential to cause wider damage to chalk compared to some of the other trenching methods mentioned. Therefore, the magnitude of impact should be Major/Moderate. We advise the mitigation measures are amended to allow for more detailed consideration particularly measure C-272. Natural England should be consulted on the Cable Burial Risk Reporting and the Outline Cable Specification and Installation Plan at the consenting stage. Within these, we would expect to see evidence that the commitments proposed have been adhered to and the loss of chalk minimised as far as possible. We disagree that the current information on the mitigation measures provided allows the reduction of the magnitude of impact to Negligible. Natural England advises that monitoring of the of the cable route through chalk will be required and that this should be considered in the monitoring plan. We advise the magnitude is amended to reflect permanent loss of irreplaceable chalk, and that there is a clear commitment to how evidence will be provided to show the mitigation measures have been adhered to. Natural England advises that further consideration is required in relation where trenched chalk will be deposited. Ideally it would infill any trench as a form of cable burial protection (rather than impacting on other habitats) decreasing the need for further external cable protection. However, it should be noted that because the structure of the chalk will be irreparable will still be classed as a permanent impact. |  | No change |  | No change |  | Please see our response to BP 1.10 in Appendix N3 of our deadline 3 submission (REP3-086). We note that any commitment in relation to infilling the cable trench with the excavated chalk would need to be secured. Our advice remains unchanged on the other aspects of this point.
F28 | 28 | While the same advice applies for any loss of cobble reef, Sabellaria spinulosa, peat and clay exposures, and bream nests etc. (as the environmental conditions may no longer be suitable where they had potentially been before), we understand that in the first instance the intention will be to avoid these habitats, whereas not all chalk can be avoided. We advise that, should micrositing not be possible, then recovery will need to be robustly demonstrated in the monitoring. The assessment should assume the worst-case scenario that these features cannot be avoided. The assessment in relation to Sabellaria spinulosa refers to recovery within two to ten years, but this does not consider if the underlying habitat has been lost or changed, and therefore Sabellaria spinulosa cannot recover in such locations. We advise this will require monitoring to demonstrate recovery. We advise that the Applicant further considers the magnitude of impact and sensitivity with regards to these features, and that monitoring of recoverability is included in the IPMP. |  | No change |  | No change |  | We note the Applicants response to written question BP 1.11. We support the seasonal restriction on works in the cable corridor, which prevents direct impacts on black seabream during the senstive season (March to July). We advise that C-273 should be updated to make it clear this incldues all work within the cable corridor (includuing preparations and UXO clearance). However, it should be noted that there may still be impacts on the underlying habtiats that support bream nesting should they not be able to be microsited around. We advise that monitoring of these underlying habitats is required to ensure they are able to reocver and are still sutiable for nesting. Our advice unchanged on this point.
F29 | 29 | We do not agree with the methodology of contextualising the magnitude of impact from long-term habitat loss, with it being 0.6% of the proposed DCO. This is an oversimplistic assessment, given that habitats are present in different proportions within the boundary. We do not consider any loss of biotopes representing subtidal chalk, Sabellaria spinulosa, stoney reef, peat and clay exposures, or bream nests as Negligible in magnitude. Based on the definitions in Table 9.18, permanent loss is either Major or Moderate magnitude, and therefore at a minimum the magnitude here needs to be Moderate, as opposed to Negligible which suggest no sensitivity of the receptor to this change. Natural England also does not agree with the concept that changing the habitat is a beneficial effect, as it represents a change from natural habitat to a habitat type that is not natural in this area. We advise that the assessment is revised by the Applicant to account for this. |  | No change |  | No change |  | No change
F30 | 30 | We advise that in addition to underwater noise from UXO clearance, the potential for this activity to physically damage the priority habitats, designated site features and seabream nests outside of the MCZ also needs to be considered. Natural England advises that the Applicant needs to consider the potential impacts from UXO detonation on benthic habitats and/or mitigation measures for making the UXO safe without impacting on benthic habitats. |  | No change |  | No change |  | No change
F31 | 45, Summary K | We advise that in relation to ‘Temporary habitat disturbance from jack-up vessels and cable maintenance works’, indirect impacts on Kingmere MCZ and Offshore Overfalls MCZ should be considered. We advise that the Applicant will need to demonstrate how ongoing works will continue to microsite around sensitive features, and that this will require ongoing data collection where there is biogenic reef. Natural England advises that monitoring will be required to inform recovery of benthic habitats from construction and the 5 yearly review of the Operations and Maintenance plan, which is yet to be agreed. We will work with the Marine Management Organisation (MMO) to secure adequate monitoring conditions. |  | No change |  | No change |  | No change
F32 | 46 | Natural England advises that further explanation is provided here as to how these mitigation measures will be applied to cable repair works during the operational period. We do not agree with the reduction to negligible here, as it is unclear that measures such as installation techniques would carry over to the operational works. We advise further information is provided by the Applicant to demonstrate how the mitigation measures would be applicable to the operation and maintenance phase. |  | No change |  | No change |  | No change
Sediment Plume
F33 | 31 | Natural England previously requested illustrative plume modelling to understand the impact ranges presented in the Table, in relation to impacts on surrounding designated sites. Whilst we note that the Applicant has attempted to address this with the provision of Figure 2.3 in Appendix 6.3, the 50m buffer on this is not discernible, and the 500m buffer is unclear. It also does not specifically demonstrate depth contours within the adjacent designated sites (Kingmere MCZ and Offshore Overfalls MCZ). We seek clarification that, given the volume of underlying chalk substate, chalk has been considered specifically in the plume modelling. Natural England is aware that persistent chalk plumes were visible as part of the Rampion 1 construction, and therefore advises that it is important that this has been specifically considered as part of Rampion 2. We advise that a clearer figure is provided by the Applicant in an updated chapter, and that further consideration is given to this matter in line with our comments on marine processes, so that the impacts on benthic features of designated sites can be clearly and fully understood. We advise that detail is added to the reporting to demonstrate chalk plumes have been considered, based on lesson learnt from plumes that occurred during Rampion 1’s construction. Monitoring of chalk plumes should be included within the IPMP. |  | No change |  | No change |  | No change
F34 | 26, 54 | In addition to considering cable laying techniques that minimise the footprint, consideration should also be given to reducing suspended sediment, and maximising recovery/avoiding persistent trenches. We advise cable installation techniques that minimise suspended sediments, and therefore secondary impacts on Kingmere MCZ, are considered. We advise this is considered further by the Applicant within the assessment (particularly the MCZ Assessment and as part of the Outline Cable Specification and Installation plan. |  | No change |  | No change |  | No change
F35 | 32, 37 | As previously highlighted to the Applicant Natural England highlights that plume modelling for Rampion 1 may no longer be appropriate for Rampion 2 due to progression of sustainable development in the convening time e.g. construction of Rampion 1 and changes to the aggregate’s licenses. Natural England advises that robust justification should be provided as to why this is still applicable. We advise this justification is provided by the Applicant as part of the consenting phase. Natural England advises that any modelling conducted in 2012 needs to be validated to consider the Rampion 2 proposals (which are closer to the aggregates sites) and would need to take into account the current aggregates licences. We advise this evidence is provided by the Applicant to inform the cumulative impact assessment and the ES updated accordingly. |  | No change |  | No change |  | No change
F36 | 33 | Natural England notes that the wording of the activity of impact line two in Table 9.8 should be clarified. We advise the wording is amended to recognise that temporary increase in SSC and sediment deposition is an issue for as far as the plume extends, and not just within the DCO limits. We advise this wording is amended by the Applicant and informs the monitoring requirements within the IPMP. |  | No change |  | No change |  | No change
F37 | 34 | We note that habitat disturbance during the operation and maintenance phase is prefaced by the word ‘temporary’. We advise that it should not be assumed that this impact would be temporary. We advise that it is also possible that cable maintenance activities could lead to temporary increase in SSC and sediment deposition. We advise this wording is amended, and that the full range of relevant impacts are assessed. |  | No change |  | No change |  | No change
F38 | 35 | We acknowledge the description that ‘Drilling mud noted as persisting and very high levels of suspended sediments expected around export cable route’. We seek clarification that this has been considered in the plume modelling. The text suggests that the release of drilling mud has the potential to persist in suspension for days or longer. We advise this timeframe is not consistent with a negligible magnitude. We advise clarification is provided by the Applicant and consideration is given to updating the magnitude with an updated ES chapter. |  | No change |  | No change |  | No change
F39 | 36 | Natural England disagrees that the impacts within the 500m buffer, where they affect the MCZs, can be determined to be Minor. The impact on features within this area should not be contextualised as being small within the context of the whole of the MCZs. We advise more detailed consideration is required in relation to impacts on the features specifically within this area of impact. We disagree with the overall magnitude of impact being Minor. We advise that further consideration is given by the Applicant to impacts on the specific features of Kingmere and Offshore Overfalls MCZs within the ES. |  | No change |  | No change |  | No change
Designated sites
F40 | 80 | Natural England advises that potential benthic supporting habitats identified in the conservation advice for the bird features of Solent and Dorset Coast SPA are listed here. We advise this is chapter is updated to include supporting habitats of the SPA which is important for wider ecosystem consideration in the EIA.
F41 | 38 | Natural England highlights there is inconsistency with the descriptions of Solent and Dorset Coast SPA and Pagham Harbour SPA. The bird features have not been mentioned here and it is unclear if the habitat description relates to the supporting habitats for these species listed in Natural England’s conservation advice. We also note that Pagham Harbour Ramsar has been omitted from this table. We advise this should be considered in relation to supporting habitats for bird features. We further note that none of the SPAs, and only Climping Beach SSSI, have been labelled on Figure 9.8 ‘Designated sites in relation to Rampion 2’. We advise all the sites under consideration should be clearly labelled. We advise this is updated by the Applicant to help support the Ornithological considerations. |  |  |  | We note that an updated figure 9.8 has been provided, however this figure still omits Beachy Head West MCZ and Utopia MCZ.
F42 | 39 | We advise the features of SSSIs should match the citation on Natural England’s Designated Sites System. We advise this is reviewed by the Applicant and the ES updated accordingly.
F43 | 40, Summary G | Natural England seeks clarification on whether habitats protected under the NERC Act/ Habitats of Principal Importance/Annex I identified in the intertidal area will be entirely avoided due to the use of HDD. We note that Climping Beach SSSI and Worthing Lumps Local Wildlife Site (LWS) will be subject to mitigation measure C-43, and so there will be no direct impacts on these sites. We seek clarification on whether access to these areas by works vehicles or equipment will be required. We advise clarity is provided on this point by the Applicant, to provided confidence in the commitment to fully avoid direct impacts on the SSSI and that priority habitats will be avoided in the intertidal area. If there is any reason why this might not be possible, this should be presented upfront as a worst-case scenario. We note that the full viability and extent of Horizontal Directional Drilling (HDD) is yet to be confirmed. We advise geotechnical data is collected and presented to support this. |  | The Applicant has provided further information, which we have provided comments on in Appendix DF 2. Our comments remain unchanged on this issue. |  | No change |  | Natural England understands that the Applicant intends to submit further infomration on this point at deadline 4. We will review this and provide further advice as required.
Other
F44 | 41 | It is in this section it is stated that ‘RED will undertake pre-construction surveys to determine the exact amount of clearance required prior to construction within the array area and the offshore export cable corridor. Micro-sitting around boulders will be considered where appropriate. Furthermore, RED propose to use a plough to remove boulders’. We advise that there is no specific commitment to this, and that consideration should be given to placing boulders on similar habitats, and not on any of the habitats listed above. We advise this is considered further by the Applicant and included in the outline Cable Specification and Installation plan. |  | No change |  | No change |  | No change
F45 | 42 | Natural England has concerns regarding the statement that ‘material excavated from HDD exit pits might also be temporarily stored within the offshore array area or export cable corridor, if and where designated as a spoil disposal area’. We disagree with the wording that measure C279 will be of ‘direct benefit to benthic habitats’. Instead, this is about minimising impact. We advise that with any disposal locations, the Applicant would need to consider potential impacts on the designated sites, avoiding locations of sensitive features and consider placement of material on similar sediment types. Natural England has particular concerns about material being stored in proximity to bream nesting habitats. Additionally, we question if the Applicant considers that they will be able to retrieve this material successfully, particularly if it were chalk. We would expect to see monitoring included in relation to any disposal locations within the DCO boundary. We advise this is further considered by the Applicant in the Outline cable specification and installation plan, and Natural England is consulted on a final plan. Monitoring to ensure that the disposal impacts whereas predicted e.g. did not impact negatively on designated site features and/or supporting habitats should be included within the IPMP. |  | No change |  | No change |  | No change
F46 | 43 | Natural England should be consulted on the final Project Environmental Management Plan (PEMP), which we understand will include a biosecurity plan to ensure that the risk of potential introduction, and spread of Marine INNS from increased vessel activity is minimised. We advise that the Applicant provides an updated outline PEMP throughout the examination process. Consultation with Natural England on the finalise plan (pre-construction) is a condition as part of the DCO/DML.
F47 | 44 | Natural England should be consulted on the final Marine Pollution Contingency Plan (MPCP) in relation to the measures to prevent accidental release of pollutants. We advise that the Applicant provides an updated outline MPCP throughout the examination process. Consultation with Natural England on the finalise plan (pre-construction) is a condition as part of the DCO/DML.
Document used: [APP-038] 5.9 Report to Inform Appropriate Assessment
F48 | 49 | Natural England notes that it is stated that ‘the distance to the Solent Maritime SAC (15.9km at closest point)’. We advise that the Applicant checks this, as based on Figure 9.8 of the Benthic Ecology Chapter, Solent Maritime SAC is outside of the study area, which we understand is based on the 16km tidal exclusion. We advise this is checked and amended as necessary.
F49 | 50 | Natural England agrees with the conclusion of no adverse effects on integrity (AEoI) alone or in combination for Solent Maritime SAC, South Wight Maritime SAC, or Solent and Isle of Wight Lagoons SAC. We understand that these sites are located outside of the 16km tidal exclusion.
Document used: [APP-040] 5.11 Draft Marine Conservation Zone assessment
F50 | 51 | We note that Utopia MCZ is in close proximity to the boundary of the study area. Therefore, we seek clarification on the preciseness of the information used to define the study area. We advise further clarity is provided by the Applicant in an updated MCZ assessment.
F51 | 53 | We note that many of the measures included have limited relevance to the MCZ Assessment specifically. Measures that reduce or prevent indirect effects are relevant, such as suspended sediments, scour, or changes to seabed processes. We advise that the Applicant update the assessment accordingly.
F52 | 55 | We note that the Outline Project Environmental Management Plan (OPEMP), is currently very high level and will be developed further pre-construction. It is key this contains sufficient measures in relation to invasive species. We advise that Natural England is consulted on the final document to agree that the final measures proposed are sufficient. And that the outline PEMP is further refined during examination.
F53 | 56 | Natural England notes that EIA terminology and methodology to assess impacts are being applied throughout the MCZ Assessment. For clarity, the MCZ Assessment should seek to define and understand the potential of the conservation objectives being hindered by external activities/impacts. We advise that, to avoid confusion, the MCZ Assessment should not use EIA terminology. Additionally, we note that our comments within the thematic chapters regarding significance of effect and magnitude also apply to this assessment, where the Applicant has brought forward these conclusions to the MCZ Assessment. We advise that the MCZ assessment should be amended to reflect our comment. Otherwise, agreements cannot be reach on the conclusions drawn. |  | No change |  | No change |  | No change
F54 | 57 | We note that indirect impacts that were assigned a ‘Negligible’ magnitude in the ES EIA have been screened out, and not taken to Stage 1 Assessment. We advise that our comments on the relevant chapters are taken into account and the screening is adjusted as necessary. We advise that our comments on the relevant thematic chapters are considered against any decisions made in the MCZ Assessment and potential impact pathways that could hinder the conservation objectives for the site assessed. |  | No change |  | No change |  | No change
F55 | 58 | Natural England advises that where impacts have been screened out due to insignificant effects on coastal and marine processes, our outstanding comments on benthic chapter should be taken into account. Natural England advises that the Applicant considers our comments on coastal and marine processes and the assessment updated as necessary noting that there may be residual benthic impact pathways. |  | No change |  | No change |  | No change
F56 | 59 | We advise that the sensitivity of both moderate energy infralittoral rock and thin mixed sediments, and subtidal chalk (a feature of Kingmere MCZ) in relation to marine INNS, is a worst-case scenario within Natural England’s advice on operations. Therefore, we advise this is assessed as High. We advise that the sensitivity is revised to High by the Applicant in an updated assessment and mitigation measures adopted accordingly. |  | No change |  | No change |  | No change
F57 | 60 | It is stated that the ‘maximum sensitivity of the benthic receptors is low, as a result of the tolerance and recoverability of the majority of the benthic receptors’. We seek clarity that the WCS in terms of all relevant benthic receptors has been used to inform the maximum sensitivity? We advise that information on the sensitivity of the receptors involved is stated by the Applicant within an updated assessment to demonstrate that the worst case in terms of sensitivity has been taken forward.
F58 | 61, 62 | Natural England agrees with the sensitivity assigned to the features of Kingmere MCZ in relation to increases in suspended sediment concentrations (SSC) and sediment deposition, as these are in line with our advice on operations. However, based on the fact the 500m buffer does overlap with an area of Kingmere MCZ, we do not agree with the assessment of a Minor magnitude of impact. We disagree with this being contextualised in relation to the site as a whole. We draw your attention to our detailed comment above on this impact. This comment also applies to Offshore Overfalls MCZ. We advise that the magnitude of impacts should be revised to consider the impact on the area of overlap specifically, as opposed to contextualising this in relation to the site as a whole.
Document used: [APP-239] 7.17 In Principle Sensitive Features Mitigation Plan, [APP-145] 6.4.9.5 ES Volume 4 Appendix 9.5 Technical Note Cable Corridor area mitigation for sensitive features, [APP-040] 5.11 Draft Marine Conservation Zone assessment.
F59 | Summary G | We advise that to understand the likely effectiveness of the mitigation measures proposed, geotechnical data is provided at the consenting stage to inform a Cable Burial Risk Assessment (CBRA), and outline Cable Specification and Installation Plan (CSIP) that both clearly take into account lessons learnt from Rampion 1. |  | The Applicant has provided further information, we have provided comments in Appendix DF 2. Our comments remain unchanged on this issue and we advise these plans are provided. |  | No change |  | Our advice remains unchanged from what was set out in our Appendix DF2 (REP2-038).
F60 | 52, 63, 65 | Natural England advises that it is key that all mitigation measures are secured in any consent issued. Natural England has concerns regarding the plan not being finalised until the post-consent/pre-construction phase, and that it is stated the mitigation measures are not confirmed. We advise that where mitigation measures are essential to the assessment, including the MCZ Assessment, we cannot agree to the assessment conclusions without sufficient certainty in the measures being progressed, and the ability to achieve the levels of mitigation required. We support the final plan needing to be signed off by Natural England but advise that further information is required to understand the feasibility and effectiveness of mitigation measures through the consenting phase. Natural England advises that there is a risk that mitigation through the mitigation plan may not achieve its aims. We advise that further investigation and information is provided by the Applicant at this stage. We advise that all mitigation measures proposed are secured in the DCO/DML. We advise that further information is required, particularly geotechnical information to inform the Cable Burial Risk Assessment and this is to be updated during the consenting phase. |  | The Applicant has provided further information, which we have provided comments on in Appendix DF 2. Our comments remain unchanged on this issue. |  | No change |  | No change
F61 | 53 | We note that many of the measures included have limited relevance to the MCZ Assessment specifically. Measures that reduce or prevent indirect effects, such as suspended sediments, scour, or changes to seabed processes are relevant. We advise that the Applicant update the assessment accordingly.
F62 | 74 | It is suggested that paleochannels will be targeted to maximise successful burial and minimise cable protection. We advise that successful burial in paleochannels is dependent on the depth of sediment and how dynamic the area is. Our understanding is that sediments in this area are generally thin. Additionally, we advise that consideration needs to be given to the width of the paleochannels, as there is a possibility that four cables with appropriate separation distances will result in the outside cables being buried on the potentially shallower edges of the channel. Considering both these points, we advise that further geotechnical information is gathered and that a Cable Burial Risk Assessment is provided pre-consent as opposed to post consent, to provide confidence on whether burial in paleochannels is likely to be successful. We advise that a Cable Burial Risk Assessment is provided by the Applicant pre-consent due to the uncertainty of burial in paleochannels being achievable. |  | No change |  | No change |  | No change
F63 | 76 | It is stated that ‘With regards to trenching and burial, it is clear from the geophysical survey data for the offshore export cable corridor area that a mechanical trencher is required to achieve burial in chalk areas without sufficient soft sediment cover.’ We advise that this should be clearly assessed in the Benthic Ecology Chapter, as this makes some of the mitigation measures proposed for chalk unviable. We would expect to see consideration pre-consent of all options for resolving this issue of cabling through chalk, for example, consideration should be given to be possibility of pinning the cable to the seafloor to minimise the loss of this irreplaceable habitat. We advise that impacts and mitigation success is fully considered by the Applicant in an updated Benthic Chapter. |  | No change |  | No change |  | No change
F64 | 77 | In relation to ‘the ability of the nearshore trencher to continue on to successfully complete the offshore scope’, we advise that a situation may exist where minimising the environmental impacts involves using different techniques for the two areas. This should not be ruled out based on cost. We advise that it is critical the methodology selected furthest minimises the environmental impacts selected and is informed by the Cable burial risk Assessment. |  | No change |  | No change |  | No change
F65 | 64 | Natural England understands that final pre-construction survey data is required to inform micrositing. Natural England requests that further information is provided on the contents of the pre-construction surveys. Natural England advises the inclusion of full geophysical coverage (including side scan sonar) and full drop-down video coverage of all the sensitive features identified, as this is required to determine the extent of these features and inform micrositing. We advise that any data used to inform micrositing should be less than 24 months old at the time of construction. We refer the Applicant to our detailed comments above. We advise that the Applicant updates the IPMP accordingly as part of the consenting process. |  | No change |  | No change |  | No change
F66 | 66, 68, 73 | Natural England advises that post construction monitoring will be required. Natural England expect that monitoring would be undertaken to demonstrate recovery, with further measures being triggered if this was not shown. We advise this is included by the Applicant within the updated IPMP. We advise that a pre-construction monitoring plan will need to be agreed in consultation with NE and this should be guided by the IPMP which should be updated by the Applicant to ensure key questions will be answered by the monitoring. |  | No change |  | No change |  | No change
F67 | 67 | Natural England advises that the offshore MCZs are missing from this Figure. We request that these are added by the Applicant. |  | These have been added. Issue resolved
F67.5 | 69 | We advise that it should be acknowledged that up to 20% of the export cable may require cable protection, and that 54% may need to be mechanically trenched. Therefore, there is the potential for permanent habitat loss/potentially significant habitat alteration if sensitive features cannot be avoided. In reference to the points regarding ‘routeing design and micrositing’, and ‘use of specialist cable laying and installation techniques’ we advise that the Applicant has not acknowledged the above mechanical trenching situation, which potentially renders this mitigation ineffective over more than half the route already n reference to the points regarding ‘routeing design and micrositing’, and ‘use of specialist cable laying and installation techniques’ we advise that the Applicant has not acknowledged the above mechanical trenching situation, which potentially renders this mitigation ineffective over more than half the route already. We advise the limitations to the achievability of the mitigation proposed need to be fully considered by the Applicant and informed by the updated Cable Burial Risk Assessment as part of the consenting phase. |  | No change |  | No change |  | No change
F68 | 70 | We refer you to our comment above regarding these mitigation measures/commitments. Refer to our comments above.
F69 | 71, 25 | Natural England advises that across industry a 50m buffer is implement around all Sabellaria spinulosa reef to reduce the likelihood of direct impacts. We advise that the commitment/Schedule of mitigation is updated to include the 50m buffer. We understand that a 50m buffer would be applied to all sensitive features, and advise that this should be applied as a minimum to the limits of the cable corridor geophysical data collected, to account for any potential features just over the boundary. This is independent to buffering requirements in relation to other aspects. We advise this is amended to provide commitment to the buffers and the Applicant updates the IPSFMP accordingly. |  | No change |  | No change |  | No change
F70 | 72 | We note that when the environmental and technical constraints are combined visually, there already appears to be areas of potential biogenic reef that could be impacted, or where a buffer may not be possible. Whilst we support micrositing, we advise that it already appears it may not be possible to avoid some features, particularly when 4 cables will need to be installed. We also note that this figure just includes biogenic reef or potential black bream nests and advise that there are other sensitive features that have not been added (see comments above), which may compound the issue. We advise that the mapping is updated by the Applicant to include all sensitive features that require micrositing, and that discussion is provided in relation to where avoiding features may be unavailable, or buffers may be insufficient i.e. how will impacts be minimised? |  | The update to Figure 5.1 provided just increases the resolution, so our comments remain unchanged. |  | No change |  | No change
F71 | 78 | We note that both these methods require support vessels in the nearshore environment. We advise that this has the potential to further impact the chalk, due to grounding of vessels. Natural England advises that although we understand that floatation pits will not be used to aid nearshore vessels, there is no clear and consistent alternative presented. We advise that full consideration of the environmental impacts of all options is provided, alongside sufficient information to determine effectiveness. Natural England has concerns that without this information, the Applicant will find that they need to amend the methodology to included floatation pits post-consent, something that NE is unlikely to be supportive of. We advise that the Applicant provides a clear and consistent methodology alongside further information on the possible effects and feasibility. |  | See F22 |  | No change |  | Please see response to point F22.
F72 | 79 | We refer you to our comments on the Offshore In-principle Monitoring Plan.

## G - Other Plans - Marine
Point | Point Number(s) Appendix G [RR-265] | Taken from Natural England’s Relevant and Written Representations Rampion 2 Appendix G -Other Plans – Marine [RR-265] | RAG Status Rel and WR Rep, and D1 | Consultation, actions, progression | RAG Status at D2 | Consultation, actions, progression | RAG Status at D3 | Consultation, actions, progression | RAG Status at D4
Document used: [APP-240] Offshore in Principle Monitoring Plan
G1 | 1 | We advise that this is the first time Natural England has had sight of this plan, and that we have not been involved in its development. We look forward to working with the Applicant to defining the parameters of the plan to ensure it is fit for purpose.
G2 | 2 | In providing our advice Natural England is drawing on our wealth of experience of post-consent monitoring discussions and implementation. We strongly advise that rather than focusing on the exact details of the surveys as highlighted by the Applicant in the IPMP; the IPMP should set out the fundamental hypotheses/questions that will be tested by the monitoring based on the outcomes of the HRA, EIA and address issues of uncertainty and/or residual impacts. In addition, Natural England highlights that, while there is agreement that IPMPs are finalised post consent based on project design and timescales; this should not limit agreeing the IPMP prior to consent. Lessons have been learnt since the development of the IPMP for Rampion 1, which are based upon ongoing and reoccurring post consent disagreements with the developers on ecological monitoring requirements and survey effort required in order demonstrate key predictions of the Environmental Statement and/or HRA. Because this is a fundamental plan relating to all project phases - Natural England will submit detailed advice on the IPMP at Deadline 1. We will continue to work on this plan with the Applicant through the examination to process. |  | In addition to our relevant/written representation comments please also refer to Appendix G1 submitted at deadline 1. |  | No change |  | An updated In Principle Montoring Plan was submitted by the Applicant at deadline 3. Our comments at deadline 1 have not been addressed within this updated plan. Please see additional comments on specific aspects in points G2e- G2h. Once sufficent information has been provided Natual England will be able to provide more specfic rag rating than the overall rag highlighted here.
G2a | 2a | Overarching Concerns with the IPMP |  | Advice provided in Natural England's Appendix G1 at Deadline 1
G2b | 2b | 3.1 Engineering and design related monitoring |  | Advice provided in Natural England's Appendix G1 at Deadline 1
G2c | 2c | 3.2 Coastal Processes |  | Advice provided in Natural England's Appendix G1 at Deadline 1
G2d | 2d | 3.3 Offshore and intertidal ornithology |  | Advice provided in Natural England's Appendix G1 at Deadline 1
G2e | 2e | 3.4 Benthic subtidal and intertidal Ecology |  | Advice provided in Natural England's Appendix G1 at Deadline 1 |  |  |  | We note that the only amendment is the addition of peat and clay exposures, which are to be identified pre-construction and monitored post construction where identified. We advise that peat and clay exposures are not consistently added where other sensitive features are listed in table 4-3. We advise that features discussed in our benthic ecology and fish and shellfish tabs are still missing, including the identification and monitoring of areas of habitat suitable for black seabream nesting. This is particularly relevant within the cable corridor. We advise that all our other points within appendix G1, remain unaddressed.
G2f | 2f | 3.5 Fish and shellfish ecology |  | Advice provided in Natural England's Appendix G1 at Deadline 1
G2g | 2g | 3.6 Marine Mammals |  | Advice provided in Natural England's Appendix G1 at Deadline 1
G2h | 2h | Annex A: Natural England’s Advice on an In-Principle Monitoring Plan (IPMP) extracted and summarised from: Environmental considerations for offshore wind and cable projects - Phase IV Best Practice Advice for Post-Consent Monitoring, Version 1.0, July 2022.pdf (Parker et al 2022). |  | Advice provided in Natural England's Appendix G1 at Deadline 1 |  |  |  | We note that point 2.1.3 and commitment C-298 have been added regarding making data publicly available. We note the wording of this commitment is 'Where appropriate, the results of post-consent monitoring, data and reports will be made publicly available and provided to the relevant data repositories'. We advise that more robust wording of this condition would be 'Unless it can be demonstrated that there is a significant reason why the data cannot be made publicly available' instead of 'where appropriate'. We advise all other points remain unaddressed.
G3 | 3 | Natural England is concerned with how the purpose of the monitoring is conditioned within the DCO, we advise that the DCO/DML conditions should ensure that the monitoring is relevant to the issues raised and that adaptive management is secured should post-construction monitoring identify impacts that are significantly outside of those predicted in the Application. Natural England will work with the developer to ensure that all monitoring conditions are sufficiently fit for purpose. |  | No change |  | No change |  | No change
Document used: [APP-234] Outline Scour Protection and Cable Protection Plan
G4 | 4 | Natural England advises that a key consideration is that the type of scour protection used will be removable upon decommissioning. Natural England advises that options that involve introducing plastic to the marine environment have the potential to degrade during the lifetime of the project and raise concerns with regards to marine pollution. We advise consideration is given to this. |  | We await consultation on an updated Outline Scour Protection and Cable Protection Plan to demonstrate the inclusion of the updated commitment with regards to the use of plastics. Our advice remains that an Outline Decommissioning Plan should be submitted into the examination in relation to consideration of the removability of scour protection on decommissioning. |  | No change |  | We note that a section refered to as 'propsed mitigation measures' has been added as point 1.4 of the Outline Scour Protection and Cable Protection Plan submitted at D3 [REP3-040]. We advise that these measures are not fully in line with/ do not fully address our comments set out in our deadline 3 Appendix N3 submission and our deadline 2 Appendix DF2 submission. We particulary note that commitment C-283 only commits to removing gravel bags prior to completetion of contruction where possible. We advise that the gravel bags should be on the seabed for the minmum period required and that removal 'where possible' is not in line with the Applicants previous commitment to fully remove the gravel bags. In addtion, our advice remains that an Outline Decommissioning Plan should be submitted into the examination.
G5 | 5 | Natural England advises that we should be consulted on the final scour prevention and cable protection plan and the requirements for future surveys. We advise that consultation of Natural England on this plan is stipulated in the DCO.
G6 | 6 | We advise the Applicant considers lessons learnt from other wind farm projects alongside those from Rampion 1 in relation to potential scour and cable exposure, particularly around WTG’s. This plan should also consider the monitoring from Rampion 1. We advise that this is considered and evidenced within the plan. |  | No change |  | No change |  | No change
G7 | 7 | We note that the 20% quoted for cable protection seems to be an arbitrary figure across each aspect (inter-array cable, offshore interconnector cable, export cable) and is considerably higher than for all other OWF projects. We advise that further detail is provided within an updated plan on the information used, including any lessons learnt from Rampion 1, to inform this figure given this will be the maximum allowable amount. We advise that geotechnical data and a Cable Burial Risk Assessment (CBRA) is provided at the consenting phase to further understand the scour and cable protection requirements to ensure that a realistic worst-case scenario is presented. |  | No change |  | No change |  | No change
G8 | 8 | In relation to the figure for ‘replenishment during operations (% of construction total) 25%’, does this mean 25% of the original 20% put down during construction will need replacing during operation? Furthermore, will this be within the footprint of the protection put down during construction? We also note that this does not allow for any scour/exposure in locations that were not protected at construction. We advise that this seems unlikely, particularly in any areas of mobile sediment. This needs to be clarified. We advise that further detail is provided within an updated plan on the information used, including any lessons learnt from Rampion 1, to inform this figure given this will be the maximum allowable amount. We advise that geotechnical data and a Cable Burial Risk Assessment (CBRA) is provided at the consenting phase to further understand the scour and cable protection requirements to ensure that a realistic worst-case scenario is presented. |  | No change |  | No change |  | No change
G9 | 9 | Natural England notes that many different cable protection methodologies are included within the plan; some of which are not conducive to minimising the impact footprint and maximising recovery, as committed to in the mitigation measures. Therefore, we advise that it is critical that engineering decisions include a hierarchy of the different methodologies and their relative environmental impacts, and that these work areas are progressed in tandem. We advise that the options within the outline plan for scour prevention and cable protection should be limited to those options which sufficiently meet both engineering and ecological requirements and this is agreed as part of the consenting phase. Natural England advise that post installation/decommissioning recovery will need to be demonstrated by monitoring, particularly for methods where full recovery has not been achieved previously in similar sedimentary conditions. We advise the Applicant refines the scour prevention and cable protection options included within the outline plan prior to consent. |  | No change |  | No change |  | No change
G10 | 10 | It is stated that ‘In the inshore area approaching the landfall, duct extensions may be required to enable the landfall Horizontal Directional Drilling (HDD) ducts to be extended further offshore to facilitate cable installation from an installation vessel situated offshore. These duct extensions will be of a similar diameter to the HDD ducts and installed in their own trench at a similar depth of cover to the export cables. The duct extensions will be backfilled before the arrival of the cable installation vessel.’ We advise that this does not appear to have been considered within the ES. Natural England would potentially support extension of the HDD further offshore if it could be demonstrated that this would further minimise the loss and damage of habitats, such as irreplaceable chalk. However, in order to understand this, all potential methodologies should be clearly set out and assessed. Especially, as written, there still appears to be significant inconsistencies and uncertainties regarding nearshore installation methodologies. Natural England advise that this is fully considered in an updated ES. We advise that within the updated plan and/or ES a clear appraisal of consistent options is required. Lessons learnt of the limitations and constraints of constructing in shallow chalk needs to be clearly presented and discussed. |  | The Applicant has provided further information, which we have provided comments on in Appendix DF 2. Our comments remain unchanged on this issue. |  | No change |  | No change. See our deadline 3 Appendix N3 submission and our deadline 2 Appendix DF2 and N2 submissions.
G11 | 11 | It is stated that where ground conditions are not suitable, the ‘construction of temporary sand/gravel beds may be required.’ We advise this is not what is assessed in the benthic chapter of the ES (where bag material is mentioned). We have concerns regarding the environmental impacts of loose material being placed on the seabed and the ability to retrieve this after the works as required by OSPAR. Additionally, we advise that the grounding of vessels with or without a buffering material under the barge will damage underlying habitats. As per comment above. |  | The Applicant has provided further information, which we have provided comments on in Appendix DF 2. Our comments remain unchanged on this issue. |  | No change |  | No change. We refer you to our deadline 2 Appendix DF2 and N2 submissions. We particulary note that C-283 - still only suggests gravel bags, 'will be removed prior to the completion of construction, where practicable', as opposed to commiting to them being fully removed.
Document used: [APP-233] Outline Project Environmental Management Plan (offshore)
G12 | 12 | Natural England understand that the final Project Environmental Management Plan (PEMP) will be produced prior to construction and will be developed following the detailed design process. We advise that until these details are fully understood Natural England cannot provide final comment on the suitability of the management measures proposed. Therefore, we advise that a more detail is provided within an updated plan to provide the necessary comfort to the Secretary of State that impacts will and can be sufficiently managed. We advise a holistic approach to the final plan to bring together all agreed measures across the ES and to ensure that the contractor is fully aware of all commitments. We advise that an updated plan is submitted into examination and that Natural England are consulted on the final version prior to construction. |  | No change |  | No change |  | No change
G13 | 13 | We advise that pollution incidents, reports, and situation updates should be emailed to the Natural England Marine Incidents Mailbox:marineincidents@naturalengland.org.uk. We advise that Appendix A is primarily a list of headings, with the details to be included in the final plan. Therefore, we cannot comment on the suitability of the measures to be included. We advise this contact is added to the plan. We advise that an updated plan is submitted into examination and that Natural England are consulted on the final version prior to construction. |  | No change |  | No change |  | No change
G14 | 14 | We advise that until this plan has been produced, we cannot comment on the suitability of the measures to be included. We advise that an updated plan is submitted into examination and that Natural England are consulted on the final version prior to construction. |  | No change |  | No change |  | No change
Document used: [APP-238] Outline Offshore Operations and Maintenance Plan
G15 | 15 | Natural England understands that this is an outline plan, which will be developed post consent. We advise that clarity should be provided regarding how the potential impacts of the finalised plan will be checked against the assessments made in the ES, MCZ Assessment, HRA etc. We advise that sufficient information should be provided at the preconsent stage to allow operations and maintenance (O&M) activities to be fully assessed. We advise that this plan is developed further preconsent to provided sufficient certainty in the accuracy of what is included in the assessments. |  | No change |  | No change |  | No change
G16 | 16 | Whilst an ‘additional Marine License may be required where works exceed those assessed within the ES or described within the DCO’, we advise that all reasonably predictable activities should be considered within the ES at the pre-consent stage, and sufficient data should be gathered to avoid the need for further licences unless something unpredictable comes up. In relation to unpredictable works, we advise that the Applicant seeks to understand what may have been required on other offshore wind projects to date, alongside lessons learnt from Rampion 1, to inform their predictions at the pre-consent stage. We also advise including a definition of what constitutes emergency work. Natural England advise that sufficient information needs to be gathered at the consenting stage, to minimise the requirements for unexpected further licences. |  | No change |  | No change |  | No change
G17 | 17 | In relation to cable repair/replacement/new cable protection, we advise that the Applicant seeks to gather sufficient information to give confidence that the ES assessment is as accurate as possible. We advise this includes gathering and considering geophysical and geotechnical information, as well as consulting requirements from other projects (including Rampion 1) for similar sedimentary conditions. We advise further information is provided and lessons learnt from Rampion 1 should be considered in relation to export cable cables not functioning immediately after installation. |  | No change |  | No change |  | No change
G18 | 18 | We advise undertaking required monitoring and recording and in turn this should be used to inform 5 yearly reviews of the activities, which Natural England wish to be consulted on. We advise that deployment of scour/cable protection under the DCO should be within the first 10 years from commencement of operations. We advise this is stipulated and is a condition of the DCO/dML. |  | No change |  | No change |  | We refer you to our advice in tab A (DCO DML) point A9 in relation to the deployment of scour protection.All other points remain unaddressed.
G19 | 19 | Where seabed disturbance is necessary and use of equipment such as jack-up barges is required, the Applicant should provide details showing how they will ensure that sensitive features (as identified in the benthic and fish ecology chapters), will be avoided. This is particularly pertinent to activities that could directly disturb ephemeral features such as Sabellaria spinulosa and inter annual variation of black bream nests. We advise that the preconstruction data (greater than 24 months old) will not be sufficient to inform micrositing of activities during the O&M phase. We advise that consideration needs to be given to ongoing data collection required to inform micrositing of activities during the lifetime of the project. We advise this is considered and further details provided as part of the consenting phase. |  | No change |  | No change |  | No change
G20 | 20 | Natural England would support reburial where exposure has occurred, or where cable repair/replacement is required, over the placement of rock protection. This would potentially allow recovery following reburial, whereas the addition of scour protection would lead to permanent habitat change/loss. We advise that the Applicant includes a cable burial hierarchy which make reburial the priority.
G21 | 21 | In line with the commitment to not undertake construction activities in the cable corridor during the sensitive season for black seabream, and the final piling mitigation, which is yet to be agreed, we advise that consideration is given to the impacts of operation and maintenance (O&M) activities. In relation to black seabream we advise that the Applicant also commits to only undertaking planned O&M activities outside of the sensitive period and that consideration is given to how impacts could be reduce during the sensitive period for any emergency works where a potential pathway for impact is identified. Natural England advise that the potential pathway for impact will depend on the activity and the location. We would have concerns for example should cable repair/reburial/replacement be undertaken in close proximity to the MCZ given the location of known seabream nesting areas. We advise it may be useful to set out a disturbance management plan, which sets out parameters of certain areas and when Natural England might need to be reconsulted for more significant activities in sensitive locations. We advise that this needs to be considered further by the Applicant. And a clear definition of what constitutes emergency works should be presented. We advise that a disturbance management plan should be consider in relation to O & M activities in sensitive areas. |  | No change |  | No change |  | No change
G22 | 22 | We note that there is currently no information on how the impacts of O&M works will be monitored. We advise that clarity is needed on this. We advise that the Applicant considers this further in an updated plan. |  | No change |  | No change |  | No change

## H - Landscape and Visual Impact
Point | Point Number(s) Appendix H - Landscape and Visual Impact [RR-265] | Taken from Natural England’s Relevant and Written Representations Rampion 2 Appendix H - Landscape and Visual Impact [RR-265] | RAG Status Rel and WR Rep D1 | Consualtion, actions, progression | RAG Status at D2 | Consualtion, actions, progression | RAG Status at D3 | Consualtion, actions, progression | RAG Status at D4
H1 | Detailed comments point 1 | TOPIC: HDD feasibility No feasibility studies are presented for the proposed use of the HDD technique for the trenchless crossings of the chalk scarps. The chalk scarps are one of the most sensitive landscape features of the SDNP and one of the reasons for its designation as a National Park. The assessment in the LVIA that no residual harm will result from the proposals is entirely predicted upon this mitigation measure. Natural England has advised and continues to advise, that without further information regarding the feasibility of HDD in relation to these scarps, all conclusions with regard to residual landscape and visual effects on the landscape of the SDNP as a consequence of the cable route can only be considered provisional and optimistic. Natural England has significant concerns about the permanent harm to the special qualities of the SDNP as a result of the reliance placed on the HDD crossing embedded mitigation measure which proposes a trenchless crossing method of taking the cable route through Michelgrove Park and Sullington Hill chalk scarps. The landscape and visual effects assessment in the Environmental Statement, and the assessed harm to the special qualities of the SDNP are all predicted upon the success of this mitigation measure. Undertake all site investigations and detailed studies for the HDD works on the chalk scarps prior to the commencement of the works through the SDNP to remove all ambiguity about the techniques likely efficacy. Full pre-commencement ground assessments to be undertaken for both chalk scarps, taking into account their individual ground conditions and topographies. |  | No change |  | No change |  | No change
H2 | Detailed comments point 2 | TOPIC: HDD feasibility and Ancient Woodland Michelgrove Park chalk scarp supports substantial areas of AW, a landscape feature of significant time depth. No feasibility studies for HDD have been presented which show that the Ancient Woodland at Michelgrove Park can be protected. Undertake all site investigations and detailed studies for the HDD works on the chalk scarps prior to the commencement of the works through the SDNP. Full pre-commencement ground assessments to be undertaken for Michelgrove Park chalk scarp, taking into account the Ancient Woodland. |  | No change |  | No change |  | No change
H3 | Summary of Natural England's advice - Paragraph 1.20 | TOPIC: HDD feasibility and defining landscape features of the SDNP The chalk scarps are a defining landscape feature of the two landscape character areas where trenchless crossings are proposed (B4: Angmering and Clapham Wooded Estate Downland relating to proposed alternative trenchless crossing TC-12a at Michelgrove Park and A3: Arun to Adur Open Downs where the rest of the trenchless crossings associated with Michelgrove Park and all those relating to Sullington Hill apart from TC-15a). The proposals to undertake site investigations in detailed stages puts the landscape of the SDNP at greater risk of harm. If one or both of the chalk scarps prove unsuitable for HDD, an alternative solution would have to be found, most likely once construction of the cable route has commenced through the National Park. In order to protect the landscape of the SDNP, all site investigation works should be undertaken prior to the commencement of the construction of any part of the cable route through the SDNP. Failure to do so would put the SDNP landscape at substantial risk of harm. The lack of detailed feasibility studies on trenchless crossings (and HDD) invalidates the assessment in the LVIA that there will be no residual effects on the SDNP and its special qualities, setting or integrity, as the assessment is not supported by credible evidence. As a result, the landscape effects during the construction phase on these landscape character areas should be Major and Significant. Reassess the landscape and visual effects on the SDNP based on the worst case (failure of HDD through the chalk scarps) |  | No change |  | No change |  | No change
H4 | Summary of Natural England's advice - Paragraph 1.20 & Point 8 of detailed comments | TOPIC: HDD and no specific commitment relating directly to the chalk scarps Natural England notes that trenchless crossings are mentioned in the Crossings Schedule (APP-122 Volume 4, Appendix 4.1) for Michelgrove Park and Sullington Hill. However, Michelgrove Park is not mentioned in the Commitments register [APP-254] in relation to trenchless crossings and the commitment in relation to trenchless crossings at Sullington Hill is relation to the Local Wildlife Site and not in relation to the chalk scarp (Commitments C-114 and C-278). Across the Rampion 2 DCO documents where reference is made to trenchless crossing techniques (including HDD) its use is set out as being ‘… to avoid or minimise identified constraints, such as main watercourses, railways and roads that form part of the Strategic Highways Network’ (para 1.2.3). This is repeated in several documents, including in Commitment C-5 which refers to main rivers, watercourses, railways and roads. The lack of clear commitments to trenchless crossings for the two most sensitive landscape features within the SDNP, which contribute significant to Special Quality 1, create further uncertainty about the use of HDD to mitigate the effects on the natural beauty of the designated landscape Add a commitment to protect the landscape of the SDNP in particular one of its key landscape features, the chalk scarps. |  | No change |  | No change |  | No change
H5 | Summary of Natural England's advice - Paragraph 1.19 & Point 4 of detailed comments | TOPIC: HDD compound - TC-12b Even if HDD is deemed feasible, the substantial construction equipment needed for drilling and servicing the drilling operation would significantly threaten the highly sensitive landscape character and the special qualities of the SDNP. The effects will be all the more serious if trenchless crossing alternative option TC-12b is used given its planned location in a clearing within the woodland of Michelgrove Park. Provide detailed information as to how the AW adjacent to the area proposed for TC-12b can be protected given the substantial equipment which will be needed for the trenchless crossing works. |  | No change |  | No change |  | No change
H6 | Summary of Natural England's advice - Paragraph 1.9 | TOPIC: SDNP Special Qualities - The significant effects on Special Qualities 1 and 3 are set out as being short term and temporary, limited to the construction phase and largely reversible due to the mitigation measures proposed. Natural England does not agree with the assessment for the following reasons: Special Quality 1: ‘diverse, inspirational landscapes and breath-taking views’ a) In relation to Special Quality, it is noted in paragraphs 3.3.38-3.3.40 that planting will be undertaken in years 1 to 10, and that ‘…localised and significant effects on particular landscape elements (trees, woodland and hedges) will be sustained through Years 1 to 10 reflecting the loss of mature trees, woodland and hedges that cannot be replaced in Year 1.’ It is assumed that these localised effects will be considered in isolation and that; ‘…will not be sufficient in number, density, pattern or distribution to sustain significant effects on landscape character. There will be no obvious ‘linkage’ between them due to the reinstatement of the onshore cable corridor.’b) Natural England does not agree with this statement. The experience of the landscape and breath-taking views of the SDNP are enjoyed by being in the landscape, whether by means of walking, cycling, horse riding or other pursuits. The landscape is therefore experienced in an active, mobile, and sequential way. Prior to construction commencing preparatory works will be undertaken which will; ‘…include vegetation clearance, access road construction, installation of drainage systems, stone fill, installation of a construction compound, temporary site offices, fencing, delivery of materials, plant, machinery and fuel’ (para. 4.5.56, Chapter 4: Proposed Development) c) In addition, up to 66 joint bays, and 264 separate link boxes and fibre optic cable junction boxes are proposed. Commitment C-19 refers to route joint bays/pits at 600m to 1,000m intervals, which will extend along the full length of the route. These will not only have an industrialising effect on the landscape, but it is likely that they will be fenced as they are along the Rampion 1 cable route. All of these new alien features will all act to highlight the route to those who move through the landscape of the National Park. The localised and significant effects will be experienced therefore, not as isolated incidents, but as significant construction works traversing through and detracting from the South Downs landscape and breath-taking views; they will be clearly sequential. This would be particularly evident in the A3: Arun to Adur Open Downs landscape character area, where it would significantly change the character of this open downland landscape and damage its natural beauty for more than 10 years which in LIVA terms is long term. d) Paragraph 3.3.38, which relates to the state of the landscape at the end of the construction phase, notes that as a minimum the fencing and haul roads will be removed and that topsoil and, where required, grass/pasture will be reinstated. The planting will be undertaken between years 1 and 10, and therefore the users of this landscape will experience changes to it for at least 10 years, if not longer as the planting in year 10 will need time to establish (again this is long term as set out in the LVIA). In addition, no trees removed for the cable route can be replaced over the route. As a result there will be permanent changes to the structure of field boundaries and thus patterns in the landscape which will continue to provide a visual indicator of the route of the cable for the long term. The Rampion 1 cable route remains visible in several of the sections, in particular around Truleigh Hill area. e) We would therefore consider that significant effects on the landscape of the SDNP and its special qualities are under assessed. Effects will extend for at least the medium term (6 to 10 years based on the LVIA methodology) into the operation and maintenance phase, with permanent effects lasting longer than 10 years. These comments are notwithstanding our considerable concerns in relation to embedded mitigation measures (C-19, C-115, C235, C-236) as set out below. Special Quality 3: ‘tranquil and unspoilt places’ f) In relation to Special Quality 3, the LVIA notes that the duration of the construction phase effects will be ‘…limited to a few days as the works pass through the landscape’ (para. 3.3.55). Commitment C-19 sets out to reinstate the landscape in ‘…as short a timeframe as possible’ and to complete the cable installation in discrete sections. While Natural England welcomes this approach and the acknowledgement of the acute contrast with the perceptual character, we do not agree that the effect on the tranquillity of the landscape can be limited to a few days. The cable corridor through the National Park is approximately 12km in length. As set out in Table 1-36 (PRoW along the cable route within the SDNP) the construction phase will continue for 4 years. The tranquillity of the National Park can be experienced in motion, in the same way as views and the diversity of the landscape. The sound of construction in the tranquil landscape will reach further than the visible activity which may be screened from view and movement of construction vehicles and the sound they make will have a significant effect on this special quality. g) SDNP is designated as an International Dark Sky Reserve. Paragraph 3.3.20 states that there would be no effect on this designation due to embedded mitigation measures. Those quoted are: C-22 (sets out working hours as 0700 to 1900 Monday to Friday); C-66 (minimising effects on the special qualities of the SDNP, through design and compliance with policy) and C-200 (directional task lighting where needed to limit effects on walkers and residents of the SDNP). The Outline Code of Construction Practice (document 7.02) states that Horizontal Directional Drilling (HDD) work will continue for 24 hours, 7 days a week. The detailed description of Special Quality 3 includes the retention of dark night skies. Natural England welcomes the commitments referred to in relation to lighting, but there is no assessment of the landscape effects of the necessary lighting that will be needed for the HDD work where the cable extends through the scarp at Michelgrove Park or Sullington Hill. |  | No change |  | No change |  | No change
H7 | Summary of Natural England's advice - Paragraph 1.9 g) | TOPIC: SDNP Special quality 3 - lighting impact on International Dark Sky Reserve No mention of lighting for trenchless crossing compounds is mentioned in the maximum parameters and assessment assumptions for the landscape and visual impact assessment (Chapter 18, Table 18-24). The Viewpoint Analyse mentions vehicle and task lighting in relation to the identified viewpoints, but there is no mention of the lighting needed for the trenchless crossing compounds given their 24 hour, 7 day a week working hours. Underassessment of the effects on SDNP special quality 3 ('tranquil and unspoilt places') given the lack of adequate assessment of the effects of the 24/7 lighting required for trenchless crossings at Michelgrove Park and Sullington Hill. Reassess the effect on SDNP special quality 3 based on the effects on the International Dark Sky Reserve. |  | No change |  | No change |  | No change
H8 | Summary of Natural England's advice - Paragraph 1.8 | TOPIC: Under assessment of the harm to the statutory purpose of the SDNP - geographic extent There is an incorrect reliance on the mitigating effect of geographic extent on the assessed harm to the special qualities. For Special qualities 1 and 3, ‘diverse, inspirational landscapes and breath-taking views’ and ‘tranquil and unspoilt places’ the effect is considered to be limited to ‘…approximately 250m to 650m of the onshore cable corridor…’, while in the case of ‘great opportunities for recreational activities and learning experiences’ a quantitative measure is applied to the extent of the effect. For the assessment of landscape effects in GLVIA geographical location is a constituent component of an assessment of magnitude of change, for the assessment of the special qualities and thus the assessment of effects on the statutory purpose of a designated landscape, the extent of geographical harm is irrelevant. The assessment finds that the special qualities of the SDNP will be harmed. The natural beauty of the National Park and the opportunities afforded for open-air recreation are the reasons for which it was designated in statute. Any harm to the natural beauty harms the purpose of the designation, and this cannot be moderated by a quantitative judgement about the size or scale of the harm in relation to a particular part of the SDNP or to any of its special qualities. We conclude that the primary statutory purpose of the SDNP, to conserve and enhance natural beauty, is harmed by the proposed development as described in the ES. The LVIA under assesses the harm to the statutory purpose of the SDNP through the under assessment of the landscape of the SDNP and its special qualities, due to the incorrect application of geographical extent. Rewrite the assessment of the effects upon the SDNP, with reference to the designating legislation. |  | No change |  | No change |  | No change
H9 | Summary of Natural England's advice - Paragraph 1.10 | TOPIC: LVIA, Natural Beauty Commitment C-66 and C-67 are aimed at reducing the effects of the proposed development on the SDNP. While we welcome these in principle, we do not believe that they will have any meaningful effect. C-66 aims to minimise the effects on the special qualities of the National Park ‘…through careful design consideration in terms of scale, size and location, and taking account of the relevant policy and guidance.’ The proposed development is assessed in the LVIA as having a significant effect on two special qualities of the SDNP during the construction phase, and we consider that this extends into the long term. Natural England therefore advises that the natural beauty of the designation will be harmed. |  | No change |  | No change |  | No change
H10 | Detailed comments point 13 | TOPIC: LVIA assessment methodology The LVIA assessment methodology is based on 'moderate' levels of effect being judged as either significant or not significant, subject to the assessor's opinion. Natural England notes that the guidance provided in GLVIA3 relates to the general assessment of landscape and visual effects but does not give details of how to assess designated landscapes. Based on the national importance of designated landscapes and their protection in statute, all 'moderate' effects in the context of a designated landscape should be regarded as significant; and the assessment altered accordingly. |  | No change |  | No change |  | No change
H11 | Detailed comments point 14 | TOPIC: LVIA visualisations The LVIA figures are labelled as Type 1 Visualisations, however if they are based on the LVIA methodology and the guidance set out in the Landscape Institute Technical Guidance Note 06/19, they should be labelled as Type 2 visualisations. Clarification as to whether or not the visualisations follow the wireframe/wireline protocols as set out in the LVIA methodology are required. Natural England asks for clarification that the viewpoint images as presented are Type 2 visualisations.
H12 | Detailed comments point 9 & 10 | TOPIC: Commitment C-115 - hedgerows, embedded measures - worst case scenario Under assessment of the effects of the cable route through the SDNP as a result of this commitment, as it underpins the assessment of the likely harm to the special qualities of the SDNP and the landscape and visual assessment of it. Based on the commitment, we conclude that the effects on the SDNP have been under assessed in the LVIA. Commitment C-115 will not prevent the severance of significant numbers of the field boundaries along the cable route, and thus there will be significant harm to the landscape character and visual amenity of the SDNP and its special qualities. A number of significant concerns in relation to the likely efficacy of commitment C-115: - Likely success of proposed translocation, given the soil and climactic conditions of the SDNP; - Uncertain language related to the commitment diluting it to no more than a commitment for hedgerow replanting; - Decisions regarding translocation assigned to an ECoW Reassess effects on the SDNP to take into account the worst case scenario where no hedgerows are successfully translocated; and the inability of any trees to be replanted over the cable route (which is irrespective of the success or failure of commitment C-115) Provide greater clarification and more information/studies to prove the likely efficacy of the commitment as applied to the SDNP. Instruct the ECoW to consider effects on landscape character and visual amenity in all decisions regarding translocation and replacement of hedgerows. |  | No change |  | No change |  | No change - We understand that the Applicant intends on submitting further updated documents and information pertaining to this issue at deadline 4. Natural England will provided an update on this point when we have had the opputnity to review this additional information.
H13 | Summary of Natural England's advice - Paragraph 1.126 & Detailed comments point 11 | TOPIC: Commitment C-19 - cable reinstatement, hedgerows, commitment register Commitment C-19 is referred to in the LVIA as committing to the reinstatement of hedgerows at 600m to 1000m intervals. Commitment C-19 refers to interval lengths for joint bays/pits only, and to reinstate as 'in a shorter timeframe as possible' There are no other commitments which mention backfilling on a rolling programme of 600m to 1,000m. There are also no clear indications as to the maximum length of time to be taken before backfilling commences or any indication of the length of cable route to be reinstated within the commitments register. The Proposed Development Parameters do not include mention of a backfilling duration. In addition, the use of the wording ‘as practicable’ allows for considerable flexibility and make the commitment uncertain. Clarify Commitment C-19 to include reinstatement in 600m to 1000m intervals; add these to the Proposed Development Parameters, and remove ‘as practicable’ from the commitment wording. |  | No change |  | No change |  | No change
H14 | Summary of Natural England's advice - Paragraph 1.27 | TOPIC: Avoiding removal of key landscape characteristics Commitments C-21, C-115 and C-174 are claimed in the LVIA, Executive Summary and the Outline Code of Construction Practice to avoid landscape elements where these are key characteristics. Commitment C-21 relates to vegetation removal in the context of breeding birds; with Commitments C-115 and C-174 there is not sufficient evidence to have confidence in their measures. There is thus an over statement of the benefits of commitments C-21, C-115, C-174 in relation to reducing or removing significant environmental effects as far as possible/ avoiding the removal of key landscape characteristics. Reassess the landscape and visual effects taking into account the uncertainty of each commitment and the lack of evidence / clear commitments which show that the suggested environmental protections will be achieved. |  | No change |  | No change |  | No change
H15 | Summary of Natural England's advice - Paragraph 1.30 | TOPIC: Cultural Heritage The accepted definition of landscape is an area of land ‘… as perceived by people, whose character is the result of the action and interaction of natural and / or human factors.’ The definition highlights that landscape has a long temporal dimension, and its current state is the result of millennia of changes to the landscape, both human and naturally induced. Any harm to the cultural heritage of the landscape will result in harm to the landscape character, and therefore any damage to the cultural heritage of the SDNP would significantly damage the landscape character of the National Park. We defer to Historic England and the Local Authorities to comment on the historic environment part of the application.
Additional Issues following Relevant and Written Representations submission 06/11/2023
Section 245 (Protected Landscapes) of the Levelling Up and Regeneration Act 2023
H16 | New issue at deadline 1 | Section 245 (Protected Landscapes) of the Levelling Up and Regeneration Act 2023 places a duty on relevant authorities in exercising or performing any functions in relation to, or so as to affect, land in a National Park, the Broads or an Area of Outstanding Natural Beauty (“National Landscape”) in England, to seek to further the statutory purposes of the area. The duty applies to local planning authorities and other decision makers in making planning decisions on development and infrastructure proposals, as well as to other public bodies and statutory undertakers. It is anticipated that the government will provide guidance on how the duty should be applied in due course. In the meantime, and without prejudicing that guidance, Natural England advises that: the duty to ‘seek to further’ is an active duty, not a passive one. Any relevant authority must take all reasonable steps to explore how the statutory purposes of the protected landscape (A National Park, the Broads, or an AONB) can be furthered; The new duty underlines the importance of avoiding harm to the purposes of protected landscapes but also to seek to further the conservation and enhancement of a protected landscape. That goes beyond mitigation and like for like measures and replacement. A relevant authority must be able to demonstrate with reasoned evidence what measures can be taken to further the statutory purpose. The proposed measures to further the statutory purposes of a protected landscape, should explore what is possible in addition to avoiding and mitigating the effects of the development, and should be appropriate, proportionate to the type and scale of the development and its implications for the area and effectively secured. Natural England’s view is that the proposed measures should align with and help to deliver the aims and objectives of the designated landscape’s statutory management plan. The relevant protected landscape team/body should be consulted. |  | No change |  | No change |  | No change

## J - Terrestrial Ecology
Point | Point Number(s) from Appendix J [RR-265] | Taken from Natural England’s Relevant and Written Representations Rampion 2 Appendix J - Terrestrial Ecology [RR-265] | RAG Status Rel and WR Rep D1 | Consultation, actions, progression | RAG Status at D2 | Consultation, actions, progression | RAG Status at D2.5 | Consultation, actions, progression | RAG Status at D3 | Consultation, actions, progression | RAG Status at D4
J1 | 8 | TOPIC: Severance at Landscape Scale We continue to advise that a fundamental requirement of the scheme is to demonstrate that the functionality of this environment can be maintained. We advise that the nature of this scheme requires a bespoke assessment of the impact of severance at a landscape -scale and that the severing impact of the scheme across interlinking habitats (regardless of species richness) must be fully understood. It is not clear from the evidence provided how this significant impact has been assessed. The scale of linear habitat affected makes this of critical importance. We advise that this assessment should be clearly integrated to include landscape and ecology and include all linear habitat features. The assessment must demonstrate how harm will be avoided and mitigated. Where this is demonstrably unavoidable and linear habitats are severed compensation must assess severance at the time of impact, confidence in efficacy of reinstatement and a clear timeframe for reinstatement. |  | No change |  | On further reflection Natural England has closed out this R&I as we feel it is a duplicate of our LVIA log comment.
J2 | 3 & 4 | TOPIC: FLL, Pintail Natural England note that a foraging range of ~18km (utilised by the northern pintail) has been stated, which has been used to assess the available functionally linked land (FLL), and then compared against the portion of the FLL which will be temporarily impacted during the construction phase. The ~18km foraging range appears to have been selected from a USA study from SW Louisiana, out of a comparison of 16 other foraging ranges studies (Johnson et al., 2014). Of this data set, “~18km” appears to be the highest figure chosen, whilst a study in France evidenced a foraging range of 1.3km. Natural England question why "~18km" was chosen to estimate the likely foraging range of pintails, when the France figure may be more representative, due to closer proximity. A much lower foraging range of 1.3km (France) would mean the northern pintail relies on the FLL a lot more than a pintail from Louisiana (~18km). Natural England request further explanation be provided by RED, to understand any likely impacts in relation to land take/land cover change effects, to the conservation objectives of the northern pintail of the Arun Valley Ramsar site. |  | No change |  | No change |  | No change |  | Please see response to ExAQ at deadline 3. Natural England has discussed this with the Applicant. Once further clarifiaction is provided Natural England is confident this issue can be progressed.
J3 | 5 | TOPIC: FLL Natural England note that the area of land left behind following construction may take several years to recover / fully re-establish. This linear habitat fragmentation causes severance of the landscape which could impact upon the Northern Pintail. Works may not be taking place during the vast majority of time Pintail is present, but habitat degradation may last for years after the construction and impact the species for negatively for years. In general, Natural England note that temporary loss of functionally linked land of the Arun Valley SPA and Ramsar site could occur for a number of years post construction. We note that reinstatement of the cable route corridor is proposed to take place within two years of the initial habitat loss. Natural England advises there is not sufficient certainty that full reinstatement to previous condition, and agricultural use, is likely to occur within the proposed time frame and is likely to be greatly longer if the construction phase is to last up to five years. This is made more likely if temporary fencing is to remain in place for the entirety of the five-year construction period. Furthermore, temporary fencing of the cable route within the FLL could be maintained beyond the five-year construction period (as seen with original Rampion cable route development), which could add further time delay until the FLL is fully reinstated to its previous agricultural use. Natural England advise that further assessment should be made into potential impacts of temporary loss of FLL. Precautionary principle should be applied to allow for a longer period of habitat loss and reinstatement back to previous condition. With regard to temporary fencing, Natural England advise that detail should be provided to demonstrate when or if temporary fencing will be removed following the construction period. |  | No change |  | No change |  | No change |  | No change
J4 | 5 & 6 | TOPIC: FLL In some circumstances, it appears the land disturbed by open trenching along the cable corridor will not be reinstated for 2 years post cable installation, meaning there is the potential for the existing habitat to not return to the standard it was before, for many years. This linear habitat fragmentation causes severance of the landscape which could impact upon species, for example displacing important bird species using the area as functionally linked land (FLL). Natural England advise that greater detail should be provided on the efficacy of embedded mitigation measure C-103 to prevent long sections of lost habitat awaiting reinstatement too long and causing severance through fragmentation. Can reinstatement begin as soon as practically possible, i.e. within a year, for the majority of the corridor of habitat lost following construction to prevent there being large gaps of habitat degradation? |  | No change |  | No change |  | No change |  | No change
J5 | 7 | TOPIC: FLL Natural England note that the ‘…works will mainly be undertaken outside the period when wigeon and teal are present…’. Natural England question why works cannot take place entirely outside the periods where the birds are present, instead of ‘mainly’.
J6 | 9 | TOPIC: Water Neutrality Natural England advise that additional details be submitted, which considers how water neutrality could be demonstrated, without overly relying on a strategic mitigation scheme which is yet to become operational. Further consideration of how suitable water neutrality mitigation can be suitable secured, should be considered and provided by RED. To support in the assessment, Natural England would advise that an estimated water use should be calculated to inform the evidence base, for which mitigation measures should be proposed against. Without these details, it may not be possible to conclude with certainty, of no adverse effect on the integrity of the Arun Valley designated sites, from over abstraction of groundwater from within the Sussex North Water Supply Zone. Be advised that it is also not apparent whether the SNOWS strategy will have sufficient capacity to offset this proposal’s water demands in addition to the demands of wider development in Sussex North. This is an additional reason why the estimated water use should be calculated. |  | No change |  | Please see updated advice provided in our written response to Examiners Questions Appendix N2.5. Once the Applicants commitments are secured within a named plan this issue can be considered resolved. |  | No change |  | No change
J7 | 10 | TOPIC: Water Neutrality Natural England note that water use within the SNWSZ during the construction phase of the proposal, has not been screened to determine whether any increase in water use is likely to have a significant effect (LSE) on Arun Valley designated sites (SPA, SAC and Ramsar site). Natural England advise that RED conduct a routine screening exercise, to determine whether increased water use during the construction phase of the proposal is likely to have a significant effect (LSE) on the Arun Valley designated sites. |  | No change |  | No change |  | No change |  | No change
J8 | 29 | TOPIC: Water Neutrality Natural England question whether no LSEs on hydrological regimes across designated sites can be concluded, as mitigation will need to be demonstrate Water Neutrality for the proposed development. Natural England advise that clarification should be provided, to determine whether the requirement to demonstrate water neutrality for the Arun Valley designated sites, relates to changes in hydrological regimes of the Arun Valley designated sites. |  | No change |  | No change |  | No change |  | No change
J9 | 11 | TOPIC: LWS, wording clarification Natural England note the reference to ‘some designated sites’. Does this relate to SSSIs and Local Wildlife Sites (LWS)? Clarification of ‘some designated sites’ requested.
J10 | 12 | TOPIC: HDD Natural England are concerned that RED are overly reliant on specific embedded measures (i.e. HDD), to mitigate against permanent loss of irreplaceable habitats such as Ancient Woodland. Site specific feasibility studies for embedded measures such as HDD have not been undertaken to date. Natural England advise that the commitment register should be updated, so that open trenching is not a back-up option through irreplaceable habitats if trenchless crossing operations were to fail. |  | No change |  | No change |  | No change |  | No change
J11 | 14 | TOPIC: HDD, PAWS Natural England are concerned with the proposed permanent and irreplaceable loss of approximately 0.99 ha of plantation on ancient woodland soils (PAWS), associated with proposed LACR-02. Natural England does not endorse the loss of and damage to ancient woodlands, which are afforded significant protection in planning policy. This route option should only be considered where no other routes are found to be viable. Should this route be selected Natural England request to be consulted to ensure the best environmental outcomes and that the least impactful methodology is used. |  | No change |  | No change |  | No change |  | No change
J12 | 15 & 16 | TOPIC: HDD Trenchless crossings are an embedded mitigation measure, which if enacted successfully, will avoid impacts to ancient woodland. However, Natural England note that most mitigation measures carry their own risks. Without understanding these risks, it can be difficult to assess whether the mitigation will be effective, and the damage avoided. Natural England advise that reassurances are needed to ensure this significant effect are truly avoided. We note that there appears to be a risk of regressing to open trench techniques through irreplaceable habitats, should trenchless techniques not be possible. |  | No change |  | No change |  | No change |  | No change
J13 | 30 | TOPIC: HDD feasibility Natural England question whether the Environmental Statement has an over reliance on trenchless crossing as an embedded measure. Natural England notes that alternative installation options to trenchless techniques could result in irreparable damage to Ancient Woodlands and Chalk Scarps. Therefore, we advise that in order to provide the decision makers with the necessary confidence that mitigation measures are deliverable, an Outline Trenchless Crossing Feasibility Study is submitted into the examination. We advise that the Outline Landscape Ecology Management Plan should secure the provision and sign off, of a final version which will need to be agreed post consent and prior to construction. |  | No change |  | No change |  | No change |  | No change
J14 | 17 | TOPIC: Embedded measures, HDD, Hedgerows Natural England note that efficacy of a number of embedded mitigation measures have not been fully assessed with sufficient detail. Natural England advise that greater detail should be provided on the efficacy of embedded mitigation measures C-5, C-43 (trenchless crossings) and C-115 (hedgerows).Natural England note that detailed feasibility assessment for trenchless crossings is proposed to be conducted post DCO acceptance. |  | No change |  | No change |  | No change |  | No change
J15 | 38 | TOPIC: HDD Natural England note that no detailed feasibility to outline the risks of trenchless crossings has been submitted to date. Natural England note that RED have stated that impacts to irreplaceable habitats (such as ancient woodland) will be reassessed if an alternative option to trenchless crossings is required. Natural England notes that alternative installation options to trenchless techniques could result in irreparable damage to Ancient Woodlands and Chalk Scarps. Therefore, we advise that in order to provide the decision makers with the necessary confidence that mitigation measures are deliverable, an Outline Trenchless Crossing Feasibility Study is submitted into the examination. We advise that the Outline Landscape Ecology Management Plan should secure the provision and sign off, of a final version which will need to be agreed post consent and prior to construction. |  | No change |  | No change |  | No change |  | No change
J16 | 121 | TOPIC: HDD Natural England note that ground investigation works are to be conducted post DCO acceptance. As ground investigation works are key to understanding the risks and feasibility of trenchless crossings, Natural England has consistently advised that ground investigation works be brought forward to inform the Environmental Statement of the DCO submission, specifically for trenchless crossing locations below sensitive habitats (e.g. ancient woodland) and in visually sensitive locations (e.g. chalk scarp at Sullington Hill LWS) Natural England notes that alternative installation options to trenchless techniques could result in irreparable damage to Ancient Woodlands and Chalk Scarps. Therefore, we advise that in order to provide the decision makers with the necessary confidence that mitigation measures are deliverable, an Outline Trenchless Crossing Feasibility Study is submitted into the examination. We advise that the Outline Landscape Ecology Management Plan should secure the provision and sign off, of a final version which will need to be agreed post consent and prior to construction. |  | No change |  | No change |  | No change |  | No change
J17 | 36 | TOPIC: HDD, Climping Beach SSSI Natural England note that trenchless techniques such as HDD is a form of mitigation that carries its own risks. Proposed trenchless crossing at Climping beach could be located beneath the western end of Climping Beach SSSI, though we note that Climping Beach SSSI could be completely avoided. Natural England advise that the mitigation hierarchy should be followed at Climping Beach SSSI. Impacts should be ‘avoided, mitigated or as a last resort compensated’. Natural England would advise that HDD beneath Climping Beach SSSI should be avoided, in the first instance, before wholly relying on the embedded mitigation measure of trenchless techniques. |  | No change |  | No change |  | No change |  | No change
J18 | 37 | TOPIC: HDD, Climping Beach SSSI Natural England note that monitoring during HDD night time operations have not been detailed. It is also not clear if Climping Beach SSSI will receive increased levels of light during the night time operations. Natural England request that details are submitted, to outline what type of monitoring will occur during HDD operations at night time. Further impacts should be assessed if likely impacts to Climping Beach SSSI are expected from this type of monitoring.
J19 | 49 | TOPIC: HDD It is not clear whether the cable route splits into two sections at TC-12 and TC-15. Natural England seek clarification as to the purpose of having multiple options at TC-12 and TC-15. Would the worst-case scenario see all trenchless crossings compound alternatives used to install the proposed cables?
J20 | 26 | TOPIC: HDD, noise, SDNP Natural England note that trenchless crossing locations will result in noise levels of between 55dB and 75dB within the SDNP, which will likely impact the high tranquillity of the area. Natural England note that the elevated noise levels will result in harm to special quality 3 of the SDNP, ‘tranquil and unspoilt places’. Natural England request further clarification on how embedded mitigation measures (i.e. C-26) can reduce the noise levels within the SDNP. Have noise levels of 75dB been calculated, without consideration of embedded mitigation measures? |  | No change |  | On further reflection Natural England has closed out this R&I as we feel it is a duplicate of our LVIA log comments.
J21 | 120 | TOPIC: HDD, Commitment register, AW Natural England welcome commitment for all ancient woodland to be retained. Natural England requests clarification as to whether this commitment only relates to trenchless crossing operations. Natural England seeks clarification as to the specifics of this commitment. |  | No change |  | No change |  | No change |  | Natural England welcomes that more specific details have been added to C-216, however our concerns remain regarding the achievability of HDD, without geotechnical information being available.
J22 | 118 | TOPIC: Embedded measure, SDNP, replacement planting Natural England acknowledge that replacement planting will be characteristic of the area and resilient to climate change. Natural England advise that careful consideration of the landscape characteristics of the SDNP should be considered when selecting replacement planting within the SDNP.
J23 | 1 & 114 | TOPIC: Embedded measure, Light impact, SDNP Natural England note that impacts of lighting to the South Downs National Park’s dark skies has not been referenced. Lighting design commitment has not considered avoiding and minimising lighting impacts to the SDNP International Dark Sky Reserve. Increase in lighting in the SDNP during the construction phase should be mitigated against if the impact cannot be avoided in the first instance. Natural England advise that the commitment should also reference and consider minimising impacts to SDNP International Dark Sky Reserve. |  | No change |  | On further reflection Natural England has closed out this R&I as we feel it is a duplicate of our LVIA log comments.
J24 | 25 | TOPIC: Construction compound, noise, SDNP Natural England note that there are no temporary construction compounds within the SDNP, however there is one proposed temporary construction compound at Washington, which is adjacent to the SDNP boundary. We further note that tranquillity of the SDNP adjacent to the proposed construction compound has been classed as being relatively low, due the existing noise levels from A283. Natural England question whether the tranquillity of the area already being low is a valid reason to add more noise impact to the SDNP. Natural England request further clarification and quantification of the terms ‘substantially lower’ and ‘most of the works’.
J25 | 27 | TOPIC: Noise, SDNP Natural England note that the worst-case noise levels for works close to sensitive receptors, will be for a maximum of two days. Using residential receptor, this magnitude of change has been classed as low. Construction throughout the SDNP will last considerably longer than two days. When assessing the noise level over a much longer time period. Natural England question whether by concluding minor adverse significance to individual receptors within the SDNP, is RED under assessing the cumulative impact to the whole of the SDNP from the construction works.
J26 | 28 | TOPIC: Noise, SDNP “The noise levels predicted at human receptors are above the SOAEL identified in Table 21-26. However, these levels are for a very temporary period. The toxicological effects of noise as stated in WHO guidance, upon which the SOAEL is based, are relevant to a longer duration and therefore are not considered relevant.” Natural England request further information on this statement. What longer duration is being referred to? Weeks and months as opposed to days?
J27 | 31 | TOPIC: Hedgerows, embedded measures Natural England note that 30 hedgerows were not accessible for survey. Will these 30 hedgerows be assumed to be “important” as a precaution. Clarification requested on importance of un-assessed hedgerows.
J28 | 2 | TOPIC: Air Quality Natural England seek clarification as to why information has not been provided relating to traffic modelling/air quality. We are of the understanding that air quality impacts to designated sites have not been considered within the Air Quality (AQ) chapter or RIAA, as air quality impacts were scoped out of having a likely significant effect.
J29 | 45 | TOPIC: Traffic, Air Quality Natural England query why traffic generation has only been calculated for a 5-day working week when it says the working hours will be Mon-Fri 07:00-19:00 and Sat 08:00-13:00. Further consideration advised.
J30 | 46 | TOPIC: Traffic, Air Quality Natural England note that 100 vehicle movements per day during operation associated with the development is far below what we would normally screen in for traffic related air quality impacts. No further comments.
J31 | 47 | TOPIC: Traffic, Air Quality Natural England note that 39 HGV’s per day during construction is below the 200 AADT screening threshold for traffic related air quality impacts. No further comments.
J32 | 32 | TOPIC: Air Quality, Amberley Mount to Sullington Hill SSSI Natural England note that the access track adjacent to Amberley Mount to Sullington Hill SSSI, is only to be utilised during the operational phase (by use of 4 x 4 vehicles). This clarification since the original PEIR is welcome, as we had previous concerns that HGV and LGVs would utilise this access route during the construction phase, which could’ve led to air quality impacts (dust suppression) to the adjacent SSSI.
J33 | 35 | TOPIC: Energy expenditure, The Mens SAC ‘Given that barbastelle will cross disturbed areas (such as the A27) and make nightly long-distance movements it is likely that individual bats could make minor deviations in flight routes to avoid the disturbance source without resulting in detectable increases in energy expenditure.’ – Natural England question why level of disturbance and energy expenditure is being compared against existing infrastructure. Is this an attempt to reduce the significance of impacts to Barbestelle bats from The Mens SAC? Additional clarification should be provided to show how impacts from road crossings (A27) are directly comparable with HDD compounds (which are to be lit all night long, with increased levels of noise).
J34 | 18 | TOPIC: Embedded measures Natural England note that the wording of securing mechanism is ambiguous such as “where possible” and “as far as practicable” are still used and relied on in a number of embedded mitigation measures. We advise that clarity is required when using embedded mitigation and that location and impact should be explicit along with suggested mitigation so that stakeholders can assess baseline, impact and mitigation readily. Care must be taken to ensure that mitigation one impact will not cause additional impacts (for example unsuitable planting impacting landscape character) . Greater detail of embedded mitigation measures which utilise these ambiguous terms, should be provided, to greater fully understand the risks and likely success rates of these mitigation measures. For all measures we advise that clarity is required for commitment measures and that terms “where practicable” for example are removed as this does not provide sufficient certainty of efficacy of mitigation and in addition and furthermore does not allow a robust and defined conclusion of impacts . |  | No change |  | No change |  | No change |  | No change
J35 | 117 | TOPIC: Embedded measure, HDD, river crossing night time monitoring During HDD operations under waterways, how will rivers appropriately be monitored during the night time. Natural England advise that further clarification should be provided to outline how night time monitoring will be conducted during 24hr HDD operations.
J36 | 112 | TOPIC: Embedded measures Natural England note that numerous commitments include flexible wording such as 'where practical, as far as reasonably practical, as far as reasonably possible, practicable minimum, as practical, or are not practical, wherever possible, minimal time possible, shortest practical timeframe'. Such wording reduces the confidence if the delivery of the proposed commitments, which also make up embedded mitigation measures. We observed such wording used in the following commitments C-1, C-6, C-7, C-12, C-17, C-19, C-27, C-67, C-75, C-78, C-115, C-117 and C-128. Natural England note there is regular use of ambiguous terms utilised within a number of the embedded measures and commitments. As these embedded mitigation measures are to be relied upon for the project. Natural England advise that such terms should be further defined by RED, to understand the likely parameters and improve confidence in the delivery of these measures. |  | No change |  | Please see updated advice provided in additional submission Appendix J2.5a. |  | No change |  | Natural England will review the updated Commitments Register we understand will be submitted at deadline 4, and provide further advice at deadline 5 on whether our concerns regarding the commitments have been addressed.
J37 | 113 | TOPIC: Remediation, embedded measure Natural England acknowledge the commitment that areas of temporary habitat loss will behind reinstatement within 2 years of loss. However, to ensure the successful reinstatement of sensitive habitat, or habitats in visually sensitive locations, this maximum timeframe of within 2 years, could be shortened for sensitive habitats and habitats in visually sensitive locations. Natural England advise that an additional commitment could be made of sensitive habitats (i.e. calcareous grassland being reinstated within 6 months of the temporary habitat loss. |  | No change |  | Please see updated advice provided in additional submission Appendix J2.5a. |  | No change |  | No change
J38 | 40 | TOPIC: Hedgerows, embedded measures As a precaution, potentially important hedgerows should be crossed via trenchless techniques. H245, H372, H464, H474, appears to be being crossed via trenched notched technique (14m temporary loss), as opposed to trenchless techniques (6m temporary loss), which has been stated for potentially important hedgerows H527 and H528. Natural England request clarification be provided on how specified potentially important hedgerows are being crossed.
J39 | 41 | TOPIC: Hedgerows, embedded measures Natural England also question why important hedgerows have the same length of temporary loss as not important hedgerow (noted for H481). Have embedded measures such as trenchless crossings not been assumed when calculating the estimated length of loss (i.e. depicting the realistic worst case scenario). Clarification from RED requested.
J40 | 42 | TOPIC: Tree line Natural England note that the length of tree line to be temporarily lost is stated as 378m – Natural England question if this temporary loss is due to an access route, or due to the proposed cable route. If temporary loss is due to the cable route, Natural England were of the understanding that trees could not be planted over the cable. Clarification from RED requested, as to the nature of the tree line reinstatement.
J41 | 43 | TOPIC: Embedded measures, Hedgerow Natural England note that reference is made to 80% success rate for embedded measure (hedgerow translocation) used in the Lake District National Park. We question whether an 80% success rate is expected for this development. Natural England advise that further justification and evidence be provided to support this 80% success rate for hedgerow translocations for this development. Local context/factors should be considered to assess the likely success rate for this development, this should be used to inform the Landscape and Ecology Management Plan (LEMP). Natural England are also concerned that temporary visual impacts to the SDNP could occur if the translocation success rate has been overstated. Collectively, temporary hedgerow loss within the SDNP could lead to significant visual impacts, until the hedgerows are fully reinstated. Natural England would therefore advise that these impacts could be appropriately avoided (or greatly reduced) to the SDNP, if trenchless techniques (such as pipe jacking) were utilised for all hedgerow crossings within the SDNP. |  | No change |  | On further reflection Natural England has closed out this R&I as we feel it is a duplicate of our LVIA log comments.
J42 | 44 | TOPIC: Hedgerow, BNG Natural England note that there is no direct compensation proposed for the permanent loss of approximately 622m of hedgerow/tree line. Majority of loss is located at the proposed substation location. Natural England would therefore expect to see substantial BNG proposed in the local area, as outlined within commitment C-104.
J43 | 48 | TOPIC: Dew pond Dew pond at Hill Barn, Warningcamp has been screened in as per Natural England’s request. Acknowledged.
J44 | 50 | TOPIC: Access route Natural England note that AA-33 to AA-35 were also considered within the 3rd statutory consultation exercise (RED, 2023a). Notification only, as Natural England acknowledge that AA-34 route (for the construction phase) has been modified to avoid impacting ancient woodland Habitat at Highden Beeches.
J45 | 51 | TOPIC: Hedgerow, embedded measures ‘At the time of reporting an estimate as to the likelihood of Importance has been made based upon a review of satellite imagery and records of adjacent and connected hedgerows that could be accessed for survey. Five of the hedgerows are unknown but potentially “important”, with the remaining 25 hedgerows unlikely to be “important”. …those considered “possibly important” are treated as if they qualify as important as a precaution’’ – Natural England note that as a precautionary approach, unassessed hedgerows have been classified as being “important”, however in Table 22-25 of the Terrestrial ecology and nature conservation report, a number of potentially important hedgerows are proposed to being notched to a total of 14m. This contradicts commitment C-115, which states that important hedgerows will be reduced to a 6m loss. Natural England request clarification on how specified potentially important hedgerows are being crossed. Why have these potentially important hedgerows been proposed to be notched with 14m of loss, when it should be reduced to 6m of loss?
J46 | 52 | TOPIC: Protected Species, Fisheries Habitat Natural England query whether periods of increased water flow (i.e. during heavy rainfalls) have been considered for the watercourses that are crossed by open trenching. Further information requested.
J47 | 53 | TOPIC: Protected Species, Fisheries Habitat ‘Final bank reinstatement may require further measures to stabilise the banks and prevent erosion’ – Natural England would like to query the length of time for post construction monitoring and remedial works. Will this also be up to 10 years after completion of construction. Clarification requested.
J48 | 54 | TOPIC: Protected Species, Fisheries Habitat ‘Keep the duration of the isolation works as short as possible.’ – is there a rough timeframe, or a maximum amount of time that can be stated? “Short as possible” is a lax term which should be further defined. Natural England request clarification on the term “short as possible”.
J49 | 55 | TOPIC: Protected Species, Fisheries Habitat Natural England defer to our standing advice for fish, which can be found on Fish: advice for making planning decisions - GOV.UK (www.gov.uk) https://www.gov.uk/guidance/fish-advice-for-making-planning-decisions Natural England defer to standing advice
J50 | 56 | TOPIC: Protected Species, GCN 250 metre (m) survey buffer around the scheme boundary. More justification will be required to explain why a 250m buffer has chosen to be pursued over a 500m buffer from the Order Limit.
J51 | 57 | TOPIC: Protected Species, GCN eDNA undertaken outside the optimal window. It is recommended the best practice guidelines and supporting eDNA guidelines are adhered to. Where there is deviation, this could present constrained or incomplete data. It is recommended that Great Crested Newt (GCN) surveys are regularly updated to ensure that impacts are fully assessed, and compensation can be well situated. |  | No change |  | Updated advice will be provided at deadline 3. |  | Please see updated advice provided in Appendix J3. |  | Natural England has advised the Applicant to work directly with Natural England's Wildlife Licensing service to agree letters of no impediment for licensable species. We will update this issue again once these have been secured.
J52 | 58 | TOPIC: Protected Species, GCN Land access, permissions denied. This has now meant that some of the data may not be comparable across breeding years. Where waterbodies fall within the impact area or within the buffer zone (either 250m or 500m) efforts should be made to repeat access requests for the survey effort. Where access has been repeatedly denied, evidence should be retained of the requests that have been made to the landowners, should a European Protected Species (EPS) mitigation licence be required. It is recommended that GCN surveys are regularly updated to ensure that impacts are fully assessed and compensation can be well situated, should an EPS mitigation licence be required.
J53 | 59 | TOPIC: Protected Species, GCN Waterbodies found to be dry. These waterbodies should still be considered as part of any future survey effort. Waterbodies that occasionally dry out may still benefit GCN by removing predators from the waterbodies, meaning less competition in subsequent GCN breeding seasons.
J54 | 60 | TOPIC: Protected Species, GCN Three waterbodies were subject to eDNA testing only as Habitat Suitability Index (HSI) data was not collected by the surveyor. It is recommended the best practice guidelines and supporting eDNA guidelines are adhered to. Where there is deviation, this could present constrained or incomplete data. Should an EPS mitigation licence be required, it is recommended that GCN surveys are regularly updated to ensure that impacts are fully assessed, and compensation can be well situated. Efforts should be taken to include HSI in future survey efforts to gain a full picture of the waterbodies involved. |  | No change |  | Updated advice will be provided at deadline 3. |  | Please see updated advice provided in Appendix J3. |  | Natural England has advised the Applicant to work directly with Natural England's Wildlife Licensing service to agree letters of no impediment for licensable species. We will update this issue again once these have been secured.
J55 | 61 | TOPIC: Protected Species, GCN Consideration of all waterbodies. From reviewing the figures, there appears to be a number of waterbodies that did not received survey effort, such as ditches and lakes. In addition, please be mindful that GCN can also choose to utilise artificial structures for breeding, such as concrete lagoons, fire ponds or disused swimming pools. Where waterbodies have been discounted for suitability, this will need to be justified should an EPS mitigation licence be required. |  | No change |  | Updated advice will be provided at deadline 3. |  | Please see updated advice provided in Appendix J3. |  | Natural England has advised the Applicant to work directly with Natural England's Wildlife Licensing service to agree letters of no impediment for licensable species. We will update this issue again once these have been secured.
J56 | 62 | TOPIC: Protected Species, GCN GCN waterbodies fall within the development boundary. Should an EPS mitigation licence be required, where GCN breeding waterbodies are being lost as a result of the development, consideration must be given to suitable and proportionate compensation. For every GCN waterbody lost, there would be the expectation of two suitable GCN waterbodies to be created.
J57 | 63 | TOPIC: Protected Species, GCN Multiple clusters of GCN waterbodies and metapopulations across the length of the route. Should an EPS mitigation licence be required, consideration needs to be given to the potential for fragmentation or severed connectivity and how this will be addressed through suitable mitigation and compensation solutions. Establishment periods for compensation habitat must be considered and built into Works Schedule approaches. This is particularly important in situations where the created compensation feature(s) is to be relied upon in a receptor area. It is also likely to be necessary to consider multiple receptor locations. Each captured GCN would ideally be moved no further than 500m from the location that it was captured and be moved to an area where it would have access to suitable supporting habitat for foraging resting and breeding.
J58 | 64 | TOPIC: Protected Species, Bats The transects and static detector surveys with the above GLVA have provided a good understanding of the likely bat species assemblage to be impacted as well as the likely bat activity levels in the proposed DCO order limits. They have also been able to provide an indication of how bats are utilising the impacted habitat. No hibernation surveys have been completed and therefore no information on the hibernation potential of the areas to be impacted has been provided. Should an EPS mitigation licence be required Natural England would expect that pre-construction surveys are conducted to further inform on bat activity as well as roost status and location. Surveys should be designed appropriately and proportionately for the impacts.
J59 | 65 | TOPIC: Protected Species, Bats Survey limitations -Some of the manual transect routes required modification due to a number of varying reasons this has now meant that some of the data may not be comparable across years. Also due to technical issues several of the passive detectors have not been successful in capturing useable data. Should an EPS mitigation licence be required these surveys may need to be repeated if an ecological interpretation of the habitat and bat activity in these areas affected cannot be made due to lack of data.
J60 | 66 | TOPIC: Protected Species, Bats Land access limitations. Once the DCO is granted it would be expected that areas previously not surveyed due to access issues should be included in the pre-construction surveys.
J61 | 67 | TOPIC: Protected Species, Hazel dormouse It is referenced that 'a full survey programme to confirm presence/likely absence of hazel dormouse in all suitable habitats within the proposed DCO Order Limits was not deemed proportionate, especially given the 'Rochdale Envelope' approach (Planning Inspectorate, 2018)' Natural England would strongly recommend that the Best Practice Guidelines outlined in 'The Dormouse Conservation Handbook, Second Edition' are adhered to. Should you choose to deviate from this, detailed justification will be required to ensure that appropriate and robust conclusions have been drawn, should an EPS mitigation licence be required. |  | No change |  | Updated advice will be provided at deadline 3. |  | Please see updated advice provided in Appendix J3. |  | Natural England has advised the Applicant to work directly with Natural England's Wildlife Licensing service to agree letters of no impediment for licensable species. We will update this issue again once these have been secured.
J62 | 68 | TOPIC: Protected Species, Hazel dormouse It is referenced that 'in line with CIEEM guidance (CIEEM, 2018), discrete 'survey sites' were selected for sampling. Natural England would strongly recommend that the Best Practice Guidelines outlined in 'The Dormouse Conservation Handbook, Second Edition' are adhered to. Should you choose to deviate from this, detailed justification will be required to ensure that appropriate and robust conclusions have been drawn, should an EPS mitigation licence be required. |  | No change |  | Updated advice will be provided at deadline 3. |  | Please see updated advice provided in Appendix J3. |  | Natural England has advised the Applicant to work directly with Natural England's Wildlife Licensing service to agree letters of no impediment for licensable species. We will update this issue again once these have been secured.
J63 | 69 | TOPIC: Protected Species, Hazel dormouse As the design of the Proposed Development evolved, a number of the survey sites are no longer within or adjacent to the proposed DCO Order Limits. Suitability and connectivity of habitat can change and may mean that dormouse adapt how they utilise the landscape. It is recommended to regularly update the surveys based on the proposed impacts within and adjacent to the proposed DCO Order Limits. With the change in the Order Limits, it may be that the survey locations are updated/adjusted in line with the Best Practice Guidelines, 'The Dormouse Conservation Handbook, Second Edition'. |  | No change |  | Updated advice will be provided at deadline 3. |  | Please see updated advice provided in Appendix J3. |  | Natural England has advised the Applicant to work directly with Natural England's Wildlife Licensing service to agree letters of no impediment for licensable species. We will update this issue again once these have been secured.
J64 | 70 | TOPIC: Protected Species, Hazel dormouse Nest tube deployment timing has ranged across the chosen sites. It is recommended that nest tubes should also be left in place for several months. Nest tubes are most frequently occupied in May and August/September. Timing their deployment is therefore important. Setting them out in April may get early results, while setting them out in June may be less immediately successful. It is best to leave them out for the entire season, from March onwards, for checking in November.
J65 | 71 | TOPIC: Protected Species, Hazel dormouse Linear impact route. Should an EPS mitigation licence be required, consideration needs to be given to the potential for fragmentation or severed connectivity and how this will be addressed through suitable mitigation and compensation solutions. Establishment periods for compensation habitat must be considered and built into Works Schedule approaches. This is particularly important in situations where the created compensation feature(s) is to be relied upon in a receptor area. There should be the aim to commit to a proposal that results in no net loss, should an EPS mitigation licence be required.
J66 | 72 | TOPIC: Protected Species, Invertebrate Natural England defer to our standing advice for invertebrates, which can be found on Invertebrates: advice for making planning decisions - GOV.UK (www.gov.uk) https://www.gov.uk/guidance/invertebrates-advice-for-making-planning-decisions Natural England defer to standing advice
J67 | 73 | TOPIC: Protected Species, Badger Badger Surveys: Survey coverage was 90.75% and looked for badger field signs only during the extended phase 1 habitat survey. The surveys conducted have found no badger setts that would be directly impacted by the proposed works in terms of sett closures. However, areas of loss of foraging ground have been identified. Natural England agree that the survey effort and survey area is appropriate and proportionate for the proposed low impact works that could affect badgers described regarding the proposed Rampion 2 Wind Farm works. Natural England agree that the preconstruction surveys should be conducted on habitat that is suitable to support badgers which is warranted to due to the high levels of badger activity in the area, the presence of badger setts that have already been recorded as well as taking into consideration the mobile nature of the species. Natural England would agree based on the survey evidence collected to date and the Environmental measures proposed in the above documents that overall impacts to badgers would be low. Should a licence be required in the future Natural England can be consulted further. Surveys to inform on licence applications should be robust and proportionate for the scales of the proposed impacts of the development. NB If a main sett is required to be damaged or destroyed then bait marking surveys are likely to be required as part of the licence application to ensure the best placement for any artificial setts proposed.
J68 | [APP-189] General advice | TOPIC: Protected Species, Badger General Badger Advice (ABS): Construction of an artificial setts must be complete prior to the exclusion works and there should be evidence that the badgers have found the sett. Evidence could be gained from a variety of monitoring techniques. Attractive bait such as peanuts as well as bedding can be used to assist the badgers locate the artificial sett. Artificial setts must be constructed: - in a suitable location, - within the territory of the affected badger social group (this can be determined using a bait-marking survey) - away from main roads, public rights of way or sources of danger to badgers, - using materials and in a manner which is sufficiently robust for long-term use by badgers, - made of materials not harmful to badgers, - of a size to reflect the importance and extent of the sett to be lost - provide a dry and well-ventilated (but not draughty) refuge, - ideally with vegetative cover immediately around the structure. - with the minimum internal diameter of artificial tunnels, chambers and sett entrances, being 300mm. No further comments.
J69 | 74 | TOPIC: Protected Species, Water Vole It has been stated that 90.75% of water vole suitable habitat has been surveyed that included the area within the red line boundary as well as a 50m buffer. For a development of this type of work and size the Water Vole Mitigation Handbook (Box 1 survey design) (Dean, Strachan, Gow, & Andrews, 2016 https://gat04-live-1517c8a4486c41609369c68f30c8-aa81074.divio-media.org/filer_public/1e/30/1e3072bf-0ffe-4df2-8ee2-e1af6f66755e/d93_-_water_vole_mitigation_handbook81824175_1.pdf) would suggest surveying for water voles within the footprint of the development boundary as well as 200m upstream and downstream. The deviation from this has not been fully explained within the documentation. Due to the small footprint of the works, the short time frame that the works are scheduled to be taking place and that all habitats lost will be reinstated, Natural England agree that the overall impacts to water voles would be low. Where it is not possible to avoid direct impacts to water vole additional surveys would be required. These surveys should be used to determine the presence or absence of water vole burrows as well as looking for field signs. Where possible the locations of the burrows and field signs should be mapped and used to inform on appropriate mitigation plans. Surveys should follow best practice as described in the Water Vole Mitigation Handbook (Dean, et al 2016). The environmental measures to reduce impacts on water vole habitats, as described within the above documents, such as the use of trenchless crossings, would appear to be appropriate and proportionate approaches. All works that may cause disturbance such as site traffic, use and storage of materials, noise and vibration should be considered, and water voles potentially displaced temporarily from the sites affected. Natural England would require additional information should a licence for displacement be required. This would include the full survey data (carried out under best practice) as well as any other limitations such as unsuitable habitat to displace into along with any necessary compensation proposals. As displacement over short areas is currently being proposed then Natural England’s CL31 (https://www.gov.uk/government/publications/water-voles-licence-to-displace-them-for-development-projects) licence may be applicable.
J70 | 76 | TOPIC: Protected Species, Water Vole General advice on water vole licensing With regard to timings, Natural England can offer general comments at this stage to factor into scheme design. If necessary, displacement during spring is the recommended approach and most likely to achieve successful results. Please see Water voles: licence to intentionally damage or destroy water vole burrows by displacement (CL31) - GOV.UK (www.gov.uk) for more information on Natural England water vole class licence that may be applicable. Given the timescales, if following the necessary detailed surveys or duration of works, trapping water voles becomes necessary during spring or autumn, there is adequate time to prepare any receptor sites ahead of trapping and as such taking water voles into captivity over winter will not be considered a viable option. It should be noted that as a result in changes in legislation brought about by Environment Act 2021, if an individual water vole licence is required for the works the application now needs to be submitted under the new purpose of ‘reasons of overriding public interest’ using new forms which have been published on Gov.uk. https://www.gov.uk/government/publications/water-voles-apply-for-a-mitigation-licence-a11 In addition A Reasoned Statement – is now mandatory for water vole applications that are submitted for the purpose of Reasons of Overriding Public Interest. With regards to compensation or suitable receptor sites, thought should be given to preparing local (same river catchment) receptor sites and / or areas of habitat that could be improved for water voles as soon as possible to give the habitat chance to establish and become suitable. If the receptor sites are not ultimately required for translocation these sites could equally be offered in terms of compensation for any water vole habitat likely to lost/disturbed during the works. No further comments.
J71 | 75 | TOPIC: Protected Species, Otter As above Natural England would expect that all suitable habitat within 200m of the proposed development footprint should be surveyed for the presence of otter. The deviation from this has not been fully explained within the documentation. Natural England are in agreement that otters can be scoped out for now and acknowledge that otters will be considered further during the implementation of the Ecological Clerk of Works role as well as in any preconstruction surveys. No further comments.
J72 | 78 | TOPIC: Protected Species, Reptiles Natural England defer to our standing advice for reptiles, which can be found on Reptiles: advice for making planning decisions - GOV.UK (www.gov.uk) https://www.gov.uk/guidance/reptiles-advice-for-making-planning-decisions Natural England defer to standing advice
J73 | 79 | TOPIC: Protected Species, Breeding birds Natural England defer to our standing advice for breeding birds, which can be found on Wild birds: advice for making planning decisions - GOV.UK (www.gov.uk) https://www.gov.uk/guidance/wild-birds-advice-for-making-planning-decisions Natural England defer to standing advice
J74 | 80 | TOPIC: Onshore Wintering Bird Report Natural England acknowledge and welcome that two seasons of wintering bird surveys have been successfully undertaken, as previously requested within our original PEIR response (16 September 2021). No further comment.
J75 | 39 | TOPIC: BNG Natural England note that 2.7ha of woodland is to be provided around the location of the onshore substation. It is however not clear if this compensation is being delivered separate, or as part of BNG delivery. Natural England advise that RED need to clearly differentiate between habitat being delivered for compensation, and habitat being delivered for BNG. Natural England advise that one clear log should be created, to clearly list and audit the habitat compensation, BNG enhancement and BNG habitat creation, being proposed for the entirety of the onshore phase of the development |  | No change |  | No change |  | No change |  | Natural England has closed out this R&I as this issue will not be resolved until post examination. Please see further comments within Appendix J4b of our deadline 4 submission.
J76 | 44 | TOPIC: Hedgerow, BNG Natural England note that there is no direct compensation proposed for the permanent loss of approximately 622m of hedgerow/tree line. Majority of loss is located at the proposed substation location. Natural England would therefore expect to see substantial BNG proposed in the local area, as outlined within commitment C-104.
J77 | 81 | TOPIC: BNG Natural England welcome the commitment of delivering a Biodiversity Net Gain (BNG) of at least 10% for all onshore and intertidal habitats subject to permanent or temporary loss as a result of the construction and operation of the proposed development. Natural England would advise that it would be beneficial if RED submitted a rough metric to demonstrate the 10%, which is then to be built upon at detailed design stage.
J78 | 82 | TOPIC: BNG To avoid confusion and double counting, there should be a clear differentiation between the delivery of compensation and enhancement (BNG). Would highly recommend that a clear log is created, to identify and track delivery of compensation and enhancements (BNG). Natural England advise that proposed delivery of compensatory habitat, and enhancement and habitat delivery from BNG, need to be set out in an easily understandable log. This is to prevent confusion and the risk for double counting.
J79 | 83 | TOPIC: BNG Natural England note that Local Nature Recovery Strategies (LNRS) will be published by March 2025. However, we are aware that some local authorities are producing interim documents, so it is sensible to keep checking if an interim report is submitted for West Sussex. No further comment. Notification only.
J80 | 84 | TOPIC: BNG Natural England note that there is no guarantee that hedgerows that have been ‘temporary lost’ will be reinstated. Natural England note that 10 years of monitoring and hedgerow reinstatement is proposed. However, is it appropriately precautionary to propose that 100% of the ‘temporary lost’ hedgerow will be successfully reinstated within the 10 year post construction monitoring period? Greater evidence should be provided to support the claim that all temporary lost hedgerows will be reinstated.
J81 | 85 | TOPIC: BNG Natural England note that numerous documents refer to loss of woodland that cannot be replaced due to the presence of cables, however the tables appear to show no permanent loss of woodland. Natural England requests clarification on this discrepancy.
J82 | 86 | TOPIC: BNG To reduce impact of severance, delivery of hedgerow units should be located in close proximity to the hedgerows which are to be temporarily and permanently lost. No further comment. Notification only.
J83 | 87 | TOPIC: Arboricultural Impact Assessment Natural England support the planting of native and naturalised species. No further comment
J84 | 88 | TOPIC: Arboricultural Impact Assessment Natural England note that species mix reference C includes Quercus cerris – Turkey Oak, which is a non-native species, which can host parasitic wasps which can indirectly affect native oak trees. Natural England advise that Turkey Oak be removed off the species mix reference C list, or justification should be provided for the selection of this species.
J85 | 89 | TOPIC: Bat Survey Natural England has no comments on the methods used in the ground level visual inspections surveys described in the above documentation.
J86 | 19 | TOPIC: Soils It is unknown whether the survey was carried out by a suitably qualified (such as member of British Society of Soil Scientists (M I Soil Sci). We have noted this in previous PEIR comments. Clarification requested
J87 | 20 | TOPIC: Soils Site information on micro relief, gradient and flood risk is absent. Further information requested.
J88 | 21 | TOPIC: Soils Munsell soil colour notation is only provided for the soil pits. Munsell colours are necessary to determine whether the soil horizon is gleyed or not. It is not clear which colours have been used in the list of auger samples, therefore it is not clear whether the wetness class ascribed to each auger observation has been correctly assessed in accordance with the published ALC criteria for grading (MAFF, 1988). However, we note that gley indicators have been identified and noted in paragraphs 2.3 – 2.7 and within Annex A. Clarification requested
J89 | 22 | TOPIC: Soils Natural England is aware of available site-specific data that has not been included as part of the published information. The applicant should use all known published data when assessing the proposals impacts within the DCO boundary. A report and accompanying map (ref 4202\056\98) can be found here (https://publications.naturalengland.org.uk/publication/5991422981832704) Natural England advise that all known published data should be used when assess the proposals impacts within the DCO boundary.
J90 | 23 | TOPIC: Soils Natural England notes there has been no lab analysis for particle size distribution analysis by the pipette method to confirm soil textures. Natural England question why this lab analysis has not been conducted.
J91 | 24 | TOPIC: Soils As mentioned above notation on micro relief, gradient and flood risk is absent however in this paragraph it is recognised that these are limiting factors in ALC grade. Natural England request clarification.
J92 | 90 | TOPIC: Soils, remediation Natural England welcome the commitment to reinstate to pre-existing conditions in line with Defra 2009 Code of Construction Practice for the Sustainable Use of Soils on Construction Sites, but this needs to go wider so that best and most versatile agricultural land is returned to the same Agricultural Land Classification (ALC) grade as pre-construction. Natural England advise that this commitment should extend, more specifically, to returning the best and most versatile land back to the same ALC grade as pre-construction. This design principle should also extend to land temporarily required for construction but being returned to a 'soft' non-agricultural after-use. |  | No change |  | No change |  | No change |  | Natural England welcomes commitments made in the Outline Soils Managemnt Plan. Natural England will review the updated Commitment Register at submitted at Deadline 4 to ensure the two align.
J93 | 91 | TOPIC: Soils, remediation ALC grades need to be maintained - 'as far as reasonably practical' seems to imply that restoration back to previous state is not necessarily a requirement. Natural England advise that wording for commitment C-7 is modified, to state that ALC will be reinstated to their pre-existing condition. |  | No change |  | No change |  | No change |  | Natural England welcomes commitments made in the Outline Soils Managemnt Plan. Natural England will review the updated Commitment Register at submitted at Deadline 4 to ensure the two align.
J94 | 92 | TOPIC: Soils, remediation 'Following construction, construction compounds will be returned to previous conditions as far as reasonably possible' Same as above comments- Natural England advise that commitment wording should be updated and should more accurately define the expectation for reinstatement. |  | No change |  | No change |  | No change |  | Natural England will review the updated Commitments Register at submitted at Deadline 4 to determine if our issues have been addressed.
J95 | 93 | TOPIC: Soils, remediation Treatment of soil during reinstatement- Natural England note that it is unclear whether subsoil material is being retained and reinstated, in the same way as topsoil. Natural England advise that both topsoil (typically top 25cm) and subsoil (typical remaining soil to 1.2m) require reinstatement. |  | No change |  | No change |  | No change |  | Natural England welcomes commitments made in the Outline Soils Managemnt Plan and has no further comments on this issue.
J96 | 95 | TOPIC: Soils, embedded measure Natural England note that the machinery to be used has not been specified. Natural England advise that the machinery used should accord with best practice as set out in Defra 2009 Code of Construction Practice for the Sustainable Use of Soils on Construction Sites, namely using excavators and dump trucks. Use of bulldozers should not be permitted for any subsoils being returned to best and most versatile quality due to the high risk of soil compaction due to repeated trafficking. Bulldozers should not normally be used, other than if a modified loose tipping method of topsoil (not subsoil) replacement is employed in line with the Defra Construction Code.
J97 | 94 | TOPIC: Soils, storage Natural England welcome the commitment to re-vegetate earthworks and exposed areas/soil stockpiles to stabilise surfaces as soon as practicable. However, subsoil stockpiles should not be covered with topsoil as it will be impossible to remove the topsoil separately without mixing when soil is removed from the stockpile. Natural England advise that subsoil stockpiles should not be covered with topsoil and that his needs to be made clear in the text. |  | No change |  | No change |  | No change |  | Natural England welcomes the clarification that the mixing of soils will be avoided in point 5.2.7 made in [APP-226]. Natural England is content with the OSMP and has no further comments on this issue.
J98 | 96 | TOPIC: Soils, SMP Natural England advise that the Soil Management Plan (SMP) should show the areas and type of topsoil and subsoil to be stripped, hail routes to be used, the location and type of each stockpile. Natural England advise that the SMP should be a key document feeding into the Materials Management Plan (MMP) and should include: the areas and type of topsoil and subsoil to be stripped, haul routes to be used, the location and type of each soil stockpile. |  | No change |  | No change |  | No change |  | Natural England welcomes the addition of point 5.2.18 made in [APP-226] 7.4 OSMP. However, we are still awaiting determinations of areas and type of topsoil and subsoil to be stripped and haul routes to be used.
J99 | 97 | TOPIC: Soils, handling Natural England advise that soil handling should normally be avoided during November to March inclusive, irrespective of soil moisture conditions, because it will generally not be possible to establish vegetative cover over winter to help dry out soils and protect them from erosion. Natural England advise that soil handling is avoided during November to March inclusive. |  | No change |  | No change |  | No change |  | Natural England will review the updated Commitments Register at submitted at Deadline 4 to determine if our issues have been addressed.
J100 | 98 | TOPIC: Soils, handling Natural England advise that soils should only be handled in a dry and friable condition. A field suitable method for assessing whether soils are in a dry and friable condition based on plastic limits is set out in Part One (Explanatory Note 4- Table 4.2) of the Institute of Quarrying's Good Practice Guide for Handling Soils in Mineral Working. We advise that this approach together with the associated rainfall protocols should be adopted. |  | No change |  | No change |  | No change |  | Natural England welcomes commitments made in the Outline Soils Managemnt Plan. Natural England will review the updated Commitments Register at submitted at Deadline 4 to ensure the two align.
J101 | 99 | TOPIC: Soils, embedded measure, seasonal measures Natural England advise that an intention to remove vegetation over the winter period needs to be balanced against the risk of soil damage from use of heavy machinery on wet soils and leaving soils bare over-winter. Natural England advise that in most circumstances, soils should remain vegetated over-winter and trafficking by heavy machinery should be avoided. |  | No change |  | No change |  | No change |  | No change
J102 | 100 | TOPIC: Soils, embedded measure, MMP It is unclear whether the proposed stage specific Materials Management Plans (MMPs) will be provided prior to consent or post consent as noted for the stage specific Soil Management Plans (SMPs). Natural England request clarification.
J103 | 101 | TOPIC: Soils, Outline Soils Management Plan (SMP) Natural England concur with this approach. We would be happy for stage specific surveys to be undertaken post consent, but would expect a more detailed desk based assessment at the planning stage. Utilising published soil information to provide a likely indication of the soil properties and likely ALC grade and using site specific post 88 ALC data where available
J104 | 102 | TOPIC: Soils, SMP Natural England support the provision of a Soil Management Plan (SMP) and we advise under para 5.1 of the Defra Construction Code of Practice (Defra, 2009). An SMP will normally form part of the Materials Management Plan for the site. It should include the following: • maps showing topsoil and subsoil types, and the areas to be stripped and left in-situ. • Methods (including machinery) for stripping, stockpiling, respreading and ameliorating the soils. • location of soil stockpiles and content (e.g. Topsoil type A, subsoil type B). • schedules of volumes for each material. • expected after-use for each soil whether topsoil to be used on site, used or sold off site, or subsoil to be retained for landscape areas, used as structural fill or for topsoil manufacture. • identification of person responsible for supervising soil management No further comments.
J105 | 103 | TOPIC: Soils, SMP, BMV The SMP should recognise the exact amount (%) of Best Most Versatile (BMV) land that has been identified in the ALC report. I.e. 53.5ha (23%) of grade 2 BMV land and 22.1ha (10%) of grade 3a BMV land totalling some 33% of the cable route is BMV land. No further comments.
J106 | 104 | TOPIC: Soils, Soil handling, ALC surveys Predictive mapping would provide an additional indication of the ALC grade, and thus the potential impact on BMV agricultural land, however, it does not provide the soil details required to inform soil management which would feed into the Soil Management Plan. There is a risk of soil damage, ALC degradation and long term or permanent loss of BMV from cable installation. Natural England advise that soil will need to be handled according to best practice and reinstated to a high standard to reduce the impacts. The results from a detailed ALC survey would provide soils data to inform a soil management plan for the whole site regardless of whether the use is permanent or temporary in nature.
J107 | 105 | Natural England support this approach. No further comments.
J108 | 106 | TOPIC: Soil storage For topsoil's the preference is for 1 to 3m height in order to minimize the impact of storage on biological processes, whereas for subsoils where the biological activity is lower, subject to safe operations, mounds are often raised to heights of 3 to 5m depending on the resilience of the soils to compaction. Additionally, will bunds be single or multi-tier? The ALC has identified gleyed subsoils therefore Natural England seek clarification of the rationale of storage over direct placement. Further information requested.
J109 | 107 | TOPIC: Soil survey As mentioned above soil colour has only been recorded for the soil pit location. Where further survey is required, Natural England request that soil colour is recorded using the Munsell colour notation where borings are taken in addition to soil pit notations.
J110 | 108 | TOPIC: Soil storage In addition to our previous comment above on C-257. We advise that stockpiles should not be positioned within the root or crown spread of trees, or adjacent to ditches, watercourses or existing or future excavations.
J111 | 109 | TOPIC: Soil compaction The depth of decompaction should reflect the depth of compaction. Additionally, where compaction is likely to take place further consideration should be given to providing a decompaction strategy to maximise the effectiveness of decompaction methods. Further guidance may be found here; IQ Soil Guidance Sheet O.pdf (hubspotusercontent30.net) https://f.hubspotusercontent30.net/hubfs/885685/Soils%20Guidance/IQ%20Soil%20Guidance%20Sheet%20O.pdf Natural England advise that our comments should be considered by RED.
J112 | 110 | TOPIC: Soils, remediation, SDNP' Any remediation required post initial restoration will be driven by commercial considerations of farming practice (land drainage is not functioning as previously) as opposed to habitat quality for biodiversity' - Natural England note that visual impacts to SDNP have not been considered in the requirement for remedial action. Natural England would advise that remediation required post initial restoration for landscape visual impacts to the SDNP should be for material consideration, if initial landscape restoration works have failed. |  | No change |  | No change |  | No change |  | Please refer to our landscape comments for any update on this point.
J113 | 111 | TOPIC: Soils, remediation Reinstatement of calcareous grasslands could prove challenging at certain times of year. The seed bank stockpile should be stored at certain times of year. The seed bank stockpile should be stored for the shortest amount of time possible, and ideally reinstated during the autumn or late winter/early spring. Timing of reinstation of the seedbank should be considered, whilst also minimising the length of time spent in a stockpile. If reinstatement is to occur during the summer months, we would expect a greater level of monitoring (and perhaps watering) during the initial reinstatement. This is to improve the success rates of reinstatement during the summer months. Additional consideration should also be given to areas of calcareous grassland to be reinstated within the SDNP, as poor or failure to reinstate could have visual landscape impacts upon the SDNP. |  | No change |  | No change |  | No change |  | No change
J114 | 116 | TOPIC: Embedded measure, soil handling, soil stockpiles Natural England note that subsoil stockpiles should not be covered with topsoil as it will be impossible to remove the topsoil separately without mixing when soil is removed from the stockpile. We advise that subsoil stockpiles should not be covered with topsoil and that this needs to be made clear in the text.
J115 | 13 | TOPIC: Alternatives, PINS Natural England note that a number proposed alternatives and modifications considered within the PEIR SIR (RED,2022) were outside of the original proposed scoping boundary (RED, 2020). Natural England are of the understanding that this has been discussed and agreed with The Planning Inspectorate.
J116 | 33 | Natural England acknowledge the separation of Importance (legislation and policy) against scale of effects. No further comments.
Additional Comments Since Relevant Representations
J117 |  | Our review of the documents submitted since our relevant/written representations have raised some significant terrestrial ecology concerns, particularly in relation to protected species. We are conducting a thorough review as expediently as possible alongside our wildlife licensing colleagues. We intend to provide an additional submission direct to the Applicant and PINs. |  |  |  | Please see updated advice provided in additional submission and updated protected species advice which will be provided at deadline 3. |  | Please see updated advice provided in additional submission Appendix J2.5 and Appendix J3. |  | Natural England has advised the Applicant to work directly with Natural England's Wildlife Licensing service to agree letters of no impediment for licensable species. We will update this issue again once these have been secured.

## I SLVIA
Point | Point/Paragraph Number(s) from Appendix I [RR-265] | Taken from Natural England’s Relevant and Written Representations SEP AND DEP Appendix I - Seascape and Landscape Visual Impact Assessment (SLVIA) - [RR-265] | RAG Status Rel and WR Rep D1 | Consultation, actions, progression | RAG Status at D2 | Consultation, actions, progression | RAG Status at D3 | Consultation, actions, progression | RAG Status at D4
1. Summary
I 1 | 1.1 | Natural England considers that the two key policy tests of concern to the Rampion 2 Examination are whether the Rampion 2 Design Principles fulfil the requirement for good design as set out in the Overarching National Policy Statement for Energy (EN-1). And (with respect to designated landscapes) the acceptability of further harm to the statutory purposes of the SDNP and special character of the SHC, and harm to the statutory purposes of the CHAONB and IoWAONB.
I 2 | 1.2 | Natural England does not agree that the Rampion 2 Design Principles fulfil the requirement for good design as set out in the Overarching National Policy Statement for Energy (EN-1). We also advise that the project will significantly affect the statutory purposes of the SDNP and the special character of SHC, as well as the statutory purposes of the CHAONB and the IoWAONB. |  | No change - additional material on design principles was submitted at Deadline 1 which NE will respond to at Deadline 3, and update all of the relevant points on the log. |  | No change |  | No change
I 3 | 1.3 | Natural England do recognise the iterative changes made to the DCO order limits between the PEIR and ES stages (as shown in Figure 15.2), as well as the use of design principles to inform these changes. However, whilst accepting that the design changes introduced following the Section 42 consultation have reduced the adverse effects of the scheme on the portion of the SDNP contained within the SHC, Natural England maintains that the proposal will significantly affect the statutory purposes of the SDNP. This is for the following reasons: |  | No change |  | No change |  | No change
I 4 | 1.3 a | The wind turbine generators (WTG) of the Rampion 2 OWF maximum design scenario are too big and located too close to the coastline of the SHC portion of the SDNP. Their sheer size and the lateral spread, combined with the marked contrast in height with the existing Rampion 1 WTG will be visually incoherent, clutter-up the seascape setting of the SDNP and dramatically degrade views out to sea, particularly from Beachy Head to Birling Gap. Natural England therefore advises that WTG should be excluded from the Rampion Zone 6 western array area, thereby adhering to the Design Principles as secured in the Rampion 1 DCO/DML. |  | No change |  | The Applicant has clarified that there is potential to add further turbines to zone 6. Our advice remains there should be no WTG in zone 6. |  | No change
I 5 | 1.3 b | The expansion of the influence of turbines westwards through development within the Rampion extension area will increase the industrialisation of the seascape setting of the SNDP, particularly for inland locations located to the west of Wilmington Hill. Their presence in the seascape setting of the SDNP will further degrade the quality of views out to sea which are already adversely influenced by the turbines of the Rampion 1 array and will lead to further loss of the natural beauty for which this landscape was designated. |  | No change |  | No change |  | No change
I 6 | 1.3 c | The westward expansion will also result in significant effects on the seascape setting of the CHAONB (although this will be limited) and more extensively the eastern portions of the IoWAONB at Bembridge Down and St. Boniface Down, resulting in further loss of natural beauty for these designations as well. |  | No change |  | No change |  | No change
I 7 | 1.4 | Our assessment of the SLVIA has identified further evidence that Natural England will require to fully understand the impacts of the project on protected landscapes. This information will allow Natural England to advise on whether the current proposed design is the ‘least worst possible’.
2. A summary of the key further evidence needed to inform the SLVIA
I 8 | 2.1 | This section summarises the further evidence that Natural England require from the Applicant to fully understand the impacts to designated landscapes and advise on whether the current proposed design is the ‘least worst possible’ i.e. that sufficient effort has been taken to avoid, reduce and mitigate impacts.
I 9 | 2.1 a | Detail on how the Rampion 1 Design Principles have influenced the Rampion 2 maximum design scenario. |  | No change |  | No change |  | No change
I 10 | 2.1 b | The Applicant’s justification for why the Rampion 1 mitigation measures do not directly apply to the Rampion 2 project. |  | No change |  | No change |  | No change
I 11 | 2.1 c | Evidence to demonstrate why constructing more WTG in the Zone 6 (Eastern Array Area) than described within the indicative layout would not present a ‘greater worse-case effect’. |  | No change |  | No change |  | No change
I 12 | 2.1 d | Evidence to show that a greater densification of WTG in either the Zone 6 Area or Extension Area will not materially increase the effect of the Proposed Development on coastal views from protected landscapes. |  | No change |  | No change |  | No change
I 13 | 2.1 e | An explanation of the balancing exercise that was undertaken between the spatial extent of the Rampion 2 array and the apparent height of Rampion 2 WTGs. |  | No change |  | No change |  | No change
I 14 | 2.1 f | A report on the cumulative visual effects, which includes an assessment of the visual effects from the perceived heights of the Rampion 2 WTGs in comparison to the Rampion 1 WTGs. |  | No change |  | No change |  | No change
I 15 | 2.1 g | Paragraph 15.7.29 states that ‘the less HFoV that is affected, the lower the magnitude of change’. The Applicant should provide a detailed explanation of how the magnitude of change at representative viewpoints has been determined exactly, given the Preliminary Environmental Impact Report (PEIR) or Environmental Statement (ES) design option. |  | No change |  | No change |  | No change
I 16 | 2.1 h | A demonstration of how the design of Rampion 2 limits as far as possible the horizontal field of view (HFoV)of WTG from the SDNP and the SHC. |  | No change |  | No change |  | No change
I 17 | 2.1 i | A clear and direct assessment of the impact that the Rampion 2 Design Principles have on the special qualities of the SDNP. |  | No change |  | No change |  | No change
I 18 | 2.1 j | Justification as to how the natural beauty of the SDNP, in those proportions of the National Park adversely effected by the scheme, will remain unchanged given the SLVIA conclusion that significant harm is likely to occur to Special Quality 1 - diverse, inspirational landscapes and breath-taking views. |  | No change |  | No change |  | No change
I 19 | 2.1 k | A conclusion on the significance of the change to tranquillity (SDNP Special Quality 3 – tranquil and unspoilt places) at night-time ‘around the tops of the downs’ where ‘tranquillity is greatest’. |  | No change |  | No change |  | No change
I 20 | 2.1 l | An assessment of the impact that the Rampion 2 Design Principles have on the special qualities of the CHAONB and IoWAONB. |  | No change |  | No change |  | No change
I 21 | 2.1 m | A technical assessment, inclusive of modelling work, on potential visual effects from both navigation and aviation lighting to IoWAONB Special Quality 5 – great opportunities for recreational activities and learning experiences. |  | No change |  | No change |  | No change
3. Detailed Advice
I 22 | 3.1 | Natural England welcomes the efforts of the Applicant in updating the design of the Rampion 2 project, and developing the four Design Principles that now underpin it. In particular, Natural England note the reduction in the extent of the eastern boundary of Rampion 2; a design change to ensure that the DCO for Rampion 2 does not compromise the Structures Exclusion Zone (SEZ) crucial to the Rampion 1 DCO (which serves to mitigate impacts of Rampion 1 on the SDNP and SHC). However, it should be noted that although there is a notable reduction in impact, the updated design will still cause harm to the Statutory purposes of the SDNP, including the SHC, CHAONB and the IoWAONB. Natural England continues to consider that these design principles have greater potential to reduce the potential impacts of the proposal on designated landscapes. |  | No change |  | No change |  | No change
I 23 | 3.2 | 3.2 On page 85 of the SLVIA it is noted by the Applicant that; ‘These Design Principles were developed in consultation with Natural England, drawing on the Rampion 1 Design Principles and those specifically recommended by Natural England for Rampion 2 during consultations.’ While the SLVIA is true in stating that the new Design Principles for the Rampion 2 project ‘have been developed in consultation with stakeholders’ (para 15.7.24), this statutory consultation is the first time that Natural England have seen and commented on the details of the evolved design of Rampion 2 since PEIR, and the Design Principles that informed it. (as described from page 286 of ES Chapter 15).
I 24 | 3.3 | We wish to highlight that Natural England proposed a set of design principles for the Rampion 2 development in our Section 42 advice, as follows:
I 25 | 3.3 a | There should be no turbines constructed within Zone 6 |  | No change |  | No change |  | No change
I 26 | 3.3 b | Reducing the combined horizontal extent (lateral spread) of turbines associated with a visually combined R1 and R2 scheme, or |  | No change |  | No change |  | No change
I 27 | 3.3 c | There should be perceptible separation distance (from all land-based viewpoints) between the existing R1 OWF and the new R2 array by concentrating development in the western end of the Rampion Extension area. The distance should be sufficient that a clear distinction can be made between the two arrays, in order that they are perceived as separate objects in the seascape when viewed from the shore and from within the SDNP. |  | No change |  | No change |  | No change
I 28 | 3.3 d | Clear lines of sight should be left between the arrays (R1 and R2), so that open views to the horizon are maintained when viewed from shore and from within the SDNP. |  | No change |  | No change |  | No change
I 29 | 3.3 e | The design of the new array should aim to balance the two arrays as far as practicable in terms of apparent turbine size and spacing, taking advantage of the effects of perspective to reduce any apparent difference in size between turbines. |  | No change |  | No change |  | No change
I 30 | 3.3 f | Implement reduced aviation lighting intensity for the R1 array (from 2000cd to 200cd). (Nb. the Applicant has already agreed to the dimming of aviation lights to 200cd where visibility conditions permit, which is welcomed).
Policy Test: Do the Rampion 2 Design Principles fulfil the requirement for good design as set out in EN-1?
I 31 | 3.5 a | Natural England’s current position regarding the extent to which the Rampion 2 meet the policy tests in the Overarching National Policy Statement (NPS) for Energy (EN-1) is as follows: a. Proposed environmental measure C-61 demonstrates the Applicant’s commitment to applying ‘due regard’ to ‘Design Principles held in Rampion 1 Design Plan’. These Design Principles related entirely to upholding the statutory purposes of the coastal portion of the SDNP and SHC. For ease of reference the Rampion 1 Design Principles’ (Condition 11, Part 2, 11 (3a) of Schedule 13 (p.106)) are included here; |  | No change |  | No change
I 32 | 3.5 b i 2.1 a | The Rampion 2 project is now associated with four new Design Principles which ‘draw on’ (page 85 of ES SLVIA), but do not replicate, the four principles listed in Condition 11, Part 2, 11 3(a) (page 106) of the Rampion 1 DCO. Natural England consider that the purpose of the Rampion 2 Design Principles is the same as the Rampion 1 Design Principles, i.e. to reduce the risk of harm to the statutory purposes of the designations. Natural England highlights the following points: i. Natural England’s Section 42 response requested that the Applicant produce a ‘detailed account as to how the R1 Design Principles have influenced the R2 maximum design scenario as a matter of urgency’. However, NE cannot find this account within the Rampion 2 submission documents. We advise that this account is also a requirement of national policy. Section 4.5.4 of EN-1 states: ‘applicants should be able to demonstrate in their application documents how the design process was conducted and how the proposed design evolved’.
I 33 | 3.5 b ii | Natural England advises that a statement is submitted into the Examination by the Applicant on why the Rampion 1 mitigation measures do not directly apply to the Rampion 2 Project, which in effect, is a direct extension of the Rampion 1 array. We believe this is necessary because: • The Applicant’s justification for environmental measure C-61 is that ‘where appropriate, the intentions of the Design Principles established for Rampion 1 are followed through to the Rampion 2 design plan’. Consequently, the Examining Authority must be provided with information on where it was not appropriate to apply Rampion 1 Design Principles to the Rampion 2 Project, and a rationale for why this is the case. This information is not currently available in the Environmental Statement. • Natural England has identified direct consequences of the Rampion 1 DCO Design Principles not being fully applied; for example, see 3 (c) (ii) and 5 (b) within this response. |  | No change |  | No change |  | No change
I 34 | 3.5 c | Considering that the ‘maximum assessment assumptions require flexibility on the balance of WTGs located within the Zone 6 Area and Extension Area’ and appreciating that the Maximum Design Scenario (MDS) layout is ‘weighted towards the northern coastward perimeters of the wind farm array area, as close as possible to the coastline’, Natural England does not understand how a ‘greater proportion of WTGs in either zone will not result in a greater worse-case effect’ than is already presented by R1. This is because: |  | No change |  | No change |  | No change
I 35 | 3.5 c i | Natural England advised at the Section 42 consultation (and continues to advise) that there should be no turbines in the Crown Estate Zone 6 due to the potential for major adverse seascape and visual effects on the most sensitive views from within the SHC, which is located wholly within the SDNP. Therefore constructing more turbines in the Zone 6 Area than described within the indicative layout would present a ‘greater worse-case effect’. |  | No change |  | No change |  | No change
I 36 | 3.5 c ii | Evidence has not been provided with the ES to show that a greater densification of turbines in either the Zone 6 Area or Extension Area ‘will not materially increase the effect of the Proposed Development in coastal views’ (SLVIA page 277). This evidence will be crucial for the Examining Authority to consider in the light of the following factors: • the density of turbines is an important element of how the array will be perceived from many of the representative viewpoints, • the presence of a reduced perceived density of turbines is also crucial to achieving the ‘separation foreground’ Design Principle (SLVIA paragraph 15.7.49). |  | No change |  | No change |  | No change
I 37 | 3.5 c iii | Based on such evidence (when available) and to achieve the ‘separation foreground’ Design Principle, Natural England advises that there should be an agreed maximum number of turbines in each zone. This is because: • The proposed minimum spacing of the larger height turbines has reduced since the S42 consultation (Table 4-2), exacerbating the potential for a densification of turbines in either zone. • The Applicant committed to applying ‘due regard’ to ‘Design Principles held in Rampion 1 Design Plan’ with proposed environmental measure C-61. Design Principle (a) (iii) listed in Condition 11, Part 2, 11 3(a) (page 106) of the Rampion 1 DCO required the largest turbines (in any hybrid scheme) to be located to the south-western portion of the order limits and were not to be constructed in most sensitive areas of the Rampion 1 order limits. Therefore, this is in contrast with the Applicant’s request to construct in zone 6, and the flexibility being requested by the Applicant regarding the ‘balance of WTGs located within the Zone 6 Area and Extension Area’. This is of particular concern given the difference in height between the existing array and the proposed WTG for Rampion 2. |  | No change |  | No change |  | No change
I 38 | 3.5 d | Natural England agrees that the reduction in the spatial extent of the Rampion 2 array will result in a ‘better balance in apparent WTG size’ compared to the original proposal (Table 15-7, page 65). But the SLVIA does not describe any balancing exercise undertaken or contain a narrative to support this claim. Natural England would like to understand how this ‘better balance’ was determined. |  | No change |  | No change |  | No change
I 39 | 3.5 d i | A ‘better balance in apparent WTG size’ does not mean that the apparent Rampion 2 turbine sizes will not remain significant in EIA terms from key viewpoints within designated landscapes. This is because: • The apparent heights to blade tip of the nearest Rampion 2 WTGs do not fall below 0.4 degrees from any of the viewpoints included within the Environmental Statement that are situated within a designated landscape, indicating that the scale of effects from all viewpoints within designated landscapes have the potential to be significant (see Part 2 of this response for more details, and Appendix 2 for further information on apparent heights). • The apparent heights to blade tip of the nearest Rampion 2 WTGs do not fall below 0.4 degrees from any of the viewpoints included within the Environmental Statement that are situated within a designated landscape, indicating that the scale of effects from all viewpoints within designated landscapes have the potential to be significant (see Part 2 of this response for more details, and Appendix 2 for further information on apparent heights). |  | No change |  | No change |  | No change
I 40 | 3.5 d ii | Natural England agrees with paragraph 15.6.27 of the SLVIA , which reports that the perceived heights of the Rampion 2 turbines in comparison to the Rampion 1 turbines ‘is likely to be central to the potential for cumulative visual effects’. However, it is not clear where an assessment of these cumulative visual effects is undertaken within the SLVIA, or what the conclusion of this assessment on cumulative visual effects is. If it has not been undertaken this assessment should be submitted into the Examination as a matter of urgency. |  | No change |  | No change |  | No change
I 41 | 3.5 e | Natural England recognises the efforts of the Applicant in reducing the horizonal field of view of the Rampion 2 array. The SLVIA states that this Design Principle reduces the magnitude of change for many viewpoints, with significant implications for the Applicant’s own assessment of effects. However, given the substantial scale and lateral spread of development that the reduced array area still represents (bearing in mind the human eye physically cannot see the entirety of the R2 array in a single view from the majority of the representative viewpoints), clarification should be provided by the Applicant regarding how the actual decreases in magnitudes of change between design options have been determined. |  | No change |  | No change |  | No change
I 42 | 3.5 e i | Natural England advises that addressing this issue is critical to understanding the judgements made in the SLVIA, as the horizonal extent of Rampion 2 will be double or triple the horizonal extent of Rampion 1 from most viewpoints within designated landscapes (Table 15-27). This means that a very large proportion of the visible seaward horizon will be enclosed by Rampion 2. It is not clear from the SLVIA whether the significance of visual effects described have reduced simply because the Rampion 2 ES design now has a smaller Horizontal Field of View (in degrees). |  | No change |  | No change |  | No change
I 43 | 3.5 e ii | The Applicant has committed to applying due regard ‘to Design Principles held in Rampion 1 Design Plan’ with proposed environmental measure C-61. Design Principle (a) (i) listed in Condition 11, Part 2, 11 3(a) (page 106) of the Rampion 1 DCO refers to the ‘need to limit as far as possible the horizonal degree of view of wind turbine generators from the SDNP and the SHC’. However, it has not been established whether the design of Rampion 2 now limits, as far as possible, the horizonal field of view of wind turbine generators from the SDNP and the SHC. Evidence on this matter is not presented within the SLVIA and should be submitted into the Examination. |  | No change |  | No change |  | No change
I 44 | 5.5 f | Natural England supports the inclusion of the ‘wind farm separation zones’ Design Principle, as it successfully acts to significantly reduce seascape and visual effects on the most sensitive views from parts of the SHC within the SDNP. The comparative wirelines drawings presented in Figures 15.93 to 15.109, Volume 3, of the ES (Document Reference: 6.3.15) are particularly helpful in demonstrating this design success. However, contrary to aims of this Design Principle, no view from within the SDNP provides a clear line of sight between Rampion 1 and Rampion 2. In no view, with the possible exception of the view from the beach at Cuckmere Haven where westerly views are obscured by cliffs, are the WTGs of Rampion 1 and 2 actually perceived as separated. In all instances, even at Beachy Head, the visible separation ‘between arrays’ is actually a separation between the Zone 6 Area and the Extension Area of the Rampion 2 project. Consequently, in many views, Rampion 2 itself appears as two separate wind farms. |  | No change |  | No change |  | No change
I 45 | 3.6 | Due to the above, Natural England considers that the Rampion 2 Design Principles do not fulfil the requirement for good design as set out in the Overarching National Policy Statement for Energy (EN-1). |  | No change |  | No change |  | No change
Part 2 The Significance of Impacts to Protected Landscape
Policy Test - The acceptability of further harm to the statutory purposes of the SDNP and special character of the SHC, and harm to the statutory purposes of the CHAONB and IoWAONB.
I 46 | 3.7, 3.8, 3.9 | Natural England considers that the adjustment of the MDS to reflect a smaller number of turbines will reduce the magnitude and geographic extent of the seascape, landscape and visual effects of Rampion 2 on designated and defined landscapes. However, on balance the proposed Design Principles do not reduce Natural England’s judgement regarding the significance of effects on designated landscapes. The Design Principles act mainly in the SHC area within the SDNP; a very small geographic area of the SDNP with the potential to be impacted by Rampion 2. We therefore advise that the project will significantly affect the statutory purposes of the SDNP and the special character of SHC, as well as the statutory purposes of the CHAONB and the IoWAONB. |  | No change |  | No change |  | No change
I 47 | 3.10. | We advise that the Applicant provides further information as set out in Part 1 above to be able to advise in more detail regarding the likely magnitude of impact. However, on the basis of the material that has been provided, the advice below highlights where Natural England’s judgements on the significance of these reductions, in EIA terms, differ from those of the Applicant.
I 48 | 3.10 a | a. The effects of Rampion 2 on the SHC area within the SDNP (i.e. the views from Beachy Head and surrounding headland to Birling Gap) have been assessed as ‘decreasing to Not Significant (Moderate) on perceived seascape setting in panoramic views from the coastal downs between Birling Gap and Beachy Head, where the effect of Rampion 2 reduces with distance, its narrower field of view and relative balance in apparent scale and spread’. The SLVIA concludes in paragraph 15.15.21 that ‘Significant visual effects have been avoided in views from the eastern half of the Heritage Coast area of the SDNP between Beachy Head (Viewpoint 1) and Birling Gap (Viewpoint 2)’. Natural England considers that the Rampion 2 Design Principles have resulted in a reduction in the magnitude of effects in views from Beachy Head to Birling Gap. However, we still consider that these effects remain significant (major/moderate) and therefore disagree with the Applicant’s assessment. This is because: |  | No change |  | No change |  | No change
I 49 | 3.10.a. i | The apparent heights of the Zone 6, western array WTGs (MDS) will be 0.569 degrees at Beachy Head and 0.6 degrees at Birling Gap. The Rampion 2 WTGs will appear to be nearly twice the height of the Rampion 1 WTGs from these locations. See Table 1 and Appendix 2 for further detail. • The Rampion 2 turbines will be frequently perceivable from this highly sensitive protected landscape and add a sense of industrialisation to one of the last coastal stretches in Sussex Bay where relative remoteness (despite the presence of the Rampion 1 turbines) can be experienced. • The experience of SDNP Special Quality 1 ‘Breath-taking views’ is an important characteristic of this coastal stretch, and in part why the area was defined as a Heritage Coast in 1973. Impacts to this special quality here have been assessed as medium-low magnitude and Not Significant (moderate), despite the SLVIA concluding that significant harm will be caused to this quality. The impacts to SDNP Special Quality 1 along this coastal stretch are assessed by Natural England as significant (major/moderate). |  | No change |  | No change |  | No change
I 50 | 3.10.a.ii | Given the sensitivity of the landscape between Beachy Head to Birling Gap to change, Natural England does not agree that the Rampion 2 Design Principles are sufficient to remove the significance of landscape, seascape and visual effects from this ~2.5 mile stretch of designated and defined coastline. |  | No change |  | No change |  | No change
I 51 | 3.10.b | Natural England has not changed any original judgements of impact significance associated with the key representative viewpoints as presented within the R2 PEIR. It is not disputed that the recent design changes have, particularly between Beachy Head and Birling Gap, reduced landscape, seascape and visual effects on the SDNP and SHC. However, given the sheer size and lateral geographical spread of the R2 Project, and the effect that a development of this scale will have on the SDNP, this reduction of predicted impacts between Beachy Head to Birling Gap is not sufficient for Natural England to change any of our assessments of the significance of effects upon landscape, seascape and visual receptors (and by extension the SDNP) arising from R2. |  | No change |  | No change |  | No change
I 52 | 3.10.b i | The area most benefitted by the Rampion 2 Design Principles covers a distance of ~2 miles between the very sensitive viewpoints of Beachy Head and Birling Gap. The SLVIA describes the aim of the Rampion 2 Design Principles as ‘minimising harm to the special qualities of nationally designated landscapes, particularly the SDNP and the associated Sussex Heritage Coast’. However, the Design Principles Wind Farm Separation Zones and Separation Foreground do not aim to mitigate impacts to those areas of the SDNP encompassed by the ZTV (see other SDNP viewpoints). |  | No change |  | No change |  | No change
I 53 | 3.10.c | Natural England does not agree that the Design Principles that have informed the Rampion 2 design have acted to remove the significance of effects to the SDNP in relation to Special Quality 1 or for Special Quality 3. This is because; |  | No change |  | No change |  | No change
I 54 | 3.10.c i | There is no direct assessment of the impact that the Rampion 2 Design Principles have on the SDNP special qualities. This assessment should be made available within an updated Environmental Statement. |  | No change |  | No change |  | No change
I 55 | 3.10.c.ii | Critical evidence is missing from the SLVIA as described in Part 1 (1-5) of this response. |  | No change |  | No change |  | No change
I 57 | 3.10.c.iii | Natural England offers the following comments to inform an updated impact assessment: Special Quality 1. In paragraph 15.15.40 of the SLVIA the Applicant states that ‘Whilst significant harm would be caused to this quality (‘breathtaking views’ and ‘stunning, panoramic views to the sea’), this would not compromise the purpose of the designation, as the natural beauty of the SDNP will remain and opportunities will still be present for understanding and enjoyment of the special qualities of the SDNP, and Rampion 2 will not therefore undermine the statutory purpose of the SDNP or compromise the purposes of its designation.’ We do not agree with this reasoning. The Applicant concludes that the Rampion 2 project will cause significant harm to Special Quality 1, so it is illogical to conclude that it will not compromise the statutory purpose of the SDNP, which is to conserve and enhance natural beauty. Natural England agrees with the Applicant the Rampion 2 project will result in significant harm to SDNP Special Quality 1, particularly the ‘stunning, panoramic views to the sea’. We highlight that Special Quality 1 is also experienced at multiple locations within the SDNP and is particularly prominent on the tops of the downs, as experienced for example at Devils Dyke (VP17) and Levin Down (VP32). |  | No change |  | No change |  | No change
I 58 | 3.10.c.iv | Special Quality 3. The Applicant has justified in Table 15-32 (page 397) that night-time lighting of Rampion 2 will ‘result in relatively low change to the tranquillity experienced within the SDNP coastline’ and has not offered a conclusion on the significance of the change to tranquillity at night-time ‘around the tops of the downs’ where ‘tranquillity is greatest’. It is understood from Appendix 15.5, which unfortunately does not assess special qualities, that the representative night-time viewpoints from ‘tops of the downs’ were assessed as not significant due to the lighting being perceived as an ‘extension of a familiar feature’ i.e. Rampion 1. Natural England does not agree with this assessment, as the lateral spread of the Rampion 2 lighting will be perceived as a tripling of the extent of lighting that is already visible from Rampion 1. The Applicant’s should bring forward evidence-based conclusions regarding the significance of the predicted changes on the night-time tranquillity of these specific areas. |  | No change |  | No change |  | No change
I 59 | 3.10.d | Natural England’s assessment on the special qualities of the CHAONB and IoWAONB remains unchanged from our s42 response. We advised that the westward expansion of WTGs will result in significant effects on the seascape setting of the CHAONB and more extensively the eastern portions of the IoWAONB at Bembridge Down and St. Boniface Down resulting in further loss of natural beauty for these designations. We have the following further comments to make: |  | No change |  | No change |  | No change
I 60 | 3.10.d.i | We note that there is no direct assessment of the impact that the Rampion 2 Design Principles have on the special qualities of the CHAONB and IoWAONB. We advise that introducing a separation distance between the Rampion 1 and Rampion 2 arrays could exacerbate landscape, seascape and visual impacts for the CHAONB and IoWAONB. However, the SLVIA does not indicate whether this is the case, and. despite the redesign of the project our concern on this matter remains. We would like to see evidence submitted into the Examination as a matter of urgency, noting the apparent height values for viewpoints located within these designations. |  | No change |  | No change |  | No change
I 61 | 3.10.d.ii | We acknowledge the narrative provided in relation to night-time impacts to IoWAONB special quality 5 (Table 15-42). However, in the absence of a detailed assessment (inclusive of modelling work of potential lighting visual effects from both navigation and aviation lighting), we do not agree that effects can be discounted. Figure 15.25 (Zone of Theoretical Visibility for the aviation lighting of Rampion 2) indicates that all IoWAONB viewpoints, the maximum number of turbine aviation lights (34 – 42) are theoretically visible, and therefore this matter requires further assessment. |  | No change |  | No change |  | No change
I 62 | 3.10.e.i&ii&iii | We are disappointed that, despite our Section 42, the study area used for the ‘Assessment of aviation and navigation night-time lighting’ (Appendix 15.5) does not include an assessment of; i. effects on Special Quality 5 of the IoWAONB ‘dark starlit skies’; ii. effects on the Special Quality 5 of the CHAONB ‘overall sense of wilderness within the seascape’; iii. effects on landscape character. We advise that the Applicant should carry out these assessments, or submit evidence into the Examination to provide a rationale for excluding assessments (a) to (c), and how, in the absence of an assessment on night-time landscape character, how Appendix 15.5 can conclude that ‘The proposed aviation and marine navigation lighting will not result in effects on landscape character’. (SLVIA paragraph 8.1.24). |  | No change |  | No change |  | No change
Additional Issues following Relevant and Written Representations submission 06/11/2023
Section 245 (Protected Landscapes) of the Levelling Up and Regeneration Act 2023
I 67 | New issue at deadline 1 | Section 245 (Protected Landscapes) of the Levelling Up and Regeneration Act 2023 places a duty on relevant authorities in exercising or performing any functions in relation to, or so as to affect, land in a National Park, the Broads or an Area of Outstanding Natural Beauty (“National Landscape”) in England, to seek to further the statutory purposes of the area. The duty applies to local planning authorities and other decision makers in making planning decisions on development and infrastructure proposals, as well as to other public bodies and statutory undertakers. It is anticipated that the government will provide guidance on how the duty should be applied in due course. In the meantime, and without prejudicing that guidance, Natural England advises that: the duty to ‘seek to further’ is an active duty, not a passive one. Any relevant authority must take all reasonable steps to explore how the statutory purposes of the protected landscape (A National Park, the Broads, or an AONB) can be furthered; the new duty underlines the importance of avoiding harm to the purposes of protected landscapes but also to seek to further the conservation and enhancement of a protected landscape. That goes beyond mitigation and like for like measures and replacement. A relevant authority must be able to demonstrate with reasoned evidence what measures can be taken to further the statutory purpose. The proposed measures to further the statutory purposes of a protected landscape, should explore what is possible in addition to avoiding and mitigating the effects of the development, and should be appropriate, proportionate to the type and scale of the development and its implications for the area and effectively secured. Natural England’s view is that the proposed measures should align with and help to deliver the aims and objectives of the designated landscape’s statutory management plan. The relevant protected landscape team/body should be consulted. |  | No change |  | No change |  | No change