## Title page
THE PLANNING ACT 2008
THE INFRASTRUCTURE PLANNING (EXAMINATION PROCEDURE) RULES
2010
Natural England's Risk and Issues Log - Deadine 1 Submission.
For:
The construction and operation of North Falls Offshore Wind Farm, located approximately 40 km from the Suffolk Coast in the Southern North Sea.
Planning Inspectorate Reference: EN010119
18 February 2025

## How to read Risks and Issue Log
Natural England has created this Risk and Issues Log to track progress through the XXXX examination process. The Risks and Issues Log will be submitted at each deadline and marks issues with a colour from our RAG scale depending on the level of significance of the issue. All red, amber and purple issues from our Relelvant and Written Representation are included (collated where appropriate). Green and yellow issues are included if/where relevant. It should be noted that the colour scale is different from that used in the Statement of Common Ground provided by The Applicant. The Risk and Issues Log is split into multiple tabs in line with the Appendices of our Relevant Representations submission. A - Add in titles and reorder/rename tabs to match B - C- D - E - F - G - H - I - The Risk and Issues Log will be submitted alongside our written response at each deadline. This will reflect our position following a review of documents that we have considered in forming our position at each deadline. Any issues added to the log during Examination (not included in Relevant Reps) are highlighted in Red and then coded according to RAG status. Insert background text on how the R&I tabs have been set out as needed
Purple Note for Examiners and/or competent authority. May relate to DCO/DML
Red Natural England considers that unless these issues are resolved it will have to advise that (in relation to any one of them, and as appropriate) it is not possible to ascertain beyond reasonable scientific doubt that the project will not affect the integrity of an SAC/SPA/Ramsar and/or significantly hinder the conservation objectives of an MCZ and/or damage or destroy the interest features of a SSSI and/or comply fully with the Environmental Impact Assessment requirements.
Addressing these concerns may require the following:
new baseline or survey data; and/or
significant revisions to baseline characterisation and/or impact modelling and/or
significant design changes; and/or
significant mitigation
In addition, Natural England may use this category to highlight where there is a significant risk that an issue will not be sufficiently addressed within the Examination timescales. Consequently, issues that start out as Amber may progress to Red in the latter stages of the examination.
Amber Natural England does not agree with the applicant’s position or approach and consider that this could make a material difference to the outcome of the decision-making process for this project.
Natural England considers that these matters may be resolved through:
provision of additional evidence or justification to support conclusions; and/or
revisions to impact assessment methodology and/or assessment conclusions; and/or
minor to moderate revisions to impact modelling; and/or
well-designed mitigation measures that are adequately secured through the draft DCO/dML and/or
amendments to draft plans
If these issues are not addressed or are unlikely to be resolved by the end of the Examination, then they may become a Red risk as set out above.
Yellow Natural England doesn’t agree with the Applicant’s position or approach. We would ideally have liked this to be addressed but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process and would not expect these matters to be a ongoing focus of the examination. However, we reserve the right to revise our opinion should further evidence be presented.
It should be noted by interested parties that just because these issues/comments are not raised as significant concerns in this instance, it should not be understood or inferred that Natural England would be of the same view in other cases or circumstances.
Once a Risk or Issue has been categorised as yellow, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be hidden at subsequent deadlines in order to rationalise the risk and issues log.
Green Natural England is in broad agreement with the Applicant’s approach and has no significant outstanding concerns. As above, we reserve the right to revise our opinion should new evidence be presented. Once a Risk or Issue has been categorised as green, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be hidden at subsequent deadlines in order to rationalise the risk and issues log.

## PADSS
PRINCIPAL AREAS OF DISAGREEMENT SUMMARY STATEMENT (PADSS) - TAKEN FROM COVER LETTER TO NATURAL ENGLAND'S REL REPS [RR-243]
NE Ref | The principal issue in question | The brief concern held by Natural England which will be reported on in full in WR / LIR | What needs to change, or be included, or amended so as to overcome the disagreement | Likelihood of the concern being addressed during Examination | RAG rating
Development Consent Order – Appendix A
P1 | During construction monitoring conditions. | The during construction monitoring conditions within the deemed Marine Licences (dML) Schedules 8, 9 and 10 do not secure the cessation of piling if noise impact significantly exceeds predicted impacts | Natural England has provided example wording in Table 2 (Appendix A) and would recommend it is included in Schedules 8, 9 and 10. | Potential Resolution. This is subject to the Applicant securing the advised commitment.
P2 | Schedule 15 compensation only covers impacts to Lesser Black Backed Gull (LBBG). | We have concerns that we cannot rule out an Adverse Effect on Integrity (AEoI) on the Flamborough and Filey Coast (FFC) Special Protection Area (SPA). | Natural England requests that draft compensation provisions are provided for all features on a without prejudice basis where there is disagreement that an AEoI can be ruled out. | Potential Resolution. This is subject to the Applicant securing the advised commitment.
P3 | Additional mitigation measures | We highlight that throughout our Relevant Representations/Written Representations (RR/WR)appendices we have identifiedfurther mitigation measures which could be adopted by the Applicant to minimise the project’s environmental impacts, including reducing the Rochdale envelope. | Natural England advises that further mitigation measures are committed to be the Applicant and ES chapters/named plans/technical notes are updated | Potential Resolution. This is subject to the Applicant securing the advised commitment.
Marine Geology, Oceanography and Physical Processes – Appendix B
P4 | Success of subtidal Horizontal Direction Drilling (HDD). | Natural England is concerned that there is uncertainty regarding the likely success of a subtidal HDD at the landfall point. | Natural England advises that further detail and evidence is presented to support the use of HDD. | Likely. This is subject to the Applicant providing an updated assessment.
P5 | Uncertainty around Worst Case Scenario (WCS) parameters, modelling, and information used to inform assessments. | Natural England highlights that uncertainty remains in relation to assessment conclusions regarding sediment deposition during construction, seabed mobility and erosion, and sandwave recovery. | Natural England advises that further detail and updated assessments are provided by the Applicant. | Likely. This is subject to the Applicant providing updated information, modelling and assessment.
Marine Geology, Oceanography and Physical Processes and Benthic – Appendices B and C
P6 | Insufficient information on anticipated location and extent of cable protection and additional cable protection during operation and maintenance phase. | Natural England is concerned that there is insufficient information on the anticipated location and extent of cable protection measures placed near Margate and Long Sands Special Area of Conservation (MLS SAC) to rule out negative impacts to the SAC due to disruption of sediment transport pathways operating around the northern boundary. | Natural England advises that, if available, the Applicant should provide an indication of the areas where cable protection is anticipated to be needed. | Potential Resolution. This is subject to the Applicant providing updated information, modelling and assessment.
Benthic and Intertidal Ecology – Appendix C
P7 | Insufficient evidence – Indirect benthic impacts. | Following on from point P5 due to the highlighted uncertainty (reasonable scientific doubt), we cannot advise the exclusion of an Adverse Effect on Integrity (AEoI). | Natural England requires further work by the Applicant to provide a robust assessment of the potential Worst-Case area of impact on benthic communities within MLS SAC. A more robust consideration of the worst-case is also required to provide confidence in potential requirements for compensation. | Potential Resolution. This is subject to the Applicant providing updated information, modelling and assessment.
P8 | Impacts on SPAs. | Natural England is concerned with the lack of robustness in the Applicant’s current assessment of pressures/impacts on supporting benthic habitats and prey availability for SPA features. | Natural England advises that full consideration of the likely nature, extent, duration, and significance of impacts upon SPA supporting habitats and prey availability is required | Potential Resolution. This is subject to the Applicant providing updated information, modelling and assessment.
P9 | Mitigation measures for Section 41 Natural Environment and Rural Communities (NERC) Act 2006 Habitats. | Natural England advises that mitigation measures currently fail to consider all relevant NERC habitats. | Natural England advises that, mitigation commitments are made to where possible avoid impacts to all Section 41 NERC Habitats | Potential Resolution. This is subject to the Applicant securing the advised commitment.
P10 | Marine Conservation Zone Assessment (MCZA) – Insufficient consideration/evidence. | Natural England is concerned that indirect impacts upon benthic features within Kentish Knock East MCZ (KKE MCZ) have not been adequately assessed. | Natural England advises that a more robust assessment is needed regarding the anticipated worst-case sediment deposition parameters due to sandwave levelling/ seabed preparation activities in the vicinity of KKE MCZ. | Potential Resolution. This is subject to the Applicant providing updated information, modelling and assessment.
P11 | MCZ Buffer. | Following on from P10 directly above Natural England queries whether a buffer has been applied /should be applied around the infrastructure and associated activities closest to the KKE MCZ boundary as mitigation. | Natural England advises that a suitable buffer between the array infrastructure and the KKE MCZ should be applied to ensure that avoidance mitigation is effective. | Potential Resolution. This is subject to the Applicant securing the advised commitment.
P12 | Reduction/Mitigation of Impacts through Selection of Cable Protection Measures. | Natural England advises that the use of other external cable protection options to that of rock protection could reduce/mitigate the impacts | We advise that further consideration is given to other cable protection options which are more readily removeable and that an Outline Decommissioning Plan is provided at the time of consent | Potential Resolution. This is subject to the Applicant securing the advised commitment.
Fish and Shellfish Ecology – Appendix D
P13 | Overlapping spawning grounds. | We note from the Chapter 11 Fish and Shellfish Ecology Figures (volume II) that there is overlap with spawning grounds and nursery grounds for herring (Figure 11.2), and spawning grounds and nursery grounds for sand eel (Figure 11.4). | Whilst these species are not designated features of the Marine Protected Area (MPA) network sites in proximity of the works, herring are a Section 41 species under NERC, and both provide prey resources for other receptors such as red-throated diver designated within the Outer Thames Estuary (OTE) SPA. | Potential resolution. This is subject to additional information being provided by the Applicant.
P14 | Sensitivity of identified species. | Natural England defers to the view of Cefas in determining the sensitivity of the species identified | We advise the Project seeks the advice of Cefas on the sensitivity of particular species and the appropriateness of the sensitivity assigned in the assessment. | Potential resolution. This is subject to the Applicant seeking advice from Cefas in this matter.
Marine Mammals – Appendix E
P15 | Interim Population Consequences of Disturbance (iPCoD) modelling/ | Natural England does not agree with the project-alone assessment of disturbance impacts from piling as we have concerns with how the results of the iPCoD modelling are presented. | Natural England recommends that the Applicant update how the iPCoD modelling results are presented in line with our comments and present impact significance for all approaches used to assess impact. | Potential resolution. This is subject to the Applicant providing updated assessment.
P16 | Habitats Regulations Assessment (HRA) conclusions. | We have significant outstanding concerns on the Environmental Statement (ES) assessment meaning we cannot currently agree with the outcomes of the RIAA as written. | We advise that the Applicant should address concerns on the ES and cascade the changes/commitments to the RIAA. | Potential resolution. This is subject to the Applicant addressing our concerns.
P17 | Current approach to Site Integrity Plans (SIPs). | Natural England is concerned that the current approach to implementing SIPs for piling impacts to the Southern North Sea (SNS) SAC from offshore wind development does not allow sufficient time for mitigation, therefore increasing the risk that an AEoI cannot be avoided. | We strongly advise that the Applicant commit to the use of specific mitigation measures at this stage, which may be removed at a later date if the revised SIP demonstrates they are not required. | Potential resolution. This is subject to the Applicant committing to the use of specific mitigation methods, particularly noise abatement systems (NAS).
P18 | No commitment to using Noise Abatement Systems (NAS). | Natural England strongly advises the Applicant to commit to using noise abatement as mitigation should driven or part-driven piles be used during construction. | The Applicant should commit to noise abatement in the Draft Marine Mammal Mitigation Plan (MMMP) and SIP. | Potential resolution. This is subject to the Applicant committing to the use of specific mitigation methods, particularly noise abatement systems (NAS).
P19 | Incorrect approach for the incombination assessment. | We note that the dose response method was applied to calculate the number of animals disturbed instead of using the Effective Deterrent Radius (EDR) approach as outlined in the Natural England Best Practice Guidelines. | Natural England recommends that the Applicant revises the incombination assessment and applies the EDR approach as per the Best Practice Guidelines. | Likely resolution. This is subject to the Applicant revising their approach to in-combination assessment.
Offshore Ornithology – Appendix F
P20 | Adverse Effect on Integrity for red-throated diver at the OTE SPA | The Applicant has concluded that there will be no AEoI RTD at the OTE SPA. Natural England does not agree with this conclusion. | We consider that the Applicant should demonstrate to the Examination that no further reduction in impact is possible whilst retaining a viable project | Unlikely.
P21 | Conclusion of no AEoI for kittiwake, guillemot, or razorbill at the Flamborough and FFC SPA for the project alone or incombination with other plans and projects. | Natural England agrees that the project-alone impacts arising for kittiwake, guillemot and razorbill are relatively small. Nonetheless, we consider that in each case, AEoI in-combination cannot be ruled out. | Natural England welcomes the provision of without-prejudice derogations cases for these species. | Unlikely.
P22 | No in-combination assessment for guillemot for the Farne Islands SPA. | There is the potential for effects from North Falls to combine with those from Berwick Bank and other North Sea projects. | The Applicant should carry out a full in-combination assessment of impacts for guillemot at the Farne Islands SPA, to allow Natural England to advise further regarding the risks of adverse effects in-combination. | Potential resolution.
P23 | The proposed cable route partially falls within the OTE SPA. | The timing of cable installation has not been confirmed, but due to the disturbance risk to RTDs posed by vessel movements Natural England considers that mitigation by seasonal restriction is appropriate. | Natural England strongly recommends that construction and decommissioning of the export cable (EC) should not take place within the OTE SPA +2km buffer during the sensitive over wintering period for RTDs of November to March inclusive. | Potential resolution.
Ornithology Compensation – Appendix G
P24 | Uncertainty regarding the current state of anthropogenic disturbance at southwest auk colonies FFC SPA guillemot and razorbill and its relative importance compared to other causal factors such as food availability and predation. | The lack of evidence presented on recreational disturbance at the southwest auk colonies referred to is of concern. We note the project may collaborate with other developments with similar compensation plans and are aware of some limited evidence gathering. | We urge collaboration, and a general scaling up of such evidence gathering with respect to both the existing breeding birds and any disturbing activities that may impact them. | Unlikely.
P25 | Flamborough and Filey Coast SPA: Kittiwake – Artificial Nesting Structure (ANS). | Uncertainty remains regarding the successful colonisation of the proposed ANS, and the mechanism for assigning benefits arising at the ANS between the partnership OWF projects. | We recommend that a compensation ratio of 3:1 be adopted to address the range of uncertainties. We would also welcome confirmation as to whether a colour-ringing scheme could be undertaken at the “Kittiwakery” to track natal philopatry there (and recruitment elsewhere) for the purposes of establishing site connectivity with, and overall coherence of, the national site network. | Unlikely.
P26 | Alde-Ore Estuary SPA: Lesser Black Backed Gull – Breeding enhancement via predator exclusion/control/disturbance management/habitat management | None of the sites under consideration have been secured yet, and further work is needed around defining success according to the ratio of impact to observed productivity and assumed level of consequent recruitment. | We consider further work is required around defining success according to the ratio of impact (which may be subject to change within the impact assessment) to observed productivity and assumed level of consequent recruitment. | Uncertain.
P27 | OTE SPA: RTD - Installation of nesting rafts and/or habitat management to improve breeding success (or data collection to support development of sanctuary areas in the OTE SPA). | There is an acknowledged mismatch between the expected benefits (increased productivity) and the impact (habitat loss/degradation). We are not persuaded that the Applicant is proposing implementation of the measure at an appropriate scale. | We recommend that a more ambitious approach to the compensatory measure is adopted. The potential forsignificant benefits to accrue in support of the coherence of the NSN should be demonstrated. | Potential resolution.
Onshore Ecology – Appendix H
P28 | Timing of onshore surveys. | Where the timing of the characterisation surveys hasn’t been optimum Natural England’s overall confidence in mitigation proposals for protected species has been reduced | Natural England advises that preconstruction surveys should be undertaken at the optimum time of year as per the relevant guidelines for each species, to ensure that mitigation measures remain fit for purpose. | Likely. This is subject to the Applicant securing the advised commitment.
P29 | LBBG Compensation HRA. | Natural England highlights that the LBBG Compensation HRA document is relatively high level, and we have concerns around the timing of characterisation surveys to support conclusions | Natural England advises that there will need to be a further HRA that is location specific, once the final location is selected post consent. Additional environmental information will also be required to support characterisation surveys which have been carried out in the correct period. | Potential Resolution. This may also be dependent on collaboration with Five Estuaries.
P30 | Disturbance associated with users of King Charles III England Coast Path (ECP). | Natural England advises that there are possible disturbance and visual impacts for users of ECP depending on timing of opening of ECP. | We require information relating to any impacts, in addition to any restrictions required and impacts on the line of the path. | Likely. This is subject to the Applicant providing updated information, and assessment.
Seascape, Landscape and Visual Impact Assessment – Appendix I
P31 | Alone and in-combination impacts. | Natural England is concerned that North Falls Offshore Wind Farm (OWF) has the potential to significantly impact the special qualities of the Suffolk Coast and Heaths Area of Outstanding Natural Beauty (SCHAONB) and Suffolk Heritage Coast (SHC), in particular when acting cumulatively with other existing, consenting and proposed OWF projects. | Natural England will provide further detail at Deadline 1. | Uncertain.
P32 | Outer limits of significance for Seascape, Landscape and Visual Impacts (SLVIA) receptors. | Natural England is concerned that the significance of the impacts on receptors might have been underestimated. | Natural England will provide further detail at Deadline 1. | Uncertain.
Landscape and Visual Impact Assessment – Appendix J
P33 | Cumulative effects between VE and North Falls substations. | Natural England is concerned that there is a potential for incombination/cumulative impacts between this project, North Tilbury, and the VE substations. | We advise that potential incombination/cumulative impacts between North Falls, VE, and Norwich-Tilbury substations should be fully considered and assessed, when/if further evidence is available. | Uncertain.

## A - DCO
Point | Point Number(s) from Appendix A [RR-243] | Taken from Natural England’s Relevant and Written Representations North Falls OWF Appendix A - DCO | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | A1 | The during construction monitoring conditions within the deemed Marine Licences (dML) Schedules 8, 9 and 10 do not secure that piling must cease in the event the monitoring highlights the noise impact is significantly in excess of the predicted impacts assessed.
2 | A2 | Schedule 15 compensation only covers impacts to Lesser Black Backed Gull (LBBG). We cannot advise that an Adverse Effect on Integrity (AEoI) on the Flamborough and Filey Coast (FFC) Special Protection Area (SPA) can be excluded. Provision for compensatory measures for the relevant features should be included in the draft DCO on a without prejudice basis.
3 | A4 | Natural England recommends that the Applicant considers an amendment to the DCO to include the maximum volumes of drill arisings within the requirements and both dMLs.
4 | A5 | We would expect the landscape requirements to also cover survey methods, monitoring requirements and the requirement to maintain, including the potential for replanting due to plant failures. Further, we would expect to be consulted on these plans prior to their approval by the relevant Local Planning Authority (LPA).
5 | A6 | Natural England requests the text be amended to include a requirement to consult the relevant Statutory Nature Conservation Body (SNCB) on the Code of Construction Practice (CoCP) and recommends that the requirement should note the final CoCP must accord with the outline CoCP.
6 | A7 | Natural England requests that the relevant SNCB be included as a required consultee. We also note that based on the wording here, and the interpretation of onshore commencement, clearing works could be conducted prior to the submission and approval of the final Ecological Management Plan (EMP). This provision should be amended to state that no pre commencement clearance works should be undertaken until a written EMP, as relevant to the stage of the works, has been submitted to, and approved by, the LPA following consultation with the relevant SNCB.
7 | A8 | The requirement to provide a soil management plan does not include a requirement to consult the relevant SNCB. The requirement should be amended.
8 | A9 | The relevant SNCB is not listed as a consultee on the Biodiversity Net Gain (BNG) strategy, given the nature of this plan we would request consultation on this document. Further we note that no time period is given for the duration of which the strategy should be monitored, maintained or when adaptive management measures may be implemented. The requirement should ensure the strategy is enforced for a period of thirty years, or for the lifetime of the development.
9 | A10 | Due to the need to appropriately consider in-combination impacts of other developments it is important that the Site Integrity Plan (SIP) should not be submitted too early. Natural England advises this condition should be amended to give an individual timing requirement to be submitted no sooner than 9 months and no later than 6 months prior to commencement of piling.
10 | A11 | Natural England notes that the monitoring conditions only cover benthic monitoring. Ornithological and marine mammal monitoring should also be requirements due to the potential for impact.
11 | A12 | This condition does not include the requirement to pause piling in the event that noise is significantly in excess of that predicted and for potential further monitoring. These are a key mitigation for noise impacts to sensitive species and should be included as a standard.
12 | A13 | Natural England notes that this condition does not have provision for marine mammal monitoring. Further, we note the recent SoS decision for SADEP approved the following recommendation from Natural England and the Marine Management Organisation (MMO) for particular impacts requiring remediation or further mitigation works in the event of impacts being greater than predicted. Natural England requests that a similar condition is included within all dMLs.
13 | A14 | All comments provided on Schedule 8 apply to Schedule 9 and 10 where similar provisions apply.
14 | A15 | Natural England notes that nowhere within these dMLs does there appear to be any requirement to notify the MMO with regard to which build option has been chosen. As Five Estuaries is still in examination we would recommend consideration for both projects to capture a requirement to co-ordinate on the onshore cable works. We recommend consideration of including provisions for co-operation and for notification to the MMO as offshore enforcing body of the build option selected.
15 | A16 | Natural England notes that compensation provisions have been provided for LBBG only. We have advised that compensation is required for other ornithological and benthic features, specifically kittiwake, guillemot and razorbill at Flamborough & Filey Coast Special Protection Area (SPA). The compensation schedule should be updated to cover all sites where there is currently disagreement regarding an adverse effect on site integrity.
16 | A17 | All references to Natural England within this schedule should be amended to the ‘relevant SNCB’ to ensure consistency with the rest of the DCO.
17 | A18 | The Offshore Ornithology Engagement Group appears similar to the steering groups used on other compensation provisions. However, the condition does not include the need to provide and consult upon; terms of reference for the group, details of proposed meetings, timetable for the preparation and delivery of the LBBG Compensation Implementation and Monitoring Plan (CIMP), or a dispute resolution mechanism.
18 | A19 | Natural England notes the wording here is confusing as it implies that compensation may be delivered through some other unknown, or undetailed, mechanism and thus the compensation within this provision may not be required. We recommend amending this provision and consideration of how to appropriately implement a provision allowing strategic compensation options. This could also be applied to other compensation schedules provided on a without prejudice basis.
19 | A20 | The list of requirements to include in the CIMP is lacking in detail when compared to similar provisions. Within (d) we would expect to see survey methodologies, timetables for the monitoring to be conducted and reports delivered and success criteria. Within (g) we would expect to include a detailed mechanism to determine the need for any alternative compensation or adaptive management measures, along with potential further monitoring and maintenance of such measures.
20 | A21 | We note this requirement ensures that LBBG compensation must be provided three full breeding seasons prior to operation. Natural England recommends the Applicant amends the condition to reflect four full breeding seasons in line with compensation requirements for other projects.
21 | A22 | The compensation may be required for longer than the lifetime of the project and so should be maintained until the SoS approves its decommissioning in consultation with the relevant SNCB. Natural England recommends the Applicant amends the provision to require the approval of the SoS and consultation with the SNCB.
22 | A23 | The Outline Offshore Operations and Maintenance Plan should be amended to reflect the dML conditions that ensures cable protection should only be deployed up to ten years following completion of construction. We recommend this document be updated to avoid any confusion post consent.
23 | A24 | It would be helpful if the Outline Operations and Maintenance plan could specifically set out O&M activities so it can be read as a standalone document.
24 | A25 | The replacement or addition of scour protection around foundations for the lifetime of the project (Page 13) doesn’t align with comments made in the DCO and/or the Benthic Appendix.
25 | A26 | This plan doesn’t really align with the Cable statement [APP-262] and we advise that this is addressed by the Applicant.
26 | A27 | Natural England notes the Schedule of Mitigation and [APP-262] Cable Statement are not a named documents in the DCO, Natural England considers these documents should be certified under the DCO. Further, the use of terms such as ‘where practicable’ throughout the document cause concern because listing out mitigation doesn’t mean it is achievable and/or that there is commitment to do it. In addition, there is no detail to demonstrate that by undertaking the mitigation it will sufficiently minimise impacts to acceptable levels. We advise that this document is updated to clarify what is/isn’t committed to by the Applicant.
27 | A28 | There is reliance by the Applicant on monitoring as a form of mitigation, which it is not. We advise that all references to monitoring other than to test the effectiveness of mitigation measures are removed from the schedule.
28 | A29 | Natural England highlights that the document [APP-262] Cable Statement is currently overly simplified and too high level and that it is not clear how this plan aligns with the other named plans and document. Reliance on these documents alone as set out in the documents purpose could cause key commitments to not be implemented. Natural England would welcome further clarification from the Applicant on how the plans work together, and further detail being included within the document.
29 | A30 | Natural England advises that an Outline Decommissioning Plan as requested for all other OWF NSIP applications is provided at the time of consent to ensure that decommissioning is achievable and environmentally sensitive.

## B - Marine Processes
Point | Point Number(s) from Appendix B [RR-243] | Taken from Natural England’s Relevant and Written Representations North Falls OWF Appendix B - Marine Geology, Oceanography and Physical Processes | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | B1 | There is uncertainty regarding the likely success of subtidal Horizontal Directional Drilling (HDD) at the landfall point. Geotechnical/expert evidence in support of HDD should be presented. Otherwise an alternative WCS should be presented as a contingency.
2 | B2, B10 | There is uncertainty with the (realistic) WCS parameters for seabed level changes during construction from deposition. Further consideration and assessment of WCS for seabed level changes due to the different seabed preparation and construction activities is required, including sediment deposition thickness, extent, and persistence.
3 | B3, B16, B30, B31, B32 | (a)There is uncertainty regarding the wave and current modelling and a lack of information regarding seabed mobility and seabed erosion/deposition. As a result, we are currently unable to support the impact assessment conclusions relating to sediment transport processes and scour development at KKE MCZ and Annex I sandbanks. (b) Equally further consideration of bed shear stress changes and the sediment erosion/deposition potential within and adjacent to the array through the different phases for the Project alone and cumulatively with other nearby Offshore Wind Farms (OWFs) is required due to uncertainties.
4 | B4, B16, B26 | (a) Further detail on bedform mobility, morphology, stability and longevity to support the predictions of sandwave recovery is required. Anticipated location(s) of sandwave levelling should inform this. (b)Pre- and post-construction surveys should be secured in the Development Consent Order (DCO) and/or In-Principle Monitoring Plan (IPMP) to demonstrate sandwave recovery (as predicted) and ensure remedial measures will be undertaken if impacts are found to be greater than predicted.
5 | B5, B28 | Further information on the anticipated location and extent of cable protection near MLS SAC is required to demonstrate that adverse impacts to the SAC due to disruption of sediment transport pathways operating around the northern boundary and seabed morphology can be excluded. The assessment should consider total amounts of cable protection proposed across the different project phases. Please also refer to B13.
6 | B8, B28 | North Falls acknowledge that cable protection on the seabed would represent the WCS at HDD exit pits and along the intertidal cable route. Natural England is unable to agree with the Applicant's negligible significance assessment of this impact. Further clarity is require on whether rock berms for cable armouring are proposed within the intertidal, If that is the case then further investigation of potential disruption to longshore drift and the potential to impact overlapping designated sites downdrift is required.
7 | B11, B29 | Sediment deposition from sandwave levelling could led to an order of magnitude difference in seabed height which could have significant implications for sensitive receptors, such as spawning fish, benthic ecology. The significance of which will be influenced by the persistence of the mound. Further evidence from adjacent OWFs of mound persistence/redistribution and thickness should be provided to support conclusions.
8 | B12, B29 | The WCS for foundation installation requiring drilling is 10% of 34 Wind Turbine Generators (WTGs) and one Offshore Substation Platform (OSP)/Offshore Converter Platform (OCP). The rationale for this WCS is unclear. The anticipated location where drilling may be required for foundation installation has not been provided. It is also stated that aggregated mud clasts within drill spoil mounds would mostly remain static. Conversely, it is also stated that over time the mound would gradually winnow away and lower through erosion. Further clarity on WCS for persistence of drill arisings and their location is required, before we can advise on the scale and significance of changes to marine process and potential impacts to sensitive receptor from the presence of the arisings.
9 | B13 | (a) Currently the project design allows for additional cable protection allowance for both the array and platform interconnector cables (20% of the length) and the offshore export cable length (10% of the length). Further information is needed regarding the rationale as to why cable protection is needed given the alternatives, the amounts required and how they have been minimised, and their anticipated placement location demonstrating there is no overall increase in footprint, before we can advise further on potential scale and significance of the impacts. (b) Standard quantities of additional scour and/or cable protection replenished outside of benthic SACs should be committed to namely 10% of any scour prevention/cable protection laid during installation within a 10-year period only with a requirement for further marine licence beyond that.
10 | B14, B28 | It is stated that currently “the exact number of crossings are still being confirmed.” Therefore, the WCS for the number of cable protection needed at crossings is unclear. A map should be provided identifying the location of cable crossings offshore, including designated sites and sensitive receptors. And assessments updated accordingly.
11 | B11, B15 | The calculation of drill arising mound footprint is based on a mound height ‘fixed’ at the equivalent average height of the naturally occurring sandwaves on the seabed within the site i.e. 2m high. We believe that this figure could be higher at certain locations. Further clarification as to why this has been fixed as the WCS height for the drill arising mound should be provided and assessments updated.
12 | B17 | It is stated that current speeds will return to baseline conditions with progression downstream of each foundation and generally will not interact with wakes from adjacent foundations. It is also stated that these effects will be relatively small in magnitude and local. However, we are unable to agree until the WCS spatial extent of turbulent wakes have been evaluated to inform the impact assessment.
13 | B18 | Link to several points in the R&I long the Applicant should consider and address the following evidence gaps and update the assessments within the Environmental Statement (ES) chapters accordingly. • Up to date sediment transport pathways at the array and indication of sediment transport rates • Site-specific wave measurements for model calibration (within or close to the array) • Characterisation of significant bedforms along the OECC and within/adjacent to the array. • Seabed mobility/susceptibility to scour.
14 | B19, B20, B30 | There is insufficient evidence to support the conceptual approach is appropriate taken for tidal currents and sediment transport characterisation at North Falls. Further evidence/information is needed to demonstrate that the GWF, GGOW and VE modelling results are directly applicable to the conditions prevailing at North Falls. Additionally, Natural England advises further justification is needed for the conceptual approach that has been used.
15 | B21 | Wave measurements have not been gathered at the North Falls site for model validation. The data used for calibrating the wave model were collected at West Gabbard 2 and South Knock wave buoys. The model was calibrated against a range of past significant storm events, but some were underpredicted. Therefore, the modelled data may not accurately describe the baseline wave climate. Further evidence should be provided to demonstrate that the wave model data are representative of the present-day conditions at the project site.
16 | B22 | Currently there is a lack of information regarding seabed mobility and seabed erosion/deposition potential to allow us to agree with the assessment conclusions in terms of impacts to bedload transport and secondary scour due to the placement of cable protection in the array. The seabed mobility and seabed erosion/deposition potential need to be considered and assessed. Full consideration should be given to these impacts over the course of the Project and beyond. We also advise that every effort should be made to minimise the placement of external cable protection, particularly on Annex I sandbanks or adjacent to KKE MCZ where it may interrupt sediment transport pathways and affect seabed morphology. Please also refer to our advice in NE Ref B5 and B13 relating to impacts from cable protection
17 | B23 | An estimated 177 major component replacement activities are proposed per year (using jack-up vessels and/or anchoring). This is a significant number of component replacements, and no rationale has been provided for the WCS. Natural England advises that further justification is needed of this WCS
18 | B24 | The potential for temporary physical disturbance associated with Operations and Maintenance (O&M) vessels has only been considered for Annex I sandbanks in the array area. Furthermore, it is stated that all other receptors are beyond the Zone of Influence (ZoI) for this impact. Does this exclude potential impacts to the nearshore. Further clarification is needed that indentations to the seabed due to O&M vessels (and Unexploded Ordnance (UXO)clearance) are not anticipated in the nearshore zone.
19 | B25 | It is suggested that the magnitude of decommissioning impacts would be comparable to or less than those identified for construction. However, the following should be used to inform an outline decommissioning plan to inform the consent: • Potential lasting impacts to the marine physical environment and processes of any assets left in situ; and • Emerging alternatives to decommissioning such as repowering and life extension. Natural England advises that the Applicant should consider emerging alternatives to decommissioning and secure any associated monitoring in the outline decommissioning plan.
20 | B27 | It is stated that the receptors potentially affected by the cumulative change in sediment transport during operation will not experience a significant cumulative effect. However, the extent of cumulative change has not been quantified. This is important for understanding the implications of the predicted cumulative change over the lifetime of the Project at KKE MCZ and Annex I sandbanks. The cumulative change in sediment transport should be quantified and the implications to KKE MCZ and the Annex I sandbanks over the lifetime of the Project assessed.
21 | B29, B31 | The tolerance, adaptability, recoverability, and sensitivity to changes in seabed level due to foundation installation, have been assessed as ‘negligible’ for KKE MCZ. This ‘negligible’ conclusion is contradictory to Table 8.17 [APP-022] which shows that the near-field magnitude of impact is ‘medium.’ Given the proximity to KKE MCZ, presence of potentially sensitive species within the array, uncertainty regarding the WCS sediment deposition thickness and insufficient supporting site-specific evidence, we unable to agree with the conclusions of the impact assessment. Further clarification and supporting evidence are required regarding the WCS sediment deposition height to inform the impact assessment for KKE MCZ.

## C - Benthic Ecology
Point | Point Number(s) from Appendix C [RR-243] | Taken from Natural England’s Relevant and Written Representations North Falls OWF Appendix C - Benthic Ecology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | C1, C13, C38 | Further information is required to provide the necessary confidence in the Worst-Case Scenario (WCS) for cable protection requirements adjacent to Margate and Long Sands SAC, and the remaining cable route, over all project phases.
2 | C2, C33, C35, C37 | Due to uncertainty (reasonable scientific doubt) in relation to consideration of in direct impacts on MLS SAC, we cannot advise the exclusion of an Adverse Effect on Integrity (AEoI). A more detailed assessment of the likely nature and scale of impacts as a result of changes to physical and biological process following the placement of infrastructure is required. Consideration should also be given to the condition assessment for MLS SAC.
3 | C3, C20, C33, C37 | Pressures/impacts on supporting benthic habitats and prey availability for Special Protection Area (SPA) features including the Outer Thames Estuary SPA (OTE SPA) red-throated diver populations require full consideration including nature, extent, duration, and significance of impacts.
4 | C4, C33,C 37 | Further mitigation measures are required for all relevant Section 41 NERC Habitats. Natural England advises that, where possible impacts to all Section 41 NERC Habitats are avoided particularly where such habitats support rare and/or irreplaceable communities.
5 | C5, C31, C33, C37, C49, C50 | (a)Sediment deposition upon benthic features within Kentish Knock East MCZ (KKE MCZ) requires a more robust assessment regarding the anticipated worst-case sediment deposition parameters due to sandwave levelling/ seabed preparation activities in the vicinity of KKE MCZ. (b) Natural England advises that commitments should also be made and secured to avoid indirect impacts on designated features.
6 | C6, C44, C50 | Further clarification/evidence is required to demonstrate that an appropriate buffer has been applied around the infrastructure closest to the KKE MCZ boundary to ensure that direct impacts from wake effect, scour, etc. and in direct effect effects from changes to marine process will not impact on the interest features of the MCZ. Without the application of a suitable buffer, there is a risk that proposed mitigation does not sufficiently avoid impacts to the MCZ.
7 | C7, C32, C41 | (a)WCS is based on use of external cable protection in the form of rock protection, but due consideration has not been given to the use of the mitigation hierarchy and reducing/mitigating the impacts as much as possible through the choice of cable protection especially in regard to removal at the time of decommissioning. (b)An Outline Decommissioning Plan should be provided at the time of consent to ensure that mitigation measures requiring the removal of cable protection are achievable and secured. See Point 11 for more detail
8 | C8, C32, C48 | Further mitigation measures could be adopted by the Applicant to avoid, reduce, and minimise the project’s environmental impacts, including (but not limited too) reducing the Rochdale envelope to limit the types of cable protection and foundations to be used on the project.
9 | C9, C19 | There is currently no commitments relating to the minimum water depth at which the HDD exit pit location is placed. Recognising that rock protection is usually required at the exit pit location, a commitment to no rock protection landward of 10m LAT is required to mitigate potential impacts to bedload transport and any associated changes to benthic ecology along the Essex coastline.
10 | C10, C41 | The Applicant has not committed to using any specific type of cable protection, and has not considered the limitations of some methods, particularly given the potential for pathways of effect to supporting processes within Margate and Long Sands SAC whilst cable protection is in place. Due consideration should be given to the nature of the cable protection included in the project design envelop and should favour those engineering options with the greatest likelihood of successful removal at decommissioning. Unless it can be demonstrated otherwise, the scale of impacts from cable and scour protection that have been described by the Applicant have the potential to hinder the ‘maintain’ conservation objective.
11 | C11 | An outline decommissioning plan should commit to the removal of all surface laid infrastructure at the decommissioning stage. We agree with the Applicant’s assessment approach which considers that, in the continued absence of any commitments to remove specified amounts of infrastructure, including cable protection, assessments should be based on a worst-case scenario of lasting/permanent impacts under all infrastructure.
12 | C12 | (a) Natural England advises that there is insufficient detail on the proposed activities relating to the potential placement of additional scour prevention/cable protection measures over the operational lifetime of the project.(b) Further detail should be provided on the parameters for O&M activities including how total amounts have been determined, and where those amounts are likely to be placed relative to sensitive areas of seabed, such as Margate and Long Sands SAC. (c) Standard for quantities of additional scour and/or cable protection outside of benthic SACs should be committed too for the replenishment of 10% of any scour prevention/cable protection laid during installation within a 10-year period as long as the overall footprint is not increased.
13 | C14 | There is insufficient evidence regarding ground conditions to rule out HDD failure potentially requiring trenching and/or rock protection within the intertidal. If this was to occur, it could alter the significance and nature of predicted impacts on intertidal and benthic receptors including designated sites/features. Further evidence is required to provide sufficient confidence that the HDD will be successful, and that the current WCS prediction of impacts from HDD in the ECR on intertidal and subtidal habitats is realistic.
14 | C15, C26, C29, C31 | (a) in the absence of confirmed dredge disposal locations, or parameters to determine the dredge disposal location criteria, then it is not possible to determine the WCS and, therefore, robustly assess the impacts from sandwave levelling activities. (b)Commitments should be made to minimise impacts from sediment deposition.
15 | C21 | There is a risk of potential loss of backfill material loss at the subtidal HDD exit pits and therefore recoverability of any remaining trench/depression, which then may warrant the requirement for cable protection. At para. 39 of the Cable Statement engineered backfill is referred to, but no further information is provided on this. Further detail is required to better understand the likelihood of side cast sediment being lost, the quantities and the potential requirement for permanent cable protection over the lifetime of the project.
16 | C22, C51 | Further clarification on how impacts from vessels associated with landfall activities have been assessed including use of anchor barge and/or jack up barges and whether there will be any requirement for stabilisation pads and/or medium/long term impacts.
17 | C23 | The Applicant proposes that that whole of the red line boundary becomes a disposal location. However, as set out in Appendix C of our RR/WR [RR-243] we do not currently agree with the impact assessment for which site characterisation for sediment disposal is reliant upon. Further agreement on the MDS and WCS and evidence is required to support statements.
18 | C24 | Application documents should be updated to address the ambiguity between the various Application documents as to the WCS footprint of any rock berm. Based on other OWF project assessments we query if a width of 6m is realistic?
19 | C25 | Neither of the terms ‘temporary’ impacts or ‘rapid’ recovery of benthic habitats have been fully defined for relevant identified pathways of effect. An evaluation of the extent and duration of impacts on benthic habitats should be more explicitly stated in order to provide a transparent understanding of the likely impacts and recovery duration of benthic receptors, both alone and cumulatively, so that effects on designated mobile species in particular can be assessed.
20 | C27, C26, C33, C37 | The proposed mitigation within the EIA and subsequent[APP241] 7.6 Outline Project Environmental Management Plan would benefit from appropriately considering the importance and rarity of peat and clay exposures, and every effort should be made to avoid impact (particularly permanent loss) to these priority habitats where possible through mitigation measures such as micro-siting.
21 | C28 | The Applicant has included a Sabellaria spinulosa management plan at Appendix A of the PEMP. However, some of the included management measures will not be able to be implemented. The use of a core reef approach should be excluded from the PEMP.
22 | C30 | The use of dredge sediment as ballast/coastal protection/aggregates is not preferable from a nature conservation perspective. Sediment should remain within the sediment system it was removed from to best enable seabed to return it to pre-impacted state.
23 | C31 | Within the cable statement consideration should be given to mitigation measures for seabed preparation especially in relation to boulder relocation close to designated sites and near shore to ensure that sediment transport is not disrupted.
24 | C32 | In addition to points 2 and 15 further information from the Applicant is required to confirm what cable protection parameters (length and specific placement location in relation to the SAC) have been used to inform the assessments and what the accurate worst-case scenarios are with appropriate justification provided where relevant. The RIAA and relevant ES should be updated with this information
25 | C39 | The ES and RIAA in-combination assessments may require updating once further information has been provided on the worst cable rock protection requirements and any related secondary impacts within the SAC.
26 | C45 | The MCZ assessment fails to screen in or appropriately consider the potential for sediment deposition within the benthic features of Kentish Knock East MCZ (KKE MCZ), despite paragraph 72 stating that ‘sediment deposition’ is predicted as an indirect effect. In the absence of a confirmed dredge disposal locations, or parameters to determine the dredge disposal location criteria, it is not possible to determine the WCS and therefore robustly assess the impacts from foundation preparation/sandwave levelling activities upon KKE MCZ benthic features.

## D - Fish and Shellfish Ecology
Point | Point Number(s) from Appendix D [RR-243] | Taken from Natural England’s Relevant and Written Representations North Falls OWF Appendix D - Fish and Shellfish Ecology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | D1 | We advise that Natural England’s comments are read in conjunction with the advice of Cefas, however it should be noted that Natural England’s remit differs to that of Cefas with regard to fish and shellfish ecology.
2 | D2 | We note that there is overlap with spawning grounds and nursery grounds for herring (Figure 11.2), and (Figure 11.4). We note that Table 11.14 incorrectly suggests “Spawning grounds of Downs Herring located in areas adjacent to the southern array area,” as opposed to directly overlapping with it. We highlight that whilst these species are not designated any designated sites in proximity of the works, herring are a Section 41 species under the NERC Act 2006, and both provide prey resources for other receptors such as RTD designated within the Outer Thames Estuary SPA.
3 | D3 | Natural England defers to the view of Cefas in determining the sensitivity of the species identified. It is important that the ecology of each individual species is taken into account when determining potential impacts upon them. Increased Suspended Sediment Concentration (SSC) and subsequent deposition of sediment on gravid herring and their eggs and larvae should be considered in relation to the Downs Herring spawning area. In relation to temporary increase in SSC and deposition please note our comments on the marine processes chapter. Where there is overlap with the Downs spawning area, we do not agree that habitat loss will be temporary, In relation to long-term habitat loss, we advise this is permanent rather than long-term. We advise the Applicant seeks the advice of Cefas on the sensitivity of particular species, and the appropriateness of the sensitivity assigned in the assessment. When agreement is reached on the marine processes chapter, and the further characterisation work suggested by Cefas has been carried out, Natural England would welcome the opportunity to comment on an updated assessment in relation the herring and sand eel. We advise that the further baseline work as advised by Cefas is required to further understand the potential direct loss of spawning habitat, which where infrastructure is placed is likely to be permanent.

## E - Marine Mammals
Point | Point Number(s) from Appendix E [RR-243] | Taken from Natural England’s Relevant and Written Representations North Falls OWF Appendix E - Marine Mammals | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | E1, E14 | The impact significance should be presented based on each approach taken to assessing disturbance, not just based on the iPCoD modelling. We cannot agree with the assessment conclusions of the project-alone disturbance effects at this stage. We further recommended that they commit to further mitigation of project-alone impacts, should they be significant.
2 | E2 | As we have significant outstanding concerns on the Environmental Statement (ES) assessment, where the same approach is applied to Habitats Regulations Assessment (HRA), we cannot agree with the HRA conclusions at this stage. We advise that the Applicant should address concerns on the ES and cascade the changes/commitments to the HRA.
3 | E3, E38 | Natural England is concerned that the current approach to implementing Site Integrity Plans (SIPs) for piling impacts to the Southern North Sea (SNS) Special Area of Conservation (SAC) from offshore wind development does not allow sufficient time for mitigation methods, such as Noise Abatement Systems (NAS) to be procured by the Applicant prior to construction, should they be required, therefore increasing the risk that an Adverse Effect on Site Integrity cannot be avoided. We strongly advise that the Applicant commit to the use of specific mitigation measures at this stage, which may be removed at a later date if the revised SIP demonstrates they are not required.
4 | E4, E26 | We note that the Applicant has not committed to using NAS at this stage. Natural England strongly advises the Applicant to commit to using noise abatement as mitigation should driven or part-driven piles be used during construction. The Applicant should commit to noise abatement in the Draft Marine Mammal Mitigation Plan (MMMP) and Site Integrity Plan. The effect of noise abatement systems in reducing noise impacts should be included in the assessment.
5 | E6, E34 | We note that the multiple piling scenario includes simultaneous piling at East and South locations as the worst-case scenario (WCS). Natural England has concerns that the WCS no longer includes the North and South locations, as described in pre-application documentation, resulting in a reduction in the estimated number of impacted animals. Natural England highlights that the multiple piling scenario should include the combination of locations that produces the greatest estimates of impacted animals in order to constitute an accurate WCS. Natural England advises that the Applicant should re-calculate the simultaneous piling assessment based on the two locations that produce the WCS.
6 | E7 | A cut-off date for the inclusion of projects int he CEA of January 2024 is too far back since new data has been produced by other developments in recent months. We recommend that the Applicant extends the cut-off date to include up-to-date information from other OWFs into the CEA.
7 | E8 | We note that the density of harbour seal used in the assessment has significantly reduced between the Preliminary Environmental Information Report (PEIR) and the Application, from 0.0014 to 0.00048, respectively. Natural England seeks clarification in regard to the change in harbour seal densities. We would like to emphasise that the most precautionary density needs to be taken forward to the assessment. Please refer to our advice in the Best Practice Guidance Phase III. Natural England advises that the Applicant should revise the assessment so that it uses the agreed harbour seal density as presented in the PEIR or provide a sufficient justification for the change in the densities.
8 | E9 | The Applicant has assumed that other sources of noise during construction would operate constantly for 24 hours, instead of 12 hours per day as assumed in the PEIR. However, Natural England notes that for a fleeing animal, Temporary Threshold Shift (TTS) impact ranges of activities are now shorter than the ones predicted in the PEIR. It is unclear why an increase in the duration of an impact leads to a decrease in its impact range. Natural England advises that the Applicant revises the calculations of impact ranges and updates tables as required.
9 | E10 | There is a discrepancy in the assigned sensitivity to collision risk i.e. minke whale has been assigned medium compared to low sensitivity for other marine mammals. There is not a sufficient justification for this approach. We advise that sensitivity to collision risk should be medium for all species due to the potential severity of the impact resulting in injury or death of the animal. We advise that the Applicant changes the sensitivity of all species to collision risk to medium and updates the assessment.
10 | E11 | We consider that it is unclear how the number of marine mammals at risk of collision with North Falls’ vessels was calculated. We request that clarification be provided on how the number of marine mammals at risk due to increase in vessel number has been calculated.
11 | E12 | Natural England does not agree that sensitivity of seal species to disturbance effects is low. Whilst there may not be as much evidence for this species group, it would be precautionary to consider them as having medium sensitivity. We advise the Applicant should change the sensitivity of seal species to disturbance to Medium and revise the assessment.
12 | E13 | The values presented in Table 12.99 in the median impacted as a percentage of unimpacted column of this table do not correspond to the difference between the unimpacted population mean and the impacted population mean. We advise that the difference between the two presented means is included in the table, alongside the median values. The Applicant should provide information to support the value they consider to be most appropriate. Note this comment applies to all tables which present the iPCoD modelling results.
13 | E17 | Natural England does not agree that all projects with unknown construction timelines should be screened out. We consider that it would be precautionary to assume that construction for consented projects could overlap with the project if an operational date is known (as presented in Table 1.2 and is similar to the North Falls project’s operational date). Natural England advises that the Applicant should include the projects with similar operational dates in the CEA.
14 | E18 | Natural England does not agree that Permanent Threshold Shift (PTS) should be screened out of the CEA. The Project has identified a major adverse effect from piling (APP-026, Table 12.24) that the Applicant has not committed to fully mitigate at this stage. We advise that the Applicant should assess cumulative PTS impact in the CEA or fully commit to sufficient mitigation to reduce the risk of a residual PTS impact.
15 | E19 | Natural England defers to CEFAS as the underwater noise specialists to comment on the Underwater Noise Modelling Report. To note.
16 | E21 | A site Integrity Plan (SIP) will be required due to the number of noisy activities planned within/adjacent to the Southern North Sea (SNS) SAC in order to reduce disturbance to harbour porpoise. We advise that the Applicant should revise the conclusion on the requirement of a SIP.
17 | E22 | Natural England disagrees with the conclusion that no mitigation measures will be required to minimise any potential disturbance due to UXO clearance especially as this assessment does not include in-combination effects. Appropriate measures should be considered within the SIP when final project and UXO details are known. The Applicant should revise the conclusion that no mitigation measures will be required to mitigate the disturbance due to UXO clearance.
18 | E23 | The Applicant established a Monitoring Area with a minimum 700m radius, and this area will be monitored both visually and acoustically. However, there are limitations of both methods for detecting harbour porpoises. Thus, the Applicant consider ways to improve detectability of harbour porpoises in order to guarantee their detections within the Monitoring Area. Natural England is happy to discuss any other options at a later stage so they can be incorporated within the Final MMMP. We advise further consideration of options for effective monitoring of harbour porpoise within the Monitoring Array of minimum 700m and an updated MMMP be submitted prior to the end of examination.
19 | E24 | Natural England advises that, for clarity and completeness, a separate section on the procedures in the case of marine mammal detections should be included in the MMMP for all possible scenarios. Currently, this information is included under the section ‘1.3.2.1.1 Marine Mammal Observers’ We advise that the Applicant includes a separate section within the MMMP on the procedures that should be followed when marine mammals are detected within the Monitoring Area.
20 | E25 | We note that, for clarity and completeness, it should be clearly stated that “for any breaks in piling of less than 10 minutes, piling may continue as required (i.e. as if there was no break)” as long as no marine mammals have been detected within the Monitoring Area during this time. We advise that the Applicant should add the mention of no marine mammal detections during the breaks in piling within this section.
21 | E27 | There is a lack of commitment to some of the mitigation measures listed for the UXO clearance. We would like to emphasize that the UXO clearance should be performed during suitable conditions for both MMObs and PAM operators. We advise that the Applicant should refer to the new UXO guidance and mitigation guidelines that were published in January 2025 as part of the Defra Marine Noise Package. Please refer to our Deadline 1 cover letter for further information.
22 | E28 | It is stated that the ramp up would be a minimum of 30 minutes. This is not in line with the worst-case scenarios outlined in Chapter 12 (Table 12.1) where it is stated that ramp up would be a minimum of 80 minutes. Consistency is required to implement mitigation measures. Natural England suggests that the MMMP should be consistent regarding the chosen duration of ramp up.
23 | E29 | Natural England does not agree with the statement made in paragraph 829 that marine mammals “get accustomed” to the presence of vessels. Also, paragraph 830 states that vessels, once on-site, would be stationary or slow moving, and therefore the potential for disturbance would be minimal. However, this is not the case for maintenance vessels which use maximum power to keep their position next to a turbine. Natural England advises that the Applicant re-assesses the effect of vessel presence on marine mammals following up to date evidence-based findings.
24 | E30 | Natural England notes, the In-Principle Monitoring Plan (IPMP) should examine the assumptions made within the marine mammal assessment and identify monitoring that seeks to validate one or more of these. Consideration should be given to the areas of the assessment where assumptions have been made and where the project could contribute to filling knowledge gaps that would inform validate the project’s assessment conclusions, such as areas of high uncertainty or low confidence. Detailed requirements for In-Principal monitoring, can be found in Parker et al. (2022d). This document outlines Natural England’s recommendations for an effective IPMP and should be considered when planning monitoring post-consent. Natural England notes that the Applicant proposed to conduct additional monitoring besides the standard requirement for noise measurements for the first four piled foundations.
25 | E31 | Natural England notes that within the Operation and Maintenance Plan the Applicant states that the use of sub-bottom profilers would not require a further marine licence over the lifetime of the project. However, due to the unknown parameters of these surveys and the potential for cumulative underwater noise impacts we highlight that the MMO should be contacted prior to their use, to ascertain if a marine licence is required or not. Natural England advises that the Applicant seek further advice from MMO with regard to the requirement to obtain a marine licence for the use of sub-bottom profilers.
26 | E32 | Natural England is not content with the Applicant’s response that PAM is considered as a potential mitigation measure for UXO clearance. The acoustic monitoring should be conducted alongside the visual monitoring during the UXO clearance. This needs to be clearly reflected in the MMMP. We advise that the MMMP should correctly refer to PAM as a standard mitigation tool, not potential mitigation measure. Refer to the “JNCC guidance for the use of Passive Acoustic Monitoring in UK waters for minimising the risk of injury to marine mammals from offshore activities (2023)”.
27 | E33, E5, E36 | For HRA-level assessments of SACs designated for harbour porpoise, an Effective Deterrent Radius (EDR approach should be used to assess behavioural responses. Advice on the use of EDRs is set out within the joint Statutory Nature Conservation Body (SNCB) guidance note on assessing the significance of noise disturbance to SACs designated for harbour porpoise. We recommend that the assessment should be based solely on the EDR approach to assess disturbance of piling.
28 | E35 | The Applicant predicts that both the 20% spatial daily threshold and the 10% seasonal threshold could be exceeded in almost all scenarios. However, it is suggested that this scenario is unlikely thanks to other OWF SIPs, concluding that the adverse effect on the integrity of the SNS SAC will be avoided with appropriate SIPs. Since these SIPs have not yet been developed, it is not sufficient to conclude that adverse effects on the integrity of the SNS SAC will be avoided. At this stage, Natural England cannot agree that the integrity of the SAC will be preserved especially as there was no commitment to the use of NAS. The Applicant should commit to the use of noise abatement systems and incorporate this into the draft MMMP and SIP and incorporate this into the assessment.
29 | E39 | Table 4.8 indicates that the average overlap with seasonal area of the SNS SAC is 15.14% for high order clearance. thus the conclusion in paragraph 51 stating: “The assessment indicates that for both high and low-order UXO clearance, less than 10% of the winter area of the SNS SAC would be affected.” is incorrect. We advise that the Applicant corrects the statement in the named paragraph and correctly present the outcome of the assessment for the high order clearance.

## F - Offshore Ornithology
Point | Point Number(s) from Appendix F [RR-XXX] | Taken from Natural England’s Relevant and Written Representations North Falls OWF Appendix F - Offshore Ornithology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | F1, F23, F35, F36 | Natural England cannot rule out an adverse effect on integrity (AEOI) for red-throated diver (RTD) at the Outer Thames Estuary Special Protection Area (OTE SPA) from the project alone. We advise that the project will contravene the SACO attribute to “Reduce the frequency, duration and / or intensity of disturbance affecting roosting, foraging, feeding, moulting and/or loafing birds so that they are not significantly disturbed” and to “maintain the extent, distribution and availability of suitable habitat (either within or outside the site boundary) which supports the feature for all necessary stages of the non-breeding/wintering period (moulting, roosting, loafing, feeding).” To more fully understand the nature and scale of impact we advise that the proportion of the SPA that could be ‘most’ impacted by North Falls OWF, i.e., the area within the 12km buffer to which the array is closer than any other OWF, should also be presented. Natural England welcome the partial mitigation of impact by updates to the proposed location of the array area since PEIR submission. We consider that the Applicant should demonstrate to the Examination that no further reduction in impact by increasing the distance between the SPA and the array is possible whilst retaining a viable project. If any further mitigation of the impact is not possible, we advise that every effort must now be made to ensure effective compensatory measures can be delivered.
2 | F2 | Natural England agree that the project-alone impacts arising for Flamborough and Filey Coast SPA (FFC SPA) kittiwake, guillemot and razorbill are relatively small. Nonetheless, we consider that in each case, AEOI in-combination cannot be ruled out, and therefore welcome the provision of withoutprejudice derogations cases for these species.
3 | F3, F26 | The Applicant should carry out a full in-combination assessment of impacts for guillemot at the Farne Islands SPA, to allow Natural England to advise further regarding the risks of adverse effects in-combination. We request that impacts at 70% displacement and 2% mortality are presented but highlight that, ideally, full matrices would be included in the submitted documents for all displacement assessments.
4 | F4, F16 | Natural England strongly recommends that construction and decommissioning of the export cable (EC) should not take place within the OTE SPA +2km buffer during the sensitive over wintering period for RTDs of November to March inclusive. This mitigation should be appropriately secured. All vessels should follow Natural England best practice guidelines on vessel movements during all other phases of the development for both the EC and array.
6 | F6 | It is not clear if cable laying vessels will also have guard vessels in attendance. If guard vessels are present, the area of potential displacement impact around cable laying will be greater and therefore the assessment may need updating. If guard vessels are required, please detail how many, operating distance from the cable laying vessels, etc.
7 | F7 | An average of 3 vessel trips per day are predicted over the two-year construction period. It is stated that up to 35 vessels could be operating at any one time. Assuming that many of these vessels could be smaller support vessels, the daily number of trips to port appears to be low. An updated assessment should clarify the expected number of vessels that require daily mobilisation to the construction site from a local port.Similar should also be provided for Operation and Maintenance activities
8 | F10 | Natural England advise that UXO clearance at the OTE SPA should not be undertaken in the sensitive over-winter period for RTD. A suitable buffer should be considered of at least 2km to account for vessel impacts. However, it is unclear if this buffer is sufficient for any potential impacts from noise. This impact pathway should be investigated.
9 | F12 | We do not agree that all project alone impacts of <2 birds can be screened out of further assessment. The scale of these impacts should also be considered in light of any existing significant cumulative impacts and AEOI judgements and the potential for any material contribution. We advise that the Applicant needs to fully justify screening these species out of further assessment. Furthermore, they should consider existing adverse effect rulings and significant impacts, in addition to the potential to contribute to existing impacts. Further assessment may be required if a material contribution to existing impacts is possible.
10 | F13 | The Applicant has not considered information made available after March 2024 in their cumulative effects assessment (CEA). The cumulative effects assessment should be updated to reflect the latest impact estimates from the Five Estuaries, Dogger Bank South, and Outer Dowsing projects. We recommend the Applicant collaborate with the above developers to agree how updated impact values (based on SNCB advice) can be efficiently incorporated into each other’s assessments as the Examinations of all four projects progress.
11 | F17 | The Applicant concludes effect significance for guillemot, razorbill, RTD, and gannet is minor adverse (not significant in EIA terms). Natural England do not agree with these conclusions. Natural England has already identified significant adverse impacts at the EIA scale to gannet, kittiwake, great blackbacked gull, guillemot, razorbill, and RTD from OWF in the North Sea, irrespective of the contribution of North Falls to the cumulative impact totals. We consider that the project will make an additional contribution to those impacts. We advise that every effort is made to mitigate these impacts.
12 | F22 | Natural England agree that some consideration of the diminishing displacement effect with distance from an array is appropriate. However, we do not believe the EDA is an appropriate way to quantify this. We maintain that with respect to the availability of suitable habitat, the entire area of effect must be considered as impacted to some extent. Natural England do not agree that using the total area to assess potential displacement impacts in any way overstates the scale of the impact.
13 | F23 | Natural England agree that two major shipping lanes run through this area and will impact RTD distribution. However, RTDs are still present, and indeed were present at sufficient density for this area of the SPA to be classified for their protection. We consider it highly likely that that these birds would be subject to further displacement by a turbine array. Furthermore, this displacement may be permanent whereas, at present, there may be temporally limited displacementimpacts with resettlement of habitat between vessel movements. Natural England confirm that we consider the ‘novel’ area that the project will impact through disturbance and displacement to be 54.5 km2, constituting 1.4% of the SPA area. We consider this has the potential to result in an AEOI for the project alone.
14 | E24 | The Applicant’s stated AOE SPA LBBG population of 1880 AON is larger than that used by the Five Estuaries (VE) OWF assessment of 1749 AON. We highlight that assessing impacts against a larger population could lead to an underestimation of impact scale and advise that the population count used by Five Estuaries OWF considers the best available contemporary data and is, therefore, the most appropriate count. The Applicant should therefore use the same count in an updated impact assessment.
15 | F25 | Natural England requested that the North Falls apportioning should be aligned with VE OWF. We note that while the underlying methodology applied is the same for both projects, the colonies and their populations under consideration are not. Given their proximity and similar application stages, Natural England continues to advise that North Falls and VE apportioning approaches should be aligned. Natural England note that a more precautionary approach to apportioninghas been presented by the Applicant compared to that of VE OWF. However, With that in mind, we advise that North Falls OWF's use of historic population counts that do not align with the baseline data collection does not follow best practice guidance. We continue to advise that VE OWF and NF OWF should collaborate and align their approaches to apportioning where appropriate. We anticipate that should this be addressed, the estimated project alone impacts to lesser black-backed gull at AOE SPA from North Falls should be reduced.
16 | F27 | Most parameters for the Population Viability Analysis (PVA) modelling are as we would expect, however, there are three input parameters that do not follow Natural England guidance. 1. Years for burn-in is 4, not 5. 2. Impacts have been applied separately for immatures, we advise that this option is not selected. 3. Random seeds have beenmatched for impact scenarios. However, standard errors of impacts are not available. In this case, random seeds should not be matched for impact scenarios.We advise that a 5- year burn-in period is adopted, random seeds are not matched, and impacts are not applied separately to immatures if any further PVA modelling is undertaken.
17 | F28 | The results presented in Table 4.23 for the scenarios relating to Tier 1-5 appear to be assigned to the wrong scenario. When effects from OWFs with compensation are excluded, the predicted adult mortality should decrease (as for the Tier 1-3 scenarios. We advise that table 4.23 should be checked and amended, as needed.
18 | F29 | We note the relatively modest contribution to the OTE SPA RTD in-combination mortality totals from the North Falls project. Nevertheless, Natural England consider that the in-combination assessment does highlight the risk of population level impacts arising from displacement mortality. As the non-breeding RTD population at the OTE SPA is drawn from a biogeographic scale breeding population, we do not recommend further investigation of the impact by PVA. While the impacts to habitat availability and feature distribution remain our primary concern for RTD in the OTE SPA (in relation to the North Falls project and more generally), we consider that the potential scale of mortality estimated adds weight to the requirement for the project to deliver effective compensatory measures.
19 | F30 | Natural England continue to advise that the North Falls and Five Estuaries projects should both be considering the same LBBG data when conducting cumulative and in-combination assessments. We advise that the Applicant should coordinate with VE and update the assessments. This advice applies to all species which are assessed incombination.
20 | F31 | In the SADEP Examination, Natural England could not rule out AEOI for guillemot at FFC SPA from an estimated an in-combination annual mortality of 1,498 guillemot based on 70% displacement and 2% mortality, resulting in a reduction in population growth rate of 1.4%. Under the same parameters, the Applicant estimates an in-combination mortality of 1,172 guillemot which results in a 0.5% reduction in population growth rate. It would be useful to fully understand the differences in the in-combination assessment (and PVA) the Applicant presents compared to that from which SoS concluded that AEOI could not be ruled out in combination for guillemot at FFC SPA in the SADEP consent decision.
21 | F32 | In the SADEP Examination, Natural England could not rule out AEOI for razorbill at FFC SPA. As similarly noted for guillemot, despite considering very similar in-combination data, the Applicants PVA has resulted in a significantly lower reduction in growth rate than that calculated by SADEP. It would be useful to fully understand the differences in the in-combination assessment (and PVA) the Applicant presents compared to that from which Natural England previously concluded that AEOI could not be ruled out in combination for razorbill at FFC SPA in the SADEP consent decision.
22 | F33 | The Applicant suggests that the lack of evidence for RTDs suffering mass mortality events during seabird wrecks may suggest they are less energetically constrained during the non-breeding season than other seabird species (e.g., auks). While it is true that RTDs do not appear to suffer in such wrecks, Natural England do not believe the evidence supports this extrapolation. We would highlight that RTDs tend to winter in more sheltered coastal waters where they are less exposed to major storm events. It is also relevant that populations of wintering RTDs are much smaller than, e.g., guillemot. Thus, much lower numbers of wrecked birds would be expected even if they were similarly exposed. Furthermore, we highlight that RTDs are much more constrained by habitat than sea bird species typically involved in wrecks, as they require shallow water. Therefore, regardless of energetic constraint, developments that reduce the suitability of already limited areas of preferred RTD habitat are problematic. As birds become increasingly constrained, increased competition with other divers is likely to occur.
23 | F34 | Natural England request that the area of North Falls OWF's impact that overlaps with 12km buffers of existing OWFs is further investigated, and the areas that will be closer to North Falls (and thus likely to be primarily impacted by North Falls once operational) are also calculated and presented. This should facilitate comparative review of three spatial areas of impact, all of which we consider to be important. 1. Total area impacted. 2. Novel area impacted. 3. Area where impacts may be exacerbated.
24 | F35 | With respect to a minimum air gap of 27m above MHWS Natural England again highlight that any increases to this air gap will reduce collision impacts, at both EIA and HRA scales. We question whether further increases in the air gap might be possible to further mitigate this impact by reducing collision risk and recommend that the Applicant presents information to demonstrate that an increase is not possible from an engineering perspective. Natural England continue to advise that the mitigation hierarchy is followed until demonstrably exhausted, and that all options to mitigate impacts are employed prior to the reliance on compensatory measures. This mitigation should be appropriately secured.
25 | F37 | The Applicant outlines the current situation regarding the area of the OTE SPA currently subject to in-combinationdisplacement impacts on RTD arising from OWFs. It is stated that 49% of the SPA is within 12km of an OWF and thus impacted. The addition of North Falls will result in displacement impacts across a further 2% of the SPA (i.e., an additional 54.38km2). Natural England consider this to be a meaningful contribution. We note a minor discrepancy between the project alone and in-combination assessment. The former refers to an area of 54.5km2 being impacted, this being defined as 1.4% of the SPA area. The minor discrepancy in area impacted and the percentage of the OTE SPA that are represents should be clarified and the documents updated, as necessary. Natural England note that the project has reduced the scale of the proposed OWF and increased the distance from the array area to the OTE SPA, which we welcome. However, given the scale of the impact to RTD, if no other mitigation measures are available, thenefforts should be focussed on ensuringthat appropriate compensatory measures can be delivered that make a meaningful contribution to the existing AEOI. Thus, we welcome the submitted (without prejudice) report on potential compensation measures for RTD.
26 | F39 | We do not agree that the Project makes no material contribution to the in-combination mortality of kittiwake at FFC SPA. Natural England note that the project apportions 0.8 collisions a year to the FFC SPA population, none of which are in the breeding season, and therefore the in-combination contribution is small. Natural England welcome the provision of a without prejudice derogation case for compensating impacts to kittiwake at the FFC SPA, in the event of SoS considering an in-combination AEOI cannot be ruled out.
27 | F40 | We do not agree that the North Falls project will make no material contribution to the acknowledged incombination AEOI on guillemot at FFC SPA. We note the Applicant predicts project-alone mortality impacts of 1 bird(95% CLs 0-3) at 50% displacement 1% mortality, increasing to 3 (95% CLs 1-9)birds at 70% displacement and 2% mortality. Natural England therefore conclude that an AEOI in-combination cannot be ruled out. espite the Applicant’s conclusions, we welcome the provision of an incombination assessment, investigation of impact by PVA and the provision of a without prejudice derogations case. We consider that our input through the Examination period would be best spent ensuring a suitable derogations case can be delivered.
28 | F41 | We do not agree that the North Falls project will make no material contribution to the in-combination impact on razorbill at FFC SPA. Natural England highlight that we concluded during the Hornsea 4 and SADEP Examinations that AEOI on the razorbill feature of the FFC SPA for displacement impacts incombination with other plans and projects could not be ruled out. Despite the Applicant’s conclusions, we welcome the provision of an incombination assessment, investigation of impact by PVA and the provision of a without prejudice derogations case. Natural England request clarity regarding the PVA resulting in a smaller reduction in population growth rate compared to the SADEP OWF PVA, despite a greater impact being investigated. Natural England anticipate that our previous judgements regarding AEOI for razorbill at FFC SPA are highly likely to be maintained given the increased incombination mortality impact, albeit the projects contribution to the incombination total is small

## G - Offshore Orni Compensation
Point | Point Number(s) from Appendix G [RR-243] | Taken from Natural England’s Relevant and Written Representations North Falls OWF Appendix G - Offshore Ornithology Compensation | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
Compensation measure: Summary Position of Compensation Measure for Guillemot and Razorbill |  |  |  | Documents reviewed:
1 | G1 | Currently there is uncertainty regarding the current state of anthropogenic disturbance at southwest auk colonies and its relative importance compared to other factors such as food availability and predation. No observational evidence has been presented, although the proposed measures have successfully reduced recreational disturbance of other species. Overall, we consider the right measures at the right sites should deliver legitimate benefits.
2 | G3, G11 | No observational evidence is presented regarding the current state of anthropogenic disturbance at the colonies. The Applicant has carried out a qualitative assessment from a desk-based study looking at generic factors such as proximity to coastal paths, nearest settlement, and levels of localised recreational activity. These factors alone do not necessarily result in disturbance that might cause egg or chick losses. Only field-based observation, either through monitoring or communication with site managers/landowners is likely to yield this information. We understand that other projects working on similar compensation proposals have undertaken (relatively limited) field observations at some southwest UK auk colonies. We urge collaboration on this aspect.
3 | G4 | Natural England consider the Applicant should seek to compensate for their impacts to auks at FFC SPA under a 70% displacement and 2% mortality scenario. Natural England advise the consideration of a compensation ratio of 1:1 to be inappropriate. However, we do believe that given the nature of the measure proposed, the difficulties of quantifying benefits (as well as potential for subsidiary benefits to nontarget species) and the small scale of predicted impacts, a pragmatic approach to scaling the measure is appropriate.
4 | G5 | We disagree with the seasonal extent of compensation measures proposed by the Applicant. We suggest that measures to reduce recreational disturbance should be in place well before the breeding season. This may need to be as early as December/January, to be determined on a site-specific basis, to allow for cyclic prelay attendance by guillemots. This could facilitate egg-laying synchrony and increasing productivity. The scale of compensation required, in terms of the number of pairs required to produce a required number of new recruits to compensate for a given impact follows the Hornsea 4 approach. As advised for kittiwake, Natural England consider the method developed and applied by Hornsea 3 should be utilised. Given the refined geographical location of the measure Natural England advise that it would be preferable to consider locally derived demographic rates(especially for productivity) if possible. Given the implementation of measures does not necessarily scale with the potential of the site (in terms of additional nesting pairs) we consider that site selection should, primarily, focus on those with greatest chance of success for the greatest potential benefit.
5 | G6, G12 | Natural England highlight that implementation 4 breeding seasons prior to an impact occurring (at the operational phase) will risk impacts arising in advance of the measures being functional. Further, we highlight the risk of impacts arising at the construction phase. Guillemots reach breeding age maturity at 6 years old, thus it will take at least 7 breeding seasons after compensation measures are implemented for young fledged to recruit into the adult breeding population and thus provide compensation for the project’s impacts. The equivalent values for razorbill are 5 and 6, respectively. Therefore, if the Applicant wishes to retain the current implementation date, we consider that the scale of the requirements be increased to address the risk of ‘mortality debt’ accruing in the early years of the project.
6 | G7 | We note that no sites have yet been secured, although we understand that discussions are underway with other developers. We would recommend that a sufficient number of sites are secured, either by the Applicant alone or in collaboration with other Projects, as soon as possible.
Compensation measure: Summary Position of Compensation Measure for Kittiwake
7 | G13, G23 | Subject to sufficient nesting spaces being available to the project at either an onshore or offshore ANS, we consider such provision to be suitable for the project’s modest impacts. Whilst no breeding attempts were observed at the Kittiwakery in 2023 or 2024, monitoring of kittiwake activity suggests the possibility of future colonisation. However, uncertainty remains regarding the successful colonisation of the proposed ANS, and the mechanism for assigning benefits arising at the ANS between the partnership OWF projects.
8 | G16 | Natural England advise that the method developed and employed by the Hornsea 3 project is used to calculate the number of pairs required at the ANS to compensate a specific impact. This is in line with advice commissioned by The Crown Estate to inform the Round 4 strategic compensation plan for kittiwake. We note that this will result in a greater number of pairs at the ANS being required. We welcome the consideration of the 95% upper confidence interval impact estimate (2.72) to calculate the scale of compensation required and advise that this approach should be maintained in updated calculations.
9 | G17, G24 | Natural England do not consider a ratio of 1:1 to be appropriate. We highlight the uncertainties surrounding future colonisation and productivity of any colony at the ANS. Given the small impact to be compensated we agree that a single ANS location is appropriate but consider that a 3:1 compensation ratio offers a more realistic prospect of the measure delivering benefits into the UK NSN. It is not clear how any resulting compensation will be apportioned to each project with an interest in the ANS, should the measure be only partially successful. This should be clarified.
10 | G18 | The “Kittiwakery” was constructed in February 2023. Despite not yet accommodating nesting kittiwakes (as might be expected), we consider the observations of kittiwake at the site to be a positive sign. It is advantageous that the ANS is already built in recognition of the fact that it will take at least 4 years for the ANS to deliver breeding-age adult birds into the population. We would highlight the uncertainty around recruitment at ANS in general, noting that there are a number of structures that have remained vacant despite apparently being in suitable locations. Thus, we are concerned about the potential accrual of mortality debt. This would need to be recovered in future years. As the debt compounds, the nesting pairs requirement may exceed that offered by available space the ANS. This does not appear to have been specifically addressed by the Applicant (notwithstanding consideration of adaptive management) and is of particular concern due to the (unspecified) requirement for compensation for other projects reliant on the ANS.
11 | G25 | We would welcome confirmation as to whether a colour-ringing scheme could be undertaken at the “Kittiwakery” to track natal philopatry there (and recruitment elsewhere) for the purposes of establishing site connectivity with, and overall coherence of, the national site network.
Compensation measure: : Summary Position of Compensation Measure for Lesser Black Backed Gull
12 | G26 | None of the sites under consideration have been secured yet, and further work is needed around defining success according to the ratio of impact to observed productivity and assumed level of consequent recruitment. There is a risk that the limiting factor to LBBG population growth could be food supply, in which case improving nesting habitat may have no or little impact. However, predator exclusion fencing has a successful track record in increasing some LBBG colonies in the UK and predator control has been shown to be effective for regulating mammalian predation of seabird eggs/chicks. Therefore, we consider that habitat management, combined with one or more of these other measures, could prove effective. Moreover, assuming that the selected site is colonised, we feel that a 4ha site should be able to deliver the required level of compensation over the lifetime of the project. See also G36 below.
13 | G29 | Natural England advise that some updates to the calculation of impacts to lesser black-backed gull, apportioned to AOE SPA, may be required through the Examination period. We do not consider that this precludes useful ongoing discussion on the relevant compensatory measures, and the broad level of compensation required is unlikely to change.
14 | G30a | Regarding predator management, Natural England broadly welcome the Applicant’s intention to create a minimum 4ha area of predator exclusion. We consider the extent of the proposed area would be adequate based on the nesting densities as presented in Table 6.3. It would be useful for context if the lower end of the recommended Natural England/RSPB nesting density range (0.002 nests per m2) was also presented, as well as for a higher compensation ratio (e.g. 3:1) although we anticipate that 4ha will remain sufficient. We note that a joint compensation scheme with Five Estuaries OWF is being considered but there is no detail of consideration of the implications for habitat extent to account for combined impact levels. See also G36 below.
15 | G30b | Regarding habitat management, we would highlight the uncertainties around this since a suitable compensation area has yet to be secured and it is consequently unclear whether enhanced management is either necessary or possible. We do not consider it appropriate to base the compensation level on a 1:1 ratio due to remaining uncertainty of measure success. We acknowledge that a 2:1 ratio is also presented (Table 6.3) and advise that it would be appropriate to consider 3:1.
16 | G31 | Lesser black-backed gulls reach breeding age maturity at 4-5 years old. Therefore, offspring fledging from a compensation site established 3 breeding seasons before commencement of operation will not have recruited into the adult breeding population. As a result, the proposed timing of delivery will result in the accumulation of mortality debt. In addition, colonisation in year 1 is far from guaranteed. This debt will need to be recovered in future years, and the debt will compound if a suitably sized colony is not established quickly. This risk does not appear to have been specifically addressed by the Applicant. We note that lesser black-backed gulls return to their nest sites from late February and therefore suggest that the compensation area is made available before this time in Year 1 to allow pairs to scope the area before nesting commences (usually in April), in the hope that this minimises the accrual of mortality debt.
17 | G32a | We note that none of the sites under discussion have currently been secured and we would encourage the Applicant to secure agreement for this measure at an appropriate site with a landowner as soon as possible. Regarding Lantern Marshes, we understand that there have been positive discussions between North Falls and the National Trust in respect of this site and accept that an appropriately designed permanent predator exclusion fence would provide benefits beyond the management currently being undertaken by the landowner.
18 | G32b | Regarding the Five Estuaries partnership sites (VE2/Outer Trial Bank), we understand that the Applicant is in discussion regarding potential collaboration at these locations. Natural England are highly supportive of this collaboration and would welcome further information regarding how this will be achieved.
19 | G32c | Regarding Orfordness-Shingle Street, we acknowledge that anthropogenic disturbance may be impacting the lesser black backed gull colony at this site. However, quantification of the potential benefit to the colony of disturbance management measures such as awareness campaigns, warden provision or signage would require observational fieldwork.
20 | G32d | Regarding Outer Trial Bank, we accept that although lesser black backed gulls have high rates of natal philopatry, it is entirely possible that individuals fledging from this site could theoretically recruit into other nearby lesser black-backed gull colonies within the AOE SPA.
21 | G36 | Non-lethal control (trapping) of rodents on the Outer Trial Bank is highly unlikely to work. Eradication may not be effective if rats are not suppressing breeding lesser black-backed gull productivity, or the site is recolonised by rats prior to the breeding season.
Compensation measure: Summary Position of Compensation Measure for Outer Thames Estuary SPA Red Throated Diver
22 | G37, G43, G46 | Nesting rafts and habitat management are technically feasible however, site selection is likely a critical factor to the success of this measure. Therefore, we are concerned that no sites have been shortlisted or secured and the Applicant should seek to secure sites as soon as possible. We are not convinced that the Applicant will be able to demonstrate sufficient control over rafts deployed in Finland in the long term and would consequently recommend that should this measure at this location be progressed, it is done so on a trial basis alongside more extensive deployment in Scotland. We are not persuaded that the provision of 20 nesting rafts would result in significant gains for red-throated diver and therefore represent a meaningful contribution to support the coherence of the UK NSN. See also G44 below.
23 | G40 | Natural England agree with the Applicant that there is no robust way to scale the level of compensation to be delivered due to the mismatch between the expected benefits (increased productivity) and the impact (habitat loss/degradation). Nevertheless, we do consider that the scale of impact is significant. Therefore, in very broad terms, we would expect that significant benefits should be expected to arise from any delivery of a compensation measure (or package of measures). We recommend a more ambitious approach to the nest raft measure, as part of a commitment to a clearly defined package of measures.
24 | G41, G43, G46 | Natural England consider the proposal to contribute to the identification of a strategic sanctuary area through data collection requires considerable further work from the Applicant to more clearly define the aims and objectives. As a clear scheme of work is not yet evident, we cannot comment on the scale/extent of this measure. We note that discussions with SPR are in the early stages and confirm our support for such a collaboration, noting that the contribution made by North Falls needs to be clearly distinct from the DCO requirements of SPR. However, we also highlight that compensatory measures should be demonstrated as being securable and deliverable within the time frames of Examination. As the provision of nesting rafts alongside habitat management does not directly address the impact of the project, data collection to inform the identification of sanctuary areas does not represent a compensatory measure itself, and there are uncertainties about the level of benefit that might accrue at the UK NSN, Natural England advise that these measures should be proposed as a package. Consideration should be given not just to the spatial elements of the relevant datasets but also the temporal elements, to future-proof any proposed sanctuary areas for the lifetime of the Project with respect to trends in other anthropogenic activities. See also G44 below.
25 | G44 | We acknowledge the inherent risks that multiple monitoring visits might represent and recognise that anthropogenic disturbance has been reported as a factor in reduced breeding success. Nevertheless, we would advocate investigation into the feasibility of using established or emerging technologies for this purpose. We note that where site visits are required, these would be conducted by appropriately licensed individuals. We note discussion of the need for retrofitting roofs to nesting rafts should avian predation be identified as a limiting factor in breeding success. We understand that the deployment of camouflage nets over wire mesh has met with some success elsewhere. Rafts will need to be placed in sheltered locations to avoid a retrofitted structure acting as a sail in high winds. We would encourage raft design to allow for the development of natural vegetation.
26 | G45 | Success of the nest raft/habitat management measures relies heavily on the Applicant’s ability to quantify existing productivity as this measure relies on improvements to existing productivity. Identification of sites with an established (or implementable) monitoring baseline outside of the existing SPA network designated for RTD, and with no current nesting raft provision or habitat management programme, would therefore seem critical. We expect that final site selection could prove challenging and recommend that the Applicant accelerates their work in this area.

## H- Onshore Ecology and Orni
Point | Point Number(s) from Appendix H [RR-243] | Taken from Natural England’s Relevant and Written Representations North Falls OWF Appendix H - Onshore Ecology and Ornithology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | H1 | (a) overall confidence in mitigation proposals for protected species is reduced due to limitations of survey results caused by the timing of the surveys. (b) pre-construction surveys undertaken at the optimum time of year as per the relevant guidelines for each species, and appropriate mitigation will need to be secured in the Outline Landscape and Ecological Management Plan.
2 | H2 | Lesser Black Backed Gull (LBBG) Compensation Habitats Regulations Assessment (HRA) document is relatively high level and baseline surveys to support conclusions were undertaken at the wrong time of year. The limitations need to be addressed Natural England suggests that collaboration with Five Estuaries may be appropriate to address shortfalls in evidence pre-consent.
3 | H3 | A net loss is expected in watercourse module biodiversity units, which is not being addressed, even through Biodiversity Net Gain. Please see reference point 37.
4 | H4 | There are possible disturbance and visual impacts for receptors along the King Charles III England Coast Path (ECP) depending on timing of opening of ECP. Further information relating to any impacts on the associated margins, in addition to any restrictions required and impacts on the line of the path is required.
5 | H5 | The Applicant has retained the possibility of compensation for LBBG at the Shingle Street location within the Alde Ore Estuary Special Protection Area (SPA) in collaboration with The Five Estuaries (VE) project for which concerns remain.
6 | H8 | Further reductions to the Maximum Design Scenario (MDS) should be considered to minimise environmental impacts including (but not exclusively) reducing the working corridor and cable crossings.
7 | H9 | The process of backfilling as describe will potentially limited land returning to it previous use. Further detail should be included within the cable statement on ensuring that land can continue to maintain ecological function post installation and back fill.
8 | H10 | There is no information on how the proposals to reduce disturbance at the Orfordness-Shingle Street location would be measured. This should be provided with consideration of what disturbance levels are now, and how the proposed interventions success will be related to the colony success above and beyond natural variation.
9 | H11 | There is an expectation that baseline data will be collected and assessed for any compensation locations prior to construction and mitigation measures implemented. Where required additional permits will also be obtained. This commitment should be secured with appropriate timelines allow for time to undertake these surveys and include the information in reporting and development of a conservation, mitigation, and monitoring plan whilst still ensuring measures are implemented 4 breeding seasons before North Falls becomes operational. This will need to be secured with the Development Consent Order (DCO)/Deemed Marine Licence (dML) compensation conditions.
10 | H12 | Adaptive management measures will need to be secured for any compensation measures for LBBG.
11 | H13 | Where possible, a review of the current compensation proposals for LBBG should be included and an outcomes/conclusions considered in context of the proposal.
12 | H14 | Climate change resilience of any of the LBBG Compensation proposals requires further consideration. For example the long-term management of Lantern Marshes/Cobra Mist land has not yet been agreed so it is possible that it could breach again, and that breach remains leaving the area tidal. There is also mention of the area being deliberately flooded through the sluice occasionally to manage the habitats.
13 | H15 | The use of a vehicle or hides for compensation monitoring is proposed to reduce disturbance. However, commitments are required to ensure monitoring won’t impact other features. If not possible a suitable alternative will need to be provided.
14 | H16 | More detail on proposed monitoring is required. The risk of disturbing the birds during compensation monitoring should be considered and where possible the monitoring should be combined with the planned surveys to reduce the risks of disturbance. This should be considered in any outline plan and finalised prior to installation.
15 | H17 | Mitigation for vehicles damage at the compensation location in Orfordness is ‘reduced speed limited’. Considering habitats present on the site, there should be a commitment to use preapproved access routes only, avoiding areas of vegetated shingle, all staff driving vehicles should be given a full briefing on site protocols prior to any access to the site and speed limits should be monitored and repeat breaches reported.
16 | H18 | It is important to consider that material could build-up where LBBG Compensation/fencing crossed current drainage areas at Orfordness, and that blockage could then change the path of draining water and ,therefore, change hydrological processes. Documents should be updated to include a requirement to remove any build-up of material on the fence as a mitigation.
17 | H19 | Survey results notwithstanding, Holland Haven Marshes SSSI is designated for its nationally important lowland ditch systems. Therefore, characterisation of these environmental features as being of low or medium importance is inappropriate. The site is currently considered to be in favourable condition, but even where there has been some degradation of habitats, flora and fauna a duty remains to restore. And therefore every effort should be made to avoid impacts which are likely to cause damage.
18 | H20 | More can be done to avoid and reduce impacts to Holland Haven Marshes SSSI by conditioning the number of Horizontal Directional Drilling (HDD) walk over surveys and surveyors. Mitigation measures should be fully secured in the Schedule of Mitigation and named plans such as the Outline HDD method statement.
19 | H21, H25 | There have been incidents of bentonite breakout from HDD operations on other projects, which have resulted in long term habitat contamination issues on SSSIs and SPAs. An outline HDD and/or bentonite management plan is required.
20 | H22 | Natural England strongly supports coordination with Five Estuaries to minimise risk and ecological disturbance and all mitigation measures should be secured within the DCO.
21 | H23 | Fresh water abstraction from local water courses has potential implications for Holland Haven Marshes SSSI. The outline HDD method statement should be updated and consultation with relevant interested parties on the finalised plan should be secured through requirement in the DCO.
22 | H24 | Natural England advises that any comments made by the EA in relation to HDD at HHM SSSI should be given due consideration and any assessments informed by site specific geotechnical investigations.
23 | H26 | The full procurement of the DLL should be undertaken within no more than 12 months prior to the commencement of onshore construction works. The DLL has been applied for based on full temporary impacts. Therefore, when the final Landscape and Ecological Management Plan (LEMP) is produced post-DCO determination this must include details to re-instate all terrestrial habitats within the DLL boundary like for like or of better quality for GCN within 12 months of the completion of works.
24 | H27 | Where there is moderate to high potential for bat hibernation use, the preconstruction surveys should include tree climbing inspection between core wintering months to allow an assessment of the impacts to hibernating bats and to allow impacts to be avoided. Automated/static surveys may also be used when collecting data on winter bat activity. The OLEMS should be updated to require the appropriate surveys to be conducted.
25 | H28 | There is no commitment here to avoid work in functionally linked land, this is particularly relevant to Hamford Water SPA but applies to all functionally linked land within the red line boundary. Commitments to avoid work on functionally linked land to avoid impacts to supporting habitats and/or disturbing Annex I bird features during sensitive periods. If this is not possible then a management plan would be required to ensure impacts are sufficiently minimised.
26 | H29 | Natural England’s default position is for no transits routes to occur across the SSSI. Natural England advises that this commitment should be secured in the Mitigation Schedule. But should it be found not to be possible an management plan will be required.
27 | H30 | Natural England advises that it for the Applicant to determine if a badger licence is required or not. Natural England advises that the Applicant and their consultants should identify the need for a licence. If a licence is required, then Natural England recommends following the guidance regarding protected species licensing.
28 | H38 | It is unclear to Natural England if a bat European Protected Species (EPS) mitigation licence will be required. If a licence is required, then Natural England recommends following guidance regarding protected species licensing. This document should be updated to reflect the need to consider the potential for EPS licences
29 | H39 | Natural England requests to be consulted on the report of the pre-construction bat survey that is to be appended to the Environmental Management Plan (EMP).We request that our consultation be secured through requirement on the DCO.
30 | H31 | More information should be provided to address concerns over the suitability of temporary hedgerows and their use by dormice as well as removing them when they may be a place of shelter for dormice.
31 | H32 | To confirm the absence of dormice the preconstruction surveys must have sufficient survey effort index to base appropriate survey effort should be secured in the OLEMS.
32 | H33 | The Applicant’s commitment to exploring opportunities to deliver a minimum 10% BNG and advise that this should be secured by requirement in the DCO.
33 | H34 | Any deviation from BNG best practice and principles should continue to be justified and clearly reported. Updates to metric calculations over time are required to reflect design iterations and developments are encouraged to continue to maximise their potential biodiversity outcomes throughout the detailed design process. For consistency, everything within the Red Line Boundary (Order Limits) should be included in the BNG baseline calculations, including any retained habitats.
34 | H35 | (a) The project is not currently proposing to commit to achieving 10% BNG in the watercourse module due to the complexity of creating and enhancing watercourse units. Watercourses should be factored into the statutory credit calculations given the metric highlights a 29% loss in the watercourse module. (b) a clear audit trail is should be kept of any land assigned for compensation, mitigation and BNG to distinguish what is being delivered for which purpose and where.
35 | H36 | The approach to hedgerow removal is acceptable prior to mandatory BNG, but it does not reflect best practice, or the approach used for TCPA development. Best practice would be to maintain all replaced hedgerows for a minimum of 30 years in line with BNG regulations. Where the long-term management of hedgerows for this period cannot be secured, they should be treated as “habitat loss” within the BNG metric. Once BNG is mandatory, then a legal agreement would be required to secure the management for thirty years where habitats will be lost. The document should be updated to reflect this commitment.
36 | H37 | With regards to cropland and any agricultural grassland. The correct risk multiplier is should be applied within BNG calculations, in line with the Statutory Biodiversity Metric User Guide.

## I - Seascape
Point | Point Number(s) from Appendix I2 to Deadline 1 submission | Taken from Natural England’s Relevant and Written Representations North Falls OWF Appendix I - Seascape, Landscape and Visual Impact Assessment | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | I1 | Natural England welcomes the removal of the northern array area, the reduction in maximum blade tip height, and the reduction in the number of WTGs proposed for the southern array area. The design as proposed in the ES significantly decreases the risk of further harm to the natural beauty of the SECHNL and the special character of the SHC from the North Falls project. Despite this, we advise that there remains insufficient information to discount significant impacts to landscape and visual receptors within the SECHNL and SHC from turbines within the southern array area. The implications for the special qualities of the SECHNL and the special character of the SHC must be fully assessed within an updated SLVIA.
2 | I2 | Natural England disagrees with the SLVIA conclusions of: - no significant effects on special qualities of the SECHNL - no significant effects on the landscape character of onshore LCTs within the SECHNL and SHC - the significance of visual effects (including cumulative effects) particularly between Orford Ness and Bawdsey Manor. - no significant cumulative impacts on landscape character or special qualities - the significance of impacts on people using the Suffolk Coast Path. The Applicant should revise the assessment in accordance with NE's advice.
3 | I3 | Adding further offshore wind turbines into the seascape setting not conserve and enhance the natural beauty of the SECHNL or positively contribute to the special character of the SHC; it will degrade these areas further. Therefore, it is necessary to understand how much extra damage to the special qualities the turbines of the North Falls proposal will cause, so that the acceptability of further harm can be considered. See also Point 6 (I7) below.
4 | I5 | The potential impacts from the North Falls OWF on the natural beauty of the SCHNL are not fully assessed within the SLVIA. is not clear which special qualities may be associated with potential moderate-minor effects, and how the impact of the project on each special quality has been assessed. The interactions between special qualities and the project are not described. As a result, it is unclear what the impact of the North Falls project will have on the natural beauty of the SCHAONB, for instance in terms of landscape quality, scenic quality, relative wildness, or relative tranquillity.
5 | I6 | Natural England advises that the impacts of the North Falls OWF on the special character of the SHC is not assessed within the SLVIA. Heritage Coasts do not have special qualities. Instead, Heritage Coasts are defined by their special characters and the natural beauty of the area. The presence and special character of the SHC within the SECHNL helps to define that part of the designated area which is most likely to experience significant adverse effects arising from the North Falls scheme.
6 | I7 | Section 245 (Protected Landscapes) of the Levelling Up and Regeneration Act 2023 places a duty on relevant authorities in exercising or performing any functions in relation to, or so as to affect, land in a National Park, the Broads or an Area of Outstanding Natural Beauty (“National Landscape”) in England, to seek to further the statutory purposes of the area. The Applicant should provide clarity on how the project proposes to enable the decision-maker to further the purposes of the SECHNL.
7 | I8 | The significance of effects (in EIA terms) from the North Falls OWF on visual receptors at viewpoints from Orford Ness to Bawdsey Manor (located within the SCHAONB and SHC) have been underestimated. The Applicant should review NE's advice and update the assessment accordingly.
8 | I9 | Natural England’s judgement is that the sensitivity of Orford Ness is high, not medium-high as judged by the applicant. The SECHNL is a nationally protected landscape which has been designated for its natural beauty and has a statutory purpose to conserve and enhance that natural beauty. The SHC is a nationally defined landscape because of its special character, of which natural beauty is one element. Further, the criteria used by the Applicant to judge this receptor as having a medium-high sensitivity has not been clearly articulated.
9 | I10 | Natural England agree that the cumulative effect on users of the Suffolk Coast Path is significant in EIA terms, however considers the impact to be major adverse given the potential for the North Falls project to affect the special qualities (which are not fully assessed within the ES), taking the designated landscape further away from its required state. The Applicant should reconsider their assessment in the light of Natural England’s advice.
10 | I11 | Natural England’s judgement is that impacts on the following character areas is likely to be moderate and significant in EIA terms: -Coastal dunes and shingle ridges; -Coastal levels; -Saltmarsh and inter-tidal flat. The Applicant should update their assessment in the light of Natural England’s reasoning.
11 | I12 | We disagree that the North Falls OWF will have no significant cumulative impacts on the SCHNL and SHC. The Applicant’s own assessment concludes moderate significant sequential effects on users of the Suffolk Coast Path within the protected landscape. The Applicant should update their assessment in the light of NE's detailed advice on the 377.4m and 276.4m designs.

## J - Landscape VIA
Point | Point Number(s) from Appendix J [RR-243] | Taken from Natural England’s Relevant and Written Representations North Falls OWF Appendix J - Landscape and Visual Impact Assessment | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
1 | J1, J3 | There is a potential for in-combination/cumulative impacts between Norwich-Tilbury substation, North Falls, and the Five Estuaries (VE) substations. Once more information is available during examination this should fully considered and assessed, with appropriate mitigation measures applied, if necessary, including addressing winter visibility whilst mitigation screening is established.
2 | J2 | We welcome the collaboration between the North Falls and VE Offshore Wind Farm (OWF) Projects to co-locate, and design the layout of, their substations, planted screening and landscape mitigation. This is a positive development in terms of their landscape approach, and we therefore provide no further comment on this matter during examination and defer to the Local Planning Authority (LPA).