## Title page
THE PLANNING ACT 2008
THE INFRASTRUCTURE PLANNING (EXAMINATION PROCEDURE) RULES
2010
Natural England's Risk and Issues Log - Deadine 6
For:
The construction and operation of the Morecambe Generation Offshore Wind Farm located approximately 30km from the Northwest English Coast in the Irish Sea.
Planning Inspectorate Reference EN010121
15th April 2025

## How to Read Risks and Issue Log
Natural England has created this Risk and Issues Log to track progress through the Morecambe Offshore Wind Farm (Generation Assets) examination process. The Risks and Issues Log will be submitted at each deadline with issues marked with a colour from our RAG scale depending on the level of significance of the issue. It should be noted that the colour scale is different from that used in the Statement of Common Ground provided by The Applicant. The Risk and Issues Log is split into multiple tabs in line with the Appendices of our Relevant Representations submission. A- DCO B - Offshore Ornithology B1 - Offshore Ornithology compensation C- Fish and Shellfish Ecology D - Marine Mammals E - Marine Geology, Physical Processes, Water and Sediment Quality F -Subtidal Benthic Ecology The Risk and Issues Log will be submitted alongside our written response at each deadline. This will reflect our position following a review of documents that we have considered in forming our position at each deadline. Any issues added to the log during Examination (not included in Relevant Reps) are highlighted in Red in column C and then coded according to RAG status. [New Text is in red] Risks and Issues have been presented on a document by document basis for all Appendices
Purple Note for Examiners and/or competent authority. May relate to DCO/DML
Red Natural England considers that unless these issues are resolved it will have to advise that (in relation to any one of them, and as appropriate) it is not possible to ascertain beyond reasonable scientific doubt that the project will not affect the integrity of an SAC/SPA/Ramsar and/or significantly hinder the conservation objectives of an MCZ and/or damage or destroy the interest features of a SSSI and/or comply fully with the Environmental Impact Assessment requirements.
Addressing these concerns may require the following:
new baseline or survey data; and/or
significant revisions to baseline characterisation and/or impact modelling and/or
significant design changes; and/or
significant mitigation
In addition, Natural England may use this category to highlight where there is a significant risk that an issue will not be sufficiently addressed within the Examination timescales. Consequently, issues that start out as Amber may progress to Red in the latter stages of the examination.
Amber Natural England does not agree with the applicant’s position or approach and consider that this could make a material difference to the outcome of the decision-making process for this project.
Natural England considers that these matters may be resolved through:
provision of additional evidence or justification to support conclusions; and/or
revisions to impact assessment methodology and/or assessment conclusions; and/or
minor to moderate revisions to impact modelling; and/or
well-designed mitigation measures that are adequately secured through the draft DCO/dML and/or
amendments to draft plans
If these issues are not addressed or are unlikely to be resolved by the end of the Examination, then they may become a Red risk as set out above.
Yellow Natural England doesn’t agree with the Applicant’s position or approach. We would ideally have liked this to be addressed prior to the examination but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process and would not expect these matters to be a ongoing focus of the examination. However, we reserve the right to revise our opinion should further evidence be presented.
It should be noted by interested parties that just because these issues/comments are not raised as significant concerns in this instance, it should not be understood or inferred that Natural England would be of the same view in other cases or circumstances.
Once a Risk or Issue has been categorised as yellow, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be greyed out at subsequent deadlines in order to rationalise the risk and issues log.
Green Natural England is in broad agreement with the Applicant’s approach and has no significant outstanding concerns. As above, we reserve the right to revise our opinion should new evidence be presented. Once a Risk or Issue has been categorised as green, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be shaded grey at subsequent deadlines in order to rationalise the risk and issues log.

## Summary
Point | Point Number(s) from Principal Areas of Disagreement Summary Statement (PADSS) | Taken from Natural England’s Relevant and Written Representations Morecambe Generation- Principal Areas of Disagreement Summary Statement (PADSS) | RAG Status Rel Rep | Update following Procedural Deadline A | Rag Status D1 | Update following D1 | RAG status D2 | Update following D2 | RAG Status D3 | Update following D3 | RAG Status D4 | Update following D4 | RAG Status D5 | Update following D5 | RAG status D5a | Update following D5a | RAG status D6
Development Consent Order (DCO and deemed Marine License (dML)
RI_P1 | P1 | During construction monitoring condition does not require a stop to work should noise signficantly exceed the assessed level. This is a key mitigation to protect noise sensitive mammal and fish species. We ask for an update to the construction noise monitoring condition to reflect standard requirements. |  | Condition 15 has been updated with appropriate wording. |  | No change
RI_P2 | P2 | There is no pre- or post-construction benthic, marine mammal or ornithological monitoring secured by conditions. Monitoring conditions should be included. |  | No change |  | No change |  | No change |  | No change |  | No change |  | In progress. See Natural Englands response to ExQ3 3BEM2 at Appendix I3 with this submission. |  | There are outstanding concerns with the lack of detail provided for ornithological monitoring and with the appropriateness of the proposed marine mammal monitoring, but Natural England is confident these can be resolved post-consent or are not a significant risk, respectively. Benthic monitoring issues are now resolved.
Offshore Ornithology
RI_P3 | P3 | Some historic projects have not been considered quantitatively for the cumulative and in-combination assessments. This introduces the risk that impacts assessed are incomplete. We also question the apportioning of the impacts assessed to specific SPAs and therefore the results of appropriate assessments for these sites. A full quantitative assessment should be presented, following the method Natural England has previously supplied to the applicant. We also urge collaboration with other OWF projects in the Irish Sea so that the same data are being used to perform cumulative and in-combination assessments across the region. |  | No change |  | In progress. |  | In progress |  | No change |  | In progress. Some of the assessments affected by this issue have been updated. See tab B. |  | Resolved.
RI_P4 | P4 | Adverse effect on red-throated diver (RTD) at Liverpool Bay / Bae Lerpwl SPA. Due to displacement impacts on RTD we do not agree that an adverse effect on the integrity of Liverpool Bay SPA can be ruled out. The additional 18km2 of habitat used by RTD over which displacement will occur is a concern in light of the objective to restore the distribution of the species in the site. The most effective way to avoid this adverse effect would be a change to the red line boundary or commitment to an exclusion zone for structures such that no turbines are located within 10km of this area. |  | No change |  | No change. |  | No change. |  | In progress |  | In progress. See updates to tab B. |  | No change. |  | The Applicant has submitted buffer scenarios that have the potential to remove the risk of AEOI in-combination, but is not proposing to use any of them.
RI_P5 | P5 | Adverse effect on lesser black-backed gull at Morecambe Bay and Duddon Estuary SPA and Ribble and Alt Estuary SPA. Due to in-combination collision impacts, an adverse effect on the integrity of these sites cannot be ruled out. Both sites’ populations of this species are below their target so avoiding any further deterioration is imperative. Assessments should be updated to consider current population trajectories and refined apportioning of impacts. The scale of the proposed compensatory measures should be adjusted in line with the revised assessments, and landowner agreement evidenced. |  | No change |  | In progress. |  | In progress. |  | In progress. |  | No change. |  | No change. |  | No change. Amber RAG status is due to the disagreement with the Applicants conclusion that there will be no AEOI for LBBG in-combination.
Marine Mammals
RI_P6 | P6 | The applicant has not made a commitment to use Noise Abatement Systems (NAS) during construction. From January 2025 it will be an expectation that all developers proposing offshore piling activity in English waters should demonstrate best endeavours to deliver noise reductions. We anticipate that the majority of piling will not be able to proceed without noise abatement in place. The Applicant should fully commit to using noise abatement as mitigation to reduce both injury and disturbance to marine mammal receptors during construction activities. This should be reflected in a DCO/dML condition that requires consideration of NAS in the Marine Mammal Mitigation Protocol. |  | No change |  | No change |  | No change |  | No change |  | In progress. |  | In progress. |  | Resolved. The Applicant has included a condition in the dDCO requiring that noise reduction and/or abatement measures are used for all driven or part driven piles.
Benthic Ecology and Physical Processes
RI_P7 | P7 | Assessment of impacts to benthic habitats and physical processes is incomplete. The potential impacts from seabed preparation works have not been fully considered within the assessment. The Applicant should provide an updated assessment of impacts on physical processes and benthic ecology that incorporates a realistic worst case scenario for these activities. Commitments to: standard mitigation measures for benthic habitats; removal of infrastructure at decommissioning and; to measures to reduce introduction of plastics to the marine environment have not yet been secured |  | In progress. Rule 9 response presents updated worst case scenario that clarifies and includes these pressures and receptors, but this is not yet included in an updated assessment. |  | No change |  | No change. See RI_E11, RI_E13 and RI_E14 |  | No change |  | No change. Standard mitigation measures secured in principle. Micrositing requires further work. No decommissioning programme has been submitted. |  | No change. |  | No change due to lack of outline decommissioning plan. Other aspects of this summary issue are either resolved or NE does not believe they will be a material consideration for the outcome of this Examination.

## A - DCO
Point ref | Point Number(s) from Appendix A | Taken from Natural England’s Relevant and Written Representations Morecambe Generation Appendix A - Development Consent Order (DCO) | RAG Status Rel and Wri Rep | Update Following Procedural Deadline A | Rag Status D1 | Update Following D1 | Rag Status D2 | Update Following D2 | Rag Status D3 | Update Following D3 | Rag Status D4 | Update following D4 | RAG Status D5 | Update following D5 | RAG status D5a | Update following D5a | RAG status D6
RI_A3 | A3 | The during construction monitoring condition is missing a key element that provides for a stop to works should the noise monitoring highlight the noise is significantly in excess of the noise assessed within the environmental statement. This is a key mitigation to protect marine mammal and sensitive fish species. Natural England advises that the during construction noise monitoring condition is updated to match the standard requirements. |  | Condition 15 has been updated with appropriate wording. |  | No change. No further updates to DCO and dML submited at D1
RI_A4 | A4 | Natural England notes this condition requires a Marine Mammal Mitigation Protocol (MMMP). Natural England considers that this condition should refer to the requirement to consider Noise Abatement Systems (NAS) within the MMMP as these are considered important mitigation for Marine Mammals. Natural England advises that the condition to require the consideration of the use of NAS within the MMMP is amended within the dML. |  | No change |  | No change. No further updates to DCO and dML submited at D1 |  | No change. |  | No change. |  | In progress. The Applicant intends to use NAS, but it is not yet conditioned and further work is needed on the scenarios under which NAS will be used. |  | No change. |  | Resolved. The Applicant has included a condition that commits them to use of noise reduction and/or abatement for all driven or part driven piles.
RI_A5 | A5 | These conditions cover the monitoring for the project. Natural England notes that there is no pre-construction benthic, marine mammal or ornithological monitoring secured within condition 14 or post construction monitoring at condition 16. This monitoring is considered standard. We advise that monitoring conditions should be updated and informed by a pre consent In Principle Monitoring Plan. |  | No change |  | No change. No further updates to DCO and dML submited at D1 |  | No change. |  | No change. |  | No change. |  | In progress. See Natural Englands responses to ExQ3 3BEM2 and 3BEM10 at Appendix I3 of this submission for update on outstanding monitoring issues. |  | There are outstanding concerns with the lack of detail provided for ornithological monitoring and with the appropriateness of the proposed marine mammal monitoring, but Natural England is confident these can be resolved post-consent or are not a significant risk to any designated sites, respectively. Benthic monitoring issues are now resolved.
RI_A6 | A6 | The definition of Statutory Nature Conservation Body (SNCB) is fairly open to interpretation. See below an example of wording used in other DCOs which provide more certainty with regard to the SNCB. “statutory nature conservation body” means a statutory nature conservation body, being the appropriate nature conservation body as defined in Regulation 5 of the Conservation of Habitats and Species Regulations 2017(b) or its equivalent in the Conservation of Offshore Marine Habitats and Species Regulations 2017(c) This comment also applies to Schedule 6 Part 1 condition 1, which has similar wording. For brevity this comment will not be repeated |  | SNCB definition has been updated |  | No change. No further updates to DCO and dML submited at D1
RI_A7 | A7, A1 | Natural England notes that at no point within the dML is the maximum hammer energy for piling secured. This is a key metric for the impact to marine mammals and sensitive fish species. This has been secured by condition on many similar projects, see East Anglia Two as a recent example. We would expect the maximum hammer energy for monopile and pin piles to be secured within the project design conditions. |  | Max hammer energy is now secured in dML |  | No change. No further updates to DCO and dML submited at D1
RI_A8 | A8 | Within this condition there is usually a requirement to microsite the cables around features of conservation importance, as well as archaeological features. The condition as drafted only provides for exclusion of archaeological features. Natural England would note that even outside of benthic designated sites important conservation habitats such as Sabellaria spinulosa reef are protected under the NERC act and appropriate mitigation should be included. We would note this micro-siting has been included in most OWF DCOs as standard and would refer you to the East Anglia Two DCO for a recent example. Natural England advises amending the condition to include requirement to micro-site around features of conservation importance. |  | No change |  | No change. No further updates to DCO and dML submited at D1 |  | In progress, the Applicant has indicated that they will be including this condition. However, currently no update submitted into examination. |  | No change. |  | In progress. Micrositing is now included in the condition, however the delivery of this depends upon commitment to a pre-construction benthic survey designed to inform presence and extent of these features. This is yet to be specified in the IPMP. |  | No change. |  | Resolved. The IPMP now specifies appropriate survey for the purposes of verifying presence and extent of potential Annex 1 habitats.
RI_A9 | A9 | Natural England notes this allows for Operations and Maintenance Plan (OMP) to be provided based on the outline operations and maintenance plan (OOMP). The OOMP implies that cable protection may be deployed throughout the operational life of the windfarm. With regard to replenishment of existing cable protection Natural England has no concerns. However, deployment of new areas of cable protection should be limited to within a maximum period of ten years from the start of operations. This is Natural England’s standard position for cable protection deployment after construction outside of designated sites. This would apply to the deployment of scour protection in new areas as well. Please note within benthic designated sites further cable protection during the operational phase would require a new marine licence. Natural England advises that the condition is amended to make it clear new areas of cable protection can only be deployed up to ten years following submission of the updated OMP outside of designated sites. |  | No change. Addition to OOMP is useful but does not fulfill this standard requirement. |  | No change. No further updates to DCO and dML submited at D1 |  | Resolved: The Applicant has included wording which clarifies that any new cable protection and scour protection other than the replenishment of existing protection must be deployed within 10 years from the date that operation of the project commences.
RI_A10 | A10, A2 | Natural England notes that this condition provides that most of the plans and documentation submitted in condition 15 be submitted 4 months prior to the works. Natural England notes that due to the size and complexity of this project this time period is not appropriate. Given the large volume of documentation and the often complex nature of such we request this be amended to six months prior to commencement. Alternatively we are willing to discuss the required timing for each plan with the applicant and the MMO. We would refer to East Anglia Two as a recent example of an OWF development with a standard 6 months requirement. |  | In progress. Awaiting communication from applicant. |  | No change. No further updates to DCO and dML submited at D1 |  | In progress. Applicant has not yet submitted an updated timetable for pre-construction document submission into examination. |  | No change. |  | In progress. Some plans have been moved to a 6 month schedule for submission, although this is not the default proposition. See also NE's response to DC04 and our Deadline 5 cover letter. |  | No change. |  | Resolved.
RI_A11 | A11 | Natural England notes this condition allows for the use of the Marine Recovery fund as an alternative compensation. Natural England notes that there is ongoing work on strategic compensation and would support the inclusion of appropriate provisions to allow use of agreed strategic compensation. However, the wording here is insufficient, if that is its purpose. We have included details in Annex A1 below of some draft wording we proposed for a strategic benthic provision which could also be extrapolated into an appropriate provision for LBBG. Natural England recommends amending this provision and consideration of how to appropriately implement a provision allowing strategic compensation options. |  | No change. |  | No change. No further updates to DCO and dML submited at D1 |  | Issue resolved. The Applicant has included ammended wording as recommended in Annex 1 regarding the use of strategic compensation.

## B - Offshore Ornithology
Point | Point Number(s) from Appendix B | Taken from Natural England’s Relevant and Written Representations Morecambe Generation Appendix B - Offshore Ornithology | RAG Status Rel Rep | Update Following Procedural Deadline A | RAG Status D1 | Update Following D1 | RAG status D2 | Update Following D2 | RAG status D3 | Update Following D3 | Rag Status D4 | Update following D4 | RAG Status D5 | Update following D5 | RAG status D5a | Update following D5a | RAG status D6
RI_B4 | B4 | Natural England are satisfied that the project description is adequate for assessing impacts, including the worst-case design scenario parameters (i.e. the largest number of smaller turbines) provided for collision risk modelling.
RI_B5 | B5 | Natural England are satisfied that appropriate baseline data has been gathered for the purposes of ornithological impact assessment.
RI_B6 | B6 | Natural England consider that the Applicant has identified the key pressures, impacts and receptors.
RI_B7 | B7 | The rotation speed is given in this table as 7.74 whereas in the technical appendix Table 2.1 it is given as 7.64.
RI_B8 | B8, B24 | NE's advised approach to gap-filling for the CEA has not been followed. Natural England is concerned that some projects are effectively treated as having 0 impact based on highly uncertain qualitative assessments. Proxy data from nearby OWFs should be used in preference to assigning no impact to historic OWFs that lack assessments of collision and displacement impacts. Natural England is also concerned that approaches taken to filling data gaps by other projects to date (e.g., White Cross, Morgan, Mona) may not be aligned, leading to inconsistent assessments and confusion. We advise that all the Round 4 Irish Sea OWF projects should be considering the same data within their CEAs to ensure consistency across the assessments. The Applicant should therefore endeavour to work with other OWF projects in the Irish and Celtic Seas as well as relevant SNCBs to generate and agree impacts from historic projects for consideration in cumulative and in-combination assessments, following Natural England's advised approach.. |  | No change |  | In progress. Applicant has provided an update to the CEA with gap-filling in technical notes but this not yet reflected in updates to the ES chapter or assessments. Natural England will provide full comments on the CEA and gap-filling work at Deadline 3. |  | In progress. Updated CEA with gap-filling now follows NE preferred approach. It is not yet reflected in updates to the ES chapter or relevant assessment reports, but we anticipate this can be resolved once updates are made at a later deadline. |  | No change. |  | In progress. Updates have been propagated to the RIAA and we anticipate that the ES chapter will be updated at D5 |  | Resolved. ES chapter updated in line with Natural England advice.
RI_B9 | B9 | Some of the average mortality values the Applicant has calculated do not align with those recommended by Natural England. Through the EWG process with Round 4 wind farms, Natural England noted that there was some inconsistency between projects in the average mortality rates that were being used, despite them generally being based on the same source (Horswill and Robinson 2015). To rectify this, Natural England and NRW reviewed the evidence and calculation methods and produced standard mortality rates and reference populations for the key seabird species. An interim advice note containing this information was sent to the Applicant in April 2024 (see Annex B3). The differences between the Applicant’s values and Natural England’s are mostly minor and unlikely to make a material difference to the assessment. The most significant difference is for razorbill, where the Applicant has calculated an average mortality rate of 0.178, while Natural England recommend a value of 0.1302. We advise that the average mortality rates recommended in the NE and NRW interim advice note are used for the assessment (see Annex B3).
RI_B10 | B10 | There is some inconsistency in the months assigned to each season for gannet. Where a month overlaps with both a migration season and the breeding season, Natural England advise that it should be considered as the breeding season. The Applicant has shaded the seasons correctly in Table 12.16, but comparison of the seasonal mean peak abundances in Table 12.21 with the array +2km buffer abundances in Table 5.76 in the Technical Report show an inconsistency, as the mean peak abundances reported are higher than any abundance values detected in the relevant months for those seasons. Assigning abundances to the correct NE-advised seasons would mean that no gannets were detected in the wind farm array + 2km buffer in the Spring migration period of Dec-Feb, and far fewer gannets were detected in the Autumn migration period of Oct-Nov. We note that the correct NE-advised months have been used for assigning collision impacts to seasons. The assessment should be reviewed and updated as necessary. |  | Addressed by applicant in RR and Rule 9 response. No further comments on the proviso that this will be reflected in an updated ES in due course.
RI_B39 |  | Several of the total annual LCI and UCI values in the CRM results table appear to be incorrect.
RI_B11 | B11, B35 | NE has not been able to replicate the collision risk modelling results for little gull, so we are not providing comment on these results at Deadline 1. This may be due to an issue with the sCRM tool. NE does agree that due to poor undertsanding of the population and migration of little gull, the Liverpool Bay SPA is likely to be used by a greater number of birds transiting the site. We request that the Applicant provides log files for the little gull sCRM run, including full inputs and outputs. Furthermore, any methodological updates should be detailed, e.g. if a bespoke flight height distribution was used. Natural England therefore cannot comment on the impact of the Project on little gull until these issues are addressed. |  | No change at D1. Applicant has supplied flight height data directly to NE but not to the Examination. NE has not yet confirmed results. Furthermore, this data has not been presented in an updated assessment. |  | Natural England has confirmed the results of the sCRM run for little gull.
RI_B12 | B12 | The number of non-breeding collisions listed for great black-backed gull in this table is incorrect. |  | The Applicant has confirmed the error in the table, but that the correct value has been used in results.
RI_B13 | B13 | Natural England welcome the consideration of migratory birds and impact estimates derived by CRM. We note the low levels of predicted impact from the project alone relative to the contributing populations. Natural England are satisfied that the project alone will not result in any significant level of impact to migratory birds that are qualifying features of SPAs/Ramsar sites within 100km of the Project.
RI_B14 | B14 | Guillemot could be at risk of significant impacts due to cumulative displacement effects and should be considered in displacement assessments. Natural Englands recommended approach to gap-filling should be followed. |  | No change. |  | In progress. Applicant has provided an update to the CEA with gap-filling in technical notes but this not yet reflected in updates to the ES chapter or assessments. Natural England will provide full comments on the CEA and gap-filling work at Deadline 3. |  | In progress. NE agrees with the Applicants revised CEA conclusion, but this is not reflected in an updated ES chapter or relevant assessment reports, but we anticipate this can be resolved once updates are made at a later deadline. |  | No change. |  | In progress. We anticipate that the ES chapter will be updated at D5 |  | Resolved. ES chapter updated in line with Natural England advice.
RI_B15 | B15 | Natural England has some reservations regarding the use of the minimum EU wintering population for little gull to measure EIA-scale impacts against. However, this is a particularly data-poor species and no BDMPS population estimate or equivalent exists. We appreciate that the Applicant has made an effort to consider the issue and provided a value to indicate the scale of impact.
RI_B16 | B16 | Collision impacts to little gull are not currently considered in the CEA. Natural England advise that little gull abundance data from projects in the CEA is investigated and the assessment updated. |  | No change |  | In progress. Applicant has provided an update to the CEA with gap-filling in technical notes but this not yet reflected in updates to the ES chapter or assessments. Natural England will provide full comments on the CEA and gap-filling work at Deadline 3. |  | In progress. NE agrees with the Applicants revised CEA conclusion, but this is not reflected in an updated ES chapter or relevant assessment reports, but we anticipate this can be resolved once updates are made at a later deadline. |  | No change |  | In progress. Updates have been propagated to the RIAA and we anticipate that the ES chapter will be updated at D5 |  | Resolved. ES chapter updated in line with Natural England advice.
RI_B18 | B18, B37 | Significant effect on herring gull due to collision impacts cannot be ruled out based on the applicant's cumulative assessment. NE's approach to gap filling should be followed and more robust assessments may be need for herring gull depending upon the level of risk identified. |  | No change. |  | In progress. Applicant has provided an update to the CEA with gap-filling in technical notes but this not yet reflected in updates to the ES chapter or assessments. Natural England will provide full comments on the CEA and gap-filling work at Deadline 3. |  | In progress. NE agrees with the Applicants revised CEA conclusion, but this is not reflected in an updated ES chapter or relevant assessment reports, but we anticipate this can be resolved once updates are made at a later deadline. |  | No change |  | In progress. We anticipate that the ES chapter will be updated at D5 |  | Resolved. ES chapter updated in line with Natural England advice.
RI_B19 | B19 | Significant effects on lesser black-backed gull are not ruled out by the Applicants cumulative assessment. Natural England’s recommended approach to gap filling for cumulative assessments should be followed to produce a more comprehensive assessment. We note that it may then be necessary to undertake more robust assessments depending on the remaining level of risk and uncertainty. |  | No change |  | In progress. Applicant has provided an update to the CEA with gap-filling in technical notes but this not yet reflected in updates to the ES chapter or assessments. Natural England will provide full comments on the CEA and gap-filling work at Deadline 3. |  | In progress. NE agrees with the Applicants revised CEA conclusion, but this is not reflected in an updated ES chapter or relevant assessment reports, but we anticipate this can be resolved once updates are made at a later deadline. |  | No change |  | In progress. Updates have been propogated to the RIAA and we anticipate that the ES chapter will be updated at D5 |  | Resolved. ES chapter updated in line with Natural England advice.
RI_B20 | B20 | The breeding season reference population for great black-backed gull (GBBG) is overestimated due to a discrepancy in the presentation of this species in the referenced dataset. The non-breeding season BDMPS population for GBBG for SW UK & Channel of 17,742 individuals should be used as the annual reference population, in accordance with the recommendation within our interim advice note sent to the Applicant in April 2024. |  | No change |  | In progress. Applicant has updated the population figure in technical notes, but this is yet to be reflected in updates to the ES chapter or assessments. |  | No change |  | No change |  | In progress. We anticipate that the ES chapter will be updated at D5 |  | The ES chapter has been updated, however there is an error in the relevant paragraph 12.465. See Appendix B11 comment 8
RI_B21 | B21 | The cumulative assessment for GBBG is particularly affected by the approach of assigning negligible impacts to historic projects, based on qualitative assessments. There is potentially a significant underestimate of total mortality for this species, exacerbated by the assumption made in the PVA that such historic projects have zero contribution to mortality. Natural England consider that there are significant cumulative effects on GBBG at the EIA scale, especially when the correct BDMPS reference population of 17,742 birds is considered. Natural England’s recommended approach to gap filling for cumulative assessments should be followed to produce a more comprehensive assessment. We advise that the Applicant then re-runs PVA for GBBG using NE's recommended approach to gap-filling for historic projects and with this reference population as an input to indicate the significance of the adverse effect. We recommend that the applicant considers further avoidance or mitigation measures (e.g. increased air gap) to reduce the Project’s contribution to this significant cumulative effect. |  | No change |  | In progress. Applicant has provided an update to the CEA with gap-filling in technical notes but this not yet reflected in updates to the ES chapter or assessments. Natural England will provide full comments on the CEA and gap-filling work at Deadline 3. |  | In progress. Updated CEA with gap-filling now follows NE preferred approach, but is not yet reflected in updates to the ES chapter or relevant assessment reports. NE agree that this assessment indicates moderate adverse impact on great black-backed gull. This impact remains an outstanding issue. |  | No change |  | In progress. We anticipate that the ES chapter will be updated at D5 |  | The ES chapter has been updated. NE is content that the options for mitigation have been sufficiently investigated. However, significant effect cannot be ruled out at the EIA scale. See Appendix B11 comment 7. |  | No change - it remains Natural England's advice that significant adverse impacts at the EIA scale cannot be ruled out for GBBG.
RI_B23 | B23 | Natural England welcome the Applicant’s approach to HRA, in which a comprehensive list of SPAs has been considered for impacts. We note that due to the location of Morecambe OWF, protected sites from the other devolved administrations are screened into the assessment. We highlight that Natural England are the relevant SNCB to consult on impacts to English sites, but we cannot advise on integrity judgements on sites located in Wales, Scotland, Northern Ireland, the Isle of Man, or the Republic of Ireland.
RI_B25 | B25 | Natural England note that the Applicant continues to advocate for a method that effectively reduces the total area over which displacement impacts to red-throated divers are felt at the SPA by considering the diminishing displacement effect with distance from the array. Natural England highlight that the relevant conservation objective of most concern is to “Restore the distribution of the feature; preventing further deterioration, and where possible, reduce any existing anthropogenic influences impacting feature distribution.” (https://publications.naturalengland.org.uk/publication/3236717) Whilst we recognise the desire to factor in the diminishing displacement effect to the assessment somehow, we remain of the opinion that the calculation of an ‘effective displacement area’ for red-throated diver is fundamentally flawed. There is no logical way to proportionally reduce the area of habitat loss by the expected level of displacement. Some level of displacement is occurring over the full extent of the area. Ultimately, calculating a (reduced) area of effect in this way underestimates the simple % of the SPA that is subject to displacement effects.
RI_B26 | B26 | Lesser black -backed gull breeding population estimates are out of date. Natural England advise that the most recent SPA population counts for lesser black-backed gull of 862 AONs (equivalent to 1,724 breeding adults) for Morecambe Bay and Duddon Estuary SPA and 2,319 AONs (equivalent to 4,638 breeding adults) for Ribble and Alt Estuaries SPA are considered by the assessment where appropriate (e.g. when interpreting the outcomes of PVA models). |  | No change |  | In progress. Colony counts have been updated in the HRA technical note, but this is yet to be reflected in updates to the ES chapter or RIAA. |  | No change |  | In progress. The correct counts now appear in the without prejudice derogation case. However, they are not yet reflected in the ES or RIAA. |  | Resolved. Updates have been propagated to the RIAA.
RI_B27 | B27 | For lesser black-backed gull in-combination assessments, the Applicant has used the Morecambe project as a proxy for apportioning the impacts of other projects to the Morecambe Bay and Duddon Estuary SPA. However, the cluster of windfarms in question (Ormonde, Walney 1&2, Walney Extension, West of Duddon Sands) are significantly closer to the SPA colonies than the Morecambe project and are therefore likely to have a higher proportion of the birds they impact associated with this SPA. This may lead to severe underestimation of in-combination impacts. Natural England advise that an appropriate value for apportioning birds from Walney 1 & 2 (as the central OWF in the cluster) to Morecambe Bay and Duddon Estuary SPA is calculated, and that this value is used as the proxy value for other wind farms in the cluster. |  | No change |  | In progress. An appropriate proxy has been calculated, but this yet to be reflected in updates to the RIAA. |  | No change |  | No change. |  | Resolved.
RI_B28 | B28 | As noted in our PEIR response, the study by Clewley et al (2020) covered the period from 2016-2019 so there is no overlap with the aerial surveys carried out for the project. During that time connectivity with existing wind farms was found for >50% of the birds from the South Walney colony surveyed. The authors of the study noted that lesser black-backed gulls are more likely to forage offshore when rearing chicks. The study coincided with a period of very poor productivity at the South Walney colony. Productivity has since improved; hence it is possible that more offshore foraging was occurring at the time when the Project baseline characterisation surveys were carried out, and this could be expected to continue in the operational lifetime of the Project if the Walney colony continues to recover.
RI_B29 | B29 | Impacts to lesser black-backed gull have been apportioned to colonies from which Natural England considers it highly unlikely that birds will be present in the project area. Natural England advise that in the absence of evidence, expert judgement is applied to critically appraise the likelihood of colonies contributing to the population observed within the project study area. Colonies considered unlikely to display connectivity, despite technically being within potential foraging range, should be disregarded during apportioning. |  | In progress. Natural England has provded a list of relevant colonies in our Rule 9 letter response. There is potential for resolution once this is reflected in an updated assessmnet. |  | In progress. The list of colonies has been used in the technical note, but this is yet to be reflected in updates to the ES chapter or RIAA. |  | No change |  | No change. |  | Resolved. Updates have been propagated to the RIAA.
RI_B30 | B30 | The Applicant has committed to an air gap of 25m above HAT. However, their impacts on collision-sensitive species including from SPA colonies could be decreased further by increasing the air gap further. The Applicant should consider further increases to the air gap as a means of further mitigation. |  | No change |  | Applicant has provided analysis demonstarting that this measure would not provide meaningful further mitigation. See RI_B21 for our advice on this impact.
RI_B31 | B31 | The Applicant has presented a vessel management plan for minimising impacts on displacement-sensitive species, based on best practice guidance. It is not clear that the proposal is sufficient from the information presented. Potential ports for construction, operation and maintenance activity should be considered to determine if the best practice measures proposed can be implemented and adhered to. Natural England advise that further mitigation may be required such as seasonal restrictions to avoid impacts at particularly sensitive areas within the Liverpool Bay SPA. |  | No change |  | No change. No further analysis has been provided, and therefore it is unclear whether further commitments to reduce disturbance impacts beyond reliance on best practice measures are needed. |  | No change. |  | No change. |  | No change. |  | No change. We expect that the applicants D5a submission will address this issue.
RI_B32 | B32 | The Applicant concludes no AEOI from the project alone on red-throated diver at the Liverpool Bay SPA. Natural England does not agree with this conclusion. Natural England conclude that the project alone will impact red-throated diver distribution over 9.07% of the total SPA, and in particular 1.24% of the original SPA area, where red-throated diver densities were sufficiently high for these areas to qualify for inclusion within the SPA. As a result, we cannot rule out AEOI from the project alone. We note that the projects impact is slightly reduced when considered in-combination as some areas of impact are closer to other OWFs. We advise that it is appropriate that displacement impact is assigned to the OWF in closest proximity. |  | No change |  | No change. Applicant has provided further rationale for their position. |  | No change |  | No change. |  | Resolved with respect to AEOI from the project alone. Natural England continues to advise that there is an AEOI for RTD at Liverpool Bay as an in-combination effect. This issue is therefore now considered in updates to RI_B34
RI_B33 | B33 | Natural England note that 53.29% of the SPA boundary is impacted by (in-combination) OWF displacement effects on red-throated divers, with 42.55% of the original SPA being impacted. The Applicant calculates that the project contributes 8.75% and 1.06% to those in-combination totals respectively. This is slightly smaller than the project-alone impact as parts of the impacted buffer area are closer to other OWFs. We agree with the Applicant's position that the most concerning effect is that upon the original SPA boundary area. Natural England advise that the Applicant considers any opportunity to mitigate the impact on red-throated diver displacement within the original SPA boundary area, by increasing the distance between this part of the original SPA and potential turbine locations. |  | No change |  | No change. Applicant has provided further rationale for their position. |  | No change |  | No change. |  | No change. |  | No change. No updates provided at D5. |  | Whilst maintaining their position that an increased buffer distance is not required, the Applicant has presented a series of buffer distances at Deadline 5a. NE has advised that several of these could avoid an in-combination AEOI on the Liverpool Bay SPA were they to be secured.
RI_B34 | B34 | Natural England have advised that AEOI cannot be ruled out in-combination for red-throated diver at Liverpool Bay SPA since the Burbo Bank Extension OWF examination. Further, we understand from NRW and JNCC that the advice given to the Awel y Môr OWF related to specific factors in that area, namely the low numbers of divers encountered in the area and the findings of the post-construction monitoring of the Gwynt y Môr windfarm. As a result, the SNCBs concluded that Awel y Môr would not significantly affect the distribution of RTD in this particular area. It should be borne in mind that Morecambe OWF is impacting the northern part of the SPA, which to date, has been less impacted than the south. Given the ‘restore’ conservation objective for feature distribution, Natural England advise that efforts are made to mitigate the impacts of the project with respect to displacement of red-throated divers. We consider this especially critical with respect to the original SPA boundary area. |  | No change |  | No change. Applicant has provided further rationale for their position. |  | No change |  | No change - please see Appendix B9 for our position on in-principle compensation measures submitted at Deadline 3. |  | No change. NE's updated position on RTD impacts has been submitted at Annex B10. Detailed commentary on the proposed compensation measures has been submitted at Annex B4. |  | No change. No updates provided at D5. |  | See row above. See also commentary in orni compensation tab for updates regarding RTD compensation issues.
RI_B35 | B35 | Natural England cannot comment conclusively on the impact of the Project on little gull until NE Ref B11 regarding the sCRM methodology used for this species has been addressed. Natural England agrees with the Applicant that the population and migration patterns of this species are poorly understood, the SPA population is likely to be an underestimate, and that the area is likely to be used by a much larger number of gulls on a transitory basis.
RI_B36 | B36 | The results of the Applicants population viability analysis indicates a significant reduction in population size and growth rate for lesser black-backed gull. Natural England therefore considers that AEOI cannot be ruled out for this species at Morecambe Bay and Duddon Estuary SPA due to in-combination collision impacts. Whilst the contribution of the project Project is small, we retain concerns about the approach used for apportioning of impacts. Natural England advise that the apportioning is critically evaluated (RI_B27). Any changes will be reflected in the mortality increase calculation. We can then advise on the project alone impacts in the context of the likely AEOI in-combination. |  | No change |  | In progress. Updates to CEA including gap-filling approach are made in technical notes but are not yet reflected in updates to the ES chapter and RIAA. |  | In progress. Updated CEA with gap-filling now follows NE preferred approach, but is not yet reflected in updates to the ES chapter or relevant assessment reports. NE disagrees that this assessment rules out AEOI for lesser black-backed gull at Morecambe Bay and Duddon Estuary SPA |  | No change. |  | In progress. Updates have been propogated to the RIAA and we anticipate that the ES chapter will be updated at D5. However, NE maintains disagreement with the conclusion. NE is content with the apportioning for the Project, but we maintain our view that apportioning for other projects in the in-combination assessment does not follow best practice. We nonetheless believe that it is possible to reach conclusions regarding the in-combination assessment for LBBG protected sites. |  | No change. Updates have been propagated to the ES chapter but RAG status is driven by disagreement with conclusion of the RIAA. |  | No change - we maintain our advice that AEOI in-combination cannot be ruled out.
RI_B38 | B38 | Natural England considers that AEOI cannot be ruled out for LBBG at Ribble and Alt Estuaries SPA due to in-combination collision impacts. Whilst the contribution of the project Project is small, we retain concerns about the approach used for apportioning of impacts. Natural England is particularly concerned regarding impacts to this SPA given the recent population declines and noting that the projects impacts are predominantly apportioned to this SPA. Natural England advise that the apportioning is critically evaluated (RI_B27). Any changes will be reflected in the mortality increase calculation. We can then advise on the project alone impacts in the context of the likely AEOI in-combination. |  | No change |  | In progress. Updates to apportioning have been made in technical notes but are not yet reflected in updates to the ES chapter and RIAA. Natural England will provide full comments on the CEA and gap-filling work at Deadline 3. |  | In progress. Updated CEA with gap-filling now follows NE preferred approach, but is not yet reflected in updates to the ES chapter or relevant assessment reports. NE disagrees that this assessment rules out AEOI for lesser black-backed gull at Ribble and Alt Estuaries SPA |  | No change. |  | In progress. Updates have been propogated to the RIAA and we anticipate that the ES chapter will be updated at D5. NE maintains disagreement with the conclusion. |  | No change. Updates have been propagated to the ES chapter but RAG status is driven by disagreement with conclusion of the RIAA. |  | No change - we maintain our advice that AEOI in-combination cannot be ruled out.
RI_B39 |  | New issue at Deadline 4: The Applicant has stated that they consider that additional monitoring of collision impacts would not be required. As Natural England considers that the predicted impacts of the Project on the lesser black-backed gull feature of Morecambe Bay and Duddon Estuary presented by the Applicant are likely to be an underestimate of the potential impacts that could be expected to occur by the time the Project is operational, there could be value in using monitoring to determine whether this is the case. As it is unknown by what amount the predicted figures may underestimate the true impact, this represents a key uncertainty which monitoring could address. We advise the Applicant to consider methods to address this uncertainty, to confirm whether it is the case that more gulls may be found on the site during the breeding season at the time of construction/operation and whether the predicted collision impacts are accurate. | [7 empty] | New issue |  | In progress. Natural England is aware of the challenges around monitoring impacts in a way that produces meaningful evidence and would welcome the Applicant contributing to wider scale monitoring as a way of resolving this issue. |  | NE has provided commentary on this issue in our response to ExQ3 3BEM2. Whilst we do not consider it fully resolved as the measures will be detailed post examination, we do not anticipate that further progress will be made before the close of the Examination. |  | We have updated the RAG status to yellow which is better reflective of NE's position at the end of the Examination. Whilst the proposed monitoring will only be detailed post-Examination, in this instance we consider this is an acceptable level of risk.
RI_B40 |  | New issue at Deadline 4: Only post-construction monitoring is considered to be required for red-throated diver by the Applicant. It is unlikely that any changes in abundance and distribution could be determined without both pre and post construction monitoring. NE therefore advises that pre-construction monitoring is also included as required. | [7 empty] | New issue |  | No change. |  | NE has provided commentary on this issue in our response to ExQ3 3BEM2. Whilst we do not consider it fully resolved as the measures will be detailed post examination, we do not anticipate that further progress will be made during Examination. |  | We have updated the RAG status to yellow which is better reflective of NE's position at the end of the Examination. Whilst the proposed monitoring will only be detailed post-Examination, in this instance we consider this is an acceptable level of risk.

## Annex B1- Orni Compensation
Point | Point Number(s) from Appendix B1 | Taken from Natural England’s Relevant and Written Representations Morecambe Generation Appendix B1 - Offshore Ornithology Compensation | RAG Status Rel Rep | Update Following Procedural Deadline A | RAG Status D1 | Update Following D1 | RAG status D2 | Update Following D2 | RAG status D3 | Update Following D3 | Rag Status D4 | Update following D4 | RAG Status D5 | Update following D5 | RAG status D5a | Update following D5a | RAG status D6
Compensation measure: Feature Exclusion of mammalian predators at colonies using fencing
RI_G6 | Overall confidence in the measure | Natural England is moderately confident in this measure. We are content that the measure is likely to be effective, but we do not agree that the compensation level proposed and therefore the scale and extent of the measure is appropriate. Furthermore, no landowner agreement has been secured for the evaluated sites and this would be required to provide sufficient certainty that the measure is deliverable. |  | Summary comment. |  | In progress. Area quoted for Banks Marsh has potential to deliver compensation at sufficient scale, although there has been less progress on this option. No changes to scale of Steep Holm measure proposed. Applicant has confirmed formal landowner permission for Banks Marsh and in principle support of Steep Holm landowner. No updates to the proposed compensation level have been made. |  | No change. |  | No change. |  | In progress. See answer to 2HRA1 in Appendix B10. NE is confident that it is possible to deliver the measures at appropriate scale at Steep Holm. Therefore this issue is resolvable once the required scale of the intervention is agreed and secured in a plan. |  | Advice on compensation quantum and necessary scale and extent of measure has been provided at Appendix B12 of our D5a submission. We are confident that were the Applicant to propose this measure at the indicated scale and extent, this issue can be resolved. |  | Resolved. The Applicant has submitted plans that indicate the extent of the measure to be delivered will be in excess of that advised by Natural England at Deadline 5a.
RI_G7 | Theoretical merit to deliver compensation | This measure is likely to be effective and could directly benefit either the impacted population of the lesser black-backed gull (LBBG) feature of the Morecambe Bay and Duddon Estuary SPA (M&DE) or the Ribble and Alt Estuaries SPA (R&AE) if the fence was inside one of them, or the wider meta-population from which the SPAs draw their recruits if located in the vicinity. Vegetation within the fenced area would need to be monitored and some works outside the breeding season may be necessary to create optimum nesting habitat. This has been considered by the Applicant.
RI_G8 | Technical feasibility | We welcome the Applicant’s undertaking that proposed predator-proof fence design would be informed through discussion with the proposed lesser black-backed gull compensation steering group (LBBGCSG) and with reference to RSPB guidance should this compensation measure be adopted. We suggest that fence design receives careful consideration, and we highlight how capable badgers in particular can be in their ability to climb high fences. We recognise that recent predator-exclusion fencing at South Walney (M&DE SPA) appears to have contributed to an increase in nesting LBBG demonstrates that this measure can be successful in increasing the number of nesting pairs, at least in the short-term.
RI_G9 | Agreed compensation level, G2, G3 | An appropriate impact value is yet to be agreed for lesser black-backed gull at Morecambe Bay and Duddon Estuary SPA and Ribble and Alt Estuaries SPA. Natural England's advice is that the project alone impacts are currently an underestimate, meaning that the proposed compensation level is likely to be inadequate once the impact values are updated following our advice (see our Relevant Representations and Risk and Issue log tab B). Once an appropriate impact value is identified, Natural England advise that for the purposes of scaling compensatory measures, the precautionary upper confidence limit impact is the appropriate level of mortality to consider. Increases in numbers of LBBG within the recently fenced area at South Walney within the M&DE SPA, and the proposed ‘mega-fence’ at Banks Marsh within the R&AE SPA, means that the impacts on lesser black-backed gull from the project apportioned to each SPA, both alone and in-combination, are likely to increase. Therefore the compensation level is likely to be inadequate as a future-proof measure on this basis as well. We also have concerns about how the level of compensation has been calculated. A very basic calculation has been undertaken to determine the size of the breeding population that will be required to generate the required number of adults into the population each year. Only productivity and survival are considered. We advise that the method used by Hornsea 3 OWF to calculate requirements for their kittiwake compensation is also relevant to LBBG, and we recommend that this be used instead by the Applicant. Under these circumstances, it is difficult to agree with the proposed requirement to create an additional 18 lesser black-backed gull nests annually to compensate for the loss of 4 adult gulls. |  | No change |  | No change. No updates to the proposed compensation level have been made. |  | No change. |  | No change. |  | In progress. The updated RIAA now includes the correct impact level. NE will provide advice on the appropriate calculations to be used for the compensation quantum at D6. |  | Advice on the compensation quantum and necessary scale and extent of measure has been provided at Appendix B12 of our D5a submission. We are confident that were the Applicant to propose this measure at the indicated scale and extent, this issue can be resolved. |  | Resolved. The Applicant has submitted plans that indicate the extent of the measure to be delivered will be in excess of that advised by Natural England at Deadline 5a.
RI_G10 | Scale/extent of measure, G2, G3 | A site has not yet been secured, so we cannot advise on the scale of nesting habitat provision. We acknowledge that the size of the fenced areas required (assuming one of the sites in question can be secured), has been considered and would likely be adequate to deliver the proposed compensation level, even at lower LBBG nesting densities. Following our advice on the likely inadequacy of the proposed compensation level, the scale at which this measure is required to be delivered is also likely to be an underestimate. Increased foraging distances are likely to occur with increased numbers of birds at the impacted SPA colonies, meaning more birds are likely to encounter OWFs, increasing collision risk. Relocation of adults from other nearby sites with less suitable habitat is not considered in the proposed compensation ratio. We therefore advise that compensation levels could be future-proofed by considering an increase in extent of the measure (and see also comments on the proposed scrub clearance measure on Steep Holm below). |  | No change |  | In progress. Area quoted for Banks Marsh has potential to deliver compensation at sufficient scale, although there has been less progress on this option than for Steep Holm, where the scale of the measure proposed has remained the same |  | No change. |  | No change. |  | In progress. See commentary for RI_G6. |  | Advice on the compensation quantum and necessary scale and extent of measure has been provided at Appendix B12 of our D5a submission. We are confident that were the Applicant to propose this measure at the indicated scale and extent, this issue can be resolved. |  | Resolved. The Applicant has submitted plans that indicate the extent of the measure to be delivered will be in excess of that advised by Natural England at Deadline 5a.
RI_G11 | Timing: Deliverable before impact | LBBG reach breeding age maturity at 4 years old and it is unlikely that offspring fledging from the compensation site will have recruited into the adult breeding population (and thereby started providing compensation) by the time the development is operational. This is of particular relevance in light of concerns that a compensation site has yet to be secured for this measure (see below). However, we welcome the consideration of potential mortality debt under these circumstances detailed, and acknowledge that two separate compensation measures have been proposed. We consider that both are feasible options that, if successful, could potentially deliver in excess of the currently proposed compensation level, thereby addressing any accrued mortality debt early in the operational lifespan of the project. If the compensation ratio were to be found inadequate and thus recommended for a modest increase, there could be a greater initial mortality debt. We consider this debt could still be compensated for if the measure was implemented at appropriate scale.
RI_G12 | Location of measure, G1 | No landowner agreement has been secured for this measure, without this Natural England cannot be confident that it is deliverable. This should be secured as soon as possible. |  | No change |  | In progress. The Applicant refers to letter from landowner confirming in principle agreement to delivery of the measures
RI_G13 | Long term implementation | We welcome the commitment to the regular monitoring of the integrity of the fence both for predator incursion and for the state of vegetation within the compensation site, noting that even a single night of predator ingress could significantly undermine colony re-establishment. We also welcome the commitment to long-term monitoring. We recommend that the BTO ringing and colour-ringing scheme and re-sightings surveys should continue beyond the first 3 years of implementation of the compensation plan, and until such time as quantum is achieved (including the discharging of any mortality debt), to ensure that those juveniles colour-ringed at the site can be followed through to at least 4 years of age when breeding could commence. This would help document that the compensation measure had contributed additional adults into the impacted population. We are aware that colour ringing has been ongoing for many years at South Walney and is already underway on Steep Holm. Initially, hatching and fledging success should be monitored by three visits throughout the breeding season to count eggs, hatched eggs and fledging young. Drones could be used for this purpose and novel methods, such as thermal drone surveys, could be explored if it is considered they provide more accurate results. Initial ground-truthing of drone surveys would be required to calibrate the detection rate of nests/young. We recognise that individual colony performance should be considered holistically in relation to other LBBG colonies, but welcome the undertaking to explore reasons for failure and consequent adaptive management measures if considered necessary.
RI_G14 | Success criteria/Ability to prove additionality | See above.
RI_G15 | Suitable as sole measure for target species | Subject to a suitable site being secured, Natural England consider that this measure alone could theoretically deliver an appropriate level of compensation.
Compensation measure: Feature Scrub clearance and habitat management on Steep Holm
RI_G16 | Overall confidence in the measure | We are confident that this measure will be effective, but we do not agree that the proposed compensation level or extent is appropriate. |  | Summary comment. |  | In progress. No changes to scale of Steep Holm scrub clearance measure proposed. No updates to the proposed compensation level have been made. In principle support of the landowner has been confirmed. |  | No change. |  | No change. |  | In progress. See commentary for RI_G6. |  | Advice on the compensation quantum and necessary scale and extent of measure has been provided at Appendix B12 of our D5a submission. We are confident that were the Applicant to propose this measure at the indicated scale and extent, this issue can be resolved. |  | Resolved. The Applicant has submitted plans that indicate the extent of the measure to be delivered will be in excess of that advised by Natural England at Deadline 5a.
RI_G17 | Theoretical merit to deliver compensation | Steep Holm SSSI sits within the Severn Estuary SPA. Neither designation have LBBG as a designated breeding feature. Nor does the Severn Estuary Ramsar site, however it was identified for a possible future consideration as a breeding feature. In 1993, 2,040 pairs of lesser black-backed gull bred on the islands of Flat Holm and Steep Holm, representing 2.5% of the British total. Since then, numbers fluctuated on Steep Holm, increased on Flat Holm, but both have suffered notable declines in recent years (SMP database). Therefore the proposed intervention has the potential to result in increases in the LBBG population. Although LBBG appear to show high philopatry, primarily recruiting into the breeding population at the natal site, it is entirely possible that individuals fledging from Steep Holm could recruit into other nearby lesser black-backed gull colonies such as the Skomer, Skokholm and the Seas off Pembrokeshire SPA or Isles of Scilly SPA, thereby contributing to the coherence of the site network. Further, given Steep Holm sits within the Severn Estuary SPA, should the population be increased to a level where it was considered to qualify as a new feature of the SPA, these LBBGs could themselves form part of the network in due course.
RI_G18 | Technical feasibility | We welcome the Applicant’s undertaking that scrub clearance would be informed through discussion with the LBBGCSG should this compensation measure be adopted. We also recognise that habitat variables are important and welcome discussion on how a proportion of the plateau area on Steep Holm could be cleared of scrub and subsequently be subject to further enhancements. We agree that encroachment of scrub appears to be a key factor in the decline in lesser black-backed gull nests on Steep Holm and suggest that scrub clearance and habitat management is likely to be an effective measure, thereby potentially addressing impacts on lesser black-backed gull by improving productivity. We understand that the proposed works should be able to achieve SSSI consent, as potential impacts to the vascular plant assemblage SSSI feature can be avoided. Sufficient monitoring of both the plateau and cliffs during the initial years of scrub clearance should provide sufficient evidence that the measure is successful. It is worth noting that under current arrangements, Steep Holm is served by a RIB from both Weston-super-Mare and Cardiff. Trips are highly dependent on prevailing weather conditions (wind/swell) and the state of the tide, with beach availability always restricting landings on the island, and a primary consideration when travelling from Weston-super-Mare. We appreciate that coordinating scrub clearance works under these conditions may be challenging but suggest that, should this measure be adopted, opportunities for scrub clearance are maximised at an appropriate time of year (September to February), subject to landowner agreement, whenever they become available within this timeframe to mitigate the risk that no works are possible due to inaccessibility. We understand that a potential contractor for works has been identified who is able to be flexible regarding the timings of works. If appointed, it may be necessary for them to be flexible with respect to embarkation point as well.
RI_G19 | Agreed compensation level, G2, G3 | See comments on compensation level for the measure “exclusion of mammalian predators at colonies using fencing” above. |  | No change |  | No change. No updates to the proposed compensation level have been made. |  | No change. |  | No change. |  | In progress. The updated RIAA now includes the correct impact level. NE will provide advice on the appropriate calculations to be used for the compensation quantum at D6. |  | Advice on the compensation quantum and necessary scale and extent of measure has been provided at Appendix B12 of our D5a submission. We are confident that were the Applicant to propose this measure at the indicated scale and extent, this issue can be resolved. |  | Resolved. The Applicant has submitted plans that indicate the extent of the measure to be delivered will be in excess of that advised by Natural England at Deadline 5a.
RI_G20 | Scale/extent of measure, G2, G3 | Following our advice on the likely inadequacy of the proposed compensation level, the scale at which this measure is required to be delivered is also likely to be an underestimate. Increased foraging distances are likely to occur with increased numbers of birds at the impacted SPA colonies, meaning more birds are likely to encounter OWFs, increasing collision risk. Relocation of adults from other nearby sites with less suitable habitat is not considered in the proposed compensation ratio. Nesting birds from the cliff at Steep Holm could relocate to the plateau, which would need to be accounted for. We recommned that the cliff nesting birds are surveyed (likely using a drone due to practical considerations) to monitor this effect and it's implications for the level of compensation actually being delivered. Up to 40 muntjac deer are estimated to be resident on Steep Holm. Birds’ eggs can reportedly constitute a part of a muntjac’s diet. We would recommend that hatching success is monitored at nest sites with no muntjac access (e.g. on the roofs of suitable buildings) and compared with hatching success from ground nests on the plateau, to assess the possibility that muntjac are predating or destroying some eggs. We accept however that such sites may not exist and that fenced enclosures on Steep Holm would be impractical (if not impossible) due to the thin soil and limestone bedrock. Due to these factors, we advise that a greater extent for this measure than currently proposed should be considered. |  | No change |  | No change. No increase to the extent of the measure has been proiposed. |  | No change. |  | No change. |  | In progress. See commentary for RI_G6. |  | Advice on the compensation quantum and necessary scale and extent of measure has been provided at Appendix B12 of our D5a submission. We are confident that were the Applicant to propose this measure at the indicated scale and extent, this issue can be resolved. |  | Resolved. The Applicant has submitted plans that indicate the extent of the measure to be delivered will be in excess of that advised by Natural England at Deadline 5a.
RI_G21 | Timing: Deliverable before impact | LBBG reach breeding age maturity at 4 years old, and offspring fledging from the compensation site will not have recruited into the adult breeding population (and thereby started providing compensation for the project’s in-combination impacts) by the time the development is operational. However, we welcome the consideration of potential mortality debt under these circumstances and acknowledge that two separate compensation measures have been proposed. We consider that both are feasible options that, if successful, could deliver in excess of the currently proposed compensation level, should that be agreed, thereby addressing any accrued mortality debt early in the operational lifespan of the project. However, if the currently proposed compensation ratio were to be found inadequate, there would be a greater mortality debt. We consider this debt could still be compensated for if the measure was implemented at appropriate scale.
RI_G22 | Location of measure | We welcome that landowner agreement has already been secured with the Keneth Allsop Memorial Trust for this measure and are aware that further positive discussions are taking place.
RI_G23 | Long term implementation | We welcome the commitment to long-term monitoring. We also recommend that the BTO ringing and colour-ringing scheme and re-sightings surveys should continue beyond the first 3 years of implementation of the compensation plan, and until such time as quantum is achieved (including the discharging of any mortality debt), to ensure that those juveniles colour-ringed at the site can be followed through to at least 4 years of age when breeding could commence. This would help document that the specific measure had contributed additional adults to the colony directly as a result of the compensation. We are aware that colour ringing has been ongoing for many years at South Walney and already underway on Steep Holm. Initially, hatching and fledging success should be monitored by three visits throughout the breeding season to count eggs, hatched eggs and fledging young. Drones could be used for this purpose and novel methods, such as thermal drone surveys, could be explored if it is considered they provide more accurate results. Initial ground-truthing of drone surveys would be required for the plateau, at least initially, to identify a correction factor to accurately calibrate the detection rate of nests/young. These could then be applied to drone surveys of the cliffs, as ground-truthing would be impossible there. We recognise that individual colony performance should be considered holistically in relation to other lesser black-backed gull colonies but welcome the undertaking to explore reasons for failure and consequent adaptive management measures if considered necessary, although we note that supplementary feeding would not be practical on Steep Holm.
RI_G24 | Success criteria/Ability to prove additionality | See above.
RI_G25 | Suitable as sole measure for target species | Successful clearance of scrub and subsequent habitat management of an appropriately sized area could theoretically deliver the currently proposed scale of compensation for impacts on lesser black-backed gull alone.
Additional detailed comments (table 2 Relevant Reps B1)
RI_G4 | G4 | It is stated that Steep Holm; “accommodated over 1,500 nesting pairs of lesser black-backed gulls in 1995 when the island was relatively free of scrub” and references the Severn Estuary SPA citation as a source. Neither the referenced citation nor the Seabird Monitoring Programme database support this count for that year. We do accept that the count of lesser black-backed gull on Steep Holm has historically been higher. e.g. 596 AONs/pairs in 2018 (880 AONs/pairs in 1997 was part of a gap-filling exercise), and that scrub encroachment is likely to be a contributory factor in the decline. |  | Applicant acknowledged error, issue resolved provided this is reflected in updated plan
RI_G5 | G5 | The proposed monitoring measure is proposed for the first three years following implementation only. This would not allow sufficient time to see whether juveniles fledging from the compensation site(s) were being recruited into the breeding population after 4 years (as one might expect from a species exhibiting high philopatry). Colour ringing of gulls has been on-going at South Walney for some years (by RSPB/North West Gull Project) and for 2 years on Steep Holm already (by Severnside Ringing Group). The number of productivity monitoring visits should be specified as it is not currently stated. |  | No change |  | No change. No updates to the monitoring of these measures have been made. |  | No change. |  | No change. |  | No change. |  | No change. |  | The Applicant has updated the CIMP to state that monitoring will be undertaken for a minimum of four years following implementation of the measure, with the requirement for further monitoring after this period to be determined by the Steering Group. Natural England advises that further monitoring is likely to be required to provide confidence that fledged birds are recruiting back into the meta-population. NE considers that a minimum of 4 visits will be necessary to quantify hatching (2 visits) and fledging success (2 visits). All such visits will also provide opportunities for visual monitoring and recording of previously ringed chicks to evidence recruitment into the natal colony.
Compensation measure: Provision of nesting rafts for red-throated diver
RI_G26 |  | New issue at Deadline 4: The Applicant has submitted a brief outline structure for the compensation implementation and monitoring plan. Whilst the structure is appropriate, we are concerned that it contains no detailed content. The plan should be populated as far as is possible before the close of the Examination. | [7 empty] | New issue |  | No change. |  | No change. |  | A more detailed CIMP for this measure has now been submitted. There are still aspects of the CIMP that require development, so further work from the Applicant as regards specific locations and interventions to ensure that the measures can be secured must be undertaken as a priority.
RI_G27 |  | New issue at Deadline 4: We welcome the Applicant’s consideration of strategic compensation as an alternative measure. We consider that this would be a desirable solution if deliverable within the timescale of the Project. We support the principle of the Applicant making a contribution to a strategic fund, noting that as the Library of Strategic Compensation Measures (LoSCM) expands, measures relevant to red-throated diver may become available in due course. We recommend that the Applicant monitors the progress of the COWSC (Collaboration on Offshore Wind Strategic Compensation) initiative as regards suitable options, and if measures are emerging, consider what an appropriate contribution might entail. | [7 empty] | New issue |  | No change. |  | No change. |  | No update was provided by the Applicant at D5a. NE recognises that the availability of strategic compensation options remains uncertain so there is little the Applicant can do to progress this within this examination. However, we would welcome further engagement with the Applicant and other parties to discuss strategic compensation options once more information on them becomes available.
RI_G28 |  | New issue at Deadline 4: The Applicant should carefully consider whether the presence of American mink in some areas may significantly compromise the measure, and if there is a residual risk in some locations, give consideration to potential adaptive management solutions if mink predation proves to be a threat to the success of the measure. We advise that local stakeholders, including NatureScot, are consulted regarding sites where mink predation may be an issue and that this informs site selection and/or potential adaptive management solutions. | [7 empty] | New issue |  | No change. |  | The Applicant has confirmed that predator monitoring and management may be required as adaptive management. Natural England continue to recommend the consideration of local predator populations, and any exisiting management of those populations, when short listing sites.
RI_G29 |  | New issue at Deadline 4: As the proposed measure involves installing nesting rafts near SPAs designated for breeding divers, there may be some potential for the rafts to attract divers that would otherwise breed within an SPA. Even if those birds did show improved breeding success, this would nonetheless be an undesirable outcome for the NSN as fewer birds would be breeding within protected sites. It is not clear what distance from breeding RTD SPAs the Applicant has used to prevent the risk of unintended consequences, such as attracting divers out of protected locations. This should be clarified and an evidence-based rationale provided. We advise that the relevant SNCB (NatureScot) should be consulted regarding potential impacts on Scottish protected sites. | [7 empty] | New issue |  | No change. |  | No change. |  | The Applicant has committed to providing an analysis of unintended consequences on SPAs, which is welcomed, but because the final locations for nest rafts have not yet been confirmed and the analysis has not been performed, NE cannot comment on whether the planned measures will affect other SPAs in this way, noting that this would ultimately be a matter for Naturescot to advise on.
RI_G30 |  | New issue at Deadline 5: We consider that further information on the selected locations for RTD compensation and the rationale for these is much needed. This should include, among other elements, any risk of unintended consequences (e.g. drawing divers out of SPAs into areas where they are not protected), predation risk, particularly regarding American mink in mainland locations, and potential negative consequences of inappropriate habitat management. | [9 empty] | New issue |  | No change. |  | The Applicant has indicated that an assessment of the risks presented by the locations for the measure will be carried out. Because the final locations for nest rafts have not yet been confirmed and the assessment has not been performed, NE cannot comment further on the suitablility of the final locations.

## C - Fish and Shellfish Ecology
Point | Point Number(s) from Appendix C | Taken from Natural England’s Relevant and Written Representations Morecambe Generation Appendix C - Fish and Shellfish Ecology | RAG Status Rel and Wri Rep | Update Following Procedural Deadline A | RAG Status D1
NB All risks and issues identifed as yellow or green RAG at Relevant Reps, therefore NE will not make further comment on this subject unless specifically requested to through ExA Questions.
RI_C2 | C2 | Natural England are content that the detail provided is sufficient to inform the Maximum Design Scenario (MDS) and Environmental Impact Assessment (EIA) as it relates to Fish and Shellfish Ecology.
RI_C3 | C3 | Update I1D1
RI_C4 | C4 | It is stated "Adult Atlantic salmon are observed to commence entry into the Leven, Kent, Lune, and Wyre rivers during early spring, whilst sea trout commence entry in June (through until the autumn), although the upstream migration of sea trout is not considered as extensive". However, no referenced evidence is provided to support this statement.
RI_C5 | C5 | It is stated " These species are unlikely to be encountered in the windfarm site, as (except in the case of sea lamprey) they remain in close association with estuarine environments during the marine phase of their life cycle." However, no referenced evidence is provided to support this statement.
RI_C6 | C6 | In [APP-047] it is stated " The current understanding is that European eels spawn in the Sargasso Sea, but there are potentially other, more distant, spawning grounds, and the routes to and from these spawning grounds for European eels remain unclear.". However, no referenced evidence is provided to support this statement. Natural England are not aware of any potential alternative spawning grounds for European eel.
RI_C7 | C7 | Natural England defer to CEFAS on data sources, assessment methodology and conclusions in relation to herring and sandeel.
RI_C8 | C8 | The dynamics between protected avian predator species (i.e. piscivorous species of Liverpool Bay SPA) and prey (i.e. sandeel, herring) has been discussed in collaboration with Natural England ornithological specialists and impacts to birds due to prey fish losses have been deemed unlikely despite proximity to Liverpool Bay SPA.
RI_C9 | C9 | While underwater noise (UWN) modelling has been conducted to determine noise thresholds for impacts to fish as both moving fleeing and static stationary receptors, it is Natural England's view that fish should only be considered as static receptors when modelling underwater sound thresholds and assessments should be based on the static animal modelling results. Natural England’s Offshore Wind Marine Environmental Assessments: Best Practice Advice for Evidence and Data Standards states: “There is currently insufficient evidence to support the inclusion of fleeing behaviour of fish into models. Whilst some degree of movement would be expected, fish may also choose to remain in the affected area (e.g., due to prey availability or mating opportunities) despite the harmful noise exposure (Faulkner et al. 2018). Therefore, for the purposes of environmental assessments, it is currently advised that fish are considered to be stationary receptors within underwater noise models. However, applications may also assess the effects of underwater noise with fleeing behaviours included within the model, if presented in addition to assessments of stationary receptors.”
RI_C10 | C10 | Further to the above comment, while it is useful to display Temporary Threshold Shift (TTS) UWN range and impact ranges for fleeing and stationary animals in tabular format, it would be preferable to have underwater noise contour maps for the site displaying these ranges. This would allow Natural England to visually assess proximity to protected sites more easily. We advise these figures also clearly state the piling scenario modelled and includes the UWN modelling locations and protected site boundaries. While Figure 3.8 displays an example plot, this is assuming the animal is a fleeing receptor, not stationary (see comment above for reasoning). Natural England advise that it is difficult to gauge TTS and Sound Exposure Level (SEL) threshold UWN impact ranges for stationary receptors in relation to protected sites without a contour map.
RI_C11 | C11 | Natural England do not agree with the use of Marine Mammal Mitigation Protocol (MMMP) methods such as soft start and ramp up as a means of mitigation for fish species. This mitigation is designed primarily for cetaceans that regularly exhibit consistent fleeing behaviours, i.e., detect noise and move away from the area of influence. The few studies investigating fish fleeing responses do not show consistent, directional fleeing out of the area of influence. Fish responses to underwater noise are highly variable, and rarely directional (i.e., shoaling in place, or in haphazard directions, flinching, fleeing into shelter)
RI_C12 | C12 | Natural England acknowledges and agrees with findings of no or negligible impacts to Annex II diadromous fish species.
RI_C13 | C13 | Natural England acknowledges and agrees with findings of no or negligible impacts to MCZ fish features.

## D - Marine Mammals
Point | Point Number(s) from Appendix D | Taken from Natural England’s Relevant and Written Representations Morecambe Generation Appendix D - Marine Mammals | RAG Status Rel Rep D1 | Update Following Procedural Deadline A | RAG Status D1 | Update Following D1 | RAG Deadline 2 | Update Following D2 | RAG Deadline 3 | Update Following D3 | Rag Status D4 | Update following D4 | RAG Status D5 | Update following D5 | RAG status D5a | Update following D5a | RAG status D6
RI_D10 | D10 | The maximum pile diameter for monopiles and jacket piles differs between the ES Chapter and the underwater noise modelling.
RI_D11 | D11 | The maximum piling duration in the RIAA and ES is based on piling at a higher strike rate, making the duration per pin pile installed 38% shorter. The applicant should use the lower strike rate to determine the realistic maximum piling duration and use this in their assessment. |  | No change Potential resolution once Applicants rationale from Rule 9 response is included in a named plan. |  | In progress. Potential resolution once Applicants rationale from Rule 9 response is included in a named plan. |  | No change |  | No change. |  | Resolved. Update clarifies that assessment of the highest impact scenario has been made.
RI_D12 | D12 | The Applicant has used a maximum charge weight of 353.5kg for UXO, which is contrary to Natural England’s Best Practice Advice to use a nominal 750 kg weight. The donor charge for high order clearance is also typically greater than 0.5 kg, and should be added to the total NEQ. When applying for the UXO licence post-consent, ensure that an appropriate maximum UXO charge weight plus donor charge is modelled. |  | The Applicant refers back to their desk based UXO research that the worst case UXO for clearance is predicted to be 356.6kg.
RI_D13 | D13 | No reference is made to the presence of harbour seals on the Isle of Man. Given its geographical location, any harbour seals here should be included in the reference population. Clarify the presence of harbour seal on the Isle of Man and include in the assessment if necessary. |  | The Applicant states that the Manx Wildlife Trust have indicated that there is little or no information on any resident harbour seals on the Isle of Man to be considered in the Applicant's assessments. Unlikely to affect conclusion of assessment.
RI_D14 | D14 | The Applicant should clearly present the numbers added to each species’ total through their apportioning approach.
RI_D15 | D15 | Natural England advises that the reference population for grey seal should be the NW England MU alone. Revise assessment so that it is undertaken against the NW MU grey seal population alone, as the reference population. |  | The Applicant states that the 'combined population' consists of the NW MU and and the Isle of Man population, and that this approach has been justified to NE on the 12th of September. NE agreed that the differing approaches do not make a substantial change to the outcome of the assessment.
RI_D16 | D16 | The baseline noise levels have not been presented, despite the NPS requirement.
RI_D17 | D17 | Natural England agree with the project-specific harbour porpoise density used in the project assessment, which is based on the average summer density. We note that the average summer density (1.62 animals/km2) is marginally higher than the average winter density (1.53 animals/km2), meaning that it is the worst-case but also appropriate for assessment of impacts during winter (which is relevant to the Bristol Channel Approaches SAC in particular).
RI_D18 | D18 | The Applicant refers to habitat preference modelling for the Celtic and Irish Seas by Lepple (2023 unpublished). Natural England is not aware of this report, but it appears relevant to the baseline characterisation and so should be included.
RI_D19 | D19 | It is not clear what the Applicant means when they say that the (best) data from Evans and Waggitt (2023) and/or Waggit et al. (2019) were applied to the area of SCANS-IV block CS-E. We request further information on this approach.
RI_D20 | D20 | The density of harbour seal used in the assessment has significantly reduced (by a factor of 200) between the PEIR and the Application. The densities in both documents have been calculated from the same source (Carter et al., 2022), so it is unclear why they differ so significantly. Revise the assessment so that it uses the harbour seal density presented in the PEIR. Unless sufficient justification can be presented as to why it differs so significantly. |  | No change |  | No change |  | Resolved. ES value is correct
RI_D21 | D21 | Natural England advises that dolphin and seal species should be assumed to have the same (medium) sensitivity to distubance effects and over a similar range as harbour porpoise (~25km range). The sensitivity values should be changed and the assessment revised accordingly. |  | No change. Applicant to update at Deadline 1. |  | In progress. Potential resolution once updated assessment from technical note is included in Chapter 11. |  | No change |  | No change. |  | Resolved. All sensitivities updated to medium in Chapter 11.
RI_D22 | D22 | The Applicant has not presented an assessment of the impacts from vibro-piling. Whilst vibro-piling is not the worst-case, it would be beneficial to assess the impacts from it in case this pile installation method is used.
RI_D23 | D23 | It would have been beneficial to assess barrier effects to seals using the known response distances and/or dose-response relationships with the noise contours. This approach would be preferable to using the TTS distances, as disturbance can occur at greater distances than TTS.
RI_D24 | D24 | We note that, based on a TTS distance of 34 km for minke whale, there is potential for barrier effects to extend to the coast during piling.
RI_D25 | D25 | The Applicant has not presented information to justify why minke whale has a medium sensitivity to collision risk, compared to low sensitivity for other marine mammals. We advise that sensitivity to collision risk should be medium for all species. We consider this appropriate based on the statement in paragraph 11.475. The applicant should change the sensitivity of all marine mammal species to collision risk to medium and update the collison risk assessment. |  | No change. |  | No change. A rationale has been provided but no updates have been made to ES Chapter 11. |  | No change |  | NE has reviewed evidence presented in technical notes and whilst we do not agree with the approach, we do not believe it will make a material difference to outcomes in this case.
RI_D26 | D26 | The values in the collision risk rate (%) do not appear correct. For example, for harbour porpoise: the number of deaths due to physical trauma of unknown cause (n=69) plus the deaths due to physical trauma following probable impact from vessel (n=14), totalling 83, is equivalent to 6.90% of the total necropsies where cause of death was established (n=1203); not the 5.6% presented.
RI_D27 | D27 | For clarity, we advise that a single sensitivity is presented for each receptor to the impact pathway. Listing two sensitivities (e.g. Low to Medium for harbour porpoise) is not conducive for a clear assessment. The assessment should be precautionary and so use the worst-case sensitivity.
RI_D28 | D28, D4 | The significance of the disturbance impact must be presented for each of the approaches used to determine disturbance distance. Each approach and subsequent assessment of impact significance provides necessary information for Natural England to inform its advice. For example, the magnitude of impact to harbour porpoise using the EDR approach is Medium, which when combined with a Medium sensitivity, leads to a Moderate impact significance which is Significant in EIA terms. Information such as this is currently missing. It is not appropriate to only present the significance of the disturbance impact after population modelling has been undertaken. This also applies to the CEA. We advise that an assessment of cumulative impacts to cetacean species is presented using the approach that generates the worst-case numbers disturbed. The Applicant should not only present the iPCoD modelling results. Present the impact significance for each approach used to determine the disturbance range, using the combination of sensitivity and magnitude (percentage of reference population within the disturbance range). Present the cumulative impact significant for each species using the worst-case numbers disturbed i.e. not only the iPCoD modelling results. |  | No change. Potential resolution once Applicants rationale from Rule 9 response is included in a named plan. |  | In progress. Updates provided at PDA and D1 have not yet been reflected in ES Chapter 11. |  | No change |  | No change. |  | In progress. Please refer to comments in Appendix D2 to our Deadline 5 submission. |  | No update at D5a. |  | Resolved. Commitment to use of noise management measures/NAS as conditioned in the dDCO adequately manages the risk of residual disturbance impacts.
RI_D29 | D29 | We acknowledge the Applicant’s statement that the findings of Graham et al. (2017), i.e. the dose-response relationship for harbour porpoise, should not be extrapolated to other cetacean species. We then query why it has been applied to dolphin species, but not other cetacean species such as minke whale. We suggest that an alternative approach, such as determining a likely effects range from the literature as presented in Appendix 5.2.11.2 Section 6.1.2, would be more appropriate.
RI_D30 | D30 | We welcome that the Applicant has undertaken an assessment of the disturbance impact from ADD activation.
RI_D31 | D31 | We do not agree that the effect ranges of ADDs will be limited to the (minimum) distance the receptor can swim in the time that the ADD is active. To illustrate, Thompson et al (2020) showed that harbour porpoise had a 50% probability of response within 21.7km after 15 minutes of ADD playback. This highlights that the effects range of ADDs does not only correspond to the duration of the activation.
RI_D32 | D32 | In all iPCoD modelling results tables, including those in the CEA, the values in the median impacted as percentage of unimpacted column do not correspond to the unimpacted population mean and impacted population mean. We advise that the applicant present the difference between the two means in each table that displays iPCoD modelling results, and provide information to support the value they consider to be most appropriate. |  | No change. The Applicant has justified the assessment methodology they consider most appropriate, but this is not yet reflected in updated ES chapter and both means are still not presented. |  | In progress. Justification is still not shown in Chapter 11. Both the median and mean are now presented in the technical notes, but are not yet shown in updates to Chapter 11. |  | No change |  | No change. |  | Resolved.
RI_D33 | D33 | There are small discrepancies between the Tiers. Natural England’s suggested Tiers has 6 levels, not 7. We infer that our suggested Tier 5 has been split into two Tiers (Tiers 5 and 6 presented by the Applicant).
RI_D34 | D34 | The Applicant has not used the species-specific Celtic and Greater North Seas (CGNS) MU to screen in projects to the CEA for those relevant species (namely common dolphin, Risso’s dolphin, white-beaked dolphin, and minke whale), instead using the smaller Celtic and Irish Seas (CIS) MU. By taking this approach, the cumulative effects of projects in the screening area are likely to affect a subset of the CGNS MU populations, rather than the populations as a whole. Therefore, presenting the numbers impacted as a percentage of the whole CGNS MU may downplay the potential significance of this impact. This point should be acknowledged in the assessment.
RI_D35 | D35 | The CEA Screening approach has screened projects in or out on the basis of them contributing to disturbance from underwater noise. This approach is not suitable for screening out projects that may act cumulatively through other impact pathways e.g. collision risk.
RI_D36 | D36 | We do not agree with the Applicant’s assumption that all projects with unknown construction timelines will not overlap with the Morecambe construction period. We consider that it would be conservative to assume that construction for consented projects could overlap with the project, if an operational date is known (as presented in Table 4.1 for the projects listed in Paragraph 53) and is similar to the Morecambe project’s operational date.
RI_D37 | D37 | Table 4.1 does not list some of the seal MUs used in the screening area (namely MU 1 Southwest Scotland, and the Isle of Man MU). The Applicant should confirm that there are no projects that could act cumulatively in these MUs.
RI_D38 | D38 | The Project has identified a residual PTS impact that it has not commited to fully mitigate at this stage. It is not sufficient to say that mitigation for the Project would be put in place post-consent, as this is not secured. Natural England advises that this should be secured as a commitment. The PTS risk of other relevant projects should be assessed cumulatively in the CEA. |  | No change. |  | No change. This has not been addressed in technical notes, Chapter 11 or the CEA appendix. |  | No change |  | NE notes that this has been considered in a technical note [REP3_061] but still consider residual PTS should be inlcuded in the CEA. |  | In progress. Please refer to comments in Appendix D2 to our Deadline 5 submission. |  | No update at D5a. |  | Resolved. Commitment to use of noise management measures/NAS as conditioned in the dDCO adequately manages the risk of residual PTS impacts.
RI_D39 | D39 | There is a discrepancy between the activity types listed here as being screened into the CEA, and that listed in Table 5.1 of the CEA Screening document. Specifically, the ES Chapter has omitted disturbance from operational windfarms (operational after baseline surveys commenced), but included licenced disposal sites (which is listed as being screened out in the CEA Screening).
RI_D40 | D40 | The dose-response curve approach has not been used to determine the number of common dolphin impacted at White Cross. This is contrary to what is stated in Paragraph 11.760. The approach used (TTS) is not sufficiently precautionary for a disturbance impact and is not consistent with how the other projects have been assessed.
RI_D41 | D41 | This table presents that, during each piling event at Awel Y Mor OWF, 2,112 harbour porpoise will be affected by PTS but only 83 will be disturbed. We consider this improbable, given disturbance occurs over a much larger range than PTS. The Applicant should justify these values. More generally, it would be beneficial for the Applicant to summarise briefly the method used by each project to determine the number of animals affected by PTS and disturbance, for sense-checking.
RI_D42 | D42 | SNCBs have not provided formal guidance on an EDR for low order UXO clearance. Such EDRs that have been used for this purpose so far have been agreed on a case-by-case basis only.
RI_D43 | D43 | Natural England welcomes the UXO Assessment undertaken. We acknowledge that the assessment is illustrative at this stage as the UXO clearance Marine Licence will be applied for post-consent. We do not expect that additional information will be available to refine the UXO assessment envelope prior to the application for a Marine Licence. Hence we are content that the UXO assessment does not require further update at this stage.
RI_D44 | D44 | The illustrative UXO assessment concludes that UXO clearance activities should not have a significant impact on marine mammal populations so long as appropriate marine mammal mitigation is secured. The Applicant has provided a draft MMMP which contains mitigation options for UXO clearance. Our comments on the MMMP regarding UXO clearance should be addressed.
RI_D45 | D45, D70 | In the piling scenario at a higher strike rate, there is a residual injury impact because the mitigation proposed is insufficient to reduce the impact. The maximum ADD duration provided is 80 minutes, and in order to ensure a harbour porpoise was outside the PTS zone the ADD would have to be on for 92 minutes. The Applicant must present an assessment of the residual impact post-mitigation, and from this additional mitigation should be considered such as noise abatement. Alternatively, remove the higher strike rate from the project envelope. |  | No change. |  | No change. Not yet addressed in technical notes or updates to Chapter 11. |  | No change. Detailed comments on NE's position on the UWSMS in Appendix D1. |  | No change. |  | In progress. Please refer to comments in Appendix D2 to our Deadline 5 submission. |  | No update at D5a. |  | Resolved. Commitment to use of noise management measures/NAS as conditioned in the dDCO adequately manages the risk of residual PTS at the higher strike rate as noise reductions reduce the duration for which ADD is required.
RI_D46 | D46 | The Vessel Traffic Management Plan does not contain any reference to reducing collision risk or disturbance to marine mammals. It is therefore not appropriate to cross-reference that document here as it does not currently provide any marine mammal mitigation.
RI_D47 | D47 | The Applicant's quantified approach to collision risk impact does not accurately represent the actual risk of collision to marine mammals from the project alone or cumulatively, as it artificially inflates the number at risk. The quantifiied approach has not, to our best knowledge, been peer reviewed. Relying on best practice measures to reduce the risk of collision in order to conclude no residual effect to marine mammal species from collision risk is insufficient as it is not enforceable. Natural England advises that the Applicant commit to measures to reduce vessel collision. |  | No change. |  | No change. Further commitments to reduce collision impacts beyond reliance on best practice measures have not been made. |  | Resolved. Measures to reduce collision impacts will be secured through conditions.
RI_D48 | D48 | Here the Applicant has stated that “Project related vessels transiting to and from the port…[would] endeavour to stay at least 1km from the coast where possible”. This distance should be included in the Outline PEMP.
RI_D49 | D49 | Natural England highlights that Marine Wildlife Licences are typically applied for less than 1 year prior to piling. Due to financial and design commitments that will have happened prior to this licence application, the options for implementing further mitigation will be comparatively limited. Committing to mitigation now will ensure that it can be taken into account in the design and financial decisions. Hence we strongly advise that the Applicant commit to undertaking mitigation measures such as noise abatement now. We also highlight that the Applicant must demonstrate that certain EPS licencing tests are met in order to be granted an EPS licence, and that one of these test is to demonstrate that there are “no satisfactory alternatives,” which includes mitigation options.
RI_D50 | D50 | The Applicant does not appear to have presented the number of animals impacted from all cumulative disturbance pathways (piling at other OWFs; contruction activities (other than piling) at other OWFs; other industries and activities). This combined disturbance impact should be presented. Present the combined cumulative effect of disturbance from underwater noise, across the three pathways that are currently assessed only separately. |  | No change. |  | In progress. Updates including all cumulative disturbance pathways are supplied in the technical note, but are not yet reflected in updates to Chapter 11. |  | No change |  | No change |  | Resolved. Information on cumulative disturbance impacts is now included in Chapter 11.
RI_D51 | D51, D72 | Only piling impacts from other OWFS are considered as a cumulative impact for disturbance. Natural England therefore cannot agree with the conclusion in Table 11.108 and advises that other sources of disturbance to marine mammals should be considered in this assessment. We further advise that the applicant should commit to measures to reduce temporal overlap with other activities to ensure that cumulative disturbance impoacts are sufficently mitigated. A standalone vessel code of conduct should be secured as a consent condition, for all project phases, and contain appropriate measures for marine mammal mitigation. Natural England requests to be consulted on the code of conduct. |  | No change. |  | No change. Commitment to use of NAS not secured. Underwater Sound Management Strategy has not yet been provided. Vessel code of conduct has not been provided. |  | In progress: Updates to the VTMP have been made, however the applicant has not considered cumulative disturbances to marine mammals or made a commitment to reduce temporal overlap. |  | No change |  | No change |  | No update at D5a |  | The Applicant has commited to using existing vessel routes where possible to minimise disturbance to marine mammals. This issue cannot be fully resolved within this Examination as temporal measures to reduce concurrent noise with other projects have not been committed to and ports for construction and maintenance remain unconfirmed.
RI_D52 | D52 | The Applicant should provide evidence to support their statement that other offshore projects and industries would follow similar best practice measures (other than OWF).
RI_D53 | D53 | We consider that cumulative effect 6: assessment of disturbance from operational offshore turbines generators could have been included in the cumulative effect 1: disturbance from underwater noise assessment. Indeed it should be included in the combined assessment of cumulative effect 1.
RI_D54 | D54 | The scope of the OPEMP with regards to marine mammals appears appropriate. However, please see our comments on other aspects of the assessment and mitigation, which may be relevant to the content of the OPEMP regarding marine mammals. Where changes are made to other documents, they should also be made in the OPEMP.
RI_D55 | D55 | Natural England considers that there is insufficient evidence provided to agree with the EIA assessment conclusions, on the following matters: - Aspects of the seal baseline - Some of the sensitivities used - The project-alone assessment of disturbance from piling - Residual PTS risk - Aspects of the assessment of collision risk - The assessment of cumulative disturbance Some of these concerns stem from insufficient mitigation of the impact pathway. Points 3 to 6 can be addressed by securing further mitigation at this application stage. See recommended actions for the specific comments underpinning each of these areas of disagreement.
RI_D56 | D56 | Natural England considers that all relevant SACs with marine mammal features in English waters have been screened in. We also agree that the key impact pathways have been identified.
RI_D57 | D57 | Please note that it is Natural England’s remit to provide advice on the assessment in so much as it relates to SACs in English waters. We defer to the relevant SNCBs on the appropriate approach for assessing SACs outside English waters.
RI_D58 | D58 | For clarity, we agree with the Applicant’s assessment that there would be no adverse effect on integrity of the Bristol Channel Approaches SAC from the project alone. We do not necessarily agree with the terminology used by the Applicant when they state that “there would be no LSE on the harbour porpoise CIS MU population”, as the CIS MU population is not the designated SAC feature, and this conclusion takes into account mitigation.
RI_D59 | D59 | The Applicant has used a distance of 4km for their assessment of harbour porpoise disturbance during non-piling construction activities. However, the 4km distance, from Benhemma-Le Gall et al. (2021) is based only on harbour porpoise responses to non-piling construction vessels, rather than other noisy activities (such as cable installation and protection). The Applicant has not presented evidence to demonstrate that 4km is appropriate or precautionary for other noisy activities.
RI_D60 | D60 | Natural England's comments on the CEA are also relevant to the HRA in-combination assessments. Changes to the CEA should be reflected in the in-combination assessment also. Further mitigation to reduce impacts to the marine mammal populations would also reduce the risk of an impact to English marine mammal SACs in the region. |  | No change. |  | In progress. Updated information on cumulative assessment is applied to the HRA in the technical note, but this is not yet reflected in an update to the HRA screening/RIAA. NE will comment further once these changes have been propogated. |  | No change |  | No change |  | Resolved. NRW is the lead SNCB for Welsh sites.
RI_D61 | D61 | The IPMP should identify monitoring that seeks to validate areas of the marine mammal assessment where assumptions have been made with high uncertainty or low confidence. Marine mammal monitoring should be undertaken in addition to the standard monitoring of underwater noise generated from the piling of the first four piles. Further detailed discussion of this is required in the monitoring plans. See Natural England's Best Practice Advice for requirements. |  | No change. |  | No change as no update to IPMP has been provided. |  | No change |  | In progress. The IPMP [REP3_046] now includes a requirement to include marine mammal monitoring with planned ornithological aerial surveys, but there is still no commiment to monitor marine mammal responses to impacts. |  | No change |  | See response to ExQ3 3BEM2. Natural England maintains that the monitoring measures proposed are not yet adequate, however we recognise that the risk to designated sites with marine mammal features for which NE is the lead SNCB is low for this issue and do not anticipate that it will materially affect the outcome of this Examination.
RI_D62 | D62 | The Applicant should clarify how it will be secured that the final UXO MMMP will be developed in accordance with the Draft MMMP.
RI_D63 | D63 | It is not clear whether the High Order section of the table takes into account the reduction in source level through the use of a bubble curtain. When finalising the UXO MMMP post-consent, clearly state whether noise reduction has been factored into the modelling and so impact ranges. Note, it would be beneficial to present both (unabated and abated noise levels at ranges/PTS and TTS distances), for comparison to underwater noise monitoring results.
RI_D64 | D64 | The Applicant has not provided the anticipated duration of the ADD activation during UXO clearance. An illustrative example of ADD duration, based on the PTS ranges presented, would be beneficial.
RI_D65 | D65 | The Applicant has not committed to several mitigation measure options, instead saying that they will be implemented “if required”. This increases the uncertainty about what measures will be undertaken during UXO clearance, and so complicates the worst-case scenario (i.e. what the minimum mitigation is that will be implemented). Examples include: - Avoidance or relocation of UXO - Bubble curtain usage - Passive Acoustic Monitoring
RI_D66 | D66 | The final piling MMMP should present the injury ranges based on SPL also, as those distances correspond to the necessary size of the mitigation zone. When finalising the piling MMMP post-consent, present the injury ranges based on instantaneous PTS.
RI_D67 | D67 | The Applicant should clearly state the precise mitigation measures that are being relied upon to conclude no adverse effect from impact pathways covered in the ES. The current mitigation measure options outlined in Paragraph 90 increase the uncertainties around which measures will be used during piling and therefore complicates the worst-case scenario (i.e. what the minimum mitigation is that will be implemented). |  | No change. |  | No change. |  | No change. It is still unclear which measures will be delivered to mitigate for the WCS as the UWSMS indicates review of further refinements in design prior to determining the level of mitigation needed. |  | No change. |  | No change. Please refer to comments in Appendix D2 to our Deadline 5 submission. |  | No update at D5a |  | Resolved. Natural England is confident that the commitment to noise management in the dDCO means that appropriate mitigation can be delivered through the processes outlined in the UWSMS and MMMP.
RI_D68 | D68 | The break procedure outlined here, for piling breaks between 10 minutes and 2 hours, does not adhere to the JNCC piling mitigation guidelines. Revise the break procedure in the draft MMMP. |  | No change. |  | No change. No updates to the IPMP or MMMP have been provided. |  | No change. The proposed change to the break procedure still does not adhere to the JNCC guidance. |  | No change. |  | No change. Please refer to comments in Appendix D2 to our Deadline 5 submission. |  | No update at D5a |  | Resolved. The Applicant has committed to following the standard break procedure, with any potential modifications to this by exception and in consulation with SNCBs.
RI_D69 | D69 | We query the reliability of PAM in detecting all species in the project area, particularly minke whales and seals. We advise that the more precautionary approach would be to delay start up of piling until conditions allow for visual monitoring.
RI_D70 | D70 | The Applicant’s outlined approach of activating the ADD for 80 minutes is insufficient to ensure that harbour porpoise will be outside the injury zone (based on PTS from SELcum) during piling. Further mitigation is therefore required to reduce the risk of injury to harbour porpoise. We do not agree that the proposed approach is sufficient for all species. Commit to further mitigation, e.g. the use of noise abatement systems, to ensure that the risk of injury to harbour porpoise is reduced as far as possible.
RI_D71 | D71 | It is not appropriate for the MMMP to contain measures aimed at reducing the cumulative noise effects across multiple projects. A more appropriate place for these measures would be an underwater sound management strategy. See other comments on underwater sound management strategy.
61 | D72 | The “Vessel good practice to avoid marine mammal collisions” should be a standalone document, rather than an annex to the MMMP, and must be secured for all project phases. This should include pre-construction activities such as surveys. A standalone vessel code of conduct should be secured as a consent condition, for all project phases, and contain appropriate measures for marine mammal mitigation. Natural England requests to be consulted on the code of conduct. |  |  | Summary comment

## E - Geol. Phys. Proc. Sed. WQ
Point | Point Number(s) from Appendix E | Taken from Natural England’s Relevant and Written Representations Morecambe Generation Appendix E - Marine Geology, Physical Processes, Sediment and Water Quality | RAG Status Rel Rep | Update Following Procedural Deadline A | RAG Status D1 | Update FollowingD1 | RAG status D2 | Update Following D2 | RAG Status D3 | Update Following D2 | RAG Status D3 | Update Following D3 | Rag Status D4 | Update following D4 | RAG Status D5 | Update following D5 | RAG status D5a | Update following D5a | RAG status D6
RI_E7 | E7 | We advise that further detail is required in the project description to inform the Maximum Design Scenario (MDS) and Environmental Impact Assessment (EIA).
RI_E8 | E8, F7 | Cable and pipeline crossings. More specific information is required on the maximum volume figures used for cable/pipeline crossings: it should be clear whether this volume refers to the amount of cable protection material to be placed, or a broader overall volume for the crossings. Information on the location of these crossings should also be provided, in accordance with Natural Englands best practice guidance for cabling. |  | In progress. Locations and figures still to be secured in named plans and DCO |  | No change |  | No change. |  | No change. |  | NE acknowledges that quantities of cable protection for different elements of the project is provided in the relevant plan, but locations of cable crossings are not so best practice guidance has not been followed. Therefore, our advice remains unchanged. However, For this project we recognise that whilst there may be an impact on sensitive receptors, these are not designated site features allowing for a risk based decision to be made. We therefore do not anticipate further progress on this issue.
RI_E9 | E9 | Natural England agrees that the baseline description of physical processes through the desktop review of existing literature and existing data sources, project specific surveys and numerical modelling baseline scenarios are sufficient to appropriately characterise the study area.
RI_E15 |  | Natural England is content that monitoring of effects on physical processes will be captured during pre and post construction multibeam echo sounder (MBES) and side scan sonar (SSS) surveys to document bedform topography as per [APP-148]. These surveys should be secured in the IPMP.
RI_E10 | E10 | Natural England agrees with the numerical modelling approach and scenarios conducted in relation to hydrodynamics, waves and sediment transport to inform the potential changes in the Morecambe Generation physical processes study area arising from the construction, operation and decommissioning.
RI_E11 | E11, F9 | Seabed preparation activites (UXO and boulder clearance) have not been included in the assessment of impacts to physical processes or water quality. Natural England advises that physical process, marine sediment and water quality impacts due to UXO clearance and boulder clearance should be considered and assessed within an updated ES. Without consideration of these activites, there is insufficient information to assess impacts to these receptors. |  | In progress. Rule 9 response presents updated worst case scenario that clarifies and includes these pressures and receptors, but this is not yet included in an updated assessment. |  | No change |  | In progress: UXO assessment is now included in updated ES chapter. The maximum charge weight of 700kg does not follow NE best practice guidance (see also comment RI_D12) but in this instance we do not believe it will make a material difference to the outcome of the assessment. Boulder clearance has not been addressed in the updated ES chapter, so this issue cannot yet be resolved. |  | In progress: UXO assessment is now included in updated ES chapter. The maximum charge weight of 700kg does not follow NE best practice guidance (see also comment RI_D12) but in this instance we do not believe it will make a material difference to the outcome of the assessment. Boulder clearance has not been addressed in the updated ES chapter, so this issue cannot yet be resolved. |  | No change. Boulder clearance is within the scope of the overall width of disturbance used for assessments but it is not clear where and how cleared boulders are to be deposited. UXO component of this issue is considered to be resolved. |  | In progress. NE understands that the total disturbance width includes boulder deposition although this is not specified in a named plan and there is no detail on the formation in which boulders will deposited. |  | No change. See response to ExQ3 3BEM10. |  | ES chapter has been updated to specify random placement of boulders within overall disturbance corridor. Natural England advises that this measure should also include the commitment to ensure boulders are placed in a similar habitat to that from which they were taken, hence this issue is not completely resolved. Whilst this is not likely to be resolved within this Examination, we acknowledge there are no designated sites with benthic features within the project site.
RI_E13 | E13, F11 | Whilst a commitment is made to implementing mitigation measures, these are not yet secured within the DCO/dML and so it cannot be confirmed how effected they will be. |  | No change. The Schedule of Mitigation indicates the means by which meaures would be secured in the DCO/dML, but does not secure commitment to any given level of mitigation. See also comment A8 |  | No change |  | No change. We note that the Schedule of Mitigation and DCO/dML have been updated regarding other Risks and Issues but this issue has not been addressed. |  | No change. We note that the Schedule of Mitigation and DCO/dML have been updated regarding other Risks and Issues but this issue has not been addressed. |  | No change. |  | In progress, see commentary in our D5 letter. |  | No change. See response to ExQ3 3BEM2 and 3BEM10. |  | Resolved. The IPMP now includes the requirement for survey that is adequate to inform delivery of micrositing mitigation measures, should this be required. Benthic monitoring beyond this is not required.
RI_E14 | E14, F12b | Natural England notes that the Applicant is proposing to leave scour and cable protection in-situ. We advise that regardless of legislation or being outside of designated sites, the Applicant should aim to remove infrastructure. Decommissioning should aim to remove infrastructure to avoid irreversible (permanent) habitat loss, thus returning the seabed habitat to its pre-developed baseline status as required by OSPAR. Natural England advises that the Applicant considers using scour and cable protection which is more readily removable at the time of decommissioning. We would welcome and encourage this to be secured as a commitment. Ideally this would also be included in an Outline Decommissioning Plan submitted to support the consenting phase. We highlight that it is a requirement to prepare a decommissioning programme under Section 105 of the Energy Act 2004. |  | No change. The Applicant commited to providing the outline decommisioning plan during consenting. |  | No change |  | No change. |  | No change. |  | No change. |  | No change. |  | No update at D5a. |  | No change. Please refer to Natural Englands closing position statement in it's Deadline 6 cover letter.

## F - Subtidal Benthic Ecology
Point | Point Number(s) from Appendix F | Taken from Natural England’s Relevant and Written Representations Morecambe Generation Appendix F - Subtidal Benthic Ecology | RAG Status Rel Rep | Update Following Procedural Deadline A | RAG Status D1 | Update Following D1 | RAG status D2 | Update Following D2 | RAG Status D3 | Update Following D3 | Rag Status D4 | Update following D4 | RAG Status D5 | Update following D5 | RAG status D5a | Update following D5a | RAG status D6
RI_F6 | F6 | We advise that further detail is required in the project description to inform the Maximum Design Scenario (MDS) and Environmental Impact Assessment (EIA). Please see detailed comments in relevant headings of this table.
RI_F7 | F7 | Cable/pipeline crossings – Natural England notes that information pertaining to cable protection volumes for cable/pipeline crossings is unclear. In [MOR001-FLO-CON-ENV-RPT-1050] paragraph 5.73 notes that “Cable protection would be required at the crossings (and is additional to the cable protection requirements set out in Table 5.12)”. Table 5.13 sets out the cable/pipeline crossings design envelope and includes maximum cable/pipeline crossing volume per crossing (m3), and maximum cable/pipeline crossing volume for all crossings (m3). However, it is not explicit that these volumes relate to cable protection. Additionally, there is no information on location of crossings. It would be helpful if these could be provided and updated in the final ES. |  | Commentary for this issue is now amalgamated with RI_E8 in Tab E as this is the same issue. Further updates will be addressed there.
RI_F8 | F8 | Natural England agrees that the data included in the baseline characterisation for benthic ecology is sufficient to characterise the study area. Therefore, unless there is a change in the project design parameters, we will provide no further comment on the data during examination.
RI_F9 | F10 | Natural England agrees with the approach and scenarios conducted to inform the potential changes in the Morgan Generation benthic ecology study area arising from the construction, operation and decommissioning. Therefore, we advise that unless there are significant changes to project design parameters, we will provide no further comment on data during examination.
RI_F10 | F9 | Seabed preparation Natural England notes that Unexploded Ordnance (UXO) clearance has not been considered for impacts in [APP-046] on the basis that UXO clearance activities for the Project would be considered as part of a separate licence application. UXO clearance can lead to pressures such as abrasion/disturbance of the substrate on the surface of the seabed, changes in suspended solids, smothering etc. In addition, there appears to be no consideration given to boulder clearance activities. And it is unclear whether boulder clearance will be required. However, to have confidence in assessments of benthic ecology impacts it is important to understand these requirements and provide assessments for activities if they are to take place. We advise that the Application should provide sufficient information to assess the potential impacts from seabed preparation. |  | Commentary for this issue is now amalgamated with RI_E11 in Tab E as this is the same issue. Further updates will be addressed there.
RI_F11 | F11 | Natural England advises that it is key that all mitigation measures are secured in any consent issued. Whilst we understand there is a commitment to implementing them, it cannot be fully understood at this stage the level of mitigation some measures may be able to provide. |  | Commentary for this issue is now amalgamated with RI_E13 in Tab E as this is the same issue. Further updates will be addressed there.
RI_F12 | F12 | F12a: Long term degradation of plastic based geotextile bags has the potential to release plastics into the environment. Consideration should be given to use of novel technologies such as rock bags, and to removing plastics from the site after use. F12b: Natural England notes that the Applicant is proposing to leave scour and cable protection in-situ. We advise that regardless of legislation or being outside of designated sites, the Applicant should aim to remove infrastructure. Decommissioning should aim to remove infrastructure to avoid irreversible (permanent) habitat loss, thus returning the seabed habitat to its pre-developed baseline status as required by OSPAR. |  | F12a: In progress. Use of non-plastic technologies will be given consideration by the Applicant. This should be reflected by a commitment in the Schedule of Mitigation to measures to reduce impacts to the wider environment including but not restricted to alternatives to plastic use. F12b: Scour and cable protection commentary is now amalgamated with RI_14 in Tab E as this is the same issue. Further updates will be addressed there. This row will only be used for further updates and comments on F12a |  | No change. |  | No change, Schedule of Mitigation has been updated but did not address this issue. |  | No change. |  | Resolved. Consideration of alternatives to plastics secured through outline CMS. There is a risk that this may become an issue again in preconstruction period.
F13 | F13 | Natural England agrees with the MCZ screening conclusions for alone impacts. Therefore, unless there is a change in the project design parameters, we will provide no further comment on MCZs during examination.

## I - Bats
Point | NE Comment | RAG Status D3 | Update Following D3 | Rag Status D4 | Update following D4 | RAG Status D5 | Update following D5 | RAG status D5a | Update following D5a | RAG status D6
RI_I1 | Natural England does not agree with the Applicants conclusion that there is no impact pathway for bats. The Applicant should review the available evidence on bat species where crossing of the Irish Sea is known to have occurred and present findings as to the expected magnitude of effect from this pathway. Evidence sources that could inform this work have been indicated by NE in response to ExQ 1HRA3. |  | No Change. |  | The Applicant has submitted a technical note that acknowledges this impact pathway. See below for new issues arising from this note.
RI_I2 | Natural England advises that the Applicant should include evidence from the Environmental Statements of several other offshore wind farm projects in an update to this technical note as these have not yet been considered. |  |  |  | New at D5 |  | No update at D5a. |  | Resolved. The Applicant has updated the technical note with key information from the relevant Environmental Statements.
RI_I3 | Natural England advises that there is evidence on the role of barotrauma in wind turbine related bat mortality that has not been considered in the technical note and should be included. |  |  |  | New at D5 |  | No update at D5a. |  | Resolved. The Applicant has included a summary of the relevant evidence around barotrauma.
RI_I4 | Natural England advises that many of the conclusions drawn in the technical note are poorly supported and should be presented as low confidence conclusions. This is due to the paucity of evidence available directly related to bat behaviour in relation to offshore infrastructure. Whilst there are suitable methods available for improving this evidence base, including the deployment of bat detectors and night vision aids at offshore structures, we recognise that implementing this is outside the scope of this examination. |  |  |  | New at D5 |  | No update at D5a. |  | The Applicant has acknowledged that the lack of evidence around bats means that any conclusions made are inherently low confidence. Whilst NE retains concerns that this means the potential impacts on bats are not fully understood and cannot therefore mark the issue fully resolved, there is a low risk of impacts to designated sites with bat features in England, so it should not be a material concern for the outcome of this examination.