## Title page
THE PLANNING ACT 2008
THE INFRASTRUCTURE PLANNING (EXAMINATION PROCEDURE) RULES
2010
Natural England's Risk and Issues Log - Deadine 2.1 Submission.
For:
The construction and operation of Dogger Bank South (East and West) Offshore Wind Farm, located approximately 100-122 km from the North East Coast in the Southern North Sea Sea.
Planning Inspectorate Reference EN010125
27th February 2025

## How to read Risks and Issue Log
Natural England has created this Risk and Issues Log to track progress through the Dogger Bank South (East and West) examination process. The Risks and Issues Log will be submitted at each deadline and marks issues with a colour from our RAG scale depending on the level of significance of the issue. All red, amber and purple issues from our Relelvant and Written Representation are included (collated where appropriate). Green and yellow issues are included if/where relevant. It should be noted that the colour scale is different from that used in the Statement of Common Ground provided by The Applicant. Our PADSS as submitted at Relevant Represensations has also ben provided, however this will not be updated until Deadline 4. The Risk and Issues Log is split into multiple tabs in line with the Appendices of our Relevant Representations submission. A - DCO B - Marine Physical Environment C- Benthic & Intertidal Ecology D - Benthic Compensation E - Fish & Shellfish F - Marine Mammals G - Offshore Ornithology H - Offshore Ornithology Compensation I - Terrestrial Ecology & Ornithology The Risk and Issues Log will be submitted alongside our written response at each deadline. This will reflect our position following a review of documents that we have considered in forming our position at each deadline. Any issues added to the log during Examination (not included in Relevant Reps) are highlighted in Red and then coded according to RAG status.
Purple Note for Examiners and/or competent authority. May relate to DCO/DML
Red Natural England considers that unless these issues are resolved it will have to advise that (in relation to any one of them, and as appropriate) it is not possible to ascertain beyond reasonable scientific doubt that the project will not affect the integrity of an SAC/SPA/Ramsar and/or significantly hinder the conservation objectives of an MCZ and/or damage or destroy the interest features of a SSSI and/or comply fully with the Environmental Impact Assessment requirements.
Addressing these concerns may require the following:
new baseline or survey data; and/or
significant revisions to baseline characterisation and/or impact modelling and/or
significant design changes; and/or
significant mitigation
In addition, Natural England may use this category to highlight where there is a significant risk that an issue will not be sufficiently addressed within the Examination timescales. Consequently, issues that start out as Amber may progress to Red in the latter stages of the examination.
Amber Natural England does not agree with the applicant’s position or approach and consider that this could make a material difference to the outcome of the decision-making process for this project.
Natural England considers that these matters may be resolved through:
provision of additional evidence or justification to support conclusions; and/or
revisions to impact assessment methodology and/or assessment conclusions; and/or
minor to moderate revisions to impact modelling; and/or
well-designed mitigation measures that are adequately secured through the draft DCO/dML and/or
amendments to draft plans
If these issues are not addressed or are unlikely to be resolved by the end of the Examination, then they may become a Red risk as set out above.
Yellow Natural England doesn’t agree with the Applicant’s position or approach. We would ideally have liked this to be addressed but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process and would not expect these matters to be a ongoing focus of the examination. However, we reserve the right to revise our opinion should further evidence be presented.
It should be noted by interested parties that just because these issues/comments are not raised as significant concerns in this instance, it should not be understood or inferred that Natural England would be of the same view in other cases or circumstances.
Once a Risk or Issue has been categorised as yellow, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will greyed out at subsequent deadlines in order to rationalise the risk and issues log.
Green Natural England is in broad agreement with the Applicant’s approach and has no significant outstanding concerns. As above, we reserve the right to revise our opinion should new evidence be presented. Once a Risk or Issue has been categorised as green, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be greyed out at subsequent deadlines in order to rationalise the risk and issues log.

## PADSS
Ref | The principal issue in question | The brief concern held by Natural England which will be reported on in full in WR / LIR | What needs to change, or be included, or amended so as to overcome the disagreement | Likelihood of the concern being addressed during Examination | RAG
Development Consent Order (DCO)
NE1 | Maximum piling parameters not secured | The DCO does not contain any restriction of the maximum hammer energy used during piling. This is a key metric for the noise impact to marine mammals and sensitive fish species. | The maximum limit assessed should be appropriately secured in the deemed Marine Licences (dMLs). | Likely Subject to this condition being secured
NE2 | Deployment of cable protection | The DCO does not contain an end date for deployment of cable protection for within and outside of designated sites. Our standard advice is that cable protection should only be deployed for a maximum period of 10 years from the commencement of operations. Within any designated sites for benthic features, it should be stipulated that there should be no deployment of cable protection after the completion of construction. | Include a condition limiting the deployment of cable protection outside of designated sites to within 10 years of the completion of construction, and inside designated sites such as Dogger Bank SAC, no cable protection may be deployed after the completion of construction. | Likely Subject to this condition being secured.
Marine Physical Environment
NE3 | Cable protection - nearshore | Natural England is concerned that cable protection in the nearshore could disrupt longshore sediment transport and impact features of the Holderness Inshore MCZ, Humber Estuary SAC and Smithic Bank. | A commitment should be made to avoid the placement of external cable protection within shallow nearshore water (i.e. within the 10m depth contour), or alternative methods of cable burial should be explored to remove the need for cable protection between mean low water springs and the 10m contour. | Potential resolution This is subject to the Applicant securing the advised commitment
NE4 | Cable protection -Dogger Bank SAC | The presence of cable protection measures on Dogger Bank (and within Dogger Bank SAC) could modify the hydrodynamic regime and affect sediment transport pathways contributing to the ecological ‘halo effect’. See NE10. | Natural England advises that further justification is needed for the volumes of predicted external cable protection within Dogger Bank SAC. | Likely Subject to the Applicant providing further evidence.
NE5 | Flamborough Front | The presence of the Dogger Bank South Arrays (alone and in combination with other nearby offshore wind farms) could impact circulation, stratification, mixing, and sediment resuspension in the water column. This could in turn, cause changes to the Flamborough Front which could have far-reaching and long-term consequences for the wider marine ecosystem | Natural England advises that the Applicant should monitor potential changes to stratification, currents, and primary productivity during pre-construction, post-construction, and for the lifetime of the Projects. | Potential resolution This is subject to the In-Principle Monitoring Plan being updated.
Benthic and Intertidal Ecology
NE6 | Worst case habitat loss – Dogger Bank SAC | The Applicant has not considered the potential for changes to the physical and/or biological structure and function of Annex I sandbank beyond the footprint of the planned infrastructure. We are particularly concerned that secondary ‘ecological halo’ effects could be combined, resulting in broadscale changes in the benthic habitats and communities across the wider DCO area and a significant proportion of Dogger Bank SAC. | A robust assessment is needed of the potential Worst-Case area of impact on benthic communities within Dogger Bank SAC, and the nature and scale of that impact, as a result of changes to physical and biological process following the placement of structures and cable/scour protection on the seabed. | Likely This is subject to the Applicant providing an updated assessment
NE7 | Cable protection - decommissioning | The Applicant has not committed to the removal of cable and scour protection within the Dogger Bank SAC at the point of decommissioning. This will cause permanent loss of the designated sandbank feature. | In line with recent Secretary of State Decisions for OWF NSIPs the Applicant should commit to removing all on and above seabed infrastructure at the point of decommissioning. This should be secured in the DCO and an outline Decommissioning Plan. | Potential resolution
NE8 | Volumes of cable protection | The methods used to determine the amount of cable protection and any associated lasting loss/change of Annex I sandbank habitat within Dogger Bank Special Area of Conservation (SAC) are neither comprehensive nor transparent. It is therefore unclear how realistic the Maximum Design Scenario (MDS) is. | Further justification is needed for the volumes of predicted external cable protection in the Project Envelope. | Likely Subject to the Applicant providing further evidence.
NE9 | Mitigation | This mitigation included for sediment deposition is insufficient, particularly where there could be direct or indirect effects on Dogger Bank SAC or priority habitats. | Natural England advises that further mitigation options should be committed to by the Applicant. | Likely
Benthic Compensation
NE10 | Alignment between strategic and project-led compensation | Compensatory measures proposed by the Applicant as part of their project level derogation case are expected to align with the measures and approach outlined in the Dogger Bank Strategic Compensation Plan (DBSCP) and be secured as a requirement of the DCO. However, the DBSCP and the project compensation do not align, with damage to sandbanks being excluded from the compensation requirements. | Natural England advise that the DCO should secure compensation for both habitat loss and damage to Annex 1 sandbank. | Likely Subject to this being secured in the DCO
Fish and Shellfish Ecology
NE11 | Spawning habitat loss - sandeel | The full scale of potential sandeel spawning habitat loss and/or change has not been assessed. | A robust assessment is needed of the potential worst-case area of impact on spawning habitat along the ECC and within Dogger Bank SAC sandbank feature, including the nature and scale of impact as a result of changes to physical and biological processes following the placement of structures and cable/scour protection on the seabed, and implications at a localised population level. | Likely This is subject to the Applicant providing an updated assessment
NE12 | Indirect effects on seabirds and marine mammals – RIAA conclusions | Natural England disagrees that impacts on mobile designated site interest features (i.e. seabirds from FFC SPA and harbour porpoise in SNS SAC) can be ruled out based solely on no significant impacts being concluded at a regional population level in the EIA assessment for forage fish species. The RIAA assessment has also only considered direct construction impacts on prey availability rather than the operational impacts of spawning habitat loss. | Assessments on herring and sandeel should be considered at a biologically relevant population level and should include loss and/or change of spawning habitat throughout the lifetime of the project. The implications on prey abundance and distribution within the foraging areas of Annex I and Annex II species from designated sites should be assessed. | Partial resolution likely Subject to the Applicant providing an expanded assessment. However, uncertainties will likely remain that are beyond the ability of the project to address. If impacts to designated site features cannot be ruled out, consideration may need to be given to addressing the wider ecosystem functionality of sandbanks within derogation proposals.
NE13 | Baseline characterisation - sandeel abundance | Sandeel abundance data has not been used to characterise the importance of the array areas as potential sandeel habitat. | We advise that the Applicant should use sandeel abundance data (such as the North Sea Sandeel Survey) to characterise the importance of the array areas as sandeel habitat and support the assessment of impacts on localised sandeel populations | Likely This is subject to the Applicant providing an updated assessment
Marine Mammals
NE14 | Southern North Sea SAC - harbour porpoise underwater noise impacts - Outline Site Integrity Plan (SIP) | Natural England is concerned that the SIP process is being exclusively relied on to address in-combination noise levels from multiple projects on SAC harbour porpoise in the post-consent phase. The Applicant has not committed to using Noise Abatement Systems (NAS) at this stage, increasing the risk that an adverse effect on site integrity (AEoI) cannot be avoided | The Applicant should commit to specific mitigation measures at this stage, particularly NAS, in the Outline Marine Mammal Mitigation Protocol and SIP, which can be removed at a later date if the revised SIP demonstrates they are not required. | Potential Resolution If changes can be made to the Outline MMMP, it is likely this issue can be resolved.
NE15 | EIA/HRA conclusions | The conclusions are over-reliant on the outcomes of population modelling, and do not consider all assessments undertaken where higher impacts are indicated. | Assessments should be updated based on the highest predicted impact values, for all receptors and pathways, to inform the EIA and HRA conclusions. Where significant impacts cannot be ruled out, additional mitigation should be explored to avoid or reduce impacts. | Potential Resolution If the Applicant updates their EIA/HRA assessment it may be possible to resolve this issue
NE16 | Injury Zone for minke whale and harbour porpoise | The mitigation proposed by the Applicant is insufficient to mitigate the full piling injury zone for minke whale and harbour porpoise | The Applicant needs to demonstrate how the full injury zone will be mitigated, this could be through design changes or commitments to additional mitigation. | Potential Resolution If changes can be made to the Outline MMMP, it is likely this issue can be resolved.
Offshore Ornithology
NE17 | Assessment methodologies and EIA/HRA conclusions | Natural England cannot agree with the EIA or HRA conclusions presented due to several aspects of the assessment not being provided in line with SNCB guidance and/or Natural England advice given during the Evidence Plan Process (EPP) and/or our Best Practice Advice, these include: - baseline mortality rates and EIA reference populations - guillemot seasonality - gannet collision risk - approach taken to combining the impacts of the two arrays - apportioning approach for guillemot and razorbill - lack of, or incomplete in-combination assessments | Natural England advise that assessments in line with SNCB advice are provided in full, alongside the Applicant’s preferred methodology. This advice has been provided during the EPP and repeated, where necessary, in Appendix G. Natural England will not be able to advise the Examination further on the ornithology impacts of the proposals until this material is provided. | Likely This is subject to the Applicant presenting assessments that are in line with SNCB advice.
NE18 | Mitigation of likely very high impacts on seabirds | The baseline surveys indicate the potential for very high impacts on seabirds at both EIA and HRA scales. It is not clear how robustly ornithology impacts were factored in when designing the post-PEIR reductions of the array areas and whether further reduction could be undertaken to reduce impacts. | Further consideration should urgently be given to potential avoidance/ mitigation measures to reduce impacts on seabird features, such as array reductions, changes to design and layout of arrays, or increasing the hub height of turbines. Hotspot modelling of seabird densities and distributions in the study area may help to identify areas where impacts on seabird features are particularly high to inform an improved mitigation approach. | Unlikely There is no guarantee this issue will be resolved within the Examination timeframe
Ornithology Compensatory Measures
NE19 | Agreed compensation levels – all measures | As noted above, it is not possible to agree the level of compensation required until impact assessments have been provided in line with SNCB advice. Additionally, the method for generating the required amount of compensation needs to be carried out in line with SNCB advice before it can be confirmed as sufficient. | See NE17. Once the impact assessment has been updated, the outputs should be used to generate compensatory requirements in line with SNCB advice. | See NE17.
NE20 | Location for predator eradication – FFC SPA guillemot and razorbill | A location or locations to deliver predator eradication is yet to be determined. Several sites on the Applicant’s shortlist have previously been ruled out by other OWF projects, and feasibility studies have not been provided to demonstrate predator presence and auk habitat suitability at shortlisted sites. It is plausible that none of the short-listed locations are appropriate. It will not be possible to quantify the scale of compensation that might be achievable, and therefore if the impacts can be compensated, until a location or locations is identified. | Feasibility assessments for the shortlisted sites should be provided as a matter of urgency, to demonstrate the suitability of sites and the scale of compensation that could be delivered by the measure. | Potential resolution If the Applicant provides feasibility assessments for the shortlisted sites it might be possible to resolve this issue, but there is no guarantee a suitable site will be found.
Air Quality – Onshore habitats
NE21 | Air quality impacts to international and national designated sites due to construction traffic emissions. | Air quality impacts to designated sites have been assessed using JNCC decision making thresholds. However, NE does not currently accept the use of this document. We therefore advise that the modelling that has been undertaken for the pollutants should be tested against NE’s thresholds for impacts due to air emissions from traffic, as detailed in the guidance document NEA001. | Assessment of air quality impacts to international and national designated sites should be undertaken using the thresholds included in Natural England’s published guidance document NEA001. | Likely This issue could be progressed with provision of an updated air quality assessment. Natural England and the Applicant are in active discussion regarding this approach through NE’s DAS service.

## A - DCO
Point | Point Number(s) from Appendix A [RR-039] | Taken from Natural England’s Relevant and Written Representations Dogger Bank South (East and West) Appendix A - Development Consent Order | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
Development Consent Order (DCO) |  |  |  | Documents reviewed: [AS-121] 3.1 Draft Development Consent Order (Rev 03) (Tracked)
A0 | A3 | The Development Consent Order (DCO) does not contain an end date for deployment of cable protection for within and outside of designated sites. Natural England’s standard advice is that cable protection should only be deployed for a maximum period of 10 years from the commencement of operations outside of designated sites. Within any designated sites for benthic features, such as the Dogger Bank SAC, the condition should stipulate that there should be no deployment of cable protection after the completion of construction. |  | Natural England will provide further comment at Deadline 2.
A1 | A4 | The definition of maintain should be amended to show a clear linking to the Outline Offshore Operations and Maintenance Plan (OOOMP) or Environmental Statement. This comment applies to schedules 10-14 where similar provisions are recorded, for brevity have not repeated the comments (Article 1, Pg 8). |  | No change.
A2 | A5 | All references to Natural England should be replaced with ‘the Relevant SNCB’ (Article 1). |  | Issue addressed. References to Natural England have been replaced throughout the DCO.
A3 | A6 | Requirement 10 (2) lists the expected aspects to be detailed in the landscape management plan. We would note that the requirement for monitoring and maintaining of the landscaping works should also be secured here. (Schedule 2, Part 1, Requirement 10). |  | Natural England will provide further comment at Deadline 2.
A4 | A7 | The requirement wording should be updated to state which environmental topics will be included within the Code of Construction Practice (CoCP). Paragraph (4) should be amended to note that the relevant SNCB will be consulted by the relevant planning authority prior to the approval of any pre-commencement screening and fencing works. The production of the final soil management plan is not secured in the DCO wording. We advise this could be included within this requirement (Schedule 2, Part 1, Req. 19). |  | Natural England will provide further comment at Deadline 2.
A5 | A8 | Regarding the commitment to secure Biodiversity Net Gain (BNG) for this project, there is a need to secure the BNG for a minimum of 30 years, which should be reflected in the DCO wording. We also encourage the delivery of minimum 10% BNG to be secured in the DCO wording (Schedule 2, Part 1, Req.32). |  | The Applicant considers that as detail of the minimum 30 year period will be included in the BNG Strategy that it is unnecessary to include within the DCO. They also disagree with commiting to the recommended minimum 10% of BNG. Natural England maintains our advice, however as BNG is not yet mandatory for NSIPs we will not pursue this issue further.
A6 | A9 | Points A10 - A15 (RR ref) apply to Schedules 10 -14 where similar conditions apply. |  | N/A.
A7 | A10 | This condition does not include the requirement to submit an updated OOOMP. We also note that condition 10 (1) (c) requires details on cable protection. However, we assume this covers during construction cable protection only. We further note that operations and maintenance is provisioned for at condition 7. However, the wording at condition 7 only allows for the replenishment of cable protection. Natural England interprets this to mean the deemed Marine Licence (dML) only allows for new areas of cable protection to be installed during construction. Confirmation is needed of the intention with regard to the conditioning of cable protection deployment after construction. (Schedule 10, 15(1)) |  | Natural England will provide further comment at Deadline 2.
A8 | A11 | Amend condition to include consideration of the use of Noise Abatement Systems (NAS) within the final Marine Mammal Mitigation Protocol (MMMP). (Schedule 10, 15(1)(g)) |  | The Defra Marine Noise Policy paper was published on 21st January 2025. Natural England is reviewing this in terms of what it means for our advice on this project. We will provide further comment at Deadline 2, in the interim please see section 7 of our Deadline 1 cover letter.
A9 | A12 | Include a condition to secure the maximum hammer energy for piling of monopiles and pin piles(Schedule 10, Part 2). |  | Issue resolved. The Applicant has included maximum hammer energy for piling of monopiles (6,000kJ) and pin piles (3,000KJ) in Schedule 10, Part 2, Condition 15 (7), pg 124; Schedule 11, Part 2 Condition 15 (7) (pg 148); Schedule 12, Part 2, Condition 13 (10) (pg 174); Schedule 13, Part 2, Condition 13 (10) (pg 199).
A10 | A13 | Amend the condition such that the Site Integrity Plan for piling must be submitted no later than 6 months prior and no sooner than 9 months prior to piling. (Schedule 10, 16(3)) |  | Issue progressed. Natural England welcome the update that the SIP will be submitted no later than six months prior to the commencement of piling. We continue to advise it is submitted no sooner than nine months prior to piling.
A11 | A14 | This condition provides that most of the plans and documents under Condition 15 must be submitted 4 months prior to the works starting. Due to the size and complexity of this project, this time period is not appropriate. Given the large volume of documentation and the often complex nature, we request this be amended to six months prior to commencement. Alternatively, we are willing to discuss the required timing for each plan with the Applicant and the MMO. (Schedule 10, Part 2, 17(1)). |  | Natural England maintain that due to the increasing complexity of construction of large offshore works, six months is now considered an appropriate period for approval of pre-construction documentation and agreement of documents. And in some instances where high risks issues remain unresolved post consent, longer may be required.
A12 | A15 | Update the conditions to include ornithological monitoring. Further amendments may be required on monitoring condition wording in line with MMO advice. (Schedule 10, 20-22) |  | Natural England will provide further comment at Deadline 2.
A13 | A16 | Schedule 12 It is outlined for Pre-construction plans and documentation under Part 2, Condition 13 (1) (a) (v) of that “any exclusion zones or micro-siting requirements identified pursuant to 13(1)(f)(v) or relating to any habitats of principal importance identified as part of surveys undertaken in accordance with condition 19”; However, 13(1)(f)(v) does not exist. Furthermore, Condition 19 relates to Construction monitoring surveys, not pre-construction surveys (18)(4)(a). Schedule 13 Similar to above, it is outlined under Part 1 Condition 13 (1) (a) (v) that “any exclusion zones or micro-siting requirements identified pursuant to 14(1)(f)(v) or relating to any habitats of principal importance identified as part of surveys undertaken in accordance with condition 18”; However, 14(1)(f)(v) does not exist. Furthermore, Condition 18 relates to Construction monitoring surveys, not pre-construction surveys (18)(4)(a). Amend errors in Schedules 12 and 13 as needed. |  | Issue resolved. The applicant has updated the errors in cross-referencing in the DCO.
A14 | A18 | The Maximum Design Parameters for the number of piles that can be installed per day (including simultaneously and concurrently) have not been secured in the DCO/dML. A condition should be included to secure these. |  | Natural England welcomes that a condition has been added to the DCO and will be providing comments at Deadline 2.
A15 | A19 | The consent allows for deployment of cable protection but has no end date for such deployment. Include a condition limiting the deployment of cable protection outside of designated sites to within 10 years of the completion of construction and inside designated sites such as Dogger Bank SAC, no cable protection may be deployed after the completion of construction. Agreement should also be sought on what is meant by completion of construction. |  | Natural England will provide further comment at Deadline 2.
APP-231 8.6 Commitment Register
A16 | A20 | Natural England advise further clarity is required from the Applicant on the purpose of the document before we can provide any detailed nature conservation advice. |  | Issue resolved. The Applicant has confirmed that the Commitments Register is a certified document and has updated the DCO [Rev 03; AS-121]. However, this does not address our concerns with the Current Commitments Register as written.
A17 | A21 | Natural England advise that any named document should be clear on what the Applicant’s commitments/requirements are, and include any rationale/justification as to why the commitments are being made, even if how they will be delivered is currently unknown. |  | No change.
A18 | A22 | Natural England advise that a Schedule of Mitigation is provided for the DBS projects. If alternative approaches are taken by the Applicant, then any document needs to be more certain on key deliverables. |  | No change. Natural England maintain their concerns around the content and context of the Commitments Register.
APP-248 8.24 Outline Offshore Operations and Maintenance (OOOMP) Plan
A19 | A23 | The OOOMP will need updating and a final plan submitted and agreed (in consultation with the relevant SNCB) prior to construction. See A7. |  | No change.
A20 | A24 | The definition of maintain should be consistent between the DCO and OOOMP. See A1. |  | No change.
A21 | A25 | Natural England is concerned about what is and is not permitted as part of the DCO/dML through this named plan, in relation to replacement of cable protection over the lifetime of the project and any ‘allowances’ for new cable protection. We advise that further cable protection and scour prevention within Dogger Bank SAC would require a new marine licence, and that outside of the SAC a register should be kept and summited annually to the MMO on any placement of cable protection. This should include the volume, footprint and locations to ensue commitments have been adhered to and indirect impacts to designated sites avoided. See A15, A22. |  | No change - Natural England are reviewing the updated Outline Operations and Maintenance Plan (Rev 02) [AS-028] and will provide further comment at Deadline 2.
A22 | A26 | Natural England would welcome MMO views on Table 2-3 and the identification of additional scour prevention and cable protection within Dogger Bank SAC not requiring a marine licence. Additionally, we are concerned that whilst the use of sub-bottom profilers doesn’t currently require a marine licence, there may be in-combination significant impacts as a result of cumulative under water noise pressures that may not be addressed through the OOOMP proposals as written. |  | No change.

## B - Marine Physical Environment
Point | Point Number(s) from Appendix B [RR-039] | Taken from Natural England’s Relevant and Written Representations Dogger Bank South (East and West) Appendix B - Marine Physical Environment | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
B1 | B9 | For indentations on the seabed due to installation vessels, the Maximum Design Scenario (MDS) for anchoring for either DBS E or W in isolation is 244,640m2, however, the maximum total impacted area by anchoring is stated as 22,061m2. It is unclear which of these values is the MDS for seabed area affected by anchoring. This is also the case for the DBS E and DBS W concurrent/sequential scenario MDS. Clarification on the MDS for all construction scenarios is required. (7.8: Table 8-1) |  | Issue progressed. We agree with the clarification provided by the Applicant and advise that Table 8-1 of [APP-080] is updated to resolve this issue. |  | No change - no new information relevant to this issue has been submitted at this deadline.
B2 | B10 | For changes to bedload sediment transport due to cable protection measures, there are inconsistencies in the total footprint of inter-platform cable protection, number of array/inter-platform cable pipeline/cable crossings, and the total footprint of pipeline/cable crossing material for array cables and inter-platform cables across project build scenarios. Clarification is required. (7.8) |  | Issue resolved. The Applicant has confirmed that the numbers presented are correct.
B3 | B11 | The rationale behind remedial cable protection along 10% of the cable route within Dogger Bank SAC should be provided, with evidence provided to justify a realistic Worst Case Scenario (WCS). Specific locations (informed by acoustic data) of areas requiring cable protection should be identified, including identification of affected features/sensitive habitats. (7.8) |  | No change. |  | No change. See Appendix C2.1 and C2.2 of Natural England's Deadline 2 submission for further detail.
B4 | B12 | The WCS for remedial cable protection assumes 20% of the export cable route will require remedial protection outside of Dogger Bank SAC. A realistic worst-case scenario on the locations for cable protection should be identified (informed by geophysical and geotechnical data). We also advise that the rationale (including supporting evidence) for this requirement should be provided. (7.8) |  | No change. We understand the Applicant is updating the Cable Burial Risk Assessment [APP-244]. We will provide further comment when this is submitted into Examination. |  | No change. See Appendix C2.1 and C2.2 of Natural England's Deadline 2 submission for further detail.
B5 | B13 | For the Operational impact “Cable Repairs and Reburial”, the activity has been described, but no associated LSE pathways have been included. The Applicant should specify the LSEs and provide the MDS for each activity during operation (for all build scenarios). The WCS impact on each MPA and affected features should also be provided for direct and indirect effects. (7.8: Table 8-1) |  | Issue progressed. The Applicant has confirmed that text was missing from the table. We advise that Table 8-1 of [APP-080] is updated accordingly. |  | No change. Whilst an updated Outline offshore Operations and Maintenance Plan [AS-028] has been provided, this has not addressed this issue.
B6 | B14 | Clarification is needed on the WCS volumes for sandwave levelling/seabed for the export cable route. (7.5, 7.8) |  | Issue progressed. The Applicant has clarified that the sandwave clearance volume presented was incorrect. We advise that Table 8-1 of [APP-080] is updated accordingly. |  | No change.
B7 | B16 | We advise that a commitment is made and secured in the DCO to remove all on and above seabed infrastructure associated with the development within benthic designated sites (excluding cable crossings). Without this, the WCS should assess the impacts of leaving assets permanently in situ rather than restricting to the operational lifetime. (7.8) |  | No change. |  | No change - See Appendix C2.1 of Natural England's Deadline 2 submission for further detail.
B8 | B18 | The Preliminary CBRA is based on the Projects’ Red Line Boundary (RLB) at PEIR stage, which has been significantly revised. We advise that a more up-to-date and detailed pre-consent cable burial assessment should be provided, based on the most recent RLB and turbine/cable layout. This should use project specific geotechnical data and/or data from constructed offshore windfarms to consider the likelihood of burial success to inform realistic MDS parameters for cable protection requirements. (8.20) |  | No change. We understand the Applicant is updating the Cable Burial Risk Assessment [APP-244]. We will provide further comment when this is submitted into Examination. |  | No change - no new information relevant to this issue has been submitted at this deadline.
B9 | B19 | We advise that identification of regional scale sediment transport pathways is an important part of the baseline characterisation. Sediment transport pathways have been identified only for the landfall, adjacent coastline, nearshore and westernmost section of the Offshore Export Cable Corridor (OECC). We advise the Applicant to establish or infer sediment transport pathways for the remainder of the OECC and array areas. (7.8.1) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. We continue to advise that the Applicant should seek to establish a baseline characterisation of the sediment transport pathways that may be affected by the presence of the DBS projects.
B10 | B20, B36 | We consider the beach elevation change data presented in the ES from 2008-2015 to be out of date. More recent beach/shore platform elevation change data should be sought and analysed (alongside the older data collected), to inform the cable burial/asset integrity assessment and assess coastal vulnerability through the lifetime of the Projects. (7.5, 7.8). Whilst there is a commitment to carry out beach profile change monitoring if trenchless technique exit pits are located within the intertidal area, we advise that beach profile change monitoring should be carried out regardless to confirm beach recovery and support predictions regarding impacts to Holderness cliffs, and also monitor cable burial success and asset integrity over the lifetime of the Projects. (7.8) |  | Issue resolved. We are satisfied that information provided in AS-116 (10.38 Coastal Change Technical Note Rev 01) is sufficient to demonstrate that the cables will be buried at sufficient depth to prevent exposure for the lifetime of the project. See Appendix B1 of Natural England's Deadline 1 submission for further detail.
B11 | B15, B21, B22 | We advise that the modelling for changes to the wave and tidal regime should be updated to reflect the Option 1 turbine layout and removal of gravity base foundations for turbines from the project envelope. The outputs of the more realistic layout out scenario (Option 1) should be carried through to the assessment. (7.8, 7.8.8.3) |  | No change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change
B12 | B23 | We advise that Table 8-20 of [APP-080] should be revised using the 95% confidence level from the revised National Coastal Erosion Risk Mapping project. Cliff erosion is relevant in terms of reviewing whether construction impacts have altered baseline cliff erosion rates. Therefore, this should be done as part of the post construction monitoring rather than strictly being needed for the ES. |  | Issue progressed. See Appendix B1 of Natural England's Deadline 1 submission for further detail.
B13 | B24 | The ES identifies a significant secondary wave shadow component from the south to south-south-west (S-SSW) where the spatial extent, and potential impacts have not been assessed. The Applicant should provide details of the spatial extent of any wave shadow effects extending from DBS intoDogger Bank A. The implications of these wave shadow effects for the marine physical environment over the lifetime of the Projects should also be considered. (7.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. We continue to advise that it would be useful if the Applicant could provide the revised model output for waves approaching south to south-south-west (S-SSW). This will help inform understanding of the potential for in-combination effects.
B14 | B25 | The potential impacts of extending North Turnpikes Road to the beach/cliffs are unclear. We advise that further details are provided on the emergency intertidal access design including coastal morphology and sensitive habitats that may be affected by its presence. Any environmental impacts associated with its construction, operation, and subsequent removal should be fully considered and assessed. (7.5) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change - See Appendix B2 of Natural England's Deadline 2 submission for further detail.
B15 | B26 | Jack up barges, other vessels, equipment, and infrastructure may be used for trenchless landfall exit works during the different development phases. The Applicant should consider and assess all potential impacts to seabed and coastal morphology that may arise due to trenchless landfall works during the lifetime of the Projects. (7.8) |  | No change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change
B16 | B27, B66 | Clarification is needed on what material will be used to backfill trenches for landfall cable installation activities if the excavated material has been redistributed. We advise that sediment should be stored in such a way that it cannot be washed away. (7.8, 8.18) |  | No change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change
B17 | B28 | Removal or modification of sandwaves within the OECC and array areas could adversely affect nearby sandbanks, seabed topography, and affect flow and sediment transport patterns. All efforts should be made to avoid areas of sandwaves and/or minimise the need for sandwave levelling/pre-sweeping by micro-routing. If possible, dredged material should be placed to aid natural infilling of trenches. Best practice should be followed to assess and minimise potential impacts to sandwave/sandbank systems. The proposed pre- and post-construction monitoring should be used to assess geomorphological recovery after cable installation. (7.5, 7.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change - See Appendix C2.1 of Natural England's Deadline 2 submission for further detail.
B18 | B29 | Model results show 'wave shadows' with potential reductions in significant wave height of up to 0.7m, with the largest effects due to the offshore platforms in the Array Areas. The implications of the predicted changes to wave climate/height over the lifespan of the Projects need to be fully considered in terms of impacts to the seabed sediment composition, sediment mobility, and seabed morphology of the Dogger Bank SAC. (7.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. Whilst we will be providing our full comments on the Change Request at Deadline 3, we note that the maximum significant wave height reduction values do not appear to have changed in the revised Marine Physical Processes Modelling Technical Report (Rev 02) [AS-136]. We seek clarification from the Applicant on whether the wave modelling has been revised in line with the changes to the Project Design Envelope.
B19 | B30 | Hydrodynamic model results show lower current speeds (shadow effects) along the western boundary of the Arrays, but also increased current speeds inside the Arrays. Similarly, there are shadow areas in the difference plots for bed shear stress with areas of reduced bed shear stress adjacent to the western DBS W Array boundary and to the west and east of the DBS E Array boundary, but with areas of increased bed shear stress within the Arrays. The implications of predicted changes to current speeds and bed shear stress over the lifespan of the Projects need to be fully considered in terms of seabed sediment composition, sediment mobility, and seabed morphology of the Dogger Bank SAC. (7.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. We continue to advise that the Applicant needs to consider how the predicted changes (reductions and increases) in tidal current speeds and bed shear stress will affect patterns of erosion and deposition and seabed morphology within and adjacent to the arrays over the 30 year project lifespan. Furthermore, consideration should be given to changes in seabed heterogeneity over the lifespan of the project.
B20 | B31 | The potential for cumulative effects at landfall due to overlapping construction activities between DBS and Dogger Bank D should be considered and assessed. (8.8.3.2) |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change
B21 | B32 | Dogger Bank SAC should be included as a receptor in the Marine Physical Environment EIA. It should also be identified (along with other relevant designated sites) on Marine Physical Environment maps to inform understanding of potential impacts. (7.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No Change. We advise that whilst marine physical processes receptors are primarily morphological or water column features, designated sites may also be affected by physical changes to their integrity and special features thus it is appropriate to identify them as receptors and to be included in the marine physical processes impact assessment.
B22 | B33, B41 | We do not agree with the conclusions of the EIA or cumulative effects assessments for the Flamborough Front during Operation and Maintenance. We advise the Applicant should seek to reduce impacts as much as possible through consideration of the placement of foundation structures and reducing the WCS for foundation structures within Array Areas. Owing to the ecological importance of the Flamborough Front, and emerging evidence that suggests large OWF clusters (i.e. Dogger Bank) may result in substantial impacts on stratification, currents, and sediment resuspension; we also advise that the Applicant should commit to monitoring potential changes to stratification, currents, and productivity (pre-construction, post-construction, lifetime). The results of monitoring should be combined with those from other nearby OWFs and with up-to-date research such as from the University of Hull. (7.8, 8.7.3.4) |  | No change. Natural England will provide further comment at Deadline 3 on the In Principle Monitoring Plan (IPMP) [APP-247], in order to take into account all of the updates from Change Request 1, the Defra Marine Noise Policy paper and updated ornithology assessments. |  | No change.
B23 | B35, B50 | We cannot rule out an adverse effect on integrity for the Humber Estuary SAC due to the current condition allowing 10% of the cumulative export cable length to be protected from 350m seaward of MLWS to the 10m depth contour. We advise that alternative methods of cable burial and/or protection should be explored in line with the mitigation hierarchy, to remove or reduce the need for cable protection between MLWS and the 10m contour. If cable protection is not removed from the project envelope, the commitment and associated DCO condition should be refined to only placing cable protection within -9 and -10m below LAT, as the Applicant has already identified this as being the area potentially requiring cable protection. See also C13. (6.1, 7.5, 7.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change - See Appendix B2 of Natural England's Deadline 2 submission for further detail.
B24 | B37 | We advise that the Applicant should commit to the removal of all structures on and above the seabed and consider the potential decommissioning of any proposed external cable/scour protection (including evidence on the likelihood of its success and impacts). We advise that the Applicant should consider and assess the long-term impacts to the marine physical environment of any assets left in situ for the lifetime of the assets within a pre-construction outline Decommissioning plan. (7.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 3. |  | No Change - See Appendix C2.1 of Natural England's Deadline 2 submission for further detail.
B25 | B38 | We advise that the value of both Dogger Bank and Smithic Bank is high. This should be taken into consideration by the Applicant and their assessment updated where necessary. (7.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. We welcome the Applicants' acknowledgement [AS-048] that the value of both Dogger Bank and Smithc Bank are higher than low. However, our advice remains unchanged.
B26 | B39, B47 | Supporting evidence for seabed recovery from installation vessels has been provided based on pre-installation (2010) and post-removal surveys (2022) for two Met Masts in DBB and C OWFs (i.e. after a period of 12 years). There is insufficient information behind the conclusion that the duration, reversibility and, thus, magnitude of impact on seabed morphology will be low. Consequently, we are unable to agree with the assessment conclusion that effect significance will be negligible. The Applicant should provide further evidence for seabed recovery following installation vessel impacts. Additional mitigation should be explored to minimise impacts to the seabed morphology at Dogger Bank and the SAC during construction and Operation and Maintenance activities. (8.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. As stated by the Applicants [AS-048], persistent installation vessel impacts may occur on Dogger Bank where no (or little) mobile sediment overlies static geological formations. We therefore advise that the assessment of recoverability, value and sensitivity for Dogger Bank should be updated to reflect this. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail.
B27 | B40, B47 | The sensitivity of Dogger Bank (and Dogger Bank SAC) to changes in seabed level from certain construction activities has been assessed as negligible. We advise that these construction activities and similar O&M activities are likely to result in changes to the extent and distribution and physical structure of the site’s sandbank feature, which will further hinder its restore objective(s). Further mitigation measures should be adopted and secured to minimise impacts. Pre and post-construction monitoring should be committed to to validate predictions of seabed elevation change and extent of deposition, sediment composition and distribution change, and seabed recovery across the Array Areas and Inter-Platform Corridor within Dogger Bank SAC. Should impacts be found to be greater than predicted then the necessary recourse should be taken. (8.7.3.6) |  | No change. Natural England are reviewing the Applicant’s response and additional submission '10.44 Review of Evidence on Recovery of Sandbank Habitat Following Habitat Damage' [AS-025] and will provide further comment at Deadline 2. |  | No Change - See Appendix C2.1 of Natural England's Deadline 2 submission for further detail.
B28 | B42 | There is insufficient information regarding the location and significance of cable crossings and nearshore cable protection measures relative to Smithic Bank to support the assessment conclusions. The potential exchange of sediment between South Smithic and the Holderness Coast should be considered when assessing impacts to the nearshore and circulatory sediment transport processes due to the presence of nearby cable protection measures and cable crossings. (7.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. We continue to advise that more detailed information is needed regarding the proposed cable crossing with the Hornsea Four export cable corridor, and its proximity, to Smithic Bank, in order to better understand potential impacts on nearshore sediment transport processes.
B29 | B43 | There is insufficient information to support the assessment of changes to bedload sediment transport and seabed morphology due to the presence of cable protection measures on Dogger Bank. We advise that, firstly, the Applicant should attempt cable burial across Dogger Bank to avoid placement of cable protection measures within Dogger Bank SAC. Secondly, a seabed mobility assessment should be carried out to inform the cable burial assessment and, thus, the requirement for cable protection measures. Lastly, if cable protection measures are found to be necessary, potential changes to seabed sediment transport processes and seabed morphology should be fully assessed for the WCS option for cable protection measures on Dogger Bank. (7.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change - See Appendix B2 of Natural England's Deadline 2 submission for further detail.
B30 | B44 | It is suggested that the magnitude of decommissioning effects on the marine physical environment would be comparable to those during the construction phase. However, the baseline conditions at the end of design life may differ significantly from those at pre-construction and the value of receptors may change over the lifetime of the project. Consequently, the EIA cannot confidently determine decommissioning impacts at the end of the design life of the Projects. A number of alternatives to decommissioning are emerging, and whilst these alternatives may be beyond the scope of the present ES, we advise that the EIA is updated as such alternatives progress. The Applicant should provide a pre-consent outline decommissioning plan which considers the potential long-term impacts to the marine physical environment and processes of any assets left in situ. (7.5, 7.8) |  | No change. The Applicant does not agree that an outline decommissioning plan at this stage is helpful. We continue to advise that a pre-consent outline decommissioning plan is produced. We highlight that under S105 of the Energy Act 2004 a decommissioning plan must be provided to the SoS prior to construction of which the outline decommissioning plan would form the basis. |  | No change - See Appendix C2.1 of Natural England's Deadline 2 submission for further detail.
B31 | B45 | “Penetration and/or disturbance of the substratum below the surface of the seabed, including abrasion” has been screened out for Operation and Maintenance (O&M) for Offshore Annex I Habitats and Dogger Bank SAC but has been included in the assessment (Section 6.4.2.1.1). We agree this should be included in the assessment and advise the screening tables are updated. (6.1, 6.1.1) |  | Issue progressed. We continue to advise that the RIAA is updated to accurately reflect the impacts screened in, however as this impact has been included in the assessment we will not pursue this further.
B32 | B46 | For Annex 1 features of the Humber Estuary SAC, Section 6.6.1.1 of the RIAA only lists ‘Sandbanks which are slightly covered by seawater all the time’ and ‘Mudflats and sandflats not covered by seawater at low tide’ as having been assessed, despite more features being listed as screened in for assessment. We advise that the full list of features identified at Screening should be assessed in the RIAA. (6.1.1, 6.1) |  | Issue progressed. The Applicant has confirmed that the missing features should have been assessed in the RIAA. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change
B33 | B48 | Dogger Bank D OWF has not been included in the in-combination assessment for impacts to the Humber Estuary SAC - we advise this is included. (6.1) |  | No change. |  | No change - We continue to advise Dogger Bank D OWF is included in the in-combination assessment for impacts to the Humber Estuary SAC.
MCZ Assessment - Document(s) Used: [APP-240] 8.17 Stage 1 Marine Conservation Zone Assessment
B34 | B51 | Our concerns raised for the overall EIA in relation to impacts from cable installation and operation are all also relevant within the MCZ assessment. The MCZ Stage 1 impact assessment should be updated based on the comments provided on the impact assessment. (8.17) |  | No change. |  | No change - Please see our comments on the Benthic Technical note [AS-104] included within Deadline 2 Appendix C2.1.
B35 | B53 | An EIA matrix has been used to determine magnitude rather than considering if there is an impact pathway to the MCZ features and utilising conservation objectives, conservation advice and advice on operations. This section of the MCZ assessment should be updated in line with Stage 1 MCZ Assessments undertaken for other OWF projects. Until this is updated, we are unable to agree with the conclusions of this assessment. (8.17) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change - Please see our comments on the Benthic Technical note [AS-104] included within Deadline 2 Appendix C2.1.
B36 | B54 | The impacts assessment does not consider sandwave levelling along the export cable corridor. We advise against deposition of sand in locations where SSC and deposition become significantly elevated above baseline level and suggest this is secured in the commitments register. (8.17) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. The Applicant [AS-025] considers that as the offshore ECC doesn't overlap the MCZs, no direct effects will occur as a result of sandwave levelling. The Applicant has highlighted that increased SSC in the ECC from activities involved in seabed preparation for cable installation have been considered. We continue to advise against deposition of sand in locations where SSC and deposition become significantly elevated above baseline level, and that this is secured in the commitments register.
B37 | B55 | The mitigation measures to minimise scour protection do not provide certainty that impacts will be minimised to acceptable levels. Pre-construction surveys do not relate to either the MCZ or mitigation measures unless surveys cover the secondary impacts zone within the MCZ, and remedial actions are taken should impacts be greater than predicted. Further consideration is required of mitigation measures that will reduce impacts to the MCZ. (8.17) |  | No change. Natural England welcomes the Applicant's commitments to not anchoring or using jack up vessels in the MCZ , however these aren't necessarily mitigating for scour protection impacts |  | No change - we maintain our previous advice that commitments to not anchoring or using jack up vessels in the MCZ aren't necessarily mitigating for scour protection impacts and continue to advise that further consideration is required of mitigation measures that will reduce impacts to the MCZ.
B38 | B56 | We are concerned that temporary deterioration in condition is to be disregarded if the habitat is sufficiently healthy and resilient to enable recovery. Further evidence is required to demonstrate that impacts will be temporary, and recovery can occur in the short term. (8.17) |  | No change. Natural England will provide comments on [AS-104] 10.38 Benthic Ecology Technical Note at Deadline 2. |  | No Change - we maintain our previous advice.
B39 | B58 | Dogger Bank D OWF has not been included in the in-combination assessment for impacts to Spurn Point - we advise this is included. (8.17) |  | No change. |  | No change - We continue to advise Dogger Bank D OWF is included in the in-combination assessment for impacts to Spurn Point.
B40 | B60 | Further mitigation could be applied to avoid potential impacts to sediment transport on the MCZ. (8.17) |  | No change. |  | No change - Please see Appendix B2 and our comments on the Benthic Technical note [AS-104] included within Deadline 2 Appendix C2.1.
B41 | B61 | The conservation objectives for the Holderness Inshore MCZ could be hindered due to the current dML condition allowing 10% of the export cable to be protected from 350m seaward of MLWS to the 10m depth contour. This could disrupt sediment transport associated with Holderness Inshore MCZ. (8.17) |  | No change. |  | No change - Please see Appendix B2 and our comments on the Benthic Technical note [AS-104] included within Deadline 2 Appendix C2.1.
Assessment of SSSI impacts - Document(s) Used: [APP-080] 7.8 ES Chapter 8 – Marine Physical Environment
B42 | B62 | It is stated that there is a potential for impacts to Withow Gap Skipsea SSSI due to cable installation/removal. However, it is our understanding that the landfall option with the potential to interact with this SSSI has been withdrawn. We advise that the impact assessment is updated as needed. (7.8) |  | Issue Progressed. The Applicant has confirmed that the Projects no longer directly interact with the SSSI as part of any landfall works but that it was included for consideration of any potential indirect effects. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No change.
Disposal of material arising from construction activities - Document(s) Used: [APP-242] 8.18 Disposal Site Characterisation Report
B43 | B63, C54 | This document will need updating pre-consent based on comments Natural England has provided on the EIA within Appendix B and C as currently we do not agree with conclusions on the level of impacts. (8.18) |  | No change. |  | No change - no new information relevant to this issue is likely to be submitted by the Applicant and we will review once submitted
B44 | B64, C55 | The whole of the offshore windfarm array footprints, the inter-cable platform corridor and the export cable corridors will be disposal locations, but deposition will only occur where possible within the same sediment. Given that sandwave levelling is likely to be undertaken by suction hopper dredge and then sediment released at the sea surface, it is unlikely that this will occur. We advise that disposal options are explored to ensure that sediment is deposited in similar sediment types. (8.18) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change - See Appendix C2.1 of Natural England's Deadline 2 submission for further detail.
B45 | B65, C56 | We advise the mitigation in Section 5.2 does not go far enough, especially within the Dogger Bank SAC and in areas where there are priority habitats and/or indirect impacts to designated site features could occur. We advise that the following mitigation measures are adopted (but not exclusively): - All deposition of dredged sediment within the Dogger Bank SAC should be done through the use of a fall pipe and adjacent and upstream of the dredge location in same sediment type to ensure sediment stays within the site. - Drill arisings should be deposited within similar sediment characteristics i.e. not on sandbanks. Therefore, adjacent to turbines is unlikely to be appropriate. - Sandwave deposition should avoid areas of priority habitats under NERC 2006 by the inclusion of a 50m buffer around the NERC habitats. - Deposition of dredge material along the export cable should utilise a fall pipe where there is a risk of increases in suspended sediment concentrations impacting on designated site features and those of ecological importance. (8.18) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change - see point B36 and B44 and Appendix C2.1 of Natural England's Deadline 2 submission for further detail.
B46 | B66, C57 | For intertidal exit pits, we advise that alternative storage options for material from the landfall exit pits are explored (see also comments (B15) Appendix B) |  | No change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change
Scour Prevention - Document(s) Used: [APP-251] 8.27 Outline Scour Protection Plan
B47 | B67, C58 | We advise that this document needs to better consider the risk and implications of secondary scour occurring. (8.27) |  | Natural England will provide comments on [AS-081] 8.27 Outline Scour Protection Plan (Rev 02) at Deadline 2. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail.
B48 | B68, C59 | Section 1.2 - Consideration should be given to comments made in relation to minimising environmental impacts as much as possible through the choice of scour prevention/cable protection. Every effort should be made to avoid using those that are least likely to be recovered at the time of decommissioning. (8.27) |  | No change. |  | No change - We refer you to Appendix C2.1 of Natural England's Deadline 2 submission and the link to Natural England's published paper on decommissioning of cable protection.
Cable Statement - Document(s) Used: [APP-243] 8.20 Cable statement |  |  |  | Documents reviewed: [AS-079] 8.20 Cable Statement (Rev 02) (Tracked)
B49 | B69, C60 | This document will need updating pre-consent based on comments Natural England has provided on the EIA within Appendix B and C, as we currently do not agree with conclusions included within the document. (8.20) |  | Issue progressed. Natural England welcomes the Applicant's commitment to the separate bundling of pairs of the export cables as outlined in the updated Cable Statement [AS-079], and advise that this commitment is secured in the DCO. This is notwithstanding other outstanding issues such as updates to the CBRA being required. |  | No change.

## C - Benthic&Intertidal Ecology
Point | Point Number(s) from Appendix C [RR-039] | Taken from Natural England’s Relevant and Written Representations Dogger Bank South (East and West) Appendix C - Benthic and Intertidal Ecology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
C1 | C8 | There are inconsistencies in the impact assessment calculations across the various chapters/documents. For example, maximum anchoring footprint for export cable installation, total array areas and offshore ECC cable corridor construction footprint etc. We advise that the maximum temporary construction footprints are reviewed and updated where necessary. (7.05) |  | Issue progressed. The Applicant has clarified the differences in values presented and confirmed that some were incorrect. We advise that the relevant ES chapters and documents are updated as needed. |  | No change - no new information relevant to this issue has been submitted at this deadline.
C2 | C9 | It is suggested that cable protection may be used at the landfall exits, however there is a commitment to not use cable protection in the intertidal area and/or for 350m seaward of Mean Low Water Springs (MLWS). This also contradicts cable landfall activities set out in the Project Description and MCZ Stage 1 assessment that only describe cables being buried and exit pits naturally backfilling. We advise that clarity is provided on the use of cable protection at the Horizontal Direction Drilling (HDD) exit pits. (7.05) |  | No change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change
C3 | C11 | Justification is required for the WCS quantification of cable protection within and outside of Dogger Bank SAC. This should cover: - Previous experience and available information about the ground type within the Array area and along the ECC route. -Possible post-construction measures e.g. placement of additional scour replenishment during the operational phase - Implications from the removal and replacement of scour protection during cable repairs especially where a new cable loop is included - Implications from the changes in scour prevention/cable protection elevation above the seabed to ensure it remains within the parameters assessed. (7.05) |  | No change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change
C4 | C12 | Clarity is needed on how the potential for the addition of further cable/scour protection during the operational phase has been considered and included within the worst-case calculations for cable/scour protection. It is unclear whether figures provided in the Offshore Operations and Maintenance Plan (OOMP; APP-248) for replacement cable protection for the export cables have been integrated into the Project Description. Estimates for cable protection replacement requirements for the inter-array and inter-platform cables have also not been provided. We advise that the standard for quantities of additional scour and/or cable protection outside of benthic SACs is for the replenishment of 10% of any scour prevention/cable protection laid during installation within a 10-year period, as long as the overall footprint is not increased. Any additional scour prevention/cable protection during the operational phase within a designated site will require a separate Marine Licence. See C13 below. (7.05, 8.24) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. See Appendix C2.1 and C2.2 of Natural England's Deadline 2 submission for further detail.
C5 | C13 | We are concerned that Table 2-3 of the OOMP indicates that the Applicant considers the lifetime footprints presented in the Project Description to be allowances for cable protection to be installed at any point through the lifetime of the Projects, rather than the amount that will be required for the construction phase alone, which will subsequently have a footprint and impact for the lifetime of the project. We advise that the maximum design parameters for the ECC and array area, including the lifetime footprint, should be revised to only include cable/scour protection anticipated to be installed during construction. The OOMP should also be updated to reflect the licensing requirements for additional protection installed within Dogger Bank SAC during operation. (7.05, 8.25) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. See Appendix C2.1 and C2.2 of Natural England's Deadline 2 submission for further detail.
C6 | C14 | There are contradictions with regard to the inclusion of cofferdams in the Project scope, including the dimensions provided. It is also stated that the Project has committed to not using cofferdams within the exit pits. Clarification is required on the WCS for the landfall works in relation to cofferdam usage - any documents and assessments should be updated accordingly. (7.09) |  | Issue progressed. The Applicant has confirmed that no cofferdams would be used in the Projects’ Landfall Zone and that the inclusion of cofferdams within Table 9-1 was an error. The relevant ES chapters and documents should be updated to reflect this. |  | No change - no new information relevant to this issue has been submitted at this deadline.
C7 | C15, C25, C38, C47 | The Applicant has not sufficiently characterised benthic receptors within Flamborough Head SAC. All benthic receptors within the ZoI, particularly those within designated sites, need to be sufficiently characterised to enable a robust, evidenced assessment to be undertaken and presented. In the absence of characterisation of benthic receptors at a suitable resolution, the WCS needs to be presented (e.g. most sensitive biotope within the broadscale habitat used as a basis for assessments) to consider the sensitivity or recoverability of the benthic receptors to the identified pressure pathways. (7.09, 6.1) |  | No change. The Applicant has provided 10.38 Benthic Ecology Technical Note [AS-104] in response to this issue. We will provide our comments on this document at Deadline 2. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for comments on 10.38 Benthic Ecology Technical Note [AS-104].
C8 | C18 | The cumulation of benthic ‘ecological halo effect’ following the placement of structures on the seabed has not been considered. A robust assessment is needed of the potential Worst-Case area of impact on benthic communities within Dogger Bank SAC sandbank feature, and the nature and scale of that impact, as a result of changes to physical and biological processes following the placement of structures and cable/scour protection on the seabed. Once assessments have been updated, monitoring should be secured via the In principal monitoring plan to determine whether the residual impacts are as predicted. (7.09) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change - Natural England maintain our advice provided at Relevant Reps. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail.
C9 | C19 | It is unclear how the ‘value’ of receptors has been consistently incorporated into the assessment process. The Applicant has considered all biotopes within the red line boundary, with the exception of those characterised by piddocks, to be of low value. This includes biotopes representative of Annex 1 habitat within Dogger Bank SAC, and no consideration has been given to biotopes within Flamborough Head SAC. We advise that the methods and rationale for valuing benthic receptors, and how value has been used within the assessment process, is reviewed and documents updated accordingly. The significance of impacts on all benthic receptors should thereafter be reassessed. (7.09) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. We continue to advise that an appropriate value should be attributed to biotopes/habitats which contribute to Annex I features, and subsequently more appropriately used to inform the magnitude of impacts. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail.
C10 | C20 | We disagree with “Habitats or species that provide prey items for other species of conservation value” being considered of low value in the assessment. Of note are spawning/nursery grounds for sandeel and herring, both of which are an important prey resource for Annex I bird species and Annex II marine mammal features of designated sites. Within the wider marine environment impacts to habitats that provide prey availability may be considered as low, however it should be recognised that some areas remain more important than others. The importance of the ’Dogger Bank’ area for fish species is well documented. We advise that a generic low value can’t be attributed to all areas within the red line boundary. We also advise that impacts to benthic habitats which reduce/remove their ability to support benthic communities which are integral to maintaining populations of Annex I and II designated site features, needs to be fully considered within the ES. (See Sheet E for further comments on indirect effects) (7.09) |  | No change. |  | No change. We note the Applicant has contested the importance of the Dogger Bank sandbank system for prey availability and foraging species. Natural England disagrees with the justification provided and therefore maintains the advice provided in our Relevant Representation on this issue.
C11 | C21, C31 | Loss of benthic habitat as a result of UXO clearance, particularly within Dogger Bank SAC, should be added to the worst-case calculation for the EIA and RIAA, whether it be temporary or otherwise. We advise that the Applicant also needs to evidence their claim that “craters would be expected to re-fill with sediment over the course of days” (applies to both UXO detonations and jack-up operations). If depressions are created from UXO clearance or jack-up operations in areas of coarse or mixed sediments, the area may need to be considered as permanent habitat change/loss unless it can be otherwise evidenced that they will backfill with similar sediment types. We consider that recovery is altogether unlikely within the irreplaceable NERC Section 41 habitats which have been identified within the red line boundary (i.e. Piddocks with a sparse associated fauna in sublittoral very soft chalk or clay). (7.09, 6.1, 7.05) |  | No change. The Applicant has provided a Review of Evidence on Recovery of Sandbank Habitat Following Habitat Damage [AS-025] in response to this issue. We will provide our comments on this document at Deadline 2. |  | No change. See Appendix C2.1 and Section 3 of Appendix F2 of Natural England's Deadline 2 submission for further detail.
C12 | C22, C44 | The Applicant has not committed to using any specific type of cable/scour protection and has not considered the limitations some methods present with regard to successful decommissioning and/or likelihood of degradation over the lifetime of the project, which could have wider impacts in the case of grout bags/bagged solutions. Due consideration should be given to the nature of the cable/scour protection used and should favour those engineering options with the greatest likelihood of successful removal at the Projects’ end of life. We advise against the use of rock protection within designated sites and against grout bags, unless filled with locally sourced sediment similar to that within the SAC. (7.05) |  | No change. To note: We believe the Applicant's response to comment C22 in [AS-048] may be an error and are therefore basing our response on their response to comment C43 (which has been signposted from the response to C44). |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail.
C13 | C23 | We advise that the Applicant commits to bundling the export cables for each project as mitigation - this would halve the number of trenches needed (from two to one for each array) and reduce cable protection requirements. (7.05) |  | Issue progressed. We welcome the Applicant's commitment to bundling the export cables in the updated Cable Statement ([AS-079] 8.20 Cable Statement Rev 02). We advise that this commitment is secured in the DCO and/or commitment register and relevant application documents and assessments are revised accordingly. |  | No change - no new information relevant to this issue has been submitted at this deadline.
C14 | C24 | The provision of a Cable Statement/Cable Burial risk assessment is not embedded mitigation, as the specific commitments within the final detailed plans will be key in determining the effectiveness of the mitigation. Should further commitments and/or changes to project design be made by the Applicant, the impact assessment should be updated. (7.09, 6.1, 8.18) |  | No change. Please see Section 2 of our Deadline 1 cover letter for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline.
C15 | C26 | The RIAA will need updating to ensure that all revisions to the assessments are incorporated within it. |  | No change. Please see Section 3 of our Deadline 1 cover letter for further detail.
C16 | C27, C49 | We do not agree that an AEoI can be excluded from the disturbance/damage of Annex I sandbanks within the Dogger Bank SAC. Unlike more dynamic sandbanks, the length of time for recovery could be up to 25 years. We highlight that the R4 Plan Level benthic compensation includes the requirement for benthic compensation for disturbance/damage caused to Annex I ‘glacial till’ Annex I Sandbanks within Dogger Bank SAC. (6.1) |  | No change. Natural England are reviewing 10.44 Review of Evidence on Recovery of Sandbank Habitat Following Habitat Damage' [AS-025] and will provide further comment at Deadline 2. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail.
C17 | C29 | Penetration and/or disturbance of the substratum below the surface of the seabed, including abrasion, should be screened in for the Operation and Maintenance phase for Dogger Bank SAC. (6.1) |  | Issue progressed. The Applicant has clarified that this impact was screened in. We advise that the relevant Tables (6-4, 6-6) in APP-046 are updated to reflect this. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail.
C18 | C30 | Full consideration of the likely nature, extent, duration, and significance of impacts upon SPA and SAC supporting habitats is required to inform a robust assessment of the likely impacts upon designated ornithological and marine mammal features. We consider that this has not been adequately undertaken for sites including Flamborough and Filey Coast SPA and the Southern North Sea SAC. (7.09) |  | No change. |  | No change. We note the Applicant has contested the importance of the Dogger Bank sandbank system for prey availability and foraging species. Natural England disagrees with the justification provided and therefore maintains the advice provided in our Relevant Representation on this issue.
C19 | C33 | The worst-case suspended sediment concentrations from trenching activities in the ECC are inconsistent between the RIAA and EIA chapters - we advise that the EIA and/or RIAA are updated with accurate worst-case prediction values as needed. (6.1, 7.09) |  | Issue progressed. Natural England welcome the clarification provided by the Applicant in their response [AS-048] to our Rel Rep [RR-039] (C33), confirming that some of the values presented were incorrect. We will provide further comment at Deadline 2. |  | Issue progressed. As noted at DL1, the Applicant has provided clarification on the WCS SSC due to cable trenching within the array areas and offshore export cable corridor. The Applicant considers that the correction does not alter the assessment conclusions reached in the Benthic Ecology chapter [APP-085] or RIAA HRA Part 2 of 4 [APP-046]. We advise that relevant documents are updated to reflect these changes and to fully resolve this issue. We also seek confirmation from the Applicant that the predicted worst-case values for sediment deposition resulting from a sediment plume (due to trenching) have not changed as well.
C20 | C34 | The Applicant has calculated an ‘as built’ estimate for habitat loss for consented projects within Dogger Bank SAC to inform impacts to extent and distribution. These are not legally secured, thus we advise that consented parameters should be used to inform habitat loss estimates for assessment. (6.1) |  | Issue addressed. We welcome the confirmation from the Applicant that the habitat loss estimate based on consented parameters was used in the assessment.
C21 | C35 | Clarification is required on the WCS for sandwave levelling/seabed clearance. We also advise that within benthic MPAs any sediment deposition is located within areas of similar sediment type, as close to and upstream of the original sandwave, and is deposited using a fall pipe (should a suction hopper dredger be used). An outline sandwave levelling, deposition and recovery plan should be provided as either a standalone document or as part of the Cable Statement [APP-242] /Outline Cable Burial Risk Assessment. (6.1, 7.09, 8.18) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. However, we note that the Applicant has indicated that the Cable Statement would be updated to include detail relating to sandwave levelling and deposition. The most current version of this (8.20 Cable Statement, Rev 02, [AS-079]) does not include such update. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. We note there is a potential for this to become a red risk depending on the Applicant's response.
C22 | C36 | We do not agree with the RIAA assessment that habitat loss impacts in Dogger Bank SAC are “minimal”. Taking into account the many anthropogenic activities occurring and planned across the Dogger Bank SAC, when all pressures are summed it will lead to an adverse effect on the site integrity, as concluded in the Plan Level HRA. (6.1) |  | N/A
C23 | C37, C48 | We do not agree with the worst-case calculation of area of loss due to change to another seabed/sediment type for Dogger Bank SAC presented in the RIAA as we are not confident that the calculations are based on realistic worst-case calculations (C12, C13, C18, C35). We advise that a robust assessment is provided of the potential Worst-Case area of impact on benthic communities within Dogger Bank SAC sandbank feature. Consideration should be given to the nature of the impact as a result of changes to physical and biological processes, following the placement of structures and cable/scour protection on the seabed. (6.1) See also C18. |  | No change - Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. See point C8 for further information.
C24 | C39 | Natural England advise that a tidal ellipse is used to estimate the zone of greatest influence for sediment plumes for the array area and export cable corridor. We note that the Zone of Influence (ZoI) for suspended sediment has been updated to 8km (6.1, Table 6-1) based on site specific physical processes modelling undertaken. It is unclear as to where the 8km ZoI is derived from. The Applicant should provide further clarity on estimated sediment plume sizes including which values have been used to assess for Changes in Suspended Sediment Concentration and Transport due to Cable Installation (Array, Inter Platform and Export) and smothering and siltation for all relevant parts of the Application. (6.1, 7.08) |  | No change. We welcome the clarification provided in the Applicant's response that the 8km ZoI is incorrect, we will provide further comment at Deadline 2. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail.
C25 | C10, C41 | A drill arising footprint has not been provided. The placement of drill arisings adjacent to turbines may result in further habitat loss/change. As mitigation, the Applicant should commit to the placement of drill arisings in areas of similar habitat/particle size. Otherwise, this will need to be assessed similar to that of scour prevention/cable protection as a lasting impact included within the AEoI for Dogger Bank SAC and commitments to remove at the time of decommissioning will be required. (6.1) |  | No change - Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. We maintain our previous advice that the placement of drill arisings adjacent to turbines may result in further habitat loss/change. If drill arisings cannot be placed in areas of similar habitat / particle size, further assessment for habitat loss will be required. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail.
C26 | C42 | We advise that gravity based foundations are not used for offshore platforms. (6.1) |  | No change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change
C27 | C43 | A commitment to remove all on and above seabed infrastructure (including cable and scour protection) at the time of decommissioning should be secured in the DCO, as has been required for all offshore wind farms previously consented within the Dogger Bank SAC. (7.05) |  | No change. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail.
C28a | C45 | The Applicant has given consideration to identifying areas of shallow glacial till in the Offshore Development Area to inform post-consent discussions on micrositing cables. However, the DCO conditions listed do not secure this as they only refer to identifying priority habitats, which would not include glacial till. We advise this mitigation should be applicable to underlying glacial sediments within Dogger Bank SAC as well as priority habitat identified along the ECC, e.g. piddocks. We advise that the DCO conditions listed are updated to secure this. |  | Issue resolved. The relevant DCO conditions have been updated to include surficial deposits of glacial till [AS-121]. For consistency, we would welcome this also being updated in the Commitments Register.
C28b | C45 | A pre-consent Outline Cable Burial Risk Assessment within an updated Cable Statement should also be provided which considers all available geotechnical information to implement mitigation measures which further avoid, reduce and mitigate impacts by ensuring that optimal cable burial depths can be achieved, thus avoiding/reducing the need for cable protection and enabling a realistic worst case scenario to be assessed. (7.09) |  | No change. We continue to advise that an updated Outline Cable Burial Risk Assessment is provided. |  | No change - no new information relevant to this issue has been submitted at this deadline.
C29 | C46 | We note the Applicant’s comparison to the scale of impact from fisheries on Dogger Bank SAC compared to OWF, and the recent introduction of byelaws and closure of the sandeel fishery enabling recovery of the sandbank feature from this pressure. Whilst we acknowledge that fishing activity has historically had a broader impact on Dogger Bank, this does not reduce or negate the impacts of other industries which are additional to pre-existing impacts. Neither does mitigation introduced for the impacts of one industry remove the need for another industry to mitigate its impacts. (6.1) |  | N/A
Priority Habitats and Species listed under Section 41 list of the Natural Environmental and Rural Communities (NERC) Act, 2006 - Document(s) Used: [APP-085] 7.09 ES Chapter 9 – Benthic and Intertidal Ecology |  |  |  | Documents reviewed: [AS-121] 3.1 Draft Development Consent Order (Rev 03) (Tracked)
C30 | C51 | The identified biotope ‘A4.231 Piddocks with a sparse associated fauna in sublittoral very soft chalk or clay’ (and peat and clay exposures more generally) is considered likely to be irreplaceable and is also a priority habitat. The EIA would benefit from considering the importance and rarity of peat and clay exposures - every effort should be made to avoid impacts to these priority habitats, particularly where habitats support rare and/or irreplaceable communities such as boring piddocks. (7.09) |  | Issue resolved. The Applicant has considered pre-construction surveys and micro-siting. See comment below (point C31) for further information.
C31 | C52 | There is no strong commitment to avoid/microsite around Priority Habitats as listed under Section 41 of the NERC Act 2006. The adoption of mitigation measures via a Benthic Mitigation Plan should be further considered in order that impacts (particularly permanent loss), on all Section 41 Habitats are avoided and/or reduced wherever feasible through mitigation measures such as micro-siting. (7.09) |  | Issue resolved. The Applicant has provided an update to the DCO [AS-121] 3.1 Draft Development Consent Order (Rev 03) (Tracked) setting out micro-siting requirements.
Disposal of material arising from construction activities - Document(s) Used: [APP-242] 8.18 Disposal Site Characterisation Report
C32 | C54 | This document will need updating pre-consent based on comments Natural England has provided on the EIA within Appendix B and C as currently we do not agree with conclusions on the level of impacts. (8.18) |  | No change. |  | No change. We continue to advise that this document will need updating pre-consent.
C33 | C55 | The whole of the offshore windfarm array footprints, the inter-cable platform corridor and the export cable corridors will be disposal locations, but deposition will only occur where possible within the same sediment. Given that sandwave levelling is likely to be undertaken by suction hopper dredge and then sediment released at the sea surface, it is unlikely that this will occur. We advise that disposal options are explored to ensure that sediment is deposited in similar sediment types. (8.18) |  | No change. Please see point C21. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. We note there is a potential for this to become a red risk depending on the Applicant's response.
C34 | C56 | We advise the mitigation in Section 5.2 does not go far enough, especially within the Dogger Bank SAC and in areas where there are priority habitats and/or indirect impacts to designated site features could occur. We advise that the following mitigation measures are adopted (but not exclusively): - All deposition of dredged sediment within the Dogger Bank SAC should be done through the use of a fall pipe and adjacent and upstream of the dredge location in same sediment type to ensure sediment stays within the site. - Drill arisings should be deposited within similar sediment characteristics i.e. not on sandbanks. Therefore, adjacent to turbines is unlikely to be appropriate. - Sandwave deposition should avoid areas of priority habitats under NERC 2006 by the inclusion of a 50m buffer around the NERC habitats. - Deposition of dredge material along the export cable should utilise a fall pipe where there is a risk of increases in suspended sediment concentrations impacting on designated site features and those of ecological importance. (8.18) |  | No change. Please see point C21 and C25. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. We note there is a potential for this to become a red risk depending on the Applicant's response.
C35 | C57 | For intertidal exit pits, we advise that alternative storage options for material from the landfall exit pits are explored (see also comments (B15) Appendix B) |  | No change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change
Scour Prevention - Document(s) Used: [APP-251] 8.27 Outline Scour Protection Plan
C36 | C58, C59 | We advise that this document needs to better consider risk and implications of secondary scouring and highlight the need to minimise environmental impacts thourgh choice of scour prevention / cable protection. |  | See Sheet B - Marine Physical Environment (Point B47-B48). |  | See Sheet B - Marine Physical Environment (Point B47-B48).
Cable Statement - Document(s) Used: Document used: [APP-243] 8.20 Cable statement
C37 | C60 | This document will need updating pre-consent based on comments Natural England has provided on the EIA within Appendix B and C, as we currently do not agree with conclusions included within the document. (8.20) |  | See Sheet B - Marine Physical Environment (Point B49). |  | See Sheet B - Marine Physical Environment (Point B49).

## D - Benthic Compensation
Point | Point Number(s) from Appendix D [RR-039] | Taken from Natural England’s Relevant and Written Representations Dogger Bank South (East and West) Appendix D - Benthic Compensation | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Issue Resolved
Compensation Measure: New site designation or Extension for Annex I Sandbanks
D1 | Agreed compensation level | The SNCBs are not in agreement on the presented WCS of habitat damage of Annex I Sandbanks within Dogger Bank SAC. We advise that the points raised in Appendix B and C of our Relevant Representations/Written Representations (RR/WR) are addressed. |  | No change. |  | Please see Natural England's Deadline 2 cover letter
D2 | Scale/extent of measure | The SNCBs have outstanding concerns about the outcomes of the Impact Assessment and evidence used to support conclusions on scale and significance of potential impacts from cable installation activities and cable protection installation from DBS. Until these issues are resolved we do not agree with the scale and extent of the compensation measures required. This compensation measure will be led by DEFRA (with interested parties), therefore delivery mechanisms, scale costs and timeframes presented by the Applicant cannot and should not be relied upon. |  | No change. |  | Please see Natural England's Deadline 2 cover letter
D3 | Timing: Deliverable before impact | We recognise that there are likely to be time lags between impact occurring and compensation achieving the desired outcomes. In this scenario, the SNCBs would wish to see the project contribution to the measure to be such that it ensures an overall environmental net positive outcome for the impacted feature over the lifetime of the project. We advise that the points raised in Appendix B and C of our RR/WR are addressed. |  | See response to ISH agenda item 6.3 in Annex 2 of our Deadline 1 cover letter. |  | Please see Natural England's Deadline 2 cover letter
D4 | Location of measure; Long term implementation; Success criteria/Ability to prove additionality. | This is still under consideration by DEFRA, NE and JNCC and as yet, nothing has been agreed and/or secured. If and when further information becomes available during Examination we will update accordingly. However, any assurances in the security of this measure should be sought directly from DEFRA. |  | See response to ISH agenda item 6.3 in Annex 2 of our Deadline 1 cover letter. |  | Please see Natural England's Deadline 2 cover letter
Compensation Measure: Reduction of fishing pressures as a supplementary measure for Annex I Sandbanks
D5 | Theoretical merit to deliver compensation | The use of byelaws to remove fisheries pressures from another SAC has ecological merit. However, outside of a designated site this would require legislative changes to address impacts from other industries that could still occur. It is unclear how this measure will ensure the coherence of the National Site Network. We note that this is a ‘supplementary’ measure if site extension fails and is outside of the SNCBs’ remit. |  | No change. |  | No Change
D6 | Technical feasibility | Fisheries removal inside or outside of a designated site is not considered viable within the Project’s timeframe. Within designated sites the MMO and EIFCA are already implementing byelaws to reduce fisheries pressures and any option outside of a designated site will need agreement from The Crown Estate. Note, outside of designated sites this measure will not be taken forward in the R4 Plan Level Compensation Plan. The evidence is similar to that for strategic compensation for site designation / extension. Therefore we advise that a new designation/designated site extension would be the preferred mechanism. |  | No change. |  | No Change
D7 | Agreed compensation level | The SNCBs are currently not in agreement with the Applicant on the presented WCS of habitat damage of Annex I Sandbanks within Dogger Bank SAC. The SNCBs advise that the points raise in Appendices B and C of our RR/WR are addressed. |  | No change. |  | No Change
D8 | Scale/extent of measure | The scale/extent of the measure has not been presented in detail and/or agreed with Natural England, JNCC or DEFRA. |  | No change. |  | No Change
D9 | Timing: Deliverable before impact | We do not believe that this measure will be available in the project timeframes. This is outside of the SNCB remit and the Applicant will need to liaise with TCE, DEFRA, MMO (and EIFCA depending on location). |  | No change. |  | No Change
D10 | Location of measure | The location of the measure has not been presented in detail and/or agreed with TCE, Natural England, JNCC or DEFRA. This is outside of the SNCB remit and the Applicant will need to liaise with TCE, DEFRA, MMO (and EIFCA depending on location). |  | No change. |  | No Change
D11 | Long term implementation & Success criteria/Ability to prove additionality | There is a requirement for changes in legislation for the delivery of this measure outside of designated sites and therefore until that is secured further long-term implementation remains unknown. This is outside of the SNCB remit and the Applicant will need to liaise with TCE, DEFRA, MMO (and EIFCA depending on location). |  | No change. |  | No Change
D12 | Suitable as sole measure for target species | We do not believe that this is currently suitable as a sole compensatory measure. But this may change post examination of this project. |  | No change. |  | No Change
Compensation Measure: Seagrass Habitat Creation/Restoration for Annex 1 sandbanks
D13 | Theoretical merit to deliver compensation. | Please see the published ‘Offshore Wind Leasing Round 4 Dogger Bank Strategic Compensation Plan (April 2024). In section 3.4.2 it is stated that “seagrass restoration is a lower preference measure compared to those supporting the same ecological function of the habitat being compensated for”. We advise the same is true for project level compensation and welcome this not being progressed by the Applicant at this time. |  | No change. |  | No Change
D14 | Technical feasibility | Please see section 3.4.3 of ‘Offshore Wind Leasing Round 4 Dogger Bank Strategic Compensation Plan’ (April 2024) where the Steering Group's significant concerns about the deliverability of seagrass restoration are summarised. Further, "The measure is retained in the DBSCP as an additional option which could potentially be employed if the Steering Group considered that it was necessary to supplement other measures, or potentially as an adaptive management response". This is also applicable to project level compensation. NE is in the process of drafting a paper on the current seagrass restoration projects. |  | No change. |  | No Change
D15 | Agreed compensation level | The SNCBs are not in agreement with the WCS of excluding compensation for damage to Annex I sandbank. Please see our comments in Appendices B and C. |  | No change. |  | No Change
D16 | Scale/extent of measure | The scale/extent of the measure has not been presented in detail and/or agreed with the SNCBs. Please see our comments in Appendices B and C. |  | No change. |  | No Change
D17 | Timing: Deliverable before impact | It is unclear if this measure can be delivered prior to the impacts occurring. |  | No change. |  | No Change
D18 | Location of measure | The location of the measure has not been presented in detail and/or agreed with the SNCBs. |  | No change. |  | No Change
D19 | Long term implementation & Success criteria/Ability to prove additionality | N/A |  | No change. |  | No Change
D20 | Suitable as sole measure for target species | This measure could only be considered as part of a package providing <10% of the required compensation and/or potential adaptive management for part delivered compensation. There would also be a requirement for the provision of subtidal seagrass, not intertidal. Therefore, we advise that other measures are progressed first. If other options are being progressed, then there is an expectation this compensation will not be taken forward. |  | No change. |  | No Change
Detailed comments Documents used: [APP-059] 6.2.3 Appendix 3 – Project Level Dogger Bank Compensation Plan [APP-061] 6.2.3.2 Outline Dogger Bank Compensation Implementation and Monitoring Plan [APP-062] 6.2.3.3 Annex C - Extension of the Dogger Bank SAC for HRA Derogation Compensation – Rationale and Evidence Base
D21 | D2 | The Dogger Bank Strategic Compensation Plan (DBSCP) and the project compensation do not align, with the exclusion of compensation requirements for damage to sandbanks. Benthic compensation measures for habitat disturbance of Annex I sandbanks from the project level compensation documents are omitted. We would fully expect the DCO to include compensation for both habitat loss and damage. Further consideration should be given to Plan Level compensation requirements as agreed by the Secretary of State for the Depart of Energy Security and Net Zero. |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change - Please see Deadline 2 Appendix 2.1.
D22 | D3 | If the Applicant is delivering Plan Level compensation, it is assumed that they do not also have to provide project level compensation, but this is not explicit here. It is also unclear why the Applicant has developed a project level compensation plan as DEFRA are moving ahead with work on new designations as a form of compensation following the agreement by DEFRA and SoS in Feb 2024. Ultimately it will be for DEFRA to determine the amount of compensation required, irrespective of what the Applicant has detailed in Section 5 Compensation Quantum. The SNCBs request legal clarification from the Applicant on this. |  | No change. |  | No Change
D23 | D4 | It is not clear to the SNCBs the role of the Steering Group going forwards if strategic compensation is progressed by DEFRA, as they will determine individual project ‘contribution’ as set out above. The SNCBs seeks further clarity from TCE on this matter. |  | No change. |  | No Change
D24 | D5 | We do not agree with the inclusion of any ‘as built’ figures as this is not legally secured. The SNCBs advise that figures included in consents are used to inform incombination assessments. |  | No change. |  | No Change
D25 | D6 | The SNCBs welcome the Plan Level and the Project Level compensation comparison. But highlight point D2 above with regard to aligning. |  | N/A
D26 | D7 | Compensation multiplier - this is not agreed or signed up to by the SNCBs and if site extension is progressed, it will be agreed as part of DEFRAs MPA Designation work. Therefore, it is our view that it is not necessary or appropriate to agree this as part of this Examination. |  | N/A
D27 | D8 | The Applicant has submitted information on a possible site extension to the Dogger Bank SAC. The powers to designate sit with DEFRA, and there is a work programme underway to identify potential locations. Therefore, it is the SNCBs view that it is neither necessary nor appropriate to discuss the merits of a particular designated site extension as part of the Dogger Bank South Examination. |  | N/A
D28 | D9 | Whilst any monitoring requirements may fall under the responsibility of NE or JNCC, this is not yet determined and/or agreed. However, we fully expect monitoring costs associated with compensation measures to be borne by those developers requiring the compensation through the MRF. The SNCBs request further clarity is provided from DEFRA when available. |  | No change. |  | No Change
D29 | D10 | Because the SNCBs believe that disturbance should also be included in any compensation requirements, we do not agree that the need to consider adaptive management finishes once construction has completed. The SNCBs request further clarity is provided from DEFRA when available. |  | No change. |  | No Change
D30 | D11 | It is the view of the SNCBs that adaptive management will be a consideration of DEFRA’s MPA designations programme. The SNCBs request further clarity is provided from DEFRA when available. |  | No change. |  | No Change
D31 | D12 | It is not clear if a Dogger Bank CIMP will be required in addition to the Round 4 Plan Level one or the Strategic compensation work. The SNCBs request further clarity is provided from DEFRA and TCE when available. |  | No change. |  | No Change

## E - Fish and Shellfish
Point | Point Number(s) from Appendix E [RR-039] | Taken from Natural England’s Relevant and Written Representations Dogger Bank South (East and West) Appendix E - Fish and Shellfish | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
E1 | E9 | There are three potential foundation options for the Electrical Switching Platform (ESP) in the Export Cable Corridor (ECC): jacket piles, monopiles, or a gravity-based structure. Clarity is needed on if gravity bases have been included in the worst-case scenario for operational habitat loss in the ECC. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change.
E2 | E10 | Underwater noise modelling for Atlantic herring for monopile and pin-pile installations uses a worst-case position of piling in the northern most point of the DBS West array. The worst-case position at the most south-westerly point of the DBS West array should be assessed as this may result in greater overlap with the High and Very High herring spawning potential habitat. |  | No Change. Please refer to our response to Action Point 35 from Issue Specific Hearing 2, outlined in Annex 2 of our Deadline 1 Cover Letter, for further detail. |  | No Change.
E3 | E11 | Further clarity is needed regarding simultaneous piling for monopiles for the in-isolation development scenario. For two monopiles installed simultaneously, the worst-case scenario for underwater noise and vibration impacts on sandeel would be two simultaneous monopile piling events in the DBS West array area. We advise that underwater noise models are provided for the worst-case scenario in each build out scenario. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change.
E4 | E12, E25 | The Applicant has provided underwater noise modelling for three pin-piles piled concurrently across the array areas and in the ECC, and has committed to no concurrent monopiling occurring across the arrays area with the ECC, clarity needed as it is unclear if two monopiles (one in DBS West, one in DBS East) and pin piling in the ECC could occur concurrently. Clarification is needed on the worst-case scenario for concurrent piling. In the case that monopiling in the array areas can occur concurrently with pin piling within the ECC, we advise the Applicant to provide underwater noise models and figures to assess impacts on fish receptors. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change.
E5 | E13 | The Applicant should utilise sandeel abundance data (such as the North Sea sandeel dredge survey) to support the assessment of impacts on localised sandeel populations (currently only habitat suitability heat maps and drop down video have been used). |  | Natural England will be providing comments on AS-105 Heat Mapping Report: Atlantic Herring and Sandeel (Revision 1) at Deadline 2. |  | Due to staff absence, Natural England will be providing detailed comments on Fish and Shellfish at Deadline 3.
E6 | E18 | EMF impacts from cables on sandeel and Atlantic herring have not been considered. We advise that the impacts of EMF on sandeel and herring high potential spawning habitat should be assessed. |  | Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | Due to staff absence, Natural England will be providing detailed comments on Fish and Shellfish at Deadline 3.
E7 | E19 | Habitat loss for sandeel and herring from UXO clearance have not been assessed as “specific surveys to identify potential locations of UXO would not be undertaken until the DCO for the Projects is granted”. A nominal assessment should be included as has been done for other receptors, e.g. marine mammals and benthic. |  | Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | Due to staff absence, Natural England will be providing detailed comments on Fish and Shellfish at Deadline 3.
E8 | E20 | Impacts from localised heating from the cables have been assessed in reference to water temperature increase, with no specific receptors identified as being impacted. Further assessment is required for localised heating of sediment and possible impacts to high/very high potential sandeel and herring spawning habitat. |  | Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | Due to staff absence, Natural England will be providing detailed comments on Fish and Shellfish at Deadline 3.
E9 | E21 | Clarity is needed on how localised impacts on high potential spawning habitat loss due to cable protection have been assessed for sandeel and Atlantic herring. |  | No Change |  | No Change
E10 | E22 | Include a robust assessment of the potential Worst-Case area of impact on benthic communities, particularly those highlighted as spawning areas along the ECC, and within Dogger Bank SAC sandbank feature, and the nature and scale of that impact, as a result of changes to physical and biological process following the placement of structures and cable/scour protection on the seabed (benthic ‘ecological halo effect’). |  | No Change. Natural England will be providing comment on this alongside our comments on Benthic and Intertidal Ecology at Deadline 2. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail.
E11 | E23 | The Applicant has modelled fish as both stationary and fleeing receptors for underwater noise thresholds. For all underwater noise modelling Natural England advise that fish are assessed as stationary receptors, our conclusions on impacts will therefore be based on the values provided that are in line with this advice. |  | No action needed.
E12 | E26 | 'soft start and ramp-up' approaches are not appropriate piling mitigation measures for impacts to fish. We therefore advise they are removed from the assessment and a more appropriate worst-case scenario is presented. |  | No Change. |  | No Change.
E13 | E28 | Evidence for habituation has been based on ship/trawl noise and seismic air guns. We advise that habituation should not be taken into account within the assessment without provision of more appropriate supporting evidence for impulsive piling noise. |  | No Change. |  | No Change.
E14 | E29, E30, E41 | We advise the Applicant commit to additional cable protection mitigation to reduce impacts to herring and sandeel spawning habitat (also mentioned in Risk and Issues Log Points B22 and C12). In addition, the Applicant should explore options to avoid placing cable protection within high – very high potential spawning habitat areas for herring and sandeel in the ECC and array areas. Currently, the full volume/length of cable protection applied for (20% of the ECC length, 10% for the inter-array cables) could be installed within these areas. A commitment should be made to avoid placing cable protection in these areas, or to only a certain proportion of the full volume being allowed in these areas. It should also be demonstrated through the Cable Burial Risk Assessment why the volumes applied for are needed and cannot be refined down further. We consider cable protection estimates should be based on an assessment of likely burial success. |  | No Change. |  | No Change.
E15 | E29, E31, E41 | A commitment should be made to remove all on and above seabed infrastructure within high - very high potential spawning habitat for sandeel and herring at the time of decommissioning, to prevent permanent impacts to spawning areas within the ECC and array areas. We advise this should be secured in the DCO. Without such a commitment, the worst-case scenario should assess the impacts to spawning grounds if assets are left permanently in situ. (Also refer to Risk and Issues Log Benthic Point C27) |  | No Change. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail.
E16 | E29, E32, E41 | The behavioural threshold (135 dB) modelled also overlaps the high and very high spawning habitat potential sites when piling in the array areas. As well as seasonal restriction in the ECC, a seasonal restriction should also be committed to for piling in the array areas. We defer to Cefas for further advice on timings of any such restriction. |  | No Change. |  | No Change.
E17 | E33 | Suitable references and evidence should be provided to support statements used in the impact assessment to conclude negligible or minor adverse impacts (i.e. that receptors can recover from impacts within 2-10 years). |  | No Change. We are reviewing the Applicant's response and will provide further comment at Deadline 2 as needed. |  | Due to staff absence, Natural England will be providing detailed comments on Fish and Shellfish at Deadline 3.
E18 | E34, E42 | Indirect effects on Humber Estuary SAC river lamprey and sea lamprey should be screened into the assessment. |  | Natural England maintain that river lamprey and sea lamprey should be screened into the assessment, however we acknowledge that the uncertainties and data poor environment would prevent a reliable assessment being made.
E19 | E35 | The worst-case piling event for migratory fish species is likely to be when piling takes place in the ECC. Underwater noise impacts from piling in the ECC should be fully assessed for Annex II migratory fish. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request.
E20 | E36 | The cumulative assessment for Dogger Bank SAC should be updated to include the total habitat loss within the SAC, including loss occurring within any overlap of the ECCs with the site. See also E19 and E22 in relation to the total habitat loss area to be assessed. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request.
E21 | E17, E38 | We disagree that if there were no significant impacts identified for potential fish prey species in the EIA assessment then there would be no significant impacts on ornithology and marine mammal receptors. NE consider that an understanding of the relative importance of the Project site as a foraging area, and potential for any impacts on localised prey abundance and distribution is critical in framing the predicted RIAA impacts that can be quantified. Further assessment is therefore needed to understand how more localised impacts (e.g localised depletion and/or reduced resilience of the wider stock) on fish and shellfish might influence prey availability for designated seabirds and mammals. The assessments should consider both direct and indirect impact pathways to sandeel and herring at a biologically relevant population scale, for both the construction and operation phases of the Projects. For herring this would be the Banks spawning component of the North Sea stock, and for sandeel the specific genetic population present in the Project area. See Annex E1 of REP-039 for futher guidance. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No change. We note the Applicant has contested the importance of the Dogger Bank sandbank system for prey availability and foraging species. Natural England disagrees with the justification provided and therefore maintains the advice provided in our Relevant Representation on this issue.
E22 | E40 | The Applicant has proposed pre- and post- construction habitat sampling to validate statements made regarding habitat suitability and recoverability for sandeel. We advise that longer-term sandeel monitoring would provide a more robust evidence base and would be beneficial in assessing the impacts of the Project on Dogger Bank sandeel populations (e.g. changes in sediment composition that could arise from dispersing drill spoil or settling of sediments suspended by cable laying). Once assessments have been updated, monitoring should be secured via the In-Principal Monitoring Plan to determine whether the residual impacts are as predicted. This could be via provision of a post-consent Sandeel Monitoring Plan, or the inclusion of sandeel specific objectives in the Benthic Monitoring Plan. |  | Natural England will be providing comments on the In Principle Monitoring Plan (IPMP) [APP-247] at Deadline 3, in order to take into account all of the updates from Change Request 1, the Defra Marine Noise Policy paper and updated ornithology assessments. |  | No change.
E23 | E43 | We acknowledge that herring and sandeel are not designated features and therefore derogations for direct impacts to these species would not be required. However, should impacts to these species contribute to an adverse effect on site integrity for designated predator species or Annex 1 sandbank feature, consideration of prey availability/spawning habitat may need to be incorporated into compensation measures for those sites. |  | No Change. No Action needed.

## F - Marine Mammals
Point | Point Number(s) from Appendix F [RR-039] | Taken from Natural England’s Relevant and Written Representations Dogger Bank South (East and West) Appendix F -Marine Mammals | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
F1 | F8 | The Applicant has committed to no concurrent monopile installation between the Offshore Export Cable Corridor (ECC) and the Project array areas; however, it is unclear if there could be concurrent pin pile installation in the ECC with monopile installation in the array areas. Clarity is needed on the WCS for concurrent piling between the ECC and array areas. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No change
F2 | F9 | Clarity is needed on how the worst case scenario (WCS) for the maximum number of piles to be installed concurrently in 24 hours across the two arrays will be secured in the dMLs for the separate Projects. |  | Natural England welcomes that a condition has been added to the DCO and will be providing comments at Deadline 2. |  | No Change. Natural England will provide further comment on this issue when our DCO comments are provided.
F3 | F10 | Clarity is needed on the WCS for simultaneous piling across the two arrays in a concurrent build out scenario, and how the dMLs for the separate Projects will secure this. |  | Natural England welcomes that a condition has been added to the DCO and will be providing comments at Deadline 2. |  | No Change.Natural England will provide further comment on this issue when our DCO comments are provided.
F4 | F16 | Permanent Threshold Shift (PTS) should be scoped into the Cumulative Effects Assessment. We do not agree that the mitigation outlined in the MMMP and ES is sufficient to minimise the risk of injury for all PTS impact ranges (see below). Further, due to the nature of marine mammals, mitigation cannot guarantee that no animals will be at risk of PTS. |  | No Change. |  | No Change. Natural England maintain our advice provided at Relevant Representations.
F5 | F17 | Natural England have reviewed the Underwater Noise Modelling Report and have no comments to make. However, we defer to Cefas for detailed comments on the methodology undertaken. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No change.
F6 | F11, F18, F32 | The maximum predicted PTS impact range for a single pile installation is 13 km for harbour porpoise and 26 km for minke whales. These distances are too large to effectively be mitigated by Acoustic Deterrent Devices (ADDs). The Applicant needs to demonstrate how the full PTS impact range will be mitigated to ensure no injury is caused to marine mammals. Alternatively, the PTS impact range needs to be reduced to ensure ADDs can effectively deter animals from the zone of injury within 80 minutes (maximum PTS range will need to be 7.2 km for harbour porpoise and 15.6 km for minke whale). This could be achieved my reducing the maximum hammer energy in the Project envelope, or by committing to the use of NAS to reduce the sound at source. |  | The Defra Marine Noise Policy paper was published on 21st January 2025. Natural England is reviewing this in terms of what it means for our advice on this project. We will provide further comment on the relevant Outline MMMP and Draft In Principle SIP updates at Deadline 2. |  | No change. See Appendix F2 of Natural England's Deadline 2 submission for further detail.
F7 | F20 | The predicted maximum injury zone for some UXO clearance events is larger than the area for many ADDs to effectively deter marine mammals from. Provide planned ADD durations to demonstrate that the maximum injury zone for UXO clearance can be mitigated. If this is not possible, additional mitigation or methods to reduce the sound at source should be investigated. |  | As part of the Defra Marine Noise Policy paper that was published on 21st January 2025, an updated Unexploded Ordnance (UXO) Joint Position Statement was published. Natural England is reviewing this in terms of what it means for our advice on this project. We will provide further comment on the relevant Outline MMMP and Draft In Principle SIP updates at Deadline 2. |  | No change. See Appendix F2 of Natural England's Deadline 2 submission for further detail.
F8 | F21 | Natural England supports increasing the Monitoring Area (MA) to ensure it is greater than the maximum predicted impact range for PTS. Consideration should be given to how this zone can be effectively monitored to ensure all marine mammals can be detected. This may require using more marine mammal observers (MMObs) and implementing stricter limits on workable weather conditions. The MMMP should be updated as needed. |  | The Defra Marine Noise Policy paper was published on 21st January 2025. Natural England is reviewing this in terms of what it means for our advice on this project. We will provide further comment on the relevant Outline MMMP and Draft In Principle SIP updates at Deadline 2. |  | No change. See Appendix F2 of Natural England's Deadline 2 submission for further detail.
F9 | F22 | The Mitigation area/zone needs to be monitored for a minimum of 30 minutes prior to the ADD activation to reduce the risk of injury to marine mammals from the ADD. This should be updated in the MMMP. |  | Natural England will provide comment on the Outline MMMP at Deadline 2. |  | Issue Resolved . Natural England has reviewed the updates made to [AS-101] Outline MMMP and are satisfied this issue has been addressed.
F10 | F23 | Piling should not commence (or recommence) in poor visibility or hours of darkness where Marine Mammal Observers (MMOb) cannot be used. There are limitations to Passive Acoustic Monitoring (PAM) so it should be used as well as, rather than instead of MMOb to optimise the ability to detect marine mammals and provide the best mitigation. Update Outline MMMP. |  | Natural England will provide comment on the Outline MMMP at Deadline 2. |  | No Change. Please refer to Appendix F2 regarding our comments on the updated Outline MMMP.
F11 | F24 | Natural England does not agree that the mitigated impacts of Permanent Threshold Shift (PTS) from piling are minor adverse - negligible for all marine mammals (See F5-F7). These conclusions are hinged on mitigation outlined in the MMMP which is not currently sufficient to fully mitigate the predicted PTS impacts. To ensure the impacts from underwater noise caused by piling are reduced for marine mammals we advise that the sound is reduced at source, this could be by modifying the design envelope (e.g. reducing the maximum hammer energy) or by using Noise Abatement Systems. |  | The Defra Marine Noise Policy paper was published on 21st January 2025. Natural England is reviewing this in terms of what it means for our advice on this project. We will provide further comment on the relevant Outline MMMP and Draft In Principle SIP updates at Deadline 2. |  | No change. See Appendix F2 of Natural England's Deadline 2 submission for further detail.
F12 | F25 | To reduce impact of piling in the Offshore Export Cable Corridor (OECC) on grey seals, we advise the Applicant commits to changing the design envelope (e.g. foundation bases with lower construction noise, reduced hammer energy) or the use of NAS to reduce the sound at source. |  | Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No change
F13 | F26 | The number of Harbour porpoise potentially disturbed during single piling at DBS East, DBS West and both projects together is high, with up to 12.53% of the North Sea Management Unit (MU) disturbed. We consider this should result in a Major Adverse impact score. The Applicant has concluded minor adverse based on the results of iPCoD modelling alone. The EIA assessment should be updated based on the highest predicted impact values, for all receptors and pathways (not using iPCoD). Where a significant impact cannot be ruled out, the mitigation hierarchy should be explored to reduce the potential impacts. |  | No Change. |  | No Change. Please refer to Appendix F2 for detailed comments regarding Interim Population Consequences of Disturbance (iPCoD) Modelling.
F14 | F27 | The number of grey seals disturbed during single piling at DBS East, DBS West and both projects together is high, with up to 30.62% of the South-East England MU disturbed. Using the number of animals potentially disturbed, the magnitude of impact is high, resulting in an impact score of moderate (significant). The EIA assessment should be updated based on the highest predicted impact values. Where a significant impact cannot be ruled out, the mitigation hierarchy should be explored to reduce the potential impacts. |  | No Change. |  | No Change. Please refer to Appendix F2 for detailed comments regarding Interim Population Consequences of Disturbance (iPCoD) Modelling.
F15 | F28 | Natural England supports the Applicant’s commitment to a joint industry project or site-based monitoring project, and requests to be consulted on future marine mammal monitoring plans. |  | No Action Required. Natural England will be providing comments on the In Principle Monitoring Plan (IPMP) [APP-247] at Deadline 3. |  | No Change.
F16 | F29 | We do not agree with the Applicant screening out PTS from the assessment on the basis of it being screened out from the Cumulative Effects Assessment. PTS should be screened into the HRA assessment. See comment F16. |  | No Change. |  | No Change.
F17 | F33, F34 | The conclusions for the RIAA illustrate that the noise thresholds for the SNS SAC would be significantly breached by the Project in combination with other noisy activities. Additional mitigation will be needed to avoid an Adverse Effect on Site Integrity (AEoI), however the current approach to implementing Site Integrity Plans (SIPs) for piling impacts to the Southern North Sea SAC does not allow sufficient time for mitigation methods, such as NAS, to be procured by the Applicant prior to construction should they be required. We strongly advise that the Applicant commit to the use of specific mitigation measures including noise abatement in the Outline SIP and MMMP at this stage. We advise that the effect of noise abatement systems in reducing noise impacts should be included in the submitted assessments. |  | The Defra Marine Noise Policy paper was published on 21st January 2025. Natural England is reviewing this in terms of what it means for our advice on this project. We will provide further comment on the relevant Outline MMMP and Draft In Principle SIP updates at Deadline 2. |  | No Change. Please refer to Appendix F2 for detailed comments regarding the Draft In Principle Site Integrity Plan for the Southern North Sea SAC.
F18 | F35 | Natural England cannot agree to the conclusion of no AEoI on grey seals in the Humber Estuary SAC. The Applicant’s assessment suggests that more than 9% of the Humber Estuary SAC grey seal population has the potential to be impacted by disturbance from piling (monopile or jacket pin pile) in the OECC. The assessment conclusions should be updated based on the highest predicted impact values. Where an AEoI cannot be ruled out, additional mitigation should be explored to avoid or reduce impacts. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No change.
F19 | F36 | Natural England cannot agree to the conclusion of no AEoI on grey seals in the Berwickshire North Northumberland Coast (BNNC) SAC. The Applicant’s assessment suggests that more than 5% (and therefore a significant number) of the BNNC SAC grey seal population could be disturbed by piling at DBS West and OECC in isolation and together using the dose response approach. The assessment conclusions should be updated based on the highest predicted impact valuesys. Where an AEoI cannot be ruled out, additional mitigation should be explored to avoid or reduce impacts. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No change.
F20 | F37 | Indirect Effects - We disagree that it can be concluded that there is no risk of AEoI to marine mammal SAC features as a result of impacts on prey species, solely due to impacts being ruled out at EIA scale. Consideration has also only been given to temporary construction impacts on prey in the RIAA, rather than the indirect effects of permanent spawning habitat loss that will also occur. Please see Appendix E for our detailed comments on the indirect effects assessment. |  | No Change. |  | No Change. We note the Applicant has contested the importance of the Dogger Bank sandbank system for prey availability and foraging species. Natural England disagrees with the justification provided and therefore maintains the advice provided in our Relevant Representation on this issue.
F21 | New |  |  |  |  | Whilst Natural England welcomes the Applicant updating the DCO to include the Maximum Hammer Energy, we advise that within Section 3.1.5 of the Outline MMMP [AS-101] it is clearly stated what the Applicant’s intentions are regarding the commencing hammer energy in addition to the percentage of the maximum hammer energy this represents.
F22 | New |  |  |  |  | Natural England welcomes the Applicant's Scheduling of UXO clearance with other projects (Section 9.6 of Draft In Principle Site Integrity Plan) as a useful tool for minimising the area of disturbance on a particular day; however this method should be in addition to noise reducing technology as outlined in Defra’s recently published Marine Noise Package. Natural England will provide further comment following the Applicant's review of the Defra Noise Package documents and updated assessment and mitigation measures.

## G - Offshore Ornithology
Point | Point Number(s) from Appendix G [RR-039] | Taken from Natural England’s Relevant and Written Representations Dogger Bank South (East and West) Appendix G - Offshore Ornithology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 1 | Consultation, actions, progression | RAG February 27 submission | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
G1 | G11 | We do not support the approach taken by the Applicant to combine the impacts of the two arrays for several aspects of the assessment (e.g. abundance estimates and displacement) as it underrepresents the impacts. The impacts for the arrays should be calculated separately for each array and summed to represent the worst-case scenario. |  |  |  | Issue resolved. The Applicant has updated abundance estimates for the arrays combined in line with SNCB advice.
G2 | G12 | The baseline surveys undertaken are broadly appropriate, however there are outstanding issues with how the data has been characterised. |  |  |  | Issue resolved. See G3.
G3 | G13 | There is considerable variation in the abundance and density estimates between survey years for several species, however no assessment of between-year variation has been undertaken and no additional datasets have been considered when characterising the baseline. We advise that the Applicant provides an assessment of between-year variation in their baseline data with consideration of additional datasets, such as baseline data from other nearby OWF projects and modelled datasets, to characterise and assess the representativeness of the baseline. This is particularly important given that the baseline survey period includes months before and during the recent highly pathogenic avian influenza (HPAI) outbreaks. |  |  |  | Issue resolved. We are broadly satisfied that the baseline has been satisfactorily characterised.
G4 | G14 | The Applicant has not used the most recent seabird census or latest research on impacts of HPAI in there assessment (e.g. Tremlett et al 2024). The Applicant should consider all relevant evidence on seabird population trends when assessing impacts and present an updated assessment that reflects this. |  |  |  | Issue largely resolved. Natural England welcomes that the additional evidence has now been included, however we do not agree with the current interpretation of the trends in the assessment. Please see Appendix G2, Table 2 for further detail.
G5 | G11, G15 | We do not support the approach taken by the Applicant to combine the monthly abundance estimates for the two arrays. As the 2km buffers for the two arrays do not overlap, we advise that the monthly abundance estimates for the arrays combined should be calculated as the sum of the monthly abundance estimates for each separate array. |  |  |  | Issue resolved. The Applicant has updated abundance estimates for the arrays combined in line with SNCB advice.
G6 | G11, G16 | Seasonal peak abundances for the arrays combined should be calculated as the sum of the highest value from each each array, even if these occur in different months. The current approach will cause the impacts calculated in the displacement assessment to be underestimated (see G21). |  |  |  | Issue resolved. The Applicant has updated abundance estimates for the arrays combined in line with SNCB advice.
G7 | G17 | There appear to be several inconsistencies in the abundance estimates presented for razorbill. All razorbill monthly and seasonal mean peak abundance estimates for both arrays should be checked to ensure accuracy and consistency, and that the correct abundance estimates have been used for displacement assessments throughout. If necessary, updates to the assessment should be provided. |  |  |  | Issue resolved. The Applicant has confirmed that the numbers presented are correct and that no updates are needed.
G8 | G18 | The Applicant has not included an assessment of displacement impacts for the decommissioning phase. We advise that displacement impacts at decommissioning are included for all species in the displacement assessment and calculated as per construction displacement impacts. |  |  |  | No change. Natural England advise that it would be beneficial for decommissioning impacts are to be explicitly quantified in the assessment as for construction impacts.
G9 | G19 | The Applicant has not used Natural England’s advised baseline mortality rates or EIA reference populations for several species. An updated assessment should be provided using the SNCB advised EIA reference populations and baseline mortality rates to calculate annual background mortality for all species, with impacts assessed against these annual background mortality rates. |  |  |  | Issue Resolved. Natural England welcome that the Applicant has updated EIA baseline mortality rates and reference populations to reflect our advice.
G10 | G20 | The Applicant has used mean maximum foraging ranges when determining connectivity of the projects to seabird breeding colonies instead of the recommended mean maximum foraging ranges + 1SD. We advise that mean maximum foraging range plus 1SD (Woodward et al., 2019) is used to establish connectivity between the projects and seabird breeding colonies. |  |  |  | Natural England have reviewed the Applicant's response, and whilst we maintain that it would be best practice for the mean max foraging range +1SD to be used in the EIA assessment, we agree that it has been used correctly for the HRA assessment and would not materially impact the EIA conclusions. We will not pursue this further.
G11 | G21 | The displacement assessment impacts for the arrays combined do not reflect the sum of the displacement impacts of the arrays summed, due to the method used to calculate seasonal peak abundance for the arrays combined (see G16). We advise that displacement impacts are re-calculated separately for each array and then summed. |  |  |  | Issue resolved. The Applicant has updated their displacement assessment for the arrays combined in line with SNCB advice.
G12 | G22 | The spatial distribution figures show that high densities of auks (particularly guillemot and razorbill) were recorded in the area between the two arrays, but outside the 2km buffer. We consider it is likely that birds in this area will be vulnerable to cumulative displacement impacts from the arrays on either side. We advise that an assessment of cumulative displacement impacts on auks between the arrays is provided. |  |  |  | No Change. Natural England maintain our previous advice that further assessment is needed of cumulative displacement impacts on auks between the arrays. Please refer to Appendix G2, Table 2 for further detail.
G13 | G23 | The Applicant has not followed the SNCB Best Practice Guidance for calculating construction displacement impacts, which is to halve the operational impacts. We advise that the construction displacement assessment is updated. |  |  |  | Issue resolved. Natural England have reviewed the Applicant's response and are satisfied with the construction displacement assessment provided.
G14 | G24 | We do not agree with the approach taken for seasonality when assessing impacts on guillemot. We advise that the assessment is updated with August and September treated as a separate ‘chick rearing and moult’ season, with seasonal mean peaks and impacts calculated accordingly. |  |  |  | Issue resolved. This has been addressed in the Applicant's updated assessment.
G15 | G25 | Whilst the Applicant has presented the results of the displacement assessment for auks using Natural England’s advised ranges for displacement and mortality rates, they have consistently stated that these advised rates are not appropriate or evidence-based and have not considered impacts calculated using these rates in their conclusions. The forthcoming Offshore Renewables Joint Industry Programme (ORJIP) project ‘Improving understanding of distributional change for relevant seabird species (ImpUDis)’ will provide a comprehensive overview of auk displacement. Until this project returns evidence which can inform displacement rates of auks, Natural England continue to advise the use of the displacement matrix set out in our Best Practice Guidance and will base our conclusions on impacts calculated using these rates. |  |  |  | No Change. Natural England maintain the advice provided in our Relevant Representation. Please see Appendix G2, Table 2 for further detail.
G16 | G26 | The Applicant has not followed the SNCB advised approach for assessing gannet collision risk. We advise that gannet collision is assessed using an avoidance rate of 99.3%, along with a range of macro-avoidance rates between 65-85%. |  |  |  | Issue Resolved. The Applicant has updated their gannet collision risk assessment in accordance with Natural England’s advice.
G17 | G27 | We advise that disturbance and displacement impacts are screened into the cumulative assessment for Red-throated Diver and relevant mitigation measures identified e.g. use of existing shipping lanes until beyond 2km of the SPA. |  |  |  | Natural England welcome that a cumulative assessment has been provided for impacts on red-throated diver, however we advise that clarification is needed on how the values presented have been arrived at. See Appendix G2, Table 2 for further detail.
G18 | G28, G63 | Further consideration should be given to potential mitigation measures to reduce impacts on bird features, such as array reductions, changes to design and layout of arrays, or increasing the hub height of turbines. Hotspot modelling of seabird densities and distributions in the study area may help to identify areas where impacts are particularly high. |  |  |  | No Change. Natural England continue to advise that further consideration is given to potential mitigation measures to reduce impacts on seabird features, such as array reductions, changes to design and layout of arrays, or increasing the hub height of turbines. See Appendix G2, Table 2 for further detail.
G19 | G29 | We cannot agree with the EIA conclusions presented due to there being outstanding concerns with several aspects of the assessment, including: -baseline mortality rates and EIA reference populations used (G19) -guillemot seasonality (G24) -gannet collision risk (G26) -approach taken to combining the impacts of the two arrays (G11) We advise that updated assessments are provided in line with SNCB Best Practice Guidance. |  |  |  | Natural England cannot agree with the EIA conclusions presented due to there being outstanding concerns with several aspects of the assessment, including: •Discrepancies in cumulative impact figures (G54) •Lack of PVAs to assess cumulative impacts resulting in increases in background mortality rates of more than 1% (G56) •Lack of assessment of cumulative displacement impacts on auks between the arrays. (G12)
G20 | G31 | Further detail and clarity is needed on the foraging ranges and SPA populations used to calculate breeding season apportioning proportions. We advise that the more up-to-date and contemporaneous SPA populations from Seabirds Count data (Burnell et al 2023) should be used to determine proportions for apportioning during the breeding season, rather than SPA citation populations, unless more recent counts are available. |  |  |  | Issue Resolved. The Applicant has updated their apportioning of guillemot and razorbill impacts to FFC SPA in line with SNCB advice.
G21 | G32 | The adult baseline mortality for FFC SPA gannet should be recalculated using the 8.1% mortality rate from Horswill and Robinson (2015), and the rest of the assessment of impacts on this population adjusted accordingly. |  |  |  | Issue largely resolved. The Applicant has updated the adult baseline mortality rates for gannet, kittiwake, and razorbill to reflect our advice. However, we disagree with the Applicant’s characterisation of these trends in the RIAA. Please see Appendix G2, Table 2 for further detail.
G22 | G33 | The adult baseline mortality for FFC SPA kittiwake should be recalculated using the Clarkson et al (2022) population estimate, and the rest of the assessment of impacts on this population adjusted accordingly. |  |  |  | Issue largely resolved. The Applicant has updated the adult baseline mortality rates for gannet, kittiwake, and razorbill to reflect our advice. However, we disagree with the Applicant’s characterisation of these trends in the RIAA. Please see Appendix G2, Table 2 for further detail.
G23 | G34 | The adult baseline mortality and breeding season apportioning for FFC SPA puffin should be recalculated using the Clarkson et al (2022) count, and the rest of the assessment of impacts on this population adjusted accordingly. |  |  |  | Issue largely resolved. Natural England welcomes the updated calculation of adult baseline mortality for puffin at FFC SPA and note that, while the Applicant has still not followed Natural England’s advice, the discrepancy is unlikely to lead to a material difference in the impact values.
G24 | G35 | The adult baseline mortality for FFC SPA razorbill should be recalcuated using the Clarkson et al (2022) count, and the rest of the assessment of impacts on this population adjusted accordingly. |  |  |  | Issue largely resolved. The Applicant has updated the adult baseline mortality rates for gannet, kittiwake, and razorbill to reflect our advice. However, we disagree with the Applicant’s characterisation of these trends in the RIAA. Please see Appendix G2, Table 2 for further detail.
G25 | G36 | We welcome that the Applicant has provided impact values with 100% adult apportioning to SPA colonies in line with SNCB advice, alongside their own approach using stable age structure. We disagree with the use of a theoretical generalised stable age structure to apportion impacts to adults from SPA colonies as it is unlikely to represent actual proportions of adults present and may lead to underestimation of impacts. Our conclusions on impacts will therefore be based on the values provided in line with SNCB advice. |  |  |  | To note. No further action needed.
G26 | G37 | The results of displacement assessments for auks using Natural England’s advised range of displacement and mortality rates should be used to determine SPA features for Population Viability Analysis (PVA), and when assessing potential for AEoI at SPAs. |  |  |  | See G43.
G27 | G38 | We advise that for apportioning of guillemot impacts to FFC SPA, August and September be treated as a separate ‘chick rearing and moult’ season, with seasonal mean peaks and impacts calculated accordingly. |  |  |  | Issue resolved. This has been addressed in the Applicant's updated assessment.
G28 | G39 | Clarification is needed on the guillemot apportioning method. Natural England advice is that adult proportions of guillemot during August and September be calculated according to the published productivity data for guillemot at FFC SPA during the years that the baseline surveys were undertaken (Cope et al 2021, Cope et al 2022). |  |  |  | Issue resolved. This has been addressed in the Applicant's updated assessment.
G29 | G40 | We do not agree with the use of the Biologically Defined Minimum Population Scale (BDMPS) method for apportioning razorbill impacts to FFC SPA in the post-breeding migration season. Based on the published productivity data for razorbill at FFC SPA during the years that the baseline surveys were undertaken (Cope et al 2021, Cope et al 2022), and allowing for the possibility of some degree of dilution by adults from other colonies to North, we advise that 69.93% of razorbill are apportioned as breeding adults at FFC SPA during the post-breeding migration season. |  |  |  | Issue resolved. This has been addressed in the Applicant's updated assessment.
G30 | G41 | We advise that the Applicant check that the correct minimum distance between FFC SPA and the arrays has been applied when considering apportioning rates to FFC SPA for kittiwake. |  |  |  | Issue resolved. This has been addressed in the Applicant's updated assessment.
G31 | G42 | The combined impacts of collision and displacement on FFC SPA gannet in the Applicant’s assessment for the arrays combined results in an increase in mortality rate of 0.9%. If when calculated according to Natural England’s advised approach the impacts of the arrays combined on FFC SPA gannet exceed the 1% threshold, then PVA should be undertaken for impacts of the projects alone. |  |  |  | Issue Resolved. Natural England welcomes that the Applicant has undertaken PVA to assess the impacts of the projects alone on FFC SPA gannet.
G32 | G43, G44 | We advise that PVAs are carried out for the impacts of the projects alone (i.e. DBS East and West combined) on kittiwake, guillemot and razorbill at FFC SPA, as the 1% mortality rate threshold is exceeded when assessments are conducted in line with SNCB advice. |  |  |  | Issue Progressed. Natural England welcomes that the Applicant has undertaken PVAs to assess the impacts of the projects alone on guillemot, kittiwake, and gannet at FFC SPA. The advice provided in our Relevant Representations still applies to that of razorbill at FFC SPA, which is yet to be provided. Please see Appendix G2, Table 2 for further detail.
G33 | G45 | There is a discrepancy between the annual operational displacement impacts of the arrays combined on FFC SPA gannet presented in Table 9.12 (13.17) compared to the text in paragraph 109 (12.5). We advise this is checked and the appropriate values are used to calculate the impacts of displacement and collision combined. |  |  |  | Issue resolved. The Applicant has confirmed this was an error and the correct values have been used in the assessment.
G34 | G47 | The descriptions of red-throated diver densities in the area of the Greater Wash SPA crossed by the cable corridor given in Chapter 7.12 and in Chapter 6.1 do not correspond. These should be checked and assessments updated as needed. |  |  |  | Issue resolved. This has been addressed in the Applicant's updated assessment.
G35 | G48 | The assessment of impacts on red-throated diver in the Greater Wash SPA does not consider impacts of the reduction in habitat resulting from disturbance/displacement during cable installation. We advise that the implications of cable installation on extent of available habitat for red-throated diver in the Greater Wash SPA is assessed and robust mitigation brought forward. |  |  |  | Natural England have reviewed the Applicant's response and agree that in this instance habitat reduction does not need to be assessed separately to disturbance/displacement for the cable installation works. However, please see G50 (G64)and Appendix G2 for for further comment on mitigation for red-throated diver disturbance.
G36 | G49 | The initial population sizes used in the PVA for kittiwake and razorbill at FFC SPA are 91,008 and 30,673 respectively. We advise that the appropriate population sizes to use are the 2022 count figures of 89,148 (kittiwake) and 61,345 (razorbill) (Clarkson et al 202210). The PVAs for kittiwake and razorbill at FFC SPA should be re-run using the appropriate initial population sizes (Clarkson et al 2022). |  |  |  | No Change. Natural England maintain our advice that the most recent population estimate should be used as the starting population for PVAs run for this population. See G57 and Appendix G2, Table 2 for further detail.
G37 | G50 | In-combination assessments have not been carried out for a number of SPA features. We advise that it would be best practice for the Applicant carry out in-combination assessments for all SPA features that have been screened in for assessment. As a minimum, we consider that in-combination assessments should be carried out for all species that meet the 1% baseline mortality threshold (calculated according to SNCB guidance), specifically guillemot at Farne Islands SPA, and Red-throated diver at the Greater Wash SPA. We consider there would also be merit in in-combination assessments being carried out for puffins at Farne Islands SPA and FFC SPA. |  |  |  | Issue progressed. The Applicant has provided in-combination assessments for guillemot and puffin at the Farne Islands SPA, however, we have outstanding concerns with some aspects of the assessment methodology. The Applicant has also included an in-combination assessment for Red-Throated Diver in the Greater Wash SPA. Whilst we do not fully agree with the approach taken for the RTD assessment (lack of consideration of impacts from other projects), due to the low predicted impacts we do not consider it would materially change our advice. Please see Appendix G2, Table 2 for further detail.
G38 | G51 | The impacts of several relevant Tier 4 projects have been left out of the in-combination assessments, including Outer Dowsing, Five Estuaries and North Falls offshore wind farms (OWF). Dogger Bank D OWF should also be included as a Tier 6 project. The in-combination assessment should be updated to include all relevant projects. |  |  |  | Issue progressed. We welcome that the Applicant has included all relevant Tier 4 projects in their in-combination assessment, however we advise the Applicant collaborates with other Round 4 developers to agree on how updated impact values (based on SNCB advice) can be efficiently incorporated as the Examinations of these projects progress, and that the Applicant updates the Examination at an appropriate juncture.
G39 | G52 | The Applicant has excluded projects for which kittiwake compensation measures are required (Hornsea Three, Norfolk Boreas, Norfolk Vanguard, East Anglia Two, East Anglia One North, Hornsea Four, SEP&DEP) from their in-combination assessment. The Applicant should present in-combination assessments that both include and exclude compensated-for projects, for FFC SPA kittiwake. |  |  |  | Issue Resolved. The Applicant has presented in-combination totals both including and excluding compensated-for projects.
G40 | G53 | We do not support Hornsea 4 guillemot impacts being excluded from in-combination totals, as a high degree of uncertainty remains regarding the likely effectiveness of available measures to fully compensate for their impacts. We advise that in-combination totals should be presented both with and without the impacts of compensated-for projects due to the current uncertainty regarding the effectiveness of compensatory measures for auks. |  |  |  | Issue Resolved. The Applicant has presented in-combination totals both including and excluding compensated-for projects.
G41 | G54 | The in-combination totals calculated for impacts on kittiwake, guillemot, razorbill and gannet at FFC SPA do not appear to reflect the combined impacts of the arrays with other relevant projects. We note that the most recent agreed in-combination totals are for SEP & DEP. We advise that the in-combination totals for impacts on kittiwake, guillemot, razorbill and gannet at FFC SPA be recalculated, taking into account the impacts of all relevant projects (see G51&52), the DEP&SEP values, and any updated assessments resulting from advice within this Representation. |  |  |  | Issue progressed. Please refer to R&I points G58 and G59 for species specific comments.
G42 | G55 | For the in-combination assessment of displacement impacts, the Applicant has presented apportioned abundance estimates for other projects, and then presented minimum and maximum displacement impacts in the text. The full methods and displacement matrices for these assessments have not been provided, and it is therefore not possible for us to evaluate the methods or the potential range of predicted impacts. We advise that the Applicant presents the details of the in-combination displacement assessment in full to allow the methods used and full range of predicted impacts to be evaluated. |  |  |  | No change. We advise the Applicant presents in-combination totals for displacement-affected species according to the agreed impact values for each project (as for in-combination collision assessment), rather than abundance estimates. Please see Appendix G2, Table 2 for further detail.
G43 | G56 | While Natural England appreciate the Applicant presenting PVA results for guillemot and razorbill considering both ends of Natural England’s advised range for displacement and mortality rates (i.e. from 30% displacement and 1% mortality to 70% displacement and 10% mortality) as well as Natural England’s advised adult apportioning rates, we note that only a limited number of results are presented from within this range. We advise the Applicant to present the results of the full range of displacement impacts on guillemot and razorbill in the PVA modelling. |  |  |  | No Change. Natural England advise that the PVAs run to assess the predicted impacts of the projects on guillemot and razorbill populations encompass the full range of Natural England’s advised displacement and mortality. Please see Appendix G2, Table 2 for further detail.
G44 | G57 | Interpretation of PVA results: Counterfactual of Population Size When interpreting results of PVAs, assessments should focus on both the counterfactual of population growth rate (CGR) and counterfactual of population size (CPS) to quantify the relative changes in population response to anthropogenic impacts, as they have been shown to be the least sensitive metrics to misspecification of the population trend and demographic rates used in the PVA model. Our integrity judgements will take into account both the CPS and CGR metrics to quantify the relative changes in population response to impacts. |  |  |  | No change. To note.
G45 | G58 | Interpretation of PVA results: use of mean peak abundance estimates In the absence of more robust empirical evidence on within-year and between-year variations in abundance, and on turnover rates, Natural England continue to advise that the use of seasonal mean peak abundance estimates is necessary and appropriate. |  |  |  | No change. We maintain our previous advice.
G46 | G59 | Interpretation of PVA results: characterisation of 1% mortality rate Natural England disagree with the Applicant’s statement that a 1% mortality rate for the displacement assessment on gannet (and referenced for other species) is “not based on any scientific evidence”. We refer the Applicant to our comments on the characterisation of NE advice in G25. |  |  |  | No change. We maintain our previous advice.
G47 | G60 | Interpretation of PVA results: use of as built parameters We do not consider it appropriate to reduce impact estimates by considering as-built parameters unless those parameters are legally secured. Speculation of impacts from ‘as built’ scenarios in in-combination/cumulative impact assessments are of little value unless legal agreements are put in place to ensure existing projects will not expand further. Without such agreements, there is no option other than to use impacts from consented designs in in-combination and cumulative assessments. |  |  |  | No change. Natural England note that we are actively engaged with industry in considering ways that ‘as-built’ parameters can be used within assessments. However, at present, we are unable to consider appropriate the use of as-built parameters in cumulative and in-combination assessments unless these parameters can be legally secured.
G48 | G61 | Interpretation of PVA results: PVAs run as “closed populations” There is currently an absence of robust empirical evidence on the levels of immigration and emigration affecting the relevant seabird populations. In the absence of such evidence, it is impossible to construct population models that reliably represent metapopulation dynamics, and incorporating unproven assumptions about immigration and emigration into population models has the potential to underestimate development impacts on seabird populations. No assumptions can be made about unquantified resilience in wider populations, particularly given the many pressures acting on seabird populations throughout the region. |  |  |  | No change. We maintain our previous advice.
G49 | G62 | Interpretation of PVA results for FFC SPA gannet, kittiwake, guillemot and razorbill In the Applicant’s interpretation of the PVA results for in-combination impacts on gannet, kittiwake, guillemot and razorbill at FFC SPA, they cite recent population growth at the SPA as a reason for concluding no AEoI is likely. Whilst we do not dispute the evidence of population growth at the colony in past years, we do not consider it appropriate to assume the same growth rate will continue over the next 30 years. It is highly likely that the populations will experience density-dependent mechanisms over the lifetime of the Project, and there are uncertainties about the long-term population impacts of HPAI and a wide range of other environmental pressures. We note that the Applicant has acknowledged the importance of considering density dependence and other pressures including HPAI and climate change elsewhere in the Application, but they have not considered these in their interpretation of the PVA results. Further, recent surveys have shown that UK gannet, kittiwake and guillemot populations declined by 25%, 18% and 20% respectively between the results of the last seabird census which covered the period between 2015 and 2021 (Burnell et al 20234), and the summer of 2023 (Tremlett et al 20245). Natural England advise that the Applicant considers realistic assessments of current and future population trends, considering all relevant evidence, when interpreting the results of updated PVAs. |  |  |  | No change. Natural England advise that the Applicant consider realistic assessments of current and future seabird population trends, considering all relevant evidence, when assessing the significance of the predicted impacts of the projects. Please see Appendix G2, Table 2 for further detail.
G50 | G64 | We advise that careful consideration should be given to avoiding or restricting cable installation works within 2km of the Greater Wash SPA during the over-wintering period (1st November to 31st March inclusive) to avoid adverse effects. |  |  |  | No change. Please see Appendix G2, Table 2 for further detail.
G51 | G65 | We acknowledge the right of the Applicant to submit an assessment following their chosen methods, however in such circumstances an assessment should also be provided in line with SNCB advice. We are unable to comment on the assessment conclusions until such an assessment is provided. |  |  |  | Issue progressed. Natural England acknowledge and welcome the significant efforts that have been made to provide assessment values in line with SNCB advice. However, due to outstanding concerns with respect to in-combination assessments and PVAs, we remain unable to comment on the conclusions presented at this time. Please refer to Appendix G2, Table 2 for further detail.
G52 | G66 | Natural England disagree that it can be concluded that there is no risk of AEoI to ornithology SPA features as a result of impacts on prey species, solely due to impacts being ruled out at EIA scale. Consideration has also only been given to temporary construction impacts on prey in the RIAA, rather than the indirect effects of permanent spawning habitat loss that will also occur. Please see Appendix E for our detailed comments on the indirect effects assessment. |  |  |  | No change. We note the Applicant has contested the importance of the Dogger Bank sandbank system for prey availability and foraging species. Natural England disagrees with the justification provided and therefore maintains the advice provided in our Relevant Representation on this issue.
G53 | NEW | NEW ISSUE |  |  |  | Presentation of displacement matrices including upper and lower confidence intervals Whilst the Applicant has updated their displacement assessment for the arrays combined the relevant tables in ES Appendix 12-12 [APP-115] have not been updated. Natural England advise that ES Appendix 12-12 [APP-115] is updated to reflect the updated displacement assessment figures and that all displacement matrices are presented (for both EIA and the RIAA), including for the upper and lower confidence intervals. Please see Appendix G2, Table 2 for further detail.
G54 | NEW | NEW ISSUE |  |  |  | Cumulative and in-combination totals Cumulative impact totals presented in 7.12 ES Chapter 12 [AS-058] and the unapportioned in-combination totals presented in 6.1 RIAA HRA Part 4 of 4 – Marine Ornithological Features (Revision 3) [AS-086] do not always match. We advise the Applicant to check the cumulative and in-combination totals for all species. Please see Appendix G2, Table 2 for further detail.
G55 | NEW | NEW ISSUE |  |  |  | Great black-backed gull and lesser black-backed gull cumulative totals The cumulative collision totals presented for great black-backed gull and lesser black-backed gull are lower than the cumulative totals presented at SEP & DEP, despite additional impacts from several projects since the SEP&DEP examination, including those of Dogger Bank South. Natural England advise that the Applicant check the cumulative collision impacts for these species. Please see Appendix G2, Table 2 for further detail.
G56 | NEW | NEW ISSUE |  |  |  | Lack of PVAs for cumulative impact assessments The Applicant has not provided PVAs for cumulative EIA impacts, despite several of these amounting to increases in background mortality rates of over 1%, when assessed according to Natural England’s advice. Natural England advises that the Applicant run PVAs to assess projected impacts on populations wherever cumulative impacts lead to increases in background mortality rate of greater than 1% when calculated according to Natural England’s advice. Please see Appendix G2, Table 2 for further detail.
G57 | NEW | NEW ISSUE |  |  |  | Presentation of PVA inputs and outputs Natural England advise that the updated inputs and outputs for all PVA scenarios undertaken for the assessment are clearly presented in Appendix 7.12.12.13 to reflect the updated impact values in the assessment and the PVA scenarios and results presented in the RIAA. This should include presenting the log files for all PVA scenarios undertaken, in order to enable assessment of the specification and paramaterisation of the models. This applies to PVAs presented for both the projects alone and in-combination with other projects. Please see Appendix G2, Table 2 for further detail.
G58 | NEW | NEW ISSUE |  |  |  | In-combination totals for kittiwake at FFC SPA In-combination totals for impacts on kittiwake at FFC SPA appear to be lower than we would expect, given the totals presented during the SEP&DEP Examination. Natural England advise that the Applicant check in-combination figures for kittiwake at FFC SPA and correct these if necessary. Please see Appendix G2, Table 2 for further detail.
G59 | NEW | NEW ISSUE |  |  |  | In-combination totals for guillemot and razorbill at FFC SPA Natural England advise the Applicant to refer to the advice provided to DEP & SEP on the appropriate displacement and mortality rates to be used for the impacts of Hornsea 4 on guillemot and razorbill at FFC SPA, and update their in-combination totals accordingly. Natural England recommend that the impacts of these updated figures are then assessed by PVA. Please see Appendix G2, Table 2 for further detail.
G60 | NEW | NEW ISSUE |  |  |  | PVA results The results of several of the PVAs undertaken by the Applicant are not as we would expect. Natural England advise that the Applicant check the results of all PVA scenarios run for the assessment, and ensure that the inputs and outputs of all scenarios are clearly presented, along with log files. Please see Appendix G2. Table 2 and G57 for further detail.

## H- Offshore Ornithology Comp
Point | Point Number(s) from Appendix H [RR-039] | Taken from Natural England’s Relevant and Written Representations Dogger Bank South (East and West) Appendix H - Offshore Ornithology Compensation | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 1 | Consultation, actions, progression | RAG February 28 submission | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Issue Resolved
Kittiwake Compensation Document used: [APP-052] 6.2.1 Apendix 1 - Project Level Kittiwake Compensation Plan
H1 | H1 | Natural England recognises the current uncertainty around the implementation of the Kittiwake Strategic Compensation Plan (KSCP) and welcomes the provision of project-led kittiwake compensation measures, the alignment of these with the measures and approach outlined in the KSCP, and the commitment to securing these measures as a requirement of the DCO.
H2 | H2 | The Applicant has omitted the section of the KSCP which states: ‘11.1.2 The construction of two offshore SANS was preferred by the Steering Group to provide mitigation of risk of failure at one offshore SANS. Within this there was an ecological preference that these were in different locations, however it was agreed by the Steering Group that when considering the balance of economics that the two structures near to each other was perfectly acceptable.’ Further, we also highlight that only the first two options listed by the Applicant were supported by the SNCBs (Natural England and JNCC) in the Kittiwake Steering Group. This should be considered by the Applicant in the development of their project-led compensation proposals. |  |  |  | Issue Resolved. The text has been updated in Revision 2 of the Kittiwake Compensation Plan (KCP) [PDB-003].
H3 | H3 | Natural England do not agree with the predicted impact values and compenstion levels presented. We advise that the KCP is updated following any reassessments undertaken in response to the advice provided in Appendix G. Compensation metrics should be presented in line with both the Applicant’s preferred method and SNCB guidance. |  |  |  | Issue progressed. Natural England acknowledge and welcome the significant efforts that have been made to provide assessment values in line with SNCB advice. However, due to outstanding concerns with respect to in-combination assessments and PVAs, we remain unable to comment on the conclusions and impact values presented at this time. Please see Appendix G2 for further detail.
H4 | H4 | Until such time as evidence is provided to support appropriate apportioning rates of kittiwake to offshore colonies for the Dogger Bank South projects, we continue to advise that the colony apportioning method followed in the impact assessment is appropriately precautionary. |  |  |  | The Applicant has confirmed that apportioning rates have not been reduced on the basis of offshore colonies, however offshore colonies are still suggested to be an inherent source of precaution in the apportining of 100% of adult birds to FFC SPA in the KCP. We note that Dogger Bank South is not in as prominent an area for oil and gas infrastructure compared to other projects, and therefore presence of birds from offshore colonies cannot be assumed.
H5 | H5 | The impacts currently predicted for the Projects alone make DBS the highest impacting project on FFC SPA kittiwake to date, and would likely result in an adverse effect on site integrity (AEoI) alone. Further consideration needs to be given to reducing the Projects’ impacts, prior to the need for compensation. This could include reducing the overall array size, removing hotspots, concentrating turbines in cold spots, and/or raising the hub height to 40m above HAT. |  |  |  | No change. Natural England continue to advise that further consideration is given to potential mitigation measures to reduce impacts on seabird features. Please see Appendix G2 for further detail.
H6 | H6 | The Hornsea 3 (‘New Colony approach’) approach should be used to determine the appropriate scale of compensation required for ANS, as recommended in the KSCP. Further discussion will also be needed on the appropriate compensation ratio and/or means of addressing uncertainty in the level of compensation provided. |  |  |  | Natural England provided further guidance on this matter in Appendix H1 of our Deadline 1 submission [REP1-065]. We welcome that the Applicant has provided values for breeding pairs needed according to both the Hornsea 3 and 4 approaches, however only the Hornsea 4 values have been carried forward to the calculations with ratios applied. We advise that both approaches are carried through for all scale and provision assessments. Please see Appendix H2 for further detail.
H7 | H7 | The Applicant has incorrectly stated the upper estimate of nest provision required for DBS East, DBS West and ODOW as 5,000 nesting spaces. We advise that the ‘compensation envelope’ was 5,500 in the published KSCP. We also highlight that this was based on lower impact predictions than have now been submitted. |  |  |  | Issue resolved. Revision 2 of the KCP [PDB-003] has been updated in line with the value published in the KSCP. However, as noted in Revision 3 of the KCP and Appendix H2, given the higher impacts now predicted from the Dogger Bank South projects, at this stage it cannot be assumed that a 'compensation envelope' of 5,500 will be sufficient.
H8 | H8 | The compensation totals presented are based on the Applicant’s and ODOW’s preferred approaches to the assessment. We welcome that a compensation ratio greater than 1:1 has been suggested, however a ratio of 2:1 has not been agreed. Compensation totals should be provided in line with SNCB guidance alongside the Applicant’s preferred approach. |  |  |  | No change. See H6. We also advise that the ODOW values are updated to reflect revisions to their assessment. As the ODOW Examination is due to end on 4th April, we consider there is sufficient time for this to be included within the DBS Examination. Please see Appendix H2 for further detail.
H9 | H9 | ANS structures - “up to two” and “maximum capacity” suggest that fewer than two offshore ANS, each with fewer than 2,250 nesting spaces, may be considered. One offshore ANS will likely be insufficient to compensate for the impacts of the projects. We are also concerned that 4,500 nest spaces may not be sufficient to compensate for the combined impacts of the DBS projects and ODOW given the scale of DBS’s impacts. The maximum provision should be revisited following any updated assessments. |  |  |  | No change.
H10 | H10 | The Applicant’s preferred delivery approach is via a collaborative agreement. We agree that this could be an appropriate route but note that there remains a lack of clarity on how the ANS would be delivered. |  |  |  | Issue progressed. Clarification has been provided that the Applicant and ODOW will each progress one project-led offshore ANS. The two projects are also exploring the potential for nesting space to be shared to present reciprocal resilience across the compensation measure via an MOU, therefore delivering the strategic measure and approach in line with the KSCP, collaboratively through the installation of individual project-led ANS. However, at this stage it remains unclear whether a single ANS will be sufficient for the requirements of the Applicant. Please see Appendix H2 for further detail.
H11 | H11 | Project-led, collaborative and strategic compensation all being progressed in parallel creates uncertainty in what is being secured and can be expected to be delivered. We highlight that the provision of a single offshore ANS with 2,250 capacity is unlikely to be sufficient to compensate for the predicted impacts of DBS, should delivery of collaborative/strategic measures fall through.
H12 | H12 | Our comments on the shortlist of potential locations for the offshore ANS should be considered in any future refinement of the shortlist. |  |  |  | Issue progressed. Please see Appendix H2 of our Deadline 2 submission for further detail on the shortlist of sites.
H13 | H13 | The ANS should be provided at least four breeding seasons before the projects are operational. |  |  |  | No change. We note the Applicant has submitted a document relating to this issue at Deadline 2. We will review this and provide further comment at Deadline 3.
H14 | H15 | The potential impacts of ANS implementation within NNSSR SAC should be considered and if this option is to be retained, information to inform an Appropriate Assessment provided. |  |  |  | Issue resolved. The KCP has been updated to remove the area of overlap with NNSSR SAC from consideration, which is welcomed.
H15 | H16 | The Applicant should update the predicted impacts of all submitted Offshore Wind Farm applications prior to the end of Examination. |  |  |  | Issue progressed. Whilst updates have been made to the in-combination assessment, further update will likely be needed. See Appendix G2 for further detail.
H16 | H17 | The Applicant has suggested that evidence does not appear to indicate that kittiwake populations in the southern North Sea have been significantly affected by Highly Pathogenic Avian Influenza (HPAI). However, a full colony count of kittiwake numbers at FFC SPA has not been undertaken since the majority of the recent HPAI outbreaks took place. We welcome the Applicant’s comment that ongoing monitoring will provide valuable evidence in this respect.
Document Used: [APP-054] 6.2.1.2 Outline Kittiwake Compensation Implementation and Monitoring Plan
H17 | H19 | We recognise the current uncertainty around the implementation of strategic kittiwake compensation and whether the KCIMP is therefore needed, we consider that should confirmation be provided by DESNZ, we would expect a populated KCIMP to be submitted into the Examination. |  |  |  | Following the publication of the Ministerial Statement confirming that offshore ANS should be delivered at a project level, we advise that a populated KCIMP should be submitted into the Examination.
Guillemot and Razorbill Compensation Document Used: [APP-058] 6.2.2 Appendix 2 Guillemot [and Razorbill] Compensation Plan
H18 | H20 | Provide an in-combination assessment of impacts on guillemot at the Farne Islands SPA and consider the need for compensation for these impacts. |  |  |  | Issue progressed. The Applicant has provided an in-combination assessment for guillemot at the Farne Islands SPA, however, we have outstanding concerns with some aspects of the assessment methodology (see G37). Please refer to Appendix G2 for further detail.
H19 | H21 | The most recent count for razorbill at FFC SPA is the 2022 count of 45,780 individuals, which when corrected according to standard methodology gives 61,345 individuals (Clarkson et al 2022). We advise that the GRCP is updated as it currently uses the count from 2017. |  |  |  | Issue resolved. The GRCP has been updated with the most recent count data.
H20 | H22 | The GRCP should be updated following any reassessments undertaken in response to the advice provided in Appendix G. Compensation metrics should be presented in line with both the Applicant’s preferred method for calculating impacts and SNCB guidance. |  |  |  | Issue progressed. Significant efforts have been made to provide assessment values in line with SNCB advice and the compensation plans have been updated accordingly. However, due to outstanding concerns with respect to in-combination assessments and PVAs, we remain unable to comment on the conclusions and impact values presented at this time. Please refer to Appendix G2 for further detail.
H21 | H23 | Provide further detail on the methods used to calculate compensation requirements for guillemot and razorbill, and on the rationale behind the choice of method. |  |  |  | No Change. Natural England provided further guidance on this matter in Appendix H1 of our Deadline 1 submission [REP1-065].
H22 | H24 | Compensation requirements have only been provided for guillemot and razorbill using compensation ratios of 1:1 and 2:1, and only for a limited range of mortality and displacement rates using the Applicant's preferred approach. We cannot advise on an appropriate compensation ratio until further details of the compensation measures are provided, however we note that the predicted requirements already appear substantial and will be challenging to deliver. Further discussion will be needed on the scale of compensation required once the impact assessments have been updated. |  |  |  | No Change. Please refer to Appendix H2 for further detail.
H23 | H26 | Several locations included have previously been ruled out by other projects (e.g. Hornsea Four). We consider there is a significant risk that all sites on the shortlist will be deemed unsuitable for compensation. Feasibility assessments for the shortlisted sites are needed as a matter of urgency to enable other sites to be explored should these prove unsuitable. |  |  |  | Issue progressed. Natural England provided comment on the Site Refinement Report in our Rule 17 response dated 16th December 2024 [AS-008]. We acknowledge the Applicant has planned further surveys for Q1 2025, and that results will be presented at Deadline 3. Please refer to Appendix H2 for further detail.
H24 | H28 | Feasibility assessments for the shortlisted sites are needed as a matter of urgency to confirm the presence of predators and suitable auk nesting habitat and to determine the scale of compensation that could be achieved. |  |  |  | Issue progressed. Natural England provided comment on the Site Refinement Report in our Rule 17 response dated 16th December 2024 [AS-008]. We acknowledge the Applicant has planned further surveys for Q1 2025, and that results will be presented at Deadline 3. Please refer to Appendix H2 for further detail.
H25 | H29 | Consideration should be given to connectivity of the predator eradication/control locations with guillemot and razorbill populations of the impacted SPA when refining the shortlisted sites. Given connectivity is likely to be low at best, an assessment of connectivity with the national site network for these species should also be presented. |  |  |  | Issue Progressed. A connectivity assessment has been provided in Revision 3 of the GRCP. Whilst it will be limited, there is potential for some connectivity with the National Site Network. Please refer to Appendix H2 for further detail.
H26 | H30 | Beginning eradication prior to the first turbine being installed - eradication may take longer than the two years allocated, and the compensation will not be delivering until the required number of chicks are being produced and have reached age of first breeding (i.e. recruited into the breeding population). We do not consider implementation before impact to be analogous to delivering compensation before impact. |  |  |  | No Change.
H27 | H31 | There remains a significant amount of work to be done before a location or locations can be selected, and we would have expected much of this to have been done prior to the point of application, as has been done on other projects.
H28 | H32 | We agree that exploring the potential of ANS provision as a compensatory measure for guillemot and razorbill has potential as adaptive management should monitoring prove it to be effective.
H29 | H33 | We welcome commitment to implementing bycatch reduction measures as a compensatory measure if “robust evidence demonstrating the effectiveness of techniques to reduce the bycatch of auks became available.” If and when this is available, this may be a suitable adaptive management measure.
Document Used: [APP-057] 6.2.2.1. Outline Guillemot and Razorbill Compensation Implementation and Monitoring Plan
H30 | H35 | A more detailed GRCIMP should be provided as soon as possible within the Examination process. |  |  |  | Following the publication of the Ministerial Statement confirming that predator eradication should be progressed initially at a project level, we advise that a populated CIMP should be submitted into the Examination.

## I - Terrestrial Ecology & Orni
Point | Point Number(s) from Appendix I [RR-039] | Taken from Natural England’s Relevant and Written Representations Dogger Bank South (East and West) Appendix I - Terrestrial Ecology and Ornithology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Issue Resolved
I1 | I6, I13 | We advise that the air quality modelling undertaken for assessing impacts from construction traffic be tested against Natural England’s thresholds, as detailed in the guidance document NEA001. We have engaged with the Applicant regarding this approach and understand that the Applicant will be updating the assessment following advice provided through our Discretionary Advice Service (DAS). (7.26) |  | Issue resolved. See Appendix I1 of Natural England's Deadline 1 submission for further detail.
I2 | I7, I13 | We advise that potential alternate routes that could be taken by vessels plus size of the vessels is provided - this could be detailed via an outline Port Management Plan. If the operational port is in the Humber Estuary SAC/SPA, provision of a Port Management Plan should be secured in the DCO to be submitted pre construc)tion, taking into account air quality impacts and vessel management. (7.26 |  | Issue resolved. See Appendix I1 of Natural England's Deadline 1 submission for further detail.
I3 | I9, I13 | The outline Code of Construction Practice should be updated to include separation buffers for the use of back-up generators. (7.26) |  | Issue resolved. See Appendix I1 of Natural England's Deadline 1 submission for further detail.
I4 | I17 | Consideration should be given to further survey of 'dry' ponds to determine if they have permanently dried out or if it was an occasional drying event and whether great crested newt (GCN) are present. (7.18) |  | Issue resolved. See Appendix I1 of Natural England's Deadline 1 submission for further detail.
I5 | I19 | We advise: - Supervision measures relevant to soil management and handling of soils should be held by competent soil specialist and secured in the OLEM. - Soil surveyors should be named with a list of qualifications and experience on the Agricultural Land Classification (ALC) survey submitted as part of the DCO. - Soil handling methods should normally be as specified as in the Defra Construction Code of Practice for the Sustainable Use of Soils on Construction Sites - A commitment for best and most versatile (BMV) agricultural temporality required for the development to be returned to its original ALC grade - Clarification on the frequency of inspections to be undertaken to ensure soil is being managed in line with the detailed Soil Management Plan. - Production of the final SMP should be secured within the DCO wording. - The outline SMP should be updated with the recommendations listed here as needed. (7.21) |  | Issue resolved. See Appendix I1 of Natural England's Deadline 1 submission for further detail.