## Title page
THE PLANNING ACT 2008
THE INFRASTRUCTURE PLANNING (EXAMINATION PROCEDURE) RULES
2010
Natural England's Risk and Issues Log - Deadine 8 Submission.
For:
The construction and operation of Dogger Bank South (East and West) Offshore Wind Farm, located approximately 100-122 km from the North East Coast in the Southern North Sea Sea.
Planning Inspectorate Reference EN010125
3rd July 2025

## How to read Risks and Issue Log
Natural England has created this Risk and Issues Log to track progress through the Dogger Bank South (East and West) examination process. The Risks and Issues Log will be submitted at each deadline and marks issues with a colour from our RAG scale depending on the level of significance of the issue. All red, amber and purple issues from our Relelvant and Written Representation are included (collated where appropriate). Green and yellow issues are included if/where relevant. It should be noted that the colour scale is different from that used in the Statement of Common Ground provided by The Applicant. Our PADSS as submitted at Relevant Represensations has also ben provided, however this will not be updated until Deadline 4. The Risk and Issues Log is split into multiple tabs in line with the Appendices of our Relevant Representations submission. A - DCO B - Marine Physical Environment C- Benthic & Intertidal Ecology D - Benthic Compensation E - Fish & Shellfish F - Marine Mammals G - Offshore Ornithology H - Offshore Ornithology Compensation I - Terrestrial Ecology & Ornithology The Risk and Issues Log will be submitted alongside our written response at each deadline. This will reflect our position following a review of documents that we have considered in forming our position at each deadline. Any issues added to the log during Examination (not included in Relevant Reps) are highlighted in Red and then coded according to RAG status.
Purple Note for Examiners and/or competent authority. May relate to DCO/DML
Red Natural England considers that unless these issues are resolved it will have to advise that (in relation to any one of them, and as appropriate) it is not possible to ascertain beyond reasonable scientific doubt that the project will not affect the integrity of an SAC/SPA/Ramsar and/or significantly hinder the conservation objectives of an MCZ and/or damage or destroy the interest features of a SSSI and/or comply fully with the Environmental Impact Assessment requirements.
Addressing these concerns may require the following:
new baseline or survey data; and/or
significant revisions to baseline characterisation and/or impact modelling and/or
significant design changes; and/or
significant mitigation
In addition, Natural England may use this category to highlight where there is a significant risk that an issue will not be sufficiently addressed within the Examination timescales. Consequently, issues that start out as Amber may progress to Red in the latter stages of the examination.
Amber Natural England does not agree with the applicant’s position or approach and consider that this could make a material difference to the outcome of the decision-making process for this project.
Natural England considers that these matters may be resolved through:
provision of additional evidence or justification to support conclusions; and/or
revisions to impact assessment methodology and/or assessment conclusions; and/or
minor to moderate revisions to impact modelling; and/or
well-designed mitigation measures that are adequately secured through the draft DCO/dML and/or
amendments to draft plans
If these issues are not addressed or are unlikely to be resolved by the end of the Examination, then they may become a Red risk as set out above.
Yellow Natural England doesn’t agree with the Applicant’s position or approach. We would ideally have liked this to be addressed but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process and would not expect these matters to be a ongoing focus of the examination. However, we reserve the right to revise our opinion should further evidence be presented.
It should be noted by interested parties that just because these issues/comments are not raised as significant concerns in this instance, it should not be understood or inferred that Natural England would be of the same view in other cases or circumstances.
Once a Risk or Issue has been categorised as yellow, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will greyed out at subsequent deadlines in order to rationalise the risk and issues log.
Green Natural England is in broad agreement with the Applicant’s approach and has no significant outstanding concerns. As above, we reserve the right to revise our opinion should new evidence be presented. Once a Risk or Issue has been categorised as green, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be greyed out at subsequent deadlines in order to rationalise the risk and issues log.

## PADSS
Ref | The principal issue in question | The brief concern held by Natural England which will be reported on in full in WR / LIR | What needs to change, or be included, or amended so as to overcome the disagreement | Likelihood of the concern being addressed during Examination | RAG | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8
Development Consent Order (DCO)
NE1 | Maximum piling parameters not secured | The DCO does not contain any restriction of the maximum hammer energy used during piling. This is a key metric for the noise impact to marine mammals and sensitive fish species. | The maximum limit assessed should be appropriately secured in the deemed Marine Licences (dMLs). | Likely Subject to this condition being secured |  | The maximum hammer energy has been secured in the DCO.
NE2 | Deployment of cable protection | The DCO does not contain an end date for deployment of cable protection for within and outside of designated sites. Our standard advice is that cable protection should only be deployed for a maximum period of 10 years from the commencement of operations. Within any designated sites for benthic features, it should be stipulated that there should be no deployment of cable protection after the completion of construction. | Include a condition limiting the deployment of cable protection outside of designated sites to within 10 years of the completion of construction, and inside designated sites such as Dogger Bank SAC, no cable protection may be deployed after the completion of construction. | Likely Subject to this condition being secured. |  | No change. Whilst the Applicant has committed to applying for a new Marine License for cable protection installed in new areas in the operation phase, they maintain their postion that the amount of cable protection consented in the DCO is an allowance that can be used throughout the operational phase if it's within the footprint installed during construction, including within designated sites. The Applicant and Natural England maintain their positions. |  | No change. We continue to disagree with the Applicant's position and have identified risks to the Applicant's derogation case within Appendix C6 of our Deadline 6 submission for further detail. |  | No change. |  | No change. Please see Appendix B8 of Natural England's Deadline 8 submission for our final position on this matter.
Marine Physical Environment
NE3 | Cable protection - nearshore | Natural England is concerned that cable protection in the nearshore could disrupt longshore sediment transport and impact features of the Holderness Inshore MCZ, Humber Estuary SAC and Smithic Bank. | A commitment should be made to avoid the placement of external cable protection within shallow nearshore water (i.e. within the 10m depth contour), or alternative methods of cable burial should be explored to remove the need for cable protection between mean low water springs and the 10m contour. | Potential resolution This is subject to the Applicant securing the advised commitment |  | No change. The Applicant will be providing a technical report at Deadline 5 regarding the impact of cable protection in the nearshore on longshore sediment transport. |  | Issue progressed. The Applicant has carried out a detailed assessment on potential impacts to nearshore sediment transport due to the presence of nearshore cable protection [REP5-040]. Natural England remain of the view that impacts to Holderness Inshore MCZ and the Humber Estuary SAC cannot be ruled out. Please see Appendix B6 of our Deadline 6 submission. |  | No change. |  | No change. Whilst the Applicant has provided a response [REP7-131] to our advice [REP6-072] on the Applicant’s assessment [REP5-040] of the potential impacts of nearshore cable protection on nearshore sediment transport processes and coastal morphology, it is likely that our position will remain unchanged although we will endeavour to review and provide further comment on this accordingly at Deadline 9. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology.
NE4 | Cable protection -Dogger Bank SAC | The presence of cable protection measures on Dogger Bank (and within Dogger Bank SAC) could modify the hydrodynamic regime and affect sediment transport pathways contributing to the ecological ‘halo effect’. See NE10. | Natural England advises that further justification is needed for the volumes of predicted external cable protection within Dogger Bank SAC. | Likely Subject to the Applicant providing further evidence. |  | No change. The overall volume of cable protection required has been reduced due to the Change Request, however the Applicant maintains a 10% requirement is necessary for the remaining cables. The Applicant has indicated this will not change further within Examination. Therefore, there is unlikely to be agreement in examination. |  | No Change - Please see Appendix C6 of Natural England's Deadline 6 submission in relation to public interest tests |  | No change. |  | No change. We maintain our previous advice. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology.
NE5 | Flamborough Front | The presence of the Dogger Bank South Arrays (alone and in combination with other nearby offshore wind farms) could impact circulation, stratification, mixing, and sediment resuspension in the water column. This could in turn, cause changes to the Flamborough Front which could have far-reaching and long-term consequences for the wider marine ecosystem | Natural England advises that the Applicant should monitor potential changes to stratification, currents, and primary productivity during pre-construction, post-construction, and for the lifetime of the Projects. | Potential resolution This is subject to the In-Principle Monitoring Plan being updated. |  | No change. Natural England maintain that the Applicant should commit to monitoring the Flamborough Front. A meeting has been scheduled with the Applicant to discuss this further. |  | Issue progressed. The Applicant has committed to monitoring of the Flamborough Front However, the monitoring approach as outlined in the IPMP requires further detail. |  | Issue progressed. The Applicant has outlined in [REP6-052] that they will consider The Crown Estate FRONTWARD project during the pre-construction stage of the in-principal monitoring to establish the duration and frequency of occurrence of the Flamborough Front within the Array Areas, to inform the design of post-construction monitoring. This should be captured in an updated IPMP. |  | Issue satisfactorily resolved. We welcome the updated IPMP (rev 05) [REP7-116] which outlines that the Applicant will "Consider the data published from The Crown Estate FRONTWARD Project, and any new research or data that has become available since DCO submission, to inform the pre-construction baseline".
Benthic and Intertidal Ecology
NE6 | Worst case habitat loss – Dogger Bank SAC | The Applicant has not considered the potential for changes to the physical and/or biological structure and function of Annex I sandbank beyond the footprint of the planned infrastructure. We are particularly concerned that secondary ‘ecological halo’ effects could be combined, resulting in broadscale changes in the benthic habitats and communities across the wider DCO area and a significant proportion of Dogger Bank SAC. | A robust assessment is needed of the potential Worst-Case area of impact on benthic communities within Dogger Bank SAC, and the nature and scale of that impact, as a result of changes to physical and biological process following the placement of structures and cable/scour protection on the seabed. | Likely This is subject to the Applicant providing an updated assessment |  | No change. Natural England maintain our previous advice. See Appendix C4 for futher detail. |  | Issue progressed. The Applicant has provided an assessment of ecological halo effects and presented an area of worst case impact on a without prejudice basis. However, we advise that further revision is necessary. Please see Appendix C6 of our Deadline 6 submission for further detail. |  | No change |  | Issue progressed. The Applicant has updated their assessment of ecological halo effects [REP7-128]. We welcome the Applicant providing a without prejudice figure based on 50m halo impact from cable protection. But if a reduced buffer for halo effects from cable protection can be agreed then we recognise that the compensation requirement will be reduced and amounts will fall between 5km2 and 13.2km2 for habitat loss. This doesn't take account of impacts from habitat disturbance.
NE7 | Cable protection - decommissioning | The Applicant has not committed to the removal of cable and scour protection within the Dogger Bank SAC at the point of decommissioning. This will cause permanent loss of the designated sandbank feature. | In line with recent Secretary of State Decisions for OWF NSIPs the Applicant should commit to removing all on and above seabed infrastructure at the point of decommissioning. This should be secured in the DCO and an outline Decommissioning Plan. | Potential resolution |  | No change. Natural England and the Applicant maintain their respective positions. Natural England do not consider that the provision of compensation negates the need to remove project infrastructure at end of life. |  | No change. We continue to disagree with the Applicant's position and have identified risks to the Applicant's derogation case within Appendix C6 of our Deadline 6 submission for further detail. |  | Issue progressed. The Applicants have committed [REP6-044] to consider removability of cable protection as part of the development of the final Cable Statement and Decommissioning Programme to be produced for submission to the SoS. Whilst this is welcome, it is not sufficient to resolve concerns regarding the lack of a full commitment to decomissioning. |  | No change.We maintain our previous advice. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology.
NE8 | Volumes of cable protection | The methods used to determine the amount of cable protection and any associated lasting loss/change of Annex I sandbank habitat within Dogger Bank Special Area of Conservation (SAC) are neither comprehensive nor transparent. It is therefore unclear how realistic the Maximum Design Scenario (MDS) is. | Further justification is needed for the volumes of predicted external cable protection in the Project Envelope. | Likely Subject to the Applicant providing further evidence. |  | No change - NE is of the understanding that no further revisions will be made to the CBRA within Examination timeframes. We maintain our advice that further information and rationale is provided for the WCS for cable protection within DB SAC. Therefore, there is unlikely to be agreement in examination. |  | No change. |  | No change. |  | No change. We maintain our previous advice. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology.
NE9 | Mitigation | This mitigation included for sediment deposition is insufficient, particularly where there could be direct or indirect effects on Dogger Bank SAC or priority habitats. | Natural England advises that further mitigation options should be committed to by the Applicant. | Likely |  | Issue progressed. The Applicant has confirmed that they will be able to deposit like sediment on like sediment. An updated Cable Statement is due to be submitted at Deadline 4. |  | Issue progressed. Natural England is satisfied with the Applicant's updated assesments for sediment depostion in the ECC, however additional mitigation is needed. See Appendix B5 of Natural England's Deadline 5 submission for further detail. |  | Issue progressed. The Applicant has updated the Cable Statement to include additional mitigation. However, there is no change to the Applicant's position on the use of a fall pipe for depositing dredged sediment updrift of the sandbank/sandwave- we maintain our advice on this. See Sheet B, B17. |  | No change. The Applicant maintains their position [REP6-052] on not committing to depositing sediment updrift of dredging locations and that it is not technically feasible to use a fall pipe for deposition. We maintain our previous advice. See B17. Note that for offshore sandwave levelling, potential impacts could be to Holderness Offshore MCZ and nearshore sandwave levelling could have potential impacts to Holderness Inshore MCZ.
Benthic Compensation
NE10 | Alignment between strategic and project-led compensation | Compensatory measures proposed by the Applicant as part of their project level derogation case are expected to align with the measures and approach outlined in the Dogger Bank Strategic Compensation Plan (DBSCP) and be secured as a requirement of the DCO. However, the DBSCP and the project compensation do not align, with damage to sandbanks being excluded from the compensation requirements. | Natural England advise that the DCO should secure compensation for both habitat loss and damage to Annex 1 sandbank. | Likely Subject to this being secured in the DCO |  | No change. NE and the Applicant maintain their respective positions. Agreement will not be reached on this matter. |  | Issue progressed. Whilst Natural England and the Applicant continue to disagree on the impact pathways contributing to AEoI, the Applicant has now provided estimates for habitat damage and halo effects on a without prejudice basis. However we consider further refinement of the estimates are needed. See Appendix C6 of our Deadline 6 submission for further detail. |  | No change. |  | Issue progressed. The Applicant has updated their assessment of ecological halo effects [REP7-128]. We welcome the Applicant providing a without prejudice figure based on 50m halo impact from cable protection. But if a reduced buffer for halo effects from cable protection can be agreed then we recognise that the compensation requirement will be reduced and amounts will fall between 5km2 and 13.2km2 for habitat loss. This doesn't take account of impacts from habitat disturbance.
Fish and Shellfish Ecology
NE11 | Spawning habitat loss - sandeel | The full scale of potential sandeel spawning habitat loss and/or change has not been assessed. | A robust assessment is needed of the potential worst-case area of impact on spawning habitat along the ECC and within Dogger Bank SAC sandbank feature, including the nature and scale of impact as a result of changes to physical and biological processes following the placement of structures and cable/scour protection on the seabed, and implications at a localised population level. | Likely This is subject to the Applicant providing an updated assessment |  | No Change. Natural England maintain our previous advice that the Applicant should provide an assessment of the potential worst-case area of impact on sandeel spawning habitat along the ECC and within Dogger Bank SAC sandbank feature. |  | No Change. Natural England maintain our previous advice that the Applicant should provide an assessment of the potential worst-case area of impact on sandeel spawning habitat along the ECC and within Dogger Bank SAC sandbank feature. |  | No Change. The Applicant has indicated in their Response to Deadline 5 Documents [REP6-052] that the RIAA will be updated at Deadline 7 to include habitat loss from UXO into the projects footprint. |  | Issue satisfactorily resolved. Natural England welcomes the Applicant's addition of WCS for disturbance to Annex I Habitats, and habitat loss in the Dogger Bank SAC in the updated RIAA [REP7-017]. We note that these impacts to sandeel habitat are not currently outlined in the ES Chapter 10 [REP7-043] but direct the Examining Authority to the RIAA for the relevant assessments. We note that there may be further refinement to the impact values presented based on our benthic comments, see M10.
NE12 | Indirect effects on seabirds and marine mammals – RIAA conclusions | Natural England disagrees that impacts on mobile designated site interest features (i.e. seabirds from FFC SPA and harbour porpoise in SNS SAC) can be ruled out based solely on no significant impacts being concluded at a regional population level in the EIA assessment for forage fish species. The RIAA assessment has also only considered direct construction impacts on prey availability rather than the operational impacts of spawning habitat loss. | Assessments on herring and sandeel should be considered at a biologically relevant population level and should include loss and/or change of spawning habitat throughout the lifetime of the project. The implications on prey abundance and distribution within the foraging areas of Annex I and Annex II species from designated sites should be assessed. | Partial resolution likely Subject to the Applicant providing an expanded assessment. However, uncertainties will likely remain that are beyond the ability of the project to address. If impacts to designated site features cannot be ruled out, consideration may need to be given to addressing the wider ecosystem functionality of sandbanks within derogation proposals. |  | No Change. Natural England maintain that there is still a risk of AEoI to both Marine Mammal and Ornithological features as a result of impacts on prey species. The Applicant has indicated in their response to the ExA Questions [REP3-027] that a technical note relating to impacts on prey species will be provided at Deadline 4. |  | No Change. Natural England maintain that there is still a risk of AEoI to both Marine Mammal and Ornithological features as a result of impacts on prey species. Please refer to our Deadline 5 advice [REP5-056] and Appendix E6 from our Deadline 6 submission for further detail. |  | Issue Progressed. Following Natural England's sight of updated DCO conditions that will be submitted by the Applicant at Deadline 7, Natural England are able to rule out AEoI on SNS SAC harbour porpoise. Were an AEoI to be concluded for SNS SAC harbour porpoise overall, we would have considered that indirect impacts to prey species would likely be having a contributing effect. However, we do not consider the risk to harbour porpoise from indirect impacts on prey species is sufficient to drive an AEoI conclusion alone. Natural England consider that for those Ornithological features where AEoI cannot be ruled out (kittiwake, guillemot and razorbill), this impact pathway will, without resulting in an AEOI in its own right, intensify those effects on those species. |  | No change.
NE13 | Baseline characterisation - sandeel abundance | Sandeel abundance data has not been used to characterise the importance of the array areas as potential sandeel habitat. | We advise that the Applicant should use sandeel abundance data (such as the North Sea Sandeel Survey (NSSS)) to characterise the importance of the array areas as sandeel habitat and support the assessment of impacts on localised sandeel populations | Likely This is subject to the Applicant providing an updated assessment |  | No Change. Whilst a figure of NSSS data has been provided, presentation of data on relative abundance/population distribution within the project area compared to wider region, that would help to support the assessment of sandeel suitability, has not been provided. Natural England request the Applicant includes these updates in relevant assessments. |  | No change. |  | No Change |  | Whilst we maintain our previous advice. We agree with the MMO [REP5-049: 1.7.2] that the presentation of this data at this late stage in the application process will not significantly change the outcomes of the assessment.
Marine Mammals
NE14 | Southern North Sea SAC - harbour porpoise underwater noise impacts - Outline Site Integrity Plan (SIP) | Natural England is concerned that the SIP process is being exclusively relied on to address in-combination noise levels from multiple projects on SAC harbour porpoise in the post-consent phase. The Applicant has not committed to using Noise Abatement Systems (NAS) at this stage, increasing the risk that an adverse effect on site integrity (AEoI) cannot be avoided | The Applicant should commit to specific mitigation measures at this stage, particularly NAS, in the Outline Marine Mammal Mitigation Protocol and SIP, which can be removed at a later date if the revised SIP demonstrates they are not required. | Potential Resolution If changes can be made to the Outline MMMP, it is likely this issue can be resolved. |  | No Change. Natural England maintain that the Applicant should commit to Noise Abatement Systems pre-consent. We consider that this issue is resolvable subject to sufficient commitments being made. |  | No change. The Applicant has provided an illustrative assessment that demonstrates that a 10 dB reduction in construction noise, applied via primary or secondary mitigation, would likely enable adverse effects to be ruled out on all outstanding features of concern. However, a commitment has not been made to deliver this, or additional mitigation in general. We do not consider that 'consideration of' mitigation post-consent is sufficient. |  | Issue Resolved. The Applicant has given Natural England advance sight of updates to the DCO condition related to noise mitgation for piling to be submitted at Deadline 7. We are satisfied that this updated condition sufficiently secures the application of additional primary and/or secondary mitigation.
NE15 | EIA/HRA conclusions | The conclusions are over-reliant on the outcomes of population modelling, and do not consider all assessments undertaken where higher impacts are indicated. | Assessments should be updated based on the highest predicted impact values, for all receptors and pathways, to inform the EIA and HRA conclusions. Where significant impacts cannot be ruled out, additional mitigation should be explored to avoid or reduce impacts. | Potential Resolution If the Applicant updates their EIA/HRA assessment it may be possible to resolve this issue |  | No Change. Natural England acknowledge that the Applicant has now provided impacts according to EDR, however we maintain our previous advice that the Applicant should provide an assessment based on the highest predicted impact values. |  | No change. Natural England and the Applicant maintain their respective postions on this point. Agreement is unlikely to be reached. |  | No change. Natural England and the Applicant maintain their respective postions on this point. Agreement is unlikely to be reached. |  | No change. Natural England and the Applicant maintain their respective postions on this point and consider that agreement will not be reached on this matter within Examination.
NE16 | Injury Zone for minke whale and harbour porpoise | The mitigation proposed by the Applicant is insufficient to mitigate the full piling injury zone for minke whale and harbour porpoise | The Applicant needs to demonstrate how the full injury zone will be mitigated, this could be through design changes or commitments to additional mitigation. | Potential Resolution If changes can be made to the Outline MMMP, it is likely this issue can be resolved. |  | No change. Natural England maintain that the Applicant should demonstrate in their current assessment that they are able to mitigate the full injury zone for minke whale and harbour porpoise. We consider this would be resolved by the Applicant commiting to implement Noise Abatement Systems. |  | No change. The Applicant has provided an illustrative assessment that demonstrates that a 10 dB reduction in construction noise, applied via primary or secondary mitigation, would enable the full injury zone to be mitigated. However, a commitment has not been made to deliver this, or additional mitigation in general. We do not consider that 'consideration of' mitigation post-consent is sufficient. |  | Issue Resolved. The Applicant has given Natural England advance sight of updates to the DCO condition related to noise mitgation for piling to be submitted at Deadline 7. We are satisfied that this updated condition sufficiently secures the application of additional primary and/or secondary mitigation.
Offshore Ornithology
NE17 | Assessment methodologies and EIA/HRA conclusions | Natural England cannot agree with the EIA or HRA conclusions presented due to several aspects of the assessment not being provided in line with SNCB guidance and/or Natural England advice given during the Evidence Plan Process (EPP) and/or our Best Practice Advice, these include: - baseline mortality rates and EIA reference populations - guillemot seasonality - gannet collision risk - approach taken to combining the impacts of the two arrays - apportioning approach for guillemot and razorbill - lack of, or incomplete in-combination assessments | Natural England advise that assessments in line with SNCB advice are provided in full, alongside the Applicant’s preferred methodology. This advice has been provided during the EPP and repeated, where necessary, in Appendix G. Natural England will not be able to advise the Examination further on the ornithology impacts of the proposals until this material is provided. | Likely This is subject to the Applicant presenting assessments that are in line with SNCB advice. |  | Issue progressed. Significant progress has been made with the ornithology assessment. We understand the Applicant will be providing revisions on outstanding matters at Deadline 4. |  | Issue progressed. Following updates to the assessments, Natural England is statisfied that impacts for the project alone have been provided in line with SNCB advice and we have provided our conclusions with respect to EIA and HRA. Whilst we have some outstanding concerns with respect to the in-combination assessment, we understand the Applicant will be providing clarifications at Deadline 6 that will likely result in resolution. |  | Issue satisfactorily resolved. We have reviewed the additional clarifications provided by the Applicant in REP6-052 on remaining discrepancies in in-combination totals between projects, and agree that they are unlikely to have a material impact on assessment conclusions. We are satisfied that no further updates are required.
NE18 | Mitigation of likely very high impacts on seabirds | The baseline surveys indicate the potential for very high impacts on seabirds at both EIA and HRA scales. It is not clear how robustly ornithology impacts were factored in when designing the post-PEIR reductions of the array areas and whether further reduction could be undertaken to reduce impacts. | Further consideration should urgently be given to potential avoidance/ mitigation measures to reduce impacts on seabird features, such as array reductions, changes to design and layout of arrays, or increasing the hub height of turbines. Hotspot modelling of seabird densities and distributions in the study area may help to identify areas where impacts on seabird features are particularly high to inform an improved mitigation approach. | Unlikely There is no guarantee this issue will be resolved within the Examination timeframe |  | No Change. The Applicant maintains their position that no additional mitigation is required. Natural England maintain our previous advice. |  | No Change. The Applicant maintains their position that no additional mitigation is required. Natural England maintain our previous advice. |  | No change. The Applicant has confirmed [REP6-052] that they will not present hotspot modelling as 'any further reductions in the developable area within the lease boundaries would risk making the Projects economically unviable.' Whilst we note this argument, it is not within our field of expertise to comment on. Natural England maintains our previous advice [REP5-060] on the use of hotspot modelling and highlight its usage by other projects e.g. Outer Dowsing. We therefore consider that agreement will not be reached on this matter within Examination. |  | Issue progressed. Natural England welcome the Applicant's provision of some spatial mapping work in [REP7-137], however it is not sufficient to address our concerns. Please see our Deadline 8 cover letter for full details.
Ornithology Compensatory Measures
NE19 | Agreed compensation levels – all measures | As noted above, it is not possible to agree the level of compensation required until impact assessments have been provided in line with SNCB advice. Additionally, the method for generating the required amount of compensation needs to be carried out in line with SNCB advice before it can be confirmed as sufficient. | See NE17. Once the impact assessment has been updated, the outputs should be used to generate compensatory requirements in line with SNCB advice. | See NE17. |  | Issue progressed. Significant progress has been made with the ornithology assessment. We understand the Applicant will be providing revisions on outstanding matters at Deadline 4. Natural England have also provided the Applicant with further guidance regarding calculating compensation. |  | Issue progressed. Compensation requirements have now been provided for all species except Farne Islands guillemot. We understand these will be provided at Deadline 6. Whilst values have been provided according to the SNCB advised methodology, some minor clarifications are outstanding on discrepancies in some outputs. |  | Issue resolved. Impacts to Farne Islands guillemot have been included on a without prejudice basis in the Guillemot and Razorbill Compensation Plan (Revision 6) [REP6-013] submitted at Deadline 6. We are also generally satisified with the clarifications with respect to remaining discrepancies, and errors have been corrected where needed.
NE20 | Location for predator eradication – FFC SPA guillemot and razorbill | A location or locations to deliver predator eradication is yet to be determined. Several sites on the Applicant’s shortlist have previously been ruled out by other OWF projects, and feasibility studies have not been provided to demonstrate predator presence and auk habitat suitability at shortlisted sites. It is plausible that none of the short-listed locations are appropriate. It will not be possible to quantify the scale of compensation that might be achievable, and therefore if the impacts can be compensated, until a location or locations is identified. | Feasibility assessments for the shortlisted sites should be provided as a matter of urgency, to demonstrate the suitability of sites and the scale of compensation that could be delivered by the measure. | Potential resolution If the Applicant provides feasibility assessments for the shortlisted sites it might be possible to resolve this issue, but there is no guarantee a suitable site will be found. |  | Issue progressed. NE welcome the recent survey work undertaken, albeit this indicates Middle Mouse does not support rats. Worm's Head is now the sole project-led site. We advise that the views of NRW on the feasibility of this location are sought. Given the scale of potential impacts the Applicant's auk compensation will be dependent on strategic delivery on the Isles of Scilly, so we welcome the Applicant's engagement with the initiative. |  | No change. It has been confirmed in the updated GRCP [REP5-012] that Worms Head is no longer in scope. Natural England retains its concerns about Middle Mouse as rat presence has not yet been confirmed and it is likely too small to compensate for the impacts of the Project alone. The Applicant has begun investigating locations in Scotland for project-led compensation, however progress within Examination timeframes is likely to be limited. This means that the Applicant's derogation case hinges on the availability of the Isles of Scilly as a strategic compensation measure. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | A location for Project-led delivery cannot be considered to be sufficiently in scope or secured at this time. Natural England welcome the Applicant’s inclusion of the Isles of Scilly as a potential site and agree it has considerable potential. A delivery mechanism for the Isles of Scilly has yet to be established and secured, although a Task & Finish Group has been set up to progress this.
Air Quality – Onshore habitats
NE21 | Air quality impacts to international and national designated sites due to construction traffic emissions. | Air quality impacts to designated sites have been assessed using JNCC decision making thresholds. However, NE does not currently accept the use of this document. We therefore advise that the modelling that has been undertaken for the pollutants should be tested against NE’s thresholds for impacts due to air emissions from traffic, as detailed in the guidance document NEA001. | Assessment of air quality impacts to international and national designated sites should be undertaken using the thresholds included in Natural England’s published guidance document NEA001. | Likely This issue could be progressed with provision of an updated air quality assessment. Natural England and the Applicant are in active discussion regarding this approach through NE’s DAS service. |  | Issue resolved.

## A - DCO
Point | Point Number(s) from Appendix A [RR-039] | Taken from Natural England’s Relevant and Written Representations Dogger Bank South (East and West) Appendix A - Development Consent Order | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Consultation, actions, progression | RAG Deadline 9 | End of Examination Position | Issue Resolved
Development Consent Order (DCO) |  |  |  | Documents reviewed: [AS-121] 3.1 Draft Development Consent Order (Rev 03) (Tracked)
A1 | A4 | The definition of maintain should be amended to show a clear linking to the Outline Offshore Operations and Maintenance Plan (OOOMP) or Environmental Statement. This comment applies to schedules 10-14 where similar provisions are recorded, for brevity have not repeated the comments (Article 1, Pg 8). |  | No change. |  |  |  | No change. The Applicant does not consider that the definition of 'maintain' requires updating and states that key parameters related to maintenance activities will be included in the final OOOMP. We maintain our previous advice. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. |  | Issue resolved. We are satisfied that the definition of maintain is linked to the Environmental Statement, as highlighted by the Applicant [REP7-131] |  |  |  | Issue resolved. We are satisfied that the definition of maintain is linked to the Environmental Statement, as highlighted by the Applicant [REP7-131]
A2 | A5 | All references to Natural England should be replaced with ‘the Relevant SNCB’ (Article 1). |  | Issue addressed. References to Natural England have been replaced throughout the DCO. | [17 empty] | Issue addressed. References to Natural England have been replaced throughout the DCO.
A3 | A6 | Requirement 10 (2) lists the expected aspects to be detailed in the landscape management plan. We would note that the requirement for monitoring and maintaining of the landscaping works should also be secured here. (Schedule 2, Part 1, Requirement 10). |  | Natural England will provide further comment at Deadline 2. |  |  |  | Issue resolved. We are satisfied that Requirement 11 of the Draft DCO [AS-121] provides that the landscaping works must then be carried out in accordance with any landscape management plan approved under requirement 10. | [13 empty] | Issue resolved. We are satisfied that Requirement 11 of the Draft DCO [AS-121] provides that the landscaping works must then be carried out in accordance with any landscape management plan approved under requirement 10.
A4 | A7 | The requirement wording should be updated to state which environmental topics will be included within the Code of Construction Practice (CoCP). Paragraph (4) should be amended to note that the relevant SNCB will be consulted by the relevant planning authority prior to the approval of any pre-commencement screening and fencing works. The production of the final soil management plan is not secured in the DCO wording. We advise this could be included within this requirement (Schedule 2, Part 1, Req. 19). |  | Natural England will provide further comment at Deadline 2. |  |  |  | Issue progressed. We maintain our advice that environmental topics that are included in the CoCP should be listed. Regarding our advice that paragraph (4) be amended, we believe that this has been added into Draft DCO (Rev 03) [AS-121] under paragraph (5)(Schedule 2, Part 1, Requirement 19) rather than (4) however it may also be covered by paragraph (1). We request the Applicant provide clarification on whether this is correct. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue progressed. We maintain our advice that environmental topics that are included in the CoCP should be listed. We welcome the amendment to the Draft Development Consent Order (DCO) (Revision 7) [REP4-006] to Schedule 2, Part 1, Requirement 19(4) to include consultation with the relevant SNCB. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. The Applicant maintains their position [REP6-052] that they do not agree that there is a need to list the different environmental topics that will be included within any final Code of Construction Practice (CoCP) within draft DCO requirements. We maintain our previous advice. |  | No change.
A5 | A8 | Regarding the commitment to secure Biodiversity Net Gain (BNG) for this project, there is a need to secure the BNG for a minimum of 30 years, which should be reflected in the DCO wording. We also encourage the delivery of minimum 10% BNG to be secured in the DCO wording (Schedule 2, Part 1, Req.32). |  | The Applicant considers that as detail of the minimum 30 year period will be included in the BNG Strategy that it is unnecessary to include within the DCO. They also disagree with commiting to the recommended minimum 10% of BNG. Natural England maintains our advice, however as BNG is not yet mandatory for NSIPs we will not pursue this issue further. | [17 empty] | The Applicant considers that as detail of the minimum 30 year period will be included in the BNG Strategy that it is unnecessary to include within the DCO. They also disagree with commiting to the recommended minimum 10% of BNG. Natural England maintains our advice, however as BNG is not yet mandatory for NSIPs we will not pursue this issue further.
A6 | A9 | Points A10 - A15 (RR ref) apply to Schedules 10 -14 where similar conditions apply. |  | N/A. | [17 empty] | Points A10 - A15 (RR ref) apply to Schedules 10 -14 where similar conditions apply.
A7 | A10 | This condition does not include the requirement to submit an updated OOOMP. We also note that condition 10 (1) (c) requires details on cable protection. However, we assume this covers during construction cable protection only. We further note that operations and maintenance is provisioned for at condition 7. However, the wording at condition 7 only allows for the replenishment of cable protection. Natural England interprets this to mean the deemed Marine Licence (dML) only allows for new areas of cable protection to be installed during construction. Confirmation is needed of the intention with regard to the conditioning of cable protection deployment after construction. (Schedule 10, 15(1)) |  | Natural England will provide further comment at Deadline 2. |  |  |  | Issue progressed. We welcome the inclusion in Schedule 10, part 2, condition 7 (6) of the Draft DCO (Rev 03) [AS-121] that the offshore operations and maintenance plan is to be submitted at least 4 months prior to operation. This part of the issue is resolved. However, see Point A15 with regards to additional or replenishment cable protection. |  | See Point A15 with regards to additional or replenishment cable protection. |  | No change - we maintain our previous advice. Please see Point A15 for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | See Point A15 with regards to additional or replenishment cable protection. |  | Issue progressed. We welcome the inclusion in Schedule 10, part 2, condition 7 (6) of the Draft DCO (Rev 03) [AS-121] that the offshore operations and maintenance plan is to be submitted at least 4 months prior to operation. This part of the issue is resolved. However, see Point A15 with regards to additional or replenishment cable protection. |  |  |  | Issue progressed. We welcome the inclusion in Schedule 10, part 2, condition 7 (6) of the Draft DCO (Rev 03) [AS-121] that the offshore operations and maintenance plan is to be submitted at least 4 months prior to operation. This part of the issue is resolved. However, see Point A15 with regards to additional or replenishment cable protection.
A8 | A11 | Amend condition to include consideration of the use of Noise Abatement Systems (NAS) within the final Marine Mammal Mitigation Protocol (MMMP). (Schedule 10, 15(1)(g)) |  | The Defra Marine Noise Policy paper was published on 21st January 2025. Natural England is reviewing this in terms of what it means for our advice on this project. We will provide further comment at Deadline 2, in the interim please see section 7 of our Deadline 1 cover letter. |  |  |  | No Change. Natural England's advice remains that The Applicant should be committing to using Noise Abatement Sytems at this stage in the application. See Point F6 and Appendix F3 of our Deadline 3 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - we maintain our previous advice. |  | No change - We maintain our advice that a commitment to deliver mitigation (rather than consider delivering it) should be made. See Appendix F6 of Natural England's Deadline 6 submission for further detail. |  | Issue Resolved. The Applicant has given Natural England advance sight of updates to this condition to be submitted in the DCO at Deadline 7. We advise that we are satisfied that this updated condition sufficiently secures the application of additional mitigation. We note that recommended wording for this condition has also been included in The ExA's Schedule of Recommended Amendments to the Applicant’s draft DCO [PD-028], which we consider would also be sufficient to address our concerns. | [5 empty] | Issue Resolved. The Applicant has given Natural England advance sight of updates to this condition to be submitted in the DCO at Deadline 7. We advise that we are satisfied that this updated condition sufficiently secures the application of additional mitigation. We note that recommended wording for this condition has also been included in The ExA's Schedule of Recommended Amendments to the Applicant’s draft DCO [PD-028], which we consider would also be sufficient to address our concerns.
A9 | A12 | Include a condition to secure the maximum hammer energy for piling of monopiles and pin piles(Schedule 10, Part 2). |  | Issue resolved. The Applicant has included maximum hammer energy for piling of monopiles (6,000kJ) and pin piles (3,000KJ) in Schedule 10, Part 2, Condition 15 (7), pg 124; Schedule 11, Part 2 Condition 15 (7) (pg 148); Schedule 12, Part 2, Condition 13 (10) (pg 174); Schedule 13, Part 2, Condition 13 (10) (pg 199). | [17 empty] | Issue resolved. The Applicant has included maximum hammer energy for piling of monopiles (6,000kJ) and pin piles (3,000KJ) in Schedule 10, Part 2, Condition 15 (7), pg 124; Schedule 11, Part 2 Condition 15 (7) (pg 148); Schedule 12, Part 2, Condition 13 (10) (pg 174); Schedule 13, Part 2, Condition 13 (10) (pg 199).
A10 | A13 | Amend the condition such that the Site Integrity Plan for piling must be submitted no later than 6 months prior and no sooner than 9 months prior to piling. (Schedule 10, 16(3)) |  | Issue progressed. Natural England welcome the update that the SIP will be submitted no later than six months prior to the commencement of piling. We continue to advise it is submitted no sooner than nine months prior to piling. |  |  |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. We continue to advise the SIP is submitted no sooner than nine months prior to piling. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. However, we note that this has been recommended within The ExA's Schedule of Recommended Amendments to the Applicant’s draft DCO [PD-028], which is welcome. |  | No change. The Applicant maintains their position that a 9 month restriction is not necessary or proportionate as it is possible that piling programmes will be known in sufficient detail more than 9 months in advance of piling operations [REP7-131]. Natural England highlight that our concern with Site Integrity Plans being submitted signficantly in advance of works taking place is that whilst OWF piling programmes may be known more than 9 months in advance of works, other noisey activities that need to be considered in the in-combination assessment of underwater noise will not be, as they have a much shorter lead in time (e.g geophysical surveys for oil and gas).
A11 | A14 | This condition provides that most of the plans and documents under Condition 15 must be submitted 4 months prior to the works starting. Due to the size and complexity of this project, this time period is not appropriate. Given the large volume of documentation and the often complex nature, we request this be amended to six months prior to commencement. Alternatively, we are willing to discuss the required timing for each plan with the Applicant and the MMO. (Schedule 10, Part 2, 17(1)). |  | Natural England maintain that due to the increasing complexity of construction of large offshore works, six months is now considered an appropriate period for approval of pre-construction documentation and agreement of documents. And in some instances where high risks issues remain unresolved post consent, longer may be required. |  |  |  | Issue resolved. Natural England notes and welcomes the increase in consultation period on pre-construction documentation from four months to six months. | [13 empty] | Issue resolved. Natural England notes and welcomes the increase in consultation period on pre-construction documentation from four months to six months.
A12 | A15 | Update the conditions to include ornithological monitoring. Further amendments may be required on monitoring condition wording in line with MMO advice. (Schedule 10, 20-22) |  | Natural England will provide further comment at Deadline 2. |  |  |  | No change. Natural England does not consider the Construction Programme and Monitoring Plan to be sufficient to secure the necessary monitoring plans. We advise that each thematic area should be named and secured by condition. For DBS this should include monitoring plans for ornithology, benthic, marine processes, marine mammals, and sandeel. Plans should be provided least 4 months (though preferably 6) prior to the first survey. We highlight that this is a standard position and has been standard wording in DCOs since 2010. |  | Issue progressed. We welcome the inclusion of ornithological monitoring as outlined in [REP3-005] and [REP3-007]. Please see Table 1 of our Appendix J [REP3-056] submitted at Deadline 3 for further detail on monitoring. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. |  | Natural England will provide further comment on monitoring conditions at Deadline 9.
A13 | A16 | Schedule 12 It is outlined for Pre-construction plans and documentation under Part 2, Condition 13 (1) (a) (v) of that “any exclusion zones or micro-siting requirements identified pursuant to 13(1)(f)(v) or relating to any habitats of principal importance identified as part of surveys undertaken in accordance with condition 19”; However, 13(1)(f)(v) does not exist. Furthermore, Condition 19 relates to Construction monitoring surveys, not pre-construction surveys (18)(4)(a). Schedule 13 Similar to above, it is outlined under Part 1 Condition 13 (1) (a) (v) that “any exclusion zones or micro-siting requirements identified pursuant to 14(1)(f)(v) or relating to any habitats of principal importance identified as part of surveys undertaken in accordance with condition 18”; However, 14(1)(f)(v) does not exist. Furthermore, Condition 18 relates to Construction monitoring surveys, not pre-construction surveys (18)(4)(a). Amend errors in Schedules 12 and 13 as needed. |  | Issue resolved. The applicant has updated the errors in cross-referencing in the DCO. | [17 empty] | Issue resolved. The applicant has updated the errors in cross-referencing in the DCO.
A14 | A18 | The Maximum Design Parameters for the number of piles that can be installed per day (including simultaneously and concurrently) have not been secured in the DCO/dML. A condition should be included to secure these. |  | Natural England welcomes that a condition has been added to the DCO and will be providing comments at Deadline 2. |  |  |  | Natural England will provide further comment on this condition at Deadline 4. |  | Issue Resolved. Natural England are satisfied that the condition wording captures the WCS as assessed in the original ES, which was then reduced as a result of the Change Request. | [11 empty] | Issue Resolved. Natural England are satisfied that the condition wording captures the WCS as assessed in the original ES, which was then reduced as a result of the Change Request.
A15 | A19 | The Development Consent Order (DCO) does not contain an end date for deployment of cable protection for within and outside of designated sites. Natural England’s standard advice is that cable protection should only be deployed for a maximum period of 10 years from the commencement of operations outside of designated sites. Within any designated sites for benthic features, such as the Dogger Bank SAC, the condition should stipulate that there should be no deployment of cable protection after the completion of construction. |  | Natural England will provide further comment at Deadline 2. |  |  |  | Issue progressed. -We welcome the update to the OOOMP [AS-028] that a separate Marine Licence will be sought during operation for new cable and scour protection (i.e. in areas where no protection was installed during construction). -We do not agree with the Applicants' position that "no new marine licences will be sought for any additional or replenishment protection required during the operational phase in areas that were protected as part of construction, unless such protection would exceed the maximum amounts authorised by the DMLs". See Appendix C2.2 [REP2-066] of Natural England's Deadline 2 submission for further detail. -The Applicant states that the cable and scour protection reports would delineate the end of construction and that relevant DML conditions would be updated. We will provide further comment when these updates are provided. |  | No change. It is outlined in the Applicants’ Reponses to Deadline 2 Documents [REP3-028] that their position remains unchanged, whereby replenishment of cable and scour protection up to the limits set out within the DCO could be deposited within the footprints of deposition established at the construction stage. Natural England maintain our previous advice. |  | We have reviewed the Applicant's position regarding additional and replenishment of cable / scour protection and continue to disagree with it. We do not believe it is in the spirit of the Strategic Compensation Strategy or Marine Recovery Fund. In addition, there is no certainty that the Applicant will be able to use the MRF in the way they propose as the policy is not yet final. Therefore, we advise that they are planning at own risk until the MRF launches and the guidance is published. We are in discussions with DEFRA and DESNZ benthic compensation and MRF teams (respectively) and we will provide further update at Deadline 6. Please see Appendix K5 of Natural England's response to ExQ2 MCP.2.10 in our Deadline 5 submission for further detail |  | No change - Please see Deadline 6 Appendix C6 in relation to meeting the public interests tests. |  | No change. However, we note that within The ExA's Schedule of Recommended Amendments to the Applicant’s draft DCO [PD-028], the ExA has recommended the following additions for cable protection: "(g) Cable protection replenishment outside European marine designated sites with benthic habitats as qualifying features for a maximum period of ten years post construction; (7) No cable protection can be replenished within European marine designated sites with benthic habitats as qualifying features unless otherwise agreed in writing by the MMO in consultation with the relevant statutory nature conservation body and the Maritime and Coastguard Agency. (8) The undertaker is not required to comply with sub-paragraph (7) in a case of emergency." Natural England welcome article (g), however, we advise that for (7), replenishment of cable protection should be subject to a new Marine Licence. See Appendix O7 of Natural England's Deadline 7 submission for further detail. |  | No change. We maintain our advice that that there should be no deployment of cable protection after the completion of construction within any designated sites for benthic features, such as the Dogger Bank SAC. We note that the Applicant maintains their disagreement with this [REP7-130]. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology. |  |  |  | No change. We maintain our advice that that there should be no deployment of cable protection after the completion of construction within any designated sites for benthic features, such as the Dogger Bank SAC. We note that the Applicant maintains their disagreement with this [REP7-130]. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology.
A15.1 | NEW | NEW ISSUE AT DEADLINE 4 | [7 empty] | Natural England request the DCO include a condition or requirement to ensure that the project does not exceed the operational lifetime considered within the Environmental Statement. See cover letter of Natural England's Deadline 4 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - Natural England maintain our previous advice. |  | No change. |  | No change. Natural England maintain our previous advice.
APP-231 8.6 Commitment Register
A16 | A20 | Natural England advise further clarity is required from the Applicant on the purpose of the document before we can provide any detailed nature conservation advice. |  | Issue resolved. The Applicant has confirmed that the Commitments Register is a certified document and has updated the DCO [Rev 03; AS-121]. However, this does not address our concerns with the Current Commitments Register as written. | [17 empty] | Issue resolved. The Applicant has confirmed that the Commitments Register is a certified document and has updated the DCO [Rev 03; AS-121]. However, this does not address our concerns with the Current Commitments Register as written.
A17 | A21 | Natural England advise that any named document should be clear on what the Applicant’s commitments/requirements are, and include any rationale/justification as to why the commitments are being made, even if how they will be delivered is currently unknown. |  | No change. |  |  |  | No change. We maintain our advice that commitments/requirements should be clear and should include any rationale/justification as to why the commitments are being made. In particular, we note for commitment C142: "Any sediment removed from within the Dogger Bank Special Area of Conservation during construction of the authorised scheme must be disposed of within that part of the Dogger Bank Special Area of Conservation which falls within the Order limits". As detailed in Points B17, B44, B45, C21, C33, C34 and further advised in Appx C2.1 [REP2-065], we continue to advise that disposal should be in areas of similar sediment, upstream of the impacts and through the use of a fall/down pipe. Furthermore this commitment is missing cross reference to relevant ES chapter. |  | No change - no new information relevant to this issue has been submitted at this deadline. Whilst some updates re sediment disposal have been made to Points B17, B44, C21, C33, C34 for detail on sediment disposal, these have not been reflected in an updated Commitment Register . |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. The Applicant has indicated [REP5-037] that an updated revision of the Commitments Register (Revision 3) [document reference: 8.6] will be submitted at Deadline 7 alongside the updated Environmental Statement, which will include updated commitments with regards to sediment disposal. We will provide further comments accordingly. |  |  |  | Natural England will provide further comment on the Applicant's updated Commitments Register (rev03) [REP7-102] at Deadline 9.
A18 | A22 | Natural England advise that a Schedule of Mitigation is provided for the DBS projects. If alternative approaches are taken by the Applicant, then any document needs to be more certain on key deliverables. |  | No change. Natural England maintain their concerns around the content and context of the Commitments Register. |  |  |  | No change. Natural England maintain their concerns around the content and context of the Commitments Register. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. |  |  |  | Natural England will provide further comment on the Applicant's updated Commitments Register (rev03) [REP7-102] at Deadline 9.
APP-248 8.24 Outline Offshore Operations and Maintenance (OOOMP) Plan
A19 | A23 | The OOOMP will need updating and a final plan submitted and agreed (in consultation with the relevant SNCB) prior to construction. See A7. |  | No change. |  |  |  | Issue resolved. See Point A7. | [13 empty] | Issue resolved. See Point A7.
A20 | A24 | The definition of maintain should be consistent between the DCO and OOOMP. See A1. |  | No change. |  |  |  | No change. See Point A1. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. |  | No change. |  | No change. |  | Issue resolved. The definition of maintain is linked to the Environmental Statement and also linked in the Outline Offshore Operations and Maintenance Plan (OOOMP) (Revision 3) [REP2- 045] as highlighted by the Applicant [REP7-131] (see A1), |  |  |  | Issue resolved. The definition of maintain is linked to the Environmental Statement and also linked in the Outline Offshore Operations and Maintenance Plan (OOOMP) (Revision 3) [REP2-045] as highlighted by the Applicant [REP7-131] (see A1),
A21 | A25 | Natural England is concerned about what is and is not permitted as part of the DCO/dML through this named plan, in relation to replacement of cable protection over the lifetime of the project and any ‘allowances’ for new cable protection. We advise that further cable protection and scour prevention within Dogger Bank SAC would require a new marine licence, and that outside of the SAC a register should be kept and summited annually to the MMO on any placement of cable protection. This should include the volume, footprint and locations to ensue commitments have been adhered to and indirect impacts to designated sites avoided. See A15, A22. |  | No change - Natural England are reviewing the updated Outline Operations and Maintenance Plan (Rev 02) [AS-028] and will provide further comment at Deadline 2. |  |  |  | No change - please see Point A15 for further information regarding our advice on scour / cable protection replenishment. |  | No change - please see Point A15 for further information regarding our advice on scour / cable protection replenishment. |  | No change - please see Point A15 for further information regarding our advice on scour / cable protection replenishment. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. However, we note that within The ExA's Schedule of Recommended Amendments to the Applicant’s draft DCO [PD-028], the ExA has recommended the following additions for cable protection: "(g) Cable protection replenishment outside European marine designated sites with benthic habitats as qualifying features for a maximum period of ten years post construction; (7) No cable protection can be replenished within European marine designated sites with benthic habitats as qualifying features unless otherwise agreed in writing by the MMO in consultation with the relevant statutory nature conservation body and the Maritime and Coastguard Agency. (8) The undertaker is not required to comply with sub-paragraph (7) in a case of emergency." Natural England welcome article (g), however, we advise that for (7), replenishment of cable protection should be subject to a new Marine Licence. See Appendix O7 of Natural England's Deadline 7 submission for further detail. |  | No change. See A15. |  |  |  | No change. However, we note that within The ExA's Schedule of Recommended Amendments to the Applicant’s draft DCO [PD-028], the ExA has recommended the following additions for cable protection: "(g) Cable protection replenishment outside European marine designated sites with benthic habitats as qualifying features for a maximum period of ten years post construction; (7) No cable protection can be replenished within European marine designated sites with benthic habitats as qualifying features unless otherwise agreed in writing by the MMO in consultation with the relevant statutory nature conservation body and the Maritime and Coastguard Agency. (8) The undertaker is not required to comply with sub-paragraph (7) in a case of emergency." Natural England welcome article (g), however, we advise that for (7), replenishment of cable protection should be subject to a new Marine Licence. See Appendix O7 of Natural England's Deadline 7 submission for further detail.
A22 | A26 | Natural England would welcome MMO views on Table 2-3 and the identification of additional scour prevention and cable protection within Dogger Bank SAC not requiring a marine licence. Additionally, we are concerned that whilst the use of sub-bottom profilers doesn’t currently require a marine licence, there may be in-combination significant impacts as a result of cumulative under water noise pressures that may not be addressed through the OOOMP proposals as written. |  | No change. | [17 empty] | No change.

## B - Marine Physical Environment
Point | Point Number(s) from Appendix B [RR-039] | Taken from Natural England’s Relevant and Written Representations Dogger Bank South (East and West) Appendix B - Marine Physical Environment | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Consultation, actions, progression | RAG Deadline 9 | End of Examination Position | Issue Resolved
B1 | B9 | For indentations on the seabed due to installation vessels, the Maximum Design Scenario (MDS) for anchoring for either DBS E or W in isolation is 244,640m2, however, the maximum total impacted area by anchoring is stated as 22,061m2. It is unclear which of these values is the MDS for seabed area affected by anchoring. This is also the case for the DBS E and DBS W concurrent/sequential scenario MDS. Clarification on the MDS for all construction scenarios is required. (7.8: Table 8-1) |  | Issue progressed. We agree with the clarification provided by the Applicant and advise that Table 8-1 of [APP-080] is updated to resolve this issue. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. Table 4-2 in [AS-141] provides updated MDS for anchoring for the different build scenarios and stages of the development. However, we maintain that relevant application documents should be updated to reflect these changes. |  | No change. We will provide further comment once updates are provided at Deadline 7. | [7 empty] | No Change. The Applicant has submitted an updated ES chapter 8 [REP7-036]. We will provide further comment at Deadline 9. Please see our Deadline 8 cover letter for our approach to the final two deadlines.
B2 | B10 | For changes to bedload sediment transport due to cable protection measures, there are inconsistencies in the total footprint of inter-platform cable protection, number of array/inter-platform cable pipeline/cable crossings, and the total footprint of pipeline/cable crossing material for array cables and inter-platform cables across project build scenarios. Clarification is required. (7.8) |  | Issue resolved. The Applicant has confirmed that the numbers presented are correct.
B3 | B11 | The rationale behind remedial cable protection along 10% of the cable route within Dogger Bank SAC should be provided, with evidence provided to justify a realistic Worst Case Scenario (WCS). Specific locations (informed by acoustic data) of areas requiring cable protection should be identified, including identification of affected features/sensitive habitats. (7.8) |  | No change. |  | No change. See Appendix C2.1 and C2.2 of Natural England's Deadline 2 submission for further detail. |  | No change. No further information or rationale has been provided, and in [AS-141] there is no change to the 10% cable protection requirement for the array and inter-platform cables. |  | No change - the Applicant has confirmed that no further revisions will be made to the CBRA within Examination timeframes [REP3-028]. We maintain our advice that further information and rationale is provided for the WCS for cable protection within DB SAC. We advise that it would be helpful if the Applicant could provide indicative locations for remedial cable protection requirements based on currently available information. Please see Appendix B4 to our Deadline 4 submission for further information including our concerns regarding seabed mobility and cable burial risk on Dogger Bank. |  | No change. We maintain our previous advice. |  | No change. Please see Appendix C6 of Natural England's Deadline 6 response in relation to public interest tests |  | No change. The Applicant has indicated [REP5-036, MCP 2.9] that there will be no changes to the worst-case scenario assumption of a maximum of 10% of the cable route within DB SAC requiring cable protection. We maintain our previous advice. |  | No change. We maintain our previous advice. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology. |  |  |  | No change. We maintain our previous advice. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology.
B4 | B12 | The WCS for remedial cable protection assumes 20% of the export cable route will require remedial protection outside of Dogger Bank SAC. A realistic worst-case scenario on the locations for cable protection should be identified (informed by geophysical and geotechnical data). We also advise that the rationale (including supporting evidence) for this requirement should be provided. (7.8) |  | No change. We understand the Applicant is updating the Cable Burial Risk Assessment [APP-244]. We will provide further comment when this is submitted into Examination. |  | No change. See Appendix C2.1 and C2.2 of Natural England's Deadline 2 submission for further detail. |  | No change. No further information or rationale has been provided and in [AS-141], there is no change to the 20% of the export cable length requiring surface laid cable protection. We also seek clarification on whether the results of the ECR Preliminary CBRA provided in Appendix B of [REP2-040] alter this requirement (see B49). |  | No change - we maintain our advice that further information and rationale is provided for the WCS for cable protection outside of DB SAC, however the Applicant has confirmed that no further revisions will be made to the CBRA within Examination timeframes [REP3-028]. We therefore advise that it would be helpful if the Applicant could provide indicative locations for remedial cable protection requirements based on currently available information. See Appendix B4 of our Deadline 4 submission for further detail on bedform migration rates and directions, seabed mobility, and sediment transport. |  | No change. We maintain our previous advice. |  | No change. Natural England notes that in [REP5-040] the Applicant states that burial of export cables may not practicably be achievable due to the presence of chalk bedrock in the shallow subsurface. However, the known and expected locations where cable protection will be required have not been provided. Whilst, the Applicant has indicated [REP5-037] that preliminary cable protection locations for the Export Cable Route are presented in Appendix B BAS Tables of Appendix 2 of the Cable Statement (Revision 4) [REP4-050], this Appendix is difficult to interpret and does not contain finalised information (n.b we assume the reference should be to Appendix F of Appendix B of the Cable Statement). See Appendix B6 of Natural England's Deadline 6 submission for further detail |  | Issue progressed. The Applicants have updated the Cable Statement [REP6-044] with a figure showing indicative locations of protection along the ECC (outside of DB SAC). This has been based on the 2024 Burial Assessment Study in [REP6-044], which they have highlighted is preliminary and indicative only. However, the WCS for external cable protection (20% of the cable route) outside DB SAC has not been refined down based on this latest information. |  | No change. We maintain our previous advice. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology. |  |  |  | No change. We maintain our previous advice. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology.
B5 | B13 | For the Operational impact “Cable Repairs and Reburial”, the activity has been described, but no associated LSE pathways have been included. The Applicant should specify the LSEs and provide the MDS for each activity during operation (for all build scenarios). The WCS impact on each MPA and affected features should also be provided for direct and indirect effects. (7.8: Table 8-1) |  | Issue progressed. The Applicant has confirmed that text was missing from the table. We advise that Table 8-1 of [APP-080] is updated accordingly. |  | No change. Whilst an updated Outline offshore Operations and Maintenance Plan [AS-028] has been provided, this has not addressed this issue. |  | Issue progressed. The Applicant has provided the WCS volume of sediment displaced during O&M activities in the Array Areas and Offshore Export Cable Corridor in [AS-141], however the WCS impact needs to be provided for any affected MPAs. |  | No change - updates to ES documents are required to resolve. We will provide further comment once updates are provided at Deadline 7. |  | Issue progressed. The Applicant has provided worst-case operational impacts of cable repairs and reburial on relevant protected sites in Appendix A of [REP4-088]. We understand that updates to ES documents will be submitted at Deadline 7 and will provide further comment accordingly. | [5 empty] | No Change. The Applicant has submitted an updated ES chapter 8 [REP7-036]. We will provide further comment at Deadline 9. Please see our Deadline 8 cover letter for our approach to the final two deadlines.
B6 | B14 | Clarification is needed on the WCS volumes for sandwave levelling/seabed for the export cable route. (7.5, 7.8) |  | Issue progressed. The Applicant has clarified that the sandwave clearance volume presented was incorrect. We advise that Table 8-1 of [APP-080] is updated accordingly. |  | No change. |  | Issue progressed. In [AS-141] the maximum seabed area and volume disturbed by sandwave levelling within the Offshore Export Cable Corridor has been clarified. This has also been updated in the Project Description [REP1-010].' However, we advise that all relevant plans should be updated to reflect the revised parameters from the Change Request, including ES chapters. |  | No change - updates to ES documents are required to resolve. We will provide further comment once updates are provided at Deadline 7. | [7 empty] | No Change. The Applicant has submitted an updated ES chapter 8 [REP7-036]. We will provide further comment at Deadline 9. Please see our Deadline 8 cover letter for our approach to the final two deadlines.
B7 | B16 | We advise that a commitment is made and secured in the DCO to remove all on and above seabed infrastructure associated with the development within benthic designated sites (excluding cable crossings). Without this, the WCS should assess the impacts of leaving assets permanently in situ rather than restricting to the operational lifetime. (7.8) |  | No change. |  | No change - See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. Natural England maintain our previous advice. See Appendix C4 of our Deadline 4 submission for further detail. |  | No change. We have reviewed the Applicant's position regarding infrastructure decommissioning and continue to disagree with it. We do not believe it is in the spirit of the Strategic Compensation Strategy or Marine Recovery Fund. In addition, there is no certainty that the Applicant will be able to use the MRF in the way they propose as the policy is not yet final. Therefore, we advise that they are planning at own risk until the MRF launches and the guidance is published. We are in discussions with DEFRA and DESNZ benthic compensation and MRF teams (respectively) and we will provide further update at Deadline 6. |  | No change - Please see Deadline 6 Appendix C6 for further detail |  | Issue progressed. The Applicants have committed [REP6-044] to consider removability of cable protection as part of the development of the final Cable Statement and Decommissioning Programme to be produced for submission to the SoS pre construction. Whilst this is welcome, it is not sufficient to resolve concerns regarding the lack of a full commitment to decomissioning. |  | No change. We maintain our previous advice. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology. |  |  |  | No change. We maintain our previous advice. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology.
B8 | B18 | The Preliminary CBRA is based on the Projects’ Red Line Boundary (RLB) at PEIR stage, which has been significantly revised. We advise that a more up-to-date and detailed pre-consent cable burial assessment should be provided, based on the most recent RLB and turbine/cable layout. This should use project specific geotechnical data and/or data from constructed offshore windfarms to consider the likelihood of burial success to inform realistic MDS parameters for cable protection requirements. (8.20) |  | No change. We understand the Applicant is updating the Cable Burial Risk Assessment [APP-244]. We will provide further comment when this is submitted into Examination. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue progressed but not resolved. The Applicant has provided an updated Cable Statement which includes an updated Cable Burial Risk Assessment for the Export Cable Route [REP2-040], but not for the Array Areas. If available, this should be provided as well. Please see Deadline 3 Appendix B3 |  | No change. We maintain our previous advice. We note that the Applicant has confirmed in [REP3-028] that there will be no updates to the existing CBRA during Examination. Therefore we will not provide further comment on this issue unless the Applicant provides updates to the CBRA. | [7 empty] | No change. Please see Points B3 and B4 regarding 10%/20% WCS within/outside DB SAC of the cable route requiring protection. |  |  |  | No change. Please see Points B3 and B4 regarding 10%/20% WCS within/outside DB SAC of the cable route requiring protection.
B9 | B19 | We advise that identification of regional scale sediment transport pathways is an important part of the baseline characterisation. Sediment transport pathways have been identified only for the landfall, adjacent coastline, nearshore and westernmost section of the Offshore Export Cable Corridor (OECC). We advise the Applicant to establish or infer sediment transport pathways for the remainder of the OECC and array areas. (7.8.1) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. We continue to advise that the Applicant should seek to establish a baseline characterisation of the sediment transport pathways that may be affected by the presence of the DBS projects. |  | No change - no new information relevant to this issue has been submitted at this deadline. See our response to Examiner's Question (ExQ) MCP.1.2 for further detail in Appendix K of our Deadline 3 submission for further detail. |  | No change. Please see Appendix B4 of Natural England's Deadline 4 submission for further detail. |  | No change. We maintain our previous advice. Please see our Deadline 4 submission [REP4-122] for further information. |  | The Applicant has provided the requested further information [REP5-040] on sediment transport pathways offshore of 35km along the Offshore Export Cable Corridor, and on/around Dogger Bank, which is welcome. This issue is therefore resolved. | [7 empty] | The Applicant has provided the requested further information [REP5-040] on sediment transport pathways offshore of 35km along the Offshore Export Cable Corridor, and on/around Dogger Bank, which is welcome. This issue is therefore resolved.
B10 | B20, B36 | We consider the beach elevation change data presented in the ES from 2008-2015 to be out of date. More recent beach/shore platform elevation change data should be sought and analysed (alongside the older data collected), to inform the cable burial/asset integrity assessment and assess coastal vulnerability through the lifetime of the Projects. (7.5, 7.8). Whilst there is a commitment to carry out beach profile change monitoring if trenchless technique exit pits are located within the intertidal area, we advise that beach profile change monitoring should be carried out regardless to confirm beach recovery and support predictions regarding impacts to Holderness cliffs, and also monitor cable burial success and asset integrity over the lifetime of the Projects. (7.8) |  | Issue resolved. We are satisfied that information provided in AS-116 (10.38 Coastal Change Technical Note Rev 01) is sufficient to demonstrate that the cables will be buried at sufficient depth to prevent exposure for the lifetime of the project. See Appendix B1 of Natural England's Deadline 1 submission for further detail. | [17 empty] | Issue resolved. We are satisfied that information provided in AS-116 (10.38 Coastal Change Technical Note Rev 01) is sufficient to demonstrate that the cables will be buried at sufficient depth to prevent exposure for the lifetime of the project. See Appendix B1 of Natural England's Deadline 1 submission for further detail.
B11 | B15, B21, B22 | We advise that the modelling for changes to the wave and tidal regime should be updated to reflect the Option 1 turbine layout and removal of gravity base foundations for turbines from the project envelope. The outputs of the more realistic layout out scenario (Option 1) should be carried through to the assessment. (7.8, 7.8.8.3) |  | No change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change |  | Issue progressed. The Applicant has updated the Marine Physical Processes Modelling [REP2-018] to reflect the changes in the Project Design Envelope (i.e. removal of GBS foundations and reduction in the number of offshore platforms). The updated wave and hydrodynamic modelling has also been carried out for baseline, Option 1 and Option 2. We advise that all relevant documents such as relevant ES chapters be updated to reflect this. We also continue to advise that Option 1 is a more realistic layout scenario and should be carried through to such updated assessment. |  | No change - no new information relevant to this issue has been submitted at this deadline. Furthermore, updates to ES documents are required to resolve, we will provide further comment once updates are provided at Deadline 7. | [7 empty] | No Change. The Applicant has submitted an updated ES chapter 8 [REP7-036]. We will provide further comment at Deadline 9. Please see our Deadline 8 cover letter for our approach to the final two deadlines.
B12 | B23 | We advise that Table 8-20 of [APP-080] should be revised using the 95% confidence level from the revised National Coastal Erosion Risk Mapping project. Cliff erosion is relevant in terms of reviewing whether construction impacts have altered baseline cliff erosion rates. Therefore, this should be done as part of the post construction monitoring rather than strictly being needed for the ES. |  | Issue progressed. See Appendix B1 of Natural England's Deadline 1 submission for further detail. | [5 empty] | Issue progressed. Natural England welcome that updated coastal erosion predictions have been provided. We advise that these updates are included in the updated ES documents to be provided at Deadline 7. See Appendix B4 of Natural England's Deadline 4 submission for further detail. | [7 empty] | No Change. The Applicant has submitted an updated ES chapter 8 [REP7-036]. We will provide further comment at Deadline 9. Please see our Deadline 8 cover letter for our approach to the final two deadlines.
B13 | B24 | The ES identifies a significant secondary wave shadow component from the south to south-south-west (S-SSW) where the spatial extent, and potential impacts have not been assessed. The Applicant should provide details of the spatial extent of any wave shadow effects extending from DBS intoDogger Bank A. The implications of these wave shadow effects for the marine physical environment over the lifetime of the Projects should also be considered. (7.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. We continue to advise that it would be useful if the Applicant could provide the revised model output for waves approaching south to south-south-west (S-SSW). This will help inform understanding of the potential for in-combination effects. |  | No change. As noted in Appendix L of Natural England's Deadline 3 submission, it would be useful to include waves approaching from the south/southwest in the wave modelling assessment. This would help inform understanding of potential overlapping effects extending towards nearby OWFs (i.e. Dogger Bank A). Moreover, cumulative and project-specific changes to the wave climate over the lifetime of the Project need to be fully considered. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. We maintain our previous advice. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. This information has not been provided by the Applicant and therefore we cannot advise the SoS on level of risk. We reiterate our earlier advice that the implications of these wave shadows on their area of overlap with Dogger Bank A&B are unclear. Further consideration is needed to increase understanding of the implications of the predicted long-term changes in significant wave height on seabed sediment composition, seabed level/morphology, and seabed habitats within the overlap area with Dogger Bank A&B. The potential for cumulative effects are also unclear. |  |  |  | No change. This information has not been provided by the Applicant and therefore we cannot advise the SoS on level of risk. We reiterate our earlier advice that the implications of these wave shadows on their area of overlap with Dogger Bank A&B are unclear. Further consideration is needed to increase understanding of the implications of the predicted long-term changes in significant wave height on seabed sediment composition, seabed level/morphology, and seabed habitats within the overlap area with Dogger Bank A&B. The potential for cumulative effects are also unclear.
B14 | B25 | The potential impacts of extending North Turnpikes Road to the beach/cliffs are unclear. We advise that further details are provided on the emergency intertidal access design including coastal morphology and sensitive habitats that may be affected by its presence. Any environmental impacts associated with its construction, operation, and subsequent removal should be fully considered and assessed. (7.5) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change - See Appendix B2 of Natural England's Deadline 2 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. As outlined in [REP3-028], the Applicant does not intend to finalise the design of the emergency intertidal access or provide a pollution contingency plan in advance of receiving consent and / or appointing a Principal Contractor. We continue to advise that a full outline contingency plan should be included at the point of consent. |  | No change - we maintain our previous advice. See Natural England's response to ExQ2 MCP.2.1 in Appendix K5 of Natural England's Deadline 5 submission for further detail. |  | No change. Whilst we understand from the Applicant's response to ExQ2 [REP5-036] that they will be updating the OCoCP to include that the Drilling Fluid Management Plan would be agreed with relevant bodies including Natural England, we maintain our previous advice. |  | No change. The Applicant maintains their position [REP6-051]. We maintain our previous advice. |  | No change. The Applicant has submitted an updated 8.9 OCoCP (Rev05) [REP7-106] and Table 3-2 has been updated to include Natural England as a consultee for approval of the Drilling Fluid Breakout Management Plan. However, they do not intend to finalise the design of the emergency intertidal access or provide a pollution contingency plan in advance of receiving consent and / or appointing a Principal Contractor. We threfore maintain our previous advice (MCP.2.1, [REP5-062]). In line with North Falls OWF and others in examination, we would expect to see an outline HDD management plan. As this has not been provided we cannot advise on the level of risk, but recognise landfall is outwith a designated site. If the SOS is minded to consent, the provision of this plan prior to construction should be secured. This could either be provided as standalone document or as part of the landfall construction method statement. |  |  |  | No change. The Applicant has submitted an updated 8.9 OCoCP (Rev05) [REP7-106] and Table 3-2 has been updated to include Natural England as a consultee for approval of the Drilling Fluid Breakout Management Plan. However, they do not intend to finalise the design of the emergency intertidal access or provide a pollution contingency plan in advance of receiving consent and / or appointing a Principal Contractor. We threfore maintain our previous advice (MCP.2.1, [REP5-062]). In line with North Falls OWF and others in examination, we would expect to see an outline HDD management plan. As this has not been provided we cannot advise on the level of risk, but recognise landfall is outwith a designated site. If the SOS is minded to consent, the provision of this plan prior to construction should be secured. This could either be provided as standalone document or as part of the landfall construction method statement.
B15 | B26 | Jack up barges, other vessels, equipment, and infrastructure may be used for trenchless landfall exit works during the different development phases. The Applicant should consider and assess all potential impacts to seabed and coastal morphology that may arise due to trenchless landfall works during the lifetime of the Projects. (7.8) |  | No change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change |  | No Change. Whilst we acknowledge that in [AS-141], the short trenchless crossing at landfall has been removed from the proposed works, thus avoiding the need for exit pits in the intertidal area; further assessment of the potential impacts from landfall works is required. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. The Applicant has stated in [REP4-088] that the change to project design (removal of short trenchless crossing at landfall) results in a change to the receptors assessed and that such assessment in relation to landfall works will be updated in a landfall technical note to be submitted at Deadline 5, and included in the updated ES chapter to be submitted at Deadline 7. We will provide comment accordingly. |  | No change. Natural England are unclear if the landfall technical note referred to at Deadline 5 was submitted as intended. |  | No change. The Applicant has clarified [REP6-052] that an updated version of Chapter 8 - Marine Physical Environment [APP-080] will be submitted at Deadline 7, and will include the updated landfall assessment work as detailed in the Assessment of Coastal Processes at the Dogger Bank South Landfall [REP4-088] report issued at Deadline 5. We will provide comment accordingly. |  | No Change. The Applicant has submitted an updated ES chapter 8 [REP7-036]. We will provide further comment at Deadline 9. Please see our Deadline 8 cover letter for our approach to the final two deadlines.
B16 | B27, B66 | Clarification is needed on what material will be used to backfill trenches for landfall cable installation activities if the excavated material has been redistributed. We advise that sediment should be stored in such a way that it cannot be washed away. (7.8, 8.18) |  | No change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change |  | No Change. Whilst we acknowledge that in [AS-141], the short trenchless crossing at landfall has been removed from the proposed works, thus avoiding the need for exit pits in the intertidal area; further assessment of the potential for sediment to be lost should excavation at the exit pit location be required. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. We maintain our previous advice. As stated in [REP4-088], the Applicant will be submitting a technical note detailing further modelling undertaken which is focussed on wave generated currents given they are the principal driver of sediment movement in the vicinity of the Projects’ landfall location. We will provide further comment accordingly. |  | No change. The Applicant discusses only excavated exit pit material in the latest coastal processes assessment [REP5-040], not cable trenching excavated material. See Appendix B6 of Natural England's Deadline 6 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. The Applicant has confirmed that excavated material would be stored alongside the exit pits [REP6-052]. We note that the Applicant has committed to the post installation monitoring through an updated Table 1-2 of the IPMP (Rev05) [REP7-116] to include "Post-construction monitoring will confirm recovery and backfilling of the seabed at the trenchless crossing exit pits". However, the use of imported material has not been assessed as would be expected as part of an operation and maintenance activity at the time of consent. Therefore, if it is found that backfill is incomplete then Natural England advises that a separate marine licence would be required should imported material be required. We highlight this advice is not reflected in [REP7-131] and does not align with the Applicants position. We continue to advise that this scenario may be preventable through the use of a barge to store excavated material to be used to backfill. |  |  |  | No change. The Applicant has confirmed that excavated material would be stored alongside the exit pits [REP6-052]. We note that the Applicant has committed to the post installation monitoring through an updated Table 1-2 of the IPMP (Rev05) [REP7-116] to include "Post-construction monitoring will confirm recovery and backfilling of the seabed at the trenchless crossing exit pits". However, the use of imported material has not been assessed as would be expected as part of an operation and maintenance activity at the time of consent. Therefore, if it is found that backfill is incomplete then Natural England advises that a separate marine licence would be required should imported material be required. We highlight this advice is not reflected in [REP7-131] and does not align with the Applicants position. We continue to advise that this scenario may be preventable through the use of a barge to store excavated material to be used to backfill.
B17 | B28 | Removal or modification of sandwaves within the OECC and array areas could adversely affect nearby sandbanks, seabed topography, and affect flow and sediment transport patterns. All efforts should be made to avoid areas of sandwaves and/or minimise the need for sandwave levelling/pre-sweeping by micro-routing. If possible, dredged material should be placed to aid natural infilling of trenches. Best practice should be followed to assess and minimise potential impacts to sandwave/sandbank systems. The proposed pre- and post-construction monitoring should be used to assess geomorphological recovery after cable installation. (7.5, 7.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change - See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue progressed. The Applicant has said that in commitment C089 of the Commitments Register, that cable route selection/micro-siting will help avoid areas of seabed that are challenging eg. sandwaves. Can the Applicant confirm if this commitment will enable reduction of the MDS for sandwave levelling? In line with our advice in Appendix B4 to our Deadline 4 submission, we advise that the Applicant still needs to more accurately assess bedform migration direction and rates. The Applicant has also stated [REP3-028] that they can commit to depositing sediment on like sediment (within Dogger Bank SAC) and has indicated that an updated Cable Statement will be provided at Deadline 4 [REP3-028] to reflect such changes. We will provide further comment accordingly, but highlight that as with other developments currently in Examination which are impacting on Annex I sandbanks, commitments to desposit adjacent to and updrift of the sandbank using a fall/down pipe is also required to fully mitigate impacts. |  | Issue progressed. Whilst stronger commitments to mitigation are required, Natural England is satisfied with the assessment for sandwave clearance in the export cable corridor in relation to suspended sediment concentrations. See Appendix B5 of Natural England's Deadline 5 submission for further detail. |  | Issue progressed. Natural England remains concerned that the mitigation measures are not being fully implemented. And that monitoring needs to be secured in the IPMP. We believe that this issue is resolvable in examination. Please see Appendix B6 of Natural England's Deadline 6 submission for further detail. |  | Issue progressed. The Applicant has indicated [REP6-052] that they will include depositing like sediment on like sediment in an updated Commitments Register to be submitted at Deadline 7. -The Applicant has committed [REP6-044] to providing a plan as an Appendix to the Final Cable Statement(s) (should sand wave levelling be required) which will provide details on sandwave levelling, deposition, and recovery. -With regards to micro-routing, sandwave crossing and cable installation, the Cable Statement [REP6-044] has been updated to clarify that route selection and micro-siting of the cables will take place, sandwave crossing will occur at an angle as close to 90 degrees to minimise dredge volumes and that cable installation should occur as soon as possible after levelling, in line with best practice, which is welcomed. -The Applicants have also committed to pre and post construction geophysical surveys in the IPMP, but consider that there is insufficient information available to define hypotheses as a detailed sand wave characterisation study would be required which will be undertaken post-consent. We advise that the provision of a sandwave characterisation study should be explicitly included in the IPMP and secured in the DCO. -There is no change to the Applicant's position on the use of a fall pipe for depositing dredged sediment and updrift of the sandwave - we maintain our advice on this. |  | No Change. The commitment to depositing like on like sediment in Commitments Register (rev03) [REP7-102] under Ref C192 is welcomed. However, it is unclear whether the Applicant will be providing a sandwave characterisation report as advised in this point at Deadline 7. In addition, we note [REP7-131] that there is no change to the Applicant's position on the use of a fall pipe for depositing dredged sediment and updrift of the sandwave - we maintain our advice on this. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology for further detail regarding this. |  |  |  | No Change. The commitment to depositing like on like sediment in Commitments Register (rev03) [REP7-102] under Ref C192 is welcomed. However, it is unclear whether the Applicant will be providing a sandwave characterisation report as advised in this point at Deadline 7. In addition, we note [REP7-131] that there is no change to the Applicant's position on the use of a fall pipe for depositing dredged sediment and updrift of the sandwave - we maintain our advice on this. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology for further detail regarding this.
B18 | B29 | Model results show 'wave shadows' with potential reductions in significant wave height of up to 0.7m, with the largest effects due to the offshore platforms in the Array Areas. The implications of the predicted changes to wave climate/height over the lifespan of the Projects need to be fully considered in terms of impacts to the seabed sediment composition, sediment mobility, and seabed morphology of the Dogger Bank SAC. (7.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. Whilst we will be providing our full comments on the Change Request at Deadline 3, we note that the maximum significant wave height reduction values do not appear to have changed in the revised Marine Physical Processes Modelling Technical Report (Rev 02) [AS-136]. We seek clarification from the Applicant on whether the wave modelling has been revised in line with the changes to the Project Design Envelope. |  | Issue progressed. The Applicant has updated the Marine Physical Processes Modelling [AS-136, REP2-018] to reflect the changes in the Project Design Envelope. This partially addresses our initial concern. However, we wish to see consideration and assessment of wave shadow effects due to waves approaching from the south/southwest and cumulative effects with nearby OWFs (e.g. Dogger Bank A). See Appendix L of Natural England's Deadline 3 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - we maintain our previous advice. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. The Applicant maintains their position [REP6-051]. We maintain our previous advice. |  | No change. As previously advised, we wish to see consideration and assessment of wave shadow effects due to waves approaching from the south/southwest and cumulative effects with nearby OWFs (e.g. Dogger Bank A). This information has not been provided by the Applicant and we therefore cannot advise the SoS on level of risk. Further to our advice on B13 above, further information is needed to increase understanding of the implications to seabed sediment composition, seabed level/morphology, and seabed habitats due to long-term changes in significant wave height and the wave base. |  |  |  | No change. As previously advised, we wish to see consideration and assessment of wave shadow effects due to waves approaching from the south/southwest and cumulative effects with nearby OWFs (e.g. Dogger Bank A). This information has not been provided by the Applicant and we therefore cannot advise the SoS on level of risk. Further to our advice on B13 above, further information is needed to increase understanding of the implications to seabed sediment composition, seabed level/morphology, and seabed habitats due to long-term changes in significant wave height and the wave base.
B19 | B30 | Hydrodynamic model results show lower current speeds (shadow effects) along the western boundary of the Arrays, but also increased current speeds inside the Arrays. Similarly, there are shadow areas in the difference plots for bed shear stress with areas of reduced bed shear stress adjacent to the western DBS W Array boundary and to the west and east of the DBS E Array boundary, but with areas of increased bed shear stress within the Arrays. The implications of predicted changes to current speeds and bed shear stress over the lifespan of the Projects need to be fully considered in terms of seabed sediment composition, sediment mobility, and seabed morphology of the Dogger Bank SAC. (7.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. We continue to advise that the Applicant needs to consider how the predicted changes (reductions and increases) in tidal current speeds and bed shear stress will affect patterns of erosion and deposition and seabed morphology within and adjacent to the arrays over the 30 year project lifespan. Furthermore, consideration should be given to changes in seabed heterogeneity over the lifespan of the project. |  | No change. Natural England maintain our previous advice. |  | No change. Natural England maintain our previous advice. |  | No change. We continue to advise that the Applicant needs to consider how the predicted changes (reductions and increases) in tidal current speeds and bed shear stress will affect patterns of erosion and deposition and seabed morphology within and adjacent to the arrays over the 30 year project lifespan. Furthermore, consideration should be given to changes in seabed heterogeneity over the lifespan of the project. |  | Issue progressed. The Applicant has given further consideration to bed shear stresses within the array areas in the latest coastal processes assessment [REP5-040]. However, the predicted changes in bed shear stress due to interactions with Project infrastructure need to be used to assess potential changes in seabed sediment composition and distribution, sediment dynamics, seabed morphology over the lifetime of the Projects. The influence of waves should also be considered for those locations above the wave base. These results will also need to be considered in terms of depositing like-for-like dredged sediment back into the SAC [REP4-051]. See Appendix B6 of Natural England's Deadline 6 submission for further detail. |  | No Change. The Applicant has indicated [REP6-052] they will provide an updated assessment of changes to bedload sediment transport over the operational lifetime of the Projects in an updated version of Chapter 8 Marine Physical Environment [APP-080] to be submitted at Deadline 7. We will provide comment accordingly. |  | The Applicant has submitted an updated ES chapter 8 [REP7-036]. We will provide further comment at Deadline 9. Please see our Deadline 8 cover letter for our approach to the final two deadlines.
B20 | B31 | The potential for cumulative effects at landfall due to overlapping construction activities between DBS and Dogger Bank D should be considered and assessed. (8.8.3.2) |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change |  | No change. This has not been addressed in the Change Request documents. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. We maintain our previous advice. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | The DBD PEIR is now in the public domain through a Section 42 consultation. Whilst we welcome provision by the Applicant at Deadline 7 of the document '17.6 The Applicant’s Consideration of the Dogger Bank D Preliminary Environmental Information Report' [REP7-133], Natural England are currently in the process of reviewing the PEIR and therefore cannot provide further comment on the appropriateness of [REP7-133] at this time. We therefore maintain the advice provided at Deadline 7 [REP7-154], that when determining the DBS windfarms, the Secretary of State considers Dogger Bank D in their HRA. |  |  |  | The DBD PEIR is now in the public domain through a Section 42 consultation. Whilst we welcome provision by the Applicant at Deadline 7 of the document '17.6 The Applicant’s Consideration of the Dogger Bank D Preliminary Environmental Information Report' [REP7-133], Natural England are currently in the process of reviewing the PEIR and therefore cannot provide further comment on the appropriateness of [REP7-133] at this time. We therefore maintain the advice provided at Deadline 7 [REP7-154], that when determining the DBS windfarms, the Secretary of State considers Dogger Bank D in their HRA.
B21 | B32 | Dogger Bank SAC should be included as a receptor in the Marine Physical Environment EIA. It should also be identified (along with other relevant designated sites) on Marine Physical Environment maps to inform understanding of potential impacts. (7.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No Change. We advise that whilst marine physical processes receptors are primarily morphological or water column features, designated sites may also be affected by physical changes to their integrity and special features thus it is appropriate to identify them as receptors and to be included in the marine physical processes impact assessment. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. The Applicant has indicated [REP3-028] that whilst DB SAC was previously included as a receptor in PEIR, it was removed following consultation in an ETG meeting held on 29th Jan 2024. We have reviewed the minutes from this meeting and cannot see that it was discussed. Natural England maintain our previous advice. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. We continue advise that DB SAC should be included in the list of receptors and EIA in the next revision of ES Chapter 8 - Marine Physical Environment [APP-080] due to be submitted at Deadline 7. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. We continue to advise that DB SAC should be included in the list of receptors and EIA. The Applicant maintains their position that it would be erroneous to assess the receptor in the marine physical environment chapter in terms of its SAC designation which is related to habitats and instead this is considered in the RIAA HRA Part 2 of 4 – Annex I Offshore Habitats and Annex II Migratory Fish. We maintain our advice and therefore agree to disagree with the Applicant. It will be for the SoS to determine how to consider this issue |  |  |  | No change. We continue to advise that DB SAC should be included in the list of receptors and EIA. The Applicant maintains their position that it would be erroneous to assess the receptor in the marine physical environment chapter in terms of its SAC designation which is related to habitats and instead this is considered in the RIAA HRA Part 2 of 4 – Annex I Offshore Habitats and Annex II Migratory Fish. We maintain our advice and therefore agree to disagree with the Applicant. It will be for the SoS to determine how to consider this issue
B22 | B33, B41 | We do not agree with the conclusions of the EIA or cumulative effects assessments for the Flamborough Front during Operation and Maintenance. We advise the Applicant should seek to reduce impacts as much as possible through consideration of the placement of foundation structures and reducing the WCS for foundation structures within Array Areas. Owing to the ecological importance of the Flamborough Front, and emerging evidence that suggests large OWF clusters (i.e. Dogger Bank) may result in substantial impacts on stratification, currents, and sediment resuspension; we also advise that the Applicant should commit to monitoring potential changes to stratification, currents, and productivity (pre-construction, post-construction, lifetime). The results of monitoring should be combined with those from other nearby OWFs and with up-to-date research such as from the University of Hull. (7.8, 8.7.3.4) |  | No change. Natural England will provide further comment at Deadline 3 on the In Principle Monitoring Plan (IPMP) [APP-247], in order to take into account all of the updates from Change Request 1, the Defra Marine Noise Policy paper and updated ornithology assessments. |  | No change. |  | No change. See Appendix J and our response to ExQ MCP.1.1.0 in Appendix K of Natural England's Deadline 3 submission for further detail. |  | No change. The Applicant has indicated that a technical note summarising the potential effects of the Projects on the Flamborough Front and how other offshore wind farm projects have assessed their potential impacts on the feature will be provided at Deadline 4 [REP3-027]. We maintain the advice provided at Deadline 3 with respect to monitoring requirements. |  | Issue progressed. There is no change to the significance of effect (in EIA terms) in the re-assessment of impacts to Flamborough Front as provided in [REP4-092] 14.7 Review of Flamborough Front. Whilst we welcome the proposed monitoring, we continue to advise that a precautionary approach be adopted for the impact assessment. See Appendix B5 of Natural England's Deadline 5 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue progressed. The Applicant has outlined in [REP6-052] that they will consider The Crown Estate FRONTWARD project during the pre-construction stage of the in-principal monitoring to establish the duration and frequency of occurrence of the Flamborough Front within the Array Areas, to inform the design of post-construction monitoring. The Applicant maintains their position on their assessment of significance of effect (in EIA terms) of impacts to the Flamborough Front. Natural England maintain our previous advice on this. |  | Issue progressed. We welcome the updated IPMP (rev 05) [REP7-116] which outlines that the Applicant will "Consider the data published from The Crown Estate FRONTWARD Project, and any new research or data that has become available since DCO submission, to inform the pre-construction baseline". With regards to our concerns on the assessment of significance of effect (in EIA terms) of impacts to the Flamborough Front, Natural England maintain our previous advice on this. Natural England advises that as a minimum an approach similar to Hornsea Project four is adopted requiring the Applicant to provide updated modelling for the to be built project prior to construction and monitoring is secured. Please see Appendix P8 of our Deadline 8 submission for further detail. |  |  |  | Issue progressed. We welcome the updated IPMP (rev 05) [REP7-116] which outlines that the Applicant will "Consider the data published from The Crown Estate FRONTWARD Project, and any new research or data that has become available since DCO submission, to inform the pre-construction baseline". With regards to our concerns on the assessment of significance of effect (in EIA terms) of impacts to the Flamborough Front, Natural England maintain our previous advice on this. Natural England advises that as a minimum an approach similar to Hornsea Project four is adopted requiring the Applicant to provide updated modelling for the to be built project prior to construction and monitoring is secured. Please see Appendix P8 of our Deadline 8 submission for further detail.
B23 | B35, B50 | We cannot rule out an adverse effect on integrity for the Humber Estuary SAC due to the current condition allowing 10% of the cumulative export cable length to be protected from 350m seaward of MLWS to the 10m depth contour. We advise that alternative methods of cable burial and/or protection should be explored in line with the mitigation hierarchy, to remove or reduce the need for cable protection between MLWS and the 10m contour. If cable protection is not removed from the project envelope, the commitment and associated DCO condition should be refined to only placing cable protection within -9 and -10m below LAT, as the Applicant has already identified this as being the area potentially requiring cable protection. See also C13. (6.1, 7.5, 7.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change - See Appendix B2 of Natural England's Deadline 2 submission for further detail. |  | No change. Please see B49 with respect to further action needed in response to the Applicant's updated Cable Statement [REP2-040] which could progress this issue. |  | Issue progressed. We welcome the Applicant's clarification [REP3-028] that the approximate length of cable protection measures within the nearshore would be 116m per cable trench (assuming the cables were laid in a straight line) and will only protrude 50cm above the seabed. However, we require clarity on whether this is secured in a plan/document. The Applicants also propose further modelling to demonstrate that the WCS nearshore cable protection will have a limited effect on the area and that a technical note will be provided at Deadline 5 regarding the potential effects of cable protection measures on sediment transport in the nearshore environment. See Appendix B4 of Natural England's Deadline 4 submission for further detail. |  | No change. The Applicant has indicated [REP4-088] that a technical note will be provided at Deadline 5 regarding the potential effects of cable protection measures on sediment transport in the nearshore environment. We will provide further comments accordingly. |  | No change. The Applicant has carried out a more detailed assessment [REP5-040] of the potential impacts of nearshore cable protection on nearshore sediment transport processes and coastal morphology, however, there remains uncertainty regarding potential impacts to adjacent coastline. We remain unable to rule out an AEoI on the Humber Estuary SAC. See Appendix B6 of Natural England's Deadline 6 submission for further detail. |  | No change. We maintain our previous advice. However, with regards to cable protection height, we note that within The ExA's Schedule of Recommended Amendments to the Applicant’s draft DCO [PD-028], the ExA has recommended that if cable protection would be required at greater heights than 5% of navigable depth, that this should also be agreed with the MMO in consultation with the SNCB. Natural England welcome this. |  | No change. The Applicant disagrees [REP7-131] that there remains uncertainty in the assessment of nearshore cable protection on nearshore sediment transport processes and coastal morphology, and consider that sufficient evidence has been provided to rule out AEoI on the Humber Estuary Special Area of Conservation (SAC). Our submission at Deadline 6 [REP6-072] summarises our advice on the Applicant’s detailed assessment [REP5-040] of the potential impacts of nearshore cable protection on nearshore sediment transport processes and coastal morphology. Whilst the Applicant has provided a response to this [REP7-131], our position remains unchanged on the RIAA and MCZ Assessment. Although we will endeavour to review the ES chapter and provide further comment as needed at Deadline 9. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology.
B24 | B37 | We advise that the Applicant should commit to the removal of all structures on and above the seabed and consider the potential decommissioning of any proposed external cable/scour protection (including evidence on the likelihood of its success and impacts). We advise that the Applicant should consider and assess the long-term impacts to the marine physical environment of any assets left in situ for the lifetime of the assets within a pre-construction outline Decommissioning plan. (7.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 3. |  | No Change - See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. Natural England maintain our pevious advice. See also Point B7 above. |  | No change. Natural England maintain our previous advice. See also Point B7 above. |  | No change. Natural England maintain our previous advice. See also Point B7 above. |  | Issue progressed. The Applicants have committed [REP6-044] to consider removability of cable protection as part of the development of the final Cable Statement and Decommissioning Programme to be produced for submission to the SoS pre construction. Whilst this is welcome, it is not sufficient to resolve concerns regarding the lack of a full commitment to decomissioning. |  | No change. The Applicants have committed [REP6-044] to consider removability of cable protection as part of the development of the final Cable Statement and Decommissioning Programme to be produced for submission to the SoS pre construction. Whilst this is welcome, it is not sufficient to resolve concerns regarding the lack of a full commitment to decomissioning. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology. |  |  |  | The Applicants have committed [REP6-044] to consider removability of cable protection as part of the development of the final Cable Statement and Decommissioning Programme to be produced for submission to the SoS pre construction. Whilst this is welcome, it is not sufficient to resolve concerns regarding the lack of a full commitment to decomissioning. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology.
B25 | B38 | We advise that the value of both Dogger Bank and Smithic Bank is high. This should be taken into consideration by the Applicant and their assessment updated where necessary. (7.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. We welcome the Applicants' acknowledgement [AS-048] that the value of both Dogger Bank and Smithic Bank are higher than low. However, our advice remains unchanged. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. Natural England maintain our previous advice. |  | No change. The Applicant has indicated in [REP4-088] and in their Written Summaries of Oral Submissions at ISH5 [REP4-086] that as Dogger Bank is not a sand bank in terms of morphology (rather a complex set of glacial landforms covered with a veneer of sand), therefore they did not assign it a high value. Natural England directs the ExA and competent authority for the HRA to the conservation objectives for Dogger Bank SAC which sets out the high value of this Annex I sandbank. The SNCBs fundamentally disagree with the Applicant on this. Having thoroughly considered this, we do not believe that resolution will occur during examination. Therefore unless there is a change in the Applicant's position, our position will remain unchanged for the remainder of the examination In addition, we advise that Smithic Bank is a Feature of Conservation Importance with a high value due to providing shelter to the northern part of the Holderness Coast including the town of Bridlington and also has wider ecological importance. | [5 empty] | No change. Whilst we note that the Applicant has updated the value of Dogger Bank to high (from low) in the updated ES Chapter 8 [REP7-036], the Applicant does not consider its value in the definition of sensitivity and thus impacts have mostly been defined as negligible with non-significant (in EIA terms) residual effects. Natural England does not agree with this method of sensitivity assessment . With regards to Smithic Bank, the Applicant's position on the 'low' value remains unchanged. We maintain our advice that Smithic Bank is of high value. Please see our advice in 'Natural England's Comments on Environmental Statement Conclusions (from Rule 17 letter dated 19 June 2025)', Appendix P8 of our Deadline 8 submission for further detail. |  |  |  | Whilst we note that the Applicant has updated the value of Dogger Bank to high (from low) in the updated ES Chapter 8 [REP7-036], the Applicant does not consider its value in the definition of sensitivity and thus impacts/estimates of signficance have mostly been defined as negligible with non-significant (in EIA terms) residual effects. Natural England does not agree with this method of sensitivity assessment . With regards to Smithic Bank, the Applicant's position on the 'low' value remains unchanged. We maintain our advice that Smithic Bank is of high value. Please see our advice in 'Natural England's Comments on Environmental Statement Conclusions (from Rule 17 letter dated 19 June 2025)', Appendix P8 of our Deadline 8 submission for further detail.
B26 | B39, B47 | Supporting evidence for seabed recovery from installation vessels has been provided based on pre-installation (2010) and post-removal surveys (2022) for two Met Masts in DBB and C OWFs (i.e. after a period of 12 years). There is insufficient information behind the conclusion that the duration, reversibility and, thus, magnitude of impact on seabed morphology will be low. Consequently, we are unable to agree with the assessment conclusion that effect significance will be negligible. The Applicant should provide further evidence for seabed recovery following installation vessel impacts. Additional mitigation should be explored to minimise impacts to the seabed morphology at Dogger Bank and the SAC during construction and Operation and Maintenance activities. (8.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. As stated by the Applicants [AS-048], persistent installation vessel impacts may occur on Dogger Bank where no (or little) mobile sediment overlies static geological formations. We therefore advise that the assessment of recoverability, value and sensitivity for Dogger Bank should be updated to reflect this. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. |  | No change. We note the reduction in seabed impacts due to jack up vessel indentations over the lifetime of the project due to the reduction in the number of offshore platforms as outlined in [AS-141], however, the issue of seabed recovery evidence remains. |  | No change. Natural England maintain our previous advice. |  | No change. Natural England maintain our previous advice. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue progressed. Whilst the Applicant maintains their position [REP6-052] and disagreement remains on the assessment, a footprint for habitat loss from jack-up use has been provided [REP5-037] and will be included in the next iteration of the RIAA. We acknowledge that if SoS concludes that habitat disturbance contributes to AEoI, then the jacking-up footprint would be within the disturbance footprint and therefore already taken into account. |  | No change. Whist we note that the Applicant has submitted an updated 6.1 RIAA 2 of 4 –Annex I Offshore Habitats and Annex II Migratory Fish (Revision 5) [REP7-017] and updated 6.2.3 Appendix 3 - Project Level Dogger Bank Compensation Plan (R4) [REP7-021] which includes without prejudice compensation for impacts from jack up vessels which is welcomed. We note that further mitigation measures have have not been considered. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology for detail about habitat loss and Tab D Benthic compensation |  |  |  | Whist we note that the Applicant has submitted an updated 6.1 RIAA 2 of 4 –Annex I Offshore Habitats and Annex II Migratory Fish (Revision 5) [REP7-017] and updated 6.2.3 Appendix 3 - Project Level Dogger Bank Compensation Plan (R4) [REP7-021] which includes without prejudice compensation for impacts from jack up vessels which is welcomed. We note that further mitigation measures have have not been considered. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology for detail about habitat loss and Tab D Benthic compensation
B27 | B40, B47 | The sensitivity of Dogger Bank (and Dogger Bank SAC) to changes in seabed level from certain construction activities has been assessed as negligible. We advise that these construction activities and similar O&M activities are likely to result in changes to the extent and distribution and physical structure of the site’s sandbank feature, which will further hinder its restore objective(s). (a) Further mitigation measures should be adopted and secured to minimise impacts. (b) Pre and post-construction monitoring should be committed to to validate predictions of seabed elevation change and extent of deposition, sediment composition and distribution change, and seabed recovery across the Array Areas and Inter-Platform Corridor within Dogger Bank SAC. Should impacts be found to be greater than predicted then the necessary recourse should be taken. (8.7.3.6) |  | No change. Natural England are reviewing the Applicant’s response and additional submission '10.44 Review of Evidence on Recovery of Sandbank Habitat Following Habitat Damage' [AS-025] and will provide further comment at Deadline 2. |  | No Change - See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. |  | Issue progressed. The Applicant has committed to carrying out pre-construction full seabed coverage bathymetry surveys within the Order Limits in the IPMP [REP2-044]. However, further assessment and monitoring commitments are required. Natural England refers you to Deadline 3 Appendix B3 and J. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. The Applicant has indicated in [REP4-088] and in their Written Summaries of Oral Submissions at ISH5 [REP4-086] that as Dogger Bank is not a sand bank in terms of morphology (rather a complex set of glacial landforms covered with a veneer of sand), therefore they did not assign it a high value. Natural England directs the ExA and competent authority for the HRA to the conservation objectives for Dogger Bank SAC which sets out the high value of this Annex I sandbank. The SNCBs fundamentally disagree with the Applicant on this. Having thoroughly considered this, we do not beleive that resolution will occur during examination. Therefore unless there is a change in the Applicant's position, our position will remain unchanged for the remainder of the examination In addition, we advise that Smithic Bank is a Feature of Conservation Important with a high value due to providing shelter to the northern part of the Holderness Coast including the town of Bridlington and also has wider ecological importance. With regards to further assessment and monitoring requirements for sandwave monitoring, please refer to our detailed IPMP comments submitted at Deadline 3 with overarching concerns [REP3-056] as well as Appendix B5 of Natural England's Deadline 5 submission for further detail. |  | No change. Please see our advice in Appendix B6 of Natural England's Deadline 6 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | See Point B25 above. Please also see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology. |  |  |  | Natural England does not agree with the Applicants method of sensitivity assessment. which under estimates significance. Please see our advice in 'Natural England's Comments on Environmental Statement Conclusions (from Rule 17 letter dated 19 June 2025)', Appendix B8 of our Deadline 8 submission for further detail.
B28 | B42 | There is insufficient information regarding the location and significance of cable crossings and nearshore cable protection measures relative to Smithic Bank to support the assessment conclusions. The potential exchange of sediment between South Smithic and the Holderness Coast should be considered when assessing impacts to the nearshore and circulatory sediment transport processes due to the presence of nearby cable protection measures and cable crossings. (7.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. We continue to advise that more detailed information is needed regarding the proposed cable crossing with the Hornsea Four export cable corridor, and its proximity, to Smithic Bank, in order to better understand potential impacts on nearshore sediment transport processes. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. The Applicant has provided an indicative location map for the DBS/Hornsea Project 4 cable crossing in Appendix D to [REP3-028]. We advise that in order to reduce potential impacts to nearshore sediment transport processes and seabed morphology, that the DBS/Hornsea Project 4 cable crossing should be placed seaward of the 20m depth contour to the east of Smithic Bank and as distant from Holderness Offshore MCZ, as possible. Cable crossing MDS parameters should also be reduced as much as possible. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. The Applicant has clarified [REP5-037] that the approximate 116m length of nearshore cable protection measures per cable trench is an illustrative estimate rather than an absolute length to be secured within the draft DCO. Furthermore, as discussed in Appendix B6 of Natural England's Deadline 6 submission, the information currently available does not provide sufficient detail to inform understanding of the potential impact of nearshore cable crossings/protection to Smithic Bank. |  | No change. The Applicants have provided a map as part of the updated Cable Statement [REP6-044] showing preliminary and indicative cable protection locations within the ECC. However, they have also stated that it is not representative of the final proposals and the final cable protection locations will be informed by factors such as further site investigations, cable routing, updated CBRAs and burial depths achieved during installation. Therefore, it remains unclear whether cable protection may be required in proximity to Smithic Bank. |  | No change. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology. |  |  |  | Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology.
B29 | B43 | There is insufficient information to support the assessment of changes to bedload sediment transport and seabed morphology due to the presence of cable protection measures on Dogger Bank. We advise that, firstly, the Applicant should attempt cable burial across Dogger Bank to avoid placement of cable protection measures within Dogger Bank SAC. Secondly, a seabed mobility assessment should be carried out to inform the cable burial assessment and, thus, the requirement for cable protection measures. Lastly, if cable protection measures are found to be necessary, potential changes to seabed sediment transport processes and seabed morphology should be fully assessed for the WCS option for cable protection measures on Dogger Bank. (7.8) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change - See Appendix B2 of Natural England's Deadline 2 submission for further detail. |  | No change. In the updated Cable Statement [REP2-040] it is stated that Seabed Mobility studies are ongoing. These studies are needed to inform the cable burial assessment and, thus, the requirement for cable protection measures. Therefore, currently it is not clear where external cable protection measures may be needed or the potential extent of their impact on sediment transport processes and seabed morphology. See Appendix B3 of Natural England's Deadline 3 submission for further detail. |  | No change. See Appendix B4 of Natural England's Deadline 4 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue progressed. The Applicant has provided a more detailed assessment [REP5-040] of bed shear stress and sediment transport pathways at and around the Array Areas. However, as discussed in Appendix B6 of Natural England's Deadline 6 submission, these results and those in the original ES chapters need to be evaluated in the context of the different seabed sediment composition and thickness and seabed morphology areas across Dogger Bank, over the lifetime of the cable protection. |  | No change. The Applicant has indicated [REP6-051] that a refined baseline understanding of sediment transport pathways will be incorporated in the revised version of Chapter 8 Marine Physical Environment [APP-080] to be submitted at Deadline 7. The Applicant has also stated that updated predictions of future wave climate within section 8.6.3 of the revised [APP-080] have considered these changes in the assessment of construction activities and infrastructure at the landfall, where waves are the dominant driver of sediment transport. We will provide comment accordingly. |  | The Applicant has submitted an updated ES chapter 8 [REP7-036]. We will provide further comment at Deadline 9. Please see our Deadline 8 cover letter for our approach to the final two deadlines.
B30 | B44 | It is suggested that the magnitude of decommissioning effects on the marine physical environment would be comparable to those during the construction phase. However, the baseline conditions at the end of design life may differ significantly from those at pre-construction and the value of receptors may change over the lifetime of the project. Consequently, the EIA cannot confidently determine decommissioning impacts at the end of the design life of the Projects. A number of alternatives to decommissioning are emerging, and whilst these alternatives may be beyond the scope of the present ES, we advise that the EIA is updated as such alternatives progress. The Applicant should provide a pre-consent outline decommissioning plan which considers the potential long-term impacts to the marine physical environment and processes of any assets left in situ. (7.5, 7.8) |  | No change. The Applicant does not agree that an outline decommissioning plan at this stage is helpful. We continue to advise that a pre-consent outline decommissioning plan is produced. We highlight that under S105 of the Energy Act 2004 a decommissioning plan must be provided to the SoS prior to construction of which the outline decommissioning plan would form the basis. |  | No change - See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. See Point B7 above. |  | No change. We continue to advise that a pre-consent outline decommissioning plan is produced. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. We continue to advise that a pre-consent outline decommissioning plan is produced. Please see our advice in Appendix P8 'Natural England's Comments on Environmental Statement Conclusions (from Rule 17 letter dated 19 June 2025)' and Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology for further detail. |  |  |  | We continue to advise that a pre-consent outline decommissioning plan is produced. Please see our advice in Appendix P8 'Natural England's Comments on Environmental Statement Conclusions (from Rule 17 letter dated 19 June 2025)' and Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology for further detail.
B31 | B45 | “Penetration and/or disturbance of the substratum below the surface of the seabed, including abrasion” has been screened out for Operation and Maintenance (O&M) for Offshore Annex I Habitats and Dogger Bank SAC but has been included in the assessment (Section 6.4.2.1.1). We agree this should be included in the assessment and advise the screening tables are updated. (6.1, 6.1.1) |  | Issue progressed. We continue to advise that the RIAA is updated to accurately reflect the impacts screened in, however as this impact has been included in the assessment we will not pursue this further. | [13 empty] | Issue resolved. Screening Tables 6-4 and 6-6 of [REP4-015] have been updated whereby "Penetration and/or disturbance of the substratum below the surface of the seabed, including abrasion" has been screened in for O&M. |  |  |  | Issue resolved. Screening Tables 6-4 and 6-6 of [REP4-015] have been updated whereby "Penetration and/or disturbance of the substratum below the surface of the seabed, including abrasion" has been screened in for O&M.
B32 | B46 | For Annex 1 features of the Humber Estuary SAC, Section 6.6.1.1 of the RIAA only lists ‘Sandbanks which are slightly covered by seawater all the time’ and ‘Mudflats and sandflats not covered by seawater at low tide’ as having been assessed, despite more features being listed as screened in for assessment. We advise that the full list of features identified at Screening should be assessed in the RIAA. (6.1.1, 6.1) |  | Issue progressed. The Applicant has confirmed that the missing features should have been assessed in the RIAA. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change |  | No change. Change Request 1 [AS-141] has concluded that a reduction in the MDS has not changed the Applicant's conclusion of no potential AEoI on the Humber Estuary SAC, however we still require evidence that all features of the SAC have been fully covered in an updated RIAA. |  | No change. The Applicant has indicated that an updated RIAA will be provided at Deadline 4 [REP3-027] (ExQ, HRA.1.8). |  | Issue resolved. The Applicant has screened in all relevant features for the Humber Estuary SAC in the updated RIAA [REP4-015]. | [9 empty] | Issue resolved. The Applicant has screened in all relevant features for the Humber Estuary SAC in the updated RIAA [REP4-015].
B33 | B48 | Dogger Bank D OWF has not been included in the in-combination assessment for impacts to the Humber Estuary SAC - we advise this is included. (6.1) |  | No change. |  | No change - We continue to advise Dogger Bank D OWF is included in the in-combination assessment for impacts to the Humber Estuary SAC. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - no new information relevant to this issue has been submitted at this deadline. It is NE's understanding that Dogger Bank D S42 PEIR is to be consulted on from 6 June - 1 August 2025 and therefore within the timeframes of this Examination |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. |  | The DBD PEIR is now in the public domain through a Section 42 consultation. Whilst we welcome provision by the Applicant at Deadline 7 of the document '17.6 The Applicant’s Consideration of the Dogger Bank D Preliminary Environmental Information Report' [REP7-133], Natural England are currently in the process of reviewing the PEIR and therefore cannot provide further comment on the appropriateness of [REP7-133] at this time. We therefore maintain the advice provided at Deadline 7 [REP7-154], that when determining the DBS windfarms, the Secretary of State considers Dogger Bank D in their HRA. |  |  |  | The DBD PEIR is now in the public domain through a Section 42 consultation. Whilst we welcome provision by the Applicant at Deadline 7 of the document '17.6 The Applicant’s Consideration of the Dogger Bank D Preliminary Environmental Information Report' [REP7-133], Natural England are currently in the process of reviewing the PEIR and therefore cannot provide further comment on the appropriateness of [REP7-133] at this time. We therefore maintain the advice provided at Deadline 7 [REP7-154], that when determining the DBS windfarms, the Secretary of State considers Dogger Bank D in their HRA.
MCZ Assessment - Document(s) Used: [APP-240] 8.17 Stage 1 Marine Conservation Zone Assessment
B34 | B51 | Our concerns raised for the overall EIA in relation to impacts from cable installation and operation are all also relevant within the MCZ assessment. The MCZ Stage 1 impact assessment should be updated based on the comments provided on the impact assessment. (8.17) |  | No change. |  | No change - Please see our comments on the Benthic Technical note [AS-104] included within Deadline 2 Appendix C2.1. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. |  | No change. |  | No change. |  | No change. The Applicant has indicated [REP6-052] that an updated version of the Stage 1 MCZ Assessment [APP-240] will be submitted at Deadline 7 to incorporate the information provided in [REP3-025] and [REP5-040], and to reflect the latest design parameters of the Projects. We will provide comments accordingly. |  | No change. The Applicant maintains [REP7-132] that they have presented sufficient scientific evidence to conclude that the conservation objectives of maintaining the protected features of the Holderness Inshore MCZ in a favourable condition or restoring them to favourable condition will not be hindered by changes to bedload sediment transport related to the operation of the Projects (either in isolation or if both are built concurrently and / or in sequence) to support the conclusions of the Stage 1 MCZA and as a result, a Stage 2 MCZA is not required. As highlighted, further information and mitigation commitments are required, and until then we cannot advise the SoS on level of risk. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology for further detail. |  |  |  | No change. The Applicant maintains [REP7-132] that they have presented sufficient scientific evidence to conclude that the conservation objectives of maintaining the protected features of the Holderness Inshore MCZ in a favourable condition or restoring them to favourable condition will not be hindered by changes to bedload sediment transport related to the operation of the Projects (either in isolation or if both are built concurrently and / or in sequence) to support the conclusions of the Stage 1 MCZA and as a result, a Stage 2 MCZA is not required. As highlighted, further information and mitigation commitments are required, and until then we cannot advise the SoS on level of risk. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology for further detail.
B35 | B53 | An EIA matrix has been used to determine magnitude rather than considering if there is an impact pathway to the MCZ features and utilising conservation objectives, conservation advice and advice on operations. This section of the MCZ assessment should be updated in line with Stage 1 MCZ Assessments undertaken for other OWF projects. Until this is updated, we are unable to agree with the conclusions of this assessment. (8.17) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change - Please see our comments on the Benthic Technical note [AS-104] included within Deadline 2 Appendix C2.1. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. We note the Applicant's position that the Project will not hinder the conservation objectives of the MCZs however, we advise that if significant indirect impacts from DBS cable installation on designated features of the MCZ can't be excluded during Examination then we would recommend that a without prejudice MEEB proposal and/or commitments to invest in strategic compensation are progressed as was submitted for DEP and SEP. Please see Appendix B4 of Natural England's Deadline 4 submission for further detail. |  | No change. We note that further information in relation to impacts to nearshore processes is due for submission at Deadline 5 which may progress this issue. |  | No change. See Appendix B6 of Natural England's Deadline 6 submission for further detail on our outstanding concerns regarding the placement of nearshore cable protection. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. The Applicant has submitted an updated Stage 1 Marine Conservation Zone Assessment (rev 02) [REP7-112]. However, this has not addressed our concerns. The SoS will need to be satisfied that sufficient evidence has been presented to determine the significance of the impact pathways to inform their MCZ assessment |  |  |  | No Change. The Applicant has submitted an updated Stage 1 Marine Conservation Zone Assessment (rev 02) [REP7-112]. However, this has not addressed our concerns. The SoS will need to be satisfied that sufficient evidence has been presented to determine the significance of the impact pathways to inform their MCZ assessment
B36 | B54 | The impacts assessment does not consider sandwave levelling along the export cable corridor. We advise against deposition of sand in locations where SSC and deposition become significantly elevated above baseline level and suggest this is secured in the commitments register. (8.17) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. The Applicant [AS-025] considers that as the offshore ECC doesn't overlap the MCZs, no direct effects will occur as a result of sandwave levelling. The Applicant has highlighted that increased SSC in the ECC from activities involved in seabed preparation for cable installation have been considered. We continue to advise against deposition of sand in locations where SSC and deposition become significantly elevated above baseline level, and that this is secured in the commitments register. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. Natural England note the Applicant's request for clarification regarding locations for a commitment regarding no direct depositions. We propose to discuss this directly with the Applicant outside of the Examination in early May and will provide further comment at Deadline 5. |  | Issue progressed. We are satisfied with the Applicant's assessment predictions that sediment deposition from trenching and levelling for the offshore export cable corridor is predicted to be localised and the seabed recoverable, however this is dependent on the appropriate mitigation being secured. Please see Appendix B5 of Natural England's Deadline 5 submission for further detail. |  | No change. We note that the Applicant does not intend to commit to depositing sediment updrift of dredging locations. No further information has been provided with respect to using a fall pipe for deposition. See Appendix B6 of Natural England's Deadline 6 submission for further detail. |  | No change. The Applicant maintains their position [REP6-052] on not committing to depositing sediment updrift of dredging locations and that it is not technically feasible to use a fall pipe for deposition. We maintain our previous advice. See B17. |  | No change. The Applicant maintains their position [REP6-052] on not committing to depositing sediment updrift of dredging locations and that it is not technically feasible to use a fall pipe for deposition. We maintain our previous advice. See B17. Note that for offshore sandwave levelling, potential impacts could be to Holderness Offshore MCZ and nearshore sandwave levelling could have potential impacts to Holderness Inshore MCZ. |  |  |  | We note [REP7-131] that there is no change to the Applicant's position on the use of a fall pipe for depositing dredged sediment and updrift of the sandwave - we maintain our advice on this. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology for further detail regarding this.
B37 | B55 | The mitigation measures to minimise scour protection do not provide certainty that impacts will be minimised to acceptable levels. Pre-construction surveys do not relate to either the MCZ or mitigation measures unless surveys cover the secondary impacts zone within the MCZ, and remedial actions are taken should impacts be greater than predicted. Further consideration is required of mitigation measures that will reduce impacts to the MCZ. (8.17) |  | No change. Natural England welcomes the Applicant's commitments to not anchoring or using jack up vessels in the MCZ , however these aren't necessarily mitigating for scour protection impacts |  | No change - we maintain our previous advice that commitments to not anchoring or using jack up vessels in the MCZ aren't necessarily mitigating for scour protection impacts and continue to advise that further consideration is required of mitigation measures that will reduce impacts to the MCZ. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | The Applicant's assumption [REP3-028] that we are referring to (scouring around) cable protection is correct. No change - see Point B4. |  | No change - no new information relevant to this issue has been submitted at this deadline. See Point B4. |  | No change. We maintain our previous advice. See Appendix B6 of Natural England's Deadline 6 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. The Applicant has a commitment within the IPMP (rev05) [REP7-116] to pre- and post-construction monitoring of the seabed through the collection of geophysical survey data and have provided a further update to the IPMP stating "If nearshore external cable protection is installed it will be monitored, along with associated sediment accretion and scour". However, this does not go far enough as the Applicant has not provided sufficient remediation measures should monitoring demonstrate effects are greater than predicted. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology. |  |  |  | No change. The Applicant has a commitment within the IPMP (rev05) [REP7-116] to pre- and post-construction monitoring of the seabed through the collection of geophysical survey data and have provided a further update to the IPMP stating "If nearshore external cable protection is installed it will be monitored, along with associated sediment accretion and scour". However, this does not go far enough as the Applicant has not provided sufficient remediation measures should monitoring demonstrate effects are greater than predicted. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology.
B38 | B56 | We are concerned that temporary deterioration in condition is to be disregarded if the habitat is sufficiently healthy and resilient to enable recovery. Further evidence is required to demonstrate that impacts will be temporary, and recovery can occur in the short term. (8.17) |  | No change. Natural England will provide comments on [AS-104] 10.38 Benthic Ecology Technical Note at Deadline 2. |  | No Change - we maintain our previous advice. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. |  | No change. |  | No change. |  | No change. |  | No Change. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology and advice on cable protection. |  |  |  | Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology and advice on cable protection.
B39 | B58 | Dogger Bank D OWF has not been included in the in-combination assessment for impacts to Spurn Point - we advise this is included. (8.17) |  | No change. |  | No change - We continue to advise Dogger Bank D OWF is included in the in-combination assessment for impacts to Spurn Point. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. It is NE's understanding that Dogger Bank D S42 PEIR is to be consulted on from 6 June - 1 August 2025 and therefore within the timeframes of this Examination |  | No change. |  | No change. |  | No Change. However, we note that the Dogger Bank D S42 PEIR is now in the public domain. Therefore we advise that when determining DBS windfarms the Secretary of State considers Dogger Bank D in their HRA. |  | The DBD PEIR is now in the public domain through a Section 42 consultation. Whilst we welcome provision by the Applicant at Deadline 7 of the document '17.6 The Applicant’s Consideration of the Dogger Bank D Preliminary Environmental Information Report' [REP7-133], Natural England are currently in the process of reviewing the PEIR and therefore cannot provide further comment on the appropriateness of [REP7-133] at this time. We therefore maintain the advice provided at Deadline 7 [REP7-154], that when determining the DBS windfarms, the Secretary of State considers Dogger Bank D in their HRA. |  |  |  | The DBD PEIR is now in the public domain through a Section 42 consultation. Whilst we welcome provision by the Applicant at Deadline 7 of the document '17.6 The Applicant’s Consideration of the Dogger Bank D Preliminary Environmental Information Report' [REP7-133], Natural England are currently in the process of reviewing the PEIR and therefore cannot provide further comment on the appropriateness of [REP7-133] at this time. We therefore maintain the advice provided at Deadline 7 [REP7-154], that when determining the DBS windfarms, the Secretary of State considers Dogger Bank D in their HRA.
B40 | B60 | Further mitigation could be applied to avoid potential impacts to sediment transport on the MCZ. (8.17) |  | No change. |  | No change - Please see Appendix B2 and our comments on the Benthic Technical note [AS-104] included within Deadline 2 Appendix C2.1. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. The Applicant has indicated [REP3-028] that a technical note will be provided at Deadline 5 regarding the potential effects of cable protection measures on sediment transport in the nearshore environment. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. See Appendix B6 of Natural England's Deadline 6 submission for further detail on our outstanding concerns regarding the placement of nearshore cable protection. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology and advice mitigation |  |  |  | No Change. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology and advice mitigation
B41 | B61 | The conservation objectives for the Holderness Inshore MCZ could be hindered due to the current dML condition allowing 10% of the export cable to be protected from 350m seaward of MLWS to the 10m depth contour. This could disrupt sediment transport associated with Holderness Inshore MCZ. (8.17) |  | No change. |  | No change - Please see Appendix B2 and our comments on the Benthic Technical note [AS-104] included within Deadline 2 Appendix C2.1. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. See Point B23. |  | No change. The Applicant has indicated [REP4-088] that a technical note will be provided at Deadline 5 regarding the potential effects of cable protection measures on sediment transport in the nearshore environment. We will provide further comments accordingly. |  | No change. Following review of the Applicant's updated coastal processes assessment, we maintain the view that it cannot be ruled out that the conservation objectives of the Holderness Inshore MCZ will be hindered. See Appendix B6 of Natural England's Deadline 6 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology. |  |  |  | No change. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology.
Assessment of SSSI impacts - Document(s) Used: [APP-080] 7.8 ES Chapter 8 – Marine Physical Environment
B42 | B62 | It is stated that there is a potential for impacts to Withow Gap Skipsea SSSI due to cable installation/removal. However, it is our understanding that the landfall option with the potential to interact with this SSSI has been withdrawn. We advise that the impact assessment is updated as needed. (7.8) |  | Issue Progressed. The Applicant has confirmed that the Projects no longer directly interact with the SSSI as part of any landfall works but that it was included for consideration of any potential indirect effects. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No change. |  | No change. The Applicant previously stated that Withow Gap SSSI had been included for consideration of any potential indirect effects. It is not clear where potential impacts to Withow Gap SSSI have been considered following the changes made to the project design envelope through the Change Request. We request the Applicant to signpost where this has been considered. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | The Applicant has indicated [REP4-088] that the reduced WCS as a result of the Project Change Request 1 has resulted in a change to the receptors assessed, including Withow Gap SSSI and that the assessment to landfall works will be updated in a technical note to be submitted at Deadline 5. We will provide further comment accordingly. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue progressed. The Applicant has clarified [REP5-040] that as the exit pits are in the subtidal zone, there will be no direct impact to Withow Gap, Skipsea SSSI. We advise that relevant ES chapters are updated to resolve this matter. |  | The Applicant has submitted an updated ES chapter 8 [REP7-036]. We will provide further comment at Deadline 9. Please see our Deadline 8 cover letter for our approach to the final two deadlines.
Disposal of material arising from construction activities - Document(s) Used: [APP-242] 8.18 Disposal Site Characterisation Report
B43 | B63, C54 | This document will need updating pre-consent based on comments Natural England has provided on the EIA within Appendix B and C as currently we do not agree with conclusions on the level of impacts. (8.18) |  | No change. |  | No change - no new information relevant to this issue is likely to be submitted by the Applicant and we will review once submitted |  | No change. Natural England have provided comments on the updated Disposal Site Characterisation Report [REP2-036] in Appendix B3, however the updates made are largely to bring the report in line with the Change Request. |  | No change - no new information relevant to this issue has been submitted at this deadline |  | No change. |  | An updated Disposal Site Characterisation Report has been submitted [REP5-026]. Please see comments below and Appendix B6 of our Deadline 6 submission. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | An updated Disposal Site Characterisation Report (rev04) has been submitted [REP7-114], however the updates are related to location of disposal sites. Please see comments below for outstanding issues.
B44 | B64, C55 | The whole of the offshore windfarm array footprints, the inter-cable platform corridor and the export cable corridors will be disposal locations, but deposition will only occur where possible within the same sediment. Given that sandwave levelling is likely to be undertaken by suction hopper dredge and then sediment released at the sea surface, it is unlikely that this will occur. We advise that disposal options are explored to ensure that sediment is deposited in similar sediment types. (8.18) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change - See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. |  | No change. This has not been addressed in Revision 2 of the Disposal Site Characterisation Report [REP2-036]. |  | No change. The Applicant has stated [REP3-028] that they can commit to depositing like sediment on like sediment (within Dogger Bank SAC) and has indicated that an updated Cable Statement will be provided at Deadline 4 [REP3-028] to reflect such changes. We will provide further comment accordingly. |  | Issue progressed. The Applicant has committed to depositing like sediment on like sediment both within and outside of Dogger Bank SAC in the updated Cable Statement, this should be secured in the Commitment Register. Please see Appendix B5 for further advice on outstanding mitigation measures. |  | No change. We note that the Applicant does not intend to commit to depositing sediment updrift of dredging locations. No further information has been provided with respect to using a fall pipe for deposition. See Appendix B6 of Natural England's Deadline 6 submission for further detail. |  | No change. See Points B17 and B36. |  | No change. See Points B17 and B36. |  |  |  | No change. See Points B17 and B36.
B45 | B65, C56 | We advise the mitigation in Section 5.2 does not go far enough, especially within the Dogger Bank SAC and in areas where there are priority habitats and/or indirect impacts to designated site features could occur. We advise that the following mitigation measures are adopted (but not exclusively): - All deposition of dredged sediment within the Dogger Bank SAC should be done through the use of a fall pipe and adjacent and upstream of the dredge location in same sediment type to ensure sediment stays within the site. - Drill arisings should be deposited within similar sediment characteristics i.e. not on sandbanks. Therefore, adjacent to turbines is unlikely to be appropriate. - Sandwave deposition should avoid areas of priority habitats under NERC 2006 by the inclusion of a 50m buffer around the NERC habitats. - Deposition of dredge material along the export cable should utilise a fall pipe where there is a risk of increases in suspended sediment concentrations impacting on designated site features and those of ecological importance. (8.18) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change - see point B36 and B44 and Appendix C2.1 of Natural England's Deadline 2 submission for further detail. |  | No change. This has not been addressed in Revision 2 of the Disposal Site Characterisation Report [REP2-036]. |  | No change. The Applicant has stated [REP3-028] that they can commit to depositing like sediment on like sediment (within Dogger Bank SAC) and has indicated that an updated Cable Statement will be provided at Deadline 4 [REP3-028] to reflect such changes. We will provide further comment accordingly. However, we note that both Five Estuaries and Outer Dowsing OWF Applicant's have committed to use of a fall pipe adjacent and upstream of the dredge location in same sediment type to ensure sediment stays within the site. |  | Issue progressed. The Applicant has committed to depositing like sediment on like sediment both within and outside of Dogger Bank SAC in the updated Cable Statement, this should be secured in the Commitment Register. Please see Appendix B5 for further advice on outstanding mitigation measures. |  | No change. We note that the Applicant does not intend to commit to depositing sediment updrift of dredging locations. No further information has been provided with respect to using a fall pipe for deposition. See Appendix B6 of Natural England's Deadline 6 submission for further detail. |  | No change. See Points B17 and B36. |  | No change. See Points B17 and B36. |  |  |  | No change. See Points B17 and B36.
B46 | B66, C57 | For intertidal exit pits, we advise that alternative storage options for material from the landfall exit pits are explored (see also comments (B15) Appendix B) |  | No change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change |  | Issue resolved. As detailed in [AS-141], the short trenchless crossing and intertidal exit pits have been removed from the project design envelope. | [13 empty] | Issue resolved. As detailed in [AS-141], the short trenchless crossing and intertidal exit pits have been removed from the project design envelope.
B46.1 | NEW | NEW ISSUE AT DEADLINE 3 | [5 empty] | It is stated in [REP2-036] that within the arrays, seabed level could be increased by up to 0.5m where multiple cable corridors merge, but in practice the cable layout will be designed to avoid this - we require clarity on how and where this will be secured. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. The Applicant has stated [REP4-088] the "0.5m increase in seabed level is in reference to the worst-case increase in sediment accumulation calculated in the marine physical processes modelling undertaken for the Projects" and that they are unable to secure a change in seabed level of up to 0.5m as sediment transport isn't static. We request the Applicant to clarify how avoiding exceedance of the worst-case increase of 0.5m will be carried out and associated control measures. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. We consider that the information provided by the Applicant in [REP6-052] regarding avoidance of exceedance of sediment accumulation and post construction monitoring within the IPMP is not detailed enough to address our concerns. We require further clarification on this matter. |  | No change.
Scour Prevention - Document(s) Used: [APP-251] 8.27 Outline Scour Protection Plan
B47 | B67, C58 | We advise that this document needs to better consider the risk and implications of secondary scour occurring. (8.27) |  | Natural England will provide comments on [AS-081] 8.27 Outline Scour Protection Plan (Rev 02) at Deadline 2. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. |  | No change. We maintain our advice as set out in Appendix C2.1 [REP2-065] of Natural England's Deadline 2 submission. See Deadline 3 Appendix J for further detail on secondary scour considerations in the IPMP. |  | No change. We welcome the Applicants' clarification [REP3-028] on the WCS figures presented. However, oustanding concerns remain regarding seabed mobility, bedform formation and migration and scour potential (see Appendix B4 of our Deadline 4 submission). We also advise that monitoring of secondary scour needs to be better secured in the IPMP. See Appendix C4 of our Deadline 4 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue progressed. Natural England welcomes that commitments to monitoring secondary scour have been strengthened in the IPMP [REP5-028]. See Appendix B6 of Natural England's Deadline 6 submission for further detail regarding scour monitoring. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. The Applicant has a commitment within the IPMP (rev05) [REP7-116] to pre- and post-construction monitoring of the seabed through the collection of geophysical survey data and have provided a further update to the IPMP stating "If nearshore external cable protection is installed it will be monitored, along with associated sediment accretion and scour". However, this does not go far enough as the Applicant has not provided sufficient remediation measures should monitoring demonstrate effects are greater than predicted. We will endeavour to review the updated ES chapter to see if this has been addressed for Deadline 9.
B48 | B68, C59 | Section 1.2 - Consideration should be given to comments made in relation to minimising environmental impacts as much as possible through the choice of scour prevention/cable protection. Every effort should be made to avoid using those that are least likely to be recovered at the time of decommissioning. (8.27) |  | No change. |  | No change - We refer you to Appendix C2.1 of Natural England's Deadline 2 submission and the link to Natural England's published paper on decommissioning of cable protection. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. See Point B7, B24. |  | No change. See Point B7 and B24. |  | No change. We maintain our previous advice. See Appendix B6 of Natural England's Deadline 6 submission for further detail with regards to removability of cable protection. |  | Issue progressed. The Applicants have committed [REP6-044] to consider removability of cable protection as part of the development of the final Cable Statement and Decommissioning Programme to be produced for submission to the SoS pre construction. However, we maintain our previous advice. See Point B7 above. |  | No change. |  |  |  | No change. The Applicants have committed [REP6-044] to consider removability of cable protection as part of the development of the final Cable Statement and Decommissioning Programme to be produced for submission to the SoS pre construction. However, we maintain our previous advice. See Point B7 above.
Cable Statement - Document(s) Used: Document used: [APP-243] 8.20 Cable statement |  |  |  | Documents reviewed: [AS-079] 8.20 Cable Statement (Rev 02) (Tracked)
B49 | B69, C60 | This document will need updating pre-consent based on comments Natural England has provided on the EIA within Appendix B and C, as we currently do not agree with conclusions included within the document. (8.20) |  | Issue progressed. Natural England welcomes the Applicant's commitment to the separate bundling of pairs of the export cables as outlined in the updated Cable Statement [AS-079], and advise that this commitment is secured in the DCO. This is notwithstanding other outstanding issues such as updates to the CBRA being required. |  | No change. |  | Issue progressed. The Cable Statement [REP2-040] has been updated with an updated CBRA for the Export Cable Route, but not the Array Areas. Further, clarification is needed on whether the results of the ECR Preliminary CBRA alter the MDS for ECR cable protection, particularly within the 10m depth contour. See Appendix B3 of our Deadline 3 submission for further detail. |  | No change - the Applicant has indicated that an updated Cable Statement will be provided at Deadline 4, however the CBRA will not be updated again within Examination timeframes. |  | Natural England welcomes that the Cable Statement [REP4-051] has been updated with a commitment to deposit like sediment on like sediment both within and beyond the boundary of Dogger Bank SAC during sandwave levelling. We maintain our previous advice for a figure to be provided identifying cable burial risks. Please see Appendix B5 of Natural England's Deadline 5 submission for further detail. |  | No change. |  | Issue progressed. The Applicant has stated that an updated final Cable Statement will be produced for submission to the SoS. This will include a sandwave levelling, deposition, and recovery plan and consideration of removability of cable protection measures. However, our other recommendations at Rel Reps will need to be addressed. |  | No change. |  |  |  | No change. The Applicant has stated that an updated final Cable Statement will be produced for submission to the SoS. This will include a sandwave levelling, deposition, and recovery plan and consideration of removability of cable protection measures. However, our other recommendations at Rel Reps will need to be addressed.
B50 | NEW | NEW ISSUE AT DEADLINE 3 | [5 empty] | The estimated maximum dredge volumes for ECR options B and C, based on the 2022 bathymetry, are 227,886m3 and 297,391m3 respectively. However, it is unclear how these values relate to the Maximum Design scenario (MDS) parameters presented in either ES Chapter 8 [APP-080] or the Project Change Request 1 [AS-141]. We require the Applicant’s clarification on the MDS dredge volume values for the ECR . |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. The Applicant has clarified [REP4-088] that the offshore export cable route (ECR) dredge volumes in the Cable Statement [REP4-051] are indicative locations that may require dredging based on the most recent site-specific bathymetric (2022) data, whereas the WCS assessed in the ES Chapter 8 Marine Physical Environment [APP-080] and Offshore Works Change Request [AS-141] were based on a worst-case scenario whereby dredging would occur along the entire length of the export cable route (ECR). However, we are concerned that an error has been made in the values presented in [AS-141] and advise that further justification is needed for the volumes as applied for. Please see Appendix B5 of Natural England's Deadline 5 submission for further detail. |  | No change. We note that Table 7-1 of the Disposal Site Characteristion Report [REP5-026] of worst case scenario volumes have been updated to reflect cable bundling. However, this still does not address our concerns as set out in Appendix B5 of our Deadline 5 submission [REP5-054]. |  | No change. The Applicant considers [REP6-052] that as the assessment in Chapter 8 Marine Physical Environment [APP-080] already concludes that no significant effects would occur as a result of potential dredging activities for the Projects, there would be no material difference in the assessment conclusions should the figures stated in the Cable Statement (Revision 5) be used instead. The Applicant further clarifies that the dredging volume of the OECC for DBS East in isolation has been reduced to 16,560,900m³ following the commitment to the bundling of cables and that a revised figure will be included in the next revision of Chapter 8 Marine Physical Environment [APP-080] to be submitted at Deadline 7. We will provide further comment accordingly. |  | The Applicant has submitted an updated ES chapter 8 [REP7-036]. We will provide further comment at Deadline 9. Please see our Deadline 8 cover letter for our approach to the final two deadlines.

## C - Benthic&Intertidal Ecology
Point | Point Number(s) from Appendix C [RR-039] | Taken from Natural England’s Relevant and Written Representations Dogger Bank South (East and West) Appendix C - Benthic and Intertidal Ecology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Consultation, actions, progression | RAG Deadline 9 | End of Examination Position | Issue Resolved
C1 | C8 | There are inconsistencies in the impact assessment calculations across the various chapters/documents. For example, maximum anchoring footprint for export cable installation, total array areas and offshore ECC cable corridor construction footprint etc. We advise that the maximum temporary construction footprints are reviewed and updated where necessary. (7.05) |  | Issue progressed. The Applicant has clarified the differences in values presented and confirmed that some were incorrect. We advise that the relevant ES chapters and documents are updated as needed. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. Whilst Table 4-3 in [AS-141] provides updated Maximum Design Scenario (MDS) for the impact assessment; we maintain that relevant application documents should be updated to reflect these changes. |  | No change - updates to ES documents are required to resolve. We will provide further comment once updates are provided at Deadline 7. | [7 empty] | The Applicant has submitted an updated ES chapter 9 [REP7-039]. We will provide further comment at Deadline 9. Please see our Deadline 8 cover letter for our approach to the final two deadlines.
C2 | C9 | It is suggested that cable protection may be used at the landfall exits, however there is a commitment to not use cable protection in the intertidal area and/or for 350m seaward of Mean Low Water Springs (MLWS). This also contradicts cable landfall activities set out in the Project Description and MCZ Stage 1 assessment that only describe cables being buried and exit pits naturally backfilling. We advise that clarity is provided on the use of cable protection at the Horizontal Direction Drilling (HDD) exit pits. (7.05) |  | No change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change |  | Issue progressed. With the removal of the intertidal exit pits, rock protection will no longer be required in the intertidal area. However, it is not clear from the information provided in [AS-141] whether rock protection will be required at the subtidal exit pits and whether this has been accounted for in the (MDS). See Appendix C3 of Natural England's Deadline 3 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | The Applicant has stated [REP4-088] that the "intention is to bury the cables at landfall punchout" and that if this is "not possible then protection could be used" which is accounted for within the existing worst case scenario. We advise that clarification is provided on whether the exit pits could fall within 350m seaward of MLWS where there is a commitment to not use cable protection. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue resolved. The Applicant has confirmed [REP6-052] that the subtidal exit pits would not be located within 350m seaward of mean low water springs. This commitment has been added the updated Cable Statement [REP6-044]. Natural England is satisfied that the exit pits will not fall within 350m seaward of MLWS where there is a commitment to not use cable protection. However, see Sheet B - Marine Physical Environment (Point B23) for our outstanding concerns on nearshore cable protection. | [5 empty] | Issue resolved. The Applicant has confirmed [REP6-052] that the subtidal exit pits would not be located within 350m seaward of mean low water springs. This commitment has been added the updated Cable Statement [REP6-044]. Natural England is satisfied that the exit pits will not fall within 350m seaward of MLWS where there is a commitment to not use cable protection. However, see Sheet B - Marine Physical Environment (Point B23) for our outstanding concerns on nearshore cable protection.
C3 | C11 | Justification is required for the WCS quantification of cable protection within and outside of Dogger Bank SAC. This should cover: - Previous experience and available information about the ground type within the Array area and along the ECC route. -Possible post-construction measures e.g. placement of additional scour replenishment during the operational phase - Implications from the removal and replacement of scour protection during cable repairs especially where a new cable loop is included - Implications from the changes in scour prevention/cable protection elevation above the seabed to ensure it remains within the parameters assessed. (7.05) |  | No change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change |  | No change. No further information or rationale has been provided, and in [AS-141] there is no change to the 10% cable protection requirement for the array and inter-platform cables. |  | No change - we maintain our advice that further information and rationale is provided for the WCS for cable protection within and outside of DB SAC, however the Applicant has confirmed that no further revisions will be made to the CBRA within Examination timeframes [REP3-028]. We therefore advise that it would be helpful if the Applicant could provide indicative locations for remedial cable protection requirements based on currently available information. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No Change - Please see Appendix C6 of Natural England's Deadline 6 submission in relation to public interest tests |  | No change - no new information relevant to this issue has been submitted at this deadline. We note that within The ExA's Schedule of Recommended Amendments to the Applicant’s draft DCO [PD-028], the ExA has recommended the following addition re pre-construction surveys "......where cable protection is proposed within habitats of principal importance, Annex 1 subtidal habitat, habitat with suitability for sandeel or superficial deposits of glacial till, a survey report must be submitted to the MMO following completion of the relevant survey to justify with evidence the need for the proposed locations and extent of any cable protection in those locations, demonstrating how the extent of cable protection has been kept to a minimum for each". While this doesn't fully address the issues we have raised; Natural England welcomes this addition to inform further requirements for cable protection. |  | No change. We maintain our previous advice. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology. |  |  |  | We maintain our previous advice. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology.
C4 | C12 | Clarity is needed on how the potential for the addition of further cable/scour protection during the operational phase has been considered and included within the worst-case calculations for cable/scour protection. It is unclear whether figures provided in the Offshore Operations and Maintenance Plan (OOMP; APP-248) for replacement cable protection for the export cables have been integrated into the Project Description. Estimates for cable protection replacement requirements for the inter-array and inter-platform cables have also not been provided. We advise that the standard for quantities of additional scour and/or cable protection outside of benthic SACs is for the replenishment of 10% of any scour prevention/cable protection laid during installation within a 10-year period, as long as the overall footprint is not increased. Any additional scour prevention/cable protection during the operational phase within a designated site will require a separate Marine Licence. See C13 below. (7.05, 8.24) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. See Appendix C2.1 and C2.2 of Natural England's Deadline 2 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. It is outlined in the Applicants’ Reponses to Deadline 2 Documents [REP3-028] that their position remains unchanged, whereby replenishment of cable and scour protection up to the limits set out within the DCO could be deposited within the footprints of deposition established at the construction stage. Natural England maintain our previous advice. |  | No change. We have reviewed the Applicant's position regarding additional and replenishment of cable / scour protection and continue to disagree with it. We do not believe it is in the spirit of the Strategic Compensation Strategy or Marine Recovery Fund. In addition, there is no certainty that the Applicant will be able to use the MRF in the way they propose as the policy is not yet final. Therefore, we advise that they are planning at own risk until the MRF launches and the guidance is published. We are in discussions with DEFRA and DESNZ benthic compensation and MRF teams (respectively) and we will provide further update at D6. |  | Please see Appendix C6 of Natural England's Deadline 6 response in relation to public interest tests |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. We maintain our previous advice. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology. |  |  |  | We maintain our previous advice. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology.
C5 | C13 | We are concerned that Table 2-3 of the OOMP indicates that the Applicant considers the lifetime footprints presented in the Project Description to be allowances for cable protection to be installed at any point through the lifetime of the Projects, rather than the amount that will be required for the construction phase alone, which will subsequently have a footprint and impact for the lifetime of the project. We advise that the maximum design parameters for the ECC and array area, including the lifetime footprint, should be revised to only include cable/scour protection anticipated to be installed during construction. The OOMP should also be updated to reflect the licensing requirements for additional protection installed within Dogger Bank SAC during operation. (7.05, 8.25) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. See Appendix C2.1 and C2.2 of Natural England's Deadline 2 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. It is outlined in the Applicants’ Reponses to Deadline 2 Documents [REP3-028] that their position remains unchanged, whereby replenishment of cable and scour protection up to the limits set out within the DCO could be deposited within the footprints of deposition established at the construction stage. Natural England maintain our previous advice. |  | No change. We have reviewed the Applicant's position regarding additional and replenishment of cable / scour protection and continue to disagree with it. We do not believe it is in the spirit of the Strategic Compensation Strategy or Marine Recovery Fund. In addition, there is no certainty that the Applicant will be able to use the MRF in the way they propose as the policy is not yet final. Therefore, we advise that they are planning at own risk until the MRF launches and the guidance is published. We are in discussions with DEFRA and DESNZ benthic compensation and MRF teams (respectively) and we will provide further update at D6. |  | Please see Appendix C6 of Natural England's Deadline 6 response in relation to public interest tests |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. We maintain our previous advice. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology. |  |  |  | We maintain our previous advice. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology.
C6 | C14 | There are contradictions with regard to the inclusion of cofferdams in the Project scope, including the dimensions provided. It is also stated that the Project has committed to not using cofferdams within the exit pits. Clarification is required on the WCS for the landfall works in relation to cofferdam usage - any documents and assessments should be updated accordingly. (7.09) |  | Issue progressed. The Applicant has confirmed that no cofferdams would be used in the Projects’ Landfall Zone and that the inclusion of cofferdams within Table 9-1 was an error. The relevant ES chapters and documents should be updated to reflect this. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. We maintain that relevant application documents should be updated to reflect the changes in [AS-141]. |  | No change - updates to ES documents are required to resolve. We will provide further comment once updates are provided at Deadline 7. | [7 empty] | The Applicant has submitted an updated ES chapter 9 [REP7-039]. We will provide further comment at Deadline 9. Please see our Deadline 8 cover letter for our approach to the final two deadlines.
C7 | C15, C25, C38, C47 | The Applicant has not sufficiently characterised benthic receptors within Flamborough Head SAC. All benthic receptors within the ZoI, particularly those within designated sites, need to be sufficiently characterised to enable a robust, evidenced assessment to be undertaken and presented. In the absence of characterisation of benthic receptors at a suitable resolution, the WCS needs to be presented (e.g. most sensitive biotope within the broadscale habitat used as a basis for assessments) to consider the sensitivity or recoverability of the benthic receptors to the identified pressure pathways. (7.09, 6.1) |  | No change. The Applicant has provided 10.38 Benthic Ecology Technical Note [AS-104] in response to this issue. We will provide our comments on this document at Deadline 2. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for comments on 10.38 Benthic Ecology Technical Note [AS-104]. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue progressed. Natural England welcome the further characterisation of benthic receptors at a suitable resolution and more transparent consideration of the sensitivity and recoverability of designated benthic receptors to the identified pressure pathways within the ZoI [REP3-026]. We consider this aspect of the issue to be resolved. Updates to ES documents are required to fully resolve the issue, we will provide further comment once updates are provided at Deadline 7. |  | Issue progressed. This has been updated in the Applicant's RIAA [REP4-015], but should also be included within an updated ES chapter. | [5 empty] | The Applicant has submitted an updated ES chapter 9 [REP7-039]. We will provide further comment at Deadline 9. Please see our Deadline 8 cover letter for our approach to the final two deadlines.
C8 | C18 | The cumulation of benthic ‘ecological halo effect’ following the placement of structures on the seabed has not been considered. A robust assessment is needed of the potential Worst-Case area of impact on benthic communities within Dogger Bank SAC sandbank feature, and the nature and scale of that impact, as a result of changes to physical and biological processes following the placement of structures and cable/scour protection on the seabed. Once assessments have been updated, monitoring should be secured via the In principal monitoring plan to determine whether the residual impacts are as predicted. (7.09) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change - Natural England maintain our advice provided at Relevant Reps. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - Natural England maintain our previous advice. See Appendix C4 for further details. |  | No change. Natural England maintain our previous advice. See Appendix C5 of Natural England's Deadline 5 submission for further details. |  | Issue progressed. The Applicant has presented an assessment of ecological halo effects [REP5-041]. However, we consider that the estimate for worst case area of loss needs further revision. Please see Appendix C6 of Natural England's Deadline 6 submission for further details. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue progressed. The Applicant has updated assessment of ecological halo effects [REP7-128]. We welcome the Applicant providing a without prejudice figure based on 50m halo impact from cable protection. But if a reduced buffer for halo effects from cable protection can be agreed then we recognise that the compensation requirement will be reduced and amounts will fall between 5km2 and 13.2km2 for habitat loss. This doesn't take account of impacts from habitat disturbance. Natural England advises that monitoring of the halo effect needs to secured in the IPMP. Please see Appendix B8 of our Deadline 8 submission for further detail.
C9 | C19 | It is unclear how the ‘value’ of receptors has been consistently incorporated into the assessment process. The Applicant has considered all biotopes within the red line boundary, with the exception of those characterised by piddocks, to be of low value. This includes biotopes representative of Annex 1 habitat within Dogger Bank SAC, and no consideration has been given to biotopes within Flamborough Head SAC. We advise that the methods and rationale for valuing benthic receptors, and how value has been used within the assessment process, is reviewed and documents updated accordingly. The significance of impacts on all benthic receptors should thereafter be reassessed. (7.09) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. We continue to advise that an appropriate value should be attributed to biotopes/habitats which contribute to Annex I features, and subsequently more appropriately used to inform the magnitude of impacts. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. We refer you to ExQ HRA 1.3 response in Deadline 3 Appendix K. |  | No change - Natural England maintain our previous advice. |  | Issue progressed. Natural England's concerns on characterisation of benthic receptors for Flamborough Head SAC have been addressed - see Point C7. However, we maintain our previous advice with regards to the valuing of other receptors, particularly those which contribute to Annex I feature and will be subject to permamant loss/change. See Appendix C5 of Natural England's Deadline 5 submission for further details. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - the Applicant maintains their position "that in this case the value of Annex 1 habitat is intrinsically considered as part of the HRA process" [REP6-052]. Natural England maintain our previous advice. |  | No Change. Natural England continues to disagree with the Applicant regarding biotopes contributing to Annex 1 feature being classed as low value, particularly where they will be subject to permanent loss/change and therefore for which sensitivity cannot be used to downgrade overall value as per the Applicants outlined methods. However, we acknowledge these will be given further consideration in the RIAA. Please see our advice in 'Natural England's Comments on Environmental Statement Conclusions (from Rule 17 letter dated 19 June 2025)', Appendix P8 of our Deadline 8 submission for further detail. |  |  |  | Natural England continues to disagree with the Applicant regarding biotopes contributing to Annex 1 feature being classed as low value, particularly where they will be subject to permanent loss/change and therefore for which sensitivity cannot be used to downgrade overall value as per the Applicants outlined methods. However, we acknowledge these will be given further consideration in the RIAA. Please see our advice in 'Natural England's Comments on Environmental Statement Conclusions (from Rule 17 letter dated 19 June 2025)', Appendix P8 of our Deadline 8 submission for further detail.
C10 | C20 | We disagree with “Habitats or species that provide prey items for other species of conservation value” being considered of low value in the assessment. Of note are spawning/nursery grounds for sandeel and herring, both of which are an important prey resource for Annex I bird species and Annex II marine mammal features of designated sites. Within the wider marine environment impacts to habitats that provide prey availability may be considered as low, however it should be recognised that some areas remain more important than others. The importance of the ’Dogger Bank’ area for fish species is well documented. We advise that a generic low value can’t be attributed to all areas within the red line boundary. We also advise that impacts to benthic habitats which reduce/remove their ability to support benthic communities which are integral to maintaining populations of Annex I and II designated site features, needs to be fully considered within the ES. (See Sheet E for further comments on indirect effects) (7.09) |  | No change. |  | No change. We note the Applicant has contested the importance of the Dogger Bank sandbank system for prey availability and foraging species. Natural England disagrees with the justification provided and therefore maintains the advice provided in our Relevant Representation on this issue. |  | No change - no new information relevant to this issue has been submitted at this deadline. We refer you to ExQ HRA 1.3 response in Deadline 3 Appendix K. |  | No change - Natural England maintain our previous advice. |  | No change. Please see Appendix E5 of our Deadline 5 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue Progressed. Natural England welcome the Applicant's updates to the Effects on Prey Species Technical note [REP6-050]. We have provided further advice on this impact pathway in response to RIES questions 32, 46, 52,53 in Appendix N7 of our Deadline 7 submission. |  | Natural England maintains our previous advice concerns with “Habitats or species that provide prey items for other species of conservation value” being considered of low value in the assessment. Whilst we maintain our advice that a generic low value should not be attributed to all areas within the red line boundary, we note that this impact pathway has been given further consideration under HRA. Please see our response to RIES questions 32, 46, 52, 53 in [REP7-152] and Appendix P8 and B8 of our Deadline 8 submission. |  |  |  | Natural England maintains our previous advice concerns with “Habitats or species that provide prey items for other species of conservation value” being considered of low value in the assessment. Whilst we maintain our advice that a generic low value should not be attributed to all areas within the red line boundary, we note that this impact pathway has been given further consideration under HRA. Please see our response to RIES questions 32, 46, 52, 53 in [REP7-152] and Appendix P8 and B8 of our Deadline 8 submission.
C11 | C21, C31 | Loss of benthic habitat as a result of UXO clearance, particularly within Dogger Bank SAC, should be added to the worst-case calculation for the EIA and RIAA, whether it be temporary or otherwise. We advise that the Applicant also needs to evidence their claim that “craters would be expected to re-fill with sediment over the course of days” (applies to both UXO detonations and jack-up operations). If depressions are created from UXO clearance or jack-up operations in areas of coarse or mixed sediments, the area may need to be considered as permanent habitat change/loss unless it can be otherwise evidenced that they will backfill with similar sediment types. We consider that recovery is altogether unlikely within the irreplaceable NERC Section 41 habitats which have been identified within the red line boundary (i.e. Piddocks with a sparse associated fauna in sublittoral very soft chalk or clay). (7.09, 6.1, 7.05) |  | No change. The Applicant has provided a Review of Evidence on Recovery of Sandbank Habitat Following Habitat Damage [AS-025] in response to this issue. We will provide our comments on this document at Deadline 2. |  | No change. See Appendix C2.1 and Section 3 of Appendix F2 of Natural England's Deadline 2 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. Natural England welcomes the additional information provided by the Applicant in Appendix 1 of [REP3-022] however, the pathways of effect which have been considered do not address impacts from the creation of depressions from UXO clearance or jack-up operations in areas of coarse or mixed sediments. We continue to advise that impacts from the creation of depressions from UXO clearance or jack-up operations in areas of coarse or mixed sediments should be considered as permanent habitat change/loss (rather than temporary disturbance/damage) unless it can be otherwise evidenced that they will backfill with similar sediment types. Evidence from similar sediment types at Triton Knoll and Lincs OWFs are demonstrating that JUV leg depressions remain 2-10 years after installation. |  | No change. Natural England maintain our previous advice. See Appendix C5 for further details. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue progressed. We understand that the Applicant will update the RIAA HRA Part 2 of 4 Annex I Offshore Habitats and Annex II Migratory Fish (Revision 4) [REP4-014] at Deadline 7 on a without prejudice basis to include depressions from UXO clearance and jack-up operations as permanent habitat loss. Please also see Natural England's response to RIES Q12 and 18 in Appendix N of our Deadline 7 submission. |  | Natural England notes that on a without prejudice basis habitat loss from UXO clearance and use of jack up barge has been considered in the updated RIAA [REP7-017] and Project Level Dogger Bank Compensation Plan (R4) [REP7-021] we now consider this issue assessed for HRA issues. We will endeavour to review updated ES chapters in relation to access impact pathways for NERC Section 41 habitats and consideration of mitigation measures for Deadline 9.
C12 | C22, C44 | The Applicant has not committed to using any specific type of cable/scour protection and has not considered the limitations some methods present with regard to successful decommissioning and/or likelihood of degradation over the lifetime of the project, which could have wider impacts in the case of grout bags/bagged solutions. Due consideration should be given to the nature of the cable/scour protection used and should favour those engineering options with the greatest likelihood of successful removal at the Projects’ end of life. We advise against the use of rock protection within designated sites and against grout bags, unless filled with locally sourced sediment similar to that within the SAC. (7.05) |  | No change. To note: We believe the Applicant's response to comment C22 in [AS-048] may be an error and are therefore basing our response on their response to comment C43 (which has been signposted from the response to C44). |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - The Applicant has indicated that further consideration will not be given to this until post-consent. Natural England maintain our previous advice. |  | No change. |  | No change. As detailed at Deadline 4, the Applicant has indicated that further consideration will not be given to this until post-consent. We understand this to be their fixed position. Natural England also maintain our previous advice. We therefore do not believe that resolution will occur during examination. Therefore unless there is a change in the Applicant's position, our position will remain unchanged for the remainder of the examination. Please see Appendix C6 of Natural England's Deadline 6 submission in relation to public interest tests | [7 empty] | No change. As detailed at Deadline 4, the Applicant has indicated that further consideration will not be given to this until post-consent. We understand this to be their fixed position. Natural England also maintain our previous advice. We therefore do not believe that resolution will occur during examination. Therefore unless there is a change in the Applicant's position, our position will remain unchanged for the remainder of the examination. Please see Appendix C6 of Natural England's Deadline 6 submission in relation to public interest tests
C13 | C23 | We advise that the Applicant commits to bundling the export cables for each project as mitigation - this would halve the number of trenches needed (from two to one for each array) and reduce cable protection requirements. (7.05) |  | Issue progressed. We welcome the Applicant's commitment to bundling the export cables in the updated Cable Statement ([AS-079] 8.20 Cable Statement Rev 02). We advise that this commitment is secured in the DCO and/or commitment register and relevant application documents and assessments are revised accordingly. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue progressed. We welcome that this has been secured in C188 of the Commitments Register [REP2-026]. However, we continue to advise that this be secured within the DCO/dML. Please see ExQ BE1.1 response within Deadline 3 Appendix K. |  | No change - Natural England will provide further comments upon review of the Applicant's response to our Deadline 3 submissions. |  | Issue satisfactorily resolved. Whilst we would welcome this being conditioned within the DCO, we are satisfied with the Applicant's response [REP4-088] and that the updates to the Cable Statement, Commitments Register and RIAA sufficiently secure this commitment. | [9 empty] | Issue satisfactorily resolved. Whilst we would welcome this being conditioned within the DCO, we are satisfied with the Applicant's response [REP4-088] and that the updates to the Cable Statement, Commitments Register and RIAA sufficiently secure this commitment.
C14 | C24 | The provision of a Cable Statement/Cable Burial risk assessment is not embedded mitigation, as the specific commitments within the final detailed plans will be key in determining the effectiveness of the mitigation. Should further commitments and/or changes to project design be made by the Applicant, the impact assessment should be updated. (7.09, 6.1, 8.18) |  | No change. Please see Section 2 of our Deadline 1 cover letter for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. Whilst an updated Cable Burial Risk assessment was presented by the Applicant [REP2-040] no new information relevant to this issue has been submitted at this deadline. |  | No change - the Applicant has indicated that an updated Cable Statement will be provided at Deadline 4. |  | No change - see Point B49 and B50 for further detail. |  | No change. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. Please see Appendix B8 of our Deadline 8 submissions with regard to further consideration of mitgation measures |  |  |  | Please see Appendix B8 of our Deadline 8 submissions with regard to further consideration of mitgation measures
C15 | C26 | The RIAA will need updating to ensure that all revisions to the assessments are incorporated within it. |  | No change. Please see Section 3 of our Deadline 1 cover letter for further detail.
C16 | C27, C49 | We do not agree that an AEoI can be excluded from the disturbance/damage of Annex I sandbanks within the Dogger Bank SAC. Unlike more dynamic sandbanks, the length of time for recovery could be up to 25 years. We highlight that the R4 Plan Level benthic compensation includes the requirement for benthic compensation for disturbance/damage caused to Annex I ‘glacial till’ Annex I Sandbanks within Dogger Bank SAC. (6.1) |  | No change. Natural England are reviewing 10.44 Review of Evidence on Recovery of Sandbank Habitat Following Habitat Damage' [AS-025] and will provide further comment at Deadline 2. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. Please see response to ExQ BE 1.7 and 1.8 in Appendix K at Deadline 3. |  | No change - Natural England and the Applicant maintain their respective positions. It is unlikely that agreement will be reached on this matter. |  | No change. Natural England notes from the Applicants response to ExQ1 [REP4-087 page 76] that we continue to disagree in relation to this matter. Having thoroughly considered this, we do not believe that resolution will occur during examination. Therefore unless there is a change in the Applicant's position, our position will remain unchanged for the remainder of the examination. | [9 empty] | No change. Natural England notes from the Applicants response to ExQ1 [REP4-087 page 76] that we continue to disagree in relation to this matter. Having thoroughly considered this, we do not believe that resolution will occur during examination. Therefore unless there is a change in the Applicant's position, our position will remain unchanged for the remainder of the examination.
C17 | C29 | Penetration and/or disturbance of the substratum below the surface of the seabed, including abrasion, should be screened in for the Operation and Maintenance phase for Dogger Bank SAC. (6.1) |  | Issue progressed. The Applicant has clarified that this impact was screened in. We advise that the relevant Tables (6-4, 6-6) in APP-046 are updated to reflect this. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. The Applicant has indicated an updated RIAA will be provided at Deadline 4 [REP3-027]. |  | Issue resolved. Tables 6-4 and 6-6 of the updated (6.1) Report to Inform Appropriate Assessment (RIAA) Habitats Regulations Assessment (HRA) Part 2 of 4 [REP4-015] have been updated to include this effect. | [9 empty] | Issue resolved. Tables 6-4 and 6-6 of the updated (6.1) Report to Inform Appropriate Assessment (RIAA) Habitats Regulations Assessment (HRA) Part 2 of 4 [REP4-015] have been updated to include this effect.
C18 | C30 | Full consideration of the likely nature, extent, duration, and significance of impacts upon SPA and SAC supporting habitats is required to inform a robust assessment of the likely impacts upon designated ornithological and marine mammal features. We consider that this has not been adequately undertaken for sites including Flamborough and Filey Coast SPA and the Southern North Sea SAC. (7.09) |  | No change. |  | No change. We note the Applicant has contested the importance of the Dogger Bank sandbank system for prey availability and foraging species. Natural England disagrees with the justification provided and therefore maintains the advice provided in our Relevant Representation on this issue. |  | No change - no new information relevant to this issue has been submitted at this deadline. Please see response to ExQ HRA 1.3 in Appendix K at Deadline 3. |  | No change - The Applicant has indicated that a technical note relevant to this issue will be submitted at Deadline 4. |  | No change. Natural England does not consider that [REP4-093] progresses this issue. See Appendix C5 and E5 for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. Please see our response to RIES Q52 in Appendix N7 of our Deadline 7 submission. |  | No change. We maintain our advice on the importance of the Dogger Bank sandbank system for prey availability and foraging species. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology for further detail. |  |  |  | We maintain our advice on the importance of the Dogger Bank sandbank system for prey availability and foraging species. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology for further detail.
C19 | C33 | The worst-case suspended sediment concentrations from trenching activities in the ECC are inconsistent between the RIAA and EIA chapters - we advise that the EIA and/or RIAA are updated with accurate worst-case prediction values as needed. (6.1, 7.09) |  | Issue progressed. Natural England welcome the clarification provided by the Applicant in their response [AS-048] to our Rel Rep [RR-039] (C33), confirming that some of the values presented were incorrect. We will provide further comment at Deadline 2. |  | Issue progressed. As noted at DL1, the Applicant has provided clarification on the WCS SSC due to cable trenching within the array areas and offshore export cable corridor. The Applicant considers that the correction does not alter the assessment conclusions reached in the Benthic Ecology chapter [APP-085] or RIAA HRA Part 2 of 4 [APP-046]. We advise that relevant documents are updated to reflect these changes and to fully resolve this issue. We also seek confirmation from the Applicant that the predicted worst-case values for sediment deposition resulting from a sediment plume (due to trenching) have not changed as well. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. The Applicant has indicated an updated RIAA will be provided at Deadline 4 [REP3-027]. |  | Issue progressed. We note that Table 6-3 in the updated (6.1) Report to Inform Appropriate Assessment (RIAA) Habitats Regulations Assessment (HRA) Part 2 of 4 [REP4-015] has been updated. We will provide further comment once further updates are provided at Deadline 7. | [5 empty] | The Applicant has submitted an updated ES chapter 9 [REP7-039] and 6.1 RIAA 2 of 4 –Annex I Offshore Habitats and Annex II Migratory Fish (Revision 5) [REP7-017]. We will provide further comment at Deadline 9. Please see our Deadline 8 cover letter for our approach to the final two deadlines.
C20 | C34 | The Applicant has calculated an ‘as built’ estimate for habitat loss for consented projects within Dogger Bank SAC to inform impacts to extent and distribution. These are not legally secured, thus we advise that consented parameters should be used to inform habitat loss estimates for assessment. (6.1) |  | Issue addressed. We welcome the confirmation from the Applicant that the habitat loss estimate based on consented parameters was used in the assessment. | [17 empty] | Issue addressed. We welcome the confirmation from the Applicant that the habitat loss estimate based on consented parameters was used in the assessment.
C21 | C35 | Clarification is required on the WCS for sandwave levelling/seabed clearance. We also advise that within benthic MPAs any sediment deposition is located within areas of similar sediment type, as close to and upstream of the original sandwave, and is deposited using a fall pipe (should a suction hopper dredger be used). An outline sandwave levelling, deposition and recovery plan should be provided as either a standalone document or as part of the Cable Statement [APP-242] /Outline Cable Burial Risk Assessment. (6.1, 7.09, 8.18) |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. However, we note that the Applicant has indicated that the Cable Statement would be updated to include detail relating to sandwave levelling and deposition. The most current version of this (8.20 Cable Statement, Rev 02, [AS-079]) does not include such update. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. We note there is a potential for this to become a red risk depending on the Applicant's response. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. Natural England maintain our previous advice. With regards to sediment deposition, the Applicant has stated [REP3-028] that they can commit to depositing like sediment on like sediment (within Dogger Bank SAC) and has indicated that an updated Cable Statement will be provided at Deadline 4 [REP3-028] to reflect such changes. We will provide further comment accordingly. |  | Issue progressed. Natural England welcomes that the Cable Statement [REP4-051] has been updated with a commitment to deposit like sediment on like sediment both within and beyond the boundary of Dogger Bank SAC during sandwave levelling. However, additional commitments to mitigation remain required. See Appendix B5 of Natural England's Deadline 5 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. See Sheet B - Marine Physical Environment (Point B17). |  | No Change. The commitment to depositing like on like sediment in Commitments Register (rev03) [REP7-102] under Ref C192 is welcomed. However, it is unclear whether the Applicant will be providing a sandwave characterisation report as advised in this point at Deadline 7. In addition, we note [REP7-131] that there is no change to the Applicant's position on the use of a fall pipe for depositing dredged sediment and updrift of the sandwave - we maintain our advice on this. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology for further detail regarding this. |  |  |  | The commitment to depositing like on like sediment in Commitments Register (rev03) [REP7-102] under Ref C192 is welcomed. However, it is unclear whether the Applicant will be providing a sandwave characterisation report as advised in this point at Deadline 7. In addition, we note [REP7-131] that there is no change to the Applicant's position on the use of a fall pipe for depositing dredged sediment and updrift of the sandwave - we maintain our advice on this. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology for further detail regarding this.
C22 | C36 | We do not agree with the RIAA assessment that habitat loss impacts in Dogger Bank SAC are “minimal”. Taking into account the many anthropogenic activities occurring and planned across the Dogger Bank SAC, when all pressures are summed it will lead to an adverse effect on the site integrity, as concluded in the Plan Level HRA. (6.1) |  | N/A
C23 | C37, C48 | We do not agree with the worst-case calculation of area of loss due to change to another seabed/sediment type for Dogger Bank SAC presented in the RIAA as we are not confident that the calculations are based on realistic worst-case calculations (C12, C13, C18, C35). We advise that a robust assessment is provided of the potential Worst-Case area of impact on benthic communities within Dogger Bank SAC sandbank feature. Consideration should be given to the nature of the impact as a result of changes to physical and biological processes, following the placement of structures and cable/scour protection on the seabed. (6.1) See also C18. |  | No change - Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. See point C8 for further information. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. See point C8 for further information. |  | No change. See point C8 for further information. |  | Issue progressed. The Applicant has presented an assessment of ecological halo effects [REP5-041]. However, we consider that the estimate for worst case area of loss needs further revision. Please see Appendix C6 of Natural England's Deadline 6 submission for further details. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. Natural England continues to have concerns in relation to the provision of a realistic worst case scenario. Please see Appendix B8 of our Deadline 8 submissions |  |  |  | Natural England continues to have concerns in relation to provision of a realistic worst case scenario. Please see Appendix B8 of our Deadline 8 submissions
C24 | C39 | Natural England advise that a tidal ellipse is used to estimate the zone of greatest influence for sediment plumes for the array area and export cable corridor. We note that the Zone of Influence (ZoI) for suspended sediment has been updated to 8km (6.1, Table 6-1) based on site specific physical processes modelling undertaken. It is unclear as to where the 8km ZoI is derived from. The Applicant should provide further clarity on estimated sediment plume sizes including which values have been used to assess for Changes in Suspended Sediment Concentration and Transport due to Cable Installation (Array, Inter Platform and Export) and smothering and siltation for all relevant parts of the Application. (6.1, 7.08) |  | No change. We welcome the clarification provided in the Applicant's response that the 8km ZoI is incorrect, we will provide further comment at Deadline 2. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. Please see our Appendix L at Deadline 3. |  | Issue resolved. We welcome the Applicant's clarification on the Zone of Influence (ZoI) used to inform the impact assessment based on numerical modelling as provided in [REP3-026]. | [11 empty] | Issue resolved. We welcome the Applicant's clarification on the Zone of Influence (ZoI) used to inform the impact assessment based on numerical modelling as provided in [REP3-026].
C25 | C10, C41 | A drill arising footprint has not been provided. The placement of drill arisings adjacent to turbines may result in further habitat loss/change. As mitigation, the Applicant should commit to the placement of drill arisings in areas of similar habitat/particle size. Otherwise, this will need to be assessed similar to that of scour prevention/cable protection as a lasting impact included within the AEoI for Dogger Bank SAC and commitments to remove at the time of decommissioning will be required. (6.1) |  | No change - Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change. We maintain our previous advice that the placement of drill arisings adjacent to turbines may result in further habitat loss/change. If drill arisings cannot be placed in areas of similar habitat / particle size, further assessment for habitat loss will be required. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. |  | Issue progessed. A footprint for drill arisings has been provided in Table 4-3 of [AS-141], however the remainder of this issue is unaddressed. |  | No change. The Applicant has stated that drill arisings would be located adjacent to turbine foundations and within the scour protection footprint so would be captured within the existing habitat loss estimates. Natural England require further clarification on how this would be achieved in practice. See Appendix C4 for further detail. |  | No change. We maintain our previous advice. We note that the Applicant has updated Table 1-3 of the IPMP [REP4-053] stating "Should drilling be utilised to install piled foundations, the Applicants will seek to ensure that no drill mounds (i.e. sediment arising from the drilling of the Projects foundations) persist above 3m from the surrounding seabed. In the event that such drill mounds greater than 3m are found to persist, an appropriate monitoring campaign will be developed in consultation with the MMO". However, we maintain that drill arisings, should be deposited within similar sediment. We continue to query the feasbility of placing drill arising adjacent to the turbines therefore if it can be guaranteed that they will be in the footprint of any scour prevention. In addition, if within the scour prevention and cable protection footprint it compromises any commitments to only utilise removable material i.e. not rock. We also query what would happen in the likely event that it moves into surrounding Annex I sandbanks noting that arisings are not likely to behave the same as Norwegian granite designed to protect infrastructure. We advise this all requires further consideration |  | No change - The Applicants submission REP5-037 doesn't address our concerns raised in previous advice. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. Our advice from Deadline 5 remains unchanged |  |  |  | Natural England remains concerned by the additional impacts posed by the placement of drill arisings. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology.
C26 | C42 | We advise that gravity based foundations are not used for offshore platforms. (6.1) |  | No change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change |  | Issue progressed. As outlined in [AS-141], GBS foundations have been removed from the Projects’ design envelope. We advise that all relevant ES documents are updated to reflect this. |  | No change - updates to ES documents are required to resolve. We will provide further comment once updates are provided at Deadline 7. | [7 empty] | The Applicant has submitted an updated ES chapter 9 [REP7-039]. We will provide further comment at Deadline 9. Please see our Deadline 8 cover letter for our approach to the final two deadlines.
C27 | C43 | A commitment to remove all on and above seabed infrastructure (including cable and scour protection) at the time of decommissioning should be secured in the DCO, as has been required for all offshore wind farms previously consented within the Dogger Bank SAC. (7.05) |  | No change. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. Natural England maintain our previous advice. See Appendix C4 of our Deadline 4 submission for further detail. |  | No change. We have reviewed the Applicant's position regarding infrastructure decommissioning and continue to disagree with it. We do not believe it is in the spirit of the Strategic Compensation Strategy or Marine Recovery Fund. In addition, there is no certainty that the Applicant will be able to use the MRF in the way they propose as the policy is not yet final. Therefore, we advise that they are planning at own risk until the MRF launches and the guidance is published. We are in discussions with DEFRA and DESNZ benthic compensation and MRF teams (respectively) and we will provide further update at Deadline 6. |  | No Change - Please see Appendix C6 of Natural England's Deadline 6 submission in relation to public interest tests |  | Issue progressed. The Applicants have committed [REP6-044] to consider removability of cable protection as part of the development of the final Cable Statement and Decommissioning Programme to be produced for submission to the SoS pre construction. Whilst this is welcome, it is not sufficient to resolve concerns regarding the lack of a full commitment to decomissioning. |  | No change. We maintain our previous advice. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology. |  |  |  | We maintain our previous advice. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology.
C28a | C45 | The Applicant has given consideration to identifying areas of shallow glacial till in the Offshore Development Area to inform post-consent discussions on micrositing cables. However, the DCO conditions listed do not secure this as they only refer to identifying priority habitats, which would not include glacial till. We advise this mitigation should be applicable to underlying glacial sediments within Dogger Bank SAC as well as priority habitat identified along the ECC, e.g. piddocks. We advise that the DCO conditions listed are updated to secure this. |  | Issue resolved. The relevant DCO conditions have been updated to include surficial deposits of glacial till [AS-121]. For consistency, we would welcome this also being updated in the Commitments Register. | [17 empty] | Issue resolved. The relevant DCO conditions have been updated to include surficial deposits of glacial till [AS-121]. For consistency, we would welcome this also being updated in the Commitments Register.
C28b | C45 | A pre-consent Outline Cable Burial Risk Assessment within an updated Cable Statement should also be provided which considers all available geotechnical information to implement mitigation measures which further avoid, reduce and mitigate impacts by ensuring that optimal cable burial depths can be achieved, thus avoiding/reducing the need for cable protection and enabling a realistic worst case scenario to be assessed. (7.09) |  | No change. We continue to advise that an updated Outline Cable Burial Risk Assessment is provided. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue progressed. The Applicant has provided an updated Cable Statement which includes an updated Cable Burial Risk Assessment for the Export Cable Route [REP2-040], but not for the Array Areas. If available, this should be provided as well. |  | No change. The Applicant has indicated that further geotechnical surveys will be undertaken in 2025, however no further revisions will be made to the CBRA within Examination timeframes [REP3-028]. See B3 and B4. |  | No change. |  | No change. The Applicant has indicated that further consideration will not be given to this until post-consent. We understand this to be their fixed position. Natural England also maintain our previous advice. We therefore do not believe that resolution will occur during examination. Therefore unless there is a change in the Applicant's position, our position will remain unchanged for the remainder of the examination. Please see Appendix C6 of Natural England's Deadline 6 submission in relation to public interest tests |  |  |  | No change. We maintain our previous advice. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology. |  |  |  | No change. We maintain our previous advice. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology.
C29 | C46 | We note the Applicant’s comparison to the scale of impact from fisheries on Dogger Bank SAC compared to OWF, and the recent introduction of byelaws and closure of the sandeel fishery enabling recovery of the sandbank feature from this pressure. Whilst we acknowledge that fishing activity has historically had a broader impact on Dogger Bank, this does not reduce or negate the impacts of other industries which are additional to pre-existing impacts. Neither does mitigation introduced for the impacts of one industry remove the need for another industry to mitigate its impacts. (6.1) |  | N/A | [17 empty] | We note the Applicant’s comparison to the scale of impact from fisheries on Dogger Bank SAC compared to OWF, and the recent introduction of byelaws and closure of the sandeel fishery enabling recovery of the sandbank feature from this pressure. Whilst we acknowledge that fishing activity has historically had a broader impact on Dogger Bank, this does not reduce or negate the impacts of other industries which are additional to pre-existing impacts. Neither does mitigation introduced for the impacts of one industry remove the need for another industry to mitigate its impacts. (6.1)
Priority Habitats and Species listed under Section 41 list of the Natural Environmental and Rural Communities (NERC) Act, 2006 - Document(s) Used: [APP-085] 7.09 ES Chapter 9 – Benthic and Intertidal Ecology |  |  |  | Documents reviewed: [AS-121] 3.1 Draft Development Consent Order (Rev 03) (Tracked)
C30 | C51 | The identified biotope ‘A4.231 Piddocks with a sparse associated fauna in sublittoral very soft chalk or clay’ (and peat and clay exposures more generally) is considered likely to be irreplaceable and is also a priority habitat. The EIA would benefit from considering the importance and rarity of peat and clay exposures - every effort should be made to avoid impacts to these priority habitats, particularly where habitats support rare and/or irreplaceable communities such as boring piddocks. (7.09) |  | Issue resolved. The Applicant has considered pre-construction surveys and micro-siting. See comment below (point C31) for further information. | [17 empty] | Issue resolved. The Applicant has considered pre-construction surveys and micro-siting. See comment below (point C31) for further information.
C31 | C52 | There is no strong commitment to avoid/microsite around Priority Habitats as listed under Section 41 of the NERC Act 2006. The adoption of mitigation measures via a Benthic Mitigation Plan should be further considered in order that impacts (particularly permanent loss), on all Section 41 Habitats are avoided and/or reduced wherever feasible through mitigation measures such as micro-siting. (7.09) |  | Issue resolved. The Applicant has provided an update to the DCO [AS-121] 3.1 Draft Development Consent Order (Rev 03) (Tracked) setting out micro-siting requirements. | [17 empty] | Issue resolved. The Applicant has provided an update to the DCO [AS-121] 3.1 Draft Development Consent Order (Rev 03) (Tracked) setting out micro-siting requirements.
Disposal of material arising from construction activities - Document(s) Used: [APP-242] 8.18 Disposal Site Characterisation Report
C32 | C54 | This document will need updating pre-consent based on comments Natural England has provided on the EIA within Appendix B and C as currently we do not agree with conclusions on the level of impacts. (8.18) |  | No change. |  | No change. We continue to advise that this document will need updating pre-consent. |  | Issue progressed. The Applicant has provided an updated Disposal Site Characterisation Report [REP2-035] whereby values for the worst case scenarios have been updated. These changes are welcome and reduce the worst case parameters / impacts originally assessed in Chapter 9 Benthic Ecology [APP-085]. However, the reductions do not result in any changes to the outcomes of the original assessments - we continue to advise that that this document will need updating based on comments provided within worksheets B and C of this R&I log as we currently do not agree with conclusions on levels of impacts. |  | No change. |  | No change. |  | No Change. An updated Disposal Site Characterisation Report has been submitted [REP5-026]. Please see comments below and Appendix B6 of our Deadline 6 submission. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | An updated Disposal Site Characterisation Report (rev04) has been submitted [REP7-114], however the updates are related to location of disposal sites. Please see comments below for outstanding issues.
C33 | C55 | The whole of the offshore windfarm array footprints, the inter-cable platform corridor and the export cable corridors will be disposal locations, but deposition will only occur where possible within the same sediment. Given that sandwave levelling is likely to be undertaken by suction hopper dredge and then sediment released at the sea surface, it is unlikely that this will occur. We advise that disposal options are explored to ensure that sediment is deposited in similar sediment types. (8.18) |  | No change. Please see point C21. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. We note there is a potential for this to become a red risk depending on the Applicant's response. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue progressed. The Applicant has stated [REP3-027] (ExQ BE.1.15) / [REP3-028] they will commit to depositing like sediment on like sediment with respect to surficial sand, gravel and silt within Dogger Bank SAC. Separate disposal areas for DBS East, West and the ECC have also been defined and secured in the DCO. We will provide further comment accordingly. An updated Cable Statement will be provided at Deadline 4 to reflect this, but highlight that as with other developments currently in Examination which are impacting on Annex I sandbanks, commitments to desposit adjacent to and updrift of the sandbank using a fall/down pipe is also required to fully mitigate impacts. |  | Issue progressed. The Applicant has committed to depositing like sediment on like sediment both within and outside of Dogger Bank SAC in the updated Cable Statement, this should be secured in the Commitment Register. Please see Appendix B5 for further advice on outstanding mitigation measures. |  | No change. We note that the Applicant does not intend to commit to depositing sediment updrift of dredging locations. No further information has been provided with respect to using a fall pipe for deposition. See Appendix B6 of Natural England's Deadline 6 submission for further detail. |  | Issue progressed. See Sheet B - Marine Physical Environment (Point B17). |  | No Change. The commitment to depositing like on like sediment in Commitments Register (rev03) [REP7-102] under Ref C192 is welcomed. However, it is unclear whether the Applicant will be providing a sandwave characterisation report as advised in this point at Deadline 7. In addition, we note [REP7-131] that there is no change to the Applicant's position on the use of a fall pipe for depositing dredged sediment and updrift of the sandwave - we maintain our advice on this. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology for further detail regarding this. |  |  |  | No Change. The commitment to depositing like on like sediment in Commitments Register (rev03) [REP7-102] under Ref C192 is welcomed. However, it is unclear whether the Applicant will be providing a sandwave characterisation report as advised in this point at Deadline 7. In addition, we note [REP7-131] that there is no change to the Applicant's position on the use of a fall pipe for depositing dredged sediment and updrift of the sandwave - we maintain our advice on this. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology for further detail regarding this.
C34 | C56 | We advise the mitigation in Section 5.2 does not go far enough, especially within the Dogger Bank SAC and in areas where there are priority habitats and/or indirect impacts to designated site features could occur. We advise that the following mitigation measures are adopted (but not exclusively): - All deposition of dredged sediment within the Dogger Bank SAC should be done through the use of a fall pipe and adjacent and upstream of the dredge location in same sediment type to ensure sediment stays within the site. - Drill arisings should be deposited within similar sediment characteristics i.e. not on sandbanks. Therefore, adjacent to turbines is unlikely to be appropriate. - Sandwave deposition should avoid areas of priority habitats under NERC 2006 by the inclusion of a 50m buffer around the NERC habitats. - Deposition of dredge material along the export cable should utilise a fall pipe where there is a risk of increases in suspended sediment concentrations impacting on designated site features and those of ecological importance. (8.18) |  | No change. Please see point C21 and C25. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. We note there is a potential for this to become a red risk depending on the Applicant's response. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. See Point C25 re drill arisings. The Applicant has stated [REP3-027] (ExQ BE.1.15) / [REP3-028] they will commit to depositing like sediment on like sediment with respect to surficial sand, gravel and silt within Dogger Bank SAC. An updated Cable Statement will be provided at Deadline 4 to reflect this. We will provide further comment accordingly. |  | Issue progressed. The Applicant has committed to depositing like sediment on like sediment both within and outside of Dogger Bank SAC in the updated Cable Statement, this should be secured in the Commitment Register. Please see Appendix B5 for further advice on outstanding mitigation measures. |  | No change. We note that the Applicant does not intend to commit to depositing sediment updrift of dredging locations. No further information has been provided with respect to using a fall pipe for deposition. See Appendix B6 of Natural England's Deadline 6 submission for further detail. |  | Issue progressed. See Sheet B - Marine Physical Environment (Point B17) |  | No Change. The commitment to depositing like on like sediment in Commitments Register (rev03) [REP7-102] under Ref C192 is welcomed. However, it is unclear whether the Applicant will be providing a sandwave characterisation report as advised in this point at Deadline 7. In addition, we note [REP7-131] that there is no change to the Applicant's position on the use of a fall pipe for depositing dredged sediment and updrift of the sandwave - we maintain our advice on this. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology for further detail regarding this. |  |  |  | No Change. The commitment to depositing like on like sediment in Commitments Register (rev03) [REP7-102] under Ref C192 is welcomed. However, it is unclear whether the Applicant will be providing a sandwave characterisation report as advised in this point at Deadline 7. In addition, we note [REP7-131] that there is no change to the Applicant's position on the use of a fall pipe for depositing dredged sediment and updrift of the sandwave - we maintain our advice on this. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology for further detail regarding this.
C35 | C57 | For intertidal exit pits, we advise that alternative storage options for material from the landfall exit pits are explored (see also comments (B15) Appendix B) |  | No change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change |  | Issue resolved. As detailed in [AS-141], the short trenchless crossing and intertidal exit pits have been removed from the project design envelope. | [13 empty] | Issue resolved. As detailed in [AS-141], the short trenchless crossing and intertidal exit pits have been removed from the project design envelope.
Scour Prevention - Document(s) Used: [APP-251] 8.27 Outline Scour Protection Plan
C36 | C58, C59 | We advise that this document needs to better consider risk and implications of secondary scouring and highlight the need to minimise environmental impacts thourgh choice of scour prevention / cable protection. |  | See Sheet B - Marine Physical Environment (Point B47-B48). |  | See Sheet B - Marine Physical Environment (Point B47-B48). |  | See Sheet B - Marine Physical Environment (Point B47-B48). |  | No change. See Sheet B - Marine Physical Environment (Point B47-B48). |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue progressed. Natural England note that monitoring commitments for secondary scour have been strengthened in the IPMP [REP5-028]. See Appendix B6 of Natural England's Deadline 6 submission for further detail regarding scour monitoring. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. The Applicant has a commitment within the IPMP (rev05) [REP7-116] to pre- and post-construction monitoring of the seabed through the collection of geophysical survey data and have provided a further update to the IPMP stating "If nearshore external cable protection is installed it will be monitored, along with associated sediment accretion and scour". However, this does not go far enough as the Applicant has not provided sufficient remediation measures should monitoring demonstrate effects are greater than predicted. |  |  |  | No change. The Applicant has a commitment within the IPMP (rev05) [REP7-116] to pre- and post-construction monitoring of the seabed through the collection of geophysical survey data and have provided a further update to the IPMP stating "If nearshore external cable protection is installed it will be monitored, along with associated sediment accretion and scour". However, this does not go far enough as the Applicant has not provided sufficient remediation measures should monitoring demonstrate effects are greater than predicted.
C37 | NEW | [6 empty] | We highlight that as the final SCP will be provided post-consent, if the impacts of plastic based scour protection have not been included and/or fully assessed as part of the Application Environmental Statement/RIAA, a further assessment will be required at that time. And depending on the outcome may require an additional HRA assessment to inform Condition Discharge. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue Progressed. Whilst the Applicant acknowledges that use of plastics associated with scour/cable protection will require further assessment in [REP4-088], we advise that to resolve this matter a named plan should be updated to commit to considering this pre construction when final design plans are submitted. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue resolved. The Applicant has updated the Outline Scour Protection Plan [REP6-046] stating that, should they be selected for use, relevant assessments of the impacts of plastic-based scour protection will be included in the final Scour Protection Plans | [5 empty] | Issue resolved. The Applicant has updated the Outline Scour Protection Plan [REP6-046] stating that, should they be selected for use, relevant assessments of the impacts of plastic-based scour protection will be included in the final Scour Protection Plans
Cable Statement - Document(s) Used: Document used: [APP-243] 8.20 Cable statement
C38 | C60 | This document will need updating pre-consent based on comments Natural England has provided on the EIA within Appendix B and C, as we currently do not agree with conclusions included within the document. (8.20) |  | See Sheet B - Marine Physical Environment (Point B49). |  | See Sheet B - Marine Physical Environment (Point B49). |  | See Sheet B - Marine Physical Environment (Point B49). |  | No change - the Applicant has indicated that an updated Cable Statement will be provided at Deadline 4, however the CBRA will not be updated again within Examination timeframes. |  | See Sheet B - Marine Physical Environment (Point B49). |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | See Sheet B - Marine Physical Environment (Point B49). |  | No change. The Applicant has stated that an updated final Cable Statement will be produced for submission to the SoS. This will include a sandwave levelling, deposition, and recovery plan and consideration of removability of cable protection measures. However, our other recommendations at Rel Reps will need to be addressed. |  |  |  | No change. The Applicant has stated that an updated final Cable Statement will be produced for submission to the SoS. This will include a sandwave levelling, deposition, and recovery plan and consideration of removability of cable protection measures. However, our other recommendations at Rel Reps will need to be addressed.

## D - Benthic Compensation
Point | Point Number(s) from Appendix D [RR-039] | Taken from Natural England’s Relevant and Written Representations Dogger Bank South (East and West) Appendix D - Benthic Compensation | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Consultation, actions, progression | RAG Deadline 9 | End of Examination Position | Issue Resolved
Compensation Measure: New site designation or Extension for Annex I Sandbanks
D1 | Agreed compensation level | The SNCBs are not in agreement on the presented WCS of habitat damage of Annex I Sandbanks within Dogger Bank SAC. We advise that the points raised in Appendix B and C of our Relevant Representations/Written Representations (RR/WR) are addressed. |  | No change. |  | Please see Natural England's Deadline 2 cover letter |  | Please see our response to Examiner's Questions (ExQ) BE.1.6-1.8 in Appendix K, and Appendix C3 of Natural England's Deadline 3 submission for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No change. |  | No change. |  | No change. |  | No change.
D2 | Scale/extent of measure | The SNCBs have outstanding concerns about the outcomes of the Impact Assessment and evidence used to support conclusions on scale and significance of potential impacts from cable installation activities and cable protection installation from DBS. Until these issues are resolved we do not agree with the scale and extent of the compensation measures required. This compensation measure will be led by DEFRA (with interested parties), therefore delivery mechanisms, scale costs and timeframes presented by the Applicant cannot and should not be relied upon. |  | No change. |  | Please see Natural England's Deadline 2 cover letter |  | Please see our response to Examiner's Questions (ExQ) BE.1.6-1.8 in Appendix K of Natural England's Deadline 3 submission for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No change. We have reviewed the Applicant's position regarding infrastructure decommissioning and continue to disagree with it. We do not believe it is in the spirit of the Strategic Compensation Strategy or Marine Recovery Fund. In addition, there is no certainty that the Applicant will be able to use the MRF in the way they propose as the policy is not yet final. Therefore, we advise that they are planning at own risk until the MRF launches and the guidance is published. We are in discussions with DEFRA and DESNZ benthic compensation and MRF teams (respectively) and we will provide further update at Deadline 6. |  | No Change - Please see Appendix C6 of Natural England's Deadline 6 submission in relation to public interest tests |  | No change. Whilst we understand that the Applicant's position on this remains unchanged, we note [REP6-052] that the Applicant will be submitting an updated RIAA HRA Part 2 of 4 Annex I Offshore Habitats and Annex II Migratory Fish, Habitats Regulations Derogation: Provision of Evidence and Project Level Dogger Bank Compensation Plan at Deadline 7 to include without prejudice estimates for habitat loss including UXO clearance areas and jack-up footprints. This information may be helpful for determining the scale of required compensation should the SoS conclude that habitat disturbance contributes to AEoI. We will provide comment accordingly. |  | We welcome the Applicant providing a without prejudice figure based on 50m halo impact from cable protection. But if a reduced buffer for halo effects from cable protection can be agreed then we recognise that the compensation requirement will be reduced and amounts will fall between 5km2 and 13.2km2 for habitat loss
D3 | Timing: Deliverable before impact | We recognise that there are likely to be time lags between impact occurring and compensation achieving the desired outcomes. In this scenario, the SNCBs would wish to see the project contribution to the measure to be such that it ensures an overall environmental net positive outcome for the impacted feature over the lifetime of the project. We advise that the points raised in Appendix B and C of our RR/WR are addressed. |  | See response to ISH agenda item 6.3 in Annex 2 of our Deadline 1 cover letter. |  | Please see Natural England's Deadline 2 cover letter |  | No change. This will be for DEFRA to determine as part of the strategic compensation | [13 empty] | No change. This will be for DEFRA to determine as part of the strategic compensation
D4 | Location of measure; Long term implementation; Success criteria/Ability to prove additionality. | This is still under consideration by DEFRA, NE and JNCC and as yet, nothing has been agreed and/or secured. If and when further information becomes available during Examination we will update accordingly. However, any assurances in the security of this measure should be sought directly from DEFRA. |  | See response to ISH agenda item 6.3 in Annex 2 of our Deadline 1 cover letter. |  | Please see Natural England's Deadline 2 cover letter |  | No Change. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No change. |  | No change. | [7 empty] | No change. This will be for DEFRA to determine as part of the strategic compensation
Compensation Measure: Reduction of fishing pressures as a supplementary measure for Annex I Sandbanks
D5 | Theoretical merit to deliver compensation | The use of byelaws to remove fisheries pressures from another SAC has ecological merit. However, outside of a designated site this would require legislative changes to address impacts from other industries that could still occur. It is unclear how this measure will ensure the coherence of the National Site Network. We note that this is a ‘supplementary’ measure if site extension fails and is outside of the SNCBs’ remit. |  | No change. |  | No Change |  | Following publication of the DESNZ Written Ministerial Statement, the Applicant has removed Reduction of Fishing Pressures from their Dogger Bank Compensation Plan [REP2-103]. Natural England supports this decision. | [13 empty] | Following publication of the DESNZ Written Ministerial Statement, the Applicant has removed Reduction of Fishing Pressures from their Dogger Bank Compensation Plan [REP2-103]. Natural England supports this decision.
D6 | Technical feasibility | Fisheries removal inside or outside of a designated site is not considered viable within the Project’s timeframe. Within designated sites the MMO and EIFCA are already implementing byelaws to reduce fisheries pressures and any option outside of a designated site will need agreement from The Crown Estate. Note, outside of designated sites this measure will not be taken forward in the R4 Plan Level Compensation Plan. The evidence is similar to that for strategic compensation for site designation / extension. Therefore we advise that a new designation/designated site extension would be the preferred mechanism. |  | No change. |  | No Change |  | As above. | [13 empty] | As above.
D7 | Agreed compensation level | The SNCBs are currently not in agreement with the Applicant on the presented WCS of habitat damage of Annex I Sandbanks within Dogger Bank SAC. The SNCBs advise that the points raise in Appendices B and C of our RR/WR are addressed. |  | No change. |  | No Change |  | As above. | [13 empty] | As above.
D8 | Scale/extent of measure | The scale/extent of the measure has not been presented in detail and/or agreed with Natural England, JNCC or DEFRA. |  | No change. |  | No Change |  | As above. | [13 empty] | As above.
D9 | Timing: Deliverable before impact | We do not believe that this measure will be available in the project timeframes. This is outside of the SNCB remit and the Applicant will need to liaise with TCE, DEFRA, MMO (and EIFCA depending on location). |  | No change. |  | No Change |  | As above. | [13 empty] | As above.
D10 | Location of measure | The location of the measure has not been presented in detail and/or agreed with TCE, Natural England, JNCC or DEFRA. This is outside of the SNCB remit and the Applicant will need to liaise with TCE, DEFRA, MMO (and EIFCA depending on location). |  | No change. |  | No Change |  | As above. | [13 empty] | As above.
D11 | Long term implementation & Success criteria/Ability to prove additionality | There is a requirement for changes in legislation for the delivery of this measure outside of designated sites and therefore until that is secured further long-term implementation remains unknown. This is outside of the SNCB remit and the Applicant will need to liaise with TCE, DEFRA, MMO (and EIFCA depending on location). |  | No change. |  | No Change |  | As above. | [13 empty] | As above.
D12 | Suitable as sole measure for target species | We do not believe that this is currently suitable as a sole compensatory measure. But this may change post examination of this project. |  | No change. |  | No Change |  | As above. | [13 empty] | As above.
Compensation Measure: Seagrass Habitat Creation/Restoration for Annex 1 sandbanks
D13 | Theoretical merit to deliver compensation. | Please see the published ‘Offshore Wind Leasing Round 4 Dogger Bank Strategic Compensation Plan (April 2024). In section 3.4.2 it is stated that “seagrass restoration is a lower preference measure compared to those supporting the same ecological function of the habitat being compensated for”. We advise the same is true for project level compensation and welcome this not being progressed by the Applicant at this time. |  | No change. |  | No Change |  | Following publication of the DESNZ Written Ministerial Statement, the Applicant has removed Seagrass Habitat Creation/Restoration from their Dogger Bank Compensation Plan [REP2-103]. Natural England supports this decision. | [13 empty] | Following publication of the DESNZ Written Ministerial Statement, the Applicant has removed Seagrass Habitat Creation/Restoration from their Dogger Bank Compensation Plan [REP2-103]. Natural England supports this decision.
D14 | Technical feasibility | Please see section 3.4.3 of ‘Offshore Wind Leasing Round 4 Dogger Bank Strategic Compensation Plan’ (April 2024) where the Steering Group's significant concerns about the deliverability of seagrass restoration are summarised. Further, "The measure is retained in the DBSCP as an additional option which could potentially be employed if the Steering Group considered that it was necessary to supplement other measures, or potentially as an adaptive management response". This is also applicable to project level compensation. NE is in the process of drafting a paper on the current seagrass restoration projects. |  | No change. |  | No Change |  | As above. | [13 empty] | As above.
D15 | Agreed compensation level | The SNCBs are not in agreement with the WCS of excluding compensation for damage to Annex I sandbank. Please see our comments in Appendices B and C. |  | No change. |  | No Change |  | As above. | [13 empty] | As above.
D16 | Scale/extent of measure | The scale/extent of the measure has not been presented in detail and/or agreed with the SNCBs. Please see our comments in Appendices B and C. |  | No change. |  | No Change |  | As above. | [13 empty] | As above.
D17 | Timing: Deliverable before impact | It is unclear if this measure can be delivered prior to the impacts occurring. |  | No change. |  | No Change |  | As above. | [13 empty] | As above.
D18 | Location of measure | The location of the measure has not been presented in detail and/or agreed with the SNCBs. |  | No change. |  | No Change |  | As above. | [13 empty] | As above.
D19 | Long term implementation & Success criteria/Ability to prove additionality | N/A |  | No change. |  | No Change |  | As above. | [13 empty] | As above.
D20 | Suitable as sole measure for target species | This measure could only be considered as part of a package providing <10% of the required compensation and/or potential adaptive management for part delivered compensation. There would also be a requirement for the provision of subtidal seagrass, not intertidal. Therefore, we advise that other measures are progressed first. If other options are being progressed, then there is an expectation this compensation will not be taken forward. |  | No change. |  | No Change |  | As above. | [13 empty] | As above.
Detailed comments Documents used: [APP-059] 6.2.3 Appendix 3 – Project Level Dogger Bank Compensation Plan [APP-061] 6.2.3.2 Outline Dogger Bank Compensation Implementation and Monitoring Plan [APP-062] 6.2.3.3 Annex C - Extension of the Dogger Bank SAC for HRA Derogation Compensation – Rationale and Evidence Base
D21 | D2 | The Dogger Bank Strategic Compensation Plan (DBSCP) and the project compensation do not align, with the exclusion of compensation requirements for damage to sandbanks. Benthic compensation measures for habitat disturbance of Annex I sandbanks from the project level compensation documents are omitted. We would fully expect the DCO to include compensation for both habitat loss and damage. Further consideration should be given to Plan Level compensation requirements as agreed by the Secretary of State for the Depart of Energy Security and Net Zero. |  | No change. Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | No change - Please see Deadline 2 Appendix 2.1. |  | No change. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No change. The Applicant has updated (6.2) Habitats Regulations Derogation Provision of [REP4-019] and RIAA - HRA - Appendix 3 - Project Level Dogger Bank Compensation Plan - Volume 6 [REP4-028] stating "that there is no evidence to substantiate that there could be AEoI from ‘halo effects’ in habitats such as those found within the Dogger Bank". Natural England disagrees with this - see Appendix C5 of Natural England's Deadline 5 submission for further details. |  | Issue progressed. The Applicant has now provided estimates with respect to habitat damage and ecological halo effects on a without prejudice basis. However, we consider that further revisions are needed to the halo effects estimate. Please see Appendix C6 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Issue progressed. The Applicant has updated assessment of ecological halo effects [REP7-128]. We welcome the Applicant providing a without prejudice figure based on 50m halo impact from cable protection. But if a reduced buffer for halo effects from cable protection can be agreed then we recognise that the compensation requirement will be reduced and amounts will fall between 5km2 and 13.2km2 for habitat loss. This doesn't take account of impacts from habitat disturbance. The Applicant has also submitted an updated 6.1 RIAA 2 of 4 –Annex I Offshore Habitats and Annex II Migratory Fish (Revision 5) [REP7-017]. We will provide further comment at Deadline 9. Please see our Deadline 8 cover letter for our approach to the final two deadlines. Furthermore, please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology for detail about habitat loss.
D22 | D3 | If the Applicant is delivering Plan Level compensation, it is assumed that they do not also have to provide project level compensation, but this is not explicit here. It is also unclear why the Applicant has developed a project level compensation plan as DEFRA are moving ahead with work on new designations as a form of compensation following the agreement by DEFRA and SoS in Feb 2024. Ultimately it will be for DEFRA to determine the amount of compensation required, irrespective of what the Applicant has detailed in Section 5 Compensation Quantum. The SNCBs request legal clarification from the Applicant on this. |  | No change. |  | No Change |  | Issue resolved. The Project Level Dogger Bank Compensation Plan [REP2-103] has been revised to reflect delivery of strategic compensation only. | [13 empty] | Issue resolved. The Project Level Dogger Bank Compensation Plan [REP2-103] has been revised to reflect delivery of strategic compensation only.
D23 | D4 | It is not clear to the SNCBs the role of the Steering Group going forwards if strategic compensation is progressed by DEFRA, as they will determine individual project ‘contribution’ as set out above. The SNCBs seeks further clarity from TCE on this matter. |  | No change. |  | No Change |  | No change. Not for the Applicant to address. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No change. |  | No change.
D24 | D5 | We do not agree with the inclusion of any ‘as built’ figures as this is not legally secured. The SNCBs advise that figures included in consents are used to inform incombination assessments. |  | No change. |  | No Change |  | Resolved. We note that the values presented in [REP2-103] use the consented parameters. | [13 empty] | Resolved. We note that the values presented in [REP2-103] use the consented parameters.
D25 | D6 | The SNCBs welcome the Plan Level and the Project Level compensation comparison. But highlight point D2 above with regard to aligning. |  | N/A | [17 empty] | N/A
D26 | D7 | Compensation multiplier - this is not agreed or signed up to by the SNCBs and if site extension is progressed, it will be agreed as part of DEFRAs MPA Designation work. Therefore, it is our view that it is not necessary or appropriate to agree this as part of this Examination. |  | N/A | [17 empty] | N/A
D27 | D8 | The Applicant has submitted information on a possible site extension to the Dogger Bank SAC. The powers to designate sit with DEFRA, and there is a work programme underway to identify potential locations. Therefore, it is the SNCBs view that it is neither necessary nor appropriate to discuss the merits of a particular designated site extension as part of the Dogger Bank South Examination. |  | N/A | [17 empty] | N/A
D28 | D9 | Whilst any monitoring requirements may fall under the responsibility of NE or JNCC, this is not yet determined and/or agreed. However, we fully expect monitoring costs associated with compensation measures to be borne by those developers requiring the compensation through the MRF. The SNCBs request further clarity is provided from DEFRA when available. |  | No change. |  | No Change |  | No change. Not for the Applicant to address. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No change. |  | As these issues are not for the Applicant to address, we are making them purple for awareness of the Examining Authority. | [7 empty] | As these issues are not for the Applicant to address, we are making them purple for awareness of the Examining Authority.
D29 | D10 | Because the SNCBs believe that disturbance should also be included in any compensation requirements, we do not agree that the need to consider adaptive management finishes once construction has completed. The SNCBs request further clarity is provided from DEFRA when available. |  | No change. |  | No Change |  | No change. Not for the Applicant to address. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No change. |  | As these issues are not for the Applicant to address, we are making them purple for awareness of the Examining Authority. | [7 empty] | As above.
D30 | D11 | It is the view of the SNCBs that adaptive management will be a consideration of DEFRA’s MPA designations programme. The SNCBs request further clarity is provided from DEFRA when available. |  | No change. |  | No Change |  | No change. Not for the Applicant to address. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No change. |  | As these issues are not for the Applicant to address, we are making them purple for awareness of the Examining Authority. | [7 empty] | As above.
D31 | D12 | It is not clear if a Dogger Bank CIMP will be required in addition to the Round 4 Plan Level one or the Strategic compensation work. The SNCBs request further clarity is provided from DEFRA and TCE when available. |  | No change. |  | No Change |  | No change. Not for the Applicant to address. |  | The SNCBs and DEFRA's view is that the BIMP is undertaken through the MRF process. Therefore there is no need to progress as part of the examination for strategic compensation | [11 empty] | The SNCBs and DEFRA's view is that the BIMP is undertaken through the MRF process. Therefore there is no need to progress as part of the examination for strategic compensation

## E - Fish and Shellfish
Point | Point Number(s) from Appendix E [RR-039] | Taken from Natural England’s Relevant and Written Representations Dogger Bank South (East and West) Appendix E - Fish and Shellfish | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | RAG Deadline 9 | End of Examination Position | Issue Resolved
E1 | E9 | There are three potential foundation options for the Electrical Switching Platform (ESP) in the Export Cable Corridor (ECC): jacket piles, monopiles, or a gravity-based structure. Clarity is needed on if gravity bases have been included in the worst-case scenario for operational habitat loss in the ECC. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change. |  | Issue resolved. Natural England no longer deems this an issue due to the removal of the ESP in the ECC through the Change Request. | [12 empty] | Issue resolved. Natural England no longer deems this an issue due to the removal of the ESP in the ECC through the Change Request.
E2 | E10 | Underwater noise modelling for Atlantic herring for monopile and pin-pile installations uses a worst-case position of piling in the northern most point of the DBS West array. The worst-case position at the most south-westerly point of the DBS West array should be assessed as this may result in greater overlap with the High and Very High herring spawning potential habitat. |  | No Change. Please refer to our response to Action Point 35 from Issue Specific Hearing 2, outlined in Annex 2 of our Deadline 1 Cover Letter, for further detail. |  | No Change. |  | No change. Please refer to Appendix E3 (Section 1.2) of Natural England’s Deadline 3 submission. |  | No change - no new information relevant to this issue has been submitted at this deadline. It is Natural England's understanding that the Applicant will be submitting a document to address this issue ([EV10-002] Action Point 24) at Deadline 4. We will review this and provide further comment at Deadline 5. |  | No Change. As stated in 14.4 The Applicant's Response to Deadline 3 Documents, the Applicants will be submitting modelling of the most south-westerly point of DBS West Array Area at Deadline 5. Natural England will provide comment at Deadline 6. |  | Issue progressed. The Applicant has provided the requested updated modelling in [REP5-042]. This has confirmed that the south-west location of the DBS West array is more appropriate for assessing the impacts of the arrays together. See E3 and Appendix E6 of our Deadline 6 submission. |  | No Change. No new information has been provided at this deadline. |  | No Change.The Applicant maintains their disagreement with Natural England's previous advice that the Projects updated modelling [REP5-042] confirms that the south-west location of the DBS West array is a more appropriate worst case scenario for assessing the impacts of the arrays together. Natural England maintain our previous advice on this [REP6-074] relating to the worst-case location and therefore worst-case scenario for the arrays together. We therefore consider that agreement will not be reached on this matter within Examination. We do however welcome the Applicants ongoing ‘without prejudice’ discussions, in which these scenarios could be incorporated into underwater noise modelling based on the final project design. We advise that the Secretary of State considers the modelling outlined in [REP5-042] in their HRA. |  |  | No Change.The Applicant maintains their disagreement with Natural England's previous advice that the Projects updated modelling [REP5-042] confirms that the south-west location of the DBS West array is a more appropriate worst case scenario for assessing the impacts of the arrays together. Natural England maintain our previous advice on this [REP6-074] relating to the worst-case location and therefore worst-case scenario for the arrays together. We therefore consider that agreement will not be reached on this matter within Examination. We do however welcome the Applicants ongoing ‘without prejudice’ discussions, in which these scenarios could be incorporated into underwater noise modelling based on the final project design. We advise that the Secretary of State considers the modelling outlined in [REP5-042] in their HRA.
E3 | E11 | Further clarity is needed regarding simultaneous piling for monopiles for the in-isolation development scenario. For two monopiles installed simultaneously, the worst-case scenario for underwater noise and vibration impacts on sandeel would be two simultaneous monopile piling events in the DBS West array area. We advise that underwater noise models are provided for the worst-case scenario in each build out scenario. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change. |  | Issue Progressed. We welcome the Applicant has reassessed monopiling impacts for the in-isolation development scenario in [AS-142]. However when reassessing the projects combined, only pin pilling is reassessed. Natural England require further clarification as to why information on monopiling has been provided when assessing impacts of DBS West and East together. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - no new information relevant to this issue has been submitted at this deadline. Natural England would like to highlight a wording error in our Deadline 3 R&I Log that was inteded to ask: Natural England require further clarification as to why information on monopiling has not been provided when assessing impacts of DBS West and East together. This was in relation to [AS-141] 10.49 Project Change Request 1 – Offshore and Intertidal Works. |  | No Change. The updated modelling provided by the Applicant indicates that two monopiles in the DBS West array would provide the WCS for the in-isolation build out scenario. Please see Appendix E6 for further detail. |  | No Change. No new information has been provided at this deadline. |  | No Change. The Applicant has outlined in their Response to Deadline 6 Documents [REP7-131] that they maintain their position regarding the worst case scenario for the arrays together. There has been no update to the WCS for the arrays in-isolation in the updated the ES Chapter 10 [REP7-043], therefore Natural England maintains our advice at Deadline 6 [REP6-074] that a WCS should be provided for each build-out scenario. We therefore consider that agreement will not be reached on this matter within Examination. We do however welcome the Applicants ongoing ‘without prejudice’ discussions, in which these scenarios could be incorporated into underwater noise modelling based on the final project design. We advise that the Secretary of State considers the modelling outlined in [REP5-042] and our advice in [REP6-074] in their HRA. |  |  | No Change. The Applicant has outlined in their Response to Deadline 6 Documents [REP7-131] that they maintain their position regarding the worst case scenario for the arrays together. There has been no update to the WCS for the arrays in-isolation in the updated the ES Chapter 10 [REP7-043], therefore Natural England maintains our advice at Deadline 6 [REP6-074] that a WCS should be provided for each build-out scenario. We therefore consider that agreement will not be reached on this matter within Examination. We do however welcome the Applicants ongoing ‘without prejudice’ discussions, in which these scenarios could be incorporated into underwater noise modelling based on the final project design. We advise that the Secretary of State considers the modelling outlined in [REP5-042] in their HRA. and our advice in [REP6-074] in their HRA.
E4 | E12, E25 | The Applicant has provided underwater noise modelling for three pin-piles piled concurrently across the array areas and in the ECC, and has committed to no concurrent monopiling occurring across the arrays area with the ECC, clarity is needed as it is unclear if two monopiles (one in DBS West, one in DBS East) and pin piling in the ECC could occur concurrently. Clarification is needed on the worst-case scenario for concurrent piling. In the case that monopiling in the array areas can occur concurrently with pin piling within the ECC, we advise the Applicant to provide underwater noise models and figures to assess impacts on fish receptors. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change. |  | Issue Resolved. Natural England no longer deems this an issue due to the removal of the need for piling in the ECC. | [12 empty] | Issue Resolved. Natural England no longer deems this an issue due to the removal of the need for piling in the ECC.
E5 | E13 | The Applicant should utilise sandeel abundance data (such as the North Sea sandeel dredge survey) to support the assessment of impacts on localised sandeel populations (currently only habitat suitability heat maps and drop down video have been used). |  | Natural England will be providing comments on AS-105 Heat Mapping Report: Atlantic Herring and Sandeel (Revision 1) at Deadline 2. |  | Due to staff absence, Natural England will be providing detailed comments on Fish and Shellfish at Deadline 3. |  | No Change. Please refer to Appendix E3 for further detailed comments on [AS-105] Heat Mapping Report. |  | No Change. Whilst we welcome the Applicant has provided a figure of the North Sea Sandeel Survey data in Appendix A of their response to Deadline 2 documents [REP3-028], and that this further confirms the presence of sandeel in the array, there is no presentation of data on relative abundance/population distribution within the project area compared to wider region. It is our understanding that abundance indices are available from the NSSS data set and would help to support the assessment of sandeel suitability. Natural England request the Applicant includes these updates in relevant assessments. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. Please see the response to question R17.6 in Annex 2 of our Deadline 6 Cover Letter. |  | No Change. Whilst Natural England acknowledges the Applicant's Response to the Deadline 5 Documents [REP6-052] on this subject, this does not alter our previous advice [REP5-056] for the Applicant to provide data on relative abundance/population distribution within the project area compared to the wider region. We agree with the MMO [REP5-049: 1.7.2] that the presentation of this data at this late stage in the application process will not significantly change the outcomes of the assessment, but would also echo that it is disappointing that the Applicant has failed to present this data, despite repeated requests. |  |  |  |  | No Change. Whilst Natural England acknowledges the Applicant's Response to the Deadline 5 Documents [REP6-052] on this subject, this does not alter our previous advice [REP5-056] for the Applicant to provide data on relative abundance/population distribution within the project area compared to the wider region. We agree with the MMO [REP5-049: 1.7.2] that the presentation of this data at this late stage in the application process will not significantly change the outcomes of the assessment, but would also echo that it is disappointing that the Applicant has failed to present this data, despite repeated requests.
E6 | E18 | EMF impacts from cables on sandeel and Atlantic herring have not been considered. We advise that the impacts of EMF on sandeel and herring high potential spawning habitat should be assessed. |  | Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | Due to staff absence, Natural England will be providing detailed comments on Fish and Shellfish at Deadline 3. |  | Natural England remain concerned about EMF in array areas which include high and very high sandeel spawning habitat. The Applicant highlights that some receptors exhibit flexibility in their range of habitats, but Natural England highlights the high site fidelity known for sandeel. Whilst we agree they are less electrosensitive when compared with elasmobranchs, there is insufficient evidence to confirm no impact on sandeel, particularly as lost habitat across the sandbank. However, we acknowledge that the lack of evidence base would prevent a more accurate assessment being undertaken. | [12 empty] | Natural England remain concerned about EMF in array areas which include high and very high sandeel spawning habitat. The Applicant highlights that some receptors exhibit flexibility in their range of habitats, but Natural England highlights the high site fidelity known for sandeel. Whilst we agree they are less electrosensitive when compared with elasmobranchs, there is insufficient evidence to confirm no impact on sandeel, particularly as lost habitat across the sandbank. However, we acknowledge that the lack of evidence base would prevent a more accurate assessment being undertaken.
E7 | E19 | Habitat loss for sandeel and herring from UXO clearance have not been assessed as “specific surveys to identify potential locations of UXO would not be undertaken until the DCO for the Projects is granted”. A nominal assessment should be included as has been done for other receptors, e.g. marine mammals and benthic. |  | Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | Due to staff absence, Natural England will be providing detailed comments on Fish and Shellfish at Deadline 3. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - The Applicant has submitted a UXO clearance information report [REP3-013] at Deadline 3, however Natural England would like clarification on the Applicant's justification for focusing solely on marine mammals for direct injury impacts, and not including fish species. |  | No change. Natural England maintains our previous advice. For further information see our response to Issue Specific Hearing Action 28 in Appendix M5 |  | Natural England acknowledges the Applicant's response to the Deadline 4 documents [REP5-037] that they included a statement on impacts from UXO on fish in the ES Chapter [APP-091], however we maintain our previous advice that a nominal assessment of habitat loss for herring and sandeel should be included in relation to UXO clearance. We do however acknowledge that at this late stage of Examination, it may not be possible to include this. We therefore advise that it is included in the Marine Licence application for UXO clearance. |  | The Applicant has highlighted in their Response to Deadline 5 Documents [REP6-052] that the RIAA will be updated at Deadline 7 to include this habitat loss into the projects footprint. We will provide further comment at Deadline 8. |  | Issue satisfactorily resolved. Natural England welcomes the Applicant's addition of WCS for disturbance to Annex I Habitats, and habitat loss in the Dogger Bank SAC in the updated RIAA [REP7-017]. We note that these impacts to sandeel habitat are not currently outlined in the ES Chapter 10 [REP7-043] but direct the Examining Authority to the RIAA for the relevant assessments. We note that there may be further refinement to the impact values presented based on our benthic comments (see C8 in Benthic sheet). |  |  | Issue satisfactorily resolved. Natural England welcomes the Applicant's addition of WCS for disturbance to Annex I Habitats, and habitat loss in the Dogger Bank SAC in the updated RIAA [REP7-017]. We note that these impacts to sandeel habitat are not currently outlined in the ES Chapter 10 [REP7-043] but direct the Examining Authority to the RIAA for the relevant assessments. We note that there may be further refinement to the impact values presented based on our benthic comments (see C8 in Benthic sheet).
E8 | E20 | Impacts from localised heating from the cables have been assessed in reference to water temperature increase, with no specific receptors identified as being impacted. Further assessment is required for localised heating of sediment and possible impacts to high/very high potential sandeel and herring spawning habitat. |  | Natural England are reviewing the Applicant’s response and will provide further comment at Deadline 2. |  | Due to staff absence, Natural England will be providing detailed comments on Fish and Shellfish at Deadline 3. |  | No change. Our previous advice to assess localised heating impacts from cables remains. |  | No change - The Applicant submitted [REP3-032] 13.7 Bed Mobility and Thermal Environment (Revision 1) at Deadline 3, however this report does not present any new information that changes our current advice. |  | No change. Natural England maintains our previous advice. For further information see Appendix E5 and our response to Issue Specific Hearing Action 27. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. Natural England acknowledges the Applicant's Response to the Deadline 5 Documents [REP6-052] on this subject, however we maintain our previous advice that an assessment of localised heating of sediment is provided to demonstrate that there would be no LSE to both sandeel and herring. We note that the evidence cited by the Applicant suggests that sediment could be heated from cables to a distance that would overlap with sandeel burrowing depths. |  | No Change. This information has not been provided by the Applicant and therefore we cannot advise the SoS on level of risk at this Deadline. If SoS is minded to consent the projects, we advise that monitoring of heat impacts is secured. We refer to Appendix E8 for Natural England's End of Examination position for further detail. |  |  | No Change. This information has not been provided by the Applicant and therefore we cannot advise the SoS on level of risk at this Deadline. If SoS is minded to consent the projects, we advise that monitoring of heat impacts is secured. We refer to Appendix E8 for Natural England's End of Examination position for further detail.
E9 | E21 | Clarity is needed on how localised impacts on high potential spawning habitat loss due to cable protection have been assessed for sandeel and Atlantic herring. |  | No Change |  | No Change |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | The Applicant has highlighted in their Response to Deadline 5 Documents [REP6-052] that an updated RIAA will be provided at Deadline 7. We will provide further comment at Deadline 8. |  | Issue satisfactorily resolved. Natural England welcomes the Applicant's addition of WCS for disturbance to Annex I Habitats, and habitat loss in the Dogger Bank SAC in the updated RIAA [REP7-017]. We note that these impacts to sandeel habitat are not currently outlined in the ES Chapter 10 [REP7-043] but direct the Examining Authority to the RIAA for the relevant assessments. We note that there may be further refinement to the impact values presented based on our benthic comments (see C8 in Benthic sheet). |  |  | Issue satisfactorily resolved. Natural England welcomes the Applicant's addition of WCS for disturbance to Annex I Habitats, and habitat loss in the Dogger Bank SAC in the updated RIAA [REP7-017]. We note that these impacts to sandeel habitat are not currently outlined in the ES Chapter 10 [REP7-043] but direct the Examining Authority to the RIAA for the relevant assessments. We note that there may be further refinement to the impact values presented based on our benthic comments (see C8 in Benthic sheet).
E10 | E22 | Include a robust assessment of the potential Worst-Case area of impact on benthic communities, particularly those highlighted as spawning areas along the ECC, and within Dogger Bank SAC sandbank feature, and the nature and scale of that impact, as a result of changes to physical and biological process following the placement of structures and cable/scour protection on the seabed (benthic ‘ecological halo effect’). |  | No Change. Natural England will be providing comment on this alongside our comments on Benthic and Intertidal Ecology at Deadline 2. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. |  | No Change. Please refer to C8 of the Risk and Issues log and Natural England's Deadline 2, Appendix C2. |  | No change - Natural England maintain our previous advice. See Risk and Issues Ref C8 and Appendix C4 for further details. It is Natural England's understanding that the Applicant will be submitting a document to address this issue (ISH Action Point 41) at Deadline 4. We will review this and provide further comment at Deadline 5. |  | No change. Natural England maintain our previous advice. See Appendix C5 for further details. |  | Issue progressed. The Applicant has presented an assessment of ecological halo effects [REP5-041]. However, we consider that the estimate for worst case area of loss needs further revision. Please see Appendix C6 of Natural England's Deadline 6 submission for further details. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue satisfactorily resolved. Natural England welcomes the Applicant's addition of WCS for disturbance to Annex I Habitats, and habitat loss in the Dogger Bank SAC in the updated RIAA [REP7-017]. We note that these impacts to sandeel habitat are not currently outlined in the ES Chapter 10 [REP7-043] but direct the Examining Authority to the RIAA for the relevant assessments. We note that there may be further refinement to the impact values presented based on our benthic comments (see C8 in Benthic sheet). |  |  | Issue satisfactorily resolved. Natural England welcomes the Applicant's addition of WCS for disturbance to Annex I Habitats, and habitat loss in the Dogger Bank SAC in the updated RIAA [REP7-017]. We note that these impacts to sandeel habitat are not currently outlined in the ES Chapter 10 [REP7-043] but direct the Examining Authority to the RIAA for the relevant assessments. We note that there may be further refinement to the impact values presented based on our benthic comments (see C8 in Benthic sheet).
E11 | E23 | The Applicant has modelled fish as both stationary and fleeing receptors for underwater noise thresholds. For all underwater noise modelling Natural England advise that fish are assessed as stationary receptors, our conclusions on impacts will therefore be based on the values provided that are in line with this advice. |  | No action needed. | [16 empty] | The Applicant has modelled fish as both stationary and fleeing receptors for underwater noise thresholds. For all underwater noise modelling Natural England advise that fish are assessed as stationary receptors, our conclusions on impacts will therefore be based on the values provided that are in line with this advice.
E12 | E26 | 'soft start and ramp-up' approaches are not appropriate piling mitigation measures for impacts to fish. We therefore advise they are removed from the assessment and a more appropriate worst-case scenario is presented. |  | No Change. |  | No Change. |  | Issue Progressed. NE welcome that the Applicant has committed to not modelling fish as fleeing receptors and not including mitigation within their models, but would like further clarification from the Applicant that any reference to 'soft start and ramp-up' regarding fish is removed when discussing these mitigation measures. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue progressed. Natural England welcomes the Applicant's commitment (stated in 14.4 The Applicant's Response to Deadline 3 Documents) to removing any reference to 'soft start and ramp-up' regarding fish in an updated version of Chapter 10 Fish and Shellfish Ecology [APP-091], submitted into Examination at Deadline 7. | [5 empty] | Issue Resolved. We welcome the Applicant's ammendment to the updated ES Chapter 10 submitted at Deadline 7. |  |  | Issue Resolved. We welcome the Applicant's ammendment to the updated ES Chapter 10 submitted at Deadline 7.
E13 | E28 | Evidence for habituation has been based on ship/trawl noise and seismic air guns. We advise that habituation should not be taken into account within the assessment without provision of more appropriate supporting evidence for impulsive piling noise. |  | No Change. |  | No Change. |  | No Change. Natural England continue to disagree that habituation is applicable to noise sources impacting fish from the Projects. We continue to advise the Applicant provide more appropriate supporting evidence. Please refer to Appendix L for further detail. |  | No Change. Natural England continue to disagree that habituation is applicable to noise sources impacting fish from the Project.We welcome the inclusion of the 135dB threshold in the UWN modelling as requested by Cefas, and we continue to defer to Cefas regarding herring modelling assessment. Whilst we welcome the Applicant has provided additional information on habituation in their response to Deadline 2 documents [REP3-028], this document does not change our previous advice. |  | Issue Resolved. We welcome the response outlined in 14.4 The Applicant's Response to Deadline 3 Documents, and now consider this issue resolved. | [8 empty] | Issue Resolved. We welcome the response outlined in 14.4 The Applicant's Response to Deadline 3 Documents, and now consider this issue resolved.
E14 | E29, E30, E41 | We advise the Applicant commit to additional cable protection mitigation to reduce impacts to herring and sandeel spawning habitat (also mentioned in Risk and Issues Log Points B22 and C12). In addition, the Applicant should explore options to avoid placing cable protection within high – very high potential spawning habitat areas for herring and sandeel in the ECC and array areas. Currently, the full volume/length of cable protection applied for (20% of the ECC length, 10% for the inter-array cables) could be installed within these areas. A commitment should be made to avoid placing cable protection in these areas, or to only a certain proportion of the full volume being allowed in these areas. It should also be demonstrated through the Cable Burial Risk Assessment why the volumes applied for are needed and cannot be refined down further. We consider cable protection estimates should be based on an assessment of likely burial success. |  | No Change. |  | No Change. |  | No Change. Natural England maintain our previous advice. Please see Appendix C4 and ISH Action 57 in Appendix J of our Deadline 4 submission. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. Natural England maintains our previous advice. |  | No Change - Please see Appendix C6 of Natural England's Deadline 6 submission in relation to cable protection mitigation. |  | No Change. No new information has been provided at this deadline. |  | No change. We maintain our previous advice. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology. |  |  | No change. We maintain our previous advice. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology.
E15 | E29, E31, E41 | A commitment should be made to remove all on and above seabed infrastructure within high - very high potential spawning habitat for sandeel and herring at the time of decommissioning, to prevent permanent impacts to spawning areas within the ECC and array areas. We advise this should be secured in the DCO. Without such a commitment, the worst-case scenario should assess the impacts to spawning grounds if assets are left permanently in situ. (Also refer to Risk and Issues Log Benthic Point C27) |  | No Change. |  | No change. See Appendix C2.1 of Natural England's Deadline 2 submission for further detail. |  | No Change. Natural England maintain our previous advice. Please see Appendix C3 and ISH Action 57 in Appendix J of our Deadline 4 submission. |  | No Change. Please see Appendix C4 of our Deadline 4 submission for further detail. |  | No change. Natural England maintains our previous advice. |  | No Change - Please see Appendix C6 of Natural England's Deadline 6 submission in relation to cable protection mitigation. |  | Issue progressed. The Applicants have committed [REP6-044] to consider removability of cable protection as part of the development of the final Cable Statement and Decommissioning Programme to be produced for submission to the SoS pre construction. Whilst this is welcome, it is not sufficient to resolve concerns regarding the lack of a full commitment to decomissioning. |  | The Applicants have committed [REP6-044] to consider removability of cable protection as part of the development of the final Cable Statement and Decommissioning Programme to be produced for submission to the SoS pre construction. Whilst this is welcome, it is not sufficient to resolve concerns regarding the lack of a full commitment to decomissioning. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology. |  |  | The Applicants have committed [REP6-044] to consider removability of cable protection as part of the development of the final Cable Statement and Decommissioning Programme to be produced for submission to the SoS pre construction. Whilst this is welcome, it is not sufficient to resolve concerns regarding the lack of a full commitment to decomissioning. Please see Appendix B8 of our Deadline 8 submission for Natural England's End of Examination Position on the Applicant's Assessment of Marine Physical Environment & Benthic and Intertidal Ecology.
E16 | E29, E32, E41 | The behavioural threshold (135 dB) modelled also overlaps the high and very high spawning habitat potential sites when piling in the array areas. As well as seasonal restriction in the ECC, a seasonal restriction should also be committed to for piling in the array areas. We defer to Cefas for further advice on timings of any such restriction. |  | No Change. |  | No Change. |  | No change. Our previous advice remains that the the Applicant updates any reference to the worst-case scenario from underwater noise impacts on Atlantic herring to behavioural changes with a behavioural threshold of 135 dB SELss. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. Natural England maintains our previous advice. Please see Appendix E6 for further detail. |  | Issue Progressed. The Applicant has given Natural England advance sight of updates to DCO conditions related to herring seasonal restrictions for both piling and cable installation to be submitted on a without prejudice basis at Deadline 7. Whilst we will provide full comments at Deadline 8, we are provisionally satisfied that the approach being taken is appropriate and that in-combination with updates to the DCO condition for piling mitigation (see Section 3 of our Deadline 7 Cover Letter), there would be signficant reductions in impacts. We acknowledge the Applicant's stance on the use of the 135dB behavioural threshold [REP6-052], but maintain our previous advice [REP6-074] and defers to the MMO's Deadline 6 Response [REP6-069] for further justification on this matter and details surrounding proposed seasonal restrictions. |  | Issue satisfactorily resolved. Natural England welcomes the inclusion of values relating to unmitigated piling extent which have been presented by the Applicant in Appendix A of the revised Illustrative Underwater Noise Reduction Technical Note [REP7-126]. Natural England also welcome the provision for piling and cable works restrictions in the Draft Development Consent Order [REP7-011] and Herring Spawning Plan [REP7-135] to mitigate impacts on herring. We highlight that the current Herring Spawning Plan and associated piling restriction condition has been provided on a 'Without Predjudice' basis, and advise that we support MMO's position that this should be secured in the DCO. We refer to Appendix E8 for Natural England's End of Examination position. |  |  | Issue satisfactorily resolved. Natural England welcomes the inclusion of values relating to unmitigated piling extent which have been presented by the Applicant in Appendix A of the revised Illustrative Underwater Noise Reduction Technical Note [REP7-126]. Natural England also welcome the provision for piling and cable works restrictions in the Draft Development Consent Order [REP7-011] and Herring Spawning Plan [REP7-135] to mitigate impacts on herring. We highlight that the current Herring Spawning Plan and associated piling restriction condition has been provided on a 'Without Predjudice' basis, and advise that we support MMO's position that this should be secured in the DCO. We refer to Appendix E8 for Natural England's End of Examination position.
E17 | E33 | Suitable references and evidence should be provided to support statements used in the impact assessment to conclude negligible or minor adverse impacts (i.e. that receptors can recover from impacts within 2-10 years). |  | No Change. We are reviewing the Applicant's response and will provide further comment at Deadline 2 as needed. |  | Due to staff absence, Natural England will be providing detailed comments on Fish and Shellfish at Deadline 3. |  | No Change. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. Natural England and the Applicant maintain their respecitve positions on this point. We maintain that the ES needs further evidence to support ES conclusions, however we defer to MMO/Cefas for further comment on this matter. |  |  |  |  | No Change. Natural England and the Applicant maintain their respecitve positions on this point. We maintain that the ES needs further evidence to support ES conclusions, however we defer to MMO/Cefas for further comment on this matter.
E18 | E34, E42 | Indirect effects on Humber Estuary SAC river lamprey and sea lamprey should be screened into the assessment. |  | Natural England maintain that river lamprey and sea lamprey should be screened into the assessment, however we acknowledge that the uncertainties and data poor environment would prevent a reliable assessment being made. | [16 empty] | Natural England maintain that river lamprey and sea lamprey should be screened into the assessment, however we acknowledge that the uncertainties and data poor environment would prevent a reliable assessment being made.
E19 | E35 | The worst-case piling event for migratory fish species is likely to be when piling takes place in the ECC. Underwater noise impacts from piling in the ECC should be fully assessed for Annex II migratory fish. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | Issue Resolved. Natural England no longer deems this an issue due to the removal of the need for piling in the ECC. | [12 empty] | Issue Resolved. Natural England no longer deems this an issue due to the removal of the need for piling in the ECC.
E20 | E36 | The cumulative assessment for Dogger Bank SAC should be updated to include the total habitat loss within the SAC, including loss occurring within any overlap of the ECCs with the site. See also E19 and E22 in relation to the total habitat loss area to be assessed. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No Change. Please see Appendix L for more detail on providing updated habitat loss assessments. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue Progressed. Please see Appendix E5 for further detail. |  | Issue progressed. The Applicant has presented an assessment of ecological halo effects [REP5-041]. However, we consider that the estimate for worst case area of loss needs further revision. Please see Appendix C6 of Natural England's Deadline 6 submission for further details. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue Progressed. Natural England welcomes the Applicant's additional calculation of habitat loss resulting from ecological halo effects, UXO clearance and jack-up operations in the Updated RIAA HRA Part 2 of 4 – Annex I Offshore Habitats and Annex II Migratory Fish (REP7-017]. Natural England maintain our previous advice at Deadline 5 [REP5-056] that updated assessments for both existing and proposed cumulative impacts occurring within any overlapping developments including industry such aggregates, oil and gas, cables and pipelines should be provided. We refer to Appendix E8 for Natural England's End of Examination position for further detail. |  |  | Natural England welcomes the Applicant's additional calculation of habitat loss resulting from ecological halo effects, UXO clearance and jack-up operations in the Updated RIAA HRA Part 2 of 4 – Annex I Offshore Habitats and Annex II Migratory Fish (REP7-017]. However, Natural England maintain our previous advice at Deadline 5 [REP5-056] that updated assessments for both existing and proposed cumulative impacts occurring with any overlapping developments including industry such aggregates, oil and gas, cables and pipelines should be provided. We refer to Appendix E8 for Natural England's End of Examination position for further detail.
E21 | E17, E38 | We disagree that if there were no significant impacts identified for potential fish prey species in the EIA assessment then there would be no significant impacts on ornithology and marine mammal receptors. NE consider that an understanding of the relative importance of the Project site as a foraging area, and potential for any impacts on localised prey abundance and distribution is critical in framing the predicted RIAA impacts that can be quantified. Further assessment is therefore needed to understand how more localised impacts (e.g localised depletion and/or reduced resilience of the wider stock) on fish and shellfish might influence prey availability for designated seabirds and mammals. The assessments should consider both direct and indirect impact pathways to sandeel and herring at a biologically relevant population scale, for both the construction and operation phases of the Projects. For herring this would be the Banks spawning component of the North Sea stock, and for sandeel the specific genetic population present in the Project area. See Annex E1 of REP-039 for futher guidance. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No change. We note the Applicant has contested the importance of the Dogger Bank sandbank system for prey availability and foraging species. Natural England disagrees with the justification provided and therefore maintains the advice provided in our Relevant Representation on this issue. |  | No Change - no new information relevant to this issue has been submitted at this deadline |  | It is Natural England's understanding that the Applicant will be submitting a document to address this issue (as mentioned in the Applicant's response to the ExA Questions [REP3-027]) at Deadline 4. We will review this and provide further comment at Deadline 5. |  | No Change. Please see Appendix E5 for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue Progressed. Natural England welcome the Applicant's updates to the Effects on Prey Species Technical note [REP6-050]. We have provided further advice on this impact pathway in response to RIES questions 32, 46, 52,53 in Appendix N7 of our Deadline 7 submission. |  | No Change. The Applicant has submitted an updated ES Chapter 10 [REP7-043]and RIAA [REP7-017] at Deadline 8, however their position remains that there will be no significant impacts on fish prey species resulting from the Projects. Natural England maintain that for those features where AEoI cannot be ruled out (kittiwake, guillemot and razorbill), this impact pathway will, without resulting in an AEOI in its own right, intensify those effects on those species. Please see our responses to RIES Q46, Q52 and Q53 in Appendix N7 for further detail. |  |  | No Change. The Applicant has submitted an updated ES Chapter 10 [REP7-043]and RIAA [REP7-017] at Deadline 8, however their position remains that there will be no significant impacts on fish prey species resulting from the Projects. Natural England maintain that for those features where AEoI cannot be ruled out (kittiwake, guillemot and razorbill), this impact pathway will, without resulting in an AEOI in its own right, intensify those effects on those species. Please see our responses to RIES Q46, Q52 and Q53 in Appendix N7 for further detail.
E22 | E40 | The Applicant has proposed pre- and post- construction habitat sampling to validate statements made regarding habitat suitability and recoverability for sandeel. We advise that longer-term sandeel monitoring would provide a more robust evidence base and would be beneficial in assessing the impacts of the Project on Dogger Bank sandeel populations (e.g. changes in sediment composition that could arise from dispersing drill spoil or settling of sediments suspended by cable laying). Once assessments have been updated, monitoring should be secured via the In-Principal Monitoring Plan to determine whether the residual impacts are as predicted. This could be via provision of a post-consent Sandeel Monitoring Plan, or the inclusion of sandeel specific objectives in the Benthic Monitoring Plan. |  | Natural England will be providing comments on the In Principle Monitoring Plan (IPMP) [APP-247] at Deadline 3, in order to take into account all of the updates from Change Request 1, the Defra Marine Noise Policy paper and updated ornithology assessments. |  | No change. |  | Please refer to Appendix J regarding Natural England's advice regarding the IPMP. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. No new information has been provided at this deadline. |  | Natural England will provide comments on the Applicant's updated In-Principle Monitoring Plan at Deadline 9 [REP7-116]. Please also see E8.
E23 | E43 | We acknowledge that herring and sandeel are not designated features and therefore derogations for direct impacts to these species would not be required. However, should impacts to these species contribute to an adverse effect on site integrity for designated predator species or Annex 1 sandbank feature, consideration of prey availability/spawning habitat may need to be incorporated into compensation measures for those sites. |  | No Change. No Action needed. | [11 empty] | Please see Natural England's responses to RIES questions Q52 and Q53 in Appendix N7 of our Deadline 7 submission. |  |  |  |  | Please see Natural England's responses to RIES questions Q52 and Q53 in Appendix N7 of our Deadline 7 submission.

## F - Marine Mammals
Point | Point Number(s) from Appendix F [RR-039] | Taken from Natural England’s Relevant and Written Representations Dogger Bank South (East and West) Appendix F -Marine Mammals | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | Consultation, actions, progression | RAG Deadline 9 | End of Examination Position PLEASE NOTE: AS THERE ARE FEW OUTSTANDING CONCERNS REMAINING, THIS SHOULD BE CONSIDERED NATURAL ENGLAND'S CLOSING STATEMENT FOR THE MARINE MAMMALS TOPIC. | Issue Resolved
F1 | F8 | The Applicant has committed to no concurrent monopile installation between the Offshore Export Cable Corridor (ECC) and the Project array areas; however, it is unclear if there could be concurrent pin pile installation in the ECC with monopile installation in the array areas. Clarity is needed on the WCS for concurrent piling between the ECC and array areas. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No change |  | Issue Resolved. Natural England no longer deems this an issue due to the removal of the need for piling in the ECC. | [13 empty] | Issue Resolved. Natural England no longer deems this an issue due to the removal of the need for piling in the ECC.
F2 | F9 | Clarity is needed on how the worst case scenario (WCS) for the maximum number of piles to be installed concurrently in 24 hours across the two arrays will be secured in the dMLs for the separate Projects. |  | Natural England welcomes that a condition has been added to the DCO and will be providing comments at Deadline 2. |  | No Change. Natural England will provide further comment on this issue when our DCO comments are provided. |  | Natural England will provide further comment at Deadline 4 |  | Issue Resolved. Natural England are satisfied that the condition wording captures the WCS as assessed in the original ES which was then reduced as a result of the change request. | [11 empty] | Issue Resolved. Natural England are satisfied that the condition wording captures the WCS as assessed in the original ES which was then reduced as a result of the change request.
F3 | F10 | Clarity is needed on the WCS for simultaneous piling across the two arrays in a concurrent build out scenario, and how the dMLs for the separate Projects will secure this. |  | Natural England welcomes that a condition has been added to the DCO and will be providing comments at Deadline 2. |  | No Change.Natural England will provide further comment on this issue when our DCO comments are provided. |  | Natural England will provide further comment at Deadline 4 |  | Issue Resolved. Natural England are satisfied that the condition wording captures the WCS as assessed in the original ES which was then reduced as a result of the change request. | [11 empty] | Issue Resolved. Natural England are satisfied that the condition wording captures the WCS as assessed in the original ES which was then reduced as a result of the change request.
F4 | F16 | Permanent Threshold Shift (PTS) should be scoped into the Cumulative Effects Assessment. We do not agree that the mitigation outlined in the MMMP and ES is sufficient to minimise the risk of injury for all PTS impact ranges (see below). Further, due to the nature of marine mammals, mitigation cannot guarantee that no animals will be at risk of PTS. |  | No Change. |  | No Change. Natural England maintain our advice provided at Relevant Representations. |  | No Change. Natural England maintain our advice provided at Relevant Representations. |  | No Change. Natural England maintain our advice provided at Relevant Representations. |  | No change. The Applicant has acknowledged that in line with Defra Guidance, all offshore wind farms are required to use primary and/or secondary noise management measures, and this will mitigate any risk of cumulative Permanent Threshold Shift. However, the Applicant will also not commit to delivering additional primary or secondary mitigation, despite currently being unable to mitigate their full injury zone. Natural England maintain our advice that additional mitigation should be committed to. See Appendix F5 for further detail. |  | Natural England welcomes that PTS impacts have been included in the the RIAA [REP5-010], however we disagree with the assessment conclusions and that mitigation has been appropriately secured. Please see Appendix F6 of our Deadline 6 submission for further detail. |  | Issue progressed. The Applicant has given Natural England advance sight of updates to the DCO condition related to noise mitgation for piling to be submitted at Deadline 7. We advise that we are satisfied that this updated condition sufficiently secures the application of additional primary and/or secondary mitigation. However, mitigation cannot guarantee that no animals will be at risk of PTS and we therefore maintain that PTS should be included in the CEA screening. We understand that the Applicant will be submitting an updated Chapter 11-Marine Mammals [APP-095] at Deadline 7. We will provide further comment at Deadline 8. |  | No Change. Whilst we welcome updates to the DCO condition related to underwater noise mitigation for piling submitted at Deadline 7 [REP7-011], mitigation cannot guarantee that no animals will be at risk of PTS. We therefore maintain that PTS should be included in the CEA screening. In the updated ES Chapter 11 submitted at Deadline 7 [REP7-046], the Applicant states that ‘PTS has been included in the iPCoD modelling as a precautionary approach but not assessed separately'. This is insufficient to resolve our concerns as it means the cumulative assessment has only taken account of the iPCoD modelling, not the other assessment methods used in the Chapter such as dose response curves. |  |  |  | No Change. Whilst we welcome updates to the DCO condition related to underwater noise mitigation for piling submitted at Deadline 7 [REP7-011], mitigation cannot guarantee that no animals will be at risk of PTS. We therefore maintain that PTS should be included in the CEA screening. In the updated ES Chapter 11 submitted at Deadline 7 [REP7-046], the Applicant states that ‘PTS has been included in the iPCoD modelling as a precautionary approach but not assessed separately'. This is insufficient to resolve our concerns as it means the cumulative assessment has only taken account of the iPCoD modelling, not the other assessment methods used in the Chapter such as dose response curves.
F5 | F17 | Natural England have reviewed the Underwater Noise Modelling Report and have no comments to make. However, we defer to Cefas for detailed comments on the methodology undertaken. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No change. |  | Natural England defer to Cefas on the UWN methodology. | [13 empty] | Natural England defer to Cefas on the UWN methodology.
F6 | F11, F18, F32 | The maximum predicted PTS impact range for a single pile installation is 13 km for harbour porpoise and 26 km for minke whales. These distances are too large to effectively be mitigated by Acoustic Deterrent Devices (ADDs). The Applicant needs to demonstrate how the full PTS impact range will be mitigated to ensure no injury is caused to marine mammals. Alternatively, the PTS impact range needs to be reduced to ensure ADDs can effectively deter animals from the zone of injury within 80 minutes (maximum PTS range will need to be 7.2 km for harbour porpoise and 15.6 km for minke whale). This could be achieved my reducing the maximum hammer energy in the Project envelope, or by committing to the use of NAS to reduce the sound at source. |  | The Defra Marine Noise Policy paper was published on 21st January 2025. Natural England is reviewing this in terms of what it means for our advice on this project. We will provide further comment on the relevant Outline MMMP and Draft In Principle SIP updates at Deadline 2. |  | No change. See Appendix F2 of Natural England's Deadline 2 submission for further detail. |  | No Change. Natural England's advice remains that The Applicant should be committing to using Noise Abatement Sytems at this stage in the application. See Appendix F3 for further detail. |  | No Change. Natural England's advice remains that The Applicant should be committing to using Noise Abatement Sytems at this stage in the application. See Appendix F4 for further detail. |  | No change. Natural England welcomes the submission of the Illustrative Underwater Noise Reduction Technical Note at Deadline 4, and agrees that were a 10dB noise reduction to be applied, the full PTS impact range could be mitigated via ADDs. However, the Applicant has not committed to delivering this reduction. We advise the Applicant to commit to reducing the estimated noise by 10dB via primary and/or secondary mitigation, with the exact methods to be deployed determined post-consent. See Appendix F5 for further detail. |  | No Change - Natural England acknowledges the updates to the Illustrative Underwater Noise Reduction Technical Note at Deadline 5, however our Deadline 5 advice remains regarding commitments to primary and/or secondary mitigation. Please see Appendix F6 of our Deadline 6 submission for further detail. |  | Issue Resolved. The Applicant has given Natural England advance sight of updates to the DCO condition related to noise mitgation for piling to be submitted at Deadline 7. We advise that we are satisfied that this updated condition sufficiently secures the application of additional primary and/or secondary mitigation. Whilst the Applicant has not committed to specific level of noise reduction in dB, we are satisfied that the assessment provided in [REP5-033] has demonstrated that mitigation could be applied to reduce the injury zone to a level that could be fully mitigated with ADD usage of less than 80 minutes for all species. We therefore consider this issue resolved. | [5 empty] | Issue Resolved. The Applicant has given Natural England advance sight of updates to the DCO condition related to noise mitgation for piling to be submitted at Deadline 7. We advise that we are satisfied that this updated condition sufficiently secures the application of additional primary and/or secondary mitigation. Whilst the Applicant has not committed to specific level of noise reduction in dB, we are satisfied that the assessment provided in [REP5-033] has demonstrated that mitigation could be applied to reduce the injury zone to a level that could be fully mitigation within ADD usage of less than 80 minutes for all species. We therefore consider this issue resolved.
F7 | F20 | The predicted maximum injury zone for some UXO clearance events is larger than the area for many ADDs to effectively deter marine mammals from. Provide planned ADD durations to demonstrate that the maximum injury zone for UXO clearance can be mitigated. If this is not possible, additional mitigation or methods to reduce the sound at source should be investigated. |  | As part of the Defra Marine Noise Policy paper that was published on 21st January 2025, an updated Unexploded Ordnance (UXO) Joint Position Statement was published. Natural England is reviewing this in terms of what it means for our advice on this project. We will provide further comment on the relevant Outline MMMP and Draft In Principle SIP updates at Deadline 2. |  | No change. See Appendix F2 of Natural England's Deadline 2 submission for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Issue resolved. Natural England welcomes the Applicant's updates to the outline MMMP to include low order methods as default for UXO removal, and to use NAS where high order is unavoidable. Natural England advises that UXO clearance with and without additional mitigation measures including ADD durations, are presented in the final UXO clearance MMMP and UXO clearance Marine Licence Application. | [9 empty] | Issue resolved. Natural England welcomes the Applicant's updates to the outline MMMP to include low order methods as default for UXO removal, and to use NAS where high order is unavoidable. Natural England advises that UXO clearance with and without additional mitigation measures including ADD durations, are presented in the final UXO clearance MMMP and UXO clearance Marine Licence Application.
F8 | F21 | Natural England supports increasing the Monitoring Area (MA) to ensure it is greater than the maximum predicted impact range for PTS. Consideration should be given to how this zone can be effectively monitored to ensure all marine mammals can be detected. This may require using more marine mammal observers (MMObs) and implementing stricter limits on workable weather conditions. The MMMP should be updated as needed. |  | The Defra Marine Noise Policy paper was published on 21st January 2025. Natural England is reviewing this in terms of what it means for our advice on this project. We will provide further comment on the relevant Outline MMMP and Draft In Principle SIP updates at Deadline 2. |  | No change. See Appendix F2 of Natural England's Deadline 2 submission for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. Whilst Natural England welcomes the demonstrated impact reductions outlined in the Underwater Noise Reduction Technical Note [REP4-094], we advise that this reduction in noise is commited to, and then included in updated modelling and the MMMP. Please see Appendix F5 for further detail. |  | No Change - Natural England acknowledges the updates to the Illustrative Underwater Noise Reduction Technical Note at Deadline 5, however our Deadline 5 advice remains regarding commitments to primary and/or secondary mitigation. Please see Appendix F6 of our Deadline 6 submission for further detail. |  | Issue Resolved. The Applicant has given Natural England advance sight of updates to the DCO condition related to noise mitgation for piling to be submitted at Deadline 7. We advise that we are satisfied that this updated condition sufficiently secures the application of additional primary and/or secondary mitigation, and that the assessment provided in [REP5-033] has demonstrated that mitigation could be applied to reduce the injury zone to a level that could be monitored. We therefore consider this issue resolved. | [5 empty] | Issue Resolved. The Applicant has given Natural England advance sight of updates to the DCO condition related to noise mitgation for piling to be submitted at Deadline 7. We advise that we are satisfied that this updated condition sufficiently secures the application of additional primary and/or secondary mitigation, and that the assessment provided in [REP5-033] has demonstrated that mitigation could be applied to reduce the injury zone to a level that could be monitored. We therefore consider this issue resolved.
F9 | F22 | The Mitigation area/zone needs to be monitored for a minimum of 30 minutes prior to the ADD activation to reduce the risk of injury to marine mammals from the ADD. This should be updated in the MMMP. |  | Natural England will provide comment on the Outline MMMP at Deadline 2. |  | Issue Resolved . Natural England has reviewed the updates made to [AS-101] Outline MMMP and are satisfied this issue has been addressed. | [15 empty] | Issue Resolved . Natural England has reviewed the updates made to [AS-101] Outline MMMP and are satisfied this issue has been addressed.
F10 | F23 | Piling should not commence (or recommence) in poor visibility or hours of darkness where Marine Mammal Observers (MMOb) cannot be used. There are limitations to Passive Acoustic Monitoring (PAM) so it should be used as well as, rather than instead of MMOb to optimise the ability to detect marine mammals and provide the best mitigation. Update Outline MMMP. |  | Natural England will provide comment on the Outline MMMP at Deadline 2. |  | No Change. Please refer to Appendix F2 regarding our comments on the updated Outline MMMP. |  | No Change. Natural England can only agree to piling during reduced visibility / darkness if the Applicant can demonstrate that the Passive Acoustic Monitoring (PAM) equipment can cover the whole Mitigation Area (MA).See Appendix F3 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. Natural England maintains our previous advice . |  | No Change. Please see Natural England's response to question R17.40 issued in the Rule 17 letter dated 9th June 2025, provided in our Deadline 6 Cover Letter. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. Whilst we acknowledge the commitment from the Applicant in the Outline Marine Mammal Mitigation Protocol [REP7-118] to ensure the monitoring area (MA) is fully mitigated with the use of Passive Acoustic Monitoring (PAM) during hours of darkness and reduced visibility, Natural England maintain our advice that the Applicant should present evidence that the PAM equipment can cover the whole Mitigation Area and will be sufficient to detect marine mammals that vocalise infrequently. The current Illustrative Noise Document [REP7-126] presents values that would suggest PAM is not currently sufficient, even when applying a 10db noise reduction through NAS. Without this evidence Natural England cannot ascertain if the proposed PAM equipment would be sufficient. |  |  |  | No Change. Whilst we acknowledge the commitment from the Applicant in the Outline Marine Mammal Mitigation Protocol [REP7-118] to ensure the monitoring area (MA) is fully mitigated with the use of Passive Acoustic Monitoring (PAM) during hours of darkness and reduced visibility, Natural England maintain our advice that the Applicant should present evidence that the PAM equipment can cover the whole Mitigation Area and will be sufficient to detect marine mammals that vocalise infrequently. The current Illustrative Noise Document [REP7-126] presents values that would suggest PAM is not currently sufficient, even when applying a 10db noise reduction through NAS. Without this evidence Natural England cannot ascertain if the proposed PAM equipment would be sufficient.
F11 | F24 | Natural England does not agree that the mitigated impacts of Permanent Threshold Shift (PTS) from piling are minor adverse - negligible for all marine mammals (See F5-F7). These conclusions are hinged on mitigation outlined in the MMMP which is not currently sufficient to fully mitigate the predicted PTS impacts. To ensure the impacts from underwater noise caused by piling are reduced for marine mammals we advise that the sound is reduced at source, this could be by modifying the design envelope (e.g. reducing the maximum hammer energy) or by using Noise Abatement Systems. |  | The Defra Marine Noise Policy paper was published on 21st January 2025. Natural England is reviewing this in terms of what it means for our advice on this project. We will provide further comment on the relevant Outline MMMP and Draft In Principle SIP updates at Deadline 2. |  | No change. See Appendix F2 of Natural England's Deadline 2 submission for further detail. |  | No Change. See Appendix F3 for further detail regarding Noise Abatement Systems. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change.Whilst Natural England welcomes the demonstrated impact reductions outlined in the Underwater Noise Reduction Technical Note [REP4-094], we advise that this reduction in noise is commited to and then reflected in updated ES documents as needed. See Appendix F5 for further detail. |  | No Change - Natural England acknowledges the updates to the Illustrative Underwater Noise Reduction Technical Note at Deadline 5, however our Deadline 5 advice remains regarding commitments to primary and/or secondary mitigation. Please see Appendix F6 of our Deadline 6 submission for further detail. |  | Issue Progressed. The Applicant has given Natural England advance sight of updates to the DCO condition related to noise mitgation for piling to be submitted at Deadline 7. We advise that we are satisfied that this updated condition sufficiently secures the application of additional primary and/or secondary mitigation. The Applicant has indicated in their Response to the Deadline 5 documents [REP6-052] that updates to Chapter 11 Marine Mammals [APP-095] will be submitted at Deadline 7 to incorporate primary and secondary mitigation measures. Natural England will provide our final position on this matter at Deadline 8. |  | The Applicant has submitted an updated ES Chapter 11 [REP7-046] and outline MMMP [REP7-118]. We will provide further comment at Deadline 9. Please see our Deadline 8 cover letter for our approach to the final two deadlines.
F12 | F25 | To reduce impact of piling in the Offshore Export Cable Corridor (OECC) on grey seals, we advise the Applicant commits to changing the design envelope (e.g. foundation bases with lower construction noise, reduced hammer energy) or the use of NAS to reduce the sound at source. |  | Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No change |  | Issue progressed. Natural England welcome the removal of piling in the ECC however outstanding concerns remain with the grey seal assessment. See Appendix L for further detail. |  | No Change. Natural England still have outstanding concerns regarding the grey seal assessment. See Appendix F4 for further detail. |  | Issue resolved. Natural England are closing out this issue as aspects relating to the ECC have been addressed. Our outstanding concerns with grey seal impacts will be focussed in F14, F18 and F19. | [9 empty] | Issue resolved. Natural England resolved this issue as aspects relating to the ECC have been addressed.
F13 | F26 | The number of Harbour porpoise potentially disturbed during single piling at DBS East, DBS West and both projects together is high, with up to 12.53% of the North Sea Management Unit (MU) disturbed. We consider this should result in a Major Adverse impact score. The Applicant has concluded minor adverse based on the results of iPCoD modelling alone. The EIA assessment should be updated based on the highest predicted impact values, for all receptors and pathways (not using iPCoD). Where a significant impact cannot be ruled out, the mitigation hierarchy should be explored to reduce the potential impacts. |  | No Change. |  | No Change. Please refer to Appendix F2 for detailed comments regarding Interim Population Consequences of Disturbance (iPCoD) Modelling. |  | No change. See Appendix L for Natural England's advice on the use of iPCoD modelling. |  | No Change. Natural England maintains the advice provided at Deadline 3. Please see Appendix F4 for further detail. |  | No Change. No new information relevant to this issue has been submitted at this deadline. The Applicant has stated that they will present updates to the Interim Population Consequence of Disturbance modelling in a revision of the Report to Inform Appropriate Assessment (RIAA) Habitats Regulations Assessment (HRA) Part 3 of 4 - Annex II Marine Mammals (Revision 3) [APP-047] at Deadline 5. Natural England will therefore provide further comment on this at Deadline 6. |  | No Change. Natural England maintain our previous advice. Please see Appendix F6 of our Deadline 6 submission for further detail. |  | Issue satisfactorily resolved. Whilst Natural England maintain our advice in relation to the approach taken to the EIA assessment, we are satisfied that the mitigation secured in the updated DCO condition to be submitted at Deadline 7 (detailed in other points) would also resolve any outstanding concerns with respect to EIA impacts were the assessment to be conducted in line with SNCB advice. | [5 empty] | Issue satisfactorily resolved. Whilst Natural England maintain our advice in relation to the approach taken to the EIA assessment, we are satisfied that the mitigation secured in the updated DCO condition to be submitted at Deadline 7 (detailed in other points) would also resolve any outstanding concerns with respect to EIA impacts were the assessment to be conducted in line with SNCB advice.
F14 | F27 | The number of grey seals disturbed during single piling at DBS East, DBS West and both projects together is high, with up to 30.62% of the South-East England MU disturbed. Using the number of animals potentially disturbed, the magnitude of impact is high, resulting in an impact score of moderate (significant). The EIA assessment should be updated based on the highest predicted impact values. Where a significant impact cannot be ruled out, the mitigation hierarchy should be explored to reduce the potential impacts. |  | No Change. |  | No Change. Please refer to Appendix F2 for detailed comments regarding Interim Population Consequences of Disturbance (iPCoD) Modelling. |  | No change. See Appendix L for Natural England's advice on the use of iPCoD modelling. |  | No Change. Natural England maintains the advice provided at Deadline 3. Please see Appendix F4 for further detail. |  | No Change. No new information relevant to this issue has been submitted at this deadline. The Applicant has stated that they will present updates to the Interim Population Consequence of Disturbance modelling in a revision of the Report to Inform Appropriate Assessment (RIAA) Habitats Regulations Assessment (HRA) Part 3 of 4 - Annex II Marine Mammals (Revision 3) [APP-047] at Deadline 5. Natural England will therefore provide further comment on this at Deadline 6. |  | No Change. Natural England maintain our previous advice. Please see Appendix F6 of our Deadline 6 submission for further detail. |  | Issue satisfactorily resolved. Whilst Natural England maintain our advice in relation to the approach taken to the EIA assessment, we are satisfied that the mitigation secured in the updated DCO condition to be submitted at Deadline 7 (detailed in other points) would also resolve any outstanding concerns with respect to EIA impacts were the assessment to be conducted in line with SNCB advice. | [5 empty] | Issue satisfactorily resolved. Whilst Natural England maintain our advice in relation to the approach taken to the EIA assessment, we are satisfied that the mitigation secured in the updated DCO condition to be submitted at Deadline 7 (detailed in other points) would also resolve any outstanding concerns with respect to EIA impacts were the assessment to be conducted in line with SNCB advice.
F15 | F28 | Natural England supports the Applicant’s commitment to a joint industry project or site-based monitoring project, and requests to be consulted on future marine mammal monitoring plans. |  | No Action Required. Natural England will be providing comments on the In Principle Monitoring Plan (IPMP) [APP-247] at Deadline 3. |  | No Change. |  | Please refer to Appendix J regarding Natural England's advice on the IPMP. | [13 empty] | Natural England maintain our previous advice submitted at Deadline 3 [REP3-056] and will provide further comment on marine mammal monitoring plans submitted post-consent.
F16 | F29 | We do not agree with the Applicant screening out PTS from the assessment on the basis of it being screened out from the Cumulative Effects Assessment. PTS should be screened into the HRA assessment. See comment F16. |  | No Change. |  | No Change. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Issue progressed. Natural England welcomes that PTS impacts have been included in the the RIAA [REP5-010], however we disagree with the assessment conclusions and that mitigation has been appropriately secured. Please see Appendix F6 of our Deadline 6 submission for further detail. |  | Issue Resolved. The Applicant has given Natural England advance sight of updates to the DCO condition related to noise mitgation for piling to be submitted at Deadline 7. We advise that we are satisfied that this updated condition sufficiently secures the application of additional primary and/or secondary mitigation to support the assessment conclusions. We therefore consider this issue resolved | [5 empty] | Issue Resolved. The Applicant has given Natural England advance sight of updates to the DCO condition related to noise mitgation for piling to be submitted at Deadline 7. We advise that we are satisfied that this updated condition sufficiently secures the application of additional primary and/or secondary mitigation to support the assessment conclusions. We therefore consider this issue resolved
F17 | F33, F34 | The conclusions for the RIAA illustrate that the noise thresholds for the SNS SAC would be significantly breached by the Project in combination with other noisy activities. Additional mitigation will be needed to avoid an Adverse Effect on Site Integrity (AEoI), however the current approach to implementing Site Integrity Plans (SIPs) for piling impacts to the Southern North Sea SAC does not allow sufficient time for mitigation methods, such as NAS, to be procured by the Applicant prior to construction should they be required. We strongly advise that the Applicant commit to the use of specific mitigation measures including noise abatement in the Outline SIP and MMMP at this stage. We advise that the effect of noise abatement systems in reducing noise impacts should be included in the submitted assessments. |  | The Defra Marine Noise Policy paper was published on 21st January 2025. Natural England is reviewing this in terms of what it means for our advice on this project. We will provide further comment on the relevant Outline MMMP and Draft In Principle SIP updates at Deadline 2. |  | No Change. Please refer to Appendix F2 for detailed comments regarding the Draft In Principle Site Integrity Plan for the Southern North Sea SAC. |  | No Change. See Appendix F3 for further detail regarding the Draft In Principle Site Integrity Plan for the Southern North Sea SAC. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. Natural England welcomes the submission of the Illustrative Underwater Noise Reduction Technical Note at Deadline 4, and agrees that were a 10dB noise reduction to be applied, an AEoI on SNS SAC could likely be ruled out. However, the Applicant has not committed to delivering this reduction. We advise the Applicant to commit to reducing the estimated noise by 10dB via primary and/or secondary mitigation, with the exact methods to be deployed determined post-consent. See Appendix F5 for further detail. Please see Appendix F5 for further detail. |  | No Change - Natural England acknowledges the updates to the Illustrative Underwater Noise Reduction Technical Note and RIAA at Deadline 5, however our Deadline 5 advice remains regarding commitments to primary and/or secondary mitigation. Please see Appendix F6 of our Deadline 6 submission for further detail. |  | Issue Resolved. The Applicant has given Natural England advance sight of updates to the DCO condition related to noise mitgation for piling to be submitted at Deadline 7. We advise that we are satisfied that this updated condition sufficiently secures the application of additional primary and/or secondary mitigation. Whilst the Applicant has not committed to a specific level of noise reduction in dB, we are satisfied that the assessment provided in [REP5-033] has demonstrated that mitigation could be applied to reduce impacts to a level where AEoI can be ruled out. We therefore agree that an AEoI can be ruled out for harbour porpoise in SNS SAC. | [5 empty] | Issue Resolved. The Applicant has given Natural England advance sight of updates to the DCO condition related to noise mitgation for piling to be submitted at Deadline 7. We advise that we are satisfied that this updated condition sufficiently secures the application of additional primary and/or secondary mitigation. Whilst the Applicant has not committed to a specific level of noise reduction in dB, we are satisfied that the assessment provided in [REP5-033] has demonstrated that mitigation could be applied to reduce impacts to a level where AEoI can be ruled out. We therefore agree that an AEoI can be ruled out for harbour porpoise in SNS SAC.
F18 | F35 | Natural England cannot agree to the conclusion of no AEoI on grey seals in the Humber Estuary SAC. The Applicant’s assessment suggests that more than 9% of the Humber Estuary SAC grey seal population has the potential to be impacted by disturbance from piling (monopile or jacket pin pile) in the OECC. The assessment conclusions should be updated based on the highest predicted impact values. Where an AEoI cannot be ruled out, additional mitigation should be explored to avoid or reduce impacts. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No change. |  | Natural England cannot rule out AEoI on Humber Estuary SAC at this time.See Appendix L for further detail. |  | No Change. Natural England still have outstanding concerns regarding the grey seal assessment. See Appendix F4 for further detail. |  | No Change. Natural England welcomes the submission of the Illustrative Underwater Noise Reduction Technical Note at Deadline 4, and agrees that were a 10dB noise reduction to be applied, an AEoI on grey seal from the Humber Estuary SAC could likely be ruled out. However, the Applicant has not committed to delivering this reduction. We advise the Applicant to commit to reducing the estimated noise by 10dB via primary and/or secondary mitigation, with the exact methods to be deployed determined post-consent. See Appendix F5 for further detail. Please see Appendix F5 for further detail. |  | No Change - Natural England acknowledges the updates to the Illustrative Underwater Noise Reduction Technical Note and RIAA at Deadline 5, however our Deadline 5 advice remains regarding commitments to primary and/or secondary mitigation. Please see Appendix F6 of our Deadline 6 submission for further detail. |  | Issue Resolved. The Applicant has given Natural England advance sight of updates to the DCO condition related to noise mitgation for piling to be submitted at Deadline 7. We advise that we are satisfied that this updated condition sufficiently secures the application of additional primary and/or secondary mitigation. Whilst the Applicant has not committed to a specific level of noise reduction in dB, we are satisfied that the assessment provided in [REP5-033] has demonstrated that mitigation could be applied to reduce impacts to a level where AEoI can be ruled out. We therefore agree that an AEoI can be ruled out for grey seal in the Humber Estuary SAC. | [5 empty] | Issue Resolved. The Applicant has given Natural England advance sight of updates to the DCO condition related to noise mitgation for piling to be submitted at Deadline 7. We advise that we are satisfied that this updated condition sufficiently secures the application of additional primary and/or secondary mitigation. Whilst the Applicant has not committed to a specific level of noise reduction in dB, we are satisfied that the assessment provided in [REP5-033] has demonstrated that mitigation could be applied to reduce impacts to a level where AEoI can be ruled out. We therefore agree that an AEoI can be ruled out for grey seal in the Humber Estuary SAC.
F19 | F36 | Natural England cannot agree to the conclusion of no AEoI on grey seals in the Berwickshire North Northumberland Coast (BNNC) SAC. The Applicant’s assessment suggests that more than 5% (and therefore a significant number) of the BNNC SAC grey seal population could be disturbed by piling at DBS West and OECC in isolation and together using the dose response approach. The assessment conclusions should be updated based on the highest predicted impact valuesys. Where an AEoI cannot be ruled out, additional mitigation should be explored to avoid or reduce impacts. |  | No Change. Natural England will provide further comment at Deadline 3 following review of the now accepted Change Request. |  | No change. |  | Natural England cannot rule out AEoI on Berwickshire North Northumberland Coast (BNNC) SAC at this time.See Appendix L for further detail. |  | No Change. Natural England still have outstanding concerns regarding the grey seal assessment. See Appendix F4 for further detail. |  | No Change. Natural England welcomes the submission of the Illustrative Underwater Noise Reduction Technical Note at Deadline 4, and agrees that were a 10dB noise reduction to be applied, an AEoI on grey seal from the BNNC SAC could likely be ruled out. However, the Applicant has not committed to delivering this reduction. We advise the Applicant to commit to reducing the estimated noise by 10dB via primary and/or secondary mitigation, with the exact methods to be deployed determined post-consent. See Appendix F5 for further detail. Please see Appendix F5 for further detail. |  | No Change - Natural England acknowledges the updates to the Illustrative Underwater Noise Reduction Technical Note and RIAA at Deadline 5, however our Deadline 5 advice remains regarding commitments to primary and/or secondary mitigation. Please see Appendix F6 of our Deadline 6 submission for further detail. |  | Issue Resolved. The Applicant has given Natural England advance sight of updates to the DCO condition related to noise mitgation for piling to be submitted at Deadline 7. We advise that we are satisfied that this updated condition sufficiently secures the application of additional primary and/or secondary mitigation. Whilst the Applicant has not committed to a specific level of noise reduction in dB, we are satisfied that the assessment provided in [REP5-033] has demonstrated that mitigation could be applied to reduce impacts to a level where AEoI can be ruled out. We therefore agree that an AEoI can be ruled out for grey seal in BNNC SAC. | [5 empty] | Issue Resolved. The Applicant has given Natural England advance sight of updates to the DCO condition related to noise mitgation for piling to be submitted at Deadline 7. We advise that we are satisfied that this updated condition sufficiently secures the application of additional primary and/or secondary mitigation. Whilst the Applicant has not committed to a specific level of noise reduction in dB, we are satisfied that the assessment provided in [REP5-033] has demonstrated that mitigation could be applied to reduce impacts to a level where AEoI can be ruled out. We therefore agree that an AEoI can be ruled out for grey seal in BNNC SAC.
F20 | F37 | Indirect Effects - We disagree that it can be concluded that there is no risk of AEoI to marine mammal SAC features as a result of impacts on prey species, solely due to impacts being ruled out at EIA scale. Consideration has also only been given to temporary construction impacts on prey in the RIAA, rather than the indirect effects of permanent spawning habitat loss that will also occur. Please see Appendix E for our detailed comments on the indirect effects assessment. |  | No Change. |  | No Change. We note the Applicant has contested the importance of the Dogger Bank sandbank system for prey availability and foraging species. Natural England disagrees with the justification provided and therefore maintains the advice provided in our Relevant Representation on this issue. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | The Applicant has indicated in their response to the ExA Questions [REP3-027] that a technical note relating to impacts on prey species will be provided at Deadline 4. Natural England will provide comments on receipt of this document. |  | No Change. Please see Appendix E5 for further detail. |  | No Change - Natural England maintains their Deadline 5 advice, and refers to Appendix E6 for further detail on impacts to fish species. |  | Issue satisfactorily resolved. The Applicant has given Natural England advance sight of updates to the DCO condition related to noise mitgation for piling to be submitted at Deadline 7. We have also been given sight of updated conditions with respect to piling restrictions for herring. We advise that we are satisfied that these updated conditions sufficiently secure the application of additional mitigation which could substantially reduce impacts to Atlantic herring (as demonstrated in [REP5-033]). Noting that AEoI conclusions are made at feature level, were an AEoI to be concluded for SNS SAC harbour porpoise overall, we would have considered indirect impacts to prey species to be a contributing factor. However, in light of the above, we do not consider the risk to harbour porpoise from indirect impacts on prey species is sufficient to drive an AEoI conclusion alone. Please see our responses to RIES Q32 and Q52 in Appendix N for further detail. Any outstanding issues relating to indirect effects are outlined in the Fish and Shellfish section of the R&I log submitted at Deadline 7. | [5 empty] | Issue satisfactorily resolved. The Applicant has given Natural England advance sight of updates to the DCO condition related to noise mitgation for piling to be submitted at Deadline 7. We have also been given sight of updated conditions with respect to piling restrictions for herring. We advise that we are satisfied that these updated conditions sufficiently secure the application of additional mitigation which would substantially reduce impacts to Atlantic herring (as demonstrated in [REP5-033]). Noting that AEoI conclusions are made at feature level, were an AEoI to be concluded for SNS SAC harbour porpoise overall, we would have considered indirect impacts to prey species to be a contributing factor. However, in light of the above, we do not consider the risk to harbour porpoise from indirect impacts on prey species is sufficient to drive an AEoI conclusion alone. Please see our responses to RIES Q32 and Q52 in Appendix N for further detail. Any outstanding issues relating to indirect effects are outlined in the Fish and Shellfish section of this R&I log submitted at Deadline 7.
F21 | New |  |  |  |  | Whilst Natural England welcomes the Applicant updating the DCO to include the Maximum Hammer Energy, we advise that within Section 3.1.5 of the Outline MMMP [AS-101] it is clearly stated what the Applicant’s intentions are regarding the commencing hammer energy in addition to the percentage of the maximum hammer energy this represents. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Issue Resolved. Natural England welcomes the Applicant's updates regarding the commencing hammer energy in addition to the percentage of the maximum hammer energy this represents in the Outline MMMP. The Applicant must include confirmation of these values in the final MMMP. | [9 empty] | Issue Resolved. Natural England welcomes the Applicant's updates regarding the commencing hammer energy in addition to the percentage of the maximum hammer energy this represents in the Outline MMMP. The Applicant must include confirmation of these values in the final MMMP.
F22 | New |  |  |  |  | Natural England welcomes the Applicant's Scheduling of UXO clearance with other projects (Section 9.6 of Draft In Principle Site Integrity Plan) as a useful tool for minimising the area of disturbance on a particular day; however this method should be in addition to noise reducing technology as outlined in Defra’s recently published Marine Noise Package. Natural England will provide further comment following the Applicant's review of the Defra Noise Package documents and updated assessment and mitigation measures. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Issue resolved. Natural England welcomes the Applicant's updates to the outline MMMP to include low order methods as default for UXO removal, and to use NAS where high order is unavoidable. Natural England advises that UXO clearance with and without additional mitigation measures, are presented in the final UXO clearance MMMP and UXO clearance Marine Licence Application. | [9 empty] | Issue resolved. Natural England welcomes the Applicant's updates to the outline MMMP to include low order methods as default for UXO removal, and to use NAS where high order is unavoidable. Natural England advises that UXO clearance with and without additional mitigation measures, are presented in the final UXO clearance MMMP and UXO clearance Marine Licence Application.
F23 | New | [12 empty] | The following new issue was missed from the Deadline 6 submission of the R&I log [REP6-075] in error: Following updated values submitted in the RIAA [REP5-010], Natural England cannot agree to the conclusion of no AEoI on harbour seal in the Wash and North Norfolk Coast (WNNC) SAC for the project in combination with other plans or projects. Please see Appendix F6 [REP6-075] for further detail. |  | No change. Natural England are awaiting further clarification on whether the impacts presented in [REP5-010] are correct. However, following discussions with the Applicant we understand that an updated Illustrative Noise Reduction Technical Note [REP5-033] will be submitted at Deadline 7 to incorporate WNNC SAC harbour seal. In combination with the updated DCO condition detailed above, we consider it likely that this issue will be resolved within Examination. We will provide further comment at Deadline 8. |  | Issue Resolved. The Applicant has updated Illustrative Noise Reduction Technical Note [REP7-126] to include assessments for harbour seal in the Wash and North Norfolk Coast (WNNC) SAC, along with the update to the DCO condition [REP7-011] to include a commitment to noise mitigation for piling. We advise that we are satisfied that this updated condition sufficiently secures the application of additional primary and/or secondary mitigation to support the assessment conclusions. We therefore consider this issue resolved. Whilst the Applicant has not committed to a specific level of noise reduction in dB, we are satisfied that the assessment provided in the Illustrative Noise Reduction Technical Note [REP7-126] has demonstrated that mitigation could be applied to reduce impacts to a level where AEoI can be ruled out. We therefore agree that an AEoI can be ruled out for harbour seal in WNNC SAC. |  |  |  | Issue Resolved. The Applicant has updated Illustrative Noise Reduction Technical Note [REP7-126] to include assessments for harbour seal in the Wash and North Norfolk Coast (WNNC) SAC, along with the update to the DCO condition [REP7-011] to include a commitment to noise mitigation for piling. We advise that we are satisfied that this updated condition sufficiently secures the application of additional primary and/or secondary mitigation to support the assessment conclusions. We therefore consider this issue resolved. Whilst the Applicant has not committed to a specific level of noise reduction in dB, we are satisfied that the assessment provided in the Illustrative Noise Reduction Technical Note [REP7-126] has demonstrated that mitigation could be applied to reduce impacts to a level where AEoI can be ruled out. We therefore agree that an AEoI can be ruled out for harbour seal in WNNC SAC.

## G - Offshore Ornithology
Point | Point Number(s) from Appendix G [RR-039] | Taken from Natural England’s Relevant and Written Representations Dogger Bank South (East and West) Appendix G - Offshore Ornithology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 1 | Consultation, actions, progression | RAG February 27 submission | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | End of Examination Position | Issue Resolved
G1 | G11 | We do not support the approach taken by the Applicant to combine the impacts of the two arrays for several aspects of the assessment (e.g. abundance estimates and displacement) as it underrepresents the impacts. The impacts for the arrays should be calculated separately for each array and summed to represent the worst-case scenario. |  |  |  | Issue resolved. The Applicant has updated abundance estimates for the arrays combined in line with SNCB advice. | [13 empty] | Issue resolved. The Applicant has updated abundance estimates for the arrays combined in line with SNCB advice.
G2 | G12 | The baseline surveys undertaken are broadly appropriate, however there are outstanding issues with how the data has been characterised. |  |  |  | Issue resolved. See G3. | [13 empty] | Issue resolved. See G3.
G3 | G13 | There is considerable variation in the abundance and density estimates between survey years for several species, however no assessment of between-year variation has been undertaken and no additional datasets have been considered when characterising the baseline. We advise that the Applicant provides an assessment of between-year variation in their baseline data with consideration of additional datasets, such as baseline data from other nearby OWF projects and modelled datasets, to characterise and assess the representativeness of the baseline. This is particularly important given that the baseline survey period includes months before and during the recent highly pathogenic avian influenza (HPAI) outbreaks. |  |  |  | Issue resolved. We are broadly satisfied that the baseline has been satisfactorily characterised. | [13 empty] | Issue resolved. We are broadly satisfied that the baseline has been satisfactorily characterised.
G4 | G14 | The Applicant has not used the most recent seabird census or latest research on impacts of HPAI in there assessment (e.g. Tremlett et al 2024). The Applicant should consider all relevant evidence on seabird population trends when assessing impacts and present an updated assessment that reflects this. |  |  |  | Issue largely resolved. Natural England welcomes that the additional evidence has now been included, however we do not agree with the current interpretation of the trends in the assessment. Please see Appendix G2, Table 2 for further detail. | [13 empty] | Issue largely resolved. Natural England welcomes that the additional evidence has now been included, however we do not agree with the current interpretation of the trends in the assessment. Please see Appendix G2, Table 2 for further detail.
G5 | G11, G15 | We do not support the approach taken by the Applicant to combine the monthly abundance estimates for the two arrays. As the 2km buffers for the two arrays do not overlap, we advise that the monthly abundance estimates for the arrays combined should be calculated as the sum of the monthly abundance estimates for each separate array. |  |  |  | Issue resolved. The Applicant has updated abundance estimates for the arrays combined in line with SNCB advice. | [13 empty] | Issue resolved. The Applicant has updated abundance estimates for the arrays combined in line with SNCB advice.
G6 | G11, G16 | Seasonal peak abundances for the arrays combined should be calculated as the sum of the highest value from each each array, even if these occur in different months. The current approach will cause the impacts calculated in the displacement assessment to be underestimated (see G21). |  |  |  | Issue resolved. The Applicant has updated abundance estimates for the arrays combined in line with SNCB advice. | [13 empty] | Issue resolved. The Applicant has updated abundance estimates for the arrays combined in line with SNCB advice.
G7 | G17 | There appear to be several inconsistencies in the abundance estimates presented for razorbill. All razorbill monthly and seasonal mean peak abundance estimates for both arrays should be checked to ensure accuracy and consistency, and that the correct abundance estimates have been used for displacement assessments throughout. If necessary, updates to the assessment should be provided. |  |  |  | Issue resolved. The Applicant has confirmed that the numbers presented are correct and that no updates are needed. | [13 empty] | Issue resolved. The Applicant has confirmed that the numbers presented are correct and that no updates are needed.
G8 | G18 | The Applicant has not included an assessment of displacement impacts for the decommissioning phase. We advise that displacement impacts at decommissioning are included for all species in the displacement assessment and calculated as per construction displacement impacts. |  |  |  | No change. Natural England advise that it would be beneficial for decommissioning impacts are to be explicitly quantified in the assessment as for construction impacts. | [13 empty] | No change. Natural England advise that it would be beneficial for decommissioning impacts are to be explicitly quantified in the assessment as for construction impacts.
G9 | G19 | The Applicant has not used Natural England’s advised baseline mortality rates or EIA reference populations for several species. An updated assessment should be provided using the SNCB advised EIA reference populations and baseline mortality rates to calculate annual background mortality for all species, with impacts assessed against these annual background mortality rates. |  |  |  | Issue Resolved. Natural England welcome that the Applicant has updated EIA baseline mortality rates and reference populations to reflect our advice. | [13 empty] | Issue Resolved. Natural England welcome that the Applicant has updated EIA baseline mortality rates and reference populations to reflect our advice.
G10 | G20 | The Applicant has used mean maximum foraging ranges when determining connectivity of the projects to seabird breeding colonies instead of the recommended mean maximum foraging ranges + 1SD. We advise that mean maximum foraging range plus 1SD (Woodward et al., 2019) is used to establish connectivity between the projects and seabird breeding colonies. |  |  |  | Natural England have reviewed the Applicant's response, and whilst we maintain that it would be best practice for the mean max foraging range +1SD to be used in the EIA assessment, we agree that it has been used correctly for the HRA assessment and would not materially impact the EIA conclusions. We will not pursue this further. | [13 empty] | Natural England have reviewed the Applicant's response, and whilst we maintain that it would be best practice for the mean max foraging range +1SD to be used in the EIA assessment, we agree that it has been used correctly for the HRA assessment and would not materially impact the EIA conclusions. We will not pursue this further.
G11 | G21 | The displacement assessment impacts for the arrays combined do not reflect the sum of the displacement impacts of the arrays summed, due to the method used to calculate seasonal peak abundance for the arrays combined (see G16). We advise that displacement impacts are re-calculated separately for each array and then summed. |  |  |  | Issue resolved. The Applicant has updated their displacement assessment for the arrays combined in line with SNCB advice. | [13 empty] | Issue resolved. The Applicant has updated their displacement assessment for the arrays combined in line with SNCB advice.
G12 | G22 | The spatial distribution figures show that high densities of auks (particularly guillemot and razorbill) were recorded in the area between the two arrays, but outside the 2km buffer. We consider it is likely that birds in this area will be vulnerable to cumulative displacement impacts from the arrays on either side. We advise that an assessment of cumulative displacement impacts on auks between the arrays is provided. |  |  |  | No Change. Natural England maintain our previous advice that further assessment is needed of cumulative displacement impacts on auks between the arrays. Please refer to Appendix G2, Table 2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change - Natural England maintain our previous advice. |  | Issue progressed. Natural England understand that the Applicant will be submitting a cumulative displacement assessment for the full area between the two arrays at Deadline 5. This was presented to Natural England at a meeting on 7th May 2025 and we have agreed that, pending review of the full report, this will be sufficient to provide necessary context and impact conclusions would likely be unaffected. |  | No Change. The Applicant has stated that the technical note outlining displacement between the two arrays will be submitted at Deadline 6. |  | Issue resolved. We welcome the Applicant's provision of an assessment of cumulative displacement impacts on auks between the two arrays in [REP6-053]. We agree with the Applicant that the EIA and HRA assessment does not need to be updated further. |  |  |  | Issue resolved. We welcome the Applicant's provision of an assessment of cumulative displacement impacts on auks between the two arrays in [REP6-053]. We agree with the Applicant that the EIA and HRA assessment does not need to be updated further.
G13 | G23 | The Applicant has not followed the SNCB Best Practice Guidance for calculating construction displacement impacts, which is to halve the operational impacts. We advise that the construction displacement assessment is updated. |  |  |  | Issue resolved. Natural England have reviewed the Applicant's response and are satisfied with the construction displacement assessment provided. | [13 empty] | Issue resolved. Natural England have reviewed the Applicant's response and are satisfied with the construction displacement assessment provided.
G14 | G24 | We do not agree with the approach taken for seasonality when assessing impacts on guillemot. We advise that the assessment is updated with August and September treated as a separate ‘chick rearing and moult’ season, with seasonal mean peaks and impacts calculated accordingly. |  |  |  | Issue resolved. This has been addressed in the Applicant's updated assessment. | [13 empty] | Issue resolved. This has been addressed in the Applicant's updated assessment.
G15 | G25 | Whilst the Applicant has presented the results of the displacement assessment for auks using Natural England’s advised ranges for displacement and mortality rates, they have consistently stated that these advised rates are not appropriate or evidence-based and have not considered impacts calculated using these rates in their conclusions. The forthcoming Offshore Renewables Joint Industry Programme (ORJIP) project ‘Improving understanding of distributional change for relevant seabird species (ImpUDis)’ will provide a comprehensive overview of auk displacement. Until this project returns evidence which can inform displacement rates of auks, Natural England continue to advise the use of the displacement matrix set out in our Best Practice Guidance and will base our conclusions on impacts calculated using these rates. |  |  |  | No Change. Natural England maintain the advice provided in our Relevant Representation. Please see Appendix G2, Table 2 for further detail. | [13 empty] | No Change. Natural England maintain the advice provided in our Relevant Representation. Please see Appendix G2, Table 2 for further detail.
G16 | G26 | The Applicant has not followed the SNCB advised approach for assessing gannet collision risk. We advise that gannet collision is assessed using an avoidance rate of 99.3%, along with a range of macro-avoidance rates between 65-85%. |  |  |  | Issue Resolved. The Applicant has updated their gannet collision risk assessment in accordance with Natural England’s advice. | [13 empty] | Issue Resolved. The Applicant has updated their gannet collision risk assessment in accordance with Natural England’s advice.
G17 | G27 | We advise that disturbance and displacement impacts are screened into the cumulative assessment for Red-throated Diver and relevant mitigation measures identified e.g. use of existing shipping lanes until beyond 2km of the SPA. |  |  |  | Natural England welcome that a cumulative assessment has been provided for impacts on red-throated diver, however we advise that clarification is needed on how the values presented have been arrived at. See Appendix G2, Table 2 for further detail. |  | Please see Change Request Appendix L of our Deadline 3 submission for further advice on impacts to Red Throated Diver. |  | The Applicant has indicated that they will review the assessment values and update as needed at Deadline 4. Natural England will provide further comment at Deadline 5. We can also confirm that, as noted by the Applicant, the reference to array displacement in our Appendix G2 comment was made in error. |  | Issue resolved. This has been addressed in the Applicant's updated assessment. | [7 empty] | Issue resolved. This has been addressed in the Applicant's updated assessment.
G18 | G28, G63 | Further consideration should be given to potential mitigation measures to reduce impacts on bird features, such as array reductions, changes to design and layout of arrays, or increasing the hub height of turbines. Hotspot modelling of seabird densities and distributions in the study area may help to identify areas where impacts are particularly high. |  |  |  | No Change. Natural England continue to advise that further consideration is given to potential mitigation measures to reduce impacts on seabird features, such as array reductions, changes to design and layout of arrays, or increasing the hub height of turbines. See Appendix G2, Table 2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. The Applicant maintains their position that no additional mitigation is required. Natural England maintain our previous advice. We will provide further comment at Deadline 5 following review of the Applicant's ISH written summaries. |  | No Change. The Applicant maintains their position that no additional mitigation is required. Natural England maintain our previous advice and have provided further advice in response to ISH Action 7 in Appendix M5 of our Deadline 5 submission. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. The Applicant's Responses to Deadline 5 Documents [REP6-052] confirms that they will not present hotspot modelling as 'any further reductions in the developable area within the lease boundaries would risk making the Projects economically unviable.' Whilst we note this argument, it is not within our field of expertise to comment on. Natural England maintains our previous advice [REP5-060] on the use of hotspot modelling and highlight its usage by other projects e.g. Outer Dowsing. We therefore consider that agreement will not be reached on this matter within Examination. |  | Issue progressed. Natural England welcome the Applicant's provision of some spatial mapping work in [REP7-137], however it is not sufficient to address our concerns. Please see our Deadline 8 cover letter for full details. |  | Natural England welcome the Applicant's provision of some spatial mapping work in [REP7-137], however it is not sufficient to address our concerns. Please see our Deadline 8 cover letter for full details.
G19 | G29 | We cannot agree with the EIA conclusions presented due to there being outstanding concerns with several aspects of the assessment, including: -baseline mortality rates and EIA reference populations used (G19) -guillemot seasonality (G24) -gannet collision risk (G26) -approach taken to combining the impacts of the two arrays (G11) We advise that updated assessments are provided in line with SNCB Best Practice Guidance. |  |  |  | Natural England cannot agree with the EIA conclusions presented due to there being outstanding concerns with several aspects of the assessment, including: •Discrepancies in cumulative impact figures (G54) •Lack of PVAs to assess cumulative impacts resulting in increases in background mortality rates of more than 1% (G56) •Lack of assessment of cumulative displacement impacts on auks between the arrays. (G12) |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Natural England welcome that the Applicant's review of the cumulative impacts and updated PVAs will be submitted at Deadline 4 (as stated in their response to the Deadline 2 documents[REP3-028]) and will provide comment at Deadline 5. |  | Issue satisfactorily resolved. Natural England have some outstanding concerns which we would ideally like to be addressed, however we acknowledge that they will not affect the assessment conclusions. Please see Appendix G5 for Natural England's updated EIA conclusions. | [7 empty] | Issue satisfactorily resolved. Natural England have some outstanding concerns which we would ideally like to be addressed, however we acknowledge that they will not affect the assessment conclusions. Please see Appendix G5 for Natural England's updated EIA conclusions.
G20 | G31 | Further detail and clarity is needed on the foraging ranges and SPA populations used to calculate breeding season apportioning proportions. We advise that the more up-to-date and contemporaneous SPA populations from Seabirds Count data (Burnell et al 2023) should be used to determine proportions for apportioning during the breeding season, rather than SPA citation populations, unless more recent counts are available. |  |  |  | Issue Resolved. The Applicant has updated their apportioning of guillemot and razorbill impacts to FFC SPA in line with SNCB advice. | [13 empty] | Issue Resolved. The Applicant has updated their apportioning of guillemot and razorbill impacts to FFC SPA in line with SNCB advice.
G21 | G32 | The adult baseline mortality for FFC SPA gannet should be recalculated using the 8.1% mortality rate from Horswill and Robinson (2015), and the rest of the assessment of impacts on this population adjusted accordingly. |  |  |  | Issue largely resolved. The Applicant has updated the adult baseline mortality rates for gannet, kittiwake, and razorbill to reflect our advice. However, we disagree with the Applicant’s characterisation of these trends in the RIAA. Please see Appendix G2, Table 2 for further detail. | [13 empty] | Issue largely resolved. The Applicant has updated the adult baseline mortality rates for gannet, kittiwake, and razorbill to reflect our advice. However, we disagree with the Applicant’s characterisation of these trends in the RIAA. Please see Appendix G2, Table 2 for further detail.
G22 | G33 | The adult baseline mortality for FFC SPA kittiwake should be recalculated using the Clarkson et al (2022) population estimate, and the rest of the assessment of impacts on this population adjusted accordingly. |  |  |  | Issue largely resolved. The Applicant has updated the adult baseline mortality rates for gannet, kittiwake, and razorbill to reflect our advice. However, we disagree with the Applicant’s characterisation of these trends in the RIAA. Please see Appendix G2, Table 2 for further detail. | [13 empty] | Issue largely resolved. The Applicant has updated the adult baseline mortality rates for gannet, kittiwake, and razorbill to reflect our advice. However, we disagree with the Applicant’s characterisation of these trends in the RIAA. Please see Appendix G2, Table 2 for further detail.
G23 | G34 | The adult baseline mortality and breeding season apportioning for FFC SPA puffin should be recalculated using the Clarkson et al (2022) count, and the rest of the assessment of impacts on this population adjusted accordingly. |  |  |  | Issue largely resolved. Natural England welcomes the updated calculation of adult baseline mortality for puffin at FFC SPA and note that, while the Applicant has still not followed Natural England’s advice, the discrepancy is unlikely to lead to a material difference in the impact values. | [13 empty] | Issue largely resolved. Natural England welcomes the updated calculation of adult baseline mortality for puffin at FFC SPA and note that, while the Applicant has still not followed Natural England’s advice, the discrepancy is unlikely to lead to a material difference in the impact values.
G24 | G35 | The adult baseline mortality for FFC SPA razorbill should be recalcuated using the Clarkson et al (2022) count, and the rest of the assessment of impacts on this population adjusted accordingly. |  |  |  | Issue largely resolved. The Applicant has updated the adult baseline mortality rates for gannet, kittiwake, and razorbill to reflect our advice. However, we disagree with the Applicant’s characterisation of these trends in the RIAA. Please see Appendix G2, Table 2 for further detail. | [13 empty] | Issue largely resolved. The Applicant has updated the adult baseline mortality rates for gannet, kittiwake, and razorbill to reflect our advice. However, we disagree with the Applicant’s characterisation of these trends in the RIAA. Please see Appendix G2, Table 2 for further detail.
G25 | G36 | We welcome that the Applicant has provided impact values with 100% adult apportioning to SPA colonies in line with SNCB advice, alongside their own approach using stable age structure. We disagree with the use of a theoretical generalised stable age structure to apportion impacts to adults from SPA colonies as it is unlikely to represent actual proportions of adults present and may lead to underestimation of impacts. Our conclusions on impacts will therefore be based on the values provided in line with SNCB advice. |  |  |  | To note. No further action needed. | [13 empty] | To note. No further action needed.
G26 | G37 | The results of displacement assessments for auks using Natural England’s advised range of displacement and mortality rates should be used to determine SPA features for Population Viability Analysis (PVA), and when assessing potential for AEoI at SPAs. |  |  |  | See G43. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Natural England welcome that the Applicant's review of PVA's will be submitted at Deadline 4 (as stated in their response to the Deadline 2 documents [REP3-028]) and will provide comment at Deadline 5. |  | Issue resolved. This has been addressed in the Applicant's updated assessment. | [7 empty] | Issue resolved. This has been addressed in the Applicant's updated assessment.
G27 | G38 | We advise that for apportioning of guillemot impacts to FFC SPA, August and September be treated as a separate ‘chick rearing and moult’ season, with seasonal mean peaks and impacts calculated accordingly. |  |  |  | Issue resolved. This has been addressed in the Applicant's updated assessment. | [13 empty] | Issue resolved. This has been addressed in the Applicant's updated assessment.
G28 | G39 | Clarification is needed on the guillemot apportioning method. Natural England advice is that adult proportions of guillemot during August and September be calculated according to the published productivity data for guillemot at FFC SPA during the years that the baseline surveys were undertaken (Cope et al 2021, Cope et al 2022). |  |  |  | Issue resolved. This has been addressed in the Applicant's updated assessment. | [13 empty] | Issue resolved. This has been addressed in the Applicant's updated assessment.
G29 | G40 | We do not agree with the use of the Biologically Defined Minimum Population Scale (BDMPS) method for apportioning razorbill impacts to FFC SPA in the post-breeding migration season. Based on the published productivity data for razorbill at FFC SPA during the years that the baseline surveys were undertaken (Cope et al 2021, Cope et al 2022), and allowing for the possibility of some degree of dilution by adults from other colonies to North, we advise that 69.93% of razorbill are apportioned as breeding adults at FFC SPA during the post-breeding migration season. |  |  |  | Issue resolved. This has been addressed in the Applicant's updated assessment. | [13 empty] | Issue resolved. This has been addressed in the Applicant's updated assessment.
G30 | G41 | We advise that the Applicant check that the correct minimum distance between FFC SPA and the arrays has been applied when considering apportioning rates to FFC SPA for kittiwake. |  |  |  | Issue resolved. This has been addressed in the Applicant's updated assessment. | [13 empty] | Issue resolved. This has been addressed in the Applicant's updated assessment.
G31 | G42 | The combined impacts of collision and displacement on FFC SPA gannet in the Applicant’s assessment for the arrays combined results in an increase in mortality rate of 0.9%. If when calculated according to Natural England’s advised approach the impacts of the arrays combined on FFC SPA gannet exceed the 1% threshold, then PVA should be undertaken for impacts of the projects alone. |  |  |  | Issue Resolved. Natural England welcomes that the Applicant has undertaken PVA to assess the impacts of the projects alone on FFC SPA gannet. | [13 empty] | Issue Resolved. Natural England welcomes that the Applicant has undertaken PVA to assess the impacts of the projects alone on FFC SPA gannet.
G32 | G43, G44 | We advise that PVAs are carried out for the impacts of the projects alone (i.e. DBS East and West combined) on kittiwake, guillemot and razorbill at FFC SPA, as the 1% mortality rate threshold is exceeded when assessments are conducted in line with SNCB advice. |  |  |  | Issue Progressed. Natural England welcomes that the Applicant has undertaken PVAs to assess the impacts of the projects alone on guillemot, kittiwake, and gannet at FFC SPA. The advice provided in our Relevant Representations still applies to that of razorbill at FFC SPA, which is yet to be provided. Please see Appendix G2, Table 2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Natural England welcome that the additional PVA will be submitted at Deadline 4 (as stated in their response to the Deadline 2 documents [REP3-028]) and will provide comment at Deadline 5. |  | Issue Resolved. Natural England welcomes the Applicant's updated PVAs for these species. | [7 empty] | Issue Resolved. Natural England welcomes the Applicant's updated PVAs for these species.
G33 | G45 | There is a discrepancy between the annual operational displacement impacts of the arrays combined on FFC SPA gannet presented in Table 9.12 (13.17) compared to the text in paragraph 109 (12.5). We advise this is checked and the appropriate values are used to calculate the impacts of displacement and collision combined. |  |  |  | Issue resolved. The Applicant has confirmed this was an error and the correct values have been used in the assessment. | [13 empty] | Issue resolved. The Applicant has confirmed this was an error and the correct values have been used in the assessment.
G34 | G47 | The descriptions of red-throated diver densities in the area of the Greater Wash SPA crossed by the cable corridor given in Chapter 7.12 and in Chapter 6.1 do not correspond. These should be checked and assessments updated as needed. |  |  |  | Issue resolved. This has been addressed in the Applicant's updated assessment. | [13 empty] | Issue resolved. This has been addressed in the Applicant's updated assessment.
G35 | G48 | The assessment of impacts on red-throated diver in the Greater Wash SPA does not consider impacts of the reduction in habitat resulting from disturbance/displacement during cable installation. We advise that the implications of cable installation on extent of available habitat for red-throated diver in the Greater Wash SPA is assessed and robust mitigation brought forward. |  |  |  | Natural England have reviewed the Applicant's response and agree that in this instance habitat reduction does not need to be assessed separately to disturbance/displacement for the cable installation works. However, please see G50 (G64)and Appendix G2 for for further comment on mitigation for red-throated diver disturbance. | [13 empty] | Natural England have reviewed the Applicant's response and agree that in this instance habitat reduction does not need to be assessed separately to disturbance/displacement for the cable installation works. However, please see G50 (G64)and Appendix G2 for for further comment on mitigation for red-throated diver disturbance.
G36 | G49 | The initial population sizes used in the PVA for kittiwake and razorbill at FFC SPA are 91,008 and 30,673 respectively. We advise that the appropriate population sizes to use are the 2022 count figures of 89,148 (kittiwake) and 61,345 (razorbill) (Clarkson et al 202210). The PVAs for kittiwake and razorbill at FFC SPA should be re-run using the appropriate initial population sizes (Clarkson et al 2022). |  |  |  | No Change. Natural England maintain our advice that the most recent population estimate should be used as the starting population for PVAs run for this population. See G57 and Appendix G2, Table 2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Issue progressed. Natural England acknowledge that the PVA updates provided in Annex A of [AS-085] were missed in our Deadline 2 review. We welcome that the kittiwake PVA was run with the correct starting population size. We will provide further comment at Deadline 5 following the Applicant's submission of the remaining PVA updates at Deadline 4 (as stated in their response to the Deadline 2 documents [REP3-028]). |  | Issue Resolved. This has been addressed in the Applicant's updated PVAs. | [7 empty] | Issue Resolved. This has been addressed in the Applicant's updated PVAs.
G37 | G50 | In-combination assessments have not been carried out for a number of SPA features. We advise that it would be best practice for the Applicant carry out in-combination assessments for all SPA features that have been screened in for assessment. As a minimum, we consider that in-combination assessments should be carried out for all species that meet the 1% baseline mortality threshold (calculated according to SNCB guidance), specifically guillemot at Farne Islands SPA, and Red-throated diver at the Greater Wash SPA. We consider there would also be merit in in-combination assessments being carried out for puffins at Farne Islands SPA and FFC SPA. |  |  |  | Issue progressed. The Applicant has provided in-combination assessments for guillemot and puffin at the Farne Islands SPA, however, we have outstanding concerns with some aspects of the assessment methodology. The Applicant has also included an in-combination assessment for Red-Throated Diver in the Greater Wash SPA. Whilst we do not fully agree with the approach taken for the RTD assessment (lack of consideration of impacts from other projects), due to the low predicted impacts we do not consider it would materially change our advice. Please see Appendix G2, Table 2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Natural England welcome that the Applicant's review and assessment updates will be submitted at Deadline 4 (as stated in their response to the ExA Questions [REP3-027]) and will provide comment at Deadline 5. |  | Issue Progressed. We welcome that the Applicant has submitted in-combination assessments for guillemot at Farne Islands SPA. However there are still outstanding concerns around this assessment. Please see Appendix G5 for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue satisfactorily resolved. The Applicant has provided an updated in-combination assessment with the relevant projects screened in for Farnes SPA in the updated RIAA HRA Part 4 of 4 - Marine Ornithological Features (Revision 5) [REP6-009] submitted at Deadline 6. Whilst some discrepanices remain in the final totals, we consider they are unlikely to have a material impact on assessment conclusions. |  |  |  | Issue satisfactorily resolved. The Applicant has provided an updated in-combination assessment with the relevant projects screened in for Farnes SPA in the updated RIAA HRA Part 4 of 4 - Marine Ornithological Features (Revision 5) [REP6-009] submitted at Deadline 6. Whilst some discrepanices remain in the final totals, we consider they are unlikely to have a material impact on assessment conclusions.
G38 | G51 | The impacts of several relevant Tier 4 projects have been left out of the in-combination assessments, including Outer Dowsing, Five Estuaries and North Falls offshore wind farms (OWF). Dogger Bank D OWF should also be included as a Tier 6 project. The in-combination assessment should be updated to include all relevant projects. |  |  |  | Issue progressed. We welcome that the Applicant has included all relevant Tier 4 projects in their in-combination assessment, however we advise the Applicant collaborates with other Round 4 developers to agree on how updated impact values (based on SNCB advice) can be efficiently incorporated as the Examinations of these projects progress, and that the Applicant updates the Examination at an appropriate juncture. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change - no new information relevant to this issue has been submitted at this deadline. It is Natural England's understanding that Dogger Bank D Section 42 PEIR is to be consulted on from 6 June - 1 August 2025 and therefore within the timeframes of this Examination. |  | No Change. Please see Appendix G5 for outstanding projects that Natural England advise the Applicant includes in the in-combination assessments. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Whilst the DBD PEIR is now in the public domain through a Section 42 consultation, we consider it would not be proportionate to update the in-combination assessment before the close of the Examination. Therefore we advise that when determining DBS windfarms the Secretary of State considers Dogger Bank D in their HRA. |  |  |  | Whilst the DBD PEIR is now in the public domain through a Section 42 consultation, we consider it would not be proportionate to update the in-combination assessment before the close of the Examination. Therefore we advise that when determining DBS windfarms the Secretary of State considers Dogger Bank D in their HRA.
G39 | G52 | The Applicant has excluded projects for which kittiwake compensation measures are required (Hornsea Three, Norfolk Boreas, Norfolk Vanguard, East Anglia Two, East Anglia One North, Hornsea Four, SEP&DEP) from their in-combination assessment. The Applicant should present in-combination assessments that both include and exclude compensated-for projects, for FFC SPA kittiwake. |  |  |  | Issue Resolved. The Applicant has presented in-combination totals both including and excluding compensated-for projects. | [13 empty] | Issue Resolved. The Applicant has presented in-combination totals both including and excluding compensated-for projects.
G40 | G53 | We do not support Hornsea 4 guillemot impacts being excluded from in-combination totals, as a high degree of uncertainty remains regarding the likely effectiveness of available measures to fully compensate for their impacts. We advise that in-combination totals should be presented both with and without the impacts of compensated-for projects due to the current uncertainty regarding the effectiveness of compensatory measures for auks. |  |  |  | Issue Resolved. The Applicant has presented in-combination totals both including and excluding compensated-for projects. | [13 empty] | Issue Resolved. The Applicant has presented in-combination totals both including and excluding compensated-for projects.
G41 | G54 | The in-combination totals calculated for impacts on kittiwake, guillemot, razorbill and gannet at FFC SPA do not appear to reflect the combined impacts of the arrays with other relevant projects. We note that the most recent agreed in-combination totals are for SEP & DEP. We advise that the in-combination totals for impacts on kittiwake, guillemot, razorbill and gannet at FFC SPA be recalculated, taking into account the impacts of all relevant projects (see G51&52), the DEP&SEP values, and any updated assessments resulting from advice within this Representation. |  |  |  | Issue progressed. Please refer to R&I points G58 and G59 for species specific comments. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Natural England welcome that the Applicant's review and assessment updates will be submitted at Deadline 4 (as stated in their response to the ExA Questions [REP3-027]) and will provide comment at Deadline 5. |  | No Change. The in-combination totals still do not appear to reflect the combined impacts of the arrays with other relevant projects. Please see Appendix G5 for further detail. |  | No change. The Applicant presented Natural England with their reasoning for the remaining discrepancies in a meeting on 9th June 2025. We understand the Applicant intends to formally submit this clarification at Deadline 6. Without prejudice to our formal review, we consider this has the potential to satisfactorily resolve this issue. |  | Issue satisfactorily resolved. We have reviewed the additional clarifications provided by the Applicant in REP6-052 on remaining discrepancies in in-combination totals between projects, and agree that they are unlikely to have a material impact on assessment conclusions. See our Deadline 7 cover letter for further detail. |  |  |  | Issue satisfactorily resolved. We have reviewed the additional clarifications provided by the Applicant in REP6-052 on remaining discrepancies in in-combination totals between projects, and agree that they are unlikely to have a material impact on assessment conclusions. See our Deadline 7 cover letter for further detail.
G42 | G55 | For the in-combination assessment of displacement impacts, the Applicant has presented apportioned abundance estimates for other projects, and then presented minimum and maximum displacement impacts in the text. The full methods and displacement matrices for these assessments have not been provided, and it is therefore not possible for us to evaluate the methods or the potential range of predicted impacts. We advise that the Applicant presents the details of the in-combination displacement assessment in full to allow the methods used and full range of predicted impacts to be evaluated. |  |  |  | No change. We advise the Applicant presents in-combination totals for displacement-affected species according to the agreed impact values for each project (as for in-combination collision assessment), rather than abundance estimates. Please see Appendix G2, Table 2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Natural England welcome that the Applicant's review and assessment updates will be submitted at Deadline 4 (as stated in their response to the Deadline 2 documents[REP3-028]) and will provide comment at Deadline 5. |  | No Change. Please see Appendix G5 for outstanding issues in regards to the in-combination assessments. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue satisfactorily resolved. We have reviewed the additional clarifications provided by the Applicant in REP6-052 on remaining discrepancies in in-combination totals between projects, and agree that they are unlikely to have a material impact on assessment conclusions. See our Deadline 7 cover letter for further detail. |  |  |  | Issue satisfactorily resolved. We have reviewed the additional clarifications provided by the Applicant in REP6-052 on remaining discrepancies in in-combination totals between projects, and agree that they are unlikely to have a material impact on assessment conclusions. See our Deadline 7 cover letter for further detail.
G43 | G56 | While Natural England appreciate the Applicant presenting PVA results for guillemot and razorbill considering both ends of Natural England’s advised range for displacement and mortality rates (i.e. from 30% displacement and 1% mortality to 70% displacement and 10% mortality) as well as Natural England’s advised adult apportioning rates, we note that only a limited number of results are presented from within this range. We advise the Applicant to present the results of the full range of displacement impacts on guillemot and razorbill in the PVA modelling. |  |  |  | No Change. Natural England advise that the PVAs run to assess the predicted impacts of the projects on guillemot and razorbill populations encompass the full range of Natural England’s advised displacement and mortality. Please see Appendix G2, Table 2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Natural England welcome that the Applicant's review of PVAs will be submitted at Deadline 4 (as stated in their response to the Deadline 2 documents [REP3-028]) and will provide comment at Deadline 5. |  | Issue Progressed. This has been largely addressed, however results have not been provided for in-combination FFC SPA totals with Hornsea 4 using 70% displacement and 5% mortality. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue satisfactorily resolved. Whilst the Applicant has not provided the full range of displacement impacts, outputs from both ends of the impact range as well as for 70% displacement and 2% mortality have been provided. |  |  |  | Issue satisfactorily resolved. Whilst the Applicant has not provided the full range of displacement impacts, outputs from both ends of the impact range as well as for 70% displacement and 2% mortality have been provided.
G44 | G57 | Interpretation of PVA results: Counterfactual of Population Size When interpreting results of PVAs, assessments should focus on both the counterfactual of population growth rate (CGR) and counterfactual of population size (CPS) to quantify the relative changes in population response to anthropogenic impacts, as they have been shown to be the least sensitive metrics to misspecification of the population trend and demographic rates used in the PVA model. Our integrity judgements will take into account both the CPS and CGR metrics to quantify the relative changes in population response to impacts. |  |  |  | No change. To note. | [13 empty] | No change. To note.
G45 | G58 | Interpretation of PVA results: use of mean peak abundance estimates In the absence of more robust empirical evidence on within-year and between-year variations in abundance, and on turnover rates, Natural England continue to advise that the use of seasonal mean peak abundance estimates is necessary and appropriate. |  |  |  | No change. We maintain our previous advice. | [13 empty] | No change. To note.
G46 | G59 | Interpretation of PVA results: characterisation of 1% mortality rate Natural England disagree with the Applicant’s statement that a 1% mortality rate for the displacement assessment on gannet (and referenced for other species) is “not based on any scientific evidence”. We refer the Applicant to our comments on the characterisation of NE advice in G25. |  |  |  | No change. We maintain our previous advice. | [13 empty] | No change. To note.
G47 | G60 | Interpretation of PVA results: use of as built parameters We do not consider it appropriate to reduce impact estimates by considering as-built parameters unless those parameters are legally secured. Speculation of impacts from ‘as built’ scenarios in in-combination/cumulative impact assessments are of little value unless legal agreements are put in place to ensure existing projects will not expand further. Without such agreements, there is no option other than to use impacts from consented designs in in-combination and cumulative assessments. |  |  |  | No change. Natural England note that we are actively engaged with industry in considering ways that ‘as-built’ parameters can be used within assessments. However, at present, we are unable to consider appropriate the use of as-built parameters in cumulative and in-combination assessments unless these parameters can be legally secured. | [13 empty] | No change. Natural England note that we are actively engaged with industry in considering ways that ‘as-built’ parameters can be used within assessments. However, at present, we are unable to consider appropriate the use of as-built parameters in cumulative and in-combination assessments unless these parameters can be legally secured.
G48 | G61 | Interpretation of PVA results: PVAs run as “closed populations” There is currently an absence of robust empirical evidence on the levels of immigration and emigration affecting the relevant seabird populations. In the absence of such evidence, it is impossible to construct population models that reliably represent metapopulation dynamics, and incorporating unproven assumptions about immigration and emigration into population models has the potential to underestimate development impacts on seabird populations. No assumptions can be made about unquantified resilience in wider populations, particularly given the many pressures acting on seabird populations throughout the region. |  |  |  | No change. We maintain our previous advice. | [13 empty] | No change. We maintain our previous advice.
G49 | G62 | Interpretation of PVA results for FFC SPA gannet, kittiwake, guillemot and razorbill In the Applicant’s interpretation of the PVA results for in-combination impacts on gannet, kittiwake, guillemot and razorbill at FFC SPA, they cite recent population growth at the SPA as a reason for concluding no AEoI is likely. Whilst we do not dispute the evidence of population growth at the colony in past years, we do not consider it appropriate to assume the same growth rate will continue over the next 30 years. It is highly likely that the populations will experience density-dependent mechanisms over the lifetime of the Project, and there are uncertainties about the long-term population impacts of HPAI and a wide range of other environmental pressures. We note that the Applicant has acknowledged the importance of considering density dependence and other pressures including HPAI and climate change elsewhere in the Application, but they have not considered these in their interpretation of the PVA results. Further, recent surveys have shown that UK gannet, kittiwake and guillemot populations declined by 25%, 18% and 20% respectively between the results of the last seabird census which covered the period between 2015 and 2021 (Burnell et al 20234), and the summer of 2023 (Tremlett et al 20245). Natural England advise that the Applicant considers realistic assessments of current and future population trends, considering all relevant evidence, when interpreting the results of updated PVAs. |  |  |  | No change. Natural England advise that the Applicant consider realistic assessments of current and future seabird population trends, considering all relevant evidence, when assessing the significance of the predicted impacts of the projects. Please see Appendix G2, Table 2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change - Natural England maintain our previous advice. |  | No change. Natural England note that the Applicant has not considered potential future changes in seabird population trends (due to density dependence, climate change impacts, and HPAI impacts) when assessing the interpretation of the PVA results, as previously advised by Natural England. However, whilst we would welcome this being addressed, it will not materially impact our assessment conclusions. Please see our response to ISH Action 10 in Appendix M5 for further detail. | [7 empty] | No change. Natural England note that the Applicant has not considered potential future changes in seabird population trends (due to a range of environmental pressures) when assessing the interpretation of the PVA results, as previously advised by Natural England. However, whilst we would welcome this being addressed, it will not materially impact our assessment conclusions. Please see our response to ISH Action 10 in Appendix M5 for further detail.
G50 | G64 | We advise that careful consideration should be given to avoiding or restricting cable installation works within 2km of the Greater Wash SPA during the over-wintering period (1st November to 31st March inclusive) to avoid adverse effects. |  |  |  | No change. Please see Appendix G2, Table 2 for further detail. |  | No Change. Natural England welcome the update outlined in the Commitments Register (Revision 2) [REP2-026] that the use of current shipping lanes will be included in the PEMMP [REP2-042], however our advice at Deadline 2 still applies. See Appendix L for further information on red-throated diver. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Issue resolved. Natural England welcome the clarification provided by the Applicant in [REP4-088] and are satisfied that an AEoI on Red throated diver in Greater Wash SPA can be ruled out due to the very limited interaction between the cable works area and the Greater Wash SPA and 2km buffer. | [7 empty] | Issue resolved. Natural England welcome the clarification provided by the Applicant in [REP4-088] and are satisfied that an AEoI on Red throated diver in Greater Wash SPA can be ruled out due to the very limited interaction between the cable works area and the Greater Wash SPA and 2km buffer.
G51 | G65 | We acknowledge the right of the Applicant to submit an assessment following their chosen methods, however in such circumstances an assessment should also be provided in line with SNCB advice. We are unable to comment on the assessment conclusions until such an assessment is provided. |  |  |  | Issue progressed. Natural England acknowledge and welcome the significant efforts that have been made to provide assessment values in line with SNCB advice. However, due to outstanding concerns with respect to in-combination assessments and PVAs, we remain unable to comment on the conclusions presented at this time. Please refer to Appendix G2, Table 2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Natural England understand that outstanding ornithology assessment updates will be submitted at Deadline 4 (as stated in their response to the Deadline 2 documents[REP3-028]). We will provide further comment at Deadline 5. |  | Issue satisfactorily resolved. Whilst some outstanding concerns remain with in-combination values and PVAs, the Project alone assessment is now sufficient for Natural England to advise on conclusions and impact values. | [7 empty] | Issue satisfactorily resolved. Whilst some outstanding concerns remain with in-combination values and PVAs, the Project alone assessment is now sufficient for Natural England to advise on conclusions and impact values.
G52 | G66 | Natural England disagree that it can be concluded that there is no risk of AEoI to ornithology SPA features as a result of impacts on prey species, solely due to impacts being ruled out at EIA scale. Consideration has also only been given to temporary construction impacts on prey in the RIAA, rather than the indirect effects of permanent spawning habitat loss that will also occur. Please see Appendix E for our detailed comments on the indirect effects assessment. |  |  |  | No change. We note the Applicant has contested the importance of the Dogger Bank sandbank system for prey availability and foraging species. Natural England disagrees with the justification provided and therefore maintains the advice provided in our Relevant Representation on this issue. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | The Applicant has indicated in their response to the Examiner's Questions [REP3-027] that a technical note relating to impacts on prey species will be provided at Deadline 4. Natural England will provide comment at Deadline 5. |  | No Change. Please see Appendix E5 and M5 for futher detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. Natural England consider that for those features where AEoI cannot be ruled out (kittiwake, guillemot and razorbill), this impact pathway will, without resulting in an AEOI in its own right, intensify those effects on those species. Please see our responses to RIES Q46, Q52 and Q53 in Appendix N7 for further detail. |  |  |  | Natural England consider that for those features where AEoI cannot be ruled out (kittiwake, guillemot and razorbill), this impact pathway will, without resulting in an AEOI in its own right, intensify those effects on those species. Please see our responses to RIES Q46, Q52 and Q53 in Appendix N7 for further detail.
G53 | NEW | NEW ISSUE |  |  |  | Presentation of displacement matrices including upper and lower confidence intervals Whilst the Applicant has updated their displacement assessment for the arrays combined the relevant tables in ES Appendix 12-12 [APP-115] have not been updated. Natural England advise that ES Appendix 12-12 [APP-115] is updated to reflect the updated displacement assessment figures and that all displacement matrices are presented (for both EIA and the RIAA), including for the upper and lower confidence intervals. Please see Appendix G2, Table 2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No change. Natural England acknowledge the difficulties associated with summing confidence intervals. However, we maintain our previous advice that the Applicant’s original method is inappropriate for calculating seasonal peak abundances and thus displacement impacts for the arrays combined (see R&I G6 and G11), which we consider leads to under-representation of impacts on displacement-affected species. We maintain our advice that displacement matrices are provided including upper and lower confidence intervals. Please see Appendix G4 for further detail. |  | Issue satisfactorily resolved. Whilst displacement matrices including confidence intervals have not been submitted, the upper confidence level impact figures for auks have been provided for use in calculation of compensation quanta. | [7 empty] | Issue satisfactorily resolved. Whilst displacement matrices including confidence intervals have not been submitted, the upper confidence level impact figures for auks have been provided for use in calculation of compensation quanta.
G54 | NEW | NEW ISSUE |  |  |  | Cumulative and in-combination totals Cumulative impact totals presented in 7.12 ES Chapter 12 [AS-058] and the unapportioned in-combination totals presented in 6.1 RIAA HRA Part 4 of 4 – Marine Ornithological Features (Revision 3) [AS-086] do not always match. We advise the Applicant to check the cumulative and in-combination totals for all species. Please see Appendix G2, Table 2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Natural England acknowledge the Applicant’s response [REP3-028], however, we consider that there is no scientific justification for applying different methods to calculating cumulative and in-combination totals. We therefore advise that the same methods be applied to both sets of calculations, noting that it would be appropriate for the Applicant to present totals for both methods for both cumulative and in-combination totals. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. The Applicant presented Natural England with their reasoning for the remaining discrepancies in a meeting on 9th June 2025. We understand the Applicant intends to formally submit this clarification at Deadline 6. Without prejudice to our formal review, we consider this has the potential to satisfactorily resolve this issue. |  | Issue resolved. This has been addressed in the Applicant's updated RIAA [REP6-009]. |  |  |  | Issue resolved. This has been addressed in the Applicant's updated RIAA [REP6-009].
G55 | NEW | NEW ISSUE |  |  |  | Great black-backed gull and lesser black-backed gull cumulative totals The cumulative collision totals presented for great black-backed gull and lesser black-backed gull are lower than the cumulative totals presented at SEP & DEP, despite additional impacts from several projects since the SEP&DEP examination, including those of Dogger Bank South. Natural England advise that the Applicant check the cumulative collision impacts for these species. Please see Appendix G2, Table 2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Natural England welcomes that the Applicant's review of the cumulative collision totals for these species will be submitted at Deadline 4 (as stated in their response to the Deadline 2 documents [REP3-028]) and will provide comment at Deadline 5. |  | No Change. We acknowledge that the Applicants have provided updated assessments, however the totals remain lower than expected. Please see Appendix G5 for further details. |  | No Change. The Applicant presented Natural England with their reasoning for the remaining discrepancies in a meeting on 9th June 2025. We understand the Applicant intends to formally submit this clarification at Deadline 6. Without prejudice to our formal review, we consider this has the potential to satisfactorily resolve this issue. |  | Issue satisfactorily resolved. We have reviewed the additional clarifications provided by the Applicant in REP6-052 on remaining discrepancies in in-combination totals between projects, and agree that they are unlikely to have a material impact on assessment conclusions. See our Deadline 7 cover letter for further detail. |  |  |  | Issue satisfactorily resolved. We have reviewed the additional clarifications provided by the Applicant in REP6-052 on remaining discrepancies in in-combination totals between projects, and agree that they are unlikely to have a material impact on assessment conclusions. See our Deadline 7 cover letter for further detail.
G56 | NEW | NEW ISSUE |  |  |  | Lack of PVAs for cumulative impact assessments The Applicant has not provided PVAs for cumulative EIA impacts, despite several of these amounting to increases in background mortality rates of over 1%, when assessed according to Natural England’s advice. Natural England advises that the Applicant run PVAs to assess projected impacts on populations wherever cumulative impacts lead to increases in background mortality rate of greater than 1% when calculated according to Natural England’s advice. Please see Appendix G2, Table 2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Natural England welcome that additional PVAs will be submitted at Deadline 4 (as stated in their response to the Deadline 2 documents [REP3-028]) and will provide comment at Deadline 5. |  | Issue resolved. PVAs have been provided for all necessary species. | [7 empty] | Issue resolved. PVAs have been provided for all necessary species.
G57 | NEW | NEW ISSUE |  |  |  | Presentation of PVA inputs and outputs Natural England advise that the updated inputs and outputs for all PVA scenarios undertaken for the assessment are clearly presented in Appendix 7.12.12.13 to reflect the updated impact values in the assessment and the PVA scenarios and results presented in the RIAA. This should include presenting the log files for all PVA scenarios undertaken, in order to enable assessment of the specification and paramaterisation of the models. This applies to PVAs presented for both the projects alone and in-combination with other projects. Please see Appendix G2, Table 2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Natural England acknowledge that the PVA updates provided in Annex A of [AS-085] were missed in our Deadline 2 review. We will provide further comment at Deadline 5 following the Applicant's submission of the remaining PVA updates at Deadline 4 (as stated in their response to the Deadline 2 documents [REP3-028]). |  | Issue Progressed. Whilst updated PVAs have been provided some results are still not as we would expect, and so we advise the Applicant to verify the results of all PVA scenarios run for the assessment. |  | The Applicant has confirmed to Natural England that an error has been identified in the PVAs, and that updated outputs will be submitted at Deadline 6 (meeting held 9th June 2025). |  | Issue resolved. The Applicant has provided corrected PVA outputs in [REP6-019]. |  |  |  | Issue resolved. The Applicant has provided corrected PVA outputs in [REP6-019].
G58 | NEW | NEW ISSUE |  |  |  | In-combination totals for kittiwake at FFC SPA In-combination totals for impacts on kittiwake at FFC SPA appear to be lower than we would expect, given the totals presented during the SEP&DEP Examination. Natural England advise that the Applicant check in-combination figures for kittiwake at FFC SPA and correct these if necessary. Please see Appendix G2, Table 2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Natural England welcome that the Applicant's review and assessment updates will be submitted at Deadline 4 (as stated in their response to the Deadline 2 documents[REP3-028]) and will provide comment at Deadline 5. |  | No change. Whilst we acknowledge the Applicant’s comments that these discrepancies are not likely to affect the assessment conclusions or compensation quantum (REP3-028), they lead to significantly lower in-combination impacts than we would expect, and it is important that the assessment is as accurate as possible as it may be used as a reference for future projects. |  | No Change. The Applicant presented Natural England with their reasoning for the remaining discrepancies in a meeting on 9th June 2025. We understand the Applicant intends to formally submit this clarification at Deadline 6. Without prejudice to our formal review, we consider this has the potential to satisfactorily resolve this issue. |  | Issue satisfactorily resolved. We have reviewed the additional clarifications provided by the Applicant in REP6-052 on remaining discrepancies in in-combination totals between projects, and agree that they are unlikely to have a material impact on assessment conclusions. See our Deadline 7 cover letter for further detail. |  |  |  | Issue satisfactorily resolved. We have reviewed the additional clarifications provided by the Applicant in REP6-052 on remaining discrepancies in in-combination totals between projects, and agree that they are unlikely to have a material impact on assessment conclusions. See our Deadline 7 cover letter for further detail.
G59 | NEW | NEW ISSUE |  |  |  | In-combination totals for guillemot and razorbill at FFC SPA Natural England advise the Applicant to refer to the advice provided to DEP & SEP on the appropriate displacement and mortality rates to be used for the impacts of Hornsea 4 on guillemot and razorbill at FFC SPA, and update their in-combination totals accordingly. Natural England recommend that the impacts of these updated figures are then assessed by PVA. Please see Appendix G2, Table 2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Natural England welcome that the Applicant's review and assessment updates will be submitted at Deadline 4 (as stated in their response to the Deadline 2 documents[REP3-028]) and will provide comment at Deadline 5. |  | No change. Whilst we acknowledge the Applicant’s comments that these discrepancies are not likely to affect the assessment conclusions or compensation quantum (REP3-028), they lead to significantly lower in-combination impacts than we would expect, and it is important that the assessment is as accurate as possible as it may be used as a reference for future projects. |  | No Change. The Applicant presented Natural England with their reasoning for the remaining discrepancies in a meeting on 9th June 2025. We understand the Applicant intends to formally submit this clarification at Deadline 6. Without prejudice to our formal review, we consider this has the potential to satisfactorily resolve this issue. |  | Issue satisfactorily resolved. We have reviewed the additional clarifications provided by the Applicant in REP6-052 on remaining discrepancies in in-combination totals between projects, and agree that they are unlikely to have a material impact on assessment conclusions. See our Deadline 7 cover letter for further detail. For some species (including FFC SPA razorbill), we note that totals for DBS appear lower that those for ODOW due to the inclusion of Scottish projects in the ODOW assessment. We advise that projects should be screened in/out of assessments based on the BDMPS regional definitions rather than which juristication the project falls in. We would therefore expect Scottish project to have also been included in the DBS assessment. However, we acknowledge that in this instance it would not have a material impact on the assessment conclusions. |  |  |  | Issue satisfactorily resolved. We have reviewed the additional clarifications provided by the Applicant in REP6-052 on remaining discrepancies in in-combination totals between projects, and agree that they are unlikely to have a material impact on assessment conclusions. See our Deadline 7 cover letter for further detail. With respect to FFC SPA razorbill, we note that the totals for DBS appear lower that those for ODOW due to the inclusion of Scottish projects in the ODOW assessment. We advise that projects should be screened in/out of assessments based on the BDMPS regional definitions, rather than which jurisdiction the project falls in. We would therefore expect Scottish project to have also been included in the DBS assessment. However, we acknowledge that in this instance it would not have a material impact on the assessment conclusions.
G60 | NEW | NEW ISSUE |  |  |  | PVA results The results of several of the PVAs undertaken by the Applicant are not as we would expect. Natural England advise that the Applicant check the results of all PVA scenarios run for the assessment, and ensure that the inputs and outputs of all scenarios are clearly presented, along with log files. Please see Appendix G2. Table 2 and G57 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Natural England welcome the clarification provided by the Applicant on the differences between the DEP&SEP and DBS assessments, and acknowledge that the PVA updates provided in Annex A of [AS-085] were missed in our Deadline 2 review. We will provide further comment at Deadline 5 following the Applicant's submission of the remaining PVA updates at Deadline 4 (as stated in their response to the Deadline 2 documents [REP3-028]). |  | Issue Progressed. Whilst updated PVAs have been provided some results are still not as we would expect, and so we advise the Applicant to verify the results of all PVA scenarios run for the assessment. |  | The Applicant has confirmed to Natural England that an error has been identified in the PVAs, and that updated outputs will be submitted at Deadline 6 (meeting held 9th June 2025). |  | Issue resolved. The Applicant has provided corrected PVA outputs in [REP6-019]. |  |  |  | Issue resolved. The Applicant has provided corrected PVA outputs in [REP6-019].

## H- Offshore Ornithology Comp
Point | Point Number(s) from Appendix H [RR-039] | Taken from Natural England’s Relevant and Written Representations Dogger Bank South (East and West) Appendix H - Offshore Ornithology Compensation | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 1 | Consultation, actions, progression | RAG February 28 submission | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | Consultation, actions, progression | RAG Deadline 8 | End of Examination Position | Issue Resolved
Kittiwake Compensation Document used: [APP-052] 6.2.1 Appendix 1 - Project Level Kittiwake Compensation Plan
H1 | H1 | Natural England recognises the current uncertainty around the implementation of the Kittiwake Strategic Compensation Plan (KSCP) and welcomes the provision of project-led kittiwake compensation measures, the alignment of these with the measures and approach outlined in the KSCP, and the commitment to securing these measures as a requirement of the DCO. | [17 empty] | Natural England recognises the current uncertainty around the implementation of the Kittiwake Strategic Compensation Plan (KSCP) and welcomes the provision of project-led kittiwake compensation measures, the alignment of these with the measures and approach outlined in the KSCP, and the commitment to securing these measures as a requirement of the DCO.
H2 | H2 | The Applicant has omitted the section of the KSCP which states: ‘11.1.2 The construction of two offshore SANS was preferred by the Steering Group to provide mitigation of risk of failure at one offshore SANS. Within this there was an ecological preference that these were in different locations, however it was agreed by the Steering Group that when considering the balance of economics that the two structures near to each other was perfectly acceptable.’ Further, we also highlight that only the first two options listed by the Applicant were supported by the SNCBs (Natural England and JNCC) in the Kittiwake Steering Group. This should be considered by the Applicant in the development of their project-led compensation proposals. |  |  |  | Issue Resolved. The text has been updated in Revision 2 of the Kittiwake Compensation Plan (KCP) [PDB-003]. | [13 empty] | Issue Resolved. The text has been updated in Revision 2 of the Kittiwake Compensation Plan (KCP) [PDB-003].
H3 | H3 | Natural England do not agree with the predicted impact values and compenstion levels presented. We advise that the KCP is updated following any reassessments undertaken in response to the advice provided in Appendix G. Compensation metrics should be presented in line with both the Applicant’s preferred method and SNCB guidance. |  |  |  | Issue progressed. Natural England acknowledge and welcome the significant efforts that have been made to provide assessment values in line with SNCB advice. However, due to outstanding concerns with respect to in-combination assessments and PVAs, we remain unable to comment on the conclusions and impact values presented at this time. Please see Appendix G2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Natural England welcome that the Applicant's updated KCP and outstanding aspects of the ornithology assessment will be submitted at Deadline 4, and will provide comment at Deadline 5. |  | Issue Progressed. Natural England are now in agreement with the Project alone assessment and welcome the Applicant's presentation of compensation requirements according to the 'Hornsea 3 part 2' method. However, Natural England advise that the Applicant check the results of their calculations as the figures are not as expected. Please see Appendix H5 for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue satisfactorily resolved. The Applicant has provided an explanation for the difference in compensation requirements when calculated by the Applicant versus Natural England according to the H3Pt2 method [REP6-052]. Natural England maintain that it is more appropriate for a natal dispersal rate of 0.77 to be used, however the justification given for the Applicant's approach is reasonable. |  |  |  | Issue satisfactorily resolved. The Applicant has provided an explanation for the difference in compensation requirements when calculated by the Applicant versus Natural England according to the H3Pt2 method [REP6-052]. Natural England maintain that it is more appropriate for a natal dispersal rate of 0.77 to be used, however the justification given for the Applicant's approach is reasonable.
H4 | H4 | Until such time as evidence is provided to support appropriate apportioning rates of kittiwake to offshore colonies for the Dogger Bank South projects, we continue to advise that the colony apportioning method followed in the impact assessment is appropriately precautionary. |  |  |  | The Applicant has confirmed that apportioning rates have not been reduced on the basis of offshore colonies, however offshore colonies are still suggested to be an inherent source of precaution in the apportining of 100% of adult birds to FFC SPA in the KCP. We note that Dogger Bank South is not in as prominent an area for oil and gas infrastructure compared to other projects, and therefore presence of birds from offshore colonies cannot be assumed. | [13 empty] | The Applicant has confirmed that apportioning rates have not been reduced on the basis of offshore colonies, however offshore colonies are still suggested to be an inherent source of precaution in the apportioning of 100% of adult birds to FFC SPA in the KCP. We note that Dogger Bank South is not in as prominent an area for oil and gas infrastructure compared to other projects, and therefore presence of a significant number of birds from offshore colonies cannot be assumed.
H5 | H5 | The impacts currently predicted for the Projects alone make DBS the highest impacting project on FFC SPA kittiwake to date, and would likely result in an adverse effect on site integrity (AEoI) alone. Further consideration needs to be given to reducing the Projects’ impacts, prior to the need for compensation. This could include reducing the overall array size, removing hotspots, concentrating turbines in cold spots, and/or raising the hub height to 40m above HAT. |  |  |  | No change. Natural England continue to advise that further consideration is given to potential mitigation measures to reduce impacts on seabird features. Please see Appendix G2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. The Applicant maintains their position that no additional mitigation is required. Natural England maintain our previous advice. |  | No Change. The Applicant maintains their position that no additional mitigation is required. Natural England maintain our previous advice and have provided further advice in response to ISH Action 7 in Appendix M5 of our Deadline 5 submission. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. The Applicant's Responses to Deadline 5 Documents [REP6-052] confirms that they will not present hotspot modelling as 'any further reductions in the developable area within the lease boundaries would risk making the Projects economically unviable.' Whilst we note this argument, it is not within our field of expertise to comment on. The Applicant also maintains their disagreement with Natural England's previous advice that the Projects are within foraging range of breeding birds at FFC SPA. Natural England maintain our previous advice at Deadline 5 [REP5-060] relating to mitigation. We therefore consider that agreement will not be reached on this matter within Examination. |  | Issue progressed. Natural England welcome the Applicant's provision of some spatial mapping work in [REP7-137], however it is not sufficient to address our concerns. Please see our Deadline 8 cover letter for full details. |  | Issue progressed. Natural England welcome the Applicant's provision of some spatial mapping work in [REP7-137], however it is not sufficient to address our concerns. Please see our Deadline 8 cover letter for full details.
H6 | H6 | The Hornsea 3 (‘New Colony approach’) approach should be used to determine the appropriate scale of compensation required for ANS, as recommended in the KSCP. Further discussion will also be needed on the appropriate compensation ratio and/or means of addressing uncertainty in the level of compensation provided. |  |  |  | Natural England provided further guidance on this matter in Appendix H1 of our Deadline 1 submission [REP1-065]. We welcome that the Applicant has provided values for breeding pairs needed according to both the Hornsea 3 and 4 approaches, however only the Hornsea 4 values have been carried forward to the calculations with ratios applied. We advise that both approaches are carried through for all scale and provision assessments. Please see Appendix H2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change - Please refer to our updated comments on the Hornsea 3 Part 2 approach in Appendix G4. |  | Issue Progressed. We welcome the Applicant's presentation of compensation requirements according to the 'Hornsea 3 part 2' method, and that compensation requirements have been presented for a range of compensation ratios. However, we remain unable to advise on an appropriate specific compensation ratio at this time. Please see Appendix H5 for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. Please see Appendix H6 for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue satisfactorily resolved. Whilst Natural England and the Applicant do not agree on the appropriate approach to use, the Applicant has provided values in line with our advice. This has allowed us to provide our final advice on compensation requirements including consideration of ratios in Appendix H8 of our Deadline 8 submission. |  | Issue satisfactorily resolved. Whilst Natural England and the Applicant do not agree on the appropriate approach to use, the Applicant has provided values in line with our advice. This has allowed us to provide our final advice on compensation requirements including consideration of ratios in Appendix H8 of our Deadline 8 submission.
H7 | H7 | The Applicant has incorrectly stated the upper estimate of nest provision required for DBS East, DBS West and ODOW as 5,000 nesting spaces. We advise that the ‘compensation envelope’ was 5,500 in the published KSCP. We also highlight that this was based on lower impact predictions than have now been submitted. |  |  |  | Issue resolved. Revision 2 of the KCP [PDB-003] has been updated in line with the value published in the KSCP. However, as noted in Revision 3 of the KCP and Appendix H2, given the higher impacts now predicted from the Dogger Bank South projects, at this stage it cannot be assumed that a 'compensation envelope' of 5,500 will be sufficient. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change - no new information relevant to this issue has been submitted at this deadline. Natural England welcome that the Applicant's updated KCP will be submitted at Deadline 4 and will provide comment at Deadline 5. |  | Issue Progressed. Natural England acknowledge the changes made to references to the KSCP compensation envelope; however we reiterate our comments regarding the envelope being based on lower impact figures than the submitted ESs have revealed. Please see our comments in Appendix H5 for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue Progressed. Natural England welcome the updated compensation figures for Round 4, calculated according to Natural England’s advice using the Hornsea Three approach, which are presented in updates to the Project Level Kittiwake Compensation Plan (Revision 6) [REP6-010]. The Applicant should bear in mind that the compensation envelope also needs to accommodate the impacts the other Dogger Bank projects, and did not specifically take into account a reduced lead-in time to 2 years as proposed by both the Applicant and ODOW. |  |  |  | Issue Progressed. Natural England welcome the updated compensation figures for Round 4, calculated according to Natural England’s advice using the Hornsea Three approach, which are presented in updates to the Project Level Kittiwake Compensation Plan (Revision 6) [REP6-010]. The Applicant should bear in mind that the compensation envelope also needs to accommodate the impacts the other Dogger Bank projects, and did not specifically take into account a reduced lead-in time to 2 years as proposed by both the Applicant and ODOW.
H8 | H8 | The compensation totals presented are based on the Applicant’s and ODOW’s preferred approaches to the assessment. We welcome that a compensation ratio greater than 1:1 has been suggested, however a ratio of 2:1 has not been agreed. Compensation totals should be provided in line with SNCB guidance alongside the Applicant’s preferred approach. |  |  |  | No change. See H6. We also advise that the ODOW values are updated to reflect revisions to their assessment. As the ODOW Examination is due to end on 4th April, we consider there is sufficient time for this to be included within the DBS Examination. Please see Appendix H2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change - Natural England welcome that the Applicant's updated KCP will be submitted at Deadline 4 and will provide comment at Deadline 5. Please also see our updated comments on the application of compensation ratios in Appendix G4. |  | No change. Natural England disagree with the figures included for ODOW's compensation requirements. Please see Appendix H5 for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue Largely Resolved. Compensation totals have been included in the KCP [REP6-010] for DBS and ODOW according to NE's advised approach for ratios of 1:1 and 2:1. As the requirements for other ratios can be inferred from this, we consider this issue effectively resolved. |  |  |  | Issue Largely Resolved. Compensation totals have been included in the KCP [REP6-010] for DBS and ODOW according to NE's advised approach for ratios of 1:1 and 2:1. As the requirements for other ratios can be inferred from this, we consider this issue effectively resolved.
H9 | H9 | ANS structures - “up to two” and “maximum capacity” suggest that fewer than two offshore ANS, each with fewer than 2,250 nesting spaces, may be considered. One offshore ANS will likely be insufficient to compensate for the impacts of the projects. We are also concerned that 4,500 nest spaces may not be sufficient to compensate for the combined impacts of the DBS projects and ODOW given the scale of DBS’s impacts. The maximum provision should be revisited following any updated assessments. |  |  |  | No change. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change - no new information relevant to this issue has been submitted at this deadline. Natural England welcome that the Applicant's updated KCP will be submitted at Deadline 4 and will provide comment at Deadline 5. |  | No Change. Natural England acknowledge the changes made to the ANS design and refer to our comments in Appendix H5 for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. Whilst we welcome the Applicant's acknowledgement of Natural England's position on the scale and success of the compensation measure in the KCP [REP6-010], we note that the Applicant has removed their statement that 'the ANS topside design will accommodate the required number of nesting spaces, regardless of the final compensation requirement figure'. We understand from the updates to [REP6-010] and discussions with the Applicant that the current ANS designs are intended to be sufficient to compensate for impacts up to a 2:1 ratio, but were the Secretary of State to seek provision at a higher ratio, this would present challenges. |  |  |  | No Change. Whilst we welcome the Applicant's acknowledgement of Natural England's position on the scale and success of the compensation measure in the KCP [REP6-010], we note that the Applicant has removed their statement that 'the ANS topside design will accommodate the required number of nesting spaces, regardless of the final compensation requirement figure'. We understand from the updates to [REP6-010] and discussions with the Applicant that the current ANS designs are intended to be sufficient to compensate for impacts up to a 2:1 ratio, but were the Secretary of State to seek provision at a higher ratio, this would present challenges.
H10 | H10 | The Applicant’s preferred delivery approach is via a collaborative agreement. We agree that this could be an appropriate route but note that there remains a lack of clarity on how the ANS would be delivered. |  |  |  | Issue progressed. Clarification has been provided that the Applicant and ODOW will each progress one project-led offshore ANS. The two projects are also exploring the potential for nesting space to be shared to present reciprocal resilience across the compensation measure via an MOU, therefore delivering the strategic measure and approach in line with the KSCP, collaboratively through the installation of individual project-led ANS. However, at this stage it remains unclear whether a single ANS will be sufficient for the requirements of the Applicant. Please see Appendix H2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change - no new information relevant to this issue has been submitted at this deadline. Natural England welcome that the Applicant's updated KCP will be submitted at Deadline 4 and will provide comment at Deadline 5. |  | Issue progressed. Natural England welcomes that an MOU has now been signed between the Applicant and ODOW. Nevertheless we remain concerned that, in the event of ODOW not progressing, the provision of a single project-led ANS will significantly increase the risk of insufficient compensation being provided. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change. Natural England remain concerned that in the event of ODOW not progressing, the provision of a single project-led ANS will significantly increase the risk of insufficient compensation being provided. |  | No change. Natural England remain concerned that in the event of ODOW not progressing, the provision of a single project-led ANS will significantly increase the risk of insufficient compensation being provided.
H11 | H11 | Project-led, collaborative and strategic compensation all being progressed in parallel creates uncertainty in what is being secured and can be expected to be delivered. We highlight that the provision of a single offshore ANS with 2,250 capacity is unlikely to be sufficient to compensate for the predicted impacts of DBS, should delivery of collaborative/strategic measures fall through. | [17 empty] | Project-led, collaborative and strategic compensation all being progressed in parallel creates uncertainty in what is being secured and can be expected to be delivered. We highlight that the provision of a single offshore ANS with 2,250 capacity is unlikely to be sufficient to compensate for the predicted impacts of DBS, should delivery of collaborative/strategic measures fall through.
H12 | H12 | Our comments on the shortlist of potential locations for the offshore ANS should be considered in any future refinement of the shortlist. |  |  |  | Issue progressed. Please see Appendix H2 of our Deadline 2 submission for further detail on the shortlist of sites. |  | No Change. Our Deadline 2 advice still remains, please also see our additional advice outlined in Appendix H3 of our Deadline 3 submission. |  | No Change - no new information relevant to this issue has been submitted at this deadline. Natural England welcome that the Applicant's updated KCP will be submitted at Deadline 4 and will provide comment at Deadline 5. |  | No change. Natural England welcome the additional information provided by the Applicant on the site refinement process, however it remains unclear how our previous advice has been considered. We refer to Appendix H5 for further detailed comments. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue Progressed. Natural England welcomes the site selection updates included in the KCP [REP6-010] which demonstrate consideration of our previous advice. We will provide comment on the final site selected within our concluding offshore ornithology advice. |  | Issue satisfactorily resolved. The Applicant has now identified a preferred candidate site for the installation of their project-led ANS (6a). Natural England have expressed concerns regarding the proximity of this site to the area being progressed by ODOW for their project-led ANS, noting the added ecological resilience of having ANS structures in different locations. However we are generally satisfied that the location is appropriate. |  | Issue satisfactorily resolved. The Applicant has now identified a preferred candidate site for the installation of their project-led ANS (6a). Natural England have expressed concerns regarding the proximity of this site to the area being progressed by ODOW for their project-led ANS, noting the added ecological resilience of having ANS structures in different locations. However we are generally satisfied that the location is appropriate.
H13 | H13 | The ANS should be provided at least four breeding seasons before the projects are operational. |  |  |  | No change. We note the Applicant has submitted a document relating to this issue at Deadline 2. We will review this and provide further comment at Deadline 3. |  | No Change. Natural England disagree with the Applicant’s proposed reduction to 2 breeding seasons and maintain our advice provided at Relevant Representations. Please see Appendix H3 of our Deadline 3 submission for further information required to support the proposal. |  | The Applicant has acknowledged our advice [see REP3-028], but has not provided any new information. Natural England maintains our advice provided at Relevant Representations and Deadline 3. |  | No Change. Natural England maintain our previous advice. Please see Appendix H5 for further details. |  | Notwithstanding requests made in our Deadline 4 advice [REP4-125] for further clarity on certain aspects of the modelling methodology in relation to the Applicant's case for a reduced number of breeding seasons, Natural England are in agreement with the Applicant that that there would be little merit in further discussion between our parties on this topic within the remainder of Examination, and that we maintain our respective positions. Please see Appendix H6 for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. The Applicant has outlined in their Response to Deadline 6 Documents [REP7-131] that they maintain their position that the delivery of the offshore Artificial Nesting Structures (ANS) two years in advance of the Projects becoming operational, as opposed to four years as previously advised by Natural England. We maintain our Deadline 6 advice [REP6-076] and therefore consider that agreement will not be reached on this matter within Examination. |  | No Change. The Applicant has outlined in their Response to Deadline 6 Documents [REP7-131] that they maintain their position that the delivery of the offshore Artificial Nesting Structures (ANS) two years in advance of the Projects becoming operational, as opposed to four years as previously advised by Natural England. We maintain our Deadline 6 advice [REP6-076] and therefore consider that agreement will not be reached on this matter within Examination.
H14 | H15 | The potential impacts of ANS implementation within NNSSR SAC should be considered and if this option is to be retained, information to inform an Appropriate Assessment provided. |  |  |  | Issue resolved. The KCP has been updated to remove the area of overlap with NNSSR SAC from consideration, which is welcomed. | [13 empty] | Issue resolved. The KCP has been updated to remove the area of overlap with NNSSR SAC from consideration, which is welcomed.
H15 | H16 | The Applicant should update the predicted impacts of all submitted Offshore Wind Farm applications prior to the end of Examination. |  |  |  | Issue progressed. Whilst updates have been made to the in-combination assessment, further update will likely be needed. See Appendix G2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. |  | No change. |  | Nautral England are satisfied with the updated in-combination assesments provided by the Applicant (see Sheet G, G41). Whilst the DBD PEIR is now in the public domain through a Section 42 consultation, we consider it would not be proportionate to update the in-combination assessment before the close of the Examination. Therefore we advise that when determining DBS windfarms the Secretary of State considers Dogger Bank D in their HRA. |  |  |  | Nautral England are satisfied with the updated in-combination assesments provided by the Applicant (see Sheet G, G41). Whilst the DBD PEIR is now in the public domain through a Section 42 consultation, we consider it would not be proportionate to update the in-combination assessment before the close of the Examination. Therefore we advise that when determining DBS windfarms the Secretary of State considers Dogger Bank D in their HRA.
H16 | H17 | The Applicant has suggested that evidence does not appear to indicate that kittiwake populations in the southern North Sea have been significantly affected by Highly Pathogenic Avian Influenza (HPAI). However, a full colony count of kittiwake numbers at FFC SPA has not been undertaken since the majority of the recent HPAI outbreaks took place. We welcome the Applicant’s comment that ongoing monitoring will provide valuable evidence in this respect. | [17 empty] | The Applicant has suggested that evidence does not appear to indicate that kittiwake populations in the southern North Sea have been significantly affected by Highly Pathogenic Avian Influenza (HPAI). However, a full colony count of kittiwake numbers at FFC SPA has not been undertaken since the majority of the recent HPAI outbreaks took place. We welcome the Applicant’s comment that ongoing monitoring will provide valuable evidence in this respect.
Document Used: [APP-054] 6.2.1.2 Outline Kittiwake Compensation Implementation and Monitoring Plan
H17 | H19 | We recognise the current uncertainty around the implementation of strategic kittiwake compensation and whether the KCIMP is therefore needed, we consider that should confirmation be provided by DESNZ, we would expect a populated KCIMP to be submitted into the Examination. |  |  |  | Following the publication of the Ministerial Statement confirming that offshore ANS should be delivered at a project level, we advise that a populated KCIMP should be submitted into the Examination. |  | No Change. Natural England welcome the Examiner's agreement that a populated KCIMP should be submitted into the Examination at Deadline 4. |  | No Change. Natural England will provide further comment following review of the KCIMP that will be submitted into the Examination at Deadline 4. |  | Issue Resolved. Natural England welcomes the provision of the updated KCIMP, however depending on resolution of other issues, it could be beneficial to provide a further update before the close of the Examination.. Please see Appendix H5 for further details. | [7 empty] | Issue Resolved. Natural England welcomes the provision of the updated KCIMP, however depending on resolution of other issues, it could be beneficial to provide a further update before the close of the Examination.
Guillemot and Razorbill Compensation Document Used: [APP-058] 6.2.2 Appendix 2 Guillemot [and Razorbill] Compensation Plan
H18 | H20 | Provide an in-combination assessment of impacts on guillemot at the Farne Islands SPA and consider the need for compensation for these impacts. |  |  |  | Issue progressed. The Applicant has provided an in-combination assessment for guillemot at the Farne Islands SPA, however, we have outstanding concerns with some aspects of the assessment methodology (see G37). Please refer to Appendix G2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. Natural England welcome that the Applicant's updated assessment will be submitted at Deadline 4 (as stated in their response to the Deadline 2 documents[REP3-028]) and will provide comment at Deadline 5. |  | No Change. Natural England maintain our previous advice that the Applicant include consideration of compensation requirements for guillemot at the Farne Islands SPA. |  | No change. We understand the Applicant is updating the GRCP to include consideration of impacts to guillemot at the Farne Islands SPA. This is welcome and we will provide further comment once it is submitted into Examination. |  | Issue resolved. Impacts to Farne Islands guillemot have been included on a without prejudice basis in the Guillemot and Razorbill Compensation Plan (Revision 6) [REP6-013] and Revision 9 of the DCO [REP6-004] submitted at Deadline 6. |  |  |  | Issue resolved. Impacts to Farne Islands guillemot have been included on a without prejudice basis in the Guillemot and Razorbill Compensation Plan (Revision 6) [REP6-013] submitted at Deadline 6.
H19 | H21 | The most recent count for razorbill at FFC SPA is the 2022 count of 45,780 individuals, which when corrected according to standard methodology gives 61,345 individuals (Clarkson et al 2022). We advise that the GRCP is updated as it currently uses the count from 2017. |  |  |  | Issue resolved. The GRCP has been updated with the most recent count data. | [13 empty] | Issue resolved. The GRCP has been updated with the most recent count data.
H20 | H22 | The GRCP should be updated following any reassessments undertaken in response to the advice provided in Appendix G. Compensation metrics should be presented in line with both the Applicant’s preferred method for calculating impacts and SNCB guidance. |  |  |  | Issue progressed. Significant efforts have been made to provide assessment values in line with SNCB advice and the compensation plans have been updated accordingly. However, due to outstanding concerns with respect to in-combination assessments and PVAs, we remain unable to comment on the conclusions and impact values presented at this time. Please refer to Appendix G2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. Natural England welcome that the Applicant's updated ornithology assessment and an updated Auk Compensation Plan will be submitted at Deadline 4 (as stated in their response to the Deadline 2 documents[REP3-028]) and will provide comment at Deadline 5. |  | Issue Progressed. We welcome the Applicant's updated calculations. However there are currently outstanding queries with the razorbill assessment. Please see Appendix H5 for further details. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue Resolved. Natural England welcome the Applicant's clarification provided in [REP6-052] and the updated calculations for razorbill in the GRCP [REP6-013]. |  |  |  | Issue Resolved. Natural England welcome the Applicant's clarification provided in [REP6-052] and the updated calculations for razorbill in the GRCP [REP6-013].
H21 | H23 | Provide further detail on the methods used to calculate compensation requirements for guillemot and razorbill, and on the rationale behind the choice of method. |  |  |  | No Change. Natural England provided further guidance on this matter in Appendix H1 of our Deadline 1 submission [REP1-065]. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. Natural England have provided further guidance on this matter in Appendix G4 of our Deadline 4 submission. |  | Issue Progressed. We welcome the Applicants updated calculations. However there are currently outstanding queries around how the Applicant came to these values. Please see Appendix H5 for further details. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | Issue Resolved. Natural England welcome the Applicant's clarification provided in [REP6-052] and the updated calculations for razorbill in the GRCP [REP6-013]. |  |  |  | Issue Resolved. Natural England welcome the Applicant's clarification provided in [REP6-052] and the updated calculations for razorbill in the GRCP [REP6-013].
H22 | H24 | Compensation requirements have only been provided for guillemot and razorbill using compensation ratios of 1:1 and 2:1, and only for a limited range of mortality and displacement rates using the Applicant's preferred approach. We cannot advise on an appropriate compensation ratio until further details of the compensation measures are provided, however we note that the predicted requirements already appear substantial and will be challenging to deliver. Further discussion will be needed on the scale of compensation required once the impact assessments have been updated. |  |  |  | No Change. Please refer to Appendix H2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. Natural England maintains our previous advice. Please refer to Appendix G4 for detailed comments. |  | Issue Progressed. Natural England welcome the Applicant including a compensation ratio of 3:1 in [REP4-027] for guillemot and razorbill. However there are errors in the calculations which need to be resolved in order to provide full comments. |  | No change. We understand the Applicant is updating the compensation calculations, which is welcomed. Natural England will provide comments once submitted into Examination. |  | Issue Resolved. Natural England welcome the Applicant's clarification provided in [REP6-052] and the updated calculations for razorbill in the GRCP [REP6-013]. |  |  |  | Issue Resolved. Natural England welcome the Applicant's clarification provided in [REP6-052] and the updated calculations for razorbill in the GRCP [REP6-013].
H23 | H26 | Several locations included have previously been ruled out by other projects (e.g. Hornsea Four). We consider there is a significant risk that all sites on the shortlist will be deemed unsuitable for compensation. Feasibility assessments for the shortlisted sites are needed as a matter of urgency to enable other sites to be explored should these prove unsuitable. |  |  |  | Issue progressed. Natural England provided comment on the Site Refinement Report in our Rule 17 response dated 16th December 2024 [AS-008]. We acknowledge the Applicant has planned further surveys for Q1 2025, and that results will be presented at Deadline 3. Please refer to Appendix H2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Issue progressed. NE welcome the recent survey work undertaken, albeit this indicates Middle Mouse does not support rats. Worm's Head is now the sole project-led site. We advise that the views of NRW on the feasibility of this location are sought. Given the scale of potential impacts the Applicant's auk compensation will be dependent on strategic delivery on the Isles of Scilly, so we welcome the Applicant's engagement with the initiative. Please see Appendix H4 for detailed comments and H24 below. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No change. It has been confirmed in the updated GRCP [REP5-012] that Worms Head is no longer in scope. Natural England retains its concerns about Middle Mouse as rat presence has not yet been confirmed and it is likely too small to compensate for the impacts of the Project alone. The Applicant has begun investigating locations in Scotland for project-led compensation, however progress within Examination timeframes is likely to be limited. Please refer to Appendix H6 for further detail. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | A location for Project-led delivery cannot be considered to be sufficiently in scope or secured at this time. Natural England welcome the Applicant’s inclusion of the Isles of Scilly as a potential site and agree it has considerable potential. A mechanism for the strategic delivery of an Isles of Scilly eradication has yet to be established and secured, although a Task & Finish Group has been set up to progress this. |  | A location for Project-led delivery cannot be considered to be sufficiently in scope or secured at this time. Natural England welcome the Applicant’s inclusion of the Isles of Scilly as a potential site and agree it has considerable potential. A mechanism for the strategic delivery of an Isles of Scilly eradication has yet to be established and secured, although a Task & Finish Group has been set up to progress this.
H24 | H28 | Feasibility assessments for the shortlisted sites are needed as a matter of urgency to confirm the presence of predators and suitable auk nesting habitat and to determine the scale of compensation that could be achieved. |  |  |  | Issue progressed. Natural England provided comment on the Site Refinement Report in our Rule 17 response dated 16th December 2024 [AS-008]. We acknowledge the Applicant has planned further surveys for Q1 2025, and that results will be presented at Deadline 3. Please refer to Appendix H2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | Issue Progressed. The recent survey work undertaken has confirmed rat presence at Worm's Head, however further surveys are needed to confirm rats can access areas utilised by guillemot and that physical implementation of the measure is achieveable. The advice of NRW regarding the feasibility of measures at this site should be sought. We also have some outstanding concerns regarding how the scale of compensation has been calculated. Please refer to Appendix H4 for detailed comments. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No change. See H23. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | A location for Project-led delivery cannot be considered to be sufficiently in scope or secured at this time. Natural England welcome the Applicant’s inclusion of the Isles of Scilly as a potential site and agree it has considerable potential. A mechanism for the strategic delivery of an Isles of Scilly eradication has yet to be established and secured, although a Task & Finish Group has been set up to progress this. |  | A location for Project-led delivery cannot be considered to be sufficiently in scope or secured at this time. Natural England welcome the Applicant’s inclusion of the Isles of Scilly as a potential site and agree it has considerable potential. A mechanism for the strategic delivery of an Isles of Scilly eradication has yet to be established and secured, although a Task & Finish Group has been set up to progress this.
H25 | H29 | Consideration should be given to connectivity of the predator eradication/control locations with guillemot and razorbill populations of the impacted SPA when refining the shortlisted sites. Given connectivity is likely to be low at best, an assessment of connectivity with the national site network for these species should also be presented. |  |  |  | Issue Progressed. A connectivity assessment has been provided in Revision 3 of the GRCP. Whilst it will be limited, there is potential for some connectivity with the National Site Network. Please refer to Appendix H2 for further detail. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | While guillemot and razorbill do not currently occur in numbers to meet either of the criteria to be included as named assemblage components in the Isles of Scilly SPA seabird assemblage, they nevertheless form part of the SPA’s seabird assemblage and contribute to its abundance and diversity. As such, any additional breeding guillemot and razorbill on the Isles of Scilly that arise as part of the strategic approach will directly benefit the National Site Network and fall under the protective provisions of the Habitats Regulations. |  | While guillemot and razorbill do not currently occur in numbers to meet either of the criteria to be included as named assemblage components in the Isles of Scilly SPA seabird assemblage, they nevertheless form part of the SPA’s seabird assemblage and contribute to its abundance and diversity. As such, any additional breeding guillemot and razorbill on the Isles of Scilly that arise as part of the strategic approach will directly benefit the National Site Network and fall under the protective provisions of the Habitats Regulations.
H26 | H30 | Beginning eradication prior to the first turbine being installed - eradication may take longer than the two years allocated, and the compensation will not be delivering until the required number of chicks are being produced and have reached age of first breeding (i.e. recruited into the breeding population). We do not consider implementation before impact to be analogous to delivering compensation before impact. |  |  |  | No Change. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change - no new information relevant to this issue has been submitted at this deadline. |  | No Change. Natural England maintains our previous advice. |  | No change. Natural England maintains our previous advice. |  | The Applicant's Responses to Deadline 5 Documents [REP6-052] states that they maintain their intent to implement predator eradication two years in advance of turbine installation. Natural England maintain our concerns that it may take longer than two years to complete an eradication and that implementation before impact is not analogous to delivering compensation before impact. |  |  |  | The Applicant's Responses to Deadline 5 Documents [REP6-052] states that they maintain their intent to implement predator eradication two years in advance of turbine installation. Natural England maintains our concerns that it may take longer than two years to complete an eradication and that implementation before impact is not analogous to delivering compensation before impact.
H27 | H31 | There remains a significant amount of work to be done before a location or locations can be selected, and we would have expected much of this to have been done prior to the point of application, as has been done on other projects.
H28 | H32 | We agree that exploring the potential of ANS provision as a compensatory measure for guillemot and razorbill has potential as adaptive management should monitoring prove it to be effective.
H29 | H33 | We welcome commitment to implementing bycatch reduction measures as a compensatory measure if “robust evidence demonstrating the effectiveness of techniques to reduce the bycatch of auks became available.” If and when this is available, this may be a suitable adaptive management measure.
Document Used: [APP-057] 6.2.2.1. Outline Guillemot and Razorbill Compensation Implementation and Monitoring Plan
H30 | H35 | A more detailed GRCIMP should be provided as soon as possible within the Examination process. |  |  |  | Following the publication of the Ministerial Statement confirming that predator eradication should be progressed initially at a project level, we advise that a populated CIMP should be submitted into the Examination. |  | No Change. Natural England welcome the Examiner's agreement that a populated KCIMP should be submitted into the Examination at Deadline 4. |  | No Change. Natural England will provide further comment following review of the GRCIMP that will be submitted into the Examination at Deadline 4. |  | Issue progressed. Natural England welcome the provision of additional detail in the Outline GRCIMP [REP4-027], particularly the inclusion of seabird monitoring . However, we note that the Applicant has yet to identify a suitable site or eradication plan. |  | No change - no new information relevant to this issue has been submitted at this deadline. |  | No change - no new information relevant to this issue has been submitted at this deadline. The Applicant's Responses to Deadline 5 Documents [REP6-052] directs Natural England to the Guillemot [and Razorbill] Compensation Plan (Revision 6) [REP6-013], however this does not include any updates to the Outline GRCIMP [REP4-027] submitted at Deadline 4. |  | Please see Appendix H8 of Natural England's Deadline 8 submission for final comments on the GCRIMP. |  | Please see Appendix H8 of Natural England's Deadline 8 submission for final comments on the GCRIMP.

## I - Terrestrial Ecology & Orni
Point | Point Number(s) from Appendix I [RR-039] | Taken from Natural England’s Relevant and Written Representations Dogger Bank South (East and West) Appendix I - Terrestrial Ecology and Ornithology | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Deadline 1 | Consultation, actions, progression | RAG Deadline 2 | Consultation, actions, progression | RAG Deadline 3 | Consultation, actions, progression | RAG Deadline 4 | Consultation, actions, progression | RAG Deadline 5 | Consultation, actions, progression | RAG Deadline 6 | Consultation, actions, progression | RAG Deadline 7 | End of Examination Position | Issue Resolved
I1 | I6, I13 | We advise that the air quality modelling undertaken for assessing impacts from construction traffic be tested against Natural England’s thresholds, as detailed in the guidance document NEA001. We have engaged with the Applicant regarding this approach and understand that the Applicant will be updating the assessment following advice provided through our Discretionary Advice Service (DAS). (7.26) |  | Issue resolved. See Appendix I1 of Natural England's Deadline 1 submission for further detail. | [13 empty] | Issue resolved. See Appendix I1 of Natural England's Deadline 1 submission for further detail.
I2 | I7, I13 | We advise that potential alternate routes that could be taken by vessels plus size of the vessels is provided - this could be detailed via an outline Port Management Plan. If the operational port is in the Humber Estuary SAC/SPA, provision of a Port Management Plan should be secured in the DCO to be submitted pre construc)tion, taking into account air quality impacts and vessel management. (7.26 |  | Issue resolved. See Appendix I1 of Natural England's Deadline 1 submission for further detail. | [13 empty] | Issue resolved. See Appendix I1 of Natural England's Deadline 1 submission for further detail.
I3 | I9, I13 | The outline Code of Construction Practice should be updated to include separation buffers for the use of back-up generators. (7.26) |  | Issue resolved. See Appendix I1 of Natural England's Deadline 1 submission for further detail. | [13 empty] | Issue resolved. See Appendix I1 of Natural England's Deadline 1 submission for further detail.
I4 | I17 | Consideration should be given to further survey of 'dry' ponds to determine if they have permanently dried out or if it was an occasional drying event and whether great crested newt (GCN) are present. (7.18) |  | Issue resolved. See Appendix I1 of Natural England's Deadline 1 submission for further detail. | [13 empty] | Issue resolved. See Appendix I1 of Natural England's Deadline 1 submission for further detail.
I5 | I19 | We advise: - Supervision measures relevant to soil management and handling of soils should be held by competent soil specialist and secured in the OLEM. - Soil surveyors should be named with a list of qualifications and experience on the Agricultural Land Classification (ALC) survey submitted as part of the DCO. - Soil handling methods should normally be as specified as in the Defra Construction Code of Practice for the Sustainable Use of Soils on Construction Sites - A commitment for best and most versatile (BMV) agricultural temporality required for the development to be returned to its original ALC grade - Clarification on the frequency of inspections to be undertaken to ensure soil is being managed in line with the detailed Soil Management Plan. - Production of the final SMP should be secured within the DCO wording. - The outline SMP should be updated with the recommendations listed here as needed. (7.21) |  | Issue resolved. See Appendix I1 of Natural England's Deadline 1 submission for further detail. | [13 empty] | Issue resolved. See Appendix I1 of Natural England's Deadline 1 submission for further detail.