## Title page
THE PLANNING ACT 2008
THE INFRASTRUCTURE PLANNING (EXAMINATION PROCEDURE) RULES
2010
Natural England's Risk and Issues Log - Deadline 2.
For:
The construction and operation of the Outer Dowsing Offshore Wind Farm located approximately 54km from the Lincolnshire Coast in the Southern North Sea.
Planning Inspectorate Reference EN010130
27th November 2024

## How to read Risks and Issue
Natural England has created this Risk and Issues Log to track progress of issues through the Outer Dowsing Offshore Windfarm (ODOW) examination process. The Risks and Issues Log will be submitted alongside aour written representations at each deadline and marks issues with a colour from our RAG scale depending on the level of significance of the issue. All red, amber and purple issues from our Relelvant and Written Representation are included (collated where appropriate). Green and yellow issues are included if/where relevant. It should be noted that the colour scale is likely to be different from that used in any Statement of Common Ground provided by The Applicant. The Risk and Issues Log is split into multiple tabs in line with the Appendices of our Relevant Representations submission. A - DCO DML B - Marine & Coastal Processes C- Benthic & Intertidal Ecology D - Benthic Compensation E - Marine Mammals F - Offshore & Intertidal Ornithology G - Offshore Ornithology Compensation H - Onshore Ecology I - Onshore Ornithology The issues are based upon our relevant and written representatios [RR-045] and each update will reflect our position following a review of docments submitted into examination. Please note these follow the order of issues is as presented in our detailed comments in Table 2 [RR-045]. Where issues are identified across several dovcuments, these are amalgamted to avoid repetition , with reference to the summary point from Table 1 [RR-045] where applicable. Any issues added to the log during Examination (not included in Relevant Reps) are highlighted in Red and then coded according to RAG status.
Purple Note for Examiners and/or competent authority. May relate to DCO/DML
Red Natural England considers that unless these issues are resolved it will have to advise that (in relation to any one of them, and as appropriate) it is not possible to ascertain beyond reasonable scientific doubt that the project will not affect the integrity of an SAC/SPA/Ramsar and/or significantly hinder the conservation objectives of an MCZ and/or damage or destroy the interest features of a SSSI and/or comply fully with the Environmental Impact Assessment requirements.
Addressing these concerns may require the following:
new baseline or survey data; and/or
significant revisions to baseline characterisation and/or impact modelling and/or
significant design changes; and/or
significant mitigation
In addition, Natural England may use this category to highlight where there is a significant risk that an issue will not be sufficiently addressed within the Examination timescales. Consequently, issues that start out as Amber may progress to Red in the latter stages of the examination.
Amber Natural England does not agree with the applicant’s position or approach and consider that this could make a material difference to the outcome of the decision-making process for this project.
Natural England considers that these matters may be resolved through:
provision of additional evidence or justification to support conclusions; and/or
revisions to impact assessment methodology and/or assessment conclusions; and/or
minor to moderate revisions to impact modelling; and/or
well-designed mitigation measures that are adequately secured through the draft DCO/dML and/or
amendments to draft plans
If these issues are not addressed or are unlikely to be resolved by the end of the Examination, then they may become a Red risk as set out above.
Yellow Natural England doesn’t agree with the Applicant’s position or approach. We would ideally have liked this to be addressed but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process and would not expect these matters to be a ongoing focus of the examination. However, we reserve the right to revise our opinion should further evidence be presented.
It should be noted by interested parties that just because these issues/comments are not raised as significant concerns in this instance, it should not be understood or inferred that Natural England would be of the same view in other cases or circumstances.
Once a Risk or Issue has been categorised as yellow, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be greyed out at subsequent deadlines in order to rationalise the risk and issues log.
Green Natural England is in broad agreement with the Applicant’s approach and has no significant outstanding concerns. As above, we reserve the right to revise our opinion should new evidence be presented. Once a Risk or Issue has been categorised as green, Natural England will not make further comment on the matter at subsequent deadlines, unless specifically requested to through ExA Questions. These rows will then be greyed at subsequent deadlines in order to rationalise the risk and issues log.

## PADSS
Natural England's Principal Areas of Disagreement Summary Statement (PADSS) Deadline 1
Ref | The principal issue in question | The brief concern held by Natural England reported on in full in Written Representations | What needs to change, or be included or amended to overcome the disagreement? | Likelihood of the concern being addressed during Examination | Rel Rep RAG Status | Update on Progression at Deadline 1 | RAG Status D1 | Update on Progression at Deadline 2 | RAG Status D2
Marine Physical Processes and Benthic Ecology
NE1 | Sabellaria spinulosa baseline data | Natural England has concerns with the sufficiency of the data in order to draw conclusions, with any confidence, as to the presence, extent and quality of Annex I biogenic reef (Sabellaria spinulosa). | Natural England advises the Applicant re-examines the existing data, analytical approach and methods which have been used to provide a baseline of the extent and distribution of Annex I Sabellaria spinulosa reef. | Uncertain |  | Progressed. Please see our Deadline 1 Appendix C1 and R&I Log Tab C. The Applicant's clarifications should be incorporated within the technical report to ensure these can be relied upon post consent. Our position regarding supporting reef habitat will be provided at D2. |  | No Change
NE2 | Nearshore (depth of closure) area - cable protection | Natural England is unable to rule out impacts to The Wash and North Norfolk Coast SAC, The Wash SPA, The Wash Ramsar and The Wash SSSI. This is due to potential disruption of wave energy transmission, nearshore sediment pathways, and coastal morphology, due to the presence of cable protection within the shallow nearshore zone perpendicular to longshore sediment transport. | Natural England advises that cable protection should be avoided in shallow nearshore areas. We advise the Applicant should clarify the Maximum Design Scenario (MDS) for cable protection within shallow nearshore water and revisit their impact assessment conclusions. | Uncertain |  | Progressed. Please see our Deadline 1 Appendix B1 and R&I Log Tab B. Concerns remain in relation to feasibilty of Applicant's proposal to address our concern |  | Progressed. But further information required re proposed mitigation measures
NE3 | Inner Dowsing Race Bank North Ridge (IDRBNR) SAC Site Integrity: Annex I Sandbank | There will likely be an AEoI to the IDRBNR Annex I ‘Sandbanks which are slightly covered by sea water all the time’ feature from the lasting habitat loss/change due to the placement of cable protection within IDRBR. | Natural England advises the Applicant revisits the assumptions and assessment conclusions made. The Applicant must demonstrate the mitigation hierarchy has been fully explored to demonstrate that impacts are minimised. | Uncertain |  | Progressed. Please see our Deadline 1 Appendix C1 and R&I Tab C. The Applicant has committed to removeable rock protection across the Annex I Sandbank feature of the SAC, but that doesn't removed AEOI. |  | No Change
NE4 | IDRBNR SAC Site Integrity: Annex I ‘reefs’ (Sabellaria spinulosa) | Natural England is unable to advise that an AEoI for Annex I Sabellaria spinulosa reef interest feature can be ruled out due to habitat (and supporting habitat) loss/change from any placement of cable protection and disturbance during installation. There is an insufficient level of confidence in the baseline data to inform our advice. | Natural England advises the assumptions made by the Applicant to draw the conclusion of no AEoI on Annex I Sabellaria spinulosa reef features within IDRBNR are not scientifically robust and require revisiting in order that inconsistencies and contradictions between the evidence and conclusions presented are resolved. | Unlikely There is no guarantee this issue will be resolved within the examination timeframe. |  | No change. See Appendix C1 and R&I Tab C. Our position regarding supporting reef habitat will be provided at D2. |  | No Change:
NE5 | The Crown Estate Agreement for Lease | Natural England queries how the project will comply with the Export Cable Region Assessments that inform their seabed lease with The Crown Estate, given the identified AEoI. | We suggest that feedback is sought through the examination process from The Crown Estate who are obligated to ensure the outcomes of the Round 4 plan level HRA are upheld. | Unlikely |  | No change. |  | No Change
NE6 | “Without Prejudice” Benthic Compensation | Natural England cannot support the following proposed “Without Prejudice” Compensation Measures: • Alternative measures for Annex I sandbanks and Reef • Creation of Annex I reef as compensation for Annex I Sandbank Habitat • Anthropogenic Pressure Removal: Marine Debris and Awareness Campaign | Natural England believes that these approaches would not offset the predicted impacts on an interest feature and/or there is currently no delivery mechanism | Unlikely |  | No change. |  | No Change
NE7 | “Without Prejudice” Benthic Compensation | For all remaining “Without Prejudice” benthic compensation proposals not mentioned above, Natural England can see merit in their objectives. However, further progress is required on each measure to have confidence that they are achievable and would deliver effective compensation for project impacts. | Natural England advises that further work on each measure will be required during examination before we can advise on the suitability. | Uncertain Further review is likely to be undertaken during examination and with no guarantee this issue will be resolved within the examination timeframe. |  | No change. |  | No Change
Marine Mammals
NE8 | Southern North Sea SAC: effectiveness of the Site Integrity Plan (SIP) process and | Natural England is concerned that the SIP process is being exclusively relied on to address in-combination noise levels from multiple projects on SAC harbour porpoise in the post-consent phase and that no commitment has been made to the use of NAS. | To provide greater confidence that in-combination noise levels can be kept below the thresholds, the Applicant should commit to the use of Noise Abatement Systems now rather than rely on the SIP to address impacts on the SAC in the post-consent phase. This should be secured at the earliest opportunity. | Unlikely |  | No Change. |  | No Change
NE9 | Commitment to use of Noise Abatement Systems (NAS). | New issue at Deadline 1 Natural England is concerned that no commitment has been made by the Applicant to the use of NAS to reduce the impact of noise on marine mammals. | The Applicant should commit to the use of NAS as mitigation now rather than continuing to only consider it as a potential mitigation measure in the SIP post-consent. |  |  | Likely This is subject to the Applicant making a commitment to the use of NAS as mitigation. |  | No Change
Offshore Ornithology
NE10 | Assessment Methodologies | We disagree with the methods used to calculate and describe the impacts to seabird species. In particular we have significant concerns over: Apportioning of individuals to SPAs; Bioseasons and their definitions; Proportion of birds assessed as adults; Baseline Mortality Calculations; Calculations for scale of compensation required. | We have provided advice to the developer via the Section 42 consultation response, expert topic groups and a workshop held in January 2024 recommending approaches to take regarding these issues. The presented approaches departs from Natural England’s (SNCB) standard advice. The issue can be addressed. We advise the Applicant applies our advice and presents assessments in line with this to. | Likely This is subject to the Applicant presenting assessments that are in line with SNCB advice. |  | Please see our advice in Appendix F1 and R&I Tab F. Corrections to errors and inconsistencies have been made in [AS1-064] and Natural England's approach has followed through to the ORBA documentation. However some concerns remain and our advice will be updated to detail these at Deadline 2. Issue resolution is subject to clarification of the status of the ORBA within the Examination and requested updates to the original ES documentation for offshore ornithology, including the RIAA. |  | No change - please see Appendix K1 to our response to the Examiners Questions for a detailed assessment of methodological concerns. Our advice on the ORBA assessment will be provided in the event of the ORBA change request being accepted.
NE11 | Impacts on and proposed compensation for Flamborough and Filey Coast Special Protection Area (FFC SPA) Guillemot and Razorbill | Guillemot and Razorbill It is likely that NE will be unable to rule out an Adverse Effect on Integrity on FFC SPA Guillemot and Razorbill. High numbers of Auks will be impacted by the development. The departure from SNCB advice has led to attempts to apparently reduce the impacts, as presented. We welcome the Applicant’s approach to providing the 3 compensation measures relating to Auk species. There is a lack of clarity concerning mitigation for Auks. It is not clear how robustly Auks were factored in when designing the reduction of the array area and whether further reduction could be undertaken to reduce impacts. . | Guillemot and Razorbill We stress that the Applicant should present assessments undertaken in line with the SNCB advice and present the outputs of these, shifting focus from attempting to reduce impacted numbers. The proposed compensation measures will require substantial work to improve evidence and demonstrate viability and efficacy in order to demonstrate that the proposed measures can be secured and will prove to be ecologically robust. Further reduction fo the array area should be considered to reduce impacts to Auk species. | Unlikely There is no guarantee this issue will be resolved within the examination timeframe. |  | Natural England will provide further update at Deadline 2. |  | No change - see NE 10 above. No further material presented regarding compensatory measures.
NE12 | Impacts on and proposed compensation for Flamborough and Filey Coast Special Protection Area (FFC SPA) Kittiwake | We cannot yet agree on conclusions made with regards to the level of impact upon Kittiwake, based upon the Applicant's departure from the SNCB advised approach. | The Applicant should present assessments based on the SNCB guidance and propose compensation at a suitable ratio for an agreed impact value based on SNCB advice. | Likely Subject to the Applicant presenting assessment in line with SNCB advice and basing compensation upon agreed outputs. |  | Natural England will provide further update at Deadline 2. |  | No change - see NE 10 above. No further material presented regarding compensatory measures.
NE13 | Impacts on Greater Wash SPA: Red throated diver | We have significant ongoing concerns regarding the impacts to red throated diver resulting from disturbance and displacement as a result of the construction and operation of the development within the Greater Wash SPA. This includes the proposed location of the Offshore Reactive Compensation Platform within the SPA. | The Applicant should ensure that assessments are undertaken in line with SNCB guidance and present the impacts accordingly. The Applicant should make efforts to further mitigate against these impacts. | Unlikely There is no guarantee this issue will be resolved within the examination timeframe. |  | Natural England will provide further update at Deadline 2. |  | No change - we understand further information will be provided by the Applicant in due course.
Onshore Ecology
NE14 | The Wash SPA and Ramsar Site Integrity: Overwintering Annex I bird features | Until two years of baseline onshore ornithology data are considered within both the Environmental impact Assessment (EIA) and the Report to Inform the Appropriate Assessment (RIAA), Natural England cannot draw any conclusions on the proposed impacts to overwintering bird species, including the suitability of any mitigation measures to designated species of the Wash SPA and Ramsar using functionally linked land (FLL). | Natural England advises the Applicant submits an amended EIA and RIAA presenting their conclusions based on the completed two years of baseline data. We advise an Outline Annex I species mitigation management plan for designated features of the SPA is submitted into examination and agreed as part of the consent. | Likely |  | Progressed. Natural England has reviewed the year 2 data, however our concerns remain. Please see our advice in Appendix I1 and Tab I. |  | No change
NE15 | Horizontal Direction Drilling (HDD) at landfall | The landfall location at Anderby Creek, just North of Wolla Bank SSSI, has already experienced unforeseen complications and impacts from horizontal directional drilling operations during the Triton Knoll windfarm installation. | Natural England advises a more detailed plan of landfall construction methodology should be defined and submitted into examination. | Likely |  | No change. |  | No change
NE16 | Sea Bank Clay Pits SSSI | Sea Bank Clay Pits SSSI is designated for hydrological features which may be susceptible to changes in the water table. | We advise that the Applicant should provide details of mitigation measures within a named plan, which is secured within the DCO. | Likely |  | Progressed. Please see our Deadline 1 Appendix H1 and R&I Tab H. The Water Quality Management and Mitigation Plan (WQMMP) within the CoCP [PD1-039] commits to mitigation and monitoring at Sea Bank Clay Pits SSSI. However, outline measures should be presented at the cosenting phase to demonstrate feasibilty and effectiveness of potential mitigation measures. |  | No change
NE17 | Soils and Best and Most Versatile Land | Natural England has concerns that without detailed site specific soil data and Agricultural Land Classification (ALC) classification, the project is unable to show how it avoids impacting best most versatile (BMV) land. | We advise the EIA is updated to present further site specific information on detailed and semi-detailed ALC and soil function surveys. This site-specific detail informed through a site survey is required to assist the decision maker to reach a decision and apply the National Policy Statement for Renewable Energy Infrastructure (EN-3). | Uncertain Until Natural England as seen the updated information, we are unable to finalise our position. |  | No change. Please see our Deadline 1 Appendix H2 and R&I Tab H |  | No change
NE18 | Protected Species Mitigation Licence | The Applicant has yet to seek Letters of No Impediment from the Natural England Wildlife Licencing Services (NEWLS) team for a draft protected species mitigation licence for Greater Crested Newt (GCN), Water Vole, Bats, Badger and Otter. | Natural England is unable to provide a position on the likelihood of a licence being granted without having reviewed a draft licence application. It should also be noted that Natural England is unable to comment on the need for a licence, this responsibility falls to the developer. | Uncertain Review is likely to be undertaken during examination. Should a species licence be submitted, there is no guarantee any issues arising will be resolved within the examination timeframe. |  | Progressed. Letters of No Impediment have been provided by NEWLS for GCN and water vole. Natural England advises the Applicant to seek engagement regarding licences for badger and otter. Further advice regarding mitigation for bats is provided in Appendix H1 and R&I tab H. |  | No change
DCO/DML
NE19 | Marine Recovery Fund | Natural England has concerned the compensation conditions related to the use of the Marine Recovery Fund or other third-party compensation options, are not sufficient to appropriately secure compensation and revision is needed. | Natural England advises the DCO compensation conditions are amended to make it clear what will be required when opting for a third-party option, making sure to address the need for monitoring and adaptive management measures. | Likely |  | No change |  | No change
NE20 | Compensation Schedules | The compensation schedules timing requirements are not sufficient. For Kittiwake they include three full breeding seasons and not four. For all other compensation plans they do not secure that the compensation will be in place and functioning prior to impact. | Natural England advises the DCO is amended to make it clear that compensation must be in place and functioning prior to operation. | Uncertain |  | No change |  | No change

## A - DCO DML
Risk & Issue's Ref/Point | Ref from Appendix A [RR-045] | Taken from Natural England’s Relevant and Written Representations ODOW Appendix A - Development Consent Order, Deemed Marine Licences and related certified documentation [RR-045] | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Status D1 | Consultation, actions, progression | RAG Status D2 | Consultation, actions, progression | RAG Status D3 | Consultation, actions, progression | RAG Status D4 | Consultation, actions, progression | RAG Status D5 | Consultation, actions, progression | RAG Status D6
1 | A4 | 3.1 -Sched. 10, Pt 2, Cond. 13(1) (a), Pg. 124. The definition of maintain does not link to the limits of maintenance as described in the ES or to the outline Operations and Maintenance Plan. Linking to the limits of maintenance will provide clarity that only activities assessed within the ES are covered by the definition of maintenance. |  | No change. A DCO update will be provided at Deadline 2. |  | No change.
2 | A5 | 3.1 - Sched 1 Part 3 Requirement 18 Code of Construction Practice. Consider inclusion of a plan to monitor the Sea Bank Clay SSSI in the event of dewater within requirement 18. And ensure that all environmental mitigation measures are appropriately secured. |  | No change. A DCO update will be provided at Deadline 2. |  | No change.
3 | A6 | 3.1 - Sched. 10, Pt 2, Cond. 13(1) (a), Pg. 124. Natural England notes that the relevant Statutory Nature Conservation Body (SNCB) is not listed as a body that will be consulted by the Marine Management Organisation (MMO) on this document. Consider amendment to make it explicit that the relevant SNCB will be consulted. |  | No change. A DCO update will be provided at Deadline 2. |  | Condition has been appropriately updated, SNCB consultation has been secured. Resolved.
4 | A7 | 3.1 - Sched. 10, Pt. 2, Cond. 14(2) Pg. 127. A period of four months is insufficient to approve some documentation. The condition should be amended to a 6 month approval period. For the Sheringham and Dudgeon Extension Project, a 6-month period was agreed for some conditions. |  | No change. A DCO update will be provided at Deadline 2. |  | No change.
5 | A8 | 3.1 - Sched. 10 and 11 Condition 19 Pg. 129. The Applicant should include and secure within the ODOW DCO/DML wording in accordance with the SADEP DCO which contains a clause requiring adaptive management /remediation measures to be implemented, and further consultation with relevant bodies is required to inform agreement/discharge. |  | No change. A DCO update will be provided at Deadline 2. |  | No change.
6 | A9 | 3.1 - Sched. 10 Part 2 Condition 21. This condition prohibits the deployment of cable protection 10 years after the completion of construction. This condition should be amended to secure that no cable protection will be deployed within the designated site after the construction works within the designated site have completed. Please see agreement drawn to this effect for SADEP in regards to inside and outside of Cromer Shoal Chalk Beds MCZ. |  | No change. A DCO update will be provided at Deadline 2. |  | No change.
7 | A10 | All comments raised on Schedule 10 apply to Schedule 11, 12, 13, 14, 15 and 16 where similar provisions exist. For brevity Natural England will not repeat these comments. |  | No change. A DCO update will be provided at Deadline 2. |  | N/A comment for information
8 | A11 | 3.1 Schedule 16. Until further evidence is provided to refine down the 17 areas of search to 1 or maybe 2 locations the potential impacts on Annex I features within the SAC and/or the conservation objectives for the site can’t be assessed. Therefore, at this time we are unable to support the inclusion of Schedule 16. |  | No change. A DCO update will be provided at Deadline 2. |  | No change.
9 | A12 | 3.1 -Sched. 16, Pg. 202 Some of the 17 potential Annex I compensation areas of search are located where The Crown Estate has recently issued seabed lease areas to the Aggregates Industry. We acknowledge that the issue of marine spatial prioritisation is a wider seabed issue than for just this project, and we will continue to work with relevant interested parties to address this and update the Examination accordingly. |  | No change. A DCO update will be provided at Deadline 2. |  | No change.
10 | A13 | 3.1 -Sched. 11, Pt. 2, Cond .22, Pg 130. The condition should require the Site Integrity Plan (SIP) no sooner than 9 months and no later than 6 months prior to commencement of piling |  | No change. A DCO update will be provided at Deadline 2. |  | No change.
11 | A14 & A1 | 3.1 -Sched. 22 Pt. 1 Cond. 4(b), Pt. 2 Cond. 4(d), Pt. 3 Cond. 4(d), Pt. 4 Cond. 4(h), Pt. 5 Cond 4(e) Marine Recovery Fund compensation conditions should be amended to make it clear what will be required when opting for a third-party option, making sure to address the need for monitoring and adaptive management measures to appropriately secure compensation. Natural England has some preferred wording to cover requirements for use of the Marine Recovery Fund. |  | No change. A DCO update will be provided at Deadline 2. |  | No change.
12 | A15 & A3 | 3.1. -Sched. 22 Pt. 1 Cond. 4(c) & (d), Pt. 2 Cond. 4(e) & (f),Pt. 3 Cond. 4(e) & (f), Pt. 4 Cond. 4(i) & (j), Pt. 5 Cond. 4(f) & (g). Conditions enabling third party delivery do not include provisions for monitoring or for adaptive management should the compensatory measures not be effective. Natural England suggests these sections require review and amendment to make it clear exactly what will occur should the developer decide to use third party compensation. |  | No change. A DCO update will be provided at Deadline 2. |  | No change.
13 | A16 & A2 | 3.1 – Sched. 22 Pt. 1 Cond. 5. Amend the condition to reflect four full breeding seasons for kittiwake in line with compensation requirements for other projects and check the parts securing compensatory measures for other designated features (Sched. 22, Pts.2-5). The amendment should be made to ensure compensation is delivered and is sufficiently functioning prior to impact occurring. However, the wording of compensation requirements may change as discussions on the measures progress. |  | No change. A DCO update will be provided at Deadline 2. |  | No change.
14 | A17 | 3.1 –12. A requirement should be included within the DCO to secure a commitment for an Outline Annex I bird species mitigation plan with the level of detail required securing provisions relating to the geographical definition of the mitigation scheme; a timeframe for the approval process; details of pre-construction surveys and mitigation. The outline mitigation should be agreed with Natural England as part of the consenting process. |  | No change. A DCO update will be provided at Deadline 2. |  | No change.

## B - Marine & Coastal Processes
Point | Ref from Appendix B [RR-045] | Taken from Natural England’s Relevant and Written Representations ODOW Appendix B - Marine Physical Processes [ RR-045] | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Status D1 | Consultation, actions, progression | RAG Status D2 | Consultation, actions, progression | RAG Status D3 | Consultation, actions, progression | RAG Status D4 | Consultation, actions, progression | RAG Status D5 | Consultation, actions, progression | RAG Status D6
1 | B7 | O&M activity in relation to project cable repair and reburial is not well defined. Details of O&M activity should be further considered within [APP-058] 6.1.3 Chapter 3 Project Description. |  | No change. The realistic WCS presented in [APP-275] for cable remedial burial and repairs do not appear to have been assessed for impacts to affected marine physical process/environment receptors. |  | No change.
2 | B8 | There is uncertainty regarding the Maximum Design Scenario (MDS) scour volumes presented. The Applicant should clarify the results of the scour assessment presented for the WTG foundations. The WCS should also be revisited. |  | Issue resolved. See our advice in Appendix B1.
3 | B9 | Further clarification is required from the Applicant on the WCS parameters for spoil mounds due to sandwave clearance and seabed levelling and where appropriate update the impact assessment. |  | Issue Resolved. The Applicant has confirmed that an updated assessment of spoil mounds was carried out based on the revised Maximum Design Scenario (MDS) parameters and used to inform the assessment presented in the ES [APP-062].
4 | B10 & B1 | The MDS for increases in Suspended Sediment Concentration (SSC) and consequential changes to seabed level does not consider boulder clearance, pre-lay grapnel run or Unexploded Ordnance (UXO) clearance. The Applicant should consider and assess the MDS for all construction-related activities that may alter SSCs and seabed level. |  | No Change |  | No change. Clarification needed on the MDS seabed disturbance parameters for boulder clearance, pre-lay grapnel run and UXO clearance.
5 | B11 & B6 | Natural England advises that the MDS parameters for cable protection measures within shallow nearshore waters should be more clearly defined and assessed accordingly. |  | Issue Progressed. Please see our Deadline 1 Appendix B1 response. |  | Our advice remains unchanged since Deadline 1.
6 | B12 & B5 | Clarify within the OSCMP [APP-295] the MDS as fully detailed in Table 6.18 of [APP-058] for cable protection within the IDRBNR SAC in terms of specific locations, length, seabed footprint, and volume both during construction and over the lifetime of the project. The Applicant should include reference to other projects within their WCS justification. |  | No change. |  | No change.
7 | B13 | The Applicant should committ to collecting full bathymetric survey data prior to construction to inform the assessment of bedform migration directions to inform scour potential assessment (and thus detailed engineering and project design), to ensure that the ES predictions remain fit for purpose and where they are not adopt the mitigation hierarchy to reduce impacts. |  | No change. |  | No change.
8 | B14 | The Applicant should provide more detailed information regarding the thickness of Holocene/mobile beds across the study area. Further bathymetric survey data should be acquired to refine modelling results and assessment of bedform migration directions and rates. |  | No change. |  | No change.
9 | B15 & B2 | There is discrepancy between information provided within [APP-062] 6.1.7 and evidence within [APP-152] 6.3.7.3 Seabed Mobility Report [CONFIDENTIAL]. Information is required to demonstrate how potential changes to the wave regime (due to the presence of the array) have been considered in the assessment of changes to sediment transport processes and bedform migration within the array, over the lifetime of the Project and the impact assessment updated, if required. |  | No change. Please also refer to our Deadline 1 Appendix B1 response. |  | Our advice remains unchanged since Deadline 1.
10 | B16 | Inner Silver Pit glacial tunnel valley has not been included as a receptor in [APP-062]. Natural England advises that further consideration of the potential impacts of the Project on Inner Silver Pit is required. |  | Issue resolved. The applicant has confirmed in their response this has been assessed in APP-062 and APP-065.
11 | B17 & B2 | Is the scheme layout modelled presented in Figures 7.24 to 7.26 actually the realistic WCS, or whether, based on the engineering assessment [APP-152], the realistic WCS is more likely to be a scheme layout where foundations are located away from mobile sandbanks and the larger sandwaves. Further clarification/evidence from the Applicant on hydrodynamic and wave modelling of RWCS inline with the Seabed Mobility Report. |  | No change. Please see our Deadline 1 Appendix B1 and comments made in response to the additional modelling carried out due to the changes to the array (and introduction of the ORBA). |  | Our advice remains unchanged since Deadline 1.
12 | B18, B33 & B3 | Provide evidence to support the impact assessment conclusions for changes to seabed morphology and modifications to the wave, tide, and sediment transport regime due to the presence of the Offshore Reactive Compensation Platforms (ORCPs). Further consideration should be given to moving the platform north away from Inner Dowsing Sandbank and the SAC. A balance will need to be sought between SAC impacts and those of the Greater Wash SPA. |  | Not resolved. Please see our Deadline 1 Appendix B1 response. |  | Our advice remains unchanged since Deadline 1.
13 | B19 & B4 | Impacts from proposed O&M activities detailed in [APP-058 & APP-062] need to be taken account of in relevant environmental assessments as per other stages of the development. O&M related environmental impacts should be reduced through the avoid, reduce, mitigate hierarchy and inform both Project alone and in-combination/cumulative assessments. |  | No change. |  | No change.
14 | B20 | The Applicant should follow Natural England and Joint Nature Conservation Committee (JNCC) best practice for determining which projects should be included in cumulative assessments and the level of data that is available at each stage. |  | No change. |  | No change. Further clarification has been provided by NE in response to Examiners Questions Q1 BE 2.6.
15 | B21 & B2 | Natural England advises that the seabed mobility assessment for the initial operational period of the wind farm should be revisited to reflect the predicted OWF lifespan of 35 years. And any necessary changes made to the impacts assessments. |  | No change. However, the Applicant has stated that further evidence will be provided as part of a separate Project-specific Sandwave Levelling Assessment that will be submitted into the Examination. |  | Our advice remains unchanged since Deadline 1.
16 | B22 | Impacts to the Lincolnshire Coast Submerged Forest LGS should be avoided through careful selection of cable routing or installation techniques, unless it can be clearly demonstrated that the potential impacts will not affect their extent or distribution. |  | Issue progressed. The Applicant has confirmed that use of HDD at landfall will avoid interaction with exposures or near-surface layers of submerged forest within the intertidal and out to 500m seaward of MLWS. However, uncertainty remains as to how impacts to other areas of the submerged forest will be avoided. To resolve this issue this commitment to avoid the submerged forest must be secured in a named document or plan such as the CSIP. |  | Our advice remains unchanged since Deadline 1.
17 | B23 | Natural England advises liaison with the EA to gain a better understanding of the proposed changes to beach nourishment and implementation of coastal defence measures at landfall. Potential impacts to asset integrity should be assessed for the lifetime of the project, taking into account vertical changes to beach elevation, coastal retreat, and sea level rise. Consideration should also be given to potential sink holes appearing due to unconsolidated sediment layers. |  | Issue Progressed. The Applicant has confirmed that they have liaised with the EA, and will continue to do so, post-application and prior to construction. However, uncertainty remains concerning changes to beach management strategy at landfall, future coastal/beach change, and buried asset integrity over the lifetime of the project. |  | Our advice remains unchanged since Deadline 1. Environment Agency reference document [REP1-026] Natural England will keep a watching brief on this matter.
18 | B24 | The use of (Horizontal Directional Drilling) HDD at landfall has not been explicitly stated in the Schedule of Mitigation. The Applicant should include HDD at landfall in the Schedule of Mitigation. |  | This issue is resolved. this is secured in the DCO in Part 1 of Schedule 1 of the dDCO (3.1) and the Schedule of Mitigation [PD1-059].
19 | B25, B26 & B1 | Impact 1: Increase in SSC resulting in elevated turbidity and consequential changes to seabed levels. We do not agree with the conclusion of low magnitude impact, or that all marine process receptors are insensitive to this impact (construction-related increases in SSC, elevated turbidity, and changes to seabed levels). Review the EIA conclusions and the conservation objectives for the IDRBNR SAC and the Greater Wash SPA. |  | No Change |  | No change.
20 | B27 | Impact 2: Potential Impacts to Seabed Morphology. Features of the IDRBNR SAC and other Annex I sandbanks within the array and ECC may be impacted by modifications to seabed morphology due to construction-related activities within the offshore ECC and array area. The conclusions should be revisited with an assessment of impacts to the different marine physical process receptors. See our updated conservation advice (May 2023) for IDRBNR SAC. |  | No change. |  | No change.
21 | B28, B33 & B5 | Impact 2 Potential Impacts to Seabed Morphology – Use of Cable Protection Measures. We disagree with the impact assessment conclusions owing to the potentially long-lasting change to and/or loss of Annex I sandbank features, and potential change to sediment composition. The Applicant should make all efforts to avoid, reduce and mitigate impacts to IDRBNR SAC. Removable cable protection should be the only type permitted within the SAC. This mitigation measure is not committed to within several of the cable installation documents which still reference rock protection. |  | No change. |  | No change. Please see our Deadline 2 response on ExQ1 HRA 1.5 in Appendix K
22 | B29 & B6 | Impact 3. Cable protection within the shallow nearshore could interfere with wave energy transmission could affect nearshore sediment pathways and coastal morphology. We disagree with the assessment conclusion as disruption of these processes would have a likely significant effect to coastal SACs and SPAs. Owing to uncertainty regarding MDS for nearshore cable protection and beach management plans, the impact assessment conclusions should be revisited. |  | Issue Progressed. See Comments Points 5 & 17. |  | Our advice remains unchanged since Deadline 1.
23 | B30 & B6 | Impact 4: Modifications to the Wave and Tidal Regime and Associated Potential Impacts to Morphological Features (O&M). We advise that there is a pathway of effect for this impact on coastal receptors if cable protection is used in the nearshore. Natural England advises that the Applicant should revisit their assessment of receptor sensitivity for coastal receptors. Please also refer to our advice above. |  | Issue Progressed. See Point 5. |  | Our advice remains unchanged since Deadline 1.
24 | B31 | Impact 5: Seabed Scouring. within the array and ECC. There is the potential for scour (or secondary scour) and removal of seabed sediments due to the presence of cable/scour protection measures and/or cable exposures. The Applicant should consider and assess the potential for secondary scour impacts to marine processes receptors (e.g. IDRBNR SAC, Annex I sandbanks etc). |  | No change. |  | No change.

## C- Benthic & Intertidal Ecology
Point | Ref from Appendix C [RR-045] | Taken from Natural England’s Relevant and Written Representations ODOW Appendix C - Benthic & Intertidal Ecology [RR-045] | RAG Status Rel and Wri Rep D1 | Consultation, actions, progression | RAG Status D2 | Consultation, actions, progression | RAG Status D3 | Consultation, actions, progression | RAG Status D4 | Consultation, actions, progression | RAG Status D5 | Consultation, actions, progression | RAG Status D6
1 | C11, C46, C60 & C5 | Clarification is required on the cable protection design within and outwith the IDRBNR SAC and whether additional protection over the project lifetime, or secondary scour has been included for the maximum design scenario (MDS)/ worst case scenario (WCS). Update the Scour and Cable Protection Management Plan [APP-295] and RIAA [APP-235] with the WCS. DCO/DML restrictions may be required to ensure the WCS within the SAC hasn’t been exceeded during construction. |  | No change. |  | No change.
2 | C14 | More detail is required on permitted Operations and Maintenance (O&M) activities over the lifetime of the project within the ECC, especially within IDRBNR SAC. new marine licence will be required for any further protection during the project lifetime. |  | No change. |  | No change.
3 | C12 & C10 | Without an outline decommissioning plan a realistic WCS can’t be determined especially in rleation to impacts from cable protection. Natural England advises that an outline decommissioning plan in provided. |  | No change. |  | No change.
4 | C13 &C10 | It is unclear what the process will be for boulder clearance and repositioning within the IDRBNR SAC and how the project will minimise the impacts of this activity on sensitive features within the site. Mitigation measures should be adopted to minimise the impacts of this activity to Annex I feature within IDRBNR SAC. The project should present a plan for review. |  | Issue progressed. Please see our Deadline 1 Appendix C1 |  | No change.
5 | C15 | We are unable to ascertain from an ecological perspective that cables can be optimally buried. We advise that the Cable Burial Risk Assessment (CBRA) [APP-0142] is updated from an ecological perspective using geophysical and geotechnical data and this should be cross referenced with the CSIP [APP-278] |  | No change. |  | No change.
6 | C16, C17, C18, C19, C20, C21 & C1 | Applicant to re-examine the existing data, analytical approach and methods which have been used to provide a baseline [APP-155] of the extent and distribution of Annex I S. spinulosa reef. Evidence is required to provide the necessary confidence that pre-construction surveys, project mitigation and, where necessary, compensation requirements will be effectively targeted and implemented at the appropriate scale. |  | Issue progressed. Please see our Deadline 1 Appendix C1 response. |  | No change.
7 | C22, C23 , C24, C25, C26, C27 & C1 | Envision Data Analysis [APP-158] does not address concerns relating to the adequacy of methods and interpretation for determining the presence of Annex I S. spinulosa reef. Our comments to the EBS [APP-155] and Envision report [APP-158] should be considered in a review of the available data. Further information and evidence are required to demonstrate that the extent and distribution of Annex I S. spinulosa reef, particularly within the IDRBNR SAC, has been robustly determined and the precautionary principal applied. |  | Issue progressed but not resolved. Please see our Deadline 1 Appendix C1 response. |  | No change.
8 | C28 | In response to Natural England S42 comments, the Applicant states that S. spinulosa was only found ‘intermittently along a single camera transect’. This statement is incorrect and requires removal. Sabellaria spinulosa was observed along multiple video transects as per the ECC EBS [APP-155]. |  | The Applicant confirms this error has not been carried through the assessments and therefore no further action is required.
9 | C29, C42, C1 & C2 | The Applicant's conclusion of ‘no significant impacts in EIA terms’ on S. spinulosa Reef are not scientifically robust and require revisiting following a more appropriate review of the data available as per our accompanying comments. |  | Progressed: Please see our Deadline 1 Appendix C1 response. |  | No change.
10 | C30, C43 & C3 | The sandbank communities have not been attributed EUNIS/Biotope classifications and therefore it is not possible to determine the significance of impacts on Sandbank receptors and thus the conservation objectives for the IDRBNR SAC. The assumptions made by the Applicant to draw the conclusion of ‘no significant impacts in EIA terms’ relating to lasting loss/change of habitat of Sandbank habitat, especially within the SAC are not scientifically robust. The EIA methods require revisiting. |  | No change. |  | No change.
11 | C31 & C5 | Scour Protection: Natural England notes that the mitigation listed is from an engineering perspective rather than an ecological one. Schedule of Mitigation [APP-297] should be amended and it reflect commitments made to avoid rock protection in the IDRBNR SAC. We further advise the Applicant must demonstrate due regard to S. spinulosa reef within 12nm under Section 41 of the Natural Environment and Rural Communities (NERC) Act 2006. |  | No change. |  | No change.
12 | C32 & C5 | All cable protection should be removed from IDRBNR SAC at the time of decommissioning. The use of rock protection should be excluded within the SAC. The schedule of mitigation [APP-287] should be updated to reflect commitments made to avoid rock protection in the IDRBNR SAC. |  | Progressed. Please see our Deadline 1 Appendix C1 response. |  | No change.
13 | C34 & C10 | The production of a PEMP in itself cannot be considered mitigation. We have concerns with level of detail of measures included in the Outline documents and their effectiveness. Natural England requests that further details are provided on specific mitigation measures within the Outline PEMP. |  | No change. |  | No change.
14 | C35 & C10 | Disposals sites for dredged material should be agreed as part of the consenting process. Disposal sites within the IDRBNR SAC should be upstream of the sandbank to help facilitate recovery. Natural England advises that further commitments to disposal locations should be made prior to consent being granted. |  | Progressed. Natural England welcomes review of the Disposal Site characterisation report [PD1-097]. We advise the commitments within the Schedule of mitigation [PD1-059] should reflect that disposal sites should be upstream of the sandbank feature within the IDRBNR SAC and a fallpipe for deposition should be used. |  | No change.
15 | C36& C10 | There is no distinction in the Scour and Cable Protection Management Plan [APP-295] between the amount of cable protection deployed inside and outside of the IDRBNR SAC, the focus is on reducing cable protection to 5% within sandbank features only. Natural England queries if further reductions in cable protection within IDRBNR SAC can be made. |  | No Change |  | No change.
16 | C37, C4, & C10 | The Outline Biogenic Reef Mitigation Plan [APP-296], Section 2 'Consultation' appears to be incomplete. Each piece of Natural England's pre-application advice should be included, particularly to annex I reef should be included and discussed by the Applicant within this section of the mitigation plan. |  | Issue Addressed. Pre-application advice is included within the Biogenic Reef Mitigation Plan Rev2 [PD1-067].
17 | C38, C39, C57, C4 & C10 | In the Outline Biogenic Reef mitigation Plan [APP-296] provide detail on how and when pre-construction surveys will be undertaken. Comments to the baseline characterisation must be considered and the Applicant should provide a robust and well-informed pre-construction survey strategy which will confidently and accurately identify the presence and extent of S. spinulosa reef within the ECC, or areas with suitable conditions for reef formation, to appropriately facilitate and inform mitigation and compensation requirements where relevant. |  | No change. Please see our Deadline 1 Appendix C1 response. |  | No change.
18 | C40 | Applicant to provide information on how they plan to define 'known' reef and supporting reef as per the micro-siting mitigation proposed in the Scour and Cable Protection Management Plan [APP-295] . Noting the importance of potentially supporting habitat, and areas of 'potential reef' in maintaining the total feature extent. |  | No change. Please see our Deadline 1 Appendix C1 response. Our position regarding supporting reef habitat will be provided at Deadline 2. |  | No change. We will be providing further advice at Deadline 3 in relation to impacts on suitable reef habitat
19 | C41, C4 | The Applicants response to our previous advice relating to MMO fisheries byelaw closure areas is incorrect and requires revision. All documents eg [APP-296] outlining mitigation measures should be updated to include measures to avoid lasting/permanent pressures within MMO fisheries byelaw areas so that reef recovery is not hindered. |  | Progressed. Natural England welcomes the commitment in the Outline Benthic Mitigation Plan [PD1-067] to avoid cable installation within the MMO fisheries byelaw area, but advise all impacts within the byelaw areas are avoided . |  | No change.
20 | C45 | As the project refines its MDS, Natural England requests further information in the RIAA [APP-235] on how the Applicant is committing to meeting the conclusions of the Plan Level HRA and the Export Cable Region Assessment. Natural England would welcome input from the Crown Estate to better understand how the proposals meet any seabed lease conditions. |  | No change. |  | No change.
21 | C47 | The benthic and intertidal ecology sections of the RIAA [APP-235] should be updated to focus on IDRBNR SAC and potential hinderance of the conservation objectives to provide a true representation of the Habitat Regulation concerns |  | No change. |  | No change.
22 | C48,C60 C5 & C7 | Even if the Applicant is able to fully microsite the cable to avoid known Annex I reef features there will still be a loss of Annex I reef supporting habitat which we consider would be adverse effect and would require compensation. Natural England advises that impacts to supporting habitat are considered within the RIAA. Until this is resolved we do not agree with the conclusions of the RIAA in regard to impacts to Annex I reef from the placement of cable protection. |  | No change. Please see our Deadline 1 Appendix C1 response. Our position regarding supporting reef habitat will be provided at Deadline 2. |  | No change. We will be providing further advice at Deadline 3 in relation to impacts on suitable reef habitat
23 | C49 & C7 | There is disagreement with the Applicant on statements made on Annex I reef recovery. Natural England advises compensation measures do not take account of this impact. Natural England refers the ExA to the Norfolk Vanguard and Boreas Secretary of State Decisions where compensation was required due to the potential to disturb Annex I S. spinulosa Reef during cable installation |  | No change. Please see our Deadline 1 Appendix C1 response. Our position regarding supporting reef habitat will be provided at Deadline 2. |  | No change.
24 | C50 & C7 | It is a condition of all Aggregates Dredging licences that impacts to Annex I reef are avoided. References with regard to 2007 and 2001 S. spinulosa reef recovery cannot be relied upon. Natural England’s advice on likely recoverability of Annex I reef is consistent with previous examinations. There is a likelihood of there being an impasse between the professional judgement of the Applicant’s consultants and Natural England specialists on this matter. |  | No change. |  | No change.
25 | C51 & C7 | Natural England disagrees with the Applicant’s conclusion that Annex I S. spinulosa reef will recover from cable installation activities and due to uncertainties with the impact assessment we do not believe that mitigation measures in the form of micro-siting has the necessary assurances in relation to avoiding impacts within the red line boundary. There is likelihood of there being an impasse between the Applicant and Natural England on this matter. |  | No change. |  | No change.
26 | C52 | There are limitations with the evidence to support sandbank recovery following levelling. Natural England advises that monitoring sandbank recovery post construction should be incorporated within the In Principle Monitoring Plan. |  | No change. Though we note that Applicant disagrees with us on this point |  | No change.
27 | C53, C60 C5, C6 | In APP-235, the assessment of physical habitat loss needs to be considered separately from physical disturbance in considering LSE/AEoI as the receptors have different levels of sensitivity to each of these pressures. Alternatively, the worst case sensitivity should be used and considered when determining LSE and or AEoI. |  | No change. |  | No change.
28 | C54 | Several different TIER approaches for the in-combination assessment have been proposed and therefore the ongoing impacts from constructed windfarms have not been taken into account. We are unable to agree with the conclusions drawn within this report. Please refer to Natural England’s Best Practice Guidance for the SNCBs advice on using Tiers for scoping project into in-combination assessments |  | No change. |  | No change.
29 | C55, C6 | For Annex I Sandbanks within the RIAA [APP-235], every effort must be made to mitigate the project impacts to not only reduce the Project’s alone effects but also ensure that it doesn’t materially contribute to existing pressures/cumulatively and in-combination impacts. Natural England advises these pressures, including small-scale losses, should be fully considered in the in-combination impact assessment. |  | No change. |  | No change.
30 | C58, C60, C5 | Natural England considers that the impacts from cable protection are likely to result in lasting change and/or loss of Annex I Sandbank feature. The commitment to solely use removable cable protection over the Annex I Sandbank features of the IDRBNR SAC is missing from Table 6.1 [APP-235]. All mitigation of relevance to the assessment of impacts on IDRBNR SAC features should be made consistent both within, and across, the application documents. Further evidence is required to provide the necessary level of assurance that any mitigation (i.e. scour protection removal) will be fully successful. |  | No change. |  | No change.
31 | C59, C60 | Table 6.1 ‘Mitigation of Relevance to the RIAA’ [APP-235] fails to mention the MMO fisheries byelaw areas which should be managed as reef. Natural England strongly advises that avoidance of MMO byelaw areas be included within proposed mitigation for Annex I reef within the IDRBNR SAC. |  | No change. See advice to point 19. The RIAA should be updated to reflect this commitment for the MMO Byelaw areas. |  | No change.
32 | C63, C64 & C9 | Comments to the approach and methods used to identify Annex I reef, also apply to Sabellaria Reef Priority Habitat (Section 41 of the NERC Act, 2006). Mitigation measures should be adopted via the Applicants Schedule of Mitigation [APP-0287] and ES [APP-154] in order that impacts (particularly permanent loss) on all Section 41 Habitats be avoided and/or reduced wherever feasible through mitigation measures such as micro-siting and considered within the Biogenic Reef Monitoring Plan [APP-296] and IPMP [APP-276]. |  | Issue progressed but not resolved. See Appendix C1. Our position regarding supporting reef habitat will be provided at D2. |  | No change.
33 |  | Natural England believes there may be a risk of impacts to benthic/intertidal ecology receptors from nearshore cable protection amendments proposed by the Applicant. Further information is required on potential mitigation measures proposed by the Applicant to adress our concerns in relation to potential disruption of sediment transport along the near shore from cable protection. NE Ref B6, B11 and B29 |  |  |  | Please see our Deadline 2 response to ExQ HRA 1.7 within Appendix K

## D - Benthic Compensation
Point | Ref from Appendix D [RR-045] | Taken from Natural England’s Relevant and Written Representations ODOW Appendix D - Benthic Compensation [RR-045] | RAG Status Rel and Wri Rep D1 | Consultation, actions, progression | RAG Status D1 | Consultation, actions, progression | RAG Status D2 | Consultation, actions, progression | RAG Status D3 | Consultation, actions, progression | RAG Status D4 | Consultation, actions, progression | RAG Status D5 | Consultation, actions, progression | RAG Status D6
1 | Agreed compensation level & Scale/extent - all measures | Outcomes of the impact assessment and evidence to support the conclusions and the Worse Case Scenario (WCS) of lasting habitat loss/change of Annex I Sandbanks and Reef features from the placement of cable protection within Inner Dowsing Race Bank and North Ridge (IDRBNR) SAC and habitat disturbance of Annex I Sabellaria spinulosa reef from cable installation within IDRBNR SAC is not agreed. This is relevant to all compensation measures. |  | No change. |  | No change.
Strategic Compensation - New site designation or Extension for Annex I Sandbanks and Reef
2 | Agreed compensation level | Due to potential uncertainties with the delivery mechanisms and timeframes for successful delivery of the measure, further discussions (outside of individual project contributions) are required to determine individual project contributions and compensatory ratios. |  | No change. |  | No change.
3 | Delivery mechanism | As set out in the R4 plan level compensation document, the designation of a new site or existing site extension will be led on by a team in DEFRA in collaboration with interested parties therefore delivery mechanisms, costs and timeframes presented by the Applicant cannot and should not be relied upon |  | No change. |  | No change.
4 | Timing | There are likely to be time lags between impact occurring and strategic compensation achieving the desired outcomes. In this scenario, the project contribution to the measure to be such that it ensures an overall environmental net positive outcome for the impacted feature over the lifetime of the project. |  | No change. |  | No change.
5 | Location, Implementation and Additionality | For strategic compensation, the location, long term implementation and success criteria/ability to prove additionality will be determined by DEFRA, in consultation with Natural England and JNCC. This is still under consideration and as yet nothing has been agreed and/or secured. |  | No change. |  | No change.
6 | Impacts to supporting habitats | Lasting loss/change of supporting habitat for Annex I Sabellaria spinulosa reef from the placement of cable protection will further hinder the restore conservation objective for this feature as the seabed will no longer be available for Annex I S. spinulosa reef restoration. The scale and significance of the impact and required compensation for this feature is likely to be considerably greater than presented . |  | No change. |  | No change.
7 | Further limitations | Limited geotechnical and geophysical survey data has been presented with the Cable Burial Risk Assessment [APP-142] and the Cable Specification and Installation plan [APP- 278] to have confidence that the cables can be buried to optimum cable burial depth. In addition, there is limited consideration of the highly dynamic sediment transport/marine processes within IDRBNR SAC which may have implications for cable burial over the lifetime of the project. Therefore, we are concerned that the WCS presented for cable protection within IDRBNR SAC may not be realistic. |  | No change. |  | No change.
Alternative measures for Annex I Sandbanks and Reef
8 | Theoretical merit | This option is not considered viable within the Project’s timeframe. If the Applicant wishes to pursue this there will need to be agreement from The Crown Estate for a seabed lease and management measures put into place. It currently remains unclear how this measure will ensure the coherence of the National Site Network. This measure is outside of NE remit therefore the Applicant will need to liaise with TCE, DEFRA, MMO (and EIFCA depending on location). |  | No change. |  | No change.
Anthropogenic Pressure Removal – Redundant Infrastructure for Annex I Sandbanks
9 | Theoretical merit to deliver compensation | There is no evidence that redundant telecoms cables are causing a significant impact on the Annex I Sandbank feature of the IDRBNR SAC or other benthic designated sites. Unless further supportive detailed evidence is provided, Natural England does not consider their removal to constitute suitable compensation as a primary measure. |  | No change. |  | No change.
10 | Technical feasibility | There is limited evidence that the cables are sufficiently present on the surface of Annex I Sandbanks at both a spatial and temporal scale to be hindering the conservation objectives of the designated sites and the attributes of Annex I sandbanks. Once this can be demonstrated then commitments with the cable owners will need to be secured. |  | No change. |  | No change.
11 | Location of measure | The location of the measure has not been presented in detail and/or agreed with the SNCBs. |  | No change. |  | No change.
12 | Long term implementation | In order to provide the Secretary of State with the necessary comfort that the removal of redundant infrastructure can be sufficiently progressed during the consenting phase, the intention for monitoring and adaptive management [APP-245] should be set out in more detail. It is anticipated as the examination progresses this measure is either more thoroughly progressed or removed as an option if not. |  | No change. |  | No change.
13 | Success criteria/Ability to prove additionality | Please see comments regarding the technical feasibility of this proposed measure. Until this is resolved, success criteria and additionality would be hard to determine. |  | No change. |  | No change.
14 | Suitable as sole measure for target species | While Natural England considers that the removal of redundant infrastructure could be progressed as a sole measure it remains unclear if there are sufficient surface laid/exposed telecom cables on Annex I sandbanks to fully mitigated the potential project impacts. We would be supportive of this proposal being progressed as part of package if not. |  | No change. |  | No change.
15 | Impacts of telecoms within the National Site Network | Information on amount and location of surface laid/exposed cables and the spatial and temporal extent of those are required. |  | No change. |  | No change.
Anthropogenic Pressure Removal - Aggregates Industry Pressures for Annex I Sandbanks
16 | Theoretical merit | Natural England is supportive of the option for a percentage buyout of aggregate licence(s) as a compensation measure for Annex I Sandbank. Reduction of existing pressure on Annex I sandbanks would help restore Annex I sandbanks, prior to any licence renewal. We therefore encourage further detail to be included within the Application of any agreements with Aggregates industry that this measure has potential for. |  | No change. |  | No change.
17 | Technical feasibility | Natural England believes this is technically feasible as there are active Aggregate licences within the National Site Network which interact with Annex I sandbanks. However, there is currently no certainty that this measure can be secured. |  | No change. |  | No change.
18 | Timing | It is unclear if this measure can be delivered prior to the impacts occurring. |  | No change. |  | No change.
19 | Location of measure | The location of the measure has not been presented in detail and/or agreed with the SNCBs. |  | No change. |  | No change.
20 | Long term implementation | In order to provide the Secretary of State with the necessary comfort that the removal of aggregate pressures can be sufficiently progressed during the consenting phase, the intention for monitoring and adaptive management [APP-245] should be set out in more detail. It is anticipated as the examination progresses this measure is either more thoroughly progressed or removed as an option if not. |  | No change. |  | No change.
21 | Success criteria/Ability to prove additionality | The success criteria/ability to prove additionality is yet to be considered in detail and agreed with the SNCBs. |  | No change. |  | No change.
22 | Suitable as sole measure for target species | While Natural England considers that the buyout of Aggregate licences could be progressed, it remains unclear if there are any options open to the Applicant to deliver this measure either as a sole measure or as part of a package. |  | No change. |  | No change.
23 | Active licence areas willing to be bought out | Information on amount and location of available active licence locations open to being bought is required. |  | No change. |  | No change.
Anthropogenic Pressure Removal - Marine Debris and Awareness campaign for Annex I Sandbanks and Reef
24 | General | The SNCBs are not supportive of the measure for marine debris awareness campaign . Marine Debris Removal is not included in DEFRA’s Strategic Compensation Library of Measures nor the R4 Plan Level Strategic compensation measure. This measure must be removed from the list of proposed compensation measures. |  | No change. |  | No change.
Creation of Biogenic Reef
25 | Annex I Sandbanks | Natural England refers the ExA to the published ‘Offshore Wind Leasing Round 4 Dogger Bank Strategic Compensation Plan’ (April 2024). The Round 4 Plan Level Benthic Compensation Steering Group considered that Reef creation/enhancement is not of comparable ecological function to Annex I sandbank and is therefore not an appropriate measure for sandbank compensation. We consider the same to be true for sandbank systems within IDRBNR SAC and provide no further comment on this measure. |  | No change. |  | No change.
26 | Theoretical merit Annex I Reef | The creation/restoration of other reef features should not be at the detriment of existing Annex I habitats within IDRBNR SAC and/or hinder Annex I Sabellaria spinulosa reef restoration. If reef creation was to be progressed we would be more inclined towards Blue Mussel (Mytilus edulis) reef than Oyster reef which is not proven to have been historically found within the site. Natural England advises that this proposal to compensation for Annex I reef requires further development to provide the necessary confidence in it as a measure. |  | No change. |  | No change.
27 | Technical feasibility - Annex I Reef | There is limited evidence to suggest why Oyster and Blue Mussel reef are not/no longer present with IDRBNR SAC and there are no guarantees of success. In particular , the recreation of Oyster beds is proving to be challenging. Natural England advises that this proposal to compensation for Annex I reef requires further development to provide the necessary confidence in it as a measure. |  | No change. |  | No change.
28 | Agreed compensation level Annex I Reef | Due to potential uncertainties with the delivery mechanisms and timeframes for successful delivery of the measure , further discussions are required in relation to compensatory ratios which may be required. The Applicants' assessments should be undertaken in line with SNCB advice to aid in informing compensation measures. |  | No change. |  | No change.
29 | Scale/extent of measure - Annex I Reef | The scale/extent of the measure has not been presented in detail and/or agreed with Natural England, JNCC or DEFRA. |  | No change. |  | No change.
30 | Timing Annex I Reef | We do not believe that this measure will be available in the project timeframes. The proposal for compensation for Annex I reef requires further development to provide the necessary confidence in it as a measure |  | No change. |  | No change.
31 | Location of measure Annex I Reef | The location of the measure has not been presented in detail and/or agreed with Natural England, JNCC or DEFRA . Until further evidence is provided to refine down the 17 areas of search to 1 or maybe 2 locations the potential impacts on Annex I features within the SAC and/or the conservation objectives for the site , can’t be assessed. Therefore, at this time we are unable to support the inclusion of Schedule 16 and/or the 17 location s proposed. |  | No change. |  | No change.
32 | Long term implementation Annex I Reef | In order to provide the Secretary of State with the necessary comfort that the removal of redundant infrastructure can be sufficiently progressed during the consenting phase, the intention for monitoring and adaptive management [APP-245] should be set out in more detail. It is anticipated as the examination progresses this measure is either more thoroughly progressed or removed as an option if not. |  | No change. |  | No change.
33 | Success criteria/Ability to prove additionality Annex I Reef | Please see comments regarding the technical feasibility of this proposed measure. Until this is resolved, success criteria and additionality would be hard to determine. |  | No change. |  | No change.
Seagrass Habitat Creation/Restoration for Annex I Sandbanks
34 | Theoretical merit to deliver compensation | Seagrass restoration is a lower preference measure compared to those supporting the same ecological function of the habitat being compensated for. Subtidal seagrass has not been found within IDRBNR SAC, . |  | No change. |  | No change.
35 | Technical feasibility | The published ‘Offshore Wind Leasing Round 4 Dogger Bank Strategic Compensation Plan’ (April 2024), section 3.4.3 sets out "concerns about the deliverability of seagrass restoration, even on a small scale as there have been no long term successes with seagrass restoration in the UK. Seagrass restoration is included as a potential measure only where it would be a minor part of a wider package in terms of the required compensation....". This is also applicable to ODOW compensation. NE will provide further comment on the technical feasibility during examination . |  | No change. |  | No change.
36 | Timing: Deliverable before impact | It is unclear if this measure can be delivered prior to the impacts occurring. |  | No change. |  | No change.
37 | Location of measure | The location of the measure has not been presented in detail and/or agreed with the SNCBs. |  | No change. |  | No change.
38 | Long term implementation | In order to provide the Secretary of State with the necessary comfort that the removal of redundant infrastructure can be sufficiently progressed during the consenting phase, the intention for monitoring and adaptive management [APP-245] should be set out in more detail. It is anticipated as the examination progresses this measure is either more thoroughly progressed or removed as an option if not. |  | No change. |  | No change.
39 | Success criteria/Ability to prove additionality | This is yet to be considered in detail and agreed with the SNCBs. |  | No change. |  | No change.
40 | Suitable as sole measure for target species | This measure could only be considered as part of a package providing <10% of the required compensation and/or potential adaptive management for part delivered compensation. There would also be a requirement for the provision of subtidal seagrass, not intertidal. Therefore, we advise that other measures are progressed first. If other projects are being progressed then there is an expectation this compensation will not be taken forward. |  | No change. |  | No change.
41 | Details on project to be progressed | Further details on following should be provided on the particular project/s to be supported by ODOW, how this will be secured in the DCO, the location, and in what form the Applicant will provide the compensation; and how it will be demonstrated to be additional to what the seagrass project already has entrained. It is also unclear how success will be demonstrated. |  | No change. |  | No change.
Other Detailed Advice
42 | D1 | The Without Prejudice Benthic Compensation Strategy [APP-243] should be updated in light of comments provided. |  | No change. |  | No change.
43 | D2 | It is noted in Section 2 of the Without Prejudice Sandbank Compensation Plan [APP-244] avoidance of placing infrastructure within IDRBNR SAC hasn’t been possible. Nor has the avoidance of an AEoI. The predicted impacts are therefore outside of the parameters of the Crown Estate (TCE) plan-level HRA, which concluded that there will be no AEoI from the installation of ODOW cables through IDRBNR SAC. Consideration should be given to the impacts of the Race Bank offshore windfarm cabling within IDRBNR SAC and the ongoing cable exposures occurring for that project. |  | No change. |  | No change.
44 | D3 | The Outline Sandbank Compensation Implementation and Monitoring Plan [APP-245] is a skeleton document of what will be included post consent. Therefore, we are unable to provide comment at this time on its content. It is not clear if this is the most appropriate approach if Strategic Compensation is taken forward. |  | No change. |  | No change.
45 | D4 | The Without Prejudice Biogenic Reef Compensation Plan [APP-246] should be updated in light of comments provided. |  | No change. |  | No change.
46 | D5 | The Annex I Reef Compensation Implementation and Monitoring Plan [ APP-247] is a skeleton document of what will be included post consent. Therefore, we are unable to provide comment at this time on its content. |  | No change. |  | No change.
47 | D6 | Section 2 of the Benthic Compensation Evidence and Route Map [APP-248] is superfluous because of changes in approach since the time those projects were consented. Refer to our advice above as appropriate. |  | No change. |  | No change.

## E - Marine Mammals
Point | Ref from Appendix E [RR-045] | Taken from Natural England’s Relevant and Written Representations ODOW Appendix E - Marine Mammals [RR-045] | RAG Status Rel and WR Rep | Consultation, actions, progression | RAG Status D1 | Consultation, actions, progression | RAG Status D2 | Consultation, actions, progression | RAG Status D3 | Consultation, actions, progression | RAG Status D4 | Consultation, actions, progression | RAG Status D5 | Consultation, actions, progression | RAG Status D6
1 | E6 & E1 | The average summer density for harbour porpoise (2.63 individuals / km) is used in the impact assessment, rather than the average annual density to reflect the importance of the project area during the summer. |  | Issue resolved.
2 | E7, E27 & E2 | The Applicant should use population modelling, for example interim Population Consequences of Disturbance (iPCoD), to understand the impacts of the project alone and in combination with other plans and projects at a population level to provide robust evidence to inform the conclusions of the EIA and HRA. |  | Issue progressed but not resolved. See appendix E1. Natural England will wait to hear from the the Applicant to discuss the parameters that should be used in the cumulative iPCoD assessment. |  | No change.
3 | E8, E12, E13 & E3 | The mitigated impacts of Permanent Threshold Shift (PTS) and Temporary Threshold Shift (TTS) from piling and UXO clearance are not negligible for all marine mammals. Natural England strongly advises the Applicant to commit to using noise abatement as mitigation, should driven or part-driven piles be used during construction. The effect of NAS in reducing noise impacts should be included in the assessment. |  | No Change. See appendix E1. |  | No change.
4 | E9 | Disturbance impacts to harbour seal from piling which could further hinder the ‘restore’ objective of The Wash and North Norfolk Coast (WNNC) SAC should be avoided, reduced or mitigated. If impactful noise from the project reaches the SAC, additional mitigation measures, for example NAS, should be implemented. To avoid disturbance during sensitive times, activities generating impactful noise which may reach the SAC should also be avoided during pupping (June, July and August). |  | No change. |  | No change.
5 | E10 | There is concern that noise from piling of the Offshore Reactive Compensation Platform (ORCP) will cause a barrier for harbour seals entering and leaving the Wash and North Norfolk Coast SAC. The Applicant should provide a barrier effects assessment on harbour seal disturbance from piling at the ORCP. |  | No change. |  | No change.
6 | E15 | If a marine mammal is not observed leaving the mitigation zone, a delay of 20 minutes from the last sighting should be implemented before commencement of soft-start. This should be committed to within the final MMMP. |  | Issue resolved.
7 | E16 | The PAM guidance was updated in December 2023 (JNCC 2023). This updated version should be used to inform the final MMMP. Updated PAM guidance should be used to inform the final MMMP: JNCC guidance for the use of Passive Acoustic Monitoring in UK waters for minimising the risk of injury to marine mammals from offshore activities ¦ JNCC Resource Hub. |  | Issue resolved.
8 | E17 | For a maximum hammer energy of 6,600 kJ, the soft-start should commence at 10% of maximum hammer energy, not 15% as stated here. This 10% maximum hammer energy should be committed to in the final MMMP. |  | No change. See appendix E1. |  | No change.
9 | E18 | If the commencement of piling is delayed for a sufficient time to warrant the Acoustic Deterrent Device (ADD) being turned off, the break in ADD use should be more than 20 minutes to ensure a startle and flee response once reactivated. Any break in ADD use being more than 20 minutes should be committed to in the final MMMP. |  | Issue resolved.
10 | E19 | Visual marine mammal watches should commence at least 30 minutes before ADD activation. This might require the visual watch to be longer than 1 hour when the ADD activation time is longer than 30 minutes. A commitment for visual marine mammal watches for a duration of at least 30 minutes before ADD activation should be included in the final MMMP. |  | No change. |  | No change.
11 | E20 | If UXO detonation is delayed for a sufficient time to warrant the ADD being turned off, the break in ADD use should be more than 20 minutes to ensure a startle and flee response once reactivated. Any break in ADD use being more than 20 minutes should be committed to in the final MMMP. |  | Issue resolved.
12 | E21 | The mitigation and marine mammal sections do not include measures to avoid collisions with marine mammals. Measures should be included in the vessel management plan to ensure vessels operate appropriately around marine mammals, these should be finalised in accordance with best practice at the time. This may include the Scottish Marine Wildlife Watching Code. |  | Issue resolved.
13 | E23 | Harbour porpoise have been screened out from sites that are more than 26 km from the project. As wide-ranging animals, any designated site with harbour porpoise as a named feature within the North Sea Management Unit should be screened in. |  | Issue resolved.
14 | E25 | The number of seismic surveys included in the incombination assessment should be clearly stated. Two seismic surveys per year should be included in the incombination assessment. The Assessment should be updated to reflect this. |  | Issue resolved.
15 | E26, E4 | The current approach to implementing Site Integrity Plans (SIPs) for piling impacts to the Southern North Sea SAC does not allow sufficient time for mitigation methods, such as NAS, to be procured by the Applicant prior to construction, should they be required, therefore increasing the risk that an Adverse Effect on Site Integrity cannot be avoided. The use of specific mitigation measures should be committed to at this stage, which may be removed at a later date if the revised SIP demonstrates they are not required. |  | No change. |  | No change.
16 | E28 &E2 | Natural England is not confident that the levels of disturbance from underwater noise caused by piling and UXO clearance from the project alone and in-combination with other activities can be concluded as no AEoI on the Wash and North Norfolk Coast SAC. Population modelling (such as iPCoD) should be undertaken to assess the impacts of the project alone and in-combination with other activities on the population of harbour seal in the Wash and North Norfolk coast SAC. |  | Issue progressed but not resolved. See appendix E1. Natural England will wait to hear from the the Applicant to discuss the parameters that should be used in the cumulative iPCoD assessment. |  | No change.
17 | E29 | There is a high proportion of harbour seals from the Wash and North Norfolk Coast SAC disturbed from UXO clearance (7.8%). In the UXO clearance licence application, the Applicant should commit to using mitigation which reduces the sound at source, for example Low Order detonation or, as a last resort, high order with NAS. |  | No Change. |  | No change.
18 | E30 | A high proportion (68.36%) of the SNS SAC estimated to be disturbed by the project in-combination with other activities. Natural England does not agree to the conclusion of no AEoI for incombination impacts of the project for disturbance of harbour porpoise in the SNS SAC. To reduce disturbance to harbour porpoise, the Applicant needs to commit to NAS to significantly reduce the sound at source and should revise the conclusions of the assessment. |  | No change. |  | No change.
19 | E31 | The Applicant should incorporate advice from Natural England’s Best Practice Advice documents when planning In-Principal monitoring. Phase IV Best Practice Advice for Post-Consent Monitoring, Version 1.0, July 2022.pdf |  | Issue progressed but not resolved. |  | No change.
20 |  | In [PD1-045] no commitment has been made to conduct pre-piling searches by qualified Marine Mammal Observers (MMObs) as per the JNCC guidelines (JNCC Piling Guidelines (August 2010)). |  | New issue identified at Deadline 1, see Appendix E1. |  | No change.
21 |  | In [PD1-045], the Applicant has stated that Passive Acoustic Monitoring (PAM) can be used to supplement visual monitoring during periods of poor visibility, to allow piling to commence during these conditions. Natural England does not recommend piling commences during poor visibility conditions. |  | New issue identified at Deadline 1, see Appendix E1. |  | No change.
22 |  | The MMMP should consider how the increased mitigation zone [PD1-047] can be efffectively monitored to ensure all marine mammals can be detected. If effective moniroting cannot cover the PTS impact zone, other methods of mitigation or sound reduction at source will be required. |  | New issue identified at Deadline 1, see Appendix E1. |  | No change.
23 |  | No commitment has been made to conduct a pre-detonation search by a qualified MMOb in the MMMP [PD1-047]. A pre-detonation search by qualified MMObs should be adopted as per the JNCC guidelines. |  | New issue identified at Deadline 1, see Appendix E1. |  | No change.
24 |  | The Permanent Threshold Shift (PTS) onset range for high order UXO donation, could be larger than the area that can be effectively monitored by visual observers. The delay in operations therefore needs to reflect the distance a marine mammal needs to travel to flee the PTS onset range. There should also be consideration for how the remainder of the PTS onset range will be mitigated. |  | New issue identified at Deadline 1, see Appendix E1. |  | No change.
25 |  | The Applicant has stated that a PAM system may be used to supplement visual monitoring during conditions of reduced visibility. Commencement of UXO detonations should not occur during periods of reduced visibility, since the minimum mitigation requirement set out in the JNCC guidelines for UXO operations state that the mitigation zone must be visually observed. |  | New issue identified at Deadline 1, see Appendix E1. |  | No change.

## F-Offshore&Intertidal Ornitholo
Point | Ref from Appendix F [RR-045] | Taken from Natural England’s Relevant and Written Representations ODOW Appendix F - Offshore & Intertidal Ornithology | RAG Status Rel and Wri Rep | Consultation, actions, progression | RAG Status D1 | Consultation, actions, progression | RAG Status D2 | Consultation, actions, progression | RAG Status D3 | Consultation, actions, progression | RAG Status D4 | Consultation, actions, progression | RAG Status D5 | Consultation, actions, progression | RAG Status D6
1 | F2 | The Applicant has used a theoretical generalised stable age structure to apportion impacts to adults from Special Protection Area (SPA) colonies for Habitats Regulations Assessment (HRA). Where good quality site-specific ageing data is not available, the precautionary approach should be used, to assume that all ‘adult type’ birds recorded on surveys are apportioned as adults. |  | Issue resolved for ORBA assessment. Natural England welcomes the presentation of our approach to apportioning of adults alongside the Applicant's approach within the ORBA documents [PD1-091 and PD1-92]. See Appendix F1. NB This approach should be applied across all documents and updates as required. This issue resolution is subject to clarification of the status of the ORBA in the Examination, and subsequent updates to the original ES documents as required. |  | No change.
2 | F7 | Some consideration should be given within the HRA to the potential for long-term implications of Highly Pathogenic Avian Influenza (HPAI) to reduce the resiliency of populations, and how this may impact on the need for conditions to allow a population to recover to, rather than be maintained at, a target level. |  | No change. See our advice in Appendix F1. |  | No change. See our answer to Examiners Question Q1 HRA 1.1.
3 | F8 & F1 | Collision risk modelling (CRM) parameters presented throughout are not clearly defined. Please ensure parameters are clearly presented under appropriate table headings and table/figure legends/titles in an updated assessment. |  | Issue resolved for ORBA assessment. Natural England welcomes our advice is applied in the ORBA document [PD1-081], noting this is subject to clarification of the status of the ORBA in the Examination. As noted in the cover letter, Natural England requests updates are also made in 6.3.12.2 Chapter 12 Appendix 2 Collision Risk Modelling [APP-163]. |  | No change.
4 | F9, F15 & F6 | The Offshore Reactive Compensation Platform (ORCP) should be included in the MDS and considered at every stage of the project life-cycle including the O&M phase and assessed for potential disturbance and displacement impacts to red-throated diver and common scoter in both the EIA and HRA (project alone and in-combination) for the Greater Wash SPA. Alternative locations for the ORCP outside the SPA should be considered. |  | Issue progressed but not resolved. Irrespective of the status of the ORBA, refer to Advice in Appendix F1 on this issue. |  | No change - we understand further information will be provided by the Applicant in due course.
5 | F11 | Natural England requests the Applicant provides the Annex D Ornithological Census and Capture Trial document. This is relevant to the apportioning of FFC SPA . We are unable to provide advice on the merits of the Applicant’s apportioning approach until this is provided. |  | Issue progressed but not resolved. Natural England welcomes the submission of the two census reports within [AS1-064] though requests clarification on some issues. The Applicant should clearly present how the data from the offshore platform census surveys has been used to generate the apportioning figure for the FFC SPA. |  | No change.
6 | F12 | Tables of abundance and density estimates for baseline characterisation data should be presented separately for birds in flight, birds on the water, and all birds. This should include, accounting for availability bias where relevant and ‘unidentified’ groups are not identified to species level. Without this material Natural England is unable to confirm whether the impact assessment has been correctly conducted. |  | Issue progressed but not resolved. The Applicant has followed Natural England's advice in the ORBA [PD1-086]. Issue resolution is subject to the clarification of the status of the ORBA and request for updates to be reflected in the original ES documents. Natural England will respond on whether the impact assessment has been correctly conducted at Deadline 2. |  | No change.
7 | F13, F30, F46 and F1 | There are errors in the tables presenting the survey data within Appendix 12.1 Annex B. Please check and correct any errors in the baseline characterisation data tables and ensure any errors have not been carried through to the impact assessment. |  | Issue resolved. Please see our advice in Appendix F1.
8 | F14, F4 | The Applicant should set out the process by which design- and model-based estimates are used to show areas of high usage by Auks and how this has informed the refinement of the array area and demonstrates this will as far and practically and reasonably possible reduce the interaction with Auk species. A model-based approach (eg MRSea) should be pursued due to the high predicted impacts to auks, particularly guillemot, and the likely connectivity to Flamborough and Filey Coast SPA (FFC SPA). |  | Issue progressed but not resolved. Irrespective of the status of the ORBA, please see our advice in Appendix F1. |  | No change.
9 | F16 | Natural England advises use of the full breeding season not the migration-free breeding season. The full breeding seasons as outlined in Furness (2015) are :Gannet: March to September Sandwich tern: April to August. The assessments, including the cumulative and in-combination assessments, should be updated accordingly. |  | Issue progressed. See Appendix F1. Natural England welcomes the clarifications within ORBA documents [PD1-081] and [PD1-092]. Correct the information within Table 4.21 and/or the assessment as appropriate. Issue resolution is subject to the approval of the ORBA and request for updates to be reflected in updates to the ES documents. |  | No change.
10 | F17 | The Applicant has used two studies of collisions at Thanet and Aberdeen Offshore Windfarm to argue that the CRM parameters advised by SNCBs are precautionary. Natural England does not consider these provide sufficient evidence to draw wider conclusions on collision risk for other projects.
11 | F18 & F21 | The Applicant should revise the nocturnal activity factors for Sandwich tern, common tern and little gull to reflect Natural England’s advised nocturnal activity factor (NAF), in addition to, referring to and applying the nocturnal activity factor set out in Garthe and Hüppop (2004) or present empirical evidence to inform an alternative rate. |  | Issue progressed. See Appendix F1. Collision risk modelling for the area excluding the ORBA uses the NAFs as set out in Garthe and Hüppop (2004). Common tern, little gull and migratory collision risk modelling should also be rerun for the revised array area excluding the ORBA. Issue resolution is subject to the approval of the ORBA and subsequent updates to the original documents. |  | No change.
12 | F19 | The productivity and average mortality rates presented in this table for some species (particularly great black-backed gull, common tern, razorbill and puffin) are different than the updated rates provided by Natural England to all Round 4 developers. We request the Applicant updates their assessment with the updated figures shared in March 2024 moving forward. |  | Issue addressed.The ORBA Environmental Report [PD1-081] is updated with the productivity and average mortaility rates both the ORBA and pre-ORBA impacts. Issue resolution is subject to acceptance of the ORBA and requested updates to the original ES application. |  | No change.
13 | F20 | The Applicant should clarify how they have arrived at the MDS for collision risk, specifically how the greatest total swept area has been calculated from the parameters presented. |  | Issue addressed in ORBA assessment. |  | No change.
14 | F22 & F1 | There is an error in the displacement matrix presented for guillemot breeding season in the higher mortality and displacement ranges. Natural England advises the Applicant reviews all matrices to ensure that they do not contain any errors. |  | Issue resolved. Please see our advice in Appendix F1. Corrections to errors and inconsistencies have been made in [AS1-064].
15 | F23, F24 & F5 | Displacement matrices should be presented using upper and lower confidence limits, as well as the mean, for each species considered in the displacement appendix, as per our Best Practice Guidelines: Environmental considerations for offshore wind and cable projects. An updated assessment should clearly state what figures are being presented within these tables/displacement matrices. |  | Issue addressed in ORBA assessment. Please see our advice in Appendix F1. The Applicant has presented displacement matrices for upper and lower confidence limits, as well as the means, of abundance values, as requested in Natural England’s Relevant Reps. Issue resolution is subject to clarification of the status of the ORBA and subsequent updates to the original documents. |  | No change.
16 | F25 | For the Population Viability Analysis, the Applicant has stated that the recommended number of years for burn-in has been included for all species except lesser black-backed gull. Natural England advises the a justification for the inclusion of no burn-in for lesser black-backed gull is provided. |  | No change. See Appendix F1. |  | No change.
17 | F26 | A full log of input and outputs of the Population Viability Analysis (PVA) (Annex A) was not provided within the relevant Appendix. Natural England requests access to Annex A, including missing input and outputs of PVA. |  | No change. Natural England has not reviewed the PVA Annex A subsequently provided by the Applicant (AS-002] as these do not reflect the proposed ORBA. |  | No change.
18 | F28 & F44 | In addition to embedded mitigation related to the following of the Best Practice Protocol for minimising disturbance from vessel traffic to sensitive species including red-throated diver and common scoter, it may also be appropriate to condition a formal seasonal restriction on construction of the ECC and ORCPs during the sensitive over-wintering period. Intertidal restrictions for common scoter may require consideration . |  | No change. |  | No change.
19 | F29 & F45, F4 | It is unclear whether the array boundary refinements have gone as far as is practically and reasonably possible to reduce the interaction with Auk species in the array area. If not, further consideration should be given to reducing this overlap given the significant numbers present and the likelihood of connectivity to FFC SPA. |  | Issue progressed but not resolved. See Natural England's advice in the cover letter and Appendix F1. |  | No change.
20 | F30 & F1 | There are multiple errors across the submitted documents. The Applicant should provide updated/corrected documents so that we can advise on the scale and significance of impact and the appropriateness of compensatory measures. |  | Issue resolved. Please see our advice in Appendix F1. Corrections to errors and inconsistencies have been made in [AS1-064].
21 | F31 | Natural England advises full consideration should be given to the potential for displacement and disturbance to red throated diver within the Greater Wash SPA during the O&M phase as a result of vessel movements and the permanent presence of the ORCPs within the SPA. Alternative locations for the ORCP outside the SPA should be considered. |  | Issue progressed but not resolved. Irrespective of the status of the ORBA, please see our advice in Appendix F1. |  | No change.
22 | F33 & F34 | It is not clear what reference population has been used for guillemot at Flamborough & Filey Coast SPA. Natural England advises the Applicant presents a table with the reference populations used for each species at each SPA in the HRA, noting that these should be counts from year(s) closest to the years of baseline data collection. Please also revise any calculations of impacts using the correct reference populations. |  | Issue addressed in ORBA assessment. Please see our advice in Appendix F1. While we are unable to see these corrections have been made in [AS1-064], these are evident in the ORBA ornithology asessment [ PD1-091]. Issue resolution is subject to clarification of the status of the ORBA within the Examination. |  | No change.
23 | F35, F46 & F1 | The calculations of baseline mortality for guillemot at FFC SPA appear incorrect. Natural England advises the Applicant corrects the errors in these calculations of % increase in baseline mortality for guillemot, and check calculations for all species-SPA combinations. |  | Issue progressed but not resolved. Corrections to errors and inconsistencies have been made in [AS1-064]. Natural England will provded further update on these calculations at Deadline as we continue our review of the ORBA ornithology asessment [PD1-081 and PD1-091]. |  | No change.
24 | F36, F2, F3 | The RIAA should presents the complete outputs, including full displacement matrices, for Natural England’s apportioning approach to individual SPAs and also adults. Natural England’s advised approach to apportioning during the breeding season for guillemot and razorbill is to assume 100% adult-type birds are breeding adults, and to apportion 100% of these individuals to FFC SPA. A separate season with bespoke apportioning for each species in August and September should be assessed |  | Issue progressed. See Appendix F1. The Applicant has presented assessment outputs based on NE’s advised apportioning approach within the new ORBA documents. Natural England will review and comment in full on these docs at Deadline 2. Issue resolution is subject to the approval of the ORBA and subsequent updates to the original documents. |  | No change.
25 | F37, F2 & F3 | Natural England advises the Applicant provides further detail on how site-specific adult proportions for kittiwake and gannet have been calculated from the Digital Arial Survey (DAS) data including what months have been included and how the proportions are calculated. |  | Issue progressed. See Appendix F1. As presented in [PD-081], the assessment using DAS data for calculating adult apportioning should be updated by using the methods utilised by Morgan. Issue resolution is subject to clarification of the status of the ORBA and subsequent updates to the original documents. |  | No change.
26 | F38, F46, F1, F2 & F3 | The breeding season apportioning table in Annex A (Table 12) are missing the values in the ‘resulting weight for SPA’ and ‘proportional weight of SPA’ columns. It is therefore not possible to determine how the Applicant has calculated their apportioning values using the NatureScot apportioning tool. Natural England advises the Applicant corrects Table 12. |  | Issue addressed. In [PD1-092] the Applicant has updated the breeding season apportioning table in Annex A . Issue resolution is subject to clarification of the status of the ORBA and subsequent updates to the appropriate original documents.
27 | F39 | The results from Wakefield et al (2017) and Cleasby et al. (2018) does not include any information on the distributions of birds in April and cannot be used to draw inference about the potential importance of areas of the North Sea to guillemot outside of the breeding season. Natural England advises removing this paragraph, or amending this paragraph to better reflect the data limitations. |  | See Appendix F1. Natural England wish to reiterate our position that April should be considered as part of the breeding season for guillemot as defined by Furness 2015, Rather than a prolonged debate it would be more beneficial to focus the Applicant’s and our efforts on addressing them. |  | No change.
28 | F41 | Natural England has concerns over the accuracy of the alone assessment. Further we do not agree that lesser black backed gull at Alde-Ore Estuary SPA and Sandwich tern at NNC SPA can be screened out of the in-combination assessment. Small impacts need to be carried through to an in-combination assessment. The Applicant should update their assessment of the ‘alone’ impacts . The SPA features identified (and others in a similar situation) should be subject to in-combination assessment once the issues with the submitted impact assessment are rectified. |  | No change. See Appendix F1. |  | No change.
29 | F42 | Values used in the in-combination assessment for other English North Sea projects entering examination 2024/25 are likely to be subject to change through their respective Examinations. Natural England recommends the Applicant contacts the relevant developers to agree how updated values based on SNCB advice are shared and disseminated across their Examinations, to ensure the in-combination assessment is updated in a streamlined way. |  | No change. See Appendix F1. |  | No change.

## G - Offshore Orni Compensation
Point | Ref from Appendix G [RR-045] | Taken from Natural England’s Relevant and Written Representations ODOW Appendix G - Offshore Ornithology Compensation [RR-045] | RAG Status Rel and Wri Rep | Consultation, actions, progression | RAG Status D1 | Consultation, actions, progression | RAG Status D2 | Consultation, actions, progression | RAG Status D3 | Consultation, actions, progression | RAG Status D4 | Consultation, actions, progression | RAG Status D5 | Consultation, actions, progression | RAG Status D6
1 | Overall confidence in the measure | It is uncertain how the predator measures for guillemot and razorbill at Plemont will demonstrably compensate for impacts to the colony at the FFC SPA as connectivity will be very difficult to evidence. Further work to increase the evidence base and feasibility of these measures is required. |  | No change. |  | No change.
2 | Theoretical merit to deliver compensation | It is uncertain whether the removal or control of rats and other mammalian predators will lead to colonisation of guillemot and/or an increase in the number of successfully breeding razorbill. The potential reasons for the loss/decline of guillemot and razorbill breeding on Jersey should be investigated. A more detailed analysis of the potential nesting habitat for these species that is currently accessible to rats and other predators is needed to understand the potential scale of benefits. |  | No change. |  | No change.
3 | Technical feasibility & Uncertainties/ effectiveness and 7.7.5.1 (Section 8 and Table 14) and 7.5.5 Section 6.2.2 | Technical feasibility relates to the ability of the guillemot and razorbill Plemont proposal to exclude predators on an ongoing basis. It is unclear whether the recommendations for a fully-costed fence operational plan, eradication plan and biosecurity plan, have been undertaken. A more detailed assessment is required of the potential risks of intertidal incursions and any mitigation measures. Experts should be consulted on plans for all stages of the proposed measure. |  | No change. |  | No change.
4 | Agreed compensation level and scale/extent of measure | The Applicant should provide updated/corrected documents using Natural England’s approach to calculating impacts, using the upper 95% CI and at a ratio of greater than 1:1 to account for the high degree of uncertainty associated with this measure so advice can be provided. |  | No change. |  | No change.
5 | Timing: Deliverable before impact & Uncertainties: Lead in-time. 7.5.5, Table 5.1 | The Applicant has proposed a lead-in time of less than 2 years prior to impacts occurring for implementing the Plemont guillemot and razorbill predator control compensation measure. This does not provide sufficient confidence that the compensation would be delivering prior to impact occurring. The Applicant should consider the need for a longer lead in time to account for the uncertainty around how long it will take before benefits are accrued. |  | No change. |  | No change.
6 | Location of measure | Natural England has concerns around the feasibility of undertaking sustained predator control for guillemot and razorbill at this chosen Plemont site due to the issues outlined above for ‘Technical feasibility’. The documents do not assess the implications with regards to risk of reinvasion, maintenance of the fence and potential conflicts with members of the public. This matter should be clarified along with progress in securing landowner leases. |  | No change. |  | No change.
7 | Long term implementation | The need for ongoing predator control measures and maintenance of the predator fence throughout the Plemont project lifetime should be sufficiently considered when costing up the measure and finalising the Compensation Implementation and Monitoring Plan for both guillemot and razorbill. |  | No change. |  | No change.
8 | Recruitment into the National Site Network | Evidence provided suggests c.50% of guillemot and 80% of razorbill will disperse away from their natal colony, and thus a number of birds fledged from Plemont Seabird Reserve have the potential to recruit into the FFC SPA breeding population or to other sites within the National Site Network. This has not been accounted for in the Applicant’s calculations of the scale of compensation that will be delivered by the predator control measure, he proportion of birds likely to recruit into the National Site Network needs to be considered when calculating the scale of compensation required |  | No change. |  | No change.
9 | Suitable as sole measure for target species | At this stage, it is unclear to what degree the Plemont predator control measure can contribute to a package of measures. The Applicant should provides updated/corrected documents at the earliest opportunity so that further advice on the suitability of this compensatory measure can be provided. |  | No change. |  | No change.
10 | Overall confidence in the measure | The additional southwest England additional measures (disturbance reduction, habitat management and potentially additional predator control) are potentially acceptable as a secondary compensation measure for Auks. Significant additional work is required to improve understanding and develop site specific evidence to allow this to contribute, with confidence, to the compensation package. |  | No change. |  | No change.
11 | Theoretical merit to deliver compensation and technical feasibility. | It will be unlikely to be able to evidence that any reduction in pressure at the southwest colonies is actually resulting in an increase in abundance/productivity. Therefore, success will likely have to be based on the reduction in pressure only. |  | No change. |  | No change.
12 | Technical feasibility | Substantial investigation is required to determine the current level of disturbance impacting guillemot and razorbill at each of the short-listed sites in southwest England. This can then be used to determine the baseline against which the effectiveness of the proposed measures can be assessed. |  | No change. |  | No change.
13 | Agreed compensation level & Scale/extent | The Applicant should update the Examination with the findings of any southwest England site-specific studies in summer 2024 so that the likely scale of benefits can be adequately established. |  | No change. |  | No change.
14 | Timing: Deliverable before impact | A longer lead in time than one year is needed for the guillemot and razorbill southwest England additional measures to account for the uncertainty around how long it will take before benefits are accrued. |  | No change. |  | No change.
15 | Location of measure | In-situ monitoring will be needed to determine to what degree specific pressures are acting on guillemot and razorbill at each site in the southwest, and the likely effectiveness of any potential measures to reduce these pressures. The findings of this monitoring and the implications for site selection should be submitted into the Examination as soon as possible alongside any updates regarding landowner agreements. |  | No change. |  | No change.
16 | Long term implementation | Until bespoke measure for guillemot and razorbill are developed for each southwest site, with relevant landowners and managers consulted on the appropriate delivery mechanism and any consents and approvals required, it is not possible to have full confidence that the measures can be implemented long term. Fully populated species specific Implementation and Monitoring Plans should be submitted into the examination process at the earliest opportunity. |  | No change. |  | No change.
17 | Success criteria/Ability to prove additionality. 7.5.6, Section 7 | Sufficient consideration should be given to what monitoring will be required to evidence that the southwest England guillemot and razorbill additional measures has been successful in reducing the specific pressures at each site, as well as the need to monitor the target species at a regional level. Fully populated species specific Implementation and Monitoring Plans should be submitted at the earliest opportunity. Any surveys conducted in summer 2024 should include a measure of current abundance and productivity at each colony to provide a baseline. |  | No change. |  | No change.
18 | Suitable as sole measure for target species | To be able to advise on the suitability to which the southwest England additional compensatory measure can contribute to a package of measures, updated/corrected documents should be provided at the earliest opportunity. |  | No change. |  | No change.
19 | Recruitment into the National Site Network | Evidence to suggest that approximately 50% of guillemot and 80% of razorbill will disperse away from their natal colony with the potential to recruit into the FFC SPA breeding population has not been accounted for in the calculations of the scale of compensation that will be delivered by the additional guillemot and razorbill measures at colonies in the southwest. The proportion of birds likely to recruit into the National Site Network should be considered when calculating the scale of compensation required. |  | No change. |  | No change.
20 | Pressure reduction to increase productivity | Site-specific monitoring and further landowner/stakeholder engagement is required to provide confidence that the southwest sites offer pressure reduction opportunities. |  | No change. |  | No change.
21 | Overall confidence and theoretical in the measure : guillemot and razorbill | Due to existing gaps in understanding there would be associated risk relying on artificial nest structure as a compensation measure for Razorbill and Guillemot. There is merit in exploring this option, principally in the context of adaptive management. The proposed lead in times to deliver this compensation to a level where it is providing the required ecological function are unlikely to be sufficient. |  | No change. |  | No change.
22 | Technical feasibility: guillemot and razorbill | The technical feasibility for ANS for auks is an experimental, unproven measure with high degrees of uncertainty around viability, but one worth exploring, particularly as it may inform the design of future ANS for auks. |  | No change. |  | No change.
23 | 7.7.4, Section 4.2.2 & Table 4.1 | A more detailed review of ANS nesting requirements and preferences should be carried out for auks, particularly with regards to elevation and topographic complexity. |  | No change. |  | No change.
24 | 7.7.4, Table 4.1 | For ANS design, provide evidence to support the calculation of guillemot 20 pairs per nesting unit of 1m x 0.3m, or amend the calculation of pairs able to occupy each nesting unit accordingly. |  | No change. |  | No change.
25 | Scale/extent of measure: Guillemot, Razorbill and kittiwake | Natural England reiterates its previous advice to the Applicant that the provision of two structures rather than one (either for the project alone or through strategic delivery with other Round 4 Applicants) provides resilience against the possibility of a single site not being colonised, or underperforming, due to design- or location- specific issues. |  | No change. |  | No change.
26 | Timing: Deliverable before impact: Guillemot and Razorbill | The need for a longer lead in time than the three years proposed for kittiwake ANS should be considered for auks to account for the uncertainty around how long it will take before benefits are accrued, and that impacts to guillemot and razorbill are likely to begin prior to turbines being operational, during the construction of the project in 2027. |  | No change. |  | No change.
27 | Timing: Deliverable before impact: Kittiwake | At least one ANS should be in place at least 4 breeding seasons prior to operation, even if a second is in place only three breeding seasons prior. |  | No change. |  | No change.
28 | Location of measure feature: Guillemot, Razorbill and Kittiwake | Further discussions are required on any implications of the ANS on designated sites once the specific locations have been proposed. Note that this advice is provided in the context of the proposed project specific measures and does not reflect other proposed strategic solutions. |  | No change. |  | No change.
29 | Long term implementation Feature: Guillemot, Razorbill and Kittiwake | There is limited detail on the proposed monitoring, adaptive management and reporting in the event of the ANS being delivered as a project-led measure, as the Applicant has stated this will be developed post consent. Please see our overarching comment above regarding the need for more detail with the IMPs. Whilst the fine details can be agreed post-consent, the core elements of the monitoring should be specified in the IMP before then. |  | No change. |  | No change.
30 | Success criteria/Ability to prove additionality: Guillemot and Razorbill | We cannot confirm whether the stated values reflect our advice. It is not clear how success criteria/additionality will be measured in the event of the ANS being delivered as a project-led measure. It will be important to monitor productivity as well as the number of breeding pairs, which may present some challenges offshore. It will also be difficult to quantify benefits to the SPA or indeed other sites in the national site network (NSN). |  | No change. |  | No change.
31 | Success criteria/Ability to prove additionality: Kittiwake | Values for breeding pairs are presented for both the Hornsea 3 and Hornsea 4 method, albeit the starting value does not reflect Natural England’s advised approach. It is not clear how this will be measured in the event of the ANS being delivered as a project-led measure. It will be important to monitor productivity as well as the number of breeding pairs, which may present some challenges offshore. It will also be difficult to quantify benefits to the SPA or indeed other sites in the NSN. |  | No change. |  | No change.
32 | Suitable as sole measure for target species: Guillemot and Razorbill | At this stage, it is doubtful that for Auks will be suitable as a sole measure and unclear how this measure could contribute to a package of measures. The Applicant should provide updated/corrected documents at the earliest opportunity so that Natural England can provide advice on the suitability of this compensatory measure. |  | No change. |  | No change.
33 | Suitable as sole measure for target species: Kittiwake | See comment above re. scale/extent of measure. Whilst the level of impact is unclear, it is plausible that with appropriate scaling, and the potential use of two structures, this could function as a sole measure. Natural England advises the Applicant provides updated/corrected documents at the earliest opportunity so that Natural England can provide advice on the suitability of this compensatory measure. |  | No change. |  | No change.
34 | Uncertainties around effectiveness and appropriate ANS design: Guillemot and Razorbill | More information on the ANS frequency and resulting productivity is needed. The ANS design requirements for guillemot and razorbill is lacking in detail, a review of the requirements and preferences of auks is needed to inform the proposed design. A range of design parameters e.g. different sized and shaped ledges, would allow for a testing of the species’ preferences and provide resilience to the measure. |  | No change. |  | No change.
35 | Recruitment into the National Site Network: Guillemot and Razorbill | The evidence provided suggests that approximately 50% of guillemot and 80% of razorbill will disperse away from their natal colony, and thus a number of the birds fledging from offshore ANS have the potential to recruit into the FFC SPA breeding population. This has not been accounted for in the calculations of the scale of compensation that will be delivered by the measure. Natural England advises that the proportion of birds likely to recruit into the National Site Network is considered when calculating the scale of compensation required for ANS. |  | No change. |  | No change.
36 | Recruitment into the National Site Network: Kittiwake | If successful, ANS may provide kittiwake recruits into the wider population and therefore FFC SPA to some extent, although this would be challenging to predict or quantify. The proportion of birds likely to recruit into the National Site Network should be considered when calculating the scale of compensation required. |  | No change. |  | No change.
37 | General | Natural England agrees that eradication of predators including rats has been shown to lead to notable increases in productivity and population size for seabirds, but notes that this is usually in relation to islands, and that the success of this measure is substantially less proven at mainland sites. Consequently, Natural England urges caution when relying on case studies in evidencing the likely success of the proposed measure. |  | No change. |  | No change.

## H - Onshore Ecology
Point | Ref from Appendix H [RR-045] | Taken from Natural England’s Relevant and Written Representations ODOW Appendix H - Onshore Ecology [RR-045] | RAG Status Rel and Wri Rep - Jun-24 | Consultation, actions, progression | RAG Status D1 | Consultation, actions, progression | RAG Status D3 | Consultation, actions, progression | RAG Status D3 | Consultation, actions, progression | RAG Status D4 | Consultation, actions, progression | RAG Status D5 | Consultation, actions, progression | RAG Status D6
1 | H16, H17, H50 & H1 | Natural England advises using a precautionary 200m buffer for assessment of construction dust impacts to nationally and internationally designated sites. This assessment should be used to inform appropriate mitigation for designated sites from construction dust, presented in the Code of Construction Practice (CoCP) Outline Air Quality Management Plan (OAQMP) [APP-270] and secured in the DCO. |  | No change. |  | No change.
2 | H19 | The assessment of impacts on designated sites with geological features of interest has only been scoped in for the construction phase of the project. Further clarity should be included regarding the absence of impacts during the operation and maintenance phase, during cable repair and during decommissioning phase so that this can be reviewed. |  | No change. |  | No change.
3 | H21 & H8 | Ground investigation works should be undertaken at landfall especially given the sink holes and requirement for extra cable protection that occurred during the installation of Triton Knoll. Lessons learnt from Triton Knoll must be considered and preconstruction ground investigations secured via inclusion within the outline CoCP or Works Plans to avoid unforeseen direct or indirect impacts to Chapel Point to Wolla Bank SSSI. |  | No change. |  | No change.
4 | H22 | Mitigation measures for detailed construction plans in areas of potentially high sensitivity, appropriate pollution management controls to maintain the integrity of the area and plans to mark out the site boundary in areas where the project is near designated sites, to avoid or reduce disturbance from construction activities should be set out within the outline CoCP, secured by DCO Requirement 18 and included within pollution management plans |  | No change. |  | No change.
5 | H25, H27 &H7 | The only potential pathway between the Project and Sea Bank Clay Pits SSSI is if the clay pits encountered the sand and gravel horizon identified in nearby BGS logs and that horizon also extends to the HDD location. No details of suitable mitigation for this effect, should it occur, have been identified further than ‘changing the method of working’ or ‘providing a replacement water supply’. Natural England advises that details of these backup mitigation measures are agreed with the LPA/MMO in consultation with NE prior to construction and that this is secured in the CoCP prior to consent. |  | Progressed. Please see our Deadline 1 Appendix H1 response. |  | No change.
6 | H26, H27 &H7 | The commitment to the monitoring of Sea Bank Clay Pits SSSI during construction to avoid dewatering must be secured within the DCO via the appropriate named plan. |  | Issue progressed See Appendix H1. The Water Quality Management and Mitigation Plan (WQMMP) within the CoCP [PD1-039] commits to mitigation and monitoring at Sea Bank Clay Pits SSSI. The CoCP is secured within the DCO. However further details is required in the CoCP. |  | No change.
7 | H28 & H2 | Natural England advises Sea Bank Clay Pits SSSI, and its designated assemblages of breeding, passage and overwintering birds are included in assessment of noise disturbance from construction, construction traffic and decommissioning. |  | No change. |  | No change.
8 | H29 & H2 | The Impact Risk Zones (IRZs) should be used to flag any sections of the Project that have potential to disturb the designated features of nationally designated sites from construction, construction traffic and decommissioning noise pollution. This includes functionally land. Project and species specific data should be used to refine impacts assessments and inform mitigation measures. |  | No change. |  | No change.
9 | H30, H31 & H2 | The designated bird features of The Wash SSSI, SPA and Ramsar impacted by noise pollution, i.e. listed breeding and non-breeding birds, and assemblages of breeding and non-breeding birds, have not been specifically identified and assessed. The designated features of sites should be included in assessment for their unique and impacts from noise pollution from construction, construction traffic and decommissioning. This should include any FLL. |  | No change. Refer to Onshore Ornithology Tab I. |  | No change.
10 | H32, H40. H49, & H3 | A generic threshold based on the minimum compliance thresholds identified in the ABC Method (British Standard 5228:2009+A1:2014) has been used to assess disturbance from construction noise for all ecological NSRs at designated sites and within any land that is considered functionally linked to designated sites. The Applicant should identify thresholds appropriate to each receptor. Ensure the thresholds are considered in the wider spatial and temporal context. |  | No change. |  | No change.
11 | H33, H40 & H3 | Natural England requests that the construction and operational noise impact magnitudes be reviewed in line with our comments on the use of the minimum compliance ABC Method. Review the construction noise impact magnitude in terms of impacts based on thresholds of the designated features of designated ecological sites, i.e. the listed birds and mammals in their relevant spatial and temporal contexts. |  | No change. |  | No change.
12 | H34, H41 &H4 | The Applicant should collect characterisation data to ensure impacts from noise pollution can be adequately modelled and assessed for the designated features of the Sea Bank Clay Pits SSSI sensitive to noise i.e. the breeding, wintering, and passage bird assemblages.. |  | No change. |  | No change.
13 | H35, H42 & H4 | The assessment of noise impacts from construction activities along the ECC to The Wash SSSI, SPA and Ramsar does not adequately assess the ecological noise sensitive receptors (NSRs) at these designated ecological sites, the Applicant should collect baseline characterisation data at the designated sites and FLL to ensure impacts from noise pollution can be adequately modelled and assessed for the designated features of the SSSI, SPA and Ramsar sensitive to noise. |  | No change. Also Refer to Tab I for any update. |  | No change.
14 | H36, H42 & H5 | Reference should be made within the Noise and Vibration Management Plan (NVMP) [APP-269] to the targeted nature of mitigation measures for potentially impacted interest features of designated sites based on collected evidence in the EIA. The NVMP should ensure noise pollution is monitored during construction and decommissioning phases at the sensitive ecological receptor sites with appropriate mitigation implemented to manage noise pollution impacts to these receptors. |  | No change. Also Refer to Tab I for any update. |  | No change.
15 | H37, H42, H47, H51 & H5 | Depending on the survey data, noise mitigation measures are likely to be required in certain locations from September through to the end of April. The Applicant should use robust baseline data and protected sites IRZ to establish appropriate mitigation buffers around FLL in addition to that already proposed and ensure that any seasonal restriction is fit purpose. The Applicant will need to ensure the identified mitigation is included in an appropriate Management Plan, such as NVMP. |  | No change. Also Refer to Tab I for any update. |  | No change.
16 | H38 &H42 | The Applicant should ensure pre-construction baseline data is collected at the designated sites and associated FLL, and appropriate methodology is applied to adequately assess impacts to the designated features of the sites. Appropriate mitigation should be identified during the consented phase and included within the NVMP. This will need to be agreed upon with the Local Planning Authority (LPA) in consultation with NE prior to construction. |  | No change. Also Refer to Tab I for any update. |  | No change.
17 | H39 | Modelling is provided at the consenting phase to demonstrate that the stand-off distances imposed for the LAeq, 1-hour limit are adequate at mitigating activities within the LAmax limit at designated sites and any functionally linked land. |  | No change. |  | No change.
18 | H44 & H6 | Sea Bank Clay Pits SSSI and its features should be included as sensitive ecological receptors in the final Pollution Prevention and Emergency Incident Response Plan (PPEIRP) risk assessment with regards to the use of drilling fluid. We would expect to see a specific bentonite ‘frack-out’ management plan. |  | No change. |  | No change.
19 | H45 | Natural England advises that they like to see the Viking Carbon Capture and Storage pipeline and National Grid Grimsby to Walpole project are included for consideration of in-combination effects. Natural England advises the two named projects are considered within the HRA in combination assessment. |  | Progressed. The Applicant has advised that Viking Carbon Capture and Storage Pipeline is included in the RIAA addendum [PD1-096]. National Grid to Walpole remains as not scoped in. |  | No change.
20 | H46 | No mitigation is discussed in relation to construction dust and its impacts on designated sites. Natural England advises mitigation for construction dust is included within the embedded mitigation of the HRA. |  | No change. |  | No change.
21 | H48 | Within the HRA, there is no indication that the nationally and internationally designated sites have been assessed using the Impact Risk Zones (IRZs) available on Defra’s Magic Maps in the mitigation assessment. This includes important areas of FLL, which have not been assessed along the ECC. Ensures areas of FLL outside the 400m buffer and within the IRZ for Goose and Swan FLL are assessed for construction disturbance. |  | No change. Also Refer to Tab I for any update. |  | No change.
22 | H52, H56, H14 & H15 | Natural England has not yet received a draft licence application for bat species in order for us to provide a Letter of No Impediment (LoNI). The OLEMS document states that currently a EPS licence for bat species is not considered necessary. While Natural England acknowledge that the mitigation hierarchy has been used to avoid impacts. Natural England advises early engagement with NEWLS. |  | Progressed . As Natural England understands, the Applicants been in communication with NEWLS, Applicant doesn't consider a bat licence is required due to mitigation they are suggesting. Please see our Deadline 1 Appendix H1 response. |  | No change.
23 | H53 & H15 | It is noted that alterations to the redline boundary occurred after the completion of bat surveys to inform the baseline data set. Any areas not surveyed which have habitat suitable for roosting, foraging or are integral to connectivity, and that will be directly impacted by works need to have the appropriate level of surveys undertaken before conclusions on impacts and licence requirements can be made. |  | No change. |  | No change.
24 | H54 | Pre-construction tree climbing inspections are required on any trees identified via Ground Level Assessment (GLAs) as having moderate -high Potential Roosting Features (PFR’s) where there are direct impacts such as removal, structural works or likely subjected to disturbance that may impact roosting bat behaviour. This will need to be secured as part of the DCO and/or named plan. |  | Issue addresed. Natural England notes this is included within the updated OLEMS [AS1-103]
25 | H55 | Consider aggregations of Nathusius's pipistrelle in late summer/early autumn and whether any surrounding features might constitute a feature of importance. Ensure that linear features which could be impacted by works or high potential features of importance (surveyed via remote detectors and with call registrations recorded) are included within a mitigation strategy. Proposed mitigation should be presented within the OLEMS . |  | Progressed. Please see our Deadline 1 Appendix H1 response. |  | No change.
26 | H57 & H14 | Pre-construction surveys for badger should include detailed territorial analysis to ensure correct placement of any artificial badger sett(s) required as mitigation. Bait marking is considered the best method for conducting territorial analysis. This requirement should be included within the OLEMS. |  | No change. Please see our Deadline 1 Appendix H1 response. Natural England would welcome further discussion over the licencing mitigation approach for badger. |  | No change.
27 | H58 | Construction of artificial badger setts must be complete prior to the exclusion works and there should be evidence that the badgers have found the sett. Evidence could be gained from a variety of monitoring techniques. Attractive bait such as peanuts as well as bedding can be used to assist the badgers locate the artificial sett. Construction recommendations should be followed and mitigation secured in the OLEMS. |  | No change. Please see our Deadline 1 Appendix H1 response. Natural England would welcome further discussion over the licencing mitigation approach for badger. |  | No change.
28 | H59, H14 & H15 | The approach to mitigation (where setts cannot be avoided) will need to be undertake pre-commencement/preconstruction surveys to determine if a badger sett will be affected by the proposed construction and then apply for a licence. There is however no guarantee that Natural England will issue a licence and a draft species licence should be submitted prior to consent for a LoNI to be issued to provide the ExA and the decision maker the necessary level of comfort appropriate issues relating to badger species are addressed. |  | No change. Please see our Deadline 1 Appendix H1 response. Natural England would welcome further discussion over the licencing mitigation approach for badger. |  | No change.
29 | H60, H61, H62. H14 & H15 | For Great Crested Newts (GCN) it is recommended that guidance available from NEWLS is followed if a draft Letter of No Impediment (LONI )is sought. Ideally surveys involve Habitat Suitability Index appraisal and eDNA survey of ponds within the red line boundary and surrounding 250m.Where data gaps exist follow up surveys should be planned if/when access can be agreed |  | Natural England has issued a GCN LONI. The GCN mitigation should be in accordance with the LONI.
30 | H63 | Further pre-construction survey effort to confirm presence or absence of widespread and common reptiles should be undertaken The approach would be in line with t Natural England’s Standing Advice for Reptiles. This will need to be secured in the DCO/OLEMS and final mitigation design agreed with the LPA in consultation with NE. |  | Ressolved. The Applicant has updated the OLEMS according to Natural England's Standing Advice.
31 | H64, H14 &H15 | The OLEMS states that there may be a requirement to apply for an EPS mitigation licence should it not be possible to avoid disturbance impacts to otters. A draft species licence should be submitted prior to consent for a LoNI to be issued to provide the ExA and the decision maker the necessary level of comfort that Natural England, as the statutory licensing authority, has considered appropriate issues relating to otter. |  | No change. Please see our Deadline 1 Appendix H1 response. Natural England would welcome further discussion over the licencing mitigation approach for otter. |  | No change.
32 | H65 | The OLEMS document states that where impacts water vole cannot be avoided and where the CL31 licence cannot be used then either a separate displacement licence or trapping licence will be applied for. A draft species licence should be submitted prior to consent for a LoNI to be issued to provide the ExA and the decision maker the necessary level of comfort that Natural England, as the statutory licensing authority, has considered appropriate issues relating to water vole |  | Natural England has issued a water vole LONI. Mitigation for water vole should be in accordance with the LONI.
33 | H66 | We encourage developers to develop BNG proposals in adherence with well-established BNG principles: BS 8683:2021 Process for designing and implementing Biodiversity Net Gain, CIEEM/IEMA/CIRIA good practice principles (2016) and guidance (2019). Use the Defra biodiversity metric to calculate BNG and adhere to the rules and principles set out within the metric guidance. Biodiversity gains should be secured for a minimum of 30 years and be subject to adaptive management and monitoring. BNG plans should be secured by a suitably worded requirement in the DCO. |  | Please refer to our Deadline 1 Appendix H1 response. Subject to BNG being secured within the DCO, Natural England will not engage further within examination.
34 | H67 | Natural England highlights that decision makers are responsible for ensuring that they have sufficient detailed agricultural land classification (ALC) information to apply National Planning Policy Framework (NPPF) policies for NSIP applications. Natural England advises NPPF paragraph 181 and Footnote 62 is included and given further consideration. |  | No change. |  | No change.
35 | H69 & H9 | Post 1988 ALC data in the vicinity should be considered for broader context and to strengthen the assessments. |  | Progressed. The Applicant has clarified that there are no parcels of land with post 1988 ALC data in the vicinity. Further update will be provided at Deadline 2. |  | No change.
36 | H70, H71, H72, H77 & H10 | A detailed assessment of the Agricultural Land Classification (ALC) or soil function testing along the order limits to inform the route selection and the Outline Soil Management Plan (SMP) [APP-271] and Outline Code of Construction Practice was not provided. There is a requirement to identify areas of deep peat and peaty soils in the area and show how the project avoids impacting best most versatile (BMV) land. Update the ES to present further site specific information on detailed and semi detailed ALC and soil function surveys. This is required to assist the decision maker and apply the NPS (EN-3). |  | No change. Please see our Deadline 1 Appendix H2 response. |  | No change.
37 | H73, H76 & H13 | Provide a firm commitment to decommission the site after 35 years (or sooner if no longer operational), to remove all infrastructure and equipment and to return the land to its original condition and ALC grade. As part of this there should be a commitment to prepare and submit to the LPA a decommissioning plan to restore the site prior to the end of its operational use, as set out by NPS EN3. |  | No change. |  | No change.
38 | H74 | Reconsider the criteria within Table 25.21. Natural England advises using a rating of Very High to rate receptor sensitivity for soils. This is to inform placement of permanent infrastructure on lower grade land. This requirement will need to be secured as mitigation measure within the DCO and/or Soil management plan. |  | No change. |  | No change.
39 | H75 & H10 | An ALC survey should be undertaken at the route of trench line for the underground cabling and the proposed substation location. Use the data to inform the soil handling and restoration plans and the SMP. Surveys should be conducted prior to consent being granted in line with NPS for Renewables Energy Infrastructure (EN-3). |  | No change. Please see our Deadline 1 Appendix H2 response. |  | No change.
40 | H78 | The Applicant should commit to reviewing the use of surplus topsoil early in the process. A full understanding of the soil profile at donor and receptor sites is necessary. We advise that it is unlikely that the movement of Grade 1 soil will upgrade the recipient land. |  | No change. |  | No change.
41 | H79 | The ALC system is a national system, therefore the significance should also be determined in the national context. However cumulative impacts should consider all development that will result in or could lead to a loss of 20ha BMV soils. |  | No change. |  | No change.
42 | H80 | Provide further justification as to why agricultural productivity should not be assessed cumulatively for each project phase. |  | No change. |  | No change.
43 | H81 | The Planning Inspectorate’s advice note 17 should be considered alongside the IEMA guidelines “A New Perspective on Land and Soils in EIA” (February 2022) methodology for cumulative effects and the application updated accordingly. |  | No change. |  | No change.
44 | H82 | There are significant gaps in the figures presented in Para 6.1.25 [APP-080] and Table 25.27. The Applicant should ensures all other projects in the area are considered for cumulative BMV loss. |  | No change. |  | No change.
45 | H83 & H12 | All agreed measures in the Outline SMP [APP-271] should be secured by appropriate requirement within the DCO via the SMP. |  | Issue progressed. In our Deadline 2 DCO update, Natural England will confirm the Outline SMP is secured within the DCO. |  | No change.
46 | H84 & H10 | There should also be a commitment for BMV agricultural land temporarily required for the development to be returned to its original ALC grade. This includes areas such as field scale ecological mitigation areas and borrow pits where reinstatement to the physical characteristics of ‘best and most versatile’ quality may also be required. |  | No change. |  | No change.
47 | H85 | Given the very high quality of the land soil handling should include supervision by a competent soil specialist. This should be secured in the OLEMS and SMP [APP-271]. |  | No further advice is provided on this issue |  | No change.
48 | H86 & H11 | Construction work should be avoided during October to March inclusive. A field suitable method for assessing whether soils are in a dry and friable condition based on plastic limits is set out in Part One (Explanatory Note 4 – Table 4.2] of the Institute of Quarrying’s Good Practice Guide for Handling Soils in Mineral Working. This approach together with the associated rainfall protocols should be adopted and noted within the SMP [APP-271]. |  | No change. |  | No change.
49 | H89 & H12 | Machinery to be used should accord with best practice as set out in the Code of Construction Practice for the Sustainable Use of Soils on Construction Sites (DEFRA, 2009) and be outlined for a full assessment of impacts within the Outline SMP [APP-271]. |  | No change. |  | No change.
50 | H90 & H12 | The details of soil handling should be included within a Restoration Plan, accompanied by a detailed soil balance. The Outline SMP [APP-271] should note that topsoil and subsoil are to be stored separately. |  | No change. |  | No change.
51 | H91 & H12 | A commitment should be added to the SMP [APP-271] avoid mowing and stripping in wet conditions. |  | No change. |  | No change.
52 | H92 & H12 | the Outline SMP [APP-271] should include a measure to ensure the depth of decompaction reflects the depth of compaction and reference the guidance used. Where compaction is likely to take place further consideration should be given to providing a decompaction strategy to maximise the effectiveness of decompaction methods. |  | No change. |  | No change.
53 | H93 & H12 | Further information on the parameters to be used for restoration specifications of soil profiles should be provided. Details should include the target soil profiles to be reinstated and their pre development ALC grade where appropriate as determined by detailed ALC survey. |  | No change. |  | No change.
54 | H94 | For any ancient or veteran trees impacted by the Project, Natural England’s standing advice should be referred to and commitments to mitigate impacts included within the OLEMS. |  | No change. |  | No change.
55 | H96 | Natural England advises the Public Access management Plan (PAMP) is secured by an appropriate requirement within the DCO, with an Outline PAMP provided into examination. |  | No Change. Natural England advises this plan is secured within the DCO. |  | No change.
56 | New Issue D1 | Ensure all desingated sites are included within the Land Quality Assessment [AS1-059], and inform the HRA, where required |  | Please see our Deadline 1 Appendix H1 response |  | No change.

## I - Onshore Ornithology
Point | Ref from Appendix I [RR-045] | Taken from Natural England’s Relevant and Written Representations ODOW Appendix I - Onshore Ornithology [RR-045] | RAG Status Rel and Wri Rep - Jun-24 | Consultation, actions, progression | RAG Status D1 | Consultation, actions, progression | RAG Status D2 | Consultation, actions, progression | RAG Status D3 | Consultation, actions, progression | RAG Status D4 | Consultation, actions, progression | RAG Status D5 | Consultation, actions, progression | RAG Status D6
1 | I7, I15 & I1 | The Applicant should present the review and analysis of two complete years of survey data within their conclusions before Natural England can form a position on the proposed impacts of the development. |  | Issue resolved within AS1-108 Response to S51 advice - 13.2 Addendum wintering bird survey 2023/24. Please see our Deadline 1 Appendix I1.
2 | I8, I9 & I2 | Much greater detail of data and discussion on potential cropping management practices should be presented for functionally linked land (FLL) including temporal and spatial extent of cropping patterns of every arable field where foraging range of species of interest overlap with the order limits and suitable buffer. |  | Issue resolved within PD1-093 15.11 Additional clarifications relating to Natural England's Relevant Representations (Appendix I Onshore Ornithology). Please see our Deadline 1 Appendix I1.
3 | I10 & I11 | The method for assessing potential noise disturbance responses of designated species focuses on minimum compliance thresholds rather than specific species disturbance responses. The Applicant has not assessed whether land already established as functionally linked for designated overwintering bird species would also be within the decibel levels exceedance threshold. The Applicant should assess the disturbance response of each designated bird species specifically. Please see Tab H for our advice. |  | No change. Cross reference to Tab H for any update. |  | No change.
4 | I13 | Further evidence is required to demonstrate that trenchless crossing would be successful in each of the proposed locations. And, where sufficient confidence in the success of the measures cannot be established, alternative mitigation measures are presented. |  | No change. Natural England notes the Applicants response in [PD1-107]. No commitment has been made by the Applicant to seek alternative mitigation if trenchless techniques are not appropriate. |  | No change.
5 | I14 & I3 | A separate outline overwintering Annex I bird species mitigation management plan (including pink-footed geese) document should be submitted into examination to be agreed as part of the consent and secured within the DCO. This should include the additional information on the project’s current mitigation strategy as well as further measures to mitigate impacts to Annex I bird species using functionally linked land. |  | No change. |  | No change.
6 | I16 & I5 | The proposal for minimising temporary loss of functionally linked land through reinstatement of topsoil and cover crop requires further detail. Greater detail should be provided on reinstatement methods employed to mitigate temporary loss of land functionally linked to designated sites. |  | No change. Natural England notes the Applicants response in [PD1-107]. |  | No change.
7 | I17, I1 & I3 | Natural England is currently unable to provide our position on the impact assessment conclusion of No AEoI for the impacts of temporary habitat loss and disturbance to land functionally linked to designated populations of pink-footed geese. Two years of overwintering bird survey data are required to provide a robust baseline against which to assess project impacts. The Applicant should adopt suitable measures to reduce their impact and mitigations measures secured within a separate specific Annex I bird species mitigation management plan submitted into examination. |  | Progressed. Whilst the 2nd year of bird data has been provided Natural England has identified risks which require further mitigation. Please see our Deadline 1 Appendix I1 response |  | No change.
8 | I18 | The proposed additional mitigation measures to reduce the potential noise disturbance at the landfall location suggests construction of the mitigation bund in March, August, or September. Natural England advises that March is also avoided as this month overlaps with known presence of designated passage and overwintering bird species. |  | Natural England will provide further advice on updated Schedule of mitigation and AS1-096 at Deadline 2. |  | No change. We will provide further advice at Deadline 3 to take into account any changes in project design parameters.
9 | I19 | The Applicant should ensure that two years of characterisation survey data are used at the time of consent to ensure the greatest likelihood of preferred brent geese habitat within the ECC are under mitigation measures. A pre-construction survey should be undertaken to ensure that the mitigation measures remain fit for purpose. This should be secured in the In Principle Monitoring Plan. |  | Progressed. Please see our Deadline 1 response Appendix I1. Natural England welcomes the additional mitigation measures for dark-bellied brent geese. However, Natural England's advises further comments are made. |  | No change.
10 | I20 | In light of the comments above on mitigation, please amend the 8.13 Schedule of Mitigation [APP-287] document to address our advice. |  | Natural England will provide further advice on updated Schedule of mitigation at Deadline 2 |  | No change.
11 | I21 | Further site specific evidence on suitable alternative foraging habitat for dark bellied brent geese should be presented to corroborate the conclusions of No AEOI . The reassessment of the pink-footed geese impact pathway by utilising two years of data is required for a robust conclusion to be drawn. Upon inclusion of these data into the impact assessment, additional mitigation proposals may be required. |  | Progressed. Natural England will provide further advice on updated Schedule of mitigation at Deadline 2 |  | No change.
12 | I22 | Conclusions on temporary habitat loss considered no AEOI for Lapwing due to the <40% of arable fields which are being subject to temporary habitat loss. Natural England notes that this is based upon one year of survey data (peak flock count of 400). The Applicant should demonstrate that these conclusions remain valid considering the second year data which shows much higher abundances of this species identified along the onshore ECC route. |  | Progressed. Please see our Deadline 1 response Appendix I1. |  | No change.
13 | I23 | The conclusion of No AEoI from the impact of temporary habitat loss utilises a summary of “generally 50% or less” of arable fields, where golden plover were identified in the first year survey, would be subject to temporary habitat loss. Considering the second year of baseline characterisation data which shows a general trend of greater abundances of individuals within flocks compared to the first year, Natural England advises that this conclusion is reviewed and justified with a full baseline characterisation data set. |  | Progressed. Please see our Deadline 1 response Appendix I1. |  | No change.
14 | I24 | The conclusion on temporary habitat loss for curlew relies on the same evidence as those drawn for lapwing. Advice and recommendation on lapwing above is also relevant to populations of curlew. |  | Progressed. Please see our Deadline 1 response Appendix I1. |  | No change.
15 | I25 & I5 | The project has adopted mitigation in the form of localised working and reinstatement programmes to reduce impacts of disturbance and temporary habitat loss on land functionally linked to features of protected sites, in particular The Wash SPA and Ramsar. These measures have been applied at a high level across the ECC without considering specific designated species distribution patterns, species specific disturbance distances and preferred foraging habitat distribution within the route. Further information on the mitigation measures in the context of these important factors should be included. |  | Progressed. Please see our Deadline 1 response Appendix I1. |  | No change.
16 | I26 | The conclusion of No AEoI from temporary disturbance due to construction activity to populations of golden plover, which are designated interest features of the Humber Estuary SPA, The Wash Ramsar and part of The Wash SPA assemblage, is based upon 1 year of survey data. Assessment of impact should be based upon two years of baseline characterisation data and set against population trends of the species and the conservation objectives of the sites where they are designated. |  | Progressed. Please see our Deadline 1 response Appendix I1. |  | No change.
17 | I27 | A conclusion of No AEoI for the impact of temporary disturbance to populations of designated pink-footed geese using FLL is reliant on one year of baseline characterisation data and the availability of alternative foraging habitat. To have confidence in the impact conclusion, Natural England needs to understand the abundance and distribution from 2 years of baseline characterisation data. The Applicant should demonstrate how much of this land could be subject to temporary disturbance within the foraging range and subsequently whether an impact would require mitigating. |  | Progressed. Please see our Deadline 1 response Appendix I1. |  | No change.
18 |  | There is disagreement between Natural England and Applicant on the impact assessment for Dark Bellied Brent Geese, Pink Footed Goose, Lapwing, Curlew and Golden Plover. Additional focus will need to be on mitigation measures |  | New issue identified at Deadline 1, see Appendix I1. |  | No change.