Tween Bridge Solar Farm

- EN010148

RWE Renewables UK Solar and Storage Limited

Section 51 Advice Log

Version: 21/07/2025

There is a statutory duty under section 51 (s51) of the Planning Act 2008 for the Planning Inspectorate to record the advice that it gives in relation to an application or potential application, and to make this publicly available.

This document comprises a record of the advice that has been provided by the Inspectorate to the applicant (RWE Renewables UK Solar and Storage Limited) and their consultants during the pre-application stage. It will be updated by the Inspectorate after every interaction with the applicant during which s51 has been provided. The applicant will always be given the opportunity to comment on the Inspectorate’s draft record of advice before it is published.

The applicant will use this Advice Log as the basis for demonstrating regard to section 51 advice within the application.

| Project name s51 Advice Log - Index |  |
| --- | --- |
| Date of meeting | Meeting overview |
| 24/01/2025 | Project Update Meeting: - Order Limits - Layout - National Grid Substation - Project programme / timeline - Issues tracker - Commitments register - PINS pre-application advice service - Document review and feedback timescales - Schedule of meetings |
| 15/05/2025 | Project Update Meeting - Project updates - Update on statutory consultation and responses - Adequacy of Consultation and Programme Document - Submission update - Extended pre-examination stage |
| 03/07/2025 | Adequacy of Consultation Milestone (AoCM) Document |

| Project name -s51 Advice Library |  |
| --- | --- |
| Topic | Meeting date: 24 January 2025 |
| Proposed landscape and ecological mitigation and enhancement areas | In answer to questions from the Inspectorate, the Applicant said that discussions had been held with Natural England (NE) regarding the ecological assessment and the required extent of the ecological mitigation areas. Other species had been identified since non-statutory consultation requiring assessment. Noting the location of the proposed development relative to European sites, the Inspectorate advised the Applicant about the importance of working towards agreement with NE and other relevant bodies on the scope and extent of the baseline bird surveys and the required extent of the ecological mitigation areas before submission of the Development Consent Order (DCO) application, to help ensure a more efficient Examination. |
| Environmental Impact Assessment | The Applicant confirmed that the Environmental Statement would assess the worst-case scenario, including for the two cable route options connecting to the new substations if both options remain at the point of DCO application. The Applicant was also referred to the Inspectorate’s new Advice on the Commitments Register, which it was taking into account. The Applicant also stated that they are now using an Issues Tracker to record the level of risk and progress on a number of topics for the proposed development. |
| Archaeology | The Applicant explained that it was making effort to discuss and agree the approach to archaeological assessment with relevant consultation bodies including the local authority. The Inspectorate advised the Applicant to provide a robust justification for its approach, supported by reference to guidance where possible. Where there are any areas of disagreement, the Applicant should clearly explain its position in relevant application documents and why it considers its approach to be adequate. |
| Cumulative Effects | The Inspectorate advised the Applicant to review other solar projects in Lincolnshire as to how cumulative effects have been examined and the types of questions asked by Examining Authorities (see the Rule 6 and Recommendation Report for Gate Burton NSIP, as an example). For instance, waste management at the decommissioning stage had been an issue contested in examination and the extent to whether applicants had appropriate and deliverable measures and waste management plans in place. Additionally, the effects of Electromagnetic Fields (EMF) on fish from cables crossing watercourses was also an issue in contention in some solar project examinations (including Cottam, Gate Burton and West Burton). |
| Pre-application Service | In answer to questions asked by the Applicant, the Inspectorate advised that a limited number of Adequacy of Consultation Milestone (AOCM) had been received and reviewed under its new pre-application service at this stage, with comments published on its website. The Inspectorate advised the applicant to look at its comments on AOCM reports for Botley West and Beacon Fen for an idea of the type of issues being raised by the Inspectorate in its feedback. On the issue of draft document reviews, the Inspectorate advised that it was still taking approximately six weeks to review draft documents and pointed to Dean Moor Solar and Peartree Solar as examples of where recent feedback had been provided. The Inspectorate advised that typical draft documents submitted for review include the draft DCO and Explanatory Memorandum, draft Work Plans and Land Plans, the draft Consultation Report, the draft Environmental Statement project description chapter and draft Habitats Regulations Assessment (HRA) Report. A full list is provided in its 2024 Pre-application Prospectus. Noting the location of the proposed development relative to European sites, the Inspectorate advised that the documents submitted for review include the draft HRA Report. The ‘standard’ pre-application service also includes a draft document feedback review meeting with the Applicant, in addition to its written comments, where requested. The Inspectorate also advised that applicants would need to provide at least 3 months-notice if requesting to change its pre-application service tier. The likelihood and timing of this would be expected to be identified in the associated pre-application Programme Document. A draft document review is not part of the ‘basic’ tier. In respect of future Project Update Meetings and any draft document review feedback meeting, the Applicant was asked to provide indicative dates as soon as practicable, along with the timing of submitting draft documents, to ensure the Inspectorate had appropriate resources available. These meeting dates should also be reflected in the Applicant’s updated Programme Document. The applicant supplied the Inspectorate with its initial Programme Document in July 2024, in line with the Inspectorate’s Expression of Interest process. |
| Programme Document | Having reviewed the document, the Inspectorate considers overall that it covers the expected content as set out in the government’s pre-application guidance at paragraph 10, namely setting out the expected programme timescales clearly, including a good description of the development and the main issues and risks involved, its engagement strategy with the host authorities and statutory bodies, and other related information on its pre-application activities. However, in updating its Programme Document, the applicant should: - include whether the Programme Document has been shared with relevant local authorities, statutory consultees and others and whether they were content with the proposed programme; - include dates for any Evidence Plan activities and/or multiparty meetings (if applicable to the project); - a date for the Adequacy of Consultation Milestone, which should be set three months before the submission of the application; - include information about any other consents or licences being sought (if applicable to the project); - whether an Issues Tracker will be used (see the Inspectorate’s 2024 Pre-application Prospectus and the ‘Primary service features’ section for details); and - cross reference to the SoCC, as outlined in guidance. Though the risks identified by the Applicant has been included, it would be helpful to know the process by which these risks will be tracked and managed. It would also be helpful if the applicant could provide any information on its approach to design, and its progress with agreeing Planning Performance Agreements with host authorities and the procurement of discretionary services from relevant, chargeable statutory bodies (including where such authorities have agreed approaches to any mitigation). The Programme Document will need to be published and maintained on the applicant’s website (as soon as practicable) and updated throughout the pre-application stage, as needed. |
| Topic | Meeting date: 15 May 2025 |
| Project update | The applicant advised the recent changes in Government Policy, the Clean Power Action Plan (CP30), and National Grid reforms have brought forward the date the application needs to be submitted to July 2025. The applicant explained that the non-statutory consultation was accompanied by a draft Preliminary Environmental Information Report (PEIR) with a finalised version supplied at statutory consultation stage, demonstrating that they had adequately consulted on the proposals and the application is at an advanced state of completion. |
| Statutory Consultation and environmental surveys | The applicant provided an overview of changes to the proposed development’s red line boundary following consultation, to reduce possible impacts on some nearby residential dwellings and to increase the level of mitigation elsewhere. The Inspectorate asked about the level of detail provided by the applicant to consultees during statutory consultation, pointing out the need for a sufficient level of detail required for consultees to be able to provide informed feedback. The applicant provided assurance that a good level of detail about the proposed development had been provided in the PEIR and via additional printed material at venues to support the in-person events. The applicant stated that the main areas of feedback or concern from consultees concerned design, the need for solar, loss of agricultural land, visual impact, property values, cumulative effects, and issues surrounding community benefits. These matters, and the regard had to them, will be detailed in the applicant’s Consultation Report. The Inspectorate enquired about the general position of NE regarding potential effects on birds from the proposed development, along with the methodology and extent of surveys undertaken and proposed mitigation measures. The applicant stated that NE is content with the bird survey methodology. The applicant confirmed that engagement was ongoing through the use of NE’s discretionary advice service and that it was currently reviewing NE’s comments on species specific surveys. The Inspectorate sought clarification on ongoing environmental surveys and if they were to be completed before submission. The applicant confirms that all ecology surveys necessary to complete a robust ES will be done prior to submission. Following the meeting, the applicant has advised that some surveys including bats, great crested newts and water vole, will be finished following the formal submission in July 2025 and will be issued to the Inspectorate for the relevant consultees to consider during the pre-examination period. Post meeting note: The applicant should clearly set out in the application documents the dates for the submission of any outstanding survey information and how that would correspond to the overall timescales for pre-examination/ examination. The applicant is advised to provide a robust justification for its approach in the relevant application documents. The application documents should also explain the intended approach if any new features are found to be present that weren’t present in earlier surveys. The applicant is advised to present with the application evidence of agreement with relevant consultation bodies on the level of baseline data to be available at the point of DCO application. |
| Adequacy of Consultation and Programme Document | The Inspectorate asked why the Programme Document was not published on the applicant’s website. The applicant replied that no Programme Document had been used on this project to date, and that they would be writing to stakeholders at the end of May 2025 to inform them of the intended application submission date. The applicant stated that it would be providing the same or similar information contained in the Programme Document to relevant consultees, so they would not be prejudiced by its absence. The applicant also confirmed that the project timeline/milestones were updated on the project website throughout the pre-application stage. The Inspectorate advised that applicants are encouraged to produce a Programme Document at the outset and to make this available to parties online (in line with the government’s guidance on the pre-application stage at paragraph 10, which sets out the expected content of Programme Documents). The applicant was advised to provide reasons if choosing to depart from statutory guidance for any reason, or any s51 advice provided by the Inspectorate, when it submits its application (such as in the application’s cover letter). The Inspectorate outlined that part of its section 55 checklist for checking an application’s compliance with legislation, policy and guidance, includes checking whether an applicant has had regard to statutory guidance (see box 24 for further information). Additionally, the Inspectorate agreed with the applicant that it could submit its Adequacy of Consultation Milestone statement in June 2025, less than 3 months before the submission of the application (as outlined in government guidance). This owes to the recent local elections and the need to allow time for the new Council administration to provide comments on the applicant’s consultation. It is the Inspectorate’s preference to receive the statement with any views from relevant councils, in one document. |
| Submission update | The applicant confirmed the target for submitting the application for acceptance is currently 18 July 2025. The applicant confirmed that it would not be seeking to supply the Inspectorate with draft documents for review, owing to the truncated timeframe for submitting the application. |
| Potential pre-examination and examination timeline | The applicant stated the need to engage with consultees further during pre-examination as there may be issues still to agree with statutory consultees. The applicant’s intention is to not rush consultees and start the examination with agreed Statements of Common Ground. The Inspectorate advised that it would be useful for it and consultees to understand the rationale behind the applicant’s proposal for a five month extended pre-examination period. The applicant confirmed that it will be creating a potential main issues for examination document as part of its application. In answer to a question from the Inspectorate, the applicant confirmed that it had used an informal Issues Tracker for the project team to monitor progress. Identified ‘issues’ were set out in the PEIR which was consulted on in the statutory consultation. The Issues Tracker (as a primary service feature of the new pre-application process) has not been shared with the Inspectorate. The applicant was instead looking to use the Issues Tracker to underpin its potential main issues for examination document. The Inspectorate asked whether the applicant considered HRA was likely to be a main issue for the examination. The applicant confirmed that it will respond on this point in due course and noted that this will depend on the advice received from NE. The applicant updated PINS following the meeting to advise that the HRA is likely to be one of the main issues for the examination, by virtue of the site’s location in close proximity to Special Protection Areas (SPAs) and size of the site. |
| Protective Provisions | The Inspectorate enquired about protected provisions and whether any draft DCO provisions had been shared with relevant statutory undertakers. The applicant confirmed that advanced conversations had been held with the Canal and River Trust and Network Rail, as well as National Highways and others. Negotiations on protected provisions will be ongoing upon submission. |
| Grid connection | The Inspectorate asked for an update about the grid connection with National Grid. The applicant explained that there was an interdependency between CP30 and the timing of the new substation but that it would not know the precise location of the new substation until August 2025 (until National Grid has undertaken its site selection process and has advanced its application for the substation under the Town and Country Planning Act 1990). However, the applicant explained that it has undertaken a worst-case scenario assessment and has consulted upon a zone where the new substation is likely to be located. The Inspectorate advised that a Statement of Common Ground about the new substation between the applicant and National Grid could be requested by the Examining Authority during examination (should the application be accepted for examination) and to review other such requests being made in examinations where the same issue is arising. |
| Pre-submission letter | The Inspectorate informed the applicant of the pre-submission letter to be issued, including information on file sharing and the need to supply an updated GIS shapefile at least 10 working days before submission. |
| Topic | Meeting date: 3 July 2025 |
| Adequacy of Consultation Milestone (AoCM) Document | The applicant’s Adequacy of Consultation Milestone (AOCM) statement has been prepared and submitted to the Planning Inspectorate two weeks ahead of their proposed application submission date. |