## Status
Beacon Fen Energy Park: Detailed Land and Rights Negotiations Tracker
Notes:
1. All interests which are not already acquired at the point of submission should be entered in this tracker and marked as complete (column 'w') when agreement with known interests is reached
2. Any non-agreement is also counted as an objection by an affected person(s) for the purpose of this tracker
3. An entry should also be made where the interest (or potential interest) holder is not known, to allow the relevant information to be added following diligent inquiry, negotiation etc
4. An editable version of this tracker must be submitted to The Planning Inspectorate with the application as an appendix to the Statement of Reasons
Affected Person | Agent / representative 1 | Book of Reference plot number 2 | Plan reference number 3 | Description of land and rights requested 4 | Duration of temporary rights 5 | Category 1 6 |  |  | Category 2 7 | When available Interested party / affected person reference number 8 | When available Relevant representation reference number 9 | When available Written representation reference number 10 | Other document reference number 11 | Applicant's response references 12 | Special category (Crown, allotment, National Trust etc) (Select from drop down list) | Special category - other information including confirmation of status 13 | Is the affected person a statutory undertaker and is the land operational? (Select from drop down list) | Protective provision status (Select from drop down list) | Side agreements (Select from drop down list) | Status of objection 14 | Heads of Terms (Select from drop down list) | Complete (Select from drop down list) | Last Updated [DD/MM/YYYY] | Likelihood of resolution during the Examination
[6 empty] | Owners | Lessees or tenants | Occupiers
Status of Negotiations with Individual Landowners
Andrea Jane Beard | Monet Johnson – Brown & Co | 1–4 | Land Plans (AS-005) Sheet 1 | CAR | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In May 2023, the Applicant met with the Affected Person to introduce the Proposed Development. In November 2023 and February 2024, the Applicant met with the Affected Person and their Agent to discuss the Proposed Development and provisional land requirements. In December 2023, the Applicant’s Land Agent (Ardent) engaged with the Affected Person regarding a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. In March 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent met with the Affected Person’s Agent via Teams to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. In August 2025, the Applicant met with the Affected Person and their Agent to discuss the terms of a voluntary agreement, engagement is ongoing. Constructive engagement has continued between the Applicant and the Affected Person's Agent, and the latest correspondence was on the 16th October 2025. | Draft under discussion | No | 2025-10-20 | Agreement expected to be reached during Examination
Andrew Greetham | N/A | 8–3 | Land Plans (AS-005) Sheet 8 | CAR | N/A | No | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the freeholder of Plot 8-3 to introduce the Proposed Development and in relation to survey access. The Affected Person granted access in October 2023. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In March 2025, Ardent wrote to the Affected Person inviting them to take part in the Additional Consultation which took place between the 6th March and 3rd April 2025. The Affected Person is an occupier of Plot 8-3. This occupation is proposed to be dealt with through an agreement with the freeholder. The proposed agreement specifies that the land will be delivered with vacant possession and as such there have been no direct negotiations with the Affected Person at this stage. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. In August 2025, the Applicant agreed Heads of Terms with the freeholder of Plot 8-3. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Not required | Yes | 2025-09-09 | Agreement with freeholder complete
Andrew Richard Booth | Sam Booth – Hub Rural | 17–6 | Land Plans (AS-005) Sheet 17 | TP | Approximately 12 - 24 months | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in April 2023. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. A licence was signed and returned in January 2024. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In August 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-09-09 | Agreement complete
|  | 17–1 | Land Plans (AS-005) Sheet 17 | CAR | N/A | No | Yes | Yes | N/A
Ann Firth | Daniel Jobe – Brown & Co | 18–1, 18–9 | Land Plans (AS-005) Sheet 18 | CAR | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In July 2023, Ardent wrote to the Affected Person with an update on the proposed route for the grid connection. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent met with the Affected Person’s Agent on two occasions to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In July 2025, Ardent met with the Affected Person and their Agent to discuss the terms of the proposed agreement in more detail. Ardent anticipates that Heads of Terms will be agreed during Examination. Constructive engagement has continued between Ardent and the Affected Person's Agent, and the latest correspondence was on the 20th October 2025. | Draft under discussion | No | 2025-10-20 | Agreement expected to be reached during Examination
|  | 18–10 | Land Plans (AS-005) Sheet 18 | CAR | N/A | No | No | Yes | N/A
Bicker United Charity | Will Barker – Will Barker & Co | 17–2, 17–4 | Land Plans (AS-005) Sheet 17 | CAR | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In January 2025, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and to provide detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent wrote to the Affected Person inviting them to take part in the Additional Consultation which took place between the 6th March and 3rd April 2025. In March 2025, Ardent met with the Affected Person’s Agent on two occasions to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. Heads of Terms are agreed and the Applicant is awaiting a signed copy from the Affected Person's Agent. | Draft under discussion | No | 2025-10-20 | Agreement expected to be reached during Examination
Christopher Godson | Josh Pollock – Pollock Associates | 4–2, 4–3, 4–4, 4–6 | Land Plans (AS-005) Sheet 4 | CAR | N/A | No | Yes | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in May 2023. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. A licence was signed and returned in January 2024. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In March 2024, Ardent met with the Affected Person to discuss the Proposed Development, land requirements and other matters relating to a voluntary agreement. In April 2024, the Applicant and Ardent met with the Affected Person and their Agent to discuss the Proposed Development and provisional land requirements. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In January and March 2025, Ardent met with the Affected Person and their Agent to discuss the Heads of Terms and to provide more information on the proposed Bespoke Access Road. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. In August 2025, the Applicant received signed Heads of Terms from the Affected Person. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-09-09 | Agreement complete
|  | 3–8 | Land Plans (AS-005) Sheet 3 | CAL | N/A | No | No | Yes | N/A
Church Commissioners For England | N/A | 1–2 | Land Plans (AS-005) Sheet 1 | CAR | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In December 2024, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and to invite them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. The Affected Person has a mines and minerals freehold interest in Plot 1-2. The new access rights that the Applicant is seeking will not interfere with the Affected Person’s interest and as such no direct negotiations or agreement is required. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. | Not required | Yes | 2025-09-09 | Agreement not required
David George Banham | N/A | 18–5 | Land Plans (AS-005) Sheet 18 | CAR | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in April 2023. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. The Affected Person has a freehold interest in Plot 18-5, however, this plot has been adopted by the council and forms part of the public highway. The new access rights that the Applicant is seeking will not interfere with the Affected Person’s interest and as such no direct negotiations or agreement is required. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. | Not required | Yes | 2025-09-09 | Agreement not required
Dr. Michael John Elliott | Will Barker – Will Barker & Co | 9–3, 9–5, 9–6, 9–7, 9–8, 9–10, 10–2, 10–3 | Land Plans (AS-005) Sheets 9 and 10 | CAR | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In July 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in October 2023. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in February 2024. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. A licence was signed and returned in February 2024. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent met with the Affected Person’s Agent on two occasions to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In August 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-09-09 | Agreement complete
|  | 9–4 | Land Plans (AS-005) Sheet 9 | TP | Approximately 12 - 24 months | Yes | No | No | N/A
E.A. Dring (Farms) Limited | N/A | 5–2 | Land Plans (AS-005) Sheet 5 | CAR | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In December 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. The Affected Person has a mines and minerals freehold interest in Plot 5-2. The new rights that the Applicant is seeking will not interfere with the Affected Person’s interest and as such no direct negotiations or agreement is required. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. | Not required | Yes | 2025-09-09 | Agreement not required
F. Casswell (Farms) Limited | Joanna Knight – 360 Rural | 8–4, 8–5, 8–9, 9–1 | Land Plans (AS-005) Sheets 8 and 9 | CAR | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In July 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in August 2023. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in December 2023. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. A licence was signed and returned in January 2024. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent met with the Affected Person’s Agent on two occasions to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In August 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-09-09 | Agreement complete
Frances Doris Mountain as trustee of the M C M Pension Scheme | Richard Start – Longstaff | 10–5 | Land Plans (AS-005) Sheet 10 | CAR | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In July 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in August 2023. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in January 2024. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. A licence was signed and returned in January 2024. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent met with the Affected Person’s Agent on two occasions to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In October 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-10-20 | Agreement complete
|  | 10–7 | Land Plans (AS-005) Sheet 10 | TP | Approximately 12 - 24 months | Yes | No | No | N/A
George Pykett | Robert Watkins – Graham Watkins & Co | 18–35 | Land Plans (AS-005) Sheet 18 | CAR | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in August 2023. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In August 2023, Ardent wrote to the Affected Person with an update on the proposed route for the grid connection. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in December 2023. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. A licence was signed and returned in January 2024. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. In August 2025, the Applicant received signed Heads of Terms from the Affected Person. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-09-09 | Agreement complete
Gerard Amaury Arnaud March Phillipps De Lisle | Romina Llorente – Savills | 9–12, 14–2, 14–3, 14–4, 14–5, 14–6, 14–7, 14–8, 14–9 | Land Plans (AS-005) Sheets 9 and 14 | CAR | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In January 2025, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and to provide detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent wrote to the Affected Person inviting them to take part in the Additional Consultation which took place between the 6th March and 3rd April 2025. In March 2025, Ardent met with the Affected Person’s Agent to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In August 2025, Ardent had a phone call with the Affected Person's Agent and understands that the Heads of Terms are broadly agreed and that signed terms are likley to be returned in the next couple of months. In September and October 2025, Ardent requested updates on the status of the Heads of Terms from the Affected Person's Agent. | Draft under discussion | No | 2025-10-20 | Agreement expected to be reached during Examination
|  | 13–11, 13–12, 13–14, 13–16, 13–17, 14–1, 15–2, 15–3, 15–4 | Land Plans (AS-005) Sheets 13, 14 and 15 | CAR | N/A | No | No | Yes | N/A
Harry Needham | Will Barker – Will Barker & Co | 10–10, 10–13, 11–1 | Land Plans (AS-005) Sheets 10 and 11 | CAR | N/A | No | Yes | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In January 2024, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and to invite them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. In October 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-10-20 | Agreement complete
Ivanovic & Company Limited | Jonathan Stiff - Cheffins | 1–2 | Land Plans (AS-005) Sheet 1 | CAR | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In December 2024, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and to invite them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. In August 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-09-09 | Agreement complete
J. N. Booth & Sons | Sam Booth – Hub Rural | 18–35 | Land Plans (AS-005) Sheet 18 | CAR | N/A | No | Yes | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In December 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to intrusive survey works. A licence was signed and returned in January 2024. In January 2024, the Applicant’s Land Agent (Ardent) wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. The Affected Person is an agricultural tenant of Plot 18-35. The tenancy is proposed to be dealt with through an agreement with the freeholders. The proposed agreement specifies that the land will be delivered with vacant possession and as such there have been no direct negotiations with the Affected Person at this stage. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. In August 2025, the Applicant agreed Heads of Terms with the freeholders of Plot 18-35. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Not required | Yes | 2025-09-09 | Agreement with freeholders complete
James Northgrave Booth | Sam Booth – Hub Rural | 17–6 | Land Plans (AS-005) Sheet 17 | TP | Approximately 12 - 24 months | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in April 2023. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. A licence was signed and returned in January 2024. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In August 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-09-09 | Agreement complete
|  | 17–1, 17–2 | Land Plans (AS-005) Sheet 17 | CAR | N/A | No | Yes | Yes | N/A
John Cope | Daniel Jobe – Brown & Co | 9–9, 9–11, 11–8 | Land Plans (AS-005) Sheets 9 and 11 | CAR | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In August 2023, Ardent wrote to the Affected Person with an update on the proposed route for the grid connection. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in December 2023. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In July 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-09-09 | Agreement complete
John Grant (Donington) | Robbie Longstaff – Longstaff | 18–6, 18–52, 18–56 | Land Plans (AS-005) Sheet 18 | CAR | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in October 2023. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In July 2023, Ardent wrote to the Affected Person with an update on the proposed route for the grid connection. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in December 2023. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent met with the Affected Person’s Agent on two occasions to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In August 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-09-09 | Agreement complete
|  | 15–3 | Land Plans (AS-005) Sheet 15 | CAR | N/A | No | Yes | Yes | N/A
|  | 13–11, 13–12, 13–14, 13–16, 13–17, 14–1, 15–2, 15–4 | Land Plans (AS-005) Sheets 13, 14 and 15 | CAR | N/A | No | No | Yes | N/A
John Grant (Donington) Pension Scheme | Robbie Longstaff – Longstaff | 15–3 | Land Plans (AS-005) Sheet 15 | CAR | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In December 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in December 2023. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent met with the Affected Person’s Agent on two occasions to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In August 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-09-09 | Agreement complete
John Needham as trustee of the Percy Needham Trust | George Harrison – Robert-Bell | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | In July 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in September 2023. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in December 2023. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. A licence was signed and returned in December 2023. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. The Applicant has been informed that the Affected Person is recently deceased and therefore no longer a trustee of the Percy Needham Trust. In September 2025, the Applicant recieved signed Heads of Terms from the remaining Trustees' Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Not required | Yes | 2025-10-20 | Agreement not required
John Nicholas Benjamin | Daniel Jobe – Brown & Co | 18–44 | Land Plans (AS-005) Sheet 18 | CAR | N/A | No | Yes | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In November 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. In September 2025, Ardent met with the Affected Person and their Agent to discuss the terms of the proposed agreement in more detail. Ardent anticipates that Heads of Terms will be agreed with the freeholder during Examination. Constructive engagement has continued between Ardent and the Affected Person's Agent, and a meeting between the parties was held on the 20th October 2025. | Not required | No | 2025-10-20 | Agreement with freeholder expected to be reached during Examination
John Philip Stanley | Daniel Jobe – Brown & Co | 18–48 | Land Plans (AS-005) Sheet 18 | CAR | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In July 2023, Ardent wrote to the Affected Person with an update on the proposed route for the grid connection. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent met with the Affected Person’s Agent on two occasions to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In September 2025, Ardent met with the Affected Person and their Agent to discuss the terms of the proposed agreement in more detail. Ardent anticipates that Heads of Terms will be agreed during Examination. In September 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-10-20 | Agreement complete
|  | 18–28, 18–50 | Land Plans (AS-005) Sheet 18 | CAR | N/A | No | Yes | Yes | N/A
John William Howe | Josh Pollock – Pollock Associates | 2–2 | Land Plans (AS-005) Sheet 2 | CAL | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In summer 2021, the Applicant met with the Affected Person to introduce the Proposed Development. In November 2021, the Applicant issued detailed Heads of Terms to secure the land and rights required to construct and operate the Proposed Development. In March 2022, Heads of Terms were signed and solicitors were instructed. In September 2022, the Applicant secured an Option Agreement to secure the land and rights required to construct and operate the Proposed Development. The Option Agreement has been registered at Land Registry. In October 2023, the Applicant’s Land Agent (Ardent) engaged with the Affected Person in relation to survey access. Access was granted in November 2023. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. | Agreed | Yes | 2025-09-09 | Agreement complete
L & D Flowers Limited | N/A | 10–5 | Land Plans (AS-005) Sheet 10 | CAR | N/A | No | Yes | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In January 2024, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and to invite them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. In October 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-10-20 | Agreement complete
|  | 10–7 | Land Plans (AS-005) Sheet 10 | TP | Approximately 12 - 24 months | No | Yes | Yes | N/A
L C J Mountain Farms Limited | Edward Blundy – Brown & Co | 11–3, 11–6, 12–2 | Land Plans (AS-005) Sheets 11 and 12 | CAR | N/A | Yes | No | Yes | N/A | TBC | RR–026 | REP1–043 | PDA–012, REP1–041, REP1–042 | REP1–029 (Pages 90 to 94) | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In August 2023, Ardent wrote to the Affected Person with an update on the proposed route for the grid connection. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in August 2024. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person subsequently made a relevant representation [RR-026]. In September 2025, Ardent met with the Affected Person and their Agent via Teams to discuss the terms of the proposed agreement in more detail. Revised Heads of Terms were subsequently issued to the Affected Person's Agent for review. Engagement has continued between Ardent and the Affected Person, and the latest correspondence was on the 15th October 2025. | Draft under discussion | No | 2025-10-20 | The Applicant will continue to attempt to engage with the Affected Person with the objective of securing a voluntary agreement before the close of Examination
|  | 12–7, 12–8, 12–9, 12–10, 12–11, 12–14, 12–16, 12–17, 12–18, 12–19, 13–4, 13–18 | Land Plans (AS-005) Sheets 12 and 13 | CAR | N/A | Yes | No | No | N/A
|  | 13–5 | Land Plans (AS-005) Sheet 13 | TP | Approximately 12 - 24 months | Yes | No | No | N/A
|  | 9–9, 9–11, 11–8, 12–1 | Land Plans (AS-005) Sheets 9, 11 and 12 | CAR | N/A | No | Yes | Yes | N/A
Lamb Weston UK LTD | N/A | 9–9, 9–11, 11–3, 11–6, 12–2, 12–7, 12–8, 12–9, 12–10, 12–11, 12–14, 12–16, 12–17, 12–18, 12–19, 13–4, 13–18 | Land Plans (AS-005) Sheets 9, 11, 12 and 13 | CAR | N/A | No | Yes | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In October 2024, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in November 2024. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. The Affected Person is an agricultural tenant of Plots 9-9, 9-11, 11-3, 11-6, 12-2, 12-7, 12-8, 2-9, 12-10, 12-11, 12-14, 12-16, 12-17, 12-18, 12-19, 13-4, 13-5 and 13-18. The tenancies are proposed to be dealt with through agreements with the freeholders. The proposed agreements specify that the land will be delivered with vacant possession and as such there have been no direct negotiations with the Affected Person at this stage. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. | Not required | No | 2025-09-09 | The Applicant will continue to attempt to engage with the freeholders with the objective of securing a voluntary agreement before the close of Examination
|  | 13–5 | Land Plans (AS-005) Sheet 13 | TP | Approximately 12 - 24 months | No | Yes | Yes | N/A
Leslie Christopher John Mountain | Edward Blundy – Brown & Co | 12–1 | Land Plans (AS-005) Sheet 12 | CAR | N/A | Yes | No | Yes | N/A | TBC | RR–028 | N/A | N/A | REP1–029 (Page 94) | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In August 2023, Ardent wrote to the Affected Person with an update on the proposed route for the grid connection. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. The consultation period was subsequently extended to finish on the 17th March 2024 due to a minor amendment to the Proposed Development which impacted the Affected Person. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person subsequently made a relevant representation [RR-028]. In September 2025, Ardent met with the Affected Person's Agent via Teams to discuss the terms of the proposed agreement in more detail. Revised Heads of Terms were subsequently issued to the Affected Person's Agent for review. Engagement has continued between Ardent and the Affected Person, and the latest correspondence was on the 15th October 2025. | Draft under discussion | No | 2025-10-20 | The Applicant will continue to attempt to engage with the Affected Person with the objective of securing a voluntary agreement before the close of Examination
Lincolnshire County Council | N/A | 1–1, 2–1, 2–3, 4–1, 4–5, 5–3, 6–3, 7–1, 8–7, 10–1, 10–4, 10–6, 10–8, 10–9, 10–11, 11–4, 11–5, 12–4, 12–5, 14–10, 14–11, 16–1, 17–3, 18–2, 18–3, 18–4, 18–5, 18–8, 18–12, 18–20, 18–21, 18–22, 18–23, 18–24, 18–29, 18–36, 18–37, 18–45, 18–47 | Land Plans (AS-005) Sheets 1, 2, 4, 5, 6, 7, 8, 10, 11, 12, 14, 16, 17, 18 | CAR | N/A | Yes | No | Yes | N/A | TBC | RR–002 | REP1–046 | APP–281, AoC–004, REP1–016, REP1–017, REP1–044, REP1–045 | REP1–029 (Pages 61 to 76) | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In July 2023, Ardent wrote to the Affected Person with an update on the proposed route for the grid connection. In October 2023, Ardent engaged with the Affected Person in relation to additional survey access. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. The consultation period was subsequently extended to finish on the 17th March 2024 due to a minor amendment to the Proposed Development which impacted the Affected Person. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. The Affected Person has a freehold interest in Plot 14-10, however, this plot has been adopted and forms part of the public highway. The new access rights that the Applicant is seeking will not interfere with the Affected Person’s interest and as such no direct negotiations or agreement is required. All other freehold interests relate to the Affected Person’s interest as highway authority. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person subsequently made a relevant representation [RR-002]. | Not required | Yes | 2025-10-20 | Agreement not required
|  | 2–2 | Land Plans (AS-005) Sheet 2 | CAL | N/A | No | No | Yes | N/A
|  | 1–2, 4–2, 4–3, 4–4, 8–3, 8–4, 8–6, 9–2, 13–9 | Land Plans (AS-005) Sheets 1, 4, 8, 9 and 13 | CAR | N/A | No | No | Yes | N/A
Linda Elizabeth Ruby Banham | N/A | 18–5 | Land Plans (AS-005) Sheet 18 | CAR | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in April 2023. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. The Affected Person has a freehold interest in Plot 18-5, however, this plot has been adopted by the council and forms part of the public highway. The new access rights that the Applicant is seeking will not interfere with the Affected Person’s interest and as such no direct negotiations or agreement is required. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. | Not required | Yes | 2025-09-09 | Agreement not required
Mandy Karen Goodhand | N/A | 3–8 | Land Plans (AS-005) Sheet 3 | CAL | N/A | No | No | Yes | N/A | TBC | RR–032 | REP1–048 | N/A | REP1–029 (Pages 87 to 88) | N/A | N/A | Not SU | Not required | Not required | In December 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. The Affected Person is an occupier of Plot 3-8. The Applicant has secured an Option Agreement with the freeholder to secure the land and rights required to construct and operate the Proposed Development. The Option Agreement specifies that the land will be delivered with vacant possession and as such no direct negotiations or agreement is required. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person subsequently made a relevant representation [RR-032]. | Not required | Yes | 2025-10-20 | Agreement with freeholder complete
Margaret Betty Sardeson | Will Barker – Will Barker & Co | 5–2 | Land Plans (AS-005) Sheet 5 | CAR | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In October 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. A licence was signed and returned in December 2023. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In April 2024, the Applicant and Ardent met with the Affected Person and their Agent to discuss the Proposed Development and provisional land requirements. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In January 2025, Ardent met with the Affected Person’s Agent to discuss the Heads of Terms and to provide more information on the proposed Bespoke Access Road. In March 2025, Ardent met with the Affected Person’s Agent on two occasions to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. In August 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-09-09 | Agreement complete
Mark Alistair Sardeson | Josh Pollock – Pollock Associates | 6–2 | Land Plans (AS-005) Sheet 6 | CAL | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In summer 2021, the Applicant met with the Affected Person to introduce the Proposed Development. In November 2021, the Applicant issued detailed Heads of Terms to secure the land and rights required to construct and operate the Proposed Development. In March 2022, Heads of Terms were signed and solicitors were instructed. In September 2022, the Applicant secured an Option Agreement to secure the land and rights required to construct and operate the Proposed Development. The Option Agreement has been registered at Land Registry. In March 2023, the Applicant’s Land Agent (Ardent) engaged with the Affected Person in relation to survey access. Access was granted in April 2023. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In August and October 2023, Ardent engaged with the Affected Person in relation to additional survey access. Access was granted in August and November 2023 respectively. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in December 2023. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. A licence was signed and returned in December 2023. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. | Agreed | Yes | 2025-09-09 | Agreement complete
Martyn Eric Sharpe | Richard Start – Longstaff | 18–28 | Land Plans (AS-005) Sheet 18 | CAR | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in August 2023. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In July 2023, Ardent wrote to the Affected Person with an update on the proposed route for the grid connection. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. Feedback was provided over the phone in December 2023. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent met with the Affected Person’s Agent on two occasions to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In October 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-10-20 | Agreement complete
|  | 18–19, 18–53 | Land Plans (AS-005) Sheet 18 | CAR | N/A | No | No | Yes | N/A
Melbourne Holdings Limited | Will Barker – Will Barker & Co | 7–2 | Land Plans (AS-005) Sheet 7 | CAR | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In July 2023, Ardent wrote to the Affected Person with an update on the proposed route for the grid connection. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in February 2024. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. A licence was signed and returned in February 2024. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent met with the Affected Person’s Agent on two occasions to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. Constructive engagement has continued between Ardent and the Affected Person's Agent, and the latest correspondence was on the 13th October 2025. | Draft under discussion | No | 2025-10-20 | Agreement expected to be reached during Examination
|  | 7–3 | Land Plans (AS-005) Sheet 7 | TP | Approximately 12 - 24 months | Yes | No | Yes | N/A
Michael Charles Woods | N/A | 13–11, 13–12, 13–14, 13–16, 13–17, 14–1, 15–2, 15–3, 15–4 | Land Plans (AS-005) Sheets 13, 14 and 15 | CAR | N/A | No | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2025, the Applicant’s Land Agent (Ardent) wrote to the Affected Person inviting them to take part in the Additional Consultation which took place between the 6th March and 3rd April 2025. The Affected Person is an occupier of Plots 13-11, 13-12, 13-14, 13-16, 13-17, 14-1, 15-2, 15-3 and 15-4. This occupation is proposed to be dealt with through an agreement with the freeholder. The proposed agreement specifies that the land will be delivered with vacant possession and as such there have been no direct negotiations with the Affected Person at this stage. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. | Not required | No | 2025-09-09 | Agreement with freeholder expected to be reached during Examination
Michael George Godson | Josh Pollock – Pollock Associates | 3–8 | Land Plans (AS-005) Sheet 3 | CAL | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In November 2021, the Applicant met with the Affected Person to introduce the Proposed Development. In March 2022, Heads of Terms were signed and solicitors were instructed. In September 2022, the Applicant secured an Option Agreement to secure the land and rights required to construct and operate the Proposed Development. The Option Agreement has been registered at Land Registry. In March 2023, the Applicant’s Land Agent (Ardent) engaged with the Affected Person in relation to survey access. Access was granted. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In October 2023, Ardent engaged with the Affected Person in relation to additional survey access. This land was descoped in November 2023. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. | Agreed | Yes | 2025-09-09 | Agreement complete
Mowbray Edmund Stephens Mountain as trustee of the M C M Pension Scheme | Richard Start – Longstaff | 10–5 | Land Plans (AS-005) Sheet 10 | CAR | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In July 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in August 2023. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in January 2024. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. A licence was signed and returned in January 2024. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent met with the Affected Person’s Agent on two occasions to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In October 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-10-20 | Agreement complete
|  | 10–7 | Land Plans (AS-005) Sheet 10 | TP | Approximately 12 - 24 months | Yes | No | No | N/A
Nicholas Needham as trustee of the Percy Needham Trust | George Harrison – Robert-Bell | 10–10, 10–13, 11–1 | Land Plans (AS-005) Sheets 10 and 11 | CAR | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In July 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in September 2023. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in December 2023. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. A licence was signed and returned in December 2023. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In September 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-10-20 | Agreement complete
Nicola Jane Howe | Josh Pollock – Pollock Associates | 2–2 | Land Plans (AS-005) Sheet 2 | CAL | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In summer 2021, the Applicant met with the Affected Person to introduce the Proposed Development. In November 2021, the Applicant issued detailed Heads of Terms to secure the land and rights required to construct and operate the Proposed Development. In March 2022, Heads of Terms were signed and solicitors were instructed. In September 2022, the Applicant secured an Option Agreement to secure the land and rights required to construct and operate the Proposed Development. The Option Agreement has been registered at Land Registry. In October 2023, the Applicant’s Land Agent (Ardent) engaged with the Affected Person in relation to survey access. Access was granted in November 2023. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in January 2024. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. | Agreed | Yes | 2025-09-09 | Agreement complete
Patricia Lynn Mountain | Edward Blundy – Brown & Co | 12–1 | Land Plans (AS-005) Sheet 12 | CAR | N/A | Yes | No | Yes | N/A | TBC | RR–028 | N/A | N/A | REP1–029 (Page 94) | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In August 2023, Ardent wrote to the Affected Person with an update on the proposed route for the grid connection. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. The consultation period was subsequently extended to finish on the 17th March 2024 due to a minor amendment to the Proposed Development which impacted the Affected Person. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person subsequently submitted a relevant representation [RR-028]. In September 2025, Ardent met with the Affected Person's Agent via Teams to discuss the terms of the proposed agreement in more detail. Revised Heads of Terms were subsequently issued to the Affected Person's Agent for review. Engagement has continued between Ardent and the Affected Person, and the latest correspondence was on the 15th October 2025. | Draft under discussion | No | 2025-10-20 | The Applicant will continue to attempt to engage with the Affected Person with the objective of securing a voluntary agreement before the close of Examination
Patrick John Banham | N/A | 18–5 | Land Plans (AS-005) Sheet 18 | CAR | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in April 2023. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. The Affected Person has a freehold interest in Plot 18-5, however, this plot has been adopted by the council and forms part of the public highway. The new access rights that the Applicant is seeking will not interfere with the Affected Person’s interest and as such no direct negotiations or agreement is required. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. | Not required | Yes | 2025-09-09 | Agreement not required
Patrick Simon Benjamin | Daniel Jobe – Brown & Co | 18–44 | Land Plans (AS-005) Sheet 18 | CAR | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In November 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In February 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent met with the Affected Person’s Agent on two occasions to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In September 2025, Ardent met with the Affected Person and their Agent to discuss the terms of the proposed agreement in more detail. Ardent anticipates that Heads of Terms will be agreed during Examination. Constructive engagement has continued between Ardent and the Affected Person's Agent, and a meeting between the parties was held on the 20th October 2025. | Draft under discussion | No | 2025-10-20 | Agreement expected to be reached during Examination
Peter Andrew March Phillipps De Lisle | Romina Llorente – Savills | 9–12, 14–2, 14–3, 14–4, 14–5, 14–6, 14–7, 14–8, 14–9 | Land Plans (AS-005) Sheets 9 and 14 | CAR | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In January 2025, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and to provide detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent wrote to the Affected Person inviting them to take part in the Additional Consultation which took place between the 6th March and 3rd April 2025. In March 2025, Ardent met with the Affected Person’s Agent to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In August 2025, Ardent had a phone call with the Affected Person's Agent and understands that the Heads of Terms are broadly agreed and that signed terms are likley to be returned in the next couple of months. In September and October 2025, Ardent requested updates on the status of the Heads of Terms from the Affected Person's Agent. | Draft under discussion | No | 2025-10-20 | Agreement expected to be reached during Examination
|  | 13–11, 13–12, 13–14, 13–16, 13–17, 14–1, 15–2, 15–3, 15–4 | Land Plans (AS-005) Sheets 13, 14 and 15 | CAR | N/A | No | No | Yes | N/A
Richard Booth | Sam Booth – Hub Rural | 17–1 | Land Plans (AS-005) Sheet 17 | CAR | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In August 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in August 2023. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in December 2023. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. A licence was signed and returned in January 2024. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In August 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-09-09 | Agreement complete
|  | 17–4 | Land Plans (AS-005) Sheet 17 | CAR | N/A | No | Yes | Yes | N/A
Richard Pykett | Robert Watkins – Graham Watkins & Co | 18–35 | Land Plans (AS-005) Sheet 18 | CAR | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in August 2023. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In August 2023, Ardent wrote to the Affected Person with an update on the proposed route for the grid connection. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in December 2023. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. A licence was signed and returned in January 2024. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. In August 2025, the Applicant received signed Heads of Terms from the Affected Person. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-09-09 | Agreement complete
Robert Ezekiel Needham | George Harrison – Robert-Bell | 13–7 | Land Plans (AS-005) Sheet 13 | CAR | N/A | No | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the freeholder of Plot 13-7 to introduce the Proposed Development and in relation to survey access. The Affected Person granted access in October 2023. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. The Affected Person is an occupier of Plot 13-7. This occupation is proposed to be dealt with through an agreement with the freeholder. The proposed agreement specifies that the land will be delivered with vacant possession and as such there have been no direct negotiations with the Affected Person at this stage. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. In August 2025, the Applicant agreed Heads of Terms with the freeholder of Plot 13-7. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Not required | Yes | 2025-09-09 | Agreement with freeholder complete
Robin Firth | Daniel Jobe – Brown & Co | 18–1 | Land Plans (AS-005) Sheet 18 | CAR | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In July 2023, Ardent wrote to the Affected Person with an update on the proposed route for the grid connection. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent met with the Affected Person’s Agent on two occasions to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In July 2025, Ardent met with the Affected Person and their Agent to discuss the terms of the proposed agreement in more detail. Ardent anticipates that Heads of Terms will be agreed during Examination. Constructive engagement has continued between Ardent and the Affected Person's Agent, and the latest correspondence was on the 20th October 2025. | Draft under discussion | No | 2025-10-20 | Agreement expected to be reached during Examination
Rowanmoor Trustees Limited | Robbie Longstaff – Longstaff | 15–3 | Land Plans (AS-005) Sheet 15 | CAR | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in May 2023. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent met with the Affected Person’s Agent on two occasions to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In August 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-09-09 | Agreement complete
|  | 13–11, 13–12, 13–14, 13–16, 13–17, 14–1, 15–2, 15–4 | Land Plans (AS-005) Sheet 13, 14 and 15 | CAR | N/A | No | No | Yes | N/A
Roythornes Trustees Limited | Romina Llorente – Savills | 9–12, 14–2, 14–3, 14–4, 14–5, 14–6, 14–7, 14–8, 14–9 | Land Plans (AS-005) Sheets 9 and 14 | CAR | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In January 2025, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and to provide detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent wrote to the Affected Person inviting them to take part in the Additional Consultation which took place between the 6th March and 3rd April 2025. In March 2025, Ardent met with the Affected Person’s Agent to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In August 2025, Ardent had a phone call with the Affected Person's Agent and understands that the Heads of Terms are broadly agreed and that signed terms are likley to be returned in the next couple of months. In September and October 2025, Ardent requested updates on the status of the Heads of Terms from the Affected Person's Agent. | Draft under discussion | No | 2025-10-20 | Agreement expected to be reached during Examination
|  | 13–11, 13–12, 13–14, 13–16, 13–17, 14–1, 15–2, 15–3, 15–4 | Land Plans (AS-005) Sheets 13, 14 and 15 | CAR | N/A | No | No | Yes | N/A
Sandra Myra Adriane Sardeson | Josh Pollock – Pollock Associates | 6–2 | Land Plans (AS-005) Sheet 6 | CAL | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In summer 2021, the Applicant met with the Affected Person to introduce the Proposed Development. In November 2021, the Applicant issued detailed Heads of Terms to secure the land and rights required to construct and operate the Proposed Development. In March 2022, Heads of Terms were signed and solicitors were instructed. In September 2022, the Applicant secured an Option Agreement to secure the land and rights required to construct and operate the Proposed Development. The Option Agreement has been registered at Land Registry. In March 2023, the Applicant’s Land Agent (Ardent) engaged with the Affected Person in relation to survey access. Access was granted in April 2023. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In October 2023, Ardent engaged with the Affected Person in relation to additional survey access. Access was granted in November 2023. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in December 2023. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. | Agreed | Yes | 2025-09-09 | Agreement complete
Sarah Jane Bettinson | Daniel Jobe – Brown & Co | 18–9 | Land Plans (AS-005) Sheet 18 | CAR | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In August 2023, Ardent wrote to the Affected Person with an update on the proposed route for the grid connection. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent met with the Affected Person’s Agent on two occasions to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In July 2025, Ardent met with the Affected Person and their Agent to discuss the terms of the proposed agreement in more detail. Ardent anticipates that Heads of Terms will be agreed during Examination. Constructive engagement has continued between Ardent and the Affected Person's Agent, and the latest correspondence was on the 20th October 2025. | Draft under discussion | No | 2025-10-20 | Agreement expected to be reached during Examination
|  | 18–10 | Land Plans (AS-005) Sheet 18 | CAR | N/A | No | No | Yes | N/A
Shirley Ann Pugh | Robbie Longstaff – Longstaff | 13–10, 13–13, 15–1 | Land Plans (AS-005) Sheets 13 and 15 | CAR | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in September 2023. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In July 2023, Ardent wrote to the Affected Person with an update on the proposed route for the grid connection. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent met with the Affected Person’s Agent on two occasions to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In August 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-09-09 | Agreement complete
|  | 13–15 | Land Plans (AS-005) Sheet 13 | TP | Approximately 12 - 24 months | Yes | No | Yes | N/A
|  | 13–11, 13–12, 13–14, 13–16, 13–17, 14–1, 15–2, 15–3, 15–4 | Land Plans (AS-005) Sheets 13, 14 and 15 | CAR | N/A | No | No | Yes | N/A
Simon John Henry Still De Lisle | Romina Llorente – Savills | 9–12, 14–2, 14–3, 14–4, 14–5, 14–6, 14–7, 14–8, 14–9 | Land Plans (AS-005) Sheets 9 and 14 | CAR | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In January 2025, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and to provide detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent wrote to the Affected Person inviting them to take part in the Additional Consultation which took place between the 6th March and 3rd April 2025. In March 2025, Ardent met with the Affected Person’s Agent to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In August 2025, Ardent had a phone call with the Affected Person's Agent and understands that the Heads of Terms are broadly agreed and that signed terms are likley to be returned in the next couple of months. In September and October 2025, Ardent requested updates on the status of the Heads of Terms from the Affected Person's Agent. | Draft under discussion | No | 2025-10-20 | Agreement expected to be reached during Examination
|  | 13–11, 13–12, 13–14, 13–16, 13–17, 14–1, 15–2, 15–3, 15–4 | Land Plans (AS-005) Sheets 13, 14 and 15 | CAR | N/A | No | No | Yes | N/A
Staples Brothers Limited | Will Barker – Will Barker & Co | 9–3, 9–5, 9–6, 9–7, 9–8, 9–10, 10–2, 10–3 | Land Plans (AS-005) Sheets 9 and 10 | CAR | N/A | No | Yes | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In January 2024, the Applicant’s Land Agent (Ardent) engaged with the Affected Person regarding a Land Interest Questionnaire, as requested by their Agent. A completed Land Interest Questionnaire was returned in February 2024. The Applicant formally engaged with “G Veg limited”, company name changed advised in intrusive licence, received March 2024. In March 2025, Ardent wrote to the Affected Person inviting them to take part in the Additional Consultation which took place between the 6th March and 3rd April 2025. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. In October 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-10-20 | Agreement complete
|  | 9–4 | Land Plans (AS-005) Sheet 9 | TP | Approximately 12 - 24 months | No | Yes | Yes | N/A
Stephanie Johnson-Mansley | N/A | 3–8 | Land Plans (AS-005) Sheet 3 | CAL | N/A | No | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In December 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. The Affected Person is an occupier of Plot 3-8. The Applicant has secured an Option Agreement with the freeholder to secure the land and rights required to construct and operate the Proposed Development. The Option Agreement specifies that the land will be delivered with vacant possession and as such no direct negotiations or agreement is required. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. | Not required | Yes | 2025-09-09 | Agreement with freeholder complete
Stephen Anthony Beard | Monet Johnson – Brown & Co | 1–4 | Land Plans (AS-005) Sheet 1 | CAR | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In May 2023, the Applicant met with the Affected Person to introduce the Proposed Development. In November 2023 and February 2024, the Applicant met with the Affected Person and their Agent to discuss the Proposed Development and provisional land requirements. In December 2023, the Applicant’s Land Agent (Ardent) engaged with the Affected Person regarding a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. In March 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent met with the Affected Person’s Agent via Teams to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. In August 2025, the Applicant met with the Affected Person and their Agent to discuss the terms of a voluntary agreement, engagement is ongoing. Constructive engagement has continued between the Applicant and the Affected Person's Agent, and the latest correspondence was on the 16th October 2025. | Draft under discussion | No | 2025-10-20 | Agreement expected to be reached during Examination
The Executors of Christopher Henry Sardeson | Will Barker – Will Barker & Co | 5–1 | Land Plans (AS-005) Sheet 5 | CAR | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. A licence was signed and returned in December 2023. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In April 2024, the Applicant and Ardent met with the Affected Person and their Agent to discuss the Proposed Development and provisional land requirements. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In January 2025, Ardent met with the Affected Person’s Agent to discuss the Heads of Terms and to provide more information on the proposed Bespoke Access Road. In March 2025, Ardent met with the Affected Person’s Agent on two occasions to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. In August 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-09-09 | Agreement complete
|  | 5–2 | Land Plans (AS-005) Sheet 5 | CAR | N/A | Yes | No | No | N/A
The Lincoln Diocesan Trust And Board Of Finance Limited | Andrew Carter - Jas Martin and Co | 18–50 | Land Plans (AS-005) Sheet 18 | CAR | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In July 2023, Ardent wrote to the Affected Person with an update on the proposed route for the grid connection. In October 2023, Ardent engaged with the Affected Person in relation to additional survey access. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In March 2024, the Applicant and Ardent met via Teams with the Affected Person’s Agent to discuss the Proposed Development and provisional land requirements. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. In August 2025, Ardent was informed that Plot 18-50 was being dealt with by a seperate Agent to that of Plot 4-3. Heads of Terms have been re-issued to Jas Martin and Co and engagement is ongoing. Neogtiations are continuing between Ardent and the Affected Person's Agent, and the Applicant is currently awaiting a substantive response to the Heads of Terms. | Draft under discussion | No | 2025-10-20 | Agreement expected to be reached during Examination
| Lucie Muddiman – Savills | 4–3 | Land Plans (AS-005) Sheet 4 | CAR | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In July 2023, Ardent wrote to the Affected Person with an update on the proposed route for the grid connection. In October 2023, Ardent engaged with the Affected Person in relation to additional survey access. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In March 2024, the Applicant and Ardent met via Teams with the Affected Person’s Agent to discuss the Proposed Development and provisional land requirements. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. In July 2025, Ardent received feedback on the proposed Heads of Terms and engagement is ongoing. Constructive engagement has continued between Ardent and the Affected Person's Agent, and the latest correspondence was on the 16th October 2025. | Draft under discussion | No | 2025-10-20 | Agreement expected to be reached during Examination
The Thorpe & Asgarby Estate Limited | Elizabeth Allen – EA Land Agents | 4–2, 4–4, 4–6 | Land Plans (AS-005) Sheet 4 | CAR | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In October 2023, Ardent engaged with the Affected Person in relation to additional survey access. Access was granted. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. A licence was signed and returned in December 2023. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In April 2024, the Applicant and Ardent met with the Affected Person and their Agent to discuss the Proposed Development and provisional land requirements. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In January and March 2025, Ardent met with the Affected Person’s Agent to discuss the Heads of Terms and to provide more information on the proposed Bespoke Access Road. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. In August 2025, the Applicant received signed Heads of Terms from the Affected Person. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-09-09 | Agreement complete
The Vicarage Drove Project Limited | Richard Start – Longstaff | 17–7, 18–11 | Land Plans (AS-005) Sheets 17 and 18 | CAR | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In January 2025, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and to invite them to take part in a Targeted Consultation which took place between the 30th January and 28th February 2025. In February 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent met with the Affected Person’s Agent on two occasions to discuss the Heads of Terms and to provide more information on the Proposed Development. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. | Draft under discussion | No | 2025-09-09 | Agreement expected to be reached during Examination
Timothy James Booth | Sam Booth – Hub Rural | 17–6 | Land Plans (AS-005) Sheet 17 | TP | Approximately 12 - 24 months | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in April 2023. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. A licence was signed and returned in January 2024. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In August 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-09-09 | Agreement complete
|  | 17–1 | Land Plans (AS-005) Sheet 17 | CAR | N/A | No | Yes | Yes | N/A
Toby Morrhall | N/A | 3–8 | Land Plans (AS-005) Sheet 3 | CAL | N/A | No | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In December 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. The Affected Person is an occupier of Plot 3-8. The Applicant has secured an Option Agreement with the freeholder to secure the land and rights required to construct and operate the Proposed Development. The Option Agreement specifies that the land will be delivered with vacant possession and as such no direct negotiations or agreement is required. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. | Not required | Yes | 2025-09-09 | Agreement with freeholder complete
William Giles Burleigh Howe | Josh Pollock – Pollock Associates | 2–2 | Land Plans (AS-005) Sheet 2 | CAL | N/A | Yes | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In summer 2021, the Applicant met with the Affected Person to introduce the Proposed Development. In November 2021, the Applicant issued detailed Heads of Terms to secure the land and rights required to construct and operate the Proposed Development. In March 2022, Heads of Terms were signed and solicitors were instructed. In September 2022, the Applicant secured an Option Agreement to secure the land and rights required to construct and operate the Proposed Development. The Option Agreement has been registered at Land Registry. In October 2023, the Applicant’s Land Agent (Ardent) engaged with the Affected Person in relation to survey access. Access was granted in November 2023. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in January 2024. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. | Agreed | Yes | 2025-09-09 | Agreement complete
William Needham as trustee of the Percy Needham Trust | George Harrison – Robert-Bell | 10–10, 10–13, 11–1 | Land Plans (AS-005) Sheets 10 and 11 | CAR | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | In July 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in September 2023. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in December 2023. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. A licence was signed and returned in December 2023. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In September 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-10-20 | Agreement complete
Unknown | N/A | 1–4 | Land Plans (AS-005) Sheet 1 | CAR | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | Ardent continue to make diligent enquiries regarding the interest holder. | None drafted | No | 2025-09-09 | N/A
Unknown | N/A | 2-2 | Land Plans (AS-005) Sheet 2 | CAL | N/A | Yes | No | No | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | The interest holder has a mines and minerals interest in Plot 2-2. The Applicant has secured an Option Agreement with the freeholder to secure the land and rights required to construct and operate the Proposed Development. The Option Agreement specifies that the land will be delivered with vacant possession and as such no direct negotiations or agreement is required. Ardent continue to make diligent enquiries regarding the interest holder. | Not required | Yes | 2025-09-09 | Agreement not required
Unknown | N/A | 2-2 | Land Plans (AS-005) Sheet 2 | CAL | N/A | No | No | Yes | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | The interest holder is an occupier of Plot 2-2. The Applicant has secured an Option Agreement with the freeholder to secure the land and rights required to construct and operate the Proposed Development. The Option Agreement specifies that the land will be delivered with vacant possession and as such no direct negotiations or agreement is required. Ardent continue to make diligent enquiries regarding the interest holder. | Not required | Yes | 2025-09-09 | Agreement not required
Unknown | N/A | 12–3 | Land Plans (AS-005) Sheet 12 | CAR | N/A | Unknown | Unknown | Unknown | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | Ardent continue to make diligent enquiries regarding the unregistered land. | None drafted | No | 2025-09-09 | N/A
Unknown | N/A | 12–15 | Land Plans (AS-005) Sheet 12 | CAR | N/A | Unknown | Unknown | Unknown | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | Ardent continue to make diligent enquiries regarding the unregistered land. | None drafted | No | 2025-09-09 | N/A
Unknown | N/A | 18-10 | Land Plans (AS-005) Sheet 18 | CAR | N/A | Unknown | Unknown | Unknown | N/A | TBC | N/A | N/A | N/A | N/A | N/A | N/A | Not SU | Not required | Not required | Ardent continue to make diligent enquiries regarding the unregistered land. | None drafted | No | 2025-09-09 | N/A
Status of Negotiations with Statutory Undertakers
Anglian Water Services Limited | Pinsent Masons LLP | 2–1, 4–1, 5–2, 5–3, 8–4, 8–7, 10–1, 10–4, 11–5, 12–5, 13–7, 13–9, 16–1, 17–3, 17–4, 18–2, 18–3, 18–4, 18–8, 18–12, 18–19, 18–20, 18–36, 18–37, 18–47 | Land Plans (AS-005) Sheets 2, 4, 5, 8, 10, 11, 12, 13, 16, 17, 18 | CAR | N/A | No | No | Yes | Yes | TBC | RR–038 | N/A | APP–284 | REP1–029 (Pages 51 to 54) | N/A | N/A | SU and known operational | Draft under discussion | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. The consultation period was subsequently extended to finish on the 17th March 2024 due to a minor amendment to the Proposed Development which impacted the Affected Person. In December 2024, the Applicant’s Solicitors commenced engagement with the Affected Person in relation to agreeing a bespoke set of protective provisions. The Applicant has included a set of protective provisions for the benefit of the Affected Person in Schedule 11 to the Draft DCO (Document Ref: 3.1) whilst engagement is ongoing. The parties are close to agreement on the form of the protective provisions. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person subsequently submitted a relevant representation [RR-038]. Neogtiations are continuing between the Affected Person's solicitors and the Applicant's solicitors, and the Applicant is currently awaiting a substantive response on the latest draft of the protective provisions. | Not required | No | 2025-10-20 | Agreement expected to be reached during Examination
Bicker Fen Windfarm Limited | N/A | 18–9, 18–48 | Land Plans (AS-005) Sheet 18 | CAR | N/A | No | No | No | Yes | TBC | N/A | N/A | N/A | N/A | N/A | N/A | SU and known operational | Draft under discussion | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, the Applicant’s Solicitors commenced engagement with the Affected Person in relation to agreeing a bespoke set of protective provisions. The Applicant has included a set of protective provisions for the benefit of the Affected Person in Schedule 11 to the Draft DCO (Document Ref: 3.1) whilst engagement is ongoing. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. Discussions on the draft protective provisions are ongoing between the Affected Person's solicitors and the Applicant's solicitors. | Not required | No | 2025-09-09 | Agreement expected to be reached during Examination
Black Sluice Internal Drainage Board | Richard Start – Longstaff | 3–1 | Land Plans (AS-005) Sheet 3 | CAR | N/A | Yes | No | Yes | No | TBC | N/A | N/A | REP1–026 | N/A | N/A | N/A | SU and known operational | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in January 2024. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. Ardent are engaging with the Affected Person in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. The Draft DCO does not disapply any relevant byelaws of the Affected Person or the need to apply for ordinary watercourse consents for works in proximity to ordinary watercourses managed by the Affected Person. As such, on the 24th March 2025, the Affected Person confirmed to the Applicant that it did not require protective provisions to be included in the Draft DCO (Document Ref: 3.1). In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person's Agent is a member of a Land Interest Group, formed to negotiate voluntary agreements on behalf of the majority of landowners included in the Cable Route Corridor. Ardent has been regularly engaging with the Land Interest Group and recently agreed generic Heads of Terms. Following this, bespoke landowner specific Heads of Terms were re-issued to the Affected Person and their Agent in July 2025. In August 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-10-20 | Agreement complete
|  | 2–2 | Land Plans (AS-005) Sheet 2 | CAL | N/A | No | No | Yes | No
|  | 1–3, 1–4, 3–2, 3–3, 3–4, 3–5, 3–6, 3–7, 3–9, 7–2, 8–1, 8–3, 9–2, 10–6, 10–8, 10–9, 10–11, 10–12, 10–13, 11–2, 11–5, 12–4, 12–6, 12–12, 12–13, 13–1, 13–2, 13–3, 14–1, 16–1, 17–3, 17–5, 18–3, 18–4, 18–8, 18–9, 18–11, 18–14, 18–17, 18–20, 18–21, 18–23, 18–24, 18–29, 18–37, 18–45, 18–47, 18–48, 18–49, 18–51, 18–54, 18–55 | Land Plans (AS-005) Sheets 1, 3, 7, 8, 9, 10, 11, 12, 13, 14, 16, 17 and 18 | CAR | N/A | No | No | Yes | No
BT Limited | N/A | 2–2, 3–8, 6–2 | Land Plans (AS-005) Sheets 2, 3 and 6 | CAL | N/A | No | No | Yes | Yes | TBC | N/A | N/A | N/A | N/A | N/A | N/A | SU and known operational | Agreed and in latest version of DCO | Not required | In December 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. The consultation period was subsequently extended to finish on the 17th March 2024 due to a minor amendment to the Proposed Development which impacted the Affected Person. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. In March 2025, the Applicant’s Solicitors commenced engagement with the Affected Person in relation to discussing a bespoke set of protective provisions. The Applicant has included a set of generic protective provisions which benefit the Affected Person in Part 2 of Schedule 11 to the Draft DCO (Document Ref: 3.1). The Affected Person has not requested bespoke protective provisions. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. No further communications have been received by the Applicant from the Affected Person on the protective provisions or any other aspect of the Proposed Development. As such, the Applicant's working assumption is that the protective provisions in the Draft DCO are agreed. | Not required | Yes | 2025-09-09 | Agreement complete
|  | 5–2, 5–3, 7–1, 8–7, 10–1, 10–4, 10–6, 10–8, 10–9, 10–11, 11–4, 11–5, 12–4, 12–5, 13–12, 14–1, 14–6, 14–9, 15–1, 15–2, 15–3, 15–4, 16–1, 17–3, 18–2, 18–3, 18–4, 18–7, 18–8, 18–12, 18–13, 18–14, 18–16, 18–17, 18–19 | Land Plans (AS-005) Sheets 5, 7, 8, 10, 11, 12, 13, 14, 15, 16, 17 and 18 | CAR | N/A | No | No | Yes | Yes
|  | 13–15 | Land Plans (AS-005) Sheet 13 | TP | Approximately 12 - 24 months | No | No | Yes | Yes
Cadent Gas Limited | Gowling WLP (UK) LLP | 4–1 | Land Plans (AS-005) Sheet 4 | CAR | N/A | No | No | Yes | Yes | TBC | RR–017 | REP1–035 | N/A | REP1–029 (Pages 10 to 11) | N/A | N/A | SU and known operational | Draft under discussion | Not required | In December 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, the Applicant’s Solicitors commenced engagement with the Affected Person in relation to agreeing a bespoke set of protective provisions. These have not yet been provided by the Affected Person, and so the Applicant notes that it has included a set of generic protective provisions which will benefit the Affected Person in Part 1 of Schedule 11 to the Draft DCO (Document Ref: 3.1) whilst engagement is ongoing. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person subsequently submitted a relevant representation [RR-017]. Discussions on the draft protective provisions are ongoing between the Affected Person's solicitors and the Applicant's solicitors. The latest version of the draft protective provisions were shared by the Applicant with the Affected Person's solicitors on the 16th October 2025. | Not required | No | 2025-10-20 | Agreement expected to be reached during Examination
Ecotricity (Heck Fen Solar) Limited | Osborne Clarke | 9–12, 14–2, 14–3, 14–4, 14–5, 14–6, 14–7, 14–8, 14–9 | Land Plans (AS-005) Sheets 9 and 14 | CAR | N/A | No | No | No | Yes | TBC | N/A | N/A | N/A | N/A | N/A | N/A | SU and known operational | Agreed | Draft under discussion | In December 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in December 2023. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. In February 2025, the Applicant commenced engagement with the Affected Person in relation to agreeing a bespoke set of protective provisions. The Applicant has included a set of protective provisions for the benefit of the Affected Person in Schedule 11 to the Draft DCO (Document Ref: 3.1) whilst engagement is ongoing. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The protective provisions in the Draft DCO are agreed. The Applicant's solicitors are currently negotiating a cooperation agreement with the Affected Person's solicitors. | Not required | No | 2025-09-09 | Agreement expected to be reached during Examination
Environment Agency | Hugo Godwin – Environment Agency | 3–5, 3–7, 6–1, 8–1, 8–3, 13–7, 13–9 | Land Plans (AS-005) Sheets 3, 6, 8 and 13 | CAR | N/A | Yes | No | Yes | No | TBC | RR–006 | REP1–039 | REP1–024 | REP1–029 (Pages 30 to 44) | N/A | N/A | SU and known operational | Not required | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. Access was granted in October 2023. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In July 2023, Ardent wrote to the Affected Person with an update on the proposed route for the grid connection. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In December 2023, Ardent engaged with the Affected Person in relation to access for intrusive survey works. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In January 2025, Ardent issued detailed Heads of Terms to secure the rights required to construct and operate the Proposed Development. Ardent are engaging with the Affected Person in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In March 2025, Ardent met with the Affected Person’s Agent to discuss the Heads of Terms and to provide more information on the Proposed Development. The Draft DCO does not disapply the requirement to apply for environmental permits for any works associated with the Proposed Development. As such, on the 26th February 2025, the Affected Person confirmed to the Applicant that it did not require protective provisions to be included in the Draft DCO (Document Ref: 3.1). In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person subsequently submitted a relevant representation [RR-006]. In August 2025, the Applicant received signed Heads of Terms from the Affected Person's Agent. A formal legal agreement, reflecting these signed Heads of Terms, will now be progressed to secure the rights required to construct and operate the Proposed Development. | Agreed | Yes | 2025-10-20 | Agreement complete
|  | 3–6, 8–2, 13–11, 13–12, 13–14, 13–16, 13–17, 14–1, 15–2, 15–3, 15–4 | Land Plans (AS-005) Sheets 3, 8, 13, 14 and 15 | CAR | N/A | No | No | Yes | No
UK Transition Power Holdings Limited | N/A | 17–7, 18–11 | Land Plans (AS-005) Sheet 17 and 18 | CAR | N/A | No | No | No | Yes | TBC | RR–020 | REP1–040 | N/A | REP1–029 (Pages 85 to 87) | N/A | N/A | SU and known operational | Not required | Not required | In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person subsequently submitted a relevant representation [RR-020]. Discussions are continuing between the Affected Person and the Applicant regarding the interface between each parties' project. | Not required | N/A | 2025-10-20 | N/A
Heck Fen Wind Park Limited | N/A | 9–12 | Land Plans (AS-005) Sheet 9 | CAR | N/A | No | No | No | Yes | TBC | N/A | N/A | N/A | N/A | N/A | N/A | SU and known operational | Not required | Not required | In March 2025, Ardent wrote to the Affected Person inviting them to take part in the Additional Consultation which took place between the 6th March and 3rd April 2025. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. | Not required | Yes | 2025-09-09 | Agreement not required
National Gas Transmission PLC | Womble Bond Dickinson (UK) LLP | 14–1 | Land Plans (AS-005) Sheet 14 | CAR | N/A | No | No | Yes | Yes | TBC | RR–010 | N/A | REP1–022 | REP1–029 (Pages 9 to 10) | N/A | N/A | SU and known operational | Draft under discussion | Not required | In December 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, the Applicant’s Solicitors commenced engagement with the Affected Person in relation to agreeing a bespoke set of protective provisions. The Applicant has included a set of protective provisions for the benefit of the Affected Person in Schedule 11 to the Draft DCO (Document Ref: 3.1) whilst engagement is ongoing. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person subsequently submitted a relevant representation [RR-010]. Discussions on the draft protective provisions are ongoing between the Affected Person's solicitors and the Applicant's solicitors. The latest version of the draft protective provisions were shared by the Applicant with the Affected Person's solicitors on the 30th September 2025. | Not required | No | 2025-10-20 | Agreement expected to be reached during Examination
National Grid Electricity Distribution (East Midlands) PLC | N/A | 18–57 | Land Plans (AS-005) Sheet 18 | CAR | N/A | No | Yes | Yes | No | TBC | N/A | N/A | N/A | N/A | N/A | N/A | SU and known operational | Agreed | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In July 2023, Ardent wrote to the Affected Person with an update on the proposed route for the grid connection. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. The consultation period was subsequently extended to finish on the 17th March 2024 due to a minor amendment to the Proposed Development which impacted the Affected Person. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. In January 2025, the Applicant’s Solicitors commenced engagement with the Affected Person in relation to agreeing a bespoke set of protective provisions. These have not yet been provided by the Affected Person, and so the Applicant notes that it has included a set of generic protective provisions which will benefit the Affected Person in Part 1 of Schedule 11 to the Draft DCO (Document Ref: 3.1) whilst engagement is ongoing. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. No further communications have been received by the Applicant from the Affected Person on the protective provisions or any other aspect of the Proposed Development. As such, the Applicant's working assumption is that the protective provisions in the Draft DCO are agreed. | Not required | Yes | 2025-09-09 | Agreement complete
|  | 2–2, 3–8, 6–2 | Land Plans (AS-005) Sheets 2, 3, and 6 | CAL | N/A | No | No | Yes | Yes
|  | 1–1, 2–1, 2–3, 4–1, 4–6, 9–1, 9–3, 9–7, 9–8, 9–9, 9–10, 9–12, 10–6, 10–11, 11–5, 11–6, 11–7, 11–8, 12–5, 14–1, 14–11, 16–1, 17–4, 17–5, 17–7, 18–1, 18–3, 18–4, 18–5, 18–6, 18–7, 18–8, 18–9, 18–14, 18–17 | Land Plans (AS-005) Sheets 1, 2, 4, 9, 10, 11, 12, 14, 16, 17 and 18 | CAR | N/A | No | No | Yes | Yes
|  | 9–4 | Land Plans (AS-005) Sheet 9 | TP | Approximately 12 - 24 months | No | No | Yes | Yes
|  | 18–13 | Land Plans (AS-005) Sheet 18 | CAR | N/A | No | No | Yes | No
|  | 18–16, 18–19, 18–53 | Land Plans (AS-005) Sheet 18 | CAR | N/A | No | No | No | Yes
National Grid Electricity Transmission PLC | Dirk Dudman – BNP Paribas Bryan Cave Leighton Paisner LLP | 18–16, 18–17, 18–19, 18–57 | Land Plans (AS-005) Sheet 18 | CAR | N/A | Yes | No | Yes | Yes | TBC | RR–012 | REP1–049 | N/A | REP1–029 (Pages 28 to 30) | N/A | N/A | SU and known operational | Draft under discussion | Draft under discussion | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In July 2023, Ardent wrote to the Affected Person with an update on the proposed route for the grid connection. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, the Applicant’s Solicitors commenced engagement with the Affected Person in relation to agreeing a bespoke set of protective provisions. These have not yet been provided by the Affected Person, and so the Applicant notes that it has included a set of generic protective provisions which will benefit the Affected Person in Part 1 of Schedule 11 to the Draft DCO (Document Ref: 3.1) whilst engagement is ongoing. In January 2025, Ardent initiated discussions to secure the rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to a voluntary agreement, with a view to reaching a voluntary agreement before the end of Examination. In January and March 2025, Ardent met the Affected Person’s Agent via Teams to discuss the rights that the Applicant is seeking and to progress discussions regarding a voluntary agreement. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person subsequently submitted a relevant representation [RR-012]. Ardent has been in regular contact with the Affected Person's Agent with regards to securing a voluntary land agreeement, and the latest meeting was on the 21st July 2025. An agreement will be entered into at the appropriate time. Discussions on the draft protective provisions are ongoing between the Affected Person's solicitors and the Applicant's solicitors. The latest version of the draft protective provisions were shared by the Applicant with the Affected Person's solicitors on the 16th October 2025. | Draft under discussion | No | 2025-10-20 | Agreement expected to be reached during Examination
|  | 18–53, 18–54 | Land Plans (AS-005) Sheet 18 | CAR | N/A | Yes | No | Yes | No
|  | 18–13, 18–14 | Land Plans (AS-005) Sheet 18 | CAR | N/A | Yes | No | No | No
|  | 4–6, 18–20, 18–28, 18–29, 18–33, 18–34, 18–35 | Land Plans (AS-005) Sheets 4 and 18 | CAR | N/A | No | No | Yes | Yes
National Grid Viking Link Limited | Eversheds Sutherland LLP | 18–22, 18–23, 18–32, 18–36, 18–37, 18–38, 18–40 | Land Plans (AS-005) Sheet 18 | CAR | N/A | Yes | No | Yes | Yes | TBC | RR–013 | REP1–050 | REP1–023 | REP1–029 (Pages 49 to 51) | N/A | N/A | SU and known operational | Draft under discussion | Not required | In March 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. In May 2023, Ardent wrote to the Affected Person, inviting them to participate in the Non-Statutory Consultation. In July 2023, Ardent wrote to the Affected Person with an update on the proposed route for the grid connection. In December 2023, Ardent engaged with the Affected Person regarding a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in December 2023. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. The consultation period was subsequently extended to finish on the 17th March 2024 due to a minor amendment to the Proposed Development which impacted the Affected Person. In December 2024, Ardent wrote to the Affected Person inviting them to take part in the Targeted Consultation which took place between the 16th December and 19th January 2025. In February 2025, the Applicant commenced engagement with the Affected Person in relation to agreeing a bespoke set of protective provisions. The Applicant has included a set of protective provisions for the benefit of the Affected Person in Schedule 11 to the Draft DCO (Document Ref: 3.1) whilst engagement is ongoing. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person subsequently submitted a relevant representation [RR-013]. Discussions on the draft protective provisions are ongoing between the Affected Person's solicitors and the Applicant's solicitors. The latest version of the draft protective provisions were shared by the Applicant with the Affected Person's solicitors on the 8th October 2025. | Not required | No | 2025-10-20 | Agreement expected to be reached during Examination
|  | 12–5, 12–6, 12–12, 13–1, 13–2, 18–12, 18–21, 18–24, 18–25, 18–26, 18–27, 18–29, 18–30, 18–31, 18–33, 18–34, 18–39, 18–41, 18–42, 18–45, 18–46 | Land Plans (AS-005) Sheets 12, 13 and 18 | CAR | N/A | Yes | No | No | No
|  | 12–18, 12–19, 18–16, 18–19, 18–20, 18–28, 18–35, 18–44 | Land Plans (AS-005) Sheets 12 and 18 | CAR | N/A | No | No | Yes | Yes
|  | 12–7, 12–9, 12–11, 18–13, 18–16 | Land Plans (AS-005) Sheets 12 and 18 | CAR | N/A | No | No | No | Yes
Network Rail Infrastructure Limited | Jonathan Sinclair – Network Rail Infrastructure Limited Addleshaw Goddard LLP | 10–14 | Land Plans (AS-005) Sheet 10 | CAR | N/A | Yes | No | Yes | No | TBC | RR–011 | REP1–053 | N/A | REP1–029 (Pages 77 to 78) | N/A | N/A | SU and known operational | Draft under discussion | Draft under discussion | In December 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, the Applicant’s Solicitors commenced engagement with the Affected Person in relation to agreeing a bespoke set of protective provisions. The Applicant has included a set of protective provisions for the benefit of the Affected Person in Schedule 11 to the Draft DCO (Document Ref: 3.1) whilst engagement is ongoing. In January 2025, the Applicant initiated discussions to secure the rights required to construct and operate the Proposed Development. The Applicant is engaging with the Affected Person’s Agent in relation to a voluntary agreement, with a view to reaching a voluntary agreement before the end of Examination. The Applicant has received the Affected Person’s standard form Heads of Terms, and in March 2025, provided the Affected Person with feedback on the proposed terms. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person subsequently submitted a relevant representation [RR-011]. Discussions on the draft protective provisions and the need for a side agreement are ongoing between the Affected Person's solicitors and the Applicant's solicitors. Ardent has been in regular contact with the Affected Person with regards to securing a voluntary land agreeement, and the latest correspondence was on the 4th September 2025. Engagement has continued between the Ardent and the Affected Person's Agent, and the latest correspondence was on the 8th October 2025. The Applicant does not anticipate securing a voluntary land agreement with the Affected Person for the reasons set out in Pages 77 - 78 of the Applicant Responses to Relevant Representations (REP1-029). | Draft under discussion | No | 2025-10-20 | Agreement not expected to be reached during Examination
Triton Knoll OFTO Limited | Andrew Robertson - Dalcour Maclaren CMS Cameron McKenna Nabarro Olswang LLP | 13–11, 13–12, 13–14, 13–16, 13–17, 14–1, 15–2, 15–4 | Land Plans (AS-005) Sheets 13, 14 and 15 | CAR | N/A | Yes | No | Yes | No | TBC | RR–033 | N/A | N/A | REP1–029 (Pages 48 to 49) | N/A | N/A | SU and known operational | Draft under discussion | Not required | In December 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to survey access. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. The consultation period was subsequently extended to finish on the 17th March 2024 due to a minor amendment to the Proposed Development which impacted the Affected Person. In August 2024, Ardent issued detailed Heads of Terms to secure the access rights required to construct and operate the Proposed Development. In January 2025, Ardent issued detailed Heads of Terms to secure the cable rights required to construct and operate the Proposed Development. The Affected Person has appointed an Agent who Ardent are engaging with in relation to the Heads of Terms, with a view to reaching a voluntary agreement before the end of Examination. In February 2025, the Applicant’s Solicitors commenced engagement with the Affected Person in relation to agreeing a bespoke set of protective provisions. The Applicant has included a set of protective provisions for the benefit of the Affected Person in Schedule 11 to the Draft DCO (Document Ref: 3.1) whilst engagement is ongoing. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person subsequently submitted a relevant representation [RR-033]. In June 2025, the Affefted Person appointed Dalcour Maclaren to act on their behalf. In July 2025, Ardent and the Affected Person's newly appointed Agent met via Teams to discuss the Proposed Development and the rights the Applicant is seeking to acquire voluntarily. Ardent have since provided updated Heads of Terms and engagement is ongoing. Discussions on the draft protective provisions are ongoing between the Affected Person's solicitors and the Applicant's solicitors. The latest version of the draft protective provisions were shared by the Applicant with the Affected Person's solicitors on the 8th October 2025. In October 2025, Ardent received the first substantitive response to the Heads of Terms and is considering the Affected Person's proposals before responding. | Draft under discussion | No | 2025-10-20 | Agreement expected to be reached during Examination
|  | 18–2, 18–10 | Land Plans (AS-005) Sheet 18 | CAR | N/A | Yes | No | No | No
|  | 13–10, 13–13, 14–2, 14–3, 14–4, 14–5, 14–6, 14–7, 14–8, 14–9, 15–1, 15–3, 18–6, 18–9, 18–13, 18–14, 18–16, 18–17, 18–19, 18–52, 18–56 | Land Plans (AS-005) Sheets 13, 14, 15 and 18 | CAR | N/A | No | No | No | Yes
|  | 13–15 | Land Plans (AS-005) Sheet 13 | TP | Approximately 12 - 24 months | No | No | No | Yes
Vicarage Drove Energy Centre Limited | Ashfords LLP | 18–52, 18–56 | Land Plans (AS-005) Sheet 18 | CAR | N/A | No | Yes | No | Yes | TBC | RR–034 | REP1–061 | N/A | REP1–029 (Pages 88 to 90) | N/A | N/A | SU and known operational | Draft under discussion | Not required | In December 2023, the Applicant’s Land Agent (Ardent) wrote to the Affected Person to introduce the Proposed Development and in relation to a Land Interest Questionnaire. A completed Land Interest Questionnaire was returned in December 2023. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. In December 2024, the Applicant’s Solicitors commenced engagement with the Affected Person in relation to agreeing a bespoke set of protective provisions. These have not yet been provided by the Affected Person, and so the Applicant notes that it has included a set of generic protective provisions which will benefit the Affected Person in Part 1 of Schedule 11 to the Draft DCO (Document Ref: 3.1) whilst engagement is ongoing. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person subsequently submitted a relevant representation [RR-034]. Discussions on the draft protective provisions are ongoing between the Affected Person's solicitors and the Applicant's solicitors. | None drafted | No | 2025-10-20 | Agreement expected to be reached during Examination
|  | 18–6 | Land Plans (AS-005) Sheet 18 | CAR | N/A | No | No | No | Yes
Vodafone Limited | N/A | 18–14, 18–16, 18–17, 18–19 | Land Plans (AS-005) Sheet 18 | CAR | N/A | No | No | Yes | Yes | TBC | N/A | N/A | N/A | N/A | N/A | N/A | SU and known operational | Agreed and in latest version of DCO | Not required | In December 2023, the Applicant’s Land Agent (Ardent) engaged with the Affected Person regarding a Land Interest Questionnaire. In March 2025, Ardent wrote to the Affected Person inviting them to take part in the Additional Consultation which took place between the 6th March and 3rd April 2025. The Applicant has been engaging with the Affected Person and provided the standard Protective Provisions included at Part 2 of Schedule 11 to the Draft DCO (Document Ref: 3.1) in December 2024. The Affected Person has not requested bespoke protective provisions. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. No further communications have been received by the Applicant from Vodafone on the protective provisions or any other aspect of the Proposed Development. As such, the Applicant's working assumption is that the protective provisions in the Draft DCO are agreed. | Not required | Yes | 2025-09-09 | Agreement complete
Status of Negotiations with Crown Bodies
The Crown Estate Commissioners | Alexander Ireton – Carter Jonas Burges Salmon LLP | 1–4, 2–2, 3–5, 3–7, 6–1, 7–2, 7–3, 8–1, 8–3 | Land Plans (AS-005) Sheets 1, 2, 3, 6, 7 and 8 | N/A | N/A | No | No | No | Yes | TBC | N/A | N/A | N/A | N/A | Crown land | Section 135 consent: The Applicant anticipates that this will be granted during Examination Deed of Covenant: The Applicant anticipates that an agreement will be reached during Examination | Not SU | Not required | Not required | Since July 2022, the Applicant has been in contact with the Affected Person to discuss the Proposed Development and its anticipated interactions with the Affected Person. In July 2022, the Applicant discussed a Deed of Covenant with the Affected Person in relation to the Affected Person’s mines and minerals rights over Plot 2-2. Since September 2022, the Applicant has made sufficient progress with the Affected Person’s interest in relation to the rights required and anticipates that an agreement will be reached before or during Examination. In December 2023, the Applicant’s Land Agent (Ardent) engaged with the Affected Person regarding a Land Interest Questionnaire. In January 2024, Ardent wrote to the Affected Person inviting them to take part in the Statutory Consultation which took place between the 22nd January and 4th March 2024. The consultation period was subsequently extended to finish on the 31st March 2024 due to a minor amendment to the Proposed Development which impacted the Affected Person. In August 2024, the Applicant discussed a further Deed of Covenant with the Affected Person in relation to their additional rights and restrictions in Plots 1-4, 3-5, 3-7, 6-1, 7-2, 7-3, 8-1 and 8-3. Discussions are ongoing and it is expected that an agreement will be reached before or during Examination. In March 2025, the Applicant requested Section 135 consent from the Affected Person and anticipates that this will be given during Examination. In May 2025, Ardent sent a Section 56 notification of acceptance to the Affected Person. The Affected Person has recently appointed Burges Salmon LLP to deal with the Section 135 consent and Deed of Covenant. The Applicant anticipates that both will be agreed during Examination. Constructive engagement has continued between the Applicant's solicitors and the Affected Person's solicitors, and the latest correspondence was on the 20th October 2025. | Draft under discussion | No | 2025-10-20 | Agreement expected to be reached during Examination
1 Person or organisation representing the interests of the affected person(s) - enter N/A if the affected person(s) are representing themselves
2 Plot number from the Book of Reference
3 Plan reference number from the Book of Reference and Examination Library reference
4 Description of land and rights requested from the Book of Reference including restrictive covenants
5 Likely duration of any temporary rights such as temporary possesion
6 A person is within category 1 if the applicant, after making diligent inquiry, knows that the person is an owner, lessee, tenant (whatever the tenancy period) or occupier of the land, see section 57 (1) of the Planning Act 2008
7 A person is within category 2 if the applicant, after making diligent inquiry knows that the person: interested in the land or has the power to sell or convey the land or to release the land, see section 57(20) of the Planning Act 2008
8 Reference number assigned to each interested party and affected person - for Planning Inspectorate use only
9 Reference number assigned to each relevant representation in the Examination Library
10 Reference number assigned to each written representation in the Examination Library
11 Reference number assigned to any other document in the Examination Library
12 Reference numbers assigned to all of the applicant's responses in the Examination Library including specific reference to relevant sections within documents
13 Where crown land is affected, this column should include the anticipated date of consent from the crown authority
14 Narrative on negotiations to date

## Data types
Data types | Special category | Statutory undertaker (SU) and operational land status | Protective provisions status | Side agreements | Heads of Terms | Complete
Options | Crown land | Not SU | Not required | Not required | Not required | Yes
| National Trust | SU and known operational | Draft under discussion | Draft under discussion | None drafted | No
| Allotment | SU and unknown operational | Agreed | Agreed | Draft under discussion
| Commons | SU and disputed operational | Agreed and in latest version of DCO |  | Agreed
| Open space |  | No agreement on final version
N/A
Other