## Guide to the R&I Log
Introduction:
Natural England have created this Risk and Issues Spreadsheet to track progress of issues raised in our Relevant Representations throughout the Examination for Springwell Solar Project. Each issue was assigned a Red, Amber, Yellow or Green risk rating in our relevant representations, as defined below. The Rating will be updated at each deadline to clearly show progress made during examination.
Risk Rating:
Red are those where there are fundamental concerns which it may not be possible to overcome in their current form.
Amber are those where further information is required to determine the effects of the project and allow the Examining Authority to properly undertake its task and or advise that further information is required on mitigation/compensation proposals in order to provide a sufficient degree of confidence as to their efficacy.
Yellow are those where Natural England does not agree with the Applicant’s position or approach. We would ideally like this to be addressed but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process. However, we reserve the right to revise our opinion should further evidence be presented. It should be noted by interested parties that whilst these issues/comments are not raised as significant concerns in this instance, it should not be understood or inferred that Natural England would be of the same view in other cases or circumstances.
Green are those which have been successfully resolved (subject always to the appropriate requirements being adequately secured).
Additional information:
Key updates for D1 are primarily in column G.
The spreadsheet contains filters to enable ease of viewing. In particular, filtering via 'Amber' in cell F1 (titled 'RAG Status Rel Rep - Feb 2025') will show only the issues that were marked as Amber in our Relevant Representations.
Requested actions in our Relevant Representations are shown in Red Text.
NE's key updated advice at the current deadline is shows in Bold.

## R&I Log
Ref from Relevant Reps | Theme | Issue Summary | Current RAG Status | Taken from Natural England’s Relevant Representations - 02/07/2025 | RAG Status Rel Rep - 02/07/2025 | Consultation, actions, progression Prior to D1- 07/10/2025 | RAG Status D1 - 07/10/2025 | NE response to updates 11/11/2025 (following meeting with the applicant held 05/11/2025) | RAG Status 11/11/2025 | NE response to updates 13/02/2026 (following email correspondence and a meeting with the applicant held 04/02/2026) | RAG Status 13/02/2026
NE1 | Internationally & nationally designated sites | Study Area (C, O, D) | Green | The study area for statutory designated sites makes no reference to Natural England’s Impact Risk Zones (IRZ’s). However, in pre-application consultation between NE and the applicant, it was established that the study area used has identified all relevant sites and as such NE are satisfied with the study area used. (APP-058). | Green
NE2 | Internationally designated sites | Identification of relevant sites (C, O, D) | Green | The HRA Screening Report (APP-050) provides detail on the screening of Internationally Designated Sites. Natural England welcomes consideration of the Wash designations (Ramsar & SPA), and The Wash & North Norfolk Coast SAC, especially given their distance from the project at <15km and due to the potential disturbance to qualifying species & hydrological connectivity as identified in Section 4.1.2, Table 2. Natural England welcome the revised decision to scope in The Wash Ramsar and SPA for further assessment and note the inclusion of these designations in the HRA Screening Report (APP-050). | Green
NE3 | Internationally designated sites | Functionally Linked Land – The Wash SPA and Ramsar (FLL) (C,O,D) | Green | Ideally, Natural England would have liked to be provided a summary table for the HRA to display the SPA species considered in assessments undertaken by the applicant. Nonetheless, Natural England has reviewed Appendix 7.5 Wintering Bird Report (APP-094) and generally concur, aside from the screening out of impacts upon Lapwing which, as displayed in Table 4.1, had a site peak count of 452, equating to approximately 1% of the SPA population. Natural England welcome the proposed mitigation measures, specifically the proposal for a 60m buffer from the reservoir during winter months to reduce impacts on wintering birds (notably Gadwall), as outlined in Section 5.2 of the HRA Screening Report. We welcome the mitigation will be implemented via the oCEMP which will be secured by Requirement 12 of the DCO (APP-039). | Amber | No update | Amber | Natural England welcome the decision to scope in impacts upon Lapwing and note the proposed mitigation in the form of a 60m buffer area (REP1- 029, page 54). Natural England have discussed this impact pathway with the applicant; have remaining concerns regarding the residual noise at the point of the receptor (70dB at locations used by Lapwing & Gadwall). The Applicant is to revise the HRA to incorporate additional mitigation measures, including the avoidance of construction activities during the winter period where possible, and the presence of an Ecological Clerk of Works (ECoW) to ensure that work does not proceed when SPA birds are present or at risk of disturbance. NE are satisfied with the proposed mitigation in principle. NE will review when the applicant has provided the updates to the HRA. | Amber | NE met with the Applicant on 04/02/2026 to discuss the matter of potential disturbance to lapwing and gadwall during construction. NE acknowledged the applicant’s justification for the inability to avoid winter working. We welcomed the implementation of a 200‑metre buffer, noting that this measure is consistent with NatureScot’s disturbance guidance. Natural England also confirmed that it is appropriate for the ECoW to employ adaptive mitigation, utilising one or a combination of mitigation techniques or other suitable measures to minimise disturbance. In light of the distance between the Solar Array Area and the SPA, and the resulting substantial availability of suitable alternative habitat, Natural England considers the proposed mitigation to be acceptable. The Applicant has provided an updated oCEMP and HRA reflective of the above matters agreed in the meeting on 04/02/2026 and submitted these into Examination at Deadline 7. As such NE raise no further concerns and consider this agreed. | Green
NE4 | Internationally designated sites | Functionally Linked Land – The Wash and North Norfolk Coast SAC (FLL) (C, O, D) | Green | Natural England welcome the mitigation measures outlined in Section 5.28-5.2.12 of the HRA Screening Report, specifically, the avoidance of impacts to Otter through the use of Horizonal Directional Drilling (HDD) methods. Given the avoidance of impacts by HDD, NE concur with that the project is unlikely to cause an adverse effect upon Otters and therefore the Wash and North Norfolk Coast SAC and have no further comments. It is noted that further surveys for protected species will be carried out once the locations of crossings have been defined. Where additional impacts are identified, the correct licence must be obtained, with impacts to Otter re-assessed under the Habitats Regulations as appropriate. | Green
NE5 | Internationally designated sites | Hydrological Connectivity (C, O, D) | Green | Hydrological Connectivity from the development site to The Wash SPA and Ramsar and The Wash and North Norfolk Coast SAC is acknowledged within the HRA Screening Report. NE concur with the assessment that there is expected to be no adverse impacts on water quality or to the hydrological regime on the Wash SPA and Ramsar and North Norfolk Coast SAC as a result of the proposal. The nature of the proposed development, alongside the distance from the designations and embedded mitigation measures (oCEMP) means that any pollutants from the development site are highly unlikely to alter the background pollution at the designations, and thus are considered to have no appreciable effect. | Green
NE6 | Internationally designated sites | In-combination Assessment (C, O, D) | Green | Natural England welcome the consideration of the project alongside other plans/projects with the potential for in-combination effects on Internationally Designated Sites. NE welcome Table 5 of the HRA Screening Report which provides a clear summary of plans and projects with the potential for in-combination effects. NE welcome the detailed consideration of Heckington Fen Solar Park in Table 5 of the report (APP-050) and concur with the conclusion that through appropriate design and mitigation, the project is unlikely to work in-combination with the proposed development to cause a significant effect. However, it is unclear why the plans/projects identified in Appendix 4.2 Cumulative Assesment Short List (APP082) and Table 18.3 Summary of Inter-Cumulative Effects (APP-069) have not been reviewed within the HRA Screening Report. It is unclear whether all relevant cumulative impacts have been considered for the plans/projects included within Appendix 4.2 and Table 18.3. Natural England would welcome clarity on this and reasoning for their exclusion from assessment in the HRA. | Amber | No update | Amber | The applicant has provided additional details regarding previously omitted projects within their response to relevant reps and an updated version of the HRA (REP1-029 & REP2-014). Natural England welcomes this clarification and has no further comments. | Green
NE7 | Internationally designated sites | Conclusions (C, O, D) | Green | NE requires further information on Key Issue NE3 and NE6 and cannot concur with the conclusions of the HRA Screening Report (APP-050). | Amber | No update | Amber | Refer to NE3 & NE6. When an update is provided for NE3 the status will be reviewed. | Amber | Status amended to agreed following update to NE3. | Green
NE8 | Nationally designated sites (biodiversity & geodiversity) | Wilsford & Rauceby Warrens SSSI Conclusions (C, O, D) | Green | Chapter 7 of the ES (APP-058) correctly identifies the Nationally Designated Site, Wilsford & Rauceby Warrens SSSI as being within 10km of the development site. The SSSI is sensitive to pollution and could be affected by airborne contaminants and was therefore scoped in for further assessment. Para 7.6.32 states that during construction of the Proposed Development, the additional traffic required may impact the air quality of the SSSI, however, traffic modelling has shown that the assessment thresholds are not exceeded; thus NE raise no concern (APP-067). | Green |  | Green
NE9 | Nationally designated sites (biodiversity & geodiversity) | The Wash SSSI Conclusions (C, O, D) | Green | Natural England have no further advice regarding The Wash SSSI. The assessment of impacts to the qualifying features of the overlapping European designations (The Wash SPA, The Wash Ramsar, The Wash and North Norfolk Coast SAC) is considered to cover any relevant impacts to the SSSI’s notified features. As a result, this assessment does not need to be duplicated within the ES, although NE welcome the reference to the underpinning SSSI designations within the HRA Screening Report (APP-050). | Green |  | Green
NE10 | Protected species licencing | Avoidance by design & Licence identification (C, O, D) | Green | NE have been engaged by the applicant during the pre-application period, and welcome the approach to avoid impacts upon protected species via avoidance by design. Great Crested Newts Through discussions with the applicant, they have identified the need for a mitigation license for Great Crested Newt (GCN). NE also note para 7.7.8 of Chapter 7 of the ES which states that ‘A European Protected Species mitigation licence is necessary to permit construction work given the nearby GCN populations and their conservation status or the habitat in which they are found’. As it stands, Natural England are yet to receive a draft licence application. The applicant must submit the draft licence as soon as possible. Otters and Water Vole Natural England welcome the approach to avoid impacts to Otters and Water Vole through embedded measures, as outlined in Table 7.8 of Chapter 7 of the ES (APP-058). However, we note the following in Table 7.8 ‘If watercourses where water voles and otters are known to be present cannot be avoided for the Bespoke Access Road/ Cable Route Corridor, a licence and further surveys may be required’. Where this is the case and impacts cannot be avoided, Natural England should be consulted as soon as possible and a licence and further surveys may be required. Where the need for a licence is identified post- consent, the relevant license must be obtained from Natural England in the usual manner (i.e. this DCO does not preclude the project from the need to apply for the relevant mitigation licence). | Amber | A draft licence for GCN was submitted to Natural England in August 2025. Following review, a Letter of No Impediment (LoNI) was issued on 23rd September 2025 (ref: 2024-68077-EPS-AD1) in relation to the draft GCN proposals. | Green | A draft licence for GCN was submitted to Natural England in August 2025. Following review, a Letter of No Impediment (LoNI) was issued on 23rd September 2025 (ref: 2024- 68077-EPS-AD1) in relation to the draft GCN proposals. NE have no further comments. | Green
NE11 | Biodiversity net gain | Biodiversity net gain (C, O, D) | N/A | Natural England welcome the commitment to BNG, as illustrated in the Biodiversity Net Gain Strategy Document (APP-280). Paragraph 1.1.2 acknowledges that BNG is not yet a mandatory requirement for NSIPs, however, the applicant has demonstrated that it is still committed to achieving BNG. Section 4.1.1 indicates that based on the current site plans, and using the Statutory Metric (July 2024), the proposed development will give rise to: - 36.43% net gain in Habitat units - 10.79% net gain in Hedgerow units - 15.95% net gain in Watercourse units Natural England welcome the net gain in biodiversity as illustrated across all units. Additionally, Natural England welcome the commitment to habitat management and monitoring through the undertaking of BNG habitat condition assessments and review of management as outlined in the Section 6.1.1 of the BNG Strategy document (APP-280). NE also welcome the commitment to monitoring across the lifetime of the Proposed Development, which exceeds the standard 30 year requirement of BNG management and monitoring. | N/A |  |  | NE welcomes the commitment to Biodiversity Net Gain (BNG) and in the absence of mandatory BNG for this project, and has no further comments at this stage. | N/A
NE12 | Nationally designated landscapes | Nationally designated landscapes (C, O, D) | Green | The proposed development is not located within, or within the setting of any nationally designated landscapes. As a result, NE has no specific comments to make on landscape implications of this development. NE welcome the applicant’s response to NE’s previous comments on Landscape, as detailed in Table 6.1 of the ES (APP-057). We welcome the applicant’s measures to relate to prevailing character, such as the retention of field boundary vegetation and drainage channels. NE welcome the reference to Natural England’s National Character Areas and other Local Landscape Character Assessments within Chapter 6 of the ES. Nonetheless, NE note the significant number of solar developments in Lincolnshire; the examining authoirity should have regard for the landscape character of the area during the examination. | Green
NE13 | Soils and best and most versatile agricultural land | ALC Survey Methods (C, O, D) | Yellow | Natural England has reviewed the ALC surveys undertaken by the applicant (APP-267 and APP-269). The full detailed resolution of the survey (1 auger boring per hectare) is welcomed for both the Solar Array Area and Bespoke Access Corridor. Natural England note within ES Chapter 14, para14.4.7 (APP-065) that a detailed soil survey has not been carried out for the Cable Route Corridor & Bicker Fen substation extension works at the time of this assessment. It is noted in para 14.6.8 (APP-065) that a detailed soil survey of the Cable Route Corridor will be carried out pre construction to inform the site-specific SMP. It remains Natural England’s advice that there is a risk of soil damage, ALC degradation and long term or permanent loss of BMV from cable installation without proper soil management practises. Natural England therefore advise that a full ALC survey is required across the full site, including cable route, to inform avoidance, soil management and reinstatement. NE advise these surveys should be undertaken pre-consent, to inform micro-siting & avoidance of the highest quality agricultural land as far as practicable along the cable route, in line with the established principles of the Mitigation Hierarchy (i.e. avoid, then mitigate, then compensate) and NPS EN-1 paragraph 5.11.12: ‘Applicants should seek to minimise impacts on the best and most versatile agricultural land defined as land in grades 1, 2 and 3a of the Agricultural Land Classification) and preferably use land in areas of poorer quality (grades 3b, 4 and 5)’. | Amber | No update | Amber | NE note the Applicant has not undertaken an ALC survey of the cable route corridor pre-consent (REP1- 029, page 58). It remains NE’s advice that the full Order Limits should be surveyed pre-consent to inform avoidance, assessment and soil handling. However, as the Applicant has committed to a post-consent ALC survey of the cable route, the Environmental Statement (ES) impact assessment would remain unchanged, and avoidance of the highest-grade areas will be implemented wherever practicable following post-consent surveys, this item is classified as yellow. Please refer to the definition of the ‘yellow’ category comments below: ‘Yellow are those where Natural England does not agree with the Applicant’s position or approach. We would ideally like this to be addressed but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process. However, we reserve the right to revise our opinion should further evidence be presented. It should be noted by interested parties that whilst these issues/comments are not raised as significant concerns in this instance, it should not be understood or inferred that Natural England would be of the same view in other cases or circumstances’. | Yellow
NE14 | Soils and best and most versatile agricultural land | ALC Survey Results (C, O, D) | Green | The ALC survey results have been presented within ES Chapter 14 (APP 065) and split into the ALC grades within each area surveyed: Solar Array Area, Bespoke Access Corridor and Preliminary Cable Route. The detailed ALC survey results indicate that across the Proposed Solar Array Area 47.4% (250.12ha) is categorised as BMV land. Within the Bespoke Access Corridor, detailed ALC survey results indicate 85.2% (38.68ha) is categorised as BMV land. Provisional data indicates that the Cable Route Corridor consists of potentially 100% (183.89ha) of BMV land. In total, 20.37ha of ‘permanent’ development is proposed on BMV agricultural land. Table 14.13 presents a breakdown of land use across the Solar Array Area, Bespoke Access Corridor and Cable Route Corridor (provisional), broken into temporary and permanent land loss, and by ALC grade. This is welcomed, however, Natural England query the omission of Mitigation/ Enhancement areas within the breakdown, as requested in our S42 response. Natural England note that the survey for the Cable Route Corridor is to be undertaken post-consent and therefore has relied on provisional data for the assessment. NE note the applicant has used Natural England’s 1:250,000 provisional ALC data. This map is designed to give an indication of land quality at a strategic level. It does not show the breakdown of Grade 3 into Subgrades 3a and 3b, and it has a minimum map unit of 80ha. Consequently, it is not suitable for site specific assessments, for which a more detailed field survey is required (See NE13 above). NE have made further comment on the management and reinstatement of land used temporarily for the development at issues refs NE18 and NE19. | Amber | No update | Amber | Refer to NE16. | Green
NE15 | Soils and best and most versatile agricultural land | Embedded Mitigation & Avoidance of BMV land (C, O, D) | Green | It is noted that efforts have been made to avoid Best and Most Versatile Land during the site selection process (para 14.13.11). Para 14.13.12, ES Chapter 14 (APP-065) states that ALC grading was also considered in siting the BESS and onsite substation within the Solar Array Area in order to avoid hard development on Grade 2 quality land. This is welcomed by Natural England. However, para 14.6.4 (APP-065) states the built development is mostly situated on a mixture of Subgrade 3a and Subgrade 3b and avoidance of BMV land is considered to be unavoidable due to the ‘site layout and design constraints’. It does not appear that the results from the ALC surveys have been utilised to micro-site away from BMV land. Natural England therefore require further rationale for the siting on BMV land. Further information should be presented to illustrate how this has been used to minimise impacts to BMV land as far as reasonably practicable. In particular, any permanent elements of development should seek to avoid BMV. Table 14.13 (APP-065) clearly indicates ‘permanent’ elements of development with an asterisk *, however no further rationale is provided in relation to the siting of these parts of the development in relation to BMV land. Natural England refer the applicant to NPS- EN-1, paragraph 5.11.12 which states the following ‘Applicants should seek to minimise impacts on the best and most versatile agricultural land (defined as land in grades 1, 2 and 3a of the Agricultural Land Classification) and preferably use land in areas of poorer quality (grades 3b, 4 and 5)’. | Amber | No update | Amber | NE acknowledges the clarification provided regarding avoidance measures and confirms that no further concerns are raised (REP1- 029, page 59). It is recognised that complete avoidance of BMV agricultural land is not achievable. Accordingly, PINS will be required to assess this matter in accordance with the relevant provisions of the Overarching National Policy Statement for Energy (NPS EN-1), specifically: ‘5.11.12 - Applicants should seek to minimise impacts on the best and most versatile agricultural land (defined as land in grades 1, 2 and 3a of the Agricultural Land Classification) and preferably use land in areas of poorer quality (grades 3b, 4 and 5).’ ‘5.11.34 - The Secretary of State should ensure that applicants do not site their scheme on the best and most versatile agricultural land without justification. Where schemes are to be sited on best and most versatile agricultural land the Secretary of State should take into account the economic and other benefits of that land. Where development of agricultural land is demonstrated to be necessary, areas of poorer quality land should be preferred to those of a higher quality.’ | Green
NE16 | Soils and best and most versatile agricultural land | Permanent loss of BMV land (D) | Green | Chapter 14 of the ES (APP-065) indicates that based on worst case scenarios, there is a permanent loss of 14.25ha if BMV land due to Built Environment within the Solar Array Area. Within the Cable Route Corridor, the predicted permanent loss of BMV land which is to be removed from agricultural production is 2.7ha. The permanent loss of BMV agricultural land to be removed from agricultural production within the Bespoke Access Corridor is 3.98ha. This is a total of 20.37ha. Natural England would always advise that BMV land should be avoided wherever possible for permanent development, to safeguard the long-term agricultural potential of the land. Any actions which compromise options for the future use of the land, or which undermine its inherent capability should be avoided. As noted in NE14, Chapter 14 does not consider the effect of ecological enhancements/mitigation areas on agricultural land. Whilst most ecological enhancements will be able to retain the BMV resource for the lifetime of the development, where enhancements require intrusive groundworks, or include deep rooting species (i.e. woodland), this can lead to a permanent loss of BMV resource. NPS-EN1 paragraph 5.11.34 states: ‘The Secretary of State should ensure that applicants do not site their scheme on the best and most versatile agricultural land without justification’. NE consider this permanent loss of BMV land has been appropriately assessed within the ES, being attributed a ‘significant (major adverse)’ effect on agricultural land use during the Construction Phase. (ES Table 14.15, Chapter 14) (APP-065). | Amber | No update | Amber | NE welcome further clarification and justification from the Applicant regarding the use of BMV land in development (REP1- 029, page 59). The applicant states that no intrusive ecological enhancements will occur on arable land, with all tree planting to occur in field margins, not on productive farmland, serving as visual screens and improving ecological connectivity. Other ecological enhancements, such as grassland and shrubs, can later revert to agricultural use. Therefore, they state that there is no need to consider permanent agricultural land loss for the areas of ecological enhancement. NE concur that the design approach has avoided permanent loss of arable land for ecological enhancements. After decommissioning, soils will be restored to their original profile, including type, depth, and structure. As such, NE raise no further concerns. | Green
NE17 | Soils and best and most versatile agricultural land | Time Limit (D) | Green | Natural England welcome the inclusion of a 40 year maximum operational lifespan for the solar arrays and BESS, as detailed in Chaper 2 of the ES (APP-053). The inclusion of the time limit within the DCO provides further certainty the proposed temporary land use changes will remin temporary as described, subject always to appropriate soil management. | Green
NE18 | Soils and best and most versatile agricultural land | oSMP (C, D) – Soil handling | Green | Table 14.13 (APP-065) illustrates a significant area of BMV land is to be occupied by both Solar PV development, and supporting infrastructure, for the lifetime of the development. This emphasises the importance of the Soil Management Plan, to mitigate the risk of permanent loss or damage to BMV land. Natural England welcome the content of the Outline Soil Management Plan (oSMP) (APP-176). NE welcome the inclusion of rainfall “stop” criteria meaning soil handing must take account of prevailing weather conditions in order to minimise the risk of damage to soil structure (4.1.5). NE also welcome the proposal which states that ‘where possible, the work is phased so that construction elements involving soil trafficking, stripping, handling and formation of stockpiles is avoided during periods of the year where the soils are most likely to be in a wet state (December to March)’ (4.1.5). It is NEs advice that all soils should only be handled in a dry and friable condition, and it is expected that construction programmes would restrict soil handing to the | Green
NE19 | Soils and best and most versatile agricultural land | oSMP (D) – Reinstatement | Green | Section 7.6 of the oSMP (APP-176) states that ‘By following the measures included below, impacts on the agricultural capability of the land can be mitigated and the Site can be returned to agricultural use after decommissioning’ (7.6.1). NE advise that this reinstatement commitment should specify that all agricultural land to be restored will be returned to it’s original ALC grade, informed by the pre-development ALC surveys. | Amber | No update | Amber | NE acknowledges the Applicant’s position that the ALC grade may be subject to variation as a result of future climatic conditions and associated factors, including soil water regime and flooding, which lie beyond its control. Restoration to the previous ALC grade would only be achievable if climatic datasets and interactions remain consistent with baseline conditions and if external management, particularly by local drainage boards, continues to maintain appropriate water table levels. Given these dependencies, the Applicant does not consider it reasonable to assume responsibility for achieving a specific ALC grade in the future. Instead, the Applicant proposes to commit to restoration of soils to match the baseline soil profile characteristics of soil type, horizon depth and soil structure. They also propose to implement best practice soil management processes to support optimal land quality. Natural England acknowledges this viewpoint and is currently consulting with internal soil specialists. Further comments will be provided in due course. | Amber | Following consultation with internal soil specialists, NE provided the following advice to the applicant on 9th January 2026; ‘The ALC system is designed to assess the long term inherent capability of land based on soil type, horizon depth, structure, and site characteristics. Where soils are carefully restored to their baseline profile and managed appropriately, the land can regain its former classification. The current, or indeed future agricultural use of the land does not influence the grade nor does the grade necessarily reflect the current economic value of the land. Where long-term limitations outside the control of the applicant will be introduced (or removed) in the near future through the implementation of a major scheme, such as new arterial drainage, the land is classified as if the changes have already been carried out. Where no such scheme is proposed (as is the case here), or there is uncertainty about implementation, the current limitations as surveyed will be taken into account. It is acknowledged that larger scale water management changes, such as IDB changes in water table depth, may alter the Wetness limitation across a site. It is therefore NE’s advice that the commitment should remain to ensure the land is returned to the baseline ALC grade wherever possible, noting that where external factors outside the applicant’s control, such as long-term IDB driven changes to water table levels, prevent restoration to the baseline, deviations from the original grade may be unavoidable.' The Applicant has accepted NE’s advice on agricultural land reinstatement commitments and provided an updated oSMP reflective of this advice at Deadline 7. As such NE raise no further concerns and consider this agreed. | Green
NE20 | Ancient woodland and ancient/veteran trees | Ancient woodland and ancient/veteran trees | Green | Natural England welcome the additional information regarding the results of the Arboricultural Impact Assessment as detailed in (APP-058). Natural England welcome the additional information regarding ancient and veteran trees that have been identified on Site following Arboricultural Impact Assessment (APP-088). NE welcome 11.1.9 of Appendix 6 which states that all veteran trees and the tranitioning veteran tree are to be retained and protected during construction (and subsequent decommissioning) activities associated with the Propoded Development. NE welcome the embedded mitigation measures including a veteran tree buffer zone. Para 11.1.15 states that measures to ensure tree protection will be secured post-consent in the detailed CEMP and DEMP. | Green
NE21 | Connecting people with nature | Connecting people with nature | Green | Natural England note in para 15.5.23 of Chapter 15 of the ES (APP-066) that there are no accessible PRoW within the Solar Array Area, but there are PRoWs crossing the Cable Route Corridor and the Bespoke Access Corridor. NE welcome the embedded mitigation in Table 15.2 which states that for temporary closures of PRoWs, signs and posters will be installed on relevant PRoWs and local walking groups, relevant parish councils and district councils will be notified regarding any temporary footpath closures through the Community Liaison Officer. This consideration to PRoW is welcomed by Natural England. Chapter 7 of ES states that ‘The final Site is to include a permissive path. This will be linked with ecological corridors as outlined in the Biodiversity Opportunities Plan and detailed in Section 7.8. Along the permissive walkway the Applicant will erect information boards to provide the public with information on local wildlife’. Further details of the permissive path are included in Chapter 6 (APP-057) which states that PRoW Ewer/12/1 is being enhanced as a permissive path and will be in place for the operational duration of the project with plans for a small footbridge to be created over the watercourse. Natural England welcome the consideration of and introduction of new permissive path. | Green