## Guide to the R&I Log
Introduction:
Natural England have created this Risk and Issues Spreadsheet to track progress of issues raised in our Relevant Representations throughout the Examination for Fosse Green Energy Project. Each issue was assigned a Red, Amber, Yellow or Green risk rating in our relevant representations, as defined below. The Rating will be updated at each deadline to clearly show progress made during examination.
Risk Rating:
Red are those where there are fundamental concerns which it may not be possible to overcome in their current form.
Amber are those where further information is required to determine the effects of the project and allow the Examining Authority to properly undertake its task and or advise that further information is required on mitigation/compensation proposals in order to provide a sufficient degree of confidence as to their efficacy.
Yellow are those where Natural England does not agree with the Applicant’s position or approach. We would ideally like this to be addressed but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process. However, we reserve the right to revise our opinion should further evidence be presented. It should be noted by interested parties that whilst these issues/comments are not raised as significant concerns in this instance, it should not be understood or inferred that Natural England would be of the same view in other cases or circumstances.
Green are those which have been successfully resolved (subject always to the appropriate requirements being adequately secured).
Additional information:
Key updates for D1 are primarily in column G.
The spreadsheet contains filters to enable ease of viewing.
Requested actions are shown in Bold.

## R&I Log
Ref from Relevant Reps | Theme | Issue Summary | Current RAG Status | Taken from Natural England’s Relevant Representations - 27/10/2025 | RAG Status Rel Rep - 27/10/2025 | Consultation, actions & progression, following applicant's provision of their SoCG v1 - received 22/12/2025 | RAG Status D1 - 16/01/2026 | Consultation, actions, progression | RAG Status D2 | Consultation, actions, progression | RAG Status D3 | Consultation, actions, progression | RAG Status D4 | Consultation, actions, progression | RAG Status D5 | Consultation, actions, progression | RAG Status D6 | Consultation, actions, progression | RAG Status D7
NE1 | Internationally Designated Sites | Study Area | Green | The Habitats Regulations Assessment (APP-181), paragraph 2.2.2 sets out the study areas used to identify relevant internationally designated sites: - 10km for all sites - 20km for sites supporting birds - 30km for sites supporting bats It is also welcomed that a search beyond these distances has been undertaken to determine hydrological connections. NE consider the study areas used to be appropriate. | Green
NE2 | Internationally Designated Sites | Identification of Sites | Green | No relevant sites are located within the 10km, 20km or 30km study areas, with the nearest site being Birklands and Bilhaugh SAC, approximately 24km to the west of the Order Limits. It has been identified that the River Witham & other watercourses are connected to The Wash SPA and Ramsar and The Wash and North Norfolk Coast SAC, however, resulting from the distance to the Order Limits (70km), no impact pathways have been identified. Despite the hydrological connection, due to the nature of the project, distance downstream, and embedded mitigation (which includes buffer strips from all watercourses, use of HDD for key watercourse crossings, and pollution prevention measures (as detailed in fCEMP Table 4 (APP-189)) NE concur with the conclusion of the HRA and consider that no appreciable effects on the Wash designations are likely. | Green
NE3 | Internationally Designated Sites | In-Combination Assessment | Green | It is noted that the project will not have any appreciable effects upon the qualifying features of any Internationally designated sites; thus, the project cannot combine with any other plans/projects to cause a significant effect. Upon review of the assessment provided, NE concur that no in combination effects are likely. | Green
NE4 | Nationally Designated Sites | Study Area and Identification of Sites | Green | Chapter 12 (APP-033), paragraph 8.5.4 sets out the study area used to identify relevant nationally designated sites: - 5km or: - 200m from the Affected Road Network NE consider the study areas used to be appropriate and note that no relevant sites have been identified. | Green
NE5 | Nationally Designated Sites | Swanholme Lakes SSSI | Green | NE welcome the review of impact pathways between the proposed development and Swanholme Lakes SSSI in response to pre-application advice from NE and the Planning Inspectorate. NE concur that no hydrological links exist and that no further assessment is required. | Green
NE6 | Designated Landscapes | Designated Landscapes | Green | The proposed development is not located within, or within the setting of, any nationally designated landscapes. As a result, NE has no specific comments to make on landscape implications of this development. | Green
NE7 | Protected Species Licencing | Protected Species Licencing | Green | NE have not reviewed protected species survey approaches & results in detail to inform these representations and refer to our protected species standing advice here. Nonetheless, NE welcome the approach to avoid impacts upon protected species via avoidance by design, which is in line with the established ‘mitigation hierarchy’. Ultimately it is the responsibility of the developer to determine the need for any protected species licences. Chapter 8, Table 8-2 (APP-033) states: ‘With embedded mitigation and avoidance, as presented in Table 8-13, there is no requirement for protected species licences as protected species, such as Badger, will be avoided. However, where this may change (e.g. during pre-commencement checks) and if such features cannot be avoided, then NE will be consulted at the earliest opportunity’. As a result, no licence need has been identified and Natural England have not issued any Letters of No Impediment for protected species. As stated, where further survey reveals the need for any protected species licences from Natural England, further consultation will be required, and these will need to be applied for in the usual manner. Natural England are unable to provide a position on the likelihood of a licence being granted without having reviewed a draft licence application. | Green
NE8 | Soils and BMV Land | Development Design and Avoidance of BMV Land | Green | Design Principle 2 of the Planning Statement (APP-185) sets out the design principle of avoidance of BMV land wherever possible. The Planning Statement (APP-185) Appendix A ‘Site Selection Report’ (and it’s appendices in particular) set out clearly how the avoidance of Best and Most Versatile Land has been considered through the design process in line with relevant national policy. Whilst BMV land could not be avoided altogether, it is noted that the site selection process began via excluding all provisionally mapped BMV land, and worked back from there, identifying a suitable site only affecting provisionally mapped Grade 3 land (Planning Statement (APP-185) paragraph 6.3.154). | Green
NE9 | Soils and BMV Land | ALC Survey Methodology | Yellow | NE note that a full detailed ALC survey has been undertaken on the Principle Site, in line with the relevant MAFF 1988 guidelines (APP-161). This is welcomed. However, no ALC survey has been undertaken along the cable route to date. Chapter 12, paragraph 12.4.16 notes that an ALC survey of the Cable Route will be undertaken pre-construction, to inform soil handling and reinstatement. This has been secured within the fCEMP (Table 7, ID SOC-C3). This is also secured in the framework Soil Management Plan (fSMP), paragraph 7.2.2 (APP-192). It is also noted that some areas of the principal site were not surveyed due to varying constraints. NE welcome that these areas will also be surveyed pre-construction, as secured in the fSMP paragraph 7.2.2 (APP-192). ACTION: It is Natural England’s advice that an ALC survey of the full order limits should be undertaken pre-consent, to inform site wide design to avoid BMV land as far as practicable and inform the Soil Management Plan. Nonetheless, it is noted that: - A pre-construction detailed ALC survey has been secured within the fCEMP (Table 7, ID SOC-C3), which will be used to inform the SMP and restoration to the same ALC grade. - There are additional constraints around the cable route siting due to the NatPower Brant BESS scheme and shared cable route (12.4.16) - When applying IEMA’s significance criteria, presence or absence of BMV land in the cable corridor would not constitute a significant effect in EIA terms (Table 12-2 page 20) As such, in this case, this matter is considered not agreed, but unlikely to make a material difference to our advice or the outcome of the decision-making process. | Yellow | Natural England's position is unchanged & we have no further comment on this matter. | Yellow
NE10 | Soils and BMV Land | Assessment Methodology | Yellow | Natural England generally welcome the assessment methodology. Table 12-9 (APP-037) sets out the magnitude criteria for impacts to BMV land in line with IEMA’s guidance (‘A New Perspective on Land and Soil in Environmental Impact Assessment’), indicating that a permanent loss of >20ha fo BMV land would constitute a Major Magnitude effect. This is welcomed. However, Table 12-10 sets out the Sensitivity Criteria for Agricultural Land, indicating that agricultural land of ALC grades 1 & 2 is of High sensitivity, whilst Grade 3a is of medium sensitivity. This is not in line with IEMA’s guidance, having downgraded the sensitivity of BMV land. ACTION: Natural England advise that the Assessment should be amended with the sensitivity of each ALC grade assessed as: • ALC Grade 1 & 2 land: Very High • ALC Grade 3a land: High • ALC Grade 3b land: Medium • ALC Grade 4 & 5 land: Low These criteria are in line with IEMA’s ‘A New Perspective on Land and Soil in Environmental Impact Assessment’ and the ICE (2019) EIA handbook. | Amber | The applicant has provided further clarity on this matter within their draft SoCG (dated 22 December 2025). NE acknowledge the use of different terminology in the ES chapter, but continue to advise that grade 3a land should be classified as a high sensitivity receptor. Nonetheless, it is recognised that in this scenario when applying the IEMA guidance, the conclusion of the ES on this matter woudl remain unchanged. As such, this item is considered unlikely to make a material difference to our advice or the outcome of the decision-making process. See NE13 below for further comment. | Yellow
NE11 | Soils and BMV Land | ALC Survey Results – ALC Grade Boundaries | Green | Figure 12-5 (APP-106), illustrates the ALC grades mapped across the principal site. Natural England note that the ALC boundaries appear to be drawn in strict straight lines, conforming to field boundaries and grid points. Land should be graded and mapped without regard to present field boundaries, except where they coincide with permanent physical features. Usually, it is expected that ALC boundaries would be calculated using an inverse distance weighted modelling tool. ACTION: NE query the methodology used to draw ALC grade boundaries in Figure 12-5. | Amber | The applicant has provided further clarity on this matter within their draft SoCG (dated 22 December 2025). NE welcome the clarity provided on this matter and raise no further concern. | Green
NE12 | Soils and BMV Land | ALC Survey Results – BMV Area Discrepancy | Green | The ALC Survey Report (APP-161) states 241ha of BMV land was identified within the surveyed areas, yet in the ES, Table 12-5 (APP-037) indicates that 282.9ha are BMV. NE have been unable to identify any reasoning within the ES or survey report for this difference. It is noted that the Order Limits cover a smaller area than the ALC survey report, due to changes in the site boundary during the design process, but this should not cause this change in BMV area identified. ACTION: NE request clarity on the Area of the DCO site classified as BMV land. | Yellow | The applicant has provided further clarity on this matter within their draft SoCG (dated 22 December 2025). It is assumed that the ALC survey covered a wider area than the initial RLB, meaning when the RLB was updated, more BMV land which had already been surveyed was included in the order limits, despite the overall size of the site reducing; as such, the ES assessment is based on the relevant ALC survey data. NE raise no further comments. | Green
NE13 | Soils and BMV Land | ALC Survey Results – Assessment of Impacts | Green | The ES sets out that of the Overall site areas of 1018.7ha, 282.9ha of BMV land will be temporarily used for the proposed development. This has been assessed to be a minor adverse effect and not significant. Of the 282.9ha, only 1.5ha of BMV land will be permanently lost as a result of ecological enhancements associated with the proposed development. This has been assessed as a minor adverse effect, which is not significant. As per issue ref NE10, NE consider that all BMV land should be classified as high sensitivity. As a result, this low magnitude impact to a high sensitivity receptor would result in a Moderate, significant impact, as set out in Table 12-14 and paragraph 12.4.49 (APP-037). NE welcome the consideration of the impact of ecological enhancements on BMV land. Often, despite leading to a reduction in available agricultural land, ecological enhancements can retain the soil resource and protect its long-term capabilities. It is where enhancements require intrusive groundworks, or include deep rooting species (i.e. woodland), that they can lead to a permanent loss of BMV resource. ACTION: The assessment of the permanent loss of BMV land should be revisited with regard to NE10. NE also query the ecological enhancements that have been considered to cause this permanent loss of BMV land as a result of the proposed development. | Amber | The applicant has provided further clarity on this matter within their draft SoCG (dated 22 December 2025). NE acknowledge the use of different terminology in the ES chapter & recognise that when using IEMA guidelines, as less than 5ha of Grade 3a land is permanently lost, this is classified as a 'slight' or 'moderate' effect. NE's advice on other projects has been consistent with the assessment of this 'slight' or 'moderate' effect being described as 'minor' in the context of Solar development; as such, we raise no further concerns on this matter. | Green
NE14 | Soils and BMV Land | Time Limit | Green | NE note the inclusion of a 60-year lime limit for the proposed development, secured via Requirement 20. | Green
NE15 | Soils and BMV Land | Soil Management Plan | Green | NE welcome the commitment to produce a detailed SMP pre-construction. NE have reviewed the fSMP provided (APP-192), and generally welcome the principles set out. Some further comment on the fSMP is made at NE16 & NE17. ACTION: An amendment to DCO Requirement 15 is requested to ensure NE are consulted on the detailed soil management plan. | Yellow | The applicant has agreed to include NE as a consultee on the SMP within the draft SoCG (dated 22 December 2025) & this amendment should be included in the updated draft DCO to be submitted at the next examination deadline. | Green
NE16 | Soils and BMV Land | Soil Management Plan – Soil Handling | Green | fSMP paragraph 5.3.3 notes that details of on-site soil moisture assessment techniques will be outlined in the SMP (APP-192). NE recommend the use of the Institute of Quarrying’s ‘Guide to Soil Handling in Mineral Workings’ Supplementary Note 4, in this regard. NE advise that all soils should only be handled in a dry and friable condition, and it is expected that construction programmes would restrict soil handling to the drier summer period to minimise risk of soil damage (April through September) as far as reasonably practicable. Where avoidance of the wetter winter period is not possible, increased supervision by a suitably trained person is necessary, the construction period is likely to need to be generous to allow for stoppage, and further actions must be included in the Soil management Plan to minimise soil damage, in line with DEFRA’s Construction code of practice for the sustainable use of soils on construction sites ACTION: The detailed SMP should include consideration of the avoidance of soil handing in the wetter winter months. It should also set out clear stop-conditions for wet weather working. | Yellow | The applicant has provided further clarity on this matter within their draft SoCG (dated 22 December 2025). Natural England welcome the clarity provided with regard to soil handling. As NE are named as a consultee for the SMP, we are content that this item can be agreed. | Green
NE17 | Soils and BMV Land | Soil Management Plan – Soil Disposal | Green | fSMP Section 6 discusses possible recycling and disposal of soils. ACTION: NE query the need for any soil disposal, as soils should be stored in appropriate bunds for later reinstatement on-site. | Yellow | The applicant has provided further clarity on this matter within their draft SoCG (dated 22 December 2025). NE welcome the acknowledgement that soil disposal is unlikely to be required & soils will be stored appropriately on site for future reinstatement and re-use. | Green
NE18 | Soils and BMV Land | Soil Reinstatement | Green | Natural England welcome the commitment to restoration of the cable route to its original ALC grade. We also welcome the intent that the ALC grade of the principal site will be unaltered through operation and decommissioning, as secured by the fCEMP (Table 7, ID SOC-C3). ACTION: It would be beneficial to present the land take (and amount of BMV) for each part of the development, including temporary construction losses, temporary operational losses, and permanent losses. As a minimum, the detailed SMP should set out in full the methods for reinstatement of each element of the development, to ensure the soil resource is managed effectively and the BMV resource is retained across order limits. | Yellow | The applicant has provided a breakdown of land take for each element of the proposal within their draft SoCG (dated 22 December 2025). This is welcomed by NE and clearly illustrates the amounts of land, and BMV land, to be affected by each element of the proposal. NE also welcome the amendment to the fSMP to ensure full methods for reinstatement of each element of the development are included in the detailed SMP. | Green
NE19 | Other Comments | Biodiversity Net Gain (BNG) | N/A | NE have not reviewed the Biodiversity Net Gain Report ((APP-194)) and metric calculations in detail, however, it is noted that the Report indicates that the proposed development will create gains of 30.64% in Habitat units, 50.62% in Hedgerow unis and 11.83% in Watercourse units. This is welcomed. | N/A
NE20 | Other Comments | Ancient Woodland | Green | No ancient woodland is located within the order limits, although several blocks are located within 2km. There are also several Ancient and Veteran Trees located within the Order Limits. Natural England welcome the approach to retain all Ancient and Veteran Trees within the Order Limits, and note the commitment made in the Design Approach Document (APP-186) Table A-1, including EC3, to retain a 15m buffer from all ancient woodland, and establish similar buffer zones from all ancient/veteran trees based on their individual root protection zones. In the absence of direct effects or loss of Ancient Woodland and Ancient/Veteran Trees, Natural England have no specific comment to make in this regard and refer to Standing Advice. | Green
NE21 | Other Comments | Connecting People with Nature | Green | It is noted that three Public Rights of Way will be permanently diverted as a result of the project; whilst we have no specific comment to make, Natural England welcome the inclusion of the framework Public Rights of Way Management Plan (APP-195) to avoid disruption as far as practicable. NE also welcome the inclusion of several permissive paths through the order limits, to enhance the connectivity of the existing Public Rights of Way network. | Green