## Status
Document reference: EN010157/APP/4.5 Revision 3
Peartree Hill Solar Farm: Detailed Land and Rights Negotiations Tracker
Notes:
1. All interests which are not already acquired at the point of submission should be entered in this tracker and marked as complete (column 'w') when agreement with known interests is reached
2. Any non-agreement is also counted as an objection by an affected person(s) for the purpose of this tracker
3. An entry should also be made where the interest (or potential interest) holder is not known, to allow the relevant information to be added following diligent inquiry, negotiation etc
4. An editable version of this tracker must be submitted to The Planning Inspectorate with the application as an appendix to the Statement of Reasons
Book of Reference plot number 1 | PINS reference number 2 | Description of land rights requested 3 | Category 1 4 |  |  | Agent/ representative 6 | When available Interested party/ affected person reference number 7 | When available Relevant representation reference number 8 | When available Written representation reference number 9 | Other document reference number 10 | Applicant's response references 11 | Duration of temporary rights 12 | Special category (Crown, allotment, National Trust etc) (Select from drop down list) | Special category - other information including confirmation of status 13 | Is the affected person a statutory undertaker and is the land operational? (Select from drop down list) | Protective provision status (Select from drop down list) | Side agreements (Select from drop down list) | Status of objection / negotiations relating to Land Rights acquisition 14 | Heads of Terms for Land Rights (Select from drop down list) | Land Rights agreement Complete (Select from drop down list)
|  |  | Owners | Lessees or tenants | Occupiers
2A-4, 2A-5, 6-7, 10-10 | EN010157/APP/2.4 Rev 4 Sheet 10 of 18, Sheet 6 of 18 & Sheet 2A of 18 | Permanent acquisition of new rights Temporary Possession only (plot 2A-5) | Albanwise Limited |  |  | Cundalls |  | Change two consultation objection made 05.09.25 |  |  |  | 24 months |  |  | Not SU | Not required | Not required | Heads of Terms under discussion with Agent | Draft under discussion | No
17-25, 17-26 | EN010157/APP/2.4 Rev 4 Sheet 17 of 18 | Permanent acquisition of new rights | Albanwise Synergy Limited |  |  | Cundalls | [8 empty] | Not SU | Not required | Not required | Heads of Terms under discussion with Agent | Draft under discussion | No
15-7 | EN010157/APP/2.4 Rev 4 Sheet 15 of 18 | Permanent acquisition of new rights | Angela Mary Nicholson and Stuart Nicholson |  |  | Ullyotts | [8 empty] | Not SU | Not required | Not required | Heads of Terms under discussion with Agent | Draft under discussion | No
16-8, 16-9, 16-10, 17-1 | EN010157/APP/2.4 Rev 4 Sheet 16 of 18 & 17 of 18 | Permanent acquisition of new rights | Caroline Jane Palmer and Jonathan William Palmer |  |  | Frank Hill & Son | [8 empty] | Not SU | Not required | Not required | Heads of Terms under discussion with Agent | Draft under discussion | No
10-1, 10-3, 10-12, 13-1 | EN010157/APP/2.4 Rev 4 Sheet 10 of 18 & Sheet 13 of 18 | Permanent acquisition of new rights | Clare Norman and Michael Henry Norman |  |  | Brockthorpe Consultancy Ltd | [8 empty] | Not SU | Not required | Not required | Heads of Terms under discussion with Agent | Draft under discussion | No
7-3 | EN010157/APP/2.4 Rev 4 Sheet 7 of 18 | Permanent acquisition | Clare Norman and Michael Henry Norman |  |  | Brockthorpe Consultancy Ltd | [8 empty] | Not SU | Not required | Not required | Option Agreement signed | Agreed | Yes
15-9, 15-11, 15-12, 15-14, 15-17, 16-1 | EN010157/APP/2.4 Rev 4 Sheet 15 of 18 & Sheet 16 of 18 | Permanent acquisition of new rights | Coletta Holdings Limited |  |  | N/A | [8 empty] | Not SU | Not required | Not required | Heads of Terms under discussion with landowner | Draft under discussion | No
2A-1, 2A-3, 13-6, 13-8, 14-1, 14-3, 15-13 | EN010157/APP/2.4 Rev 4 Sheet 2A of 18 Sheet 13 of 18, Sheet 14 of 18 & Sheet 15 of 18 | Permanent acquisition of new rights Temporary Possession only (plot 2A-1 & 2A-3) | East Riding Of Yorkshire Council (Landowner) |  | Beverley Pasture Masters Plots 13-6, 13-8, 14-1 (Occupier) Clive Phillip Nicholson Plot 15-13 (Occupier) | N/A |  | RR-001 East Riding of Yorkshire Council |  |  |  | 24 months | Commons and Open Space (13-6, 13-8, 14-1) |  | SU and not operational | Not required | Not required | Heads of Terms under discussion with landowner | Draft under discussion | No
15-13 | EN010157/APP/2.4 Rev 4 Sheet 15 of 18 | Permanent acquisition of new rights | East Riding Of Yorkshire Council (Landowner) |  | Clive Phillip Nicholson (Occupier) | Frank Hill & Son | [8 empty] | Not SU | Not required | Not required | Heads of Terms under discussion with Agent
13-6, 13-8, 14-1 | Sheet 2A of 18 | Permanent acquisition of new rights | East Riding Of Yorkshire Council (Landowner) |  | Beverley Pasture Masters (Occupier) | Michael Glover LLP on behalf of Beverley Pasture Masters |  | RR-018 Beverley Pasture Masters |  |  |  |  | Commons and Open Space (13-6, 13-8, 14-1) |  | Not SU | Not required | Not required | Heads of Terms under discussion with Agent | Draft under discussion | No
15-3 | Sheet 13 of 18, Sheet 14 of 18 & Sheet 15 of 18 | Permanent acquisition of new rights | Margaret Rodmell (Formerly Geoffrey Rodmell and William Rodmell) |  |  | Ullyotts | [8 empty] | Not SU | Not required | Not required | Heads of Terms under discussion with Agent | Draft under discussion | No
14-13, 15-2 | EN010157/APP/2.4 Rev 4 Sheet 14 of 18 & Sheet 15 of 18 | Permanent acquisition of new rights | Jayne Briggs, Katie Jayne Sutton, Nikolas Rupert Harry Briggs |  |  | DDM Agriculture | [8 empty] | Not SU | Not required | Not required | Heads of Terms under discussion with Agent | Draft under discussion | No
15-15, 16-2, 16-4, 16-5, 16-6 | EN010157/APP/2.4 Rev 4 Sheet 15 of 18 & Sheet 16 of 18 | Permanent acquisition of new rights | John Alderson Atkinson |  |  | Dee Atkinson & Harrison | [8 empty] | Not SU | Not required | Not required | Heads of Terms under discussion with Agent | Draft under discussion | No
14-10 | EN010157/APP/2.4 Rev 4 Sheet 14 of 18 | Permanent acquisition of new rights | John Henry Wiles, Susan Lesley Wiles, John Smith, Keith Smith |  |  | Dee Atkinson & Harrison | [8 empty] | Not SU | Not required | Not required | Heads of Terms under discussion with Agent | Draft under discussion | No
17-8 | EN010157/APP/2.4 Rev 4 Sheet 17 of 18 | Permanent acquisition of new rights | Keyland Developments Limited |  |  | Carter Jonas | [8 empty] | Not SU | Not required | Not required | Heads of Terms under discussion with Agent | Draft under discussion | No
13-3 | EN010157/APP/2.4 Rev 4 Sheet 13 of 18 | Permanent acquisition of new rights | Malcolm Thompson Pearson |  |  | Frank Hill & Son | [8 empty] | Not SU | Not required | Not required | Heads of Terms signed. Option and easement agreements being documented by parties' solicitors | Agreed | No
15-6 | EN010157/APP/2.4 Rev 4 Sheet 15 of 18 | Permanent acquisition of new rights | The Executors of Michael Wingfield Boyce (c/o Penelope Jayne Wood and John Eliot Boyce) |  |  | Dee Atkinson & Harrison | [8 empty] | Not SU | Not required | Not required | Heads of Terms under discussion with Agent | Draft under discussion | No
14-12, 15-1 | EN010157/APP/2.4 Rev 4 Sheet 14 of 18 & Sheet 15 of 18 | Permanent acquisition of new rights | RFB Trustees One Limited and RFB Trustees Two Limited |  |  | Mark Caley (Agent) Wilkin Chapman Rollits (Solicitors) | [8 empty] | Not SU | Not required | Not required | Heads of Terms under discussion with Agent | Draft under discussion | No
15-5 | EN010157/APP/2.4 Rev 4 Sheet 15 of 18 | Permanent acquisition of new rights | Richard Soper and Vikki Long | [11 empty] | Not SU | Not required | Not required | Heads of Terms signed. Option and easement agreements being documented by parties' solicitors | Agreed | No
15-4 | EN010157/APP/2.4 Rev 4 Sheet 15 of 18 | Permanent acquisition of new rights | Sally Mathews |  |  | Clubleys | [8 empty] | Not SU | Not required | Not required | Heads of Terms under discussion with Agent | Draft under discussion | No
10-13, 13-2 | EN010157/APP/2.4 Rev 4 Sheet 10 of 18 & Sheet 13 of 18 | Permanent acquisition of new rights | Ferry Three Fields Limited |  |  | Frank Hill & Son | [8 empty] | Not SU | Not required | Not required | Heads of Terms under discussion with Agent | Draft under discussion | No
17-2, 17-3, 17-6 | EN010157/APP/2.4 Rev 4 Sheet 17 of 18 | Permanent acquisition of new rights | Simon Metcalf Calvert |  |  | R Hornsey and Sons | [8 empty] | Not SU | Not required | Not required | Heads of Terms under discussion with Agent | Draft under discussion | No
13-4 | EN010157/APP/2.4 Rev 4 Sheet 13 of 18 | Permanent acquisition of new rights | The King's Most Excellent Majesty In Right Of His Crown |  |  | Carter Jonas | [6 empty] | Crown land | Crown Consent being negotiated between parties solicitors and anticipated to be secured before the end of examination | Not SU | Not required | Draft under discussion | Heads of Terms under discussion with Agent. Agreement anticipated to be reached before close of examination | Draft under discussion | No
14-7, 14-17 | EN010157/APP/2.4 Rev 4 Sheet 14 of 18 | Permanent acquisition of new rights | Mary Hodgson Atkin |  |  | Michael Glover LLP | [8 empty] | Not SU | Not required | Not required | Heads of Terms under discussion with Agent | Draft under discussion | No
15-10 | EN010157/APP/2.4 Rev 4 Sheet 15 of 18 | Permanent acquisition of new rights | Fred Robinson |  | East Riding of Yorkshire Council Adopted Public Highway | Peter Ward Homes | [8 empty] | Not SU | Not required | Not required | Heads of Terms under discussion with Agent | Draft under discussion | No
14-11 | EN010157/APP/2.4 Rev 4 Sheet 14 of 18 | Permanent acquisition of new rights | George James Rogerson | [11 empty] | Not SU | Not required | Not required | Heads of Terms signed. Option and easement agreements being documented by parties' solicitors | Agreed | No
1-5, 2-5, 2-6, 2-16, 2-18, 2-19, 3-3, 3-15, 3-17, 5-1 | EN010157/APP/2.4 Rev 4 Sheet 1 of 18, Sheet 2 of 18, Sheet 3 of 18 & Sheet 5 of 18 | Permanent acquisition, Permanent acquisition of new rights (plots 2-19 & 3-15) | Caroline Mary Caley |  |  |  |  | REP2-157 Objection to using Plot 2-6 as a passing place made 10.09.25 | [6 empty] | Not SU | Not required | Not required | Option Agreement signed. The Applicant is in discussion with the landowner to amend the option agreement to incorporate plots 2-5 & 2-6. | Agreed | Yes
2-4, 2-7, 2-8, 2-9, 2-10, 2-11, 2-12a, 2-12b, 2-13, 2-15, 6-1, 11-1, 12-4, 12-7 Plots 2-4, 11-1, 12-4 & 12-7 jointly owned, see rows 40 & 50 below | EN010157/APP/2.4 Rev 4 Sheet 2 of 18, Sheet 6 of 18, Sheet 11 of 18 & Sheet 12 of 18 | Permanent acquisition, Permanent acquisition of new rights (plot 2-12a) Temporary possession only (plots 2-7, 2-8, 2-12b & 2-13) | Howard Noel Sinkler & Ian Harold Sinkler |  |  |  |  | REP2-156 Objection made 15.09.25 to the removal of any hedges on Meux Lane |  |  |  | 24 months |  |  | Not SU | Not required | Not required | Option Agreement signed. The Applicant is in discussion with the landowner to amend the option agreement to incorporate plots 2-4, 2-9, 2-10, 2-11 & 2-12a | Agreed | Yes
2-4, 11-1, 12-4, 12-7 plots jointly owned, see row 39 above and row 50 below | EN010157/APP/2.4 Rev 4 Sheet 2 of 18, Sheet 11 of 18 & Sheet 12 of 18 | Permanent acquisition | Harold Sinkler | [14 empty] | Option Agreement signed. The Applicant is in discussion with the landowner to amend the option agreement to incorporate plot 2-4. | Agreed | Yes
1-14, 5-12, 8-1, 8-4 Plots 1-14, 5-12. 8-1 & 8-4 jointly owned, see row 41 below | EN010157/APP/2.4 Rev 4 Sheet 1 of 18, Sheet 5 of 18 & Sheet 8 of 18 | Permanent acquisition | Hugh Adrian Bethell, Robert Charles Orlando Hellyer & William Anthony Bethell | [11 empty] | Not SU | Not required | Not required | Option Agreement signed | Agreed | Yes
1-14, 3-12, 4-2, 4-3, 4-10, 5-3, 5-12, 8-1, 8-4. Plots 1-14, 5-12. 8-1 & 8-4 jointly owned, see row 40 above | EN010157/APP/2.4 Rev 4 Sheet 1 of 18, Sheet 3 of 18, Sheet 4 of 18, Sheet 5 of 18 & Sheet 8 of 18 | Permanent acquisition, Temporary possession only (plot 4-10) | William Anthony Bethell | [8 empty] | 24 months |  |  | Not SU | Not required | Not required | Option Agreement signed The Applicant is in discussion with the landowner to amend the option agreement to incorporate plots 4-2 & 4-3. | Agreed | Yes
9-9, 12-3 | EN010157/APP/2.4 Rev 4 Sheet 9 of 18 & Sheet 12 of 18 | Permanent acquisition | James Arthur Stephenson | [11 empty] | Not SU | Not required | Not required | Option Agreement signed | Agreed | Yes
9-6 | EN010157/APP/2.4 Rev 4 Sheet 9 of 18 | Permanent acquisition of new rights | James Edward Farnaby |  |  | Dee Atkinson & Harrison | [8 empty] | Not SU | Not required | Not required | Heads of Terms under discussion with Agent | Draft under discussion | No
1-12 | EN010157/APP/2.4 Rev 4 Sheet 1 of 18 | Temporary possession only | Joanna Rebecca Hosdell and William Tuke Hosdell |  |  | Clubleys | [5 empty] | 24 months |  |  | Not SU | Not required | Not required | Heads of Terms signed. Option and easement agreements being documented by parties' solicitors | Agreed | No
4-4 | EN010157/APP/2.4 Rev 4 Sheet 4 of 18 | Temporary possession only | Julian Benjamin Jackson | [8 empty] | 24 months |  |  | Not SU | Not required | Not required | Heads of Terms under discussion with landowner | Draft under discussion | No
2-3 | EN010157/APP/2.4 Rev 4 Sheet 2 of 18 | Permanent acquisition | Oscar Stevenson and Ottilie Anna Stevenson | [11 empty] | Not SU | Not required | Not required | Heads of Terms under discussion with landowner | Draft under discussion | No
9-8 | EN010157/APP/2.4 Rev 4 Sheet 9 of 18 | Permanent acquisition of new rights | Pia Christina Oudijk and Redeeris Hendric Dirk Oudijk | [11 empty] | Not SU | Not required | Not required | Heads of Terms have been sent by Applicant but landowners refused to open negotiations or discussions with Applicant |  | No
1-4, 2-21, 3-1, 3-20, 5-5 | EN010157/APP/2.4 Rev 4 Sheet 1 of 18, Sheet 2 of 18, Sheet 3 of 18 & Sheet 5 of 18 | Permanent acquisition, Permanent acquisition of new rights (plot 5-5) | Richard Guy Caley | [11 empty] | Not SU | Not required | Not required | Option Agreement signed | Agreed | Yes
2-4 Plot jointly owned, see rows 40 & 50 above | EN010157/APP/2.4 Rev 4 Sheet 2 of 18 | Permanent acquisition | The Executor of Barbara Ann Sinkler | [11 empty] | Not SU | Not required | Not required | Heads of Terms under discussion with landowner | Draft under discussion | No
1-1, 1-3, 1-7, 1-10, 1-13, 1-15, 1-16, 3-4 | EN010157/APP/2.4 Rev 4 Sheet 1 of 18 & Sheet 3 of 18 | Permanent acquisition, Permanent acquisition of new rights (plots 1-7 & 1-15), Temporary possession only (plots 1-10 & 1-16) | Thomas Stephen Caley |  |  |  |  | REP2-157 Objection to using Plot 2-6 as a passing place made 10.09.25 |  |  |  | 24 months |  |  | Not SU | Not required | Not required | Option Agreement signed. The Applicant is in discussion to amend the option agreement to incorporate plots 1-10 (Temporary possession) | Agreed | Yes
2-17, 5-4, 6-2, 6-4, 6-5, 6-6, 7-1, 7-2, 9-2, 9-3, 9-4, 9-5, 10-2 | EN010157/APP/2.4 Rev 4 Sheet 2 of 18, Sheet 5 of 18, Sheet 6 of 18, Sheet 7 of 18, Sheet 9 of 18 & Sheet 10 of 18 | Permanent acquisition, Permanent acquisition of new rights (plot 9-5) | The Official Custodian For Charities on Behalf of The Leonard Chamberlain Trust (Landowner) | Eric Albert Robinson Ribey Plots 6-6, 7-1, 7-2, 9-4, 9-5, 10-2 (Tenant) | [10 empty] | Not SU | Not required | Not required | Option Agreement signed | Agreed | Yes
2-17, 5-4, 6-2, 6-4, 6-5, 6-6, 7-1, 7-2, 9-2, 9-3, 9-4, 9-5, 10-2 | EN010157/APP/2.4 Rev 4 Sheet 2 of 18, Sheet 5 of 18, Sheet 6 of 18, Sheet 7 of 18, Sheet 9 of 18 & Sheet 10 of 18 | Permanent acquisition, Permanent acquisition of new rights (plot 9-5) | The Official Custodian For Charities on Behalf of The Leonard Chamberlain Trust (Landowner) | George Andrew Beaulah Plots 2-17, 5-4, 6-2, 6-4, 9-2 (Tenant) | [10 empty] | Not SU | Not required | Not required | Option Agreement signed | Agreed | Yes
16-5, 16-9 | EN010157/APP/2.4 Rev 4 Sheet 16 of 18 | Permanent acquisition of new rights | Ineos Manufacturing (Hull) Limited |  |  | Eversheds Sutherland (Solicitors) | [8 empty] | SU and known operational | Not required | Not required | Heads of Terms under discussion with landowner's solicitor | Draft under discussion | No
3-14, 3-16, 3-18, 5-10, 13-7, 14-2 | EN010157/APP/2.4 Rev 4 Sheet 3 of 18, Sheet 5 of 18, Sheet 13 of 18 & Sheet 14 of 18 | Permanent acquisition of new rights, Permanent acquisition (plot 3-16) | Environment Agency |  |  | N/A |  | RR-005 | [6 empty] | SU and known operational | Agreed and in latest version of DCO | Not required | Heads of Terms under discussion with landowner. Protective Provisions agreed. | Draft under discussion | No
17-5, 17-7, 17-11, 17-12, 17-13, 17-14, 17-15, 17-16, 17-17, 17-18, 17-19, 17-20, 17-21, 17-22, 17-23, 17-26 | EN010157/APP/2.4 Rev 4 Sheet 17 of 18 | Permanent acquisition of new rights | National Grid Electricity Transmission plc (Landowner) | Northern Powergrid (Yorkshire) plc Plots 17-7, 17-9, 17-11, 17-14, 17-15, 17-19, 17-20, 17-22 (Tenant) |  | Addleshaw Goddard LLP (Solicitors) |  | RR-010 National Grid Electricity Transmissions plc | [6 empty] | SU and known operational | Draft under discussion | Not required | Heads of Terms under discussion with landowner. Protective Provisions under negotiation with NGET's solicitor | Draft under discussion | No
17-7, 17-11, 17-14, 17-15, 17-19, 17-20, 17-22 | EN010157/APP/2.4 Rev 4 Sheet 17 of 18 | Permanent acquisition of new rights | National Grid Electricity Transmission plc (Landowner) | Northern Powergrid (Yorkshire) plc Plots 17-7, 17-11, 17-14, 17-15, 17-19, 17-20, 17-22 (Tenant) |  | Weightmans LLP (Solicitors) |  | RR-015 Northern Powergrid (Yorkshire) plc | [6 empty] | SU and known operational | Draft under discussion | Draft under discussion | Heads of Terms under discussion with landowner. Protective Provisions and side agreement under negotiation with Northern Power Grid's solicitor | Draft under discussion | No
16-7 | EN010157/APP/2.4 Rev 4 Sheet 16 of 18 | Permanent acquisition of new rights | East Riding of Yorkshire Council [registered currently as the Secretary of State For Transport / National Highways.] The section of road is a detrunked route. The A1079 Trunk Road (County Boundary to Dunswell Drain) (Detrunking) Order 2003. This has now been transferred to the Local Highway Authority (East Riding of Yorkshire). |  | East Riding of Yorkshire Council Adopted Public Highway [currently listed as occupier but are owners] | N/A |  | RR-011 National Highways | [6 empty] | SU and known operational | Not required | Not required | Email received from National Highways 21.01.25 confirming that this land has now been transferred to the Local Highway Authority (East Riding of Yorkshire) and National Highways no longer holds an interest. Any works and grants required by the Applicant will be dealt with under the DCO | None drafted | No
3-5 | EN010157/APP/2.4 Rev 4 Sheet 3 of 18 | Permanent acquisition of new rights | The County Council of Humberside |  | East Riding of Yorkshire Council Adopted Public Highway | N/A | [8 empty] | SU and known operational | Not required | Not required | No land agreement sought with the County Council as East Riding of Yorkshire have confirmed at a meeting held on 17.02.25 with the Applicant’s Agent that this road is in the process of being transferred to them as the Local Highway Authority. Once held by the East Riding of Yorkshire Council, any works and grants required by the Applicant will be dealt with under the DCO | None drafted | No
16-3 | EN010157/APP/2.4 Rev 4 Sheet 16 of 18 | Permanent acquisition of new rights | Unknown / Unregistered - (Network Rail) Rail tracks between HS21117 on the west and east and YEA95539 to the north. |  | Network Rail Infrastructure Limited | Addleshaw Goddard LLP (Solicitors) |  | RR-013 | [6 empty] | SU and known operational | Draft under discussion | Draft under discussion | Heads of Terms under discussion with landowner. Protective Provisions and framework Agreement under negotiation with Network Rail's solicitors | Draft under discussion | No
12-8, 14-16 | EN010157/APP/2.4 Rev 4 Sheet 12 of 18 & Sheet 14 of 18 | Permanent acquisition, Permanent acquisition of new rights (plot 14-16) | National Gas plc |  |  | Fisher German LLP (Agent) Addleshaw Goddard LLP (Solicitors) |  | RR-009 | [6 empty] | SU and known operational | Draft under discussion | Not required | Heads of Terms under discussion with Agent. Protective Provisions under negotiation with National Gas Transmission's solicitor | Draft under discussion | No
12-6, 12-8, 12-9 | EN010157/APP/2.4 Rev 4 Sheet 12 of 18 | Permanent acquisition | JBM Solar Projects 33 Limited | [11 empty] | Not SU | Not required | Not required | No agreement required as the landowner is part of the RWE group | None drafted | Yes
1 Plot number from the Book of Reference
2 Plan reference number from the Book of Reference and Examination Library reference
3 Description of land and rights requested from the Book of Reference including restrictive covenants
4 A person is within category 1 if the applicant, after making diligent inquiry, knows that the person is an owner, lessee, tenant (whatever the tenancy period) or occupier of the land, see section 57 (1) of the Planning Act 2008
5 A person is within category 2 if the applicant, after making diligent inquiry knows that the person: interested in the land or has the power to sell or convey the land or to release the land, see section 57(20) of the Planning Act 2008
6 Person or organisation representing the interests of the affected person(s) - enter N/A if the affected person(s) are representing themselves
7 Reference number assigned to each interested party and affected person - for Planning Inspectorate use only
8 Reference number assigned to each relevant representation in the Examination Library
9 Reference number assigned to each written representation in the Examination Library
10 Reference number assigned to any other document in the Examination Library
11 Reference numbers assigned to all of the applicant's responses in the Examination Library including specific reference to relevant sections within documents
12 Likely duration of any temporary rights such as temporary possession
13 Where crown land is affected, this column should include the anticipated date of consent from the crown authority
14 Narrative on negotiations to date

## Data types
Data types | Special category | Statutory undertaker (SU) and operational land status | Protective provisions status | Side agreements | Heads of Terms | Complete
Options | Crown land | Not SU | Not required | Not required | None drafted | Yes
| National Trust | SU and known operational | Draft under discussion | Draft under discussion | Draft under discussion | No
| Allotment | SU and unknown operational | Agreed | Agreed | Agreed
| Commons | SU and disputed operational | Agreed and in latest version of DCO |  | Draft under discussion Agreed
| Open space | SU and not operational | No agreement on final version
Other
Commons and Open Space (13-6, 13-8, 14-1)