## Sheet1
Ref from Relevant Reps | Theme | Current RAG Status | NE RR Commentary & Advice | NE Comment on Mechanism for securing resolution | RAG Status Rel Rep - May 25 | Consultation, actions, progression | RAG Status D1 | Consultation, actions, progression | RAG Status D2 | Consultation, actions, progression | RAG Status D3 | Consultation, actions, progression | RAG Status D4 | Consultation, actions, progression | RAG Status D5 | Consultation, actions, progression | RAG Status D6 | Consultation, actions, progression | RAG Status D7 | Consultation, actions, progression | RAG Status D8
NE01 | Protected Sites | Green | The Humber Estuary SAC and Humber Estuary Ramsar include the designated features River lamprey, Lampetra fluviatilis, and Sea lamprey, Petromyzon marinus (hereby referred to collectively as “lamprey”). The River Trent is functionally linked for adult lamprey travelling upstream to spawning sites on gravel beds and the juveniles (ammocetes) residing in silts before travelling back to the designated sites. The Project has potential to impact on these species due to proximity to the functionally linked waterway and proposed trenchless crossing below the River Trent. The Project has embedded design features to avoid impacts and environmental management plans in place to mitigate remaining potential impacts from construction and decommissioning: APP-035 6.6 Chapter 6 - Biodiversity, Table 6 C2, trenchless crossing has been chosen as a method of cable installation under the River Trent to avoid direct impacts to the river bed. This is an acceptable approach where design features and mitigation measures are in place to avoid and mitigate associated impacts. The following measures discussed are appropriate to avoid and mitigate impacts from the trenchless cable crossing. -APP-035 6.6 Chapter 6 - Biodiversity, Table 6 C2, includes measures to manage risks of drilling fluid entering the watercourse through the drill profile and distance of the crossing compounds from the bank top. This is intended for any spillages to be negligible. Natural England agree with this approach in combination with the site-specific hydraulic fracture risk assessment and a bentonite fluid breakout plan (see below point). -APP-176 7.4 Outline Construction Environmental Management Plan, Table 3.5, includes further measures to manage drilling fluid breakout including a site-specific hydraulic fracture risk assessment and a bentonite fluid breakout plan, both to be included in the final CEMP. Natural England agree with this approach. -APP-035 6.6 Chapter 6 - Biodiversity, Table 6 C4, notes minimum buffer distances of 16m for works from the river bank and 5m below the riverbed to avoid direct impacts from construction and decommissioning run off and drilling fluid breakout. Natural England agree with this approach. -APP-176 7.4 Outline Construction Environmental Management Plan, Table 3.5, includes measures to manage additional silt reaching the watercourse including directing all run off to sewers, not to a watercourse, and to include the additional feature of settling tanks. Natural England agree with this approach. -APP-176 7.4 Outline Construction Environmental Management Plan, Table 3.5, includes a buffer distance of >20m from the river bank for soil storage and working soils only in dry weather. This should minimise additional fine matter from reaching the watercourse. Natural England agree with this approach. -APP-035 6.6 Chapter 6 - Biodiversity, Table 6 C12, confirms the project will monitor lamprey for five years to ensure impacts from EMF barrier effects are not impacting lamprey during operation. This is to be co-ordinated with NE, EA and other Projects using trenchless drilling under the River Trent. This is the approach agreed with previous Projects to understand further any barrier impacts from EMF to lamprey in the absence of evidence. Natural England agree with this approach. -APP-165 5.2 Shadow Habitat Regulation Assessment, 3.1.6, screened lamprey in for Appropriate Assessment as Likely Significant Effect could not be ruled out. Natural England agree with this decision. -APP-165 5.2 Shadow Habitat Regulation Assessment, 4.1.3 notes the measures included to avoid and mitigate impacts to the designated species with the appropriate commitments. This includes the monitoring of lamprey species to confirm no barrier effects from the cables emitting EMF during operation. -APP-165 5.2 Shadow Habitat Regulation Assessment, 4.1.7 notes the Project will have negligible impacts on lamprey due to the design and mitigation measures outlined with the addition of monitoring. As such this concludes no adverse effect on the integrity of the Humber Estuary SAC and Ramsar site. Natural England agree with this approach, pending the results of the monitoring. | The discussed design (avoidance) and mitigation measures are suitable to bring impacts from the Project to the designated lamprey species of the Humber Estuary SAC and Ramsar site to negligible levels. This should include outline environmental management plans becoming full environmental management plans and including the measures specified at the outline stage. They should be secured by requirement of the DCO, as outlined in the APP-187 7.15 Commitments Register, paragraph 1.1.2. Monitoring of potential barrier effects from EMF impacting lamprey species, in collaboration with EA, NE and other projects with cables crossing the River Trent with trenchless drilling, for no longer than 5 years, should be secured by requirement of the DCO. | Green | No update | Green | Examiner's Question 8.0.9 - (1) We note that NE appear to have agreed with the approach of the Applicant in considering both the previous questions. Could NE/Applicant please provide an explanation why 16m would be considered a suitable set off distance and why in respect of lamprey and their life cycle 5 years would be regarded as suitable timeframe to understand any effects. NE response - (1) Natural England are satisfied that the set off distance of 16m in combination with the measures outlined in the Construction Environment Management Plan (including a sitespecific hydraulic fracture risk assessment and a bentonite fluid breakout plan) is precautionary enough to avoid impacts from construction to functionally linked habitat of lamprey species using the River Trent from the Humber Estuary Special Area of Conservation and Ramsar site. The five years’ timeframe for monitoring is in line with the approach taken forward by other Projects with trenchless cable crossing under the River Trent, to assess barrier impacts to migrating lamprey species from EMF. A minimum of four consecutive years has been put forward for monitoring within the proposal from the University of Hull. As such, Natural England are satisfied with the timeframe put forward by the Project. | Green | No update | Green | Planning Inspectorate have submitted the RIES. It is in line with previous comments from NE, as such no comments from NE at this time. | Green
NE02 | Protected Sites | Green | APP-035 6.6 Chapter 6 – Biodiversity, Table 6.8, notes Spalford Warren SSSI is scoped out of further assessment. Natural England agree with this conclusion as the only potential impact pathway from the Project to this site is from additional air pollution from increased traffic. As outlined in APP-137 6.21 Chapter 13 Appendices 13.1 - 13.5, Table A13.4.2, Average Annual Daily Trips (AADT) of HGVs will be below 200 and so there is no likely significant effect on the designated features at the site from additional air pollution generated by traffic from the Project. | No further comments | Green
NE03 | Species | Green | APP-035 6.6 Chapter 6 – Biodiversity, Table 6.6 C11. Further assessment of the of the winter bat activity would be useful to understand further how bats are utilising the habitat year-round or justification for not undertaking hibernation surveys to be provided. | Winter bat activity surveys or justification for not including must be provided to NE. | Yellow | 14/07/25 - At joint ecology update, Applicant confirmend no suitable habitat for bat hibernation in survey area. Should be recorded in SoCG. Keeping Yellow until confirmed in SoCG. | Yellow | This has been addressed and justified in the Applicant’s response to relevant representations [REP1-075] and noted in the SoCG. Agreed in the SoCG. | Green
NE04 | BNG | n/a | APP-093 6.21 Appendix 6.10 Biodiversity Net Gain Assessment. Natural England welcome the commitment to providing BNG well over the suggested 10% provision (paragraph 4.2) and securing this for the lifetime of the project through the DCO (paragraph 3.1.4) despite the provision for BNG in NSIPs not yet being mandatory (paragraph 1.1.4). We welcome the approach taken to engage local stakeholders in the development of the BNG strategy to ensure it works for the local environment (APP-035 6.6 Chapter 6 – Biodiversity, Table 6.5). | We suggest securing a BNG commitment of at least 10% and ongoing Habitat Management and Monitoring Plan for the lifetime of the project via a requirement of the DCO. | n/a | No action / change. | n/a | Agreed in SoCG as it is secured by requirements | n/a
NE07 | CPwN | Green | APP-179 7.7 Outline Landscape and Ecology Management Plan paragraphs 4.1.12-16. Natural England welcome the provision of new permissive paths and improvements to existing pathways within the Order Limits including the Sustrans route. APP-186 7.14 Outline Public Right of Way Management Plan paragraph 3.2.1. We note access for people to PRoW will be maintained through management of PRoW during construction via the PRoW MP. | Ensure the LEMP and PRoW MP are secured by requirement of the DCO. | Green
NE08 | Soils & BMV | Green | APP-032 6.3 Detailed soil sampling is noted and welcomed. | No further comment | Green
NE09 | Soils & BMV | Green | APP-037 8.2.1 As per Natural England’s previous PEIR response (our ref 476290, dated 8th July 2024, paragraph 2.4) - The British Society of Soil Science has published the Guidance Note Benefitting from Soil Management in Development and Construction, which also contains useful guidance. | Refer to the Guidance Note Benefitting from Soil Management in Development and Construction within the Technical Guidance used for Assessment and Soil Management Plan. | Yellow | No update from Applicant. Should be recorded in SoCG. Keeping Yellow until confirmed in SoCG. | Yellow | Guidance not used, citing the Defra Construction Code of Practice instead. Suggested it is used as well as to add robustness to the SMP. Remains under discussion in the SoCG. | Yellow | No update | Yellow | Updated in SoCG following a meeting with the Applicant on 15/09/25. Agreed this point as BSSS guidance is additional and welcome but not essential. | Green
NE10 | Soils & BMV | Green | APP-037 8.3.17 As per Natural England’s previous PEIR response (our ref 476290, dated 8th July 2024, paragraph 2.8) - The temporary displacement of soil as a result of the underground cable installation and temporary haul and access roads/construction compounds can result in permanent land quality change and soil damage if undertaken inappropriately. Therefore, Natural England support the commitment to consider these impacts in the oSMP/SMP. This is required for consultees and decision makers to understand the extent (ha) and likely long-term impacts on agricultural land quality (ALC grade). | Management of stored soils should also be considered in the operational phase and managed in accordance with a Soil Management Plan (SMP) – covered in later paragraph 8.5.18. | Green
NE11 | Soils & BMV | Green | APP-037 8.5.8 Reiteration: All soils should only be handled in a dry and friable condition, and it is expected that soil handling will be confined to the drier summer period (April through September) to minimise risk of soil damage. Soil handling should normally be avoided during October to March inclusive, irrespective of soil moisture conditions, because it will generally not be possible to establish green cover over winter to help dry out soils and protect them from erosion. This would minimise the need to recondition soils, which requires additional space and time. This is particularly important for land to be restored to agricultural use. Soil handling methods should normally be as specified as in the Defra Construction Code of Practice for the Sustainable Use of Soils on Construction Sites (including accompanying Toolbox Talks). A field suitable method for assessing whether soils are in a dry and friable condition based on plastic limits set out in Part One (Explanatory Note 4 – Table 4.2 provided below in Annex 1) of the Institute of Quarrying’s Good Practice Guide for Handling Soils in Mineral Working, and this approach together with the associated rainfall protocols should be adopted. | Soils should only be handled in a dry and friable condition. The aforementioned guidance should be referenced and followed in the SMP. The full SMP should be informed by the oSMP and secured by requirement of the DCO. | Green
NE12 | Soils & BMV | Green | APP-105 A detailed review of the data has been undertaken, and the presented data methodology appears reasonably robust, following the MAFF (1988) Agricultural Land Classification for England and Wales: Guidelines and Criteria for Grading the Quality of Agricultural Land. | The name, qualification and experience of the lead surveyor undertaking the ALC survey work is not given. This is important to demonstrate the likely competence of the lead surveyor. Natural England suggest this is included in the report. | Green
NE13 | Soils & BMV | Green | APP-182 3.1.3 There is potential for compaction to occur underneath panels that cannot be ameliorated utilizing traditional farm operations. | Further information would be useful to clarify how compaction under the PV array will be considered during construction and does not continue during the operational lifespan. | Yellow | No update from Applicant. Should be recorded in SoCG. Keeping Yellow until confirmed in SoCG. | Yellow | Linked to Q3.0.2 of ExQ1. Suggested this is followed up and maintenance of solar arrays be included in the SMP for operational phase. Remains under discussion in SoCG. | Yellow | No update | Yellow | Updated in SoCG following a meeting with the Applicant on 15/09/25. Suggested this remains under discussion. Reduced agricultural practices will likely result in less potential for compaction but it’s important to address grazing practices in the LEMP to avoid overgrazing etc. There’s evidence to suggest higher compaction (~14%) underneath panels than in the gaps. This highlights the needs for greater controls during construction and ensuring that land beneath the panels is vegetated prior to installation. This will avoid the need for remediation during operational periods and decommissioning. | Yellow | No update | Yellow | No update, remains under discussion. Awaiting confirmation of changes to LEMP to insure potential impacts from soil compaction are addressed. This includes: - grazing practices to maintain vegetative cover and, - vegetation in place ahead of construction. | Yellow | Agreed in SoCG as the Applicant has committed to following the Defra Code of practice for the sustainable use of soils on construction sites within the SMP. It would be recommended to have establishment of grassland ahead of construction to ensure mitigation is bedded in ahead of construction works. | Green
NE14 | Soils & BMV | Green | APP -182 3.1.4 As per Natural England’s previous PEIR response (our ref 476290, dated 8th July 2024, paragraph 2.8) – All soils should only be handled in a dry and friable condition, and it is expected that soil handling will be confined to the drier summer period (April through September) to minimise risk of soil damage. This would minimise the need to recondition soils, which requires additional space and time. This is particularly important for land to be restored to agricultural use. Soil handling methods should normally be as specified as in the Defra Construction Code of Practice for the Sustainable Use of Soils on Construction Sites (including accompanying Toolbox Talks). | Commitment to only working soils in a dry and friable condition is made within the oSMP. It would also be useful to restate this requirement within paragraph 3.1.4 for further clarity as this is the most important technique to avoid compaction and degradation of the soil function and grade. | Green
NE15 | Soils & BMV | Green | APP-182 3.6.3 No reference is made to how soils are stored where this may be over 6 months. All storage bunds intended to remain in situ for more than 6 months or over the winter period should be grassed over and weed control and other necessary maintenance carried out. | Clarity on how soil storage bunds are managed over periods of >6 months should be included in the oSMP. | Amber | No update from Applicant. Should be recorded in SoCG. Keeping Amber until confirmed in SoCG. | Amber | No update - copy and paste error. | Amber | No update | Amber | Updated in SoCG following a meeting with the Applicant on 15/09/25. Will await to see updates in SMP as submitted at D4. | Amber | Note from consultant 14/10/25: When I went to update the SMP to include reference to storage over 6 months I noticed that it had already been included so I changed the wording within the SoCG to state this, the paragraphs soil storage is mentioned are 5.3.16 and 8.3.11. Checked the SMP and can now be resolved. | Green
NE16 | Soils & BMV | Yellow | APP-182 4.2.5 The use of concrete bases would increase the impact on both agricultural land take and soil health through continued compaction. | Natural England seek further clarification on the application of concrete shoes as bases. Would they be simply placed on top soils or would topsoil be removed and stored for restoration during the decommissioning phase? | Amber | No update from Applicant. Should be recorded in SoCG. Keeping Amber until confirmed in SoCG. | Amber | Applicant noted in SoCG that they will be used in sensitive archeological areas only and this will be recorded in the SMP. NE requested they record the extent of their use to illustrate any significance of impact. Remains under discussion in SoCG as we will review once details are included in SMP. | Amber | No update | Amber | Updated in SoCG following a meeting with the Applicant on 15/09/25. Will await to see updates in SMP as submitted at D4. | Amber | No update | Amber | No update, remains under discussion. Awaiting confirmation of changes to SMP regards to how the extensive the concrete bases are and how the soils will be managed in this scenario. | Amber | We suggest reviewing the impacts from the concrete bases post consent when more information on the extent of the PVs implemented and their contribution to total permanent loss are better known. Marked as not agreed in SoCG and will be reviewed and agreed post-consent. | Yellow
NE17 | Soils & BMV | Green | APP-182 5.3.12 It is assumed that if stockpiled correctly (in the right wetness condition), and subsequently shaped and seeded, the stockpiles can remain in place for many years with minor degradation - there is always a degree of anoxic conditions occurring in the centre, however these are quickly remediated upon soil spreading. The stockpiles would need to be maintained to avoid any growth of shrubs or trees. | The SMP should be clear about how much soil has been stored and the need to replace the soils at decommissioning to secure a certainty of soil re-use. | Amber | No update from Applicant. Should be recorded in SoCG. Keeping Amber until confirmed in SoCG. | Amber | Need further clarity on the quantity of soil to be stored and commitment to reuse it at decommissioning. Remains under discussion in SoCG. | Amber | No update | Amber | Updated in SoCG following a meeting with the Applicant on 15/09/25. This has now been agreed as the Applicant has adequately addressed issues related to soil storage. | Green | No update | Green | ExQs3 ref 13.0.1 request: Please clarify the status of the position in respect of soil storage, there appears there may be a discrepancy between Table 18.4 and the Risk and Issues Log NE17. Natural England are reviewing this and will respond at D7. | tbc | NE are retracting our comment on Table 18.4 from D4. Agreed this issue in SoCG due to following current and available best practice guidance. | Green
NE18 | Soils & BMV | Green | Natural England’s review and response to the cumulative impacts to agricultural land and soil function will be provided at the next stage. | tbc | tbc | No further update. | tbc | Comments to be given from NE at Deadline 3. | tbc | Comments provided to the Applicant for review and inclusion in the SoCG at Deadline 4. | tbc | Updated in SoCG following a meeting with the Applicant on 15/09/25. Will await to see updates in SMP as submitted at D4. | Yellow | NE provided further comments to Applicant 06/11/25: While the cumulative loss of Best and Most Versatile (BMV) land nationally appears proportionally small, the IEMA guidelines emphasize that regional and local impacts especially in high-value agricultural counties like Lincolnshire and Nottinghamshire require careful scrutiny and mitigation. The additional breakdown of BMV loss in both a national and local context is welcomed, I do have the following advice to offer; IEMA guidelines note ‘To enable an assessment of cumulative effects, it is necessary to: set out clear criteria to determine the magnitude, sensitivity, and significance of impacts’, forgive me it may well be in the document elsewhere, are the national and local figures of cumulative effect determined in terms of magnitude and significance? This should also be presented in the ES. 18.5.11 should indicate whether ‘total loss’ is permanent or temporary. | Yellow | Further comments to Applicant on 6.18.3 Chapter 18 Cumulative Effects on outstanding comments 02/12/25: Table 18.2 we suggest additional text be included. Para 18.5.11 should indicate if total loss is permanent or temporary. Para 18.5.13 Magnitude and sensitivity are noted. But the criteria for significance is not clearly stated. Is this what is alluded to in para 18.5.16? Think it needs to clearly state the significance criteria and therefore the significance of impacts from the cumulative effects. Tabulating is an effective and clear way of presenting this. Table 18.4 NE will review comments vs NE17 status and confirm at D7. Ref ExQ3 13.0.1. | Yellow | The Applicant has made agreed updates to the Cumulative Effects Chapter following our comments. As such have agreed this within the SoCG. | Green
DCO | Protected Sites | Green | Natural England welcome the inclusion of requirements to avoid and mitigate impacts to lamprey functionally linked to the Humber Estuary SAC and Ramsar site from the Project. And note these will be secured through the CEMP, DEMP and LEMP. We note the details laid out in Paragraph 1.1.2 and Table 1.1 of the Commitments Register C2, C4, C12, C14. | n/a | Green
DCO | Protected Sites | Green | Natural England welcome monitoring of barrier effects from EMF to lamprey species functionally linked to the Humber Estuary SAC and Ramsar site. We note this will be secured through the LEMP. We note the details laid out in Paragraph 1.1.2 and Table 1.1 of the Commitments Register C12. | n/a | Green
DCO | Soils & BMV | Green | We welcome the inclusion of a SMP to ensure agricultural grade and function are restored at decommissioning. We note the details laid out in paragraph 1.1.2 and Table 1.1 of the Commitments Register C46, C47, C48. | n/a | Green
DCO | BNG | n/a | We welcome the inclusion of a requirement for BNG and with reference to the planning authority and nature conservation body, for the lifetime of the Project. We would suggest a commitment in the DCO for at least 10% gains and a Habitat Management and Monitoring Plan to ensure the habitats are retained. | n/a | n/a
DCO | Soils & BMV | Green | We welcome the time limited requirement as part of the decommissioning plan to 60 years. | n/a | Green
DCO | CPwN | Green | We welcome the inclusion of new permissive paths network as secured through the LEMP to increase green infrastructure provision and PRoW MP to maintain access to PRoW during construction. We note the details laid out in Paragraph 1.1.2 and Table 1.1 of the Commitments Register C61 and C74. | n/a | Green
NE19 | Soils & BMV | Green | Added into SoCG for Deadline 2. | n/a | n/a | n/a | n/a | Applicant request on NE view on buried cables relating to agricultural land; is it acceptable to leave in situ/ commitment currently the strategy is to remain but as noted in the management plans to review based on the need and requirement on future policy & best practice. NE view for cables, if they are installed deep enough, happy to remain insitu (from an agri land and soils perspective), as they would be avoiding the soil disturbance altogether at decommissioning. The main requirement would be that they are installed deep enough to avoid any potential impact from standard agricultural practices during operation (i.e. the installation depth). The position of a minimum depth of 900mm is recognised as the industry standard. Agreed in SoCG. | Green