## Guide to the R&I Log
Introduction:
Natural England have created this Risk and Issues Spreadsheet to track progress of issues raised in our Relevant Representations throughout the Examination for Great North Road Solar and Biodiversity Park Project. Each issue was assigned a Red, Amber, Yellow or Green risk rating in our relevant representations, as defined below. The Rating will be updated at each deadline to clearly show progress made during examination.
Risk Rating:
Red are those where there are fundamental concerns which it may not be possible to overcome in their current form.
Amber are those where further information is required to determine the effects of the project and allow the Examining Authority to properly undertake its task and or advise that further information is required on mitigation/compensation proposals in order to provide a sufficient degree of confidence as to their efficacy.
Yellow are those where Natural England does not agree with the Applicant’s position or approach. We would ideally like this to be addressed but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process. However, we reserve the right to revise our opinion should further evidence be presented. It should be noted by interested parties that whilst these issues/comments are not raised as significant concerns in this instance, it should not be understood or inferred that Natural England would be of the same view in other cases or circumstances.
Green are those which have been successfully resolved (subject always to the appropriate requirements being adequately secured).
Additional information:
Key updates for D1 are primarily in column G.
The spreadsheet contains filters to enable ease of viewing. In particular, filtering via 'Amber' in cell F1 (titled 'RAG Status Rel Rep - Feb 2025') will show only the issues that were marked as Amber in our Relevant Representations.
Requested actions in our Relevant Representations are shown in Red Text.
NE's key updated advice at the current deadline is shows in Bold.

## R&I Log
Ref from Relevant Reps | Theme | Issue Summary | Current RAG Status | Taken from Natural England’s Relevant Representations - 26/09/2025 | RAG Status Rel Rep - 26/09/2025 | Consultation, actions, progression Prior to D1 - 10/12/2025 | RAG Status D1 - 10/12/2025 | NE Response to updates 16/03/2026 (following meeting with the applicant held 23/02/2026) | RAG Status - 16/03/2026
NE1 | Internationally designated sites | Screening Area & Identification of Sites (C,O,D) | Green | The HRA Screening Report (APP-316) has used a 30km study area for the screening of Internationally Designated Sites. As a result, two international sites have been identified for assessment within the HRA: Birklands and Bilhaugh SAC, located approximately 7.0 km northwest of the Order Limits, and Sherwood Forest ppSPA, situated approximately 4.5 km to the west and northwest of the Order Limits (Table A8.2.1) (APP-215). Natural England note the inclusion of the Humber Estuary SAC/Ramsar in the screening assessment due to the mobile nature of its features. Although the Humber Estuary SAC/Ramsar lies beyond the 30km ‘screening distance’ at 43km north of the Order Limits, Natural England welcome the inclusion of the site in the Habitats Regulation Assessment Screening Report (APP-316). Natural England also welcome the adoption of a ‘risk-based approach’ with regards to the screening of Sherwood Forest ppSPA given the site/designation has no formal recognition. It is considered by Natural England that all relevant Internationally Designated sites have been reviewed. | Green
NE2 | Internationally designated sites | HRA Initial Screening- Functionally Linked Land (FLL) (C, O, D) | Green | Natural England concur with the assessment set out in the HRA Screening Report (APP-316) that it is unlikely that the habitats and plants in the Order Limits have any functional link to Birklands and Bilhaugh SAC. Natural England note in section 3.2 of the report that the two potential qualifying features of Sherwood Forest ppSPA, breeding European nightjar and woodlark, have not been recorded during the breeding bird surveys. NE concur with the conclusion that the Order Limits are not functionally linked to the ppSPA given the confined range of these species and their unique habitat requirements. Section 3.3 of the HRA Screening Report concludes that likely significant effects on the Humber Estuary SAC/Ramsar are highly unlikely due to the very low likelihood of occurrence of Lamprey as a result of the large separation distance between the Development and the SAC, in-combination with embedded designed-in mitigation (APP-227). It is noted that cable burial is included as an embedded mitigation measure. Natural England acknowledge that cable burial is a factor likely to reduce EMFs, however, must note that the effect of EMFs on Migratory Lamprey are largely unknown, and there is no established burial depth considered ‘deep enough’ to avoid effects from EMF. Nonetheless, as a result of the separation distance from the SAC/Ramsar site, absence of crossings of the River Trent itself, and the other embedded mitigation set out, Natural England concur with the conclusion regarding impacts to Lamprey associated with the Humber Estuary SAC/Ramsar. | Green
NE3 | Internationally designated sites | HRA Initial Screening- Hydrological Connectivity (C, O, D) | Green | Sections 3.1 and 3.2 of the HRA Screening Report conclude that there are no direct hydrological links between the Development site and Birklands and Bilhaugh SAC and Sherwood Forest ppSPA due to the intervening distance and agricultural landscape which limit the potential for effect pathways. Natural England concur with the assessment provided in Section 3 of the HRA Screening Report and have no further comments. | Green
NE4 | Internationally designated sites | HRA Initial Screening- Air Quality (C, O, D) | Green | Sections 3.1 and 3.2 of the HRA Screening Report conclude that predicted increases in traffic movements in all phases of the Development are sufficiently small and distant from Birklands and Bilhaugh SAC and Sherwood Forest ppSPA, therefore, associated emissions increases will have a negligible effect on the nitrogen loading of the qualifying features. Chapters 14 and 16 (APP-057 & APP-059) include traffic modelling and relevant air quality assessment criteria, respectively. Natural England consider the screening criteria used to be sufficiently precautionary, and the modelled construction traffic is unlikely to exceed these criteria at any location, including within 200m of any designated sites. We therefore concur with this assessment and have no further comments. | Green
NE5 | Internationally designated sites | HRA Conclusions (Including In-Combination Assessment (C, O, D) | Green | Section 4 of the HRA screening report concludes that there will be no likely significant effects arising from the Development either alone or in-combination. It is noted that the project will not have any appreciable effect upon the qualifying features of any Internationally designated sites; thus, the project cannot combine with any other plans/projects to cause a significant effect. Upon review of the screening assessment provided, Natural England consider that, in this scenario this rationale is justified. | Green
NE6 | Nationally designated sites | Screening Area & Identification of Sites (C, O, D) | Green | The ES has used a 5km search area for all Nationally Designated sites, along with Natural England’s Impact Risk Zones (IRZs) (ES paragraph 8.5.2) (APP-051). Within the search areas, there are eight Sites of Special Scientific Interest (SSSIs). Section 8.5.2 of the ES correctly identifies that the Order Limits of the proposed development crosses several of Natural England’s IRZs including two which trigger the ‘All Planning Applications’ development category relating to Eakring and Maplebeck Meadows SSSI and Mather Wood SSSI. The ES has correctly identified that no other IRZ triggers within the Order Limits include the development category of ‘Wind and Solar Energy’. Nonetheless, Natural England welcome the consideration of impacts to Laxton Sykes SSSI due to the potential of direct hydrological connectivity. All other SSSIs have been scoped out of assessment (ES Table 8.8) (APP-051). Natural England concur with this decision and agree that impacts to any other SSSI’s identified within 5km of the Order Limits are unlikely. | Green
NE7 | Nationally designated sites | Impact Assessment- Eakring and Maplebeck Meadows SSSI | Green | Section 8.8.4 of ES Chapter 8 (APP-051) clarifies the location of the proposed development. The southern boundary of the Eakring and Maplebeck Meadows SSSI, extending approximately 1.5 km, lies adjacent to and partially within the adopted highway included in the Order Limits. Paragraph 167 of section 8.8.4 indicates that the nearest proposed construction activity to the SSSI is the construction of five new passing places. Natural England welcomes the Applicant’s efforts to locate passing places in a way that maximises their distance from the SSSI, thereby reducing potential impacts on the protected site. We welcome consideration of impacts to the site from the following impact pathways: Disturbance to Breeding Birds: Section A5.3.11.2.1 of the CEMP (APP-204) addresses comments raised by Natural England at the Section 42 consultation stage. It specifies that the construction of new passing places must not take place between March and August in order to prevent disturbance to breeding birds which are a notified feature of the SSSI. Natural England welcome this additional control measure in order to reduce the potential for adverse effects to the breeding bird assemblage at Eakring and Maplebeck Meadows SSSI. Hydrological Connectivity: Potential hydrological connectivity to the SSSI between Hagley’s Dumble and The Beck has been correctly identified in paragraph 169 of ES Chapter 8. Natural England welcome the additional safeguards from potential pollution impacts such as the use of HDD for cable crossings. This is detailed within the CEMP in section A5.3.9.4.2 which provides specific reference to the potential water pollution pathway and impact at this location and therefore addresses comments raised by Natural England at the Section 42 consultation stage. Construction Traffic Emissions and Dust: Paragraph 170 of Chapter 8 addresses comments raised at the Section 42 consultation regarding consideration of potential impacts from increased construction emissions on the SSSI. It confirms that the modelled construction traffic increases are considerably below the thresholds requiring assessment and impacts from this pathway can be ruled out. We concur with this assessment and have no further comments. Natural England are content that dust impacts to the SSSI from construction activities will be avoided, subject to securing implementation of the dust mitigation measures set out in section A5.3.7 of the oCEMP (APP-204). Decommissioning impacts are considered likely to be similar to construction and as such Natural England concur that decommissioning impacts to Eakring and Maplebeck Meadows SSSI are unlikely. | Green
NE8 | Nationally designated sites | Impact Assessment- Mather Wood SSSI (C,O,D) | Green | Section 8.8.5 of ES Chapter 8 (APP-051) correctly identifies Mather Wood SSSI as 40m from the Order Limits. Potential impact pathways from the development include both permanent and temporary habitat loss and disturbance, habitat fragmentation and habitat change. In accordance with comments raised in our Section 42 response, the oCEMP and ES Chapter 8 outline specific measures to ensure that construction activity undertaken does not encroach into the SSSI. Section 8.8.5.1 confirms that no construction works will take place within or on the boundary of the SSSI, therefore limiting permanent or temporary habitat loss. Furthermore, protective fencing is to be erected to maintain separation between works and the woodland. Hydrological connectivity is limited due to the separation of the nearest works and the SSSI by a shallow depression/valley. Natural England concur that the proposed mitigation and implementation of the CEMP will reduce the likelihood of adverse effects on the SSSI. Decommissioning impacts are considered likely to be similar to construction and as such Natural England concur that decommissioning impact to Mather Wood SSSI are unlikely. | Green
NE9 | Nationally designated sites | Impact Assessment- Laxton Sykes SSSI (C,O,D) | Green | ES Chapter 8.8.6 (APP-051) correctly identifies the direct hydrological connection via a small stream flowing northwards from the Order Limits to the SSSI over a 650m distance. Natural England note in section 8.8.6.1 that no construction works will take place within or on the boundary of the SSSI, in efforts to limit permanent or temporary habitat loss or disturbance to its notified features. This is welcomed by Natural England along with the measures outlined in the oCEMP which seek to avoid waterborne pollution and mitigate potential adverse effects mediated by surface water. Natural England agrees with the assessment presented in Section 8.8.6 of ES Chapter 8, which concludes that the potential for adverse effects is very limited. Decommissioning impacts are considered likely to be similar to construction and as such Natural England concur that decommissioning impact to Laxton Sykes SSSI are unlikely. | Green
NE10 | Nationally designated sites | Nationally Designated Sites- Conclusions (C,O,D) | Green | In summary, Natural England concur that impacts to any SSSIs during construction, operation and decommissioning are unlikely. | Green
NE11 | Designated Landscapes | Designated Landscapes (C, O, D) | Green | The proposed development is not located within, or within the setting of, any nationally designated landscapes. As a result, Natural England has no specific comments to make on the landscape implications of the development. We concur with the applicant’s assessment that nationally designated landscapes can be scoped out of further assessment (ES paragraph 7.5.3) (APP-50). | Green
NE12 | Protected Species Licencing | Avoidance by Design and Licence Identification (C, O, D) | Green | Natural England have been engaged with the applicant during the pre-application period, and generally welcome the approach taken to avoid impacts to protected species. We note that the Construction Ecological Management Plan (CEcMP) (Section A5.3.11, APP-204 included within the oCEMP) has been prepared on the basis of ‘reasonable avoidance measures’ and seeks to avoid the need for species mitigation licences. This approach is welcomed and is in line with the established ‘mitigation hierarchy’. Natural England have been engaged by the applicant with regards to protected species, however, to date, no draft licence applications have been submitted. Section A5.3.11.1.4, paragraph 168 of the CEcMP explains that draft licence applications have not been submitted because the mitigation terms are highly context dependant. The need for and scope of development licences will be determined upon completion of pre-commencement and pre-construction studies. This is in contradiction to paragraph 170 of the CEcMP where Natural England note that ‘… draft licence applications have been submitted with the DCO only for water vole for which baseline data are unlikely to substantively change the approach to mitigation or the terms of the licence’ (APP-204). To date, Natural England has not received a draft licence application for Water Vole. Please ensure this is submitted at the earliest opportunity to allow sufficient time for the issuance of a Letter of No Impediment prior to the conclusion of the examination period. Whilst obtaining a LoNI is not mandatory, it was noted in our Section 42 response to the applicant that where it is considered likely that any licences may be required, it may be valuable to consider the benefit of LoNIs for the identified species. Ultimately it is the responsibility of the developer to determine the need for any protected species licences. Where the need for licences is identified later on in the development process (i.e. upon completion of pre-commencement and pre-construction studies, as proposed by the applicant), this licence will need to be applied for in the usual manner; Natural England are unable to provide a position on the likelihood of a licence being granted without having reviewed a draft licence application. Natural England has not yet received a draft licence application for Water Vole. Please ensure this is submitted to Natural England at the earliest opportunity. Should it be determined during the examination that further species licences are likely to be required, draft applications should be submitted to Natural England as early as possible to allow for a Letter of No Impediment to be issued before the end of the examination period. | Amber | Updated information regarding species licensing has been received from the applicant. The matter is currently under review, and we are awaiting input from Natural England specialists. A formal response will be provided in due course. No changes have been made at this stage. | Amber | Natural England specialists provided the following technical input concerning the applicant’s proposed intention to use a CL31 displacement class licence for the management of water vole during construction activities. “I have, though, reviewed the ask from Mike from the GNR Team regarding the use of the CL31 Licence for their approach to water vole mitigation, and, provided that their approach is implemented exactly as proposed and outlined in the documents referenced, then their proposals are consistent with what is permissible under the CL31 approach. The only thing to flag to them is that translocation of water voles is not covered, as the CL31 Licence permits displacement only. Moving water voles to a different/distant site would require a separate licence. I appreciate they have not proposed any translocation based on the documents I’ve reviewed, but it is important that they understand that a different licence, specifically an A11 Mitigation Licence, would be required if translocation becomes a likely part of their mitigation approach. In general though, their proposals look ecologically appropriate and consistent with the CL31 conditions. With regards to whether they need to submit anything akin to a draft licence application to us for our review at this stage, I would agree with Mike that it is not necessary nor required here, given that when they do act under the CL31 they are not required to submit site-specific information ahead of use of the licence; they will only need to report on licence use as part of the end of year reporting requirements for the class licence.” Based on the above, NE raise no further concerns and consider this agreed. | Green
NE13 | Soils and best and most versatile agricultural land | ALC Survey Methodology (C, O, D) | Green | Natural England welcome Table 17.1 of Chapter 17 which provides a clear overview of previous consultation responses in respect of agricultural and soils matters. Natural England previously requested a full Agricultural Land Classification (ALC) survey to be completed across the full site, including the Cable Route Corridor. We note that the cable areas (Work no.2) have been refined and ALC surveys have been completed and reported in Technical Appendix A17.1 (APP-288, APP-298, APP-060). Natural England welcome the completion of an ALC survey across a total 2869.1 hectares (ha) of land, of which 1764.6 ha are within the Order Limits, in line with the 1988 ALC Guidelines and at a detailed level (1 auger per hectare) (APP-288). We acknowledge that due to the size of the site, the ALC mapping has been broken down into 6 maps. | Green
NE14 | Soils and best and most versatile agricultural land | ALC Survey Results and Assessment of Effects (C, O, D) | Green | The ALC survey results are presented within ES Chapter 17 (APP-060). Table 17.7 shows that 62% (1093ha) of the Order Limits are categorised as Best and Most Versatile (BMV) land. Within this, 8.5% (149.5 ha) is classified as ALC Grade 2, and 53.5% (943.9 ha) is classified as Grade 3a. Chapter 17, Paragraph 118 notes that the area of land that is going to be used for construction compounds has not been presented, although it stated that each compound is likely to be 1-2ha. Chapter 17, Paragraph 153 ‘summary of construction phase effects’ states that the quantum of BMV land to be disturbed by the development is 19.4ha. Natural England disagrees with this statement. This figure considered only the elements of the development that will be in situ for the entire operational lifespan of the proposal. There is a considerably larger area of BMV land that will be disturbed during construction only (including construction compounds, access tracks (13.4ha BMV) and cable routes (95ha BMV)). Whilst these effects are shorter term, they continue to introduce the potential for permanent adverse effects to the soil resource and agricultural land quality. Whilst it is noted that as a result of the proposed mitigation, in the form of the Soil Management Plan, and with the commitment for these areas to be restored to the same ALC grade, this is unlikely to alter the outcome of the EIA. Natural England consider the overall quantum of BMV land that will be disturbed is significantly larger than the stated 19.4ha. Recommendation to review the amount of BMV land that is temporarily disturbed, to ensure The Planning Inspectorate and Secretary of State understand the full extent of potential effects in the absence of mitigation. | Yellow | Natural England met with the applicant on 18th November 2025 to discuss the Statement of Common Ground (SoCG) and outstanding issues. The applicant will provide updated information on these matters, which Natural England will review once received. There are no changes at this time. | Yellow | NE welcome the updated Planning Statement [EN010162/APP/5.4B] to include further details on the approach to BMV policy. Whilst we welcome the updates, we maintain our view that the information presented may still be misleading in relation to the extent of BMV land that would be subject to temporary disturbance. Nonetheless, with the proposed mitigation and the commitment for these areas to be restored to the same ALC grade, it is unlikely to alter the outcome of the EIA. NE therefore considers this matter to be agreed as the outcome remains unchanged. Nonetheless, we highlight the importance of ensuring that future Environmental Statements clearly present the full extent of potential effects in the absence of mitigation, to enable both the Planning Inspectorate and the Secretary of State to be fully informed. | Green
NE15 | Soils and best and most versatile agricultural land | Development Design & Avoidance of BMV Land (C, O, D) | Amber | ES Chapter 4, Section 4.3 (APP-047) describes the site selection and design, whereby consideration was given to BMV land during the site selection process. It is noted that areas to the west of the Site Search Area were classified as higher-grade agricultural land based on the provisional Natural England maps and was therefore avoided from the outset. This avoidance of high-grade BMV land is welcomed by Natural England. However, little information is provided with regards to any further avoidance/ ‘micro-siting’ of infrastructure away from BMV land within Chapter 4 or Chapter 17 based on the full ALC survey results. Natural England refer the Applicant to our Section 42 response advice regarding avoidance of BMV land, as summarised in Table 17.1, Chapter 17 (APP-060). In response, the Applicant indicates that further consideration has been given and is reported in section 17.8. However, little reference is made in this section regarding avoidance of BMV land. In addition, Natural England’s Section 42 response advised that the Applicant should consider avoiding land of BMV quality where intrusive biodiversity enhancement is proposed. Natural England note the Applicant’s response to our advice, as outlined in Table 17.1, which states that ‘vegetation proposals such as hedges and trees do not affect the soil resource and have therefore been designed for maximum benefit (such as visual screening) rather than BMV avoidance’. Natural England will always support the implementation of ecological enhancements where they are designed and sited appropriately. Nonetheless, we cannot concur with the above statement, because woodland creation can cause permanent loss/degradation of agricultural land quality and is considered a permanent loss of BMV. If the soil profile is disturbed this can make it difficult to revert to the baseline agricultural grade/quality. It is acknowledged that hedgerows can provide soil health benefits & no concern is raised regarding hedgerows at this stage. Natural England request further detail on steps taken to avoid BMV as far as reasonably practicable for all elements of the development, in line with the NPPF mitigation hierarchy and NPS EN-1 paragraph 5.11.12. Natural England request further information regarding the amount of BMV land that could be permanently lost due to woodland planting. | Amber | Natural England met with the applicant on 18th November 2025 to discuss the Statement of Common Ground (SoCG) and outstanding issues. The applicant will provide updated information on these matters, which Natural England will review once received. There are no changes at this time. | Amber | Natural England specialists have provided detailed feedback following their review of the 'BMV Avoidance: Micro‑siting Analysis' technical note, which the applicant submitted to NE on 11/02/2026. Our formal comments have been issued to the applicant and will be submitted into the examination at Deadline 4. A summary of Natural England's updated position following review of the micro-siting technical note is as follows; The Micro‑siting Analysis for the Great North Road Solar and Biodiversity Park provides a comprehensive and well-structured review showing how the project has minimised impacts on Best and Most Versatile (BMV) agricultural land. It demonstrates a thoughtful and iterative design process supported by detailed ALC surveys, with higher‑grade soils largely avoided where practicable and unavoidable use of Grade 3a land clearly justified. The consultant provides clear rationale for permanent loss of BMV land and the commitment to restore temporary works areas to a comparable ALC grade, combined with good-practice soil management strengthens the credibility of the approach. However, the document acknowledges that 22.4ha of the proposed woodland planting occurs on BMV land. Unlike solar infrastructure, woodland represents a permanent loss of agricultural capability, and therefore cannot be restored to its former land grade. Although ecological connectivity and landscape benefits are clear, the reliance on BMV land for several planting areas may require further justification to align with policy expectations around avoiding irreversible impacts on high quality soils. Natural England consider the permanent loss of 22.4ha a major significant impact that should be captured by the Environmental Statement and considered by the Secretary of State. | Amber
NE16 | Soils and best and most versatile agricultural land | Permanent loss of BMV land (D) | Green | Section 17.8.1.6 of Chapter 17 sets out a ‘worst-case scenario’ of the loss of 4.5ha of BMV, all subgrade 3a, should the Substations/Bess infrastructure remain in-situ following the decommissioning of the project. This loss has been appropriately assessed in the EIA. | Green
NE17 | Soils and best and most versatile agricultural land | Time Limit (D) | Green | A decommissioning timeline is specified in DCO Requirement 19, securing the c. 40-year lifespan of the project. Where a time limit is applied, relevant impacts may be considered temporary, providing correct soil management and reinstatement, thus, protecting the long-term potential of the agricultural land resource. | Green
NE18 | Soils and best and most versatile agricultural land | oSMP (C, D) – Soil handling and Management | Green | Natural England note the commitment to produce a Soil Management Plan, and welcome the principles set out in the outline Soil Management Plan (oSMP) (APP-290) including separate soil handling methodologies for specific work areas based on the type of works required in each. Each element of the proposal may have a differing effect on the soil resource and must be managed appropriately. Of particular note, the oSMP states that the most suitable management decision/action to avoid adverse effects on soils is the timing of works. It is welcomed that any activity that requires soil to be moved or dug up is minimised during the winter, with works only occurring when soils are in a suitable condition. It is Natural England’s advice that soils should only be handled when they are dry and friable. Whilst the oSMP does not entirely prohibit works in the winter period, Natural England welcome the requirement for soil suitability testing before working in this period- in line with the Institute of Quarrying Field Tests for Soil Suitability. At this stage Natural England have no further comments on the oSMP. Natural England request the oSMP requirement is amended to include consultation with Natural England. | Yellow | Natural England met with the applicant on 18th November 2025 to discuss the Statement of Common Ground (SoCG) and outstanding issues. The applicant will provide updated information on these matters, which Natural England will review once received. There are no changes at this time. | Yellow | The applicant has amended the oSMP to include consultation with Natural England on the SMP. NE welcome this amendment and therefore consider this matter to now be agreed. | Green
NE19 | Soils and best and most versatile agricultural land | oSMP (D) – Reinstatement | Green | ES Chapter 17, section 17.8.1.6 states that the reinstatement to ‘comparable’ soil properties and land grade would be in accordance with a Decommissioning and Restoration Plan (DRP). It also indicates that all but 4.5 ha of BMV land is capable of restoration to a ‘comparable’ grade at the decommissioning phase. Section 9.2 of the oSMP states that ‘The objective is to remove panels and restore all fixed infrastructure areas to return the land to the same ALC grade and condition as it was when the construction phase commenced’. This is essential to allow consideration of a loss of BMV land to be temporary and is in line with NPS EN-5 paragraph 2.8.25. Natural England welcome reference to this policy in section 17.6.2 of ES Chapter 17. Whilst the intent to restore all areas to the same quality is clear, it is noted that section 9.2 of the oSMP refers specifically to reinstatement following decommissioning. Natural England recommend that a similar commitment should be made clear within the oSMP that all land disturbed temporarily during construction (access tracks, construction compounds, cable routes etc) is also restored to the same ALC grade, informed by the ALC survey. Commitment should be made clear within the oSMP that all land disturbed temporarily during construction (access tracks, construction compounds, cable routes etc) are also restored to the same ALC grade, informed by the ALC survey. | Yellow | Natural England met with the applicant on 18th November 2025 to discuss the Statement of Common Ground (SoCG) and outstanding issues. The applicant will provide updated information on these matters, which Natural England will review once received. There are no changes at this time. | Yellow | The applicant has amended paragraphs 5.43 and 9.2 in the ES Volume 4, Appendix A 17.2: Outline Soil Management Plan [EN010162/APP/6.4.17.2B] [REP3-065] to include that all land disturbed temporarily during construction is also restored to the same ALC grade, informed by the ALC survey. NE welcome this amendment and therefore consider this matter to now be agreed. | Green
NE20 | Soils and best and most versatile agricultural land | Monitoring and Research (O, D) | Green | At this stage, no soil monitoring or additional research is proposed throughout the Development. Monitoring will enable any adverse soil conditions arising during the operational phase to be identified and rectified. In addition, the long-term effects of solar development on overall soil health are not yet fully understood. Whilst similarities are expected to the benefits provided to soil health by arable reversion, the effect of solar panels on this could be better understood with further monitoring & research over the longer term. There is little evidence & understanding around the application of alternative solar technologies in England. Large scale solar proposals offer the opportunity to develop understanding & push forward the implementation of new, multi-benefit technologies & management practices. Natural England recommend that the scheme could include a scheme of soil health monitoring and/or an area dedicated to research into future technologies and/or management practises (i.e. agrivoltaics). | Yellow | Natural England met with the applicant on 18th November 2025 to discuss the Statement of Common Ground (SoCG) and outstanding issues. The applicant will provide updated information on these matters, which Natural England will review once received. There are no changes at this time. | Yellow | The applicant has outlined research partnerships aligned with the goals of Great North Road Solar and Biodiversity Park, including collaboration with Nottingham Trent University (NTU) and the co-development of a PhD project aimed at modelling how solar farm development affects soil carbon storage and biodiversity net gain over time, thereby contributing valuable research in an academic field where data is currently limited. Natural England welcome the additional research initiatives that are being pursued as part of the wider project. However, we note that the requirement in question does not constitute mitigation necessary to make the scheme acceptable in planning terms, nor is it required by planning policy. As such, both parties agree that this commitment cannot be secured through the DCO. Natural England raises no further concerns regarding soil monitoring and research and will continue to engage with the Applicant on this matter. | Green
NE21 | Biodiversity Net Gain | Biodiversity Net Gain (BNG) (C,O,D) | NE’s comments on BNG have not been attributed a RAG score, as BNG is not a mandatory requirement for the project. | ES section A8.13.1.2.1 (APP-226) acknowledges that the mandatory BNG requirement does not currently apply to Development Consent Orders (DCOs). Despite this, the Applicant has voluntarily applied the Statutory Biodiversity Metric and presents a BNG Assessment for the development. As it stands, the proposed development will give rise to: 60.70% net gain in habitat units 26.46% net gain in hedgerow units 11.05% net gain in watercourse units It should be noted that Natural England have not reviewed the Biodiversity Metric in detail. Nonetheless, Natural England welcome this provision, which exceeds the intended mandate of 10% (Biodiversity net gain for nationally significant infrastructure projects). | N/A
NE22 | Other Comments | Ancient Woodland and Ancient/ Veteran Trees | Green | Natural England welcomes the inclusion of the Arboricultural Impact Assessment (APP-225), which reflects the Applicant’s continued commitment to further screening for potential Arboricultural impacts, as highlighted in our Section 42 consultation response. Natural England welcome the additional information regarding ancient and veteran trees that have been identified on Site following the Arboricultural Impact Assessment. Natural England welcome 8.8.8.1 of ES Chapter 8 (APP-051) which states that ‘there will be no loss of or harm to ancient woodland or veteran trees’. Natural England acknowledge and welcome the embedded mitigation measures relating specifically to Ancient and Veteran trees as detailed in section A5.3.11.3.2.1 of the oCEMP (APP-204). This includes the increased Root Protection Area (RPAs) to at least 15 times the diameter of the tree and the implementation of 5m buffer zones from the tree’s canopy if that area is larger than 15 times the tree’s diameter. Natural England have no further comments with regard to Ancient Woodland and refer to Standing Advice. | Green
NE23 | Other Comments | Connecting People with Nature | Green | Document 2.4 Public Rights of Way and Permissive Routes Plan (APP-020) shows the significant number of Public Rights of Way (PRoW) in and around the Order Limits. Natural England welcome ES Technical Appendix A4.1 ‘Public Rights of Way Strategy’ (APP-200) which demonstrates the Applicant’s commitment to ensuring continuity of access, connectivity enhancement and minimisation of disruption to PRoWs and users from the development. Natural England welcome the creation of 21 new permissive footpaths and 6 permissive bridleways totalling a length of 32.6km, as shown in Figure 5.2 Landscape Masterplan (APP-081). Natural England welcome the commitment to a number of embedded enhancement measures within the Development design, as detailed in Technical Appendix A18.1 Outline Recreation Routes Management Plan (oRRMP) (APP-295). Proposals include picnic areas and benches, woodland, hedgerow and tree planting, interpretation boards and a community orchard all designed with a view to maximise the recreational benefits of each feature. As outlined in our Section 42 response, the value of these enhancement measures is recognised and encouraged by Natural England due to their ability for increased public understanding of the project and surrounding natural environment. Natural England have been engaged regarding the elements of the proposals, and indeed actions outside of the proposals delivered through the applicant’s NG+ scheme, regarding connecting people with nature. Whilst our statutory advice will not provide further comment on this, opportunities for further non-statutory engagement are welcomed. | Green