## Guide to the R&I Log
Introduction:
Natural England have created this Risk and Issues Spreadsheet to track progress of issues raised in our Relevant Representations throughout the Examination for teh Steeple Renewables Project. Each issue was assigned a Red, Amber, Yellow or Green risk rating in our relevant representations, as defined below. The Rating will be updated at each deadline to clearly show progress made during examination.
Risk Rating:
Red are those where there are fundamental concerns which it may not be possible to overcome in their current form.
Amber are those where further information is required to determine the effects of the project and allow the Examining Authority to properly undertake its task and or advise that further information is required on mitigation/compensation proposals in order to provide a sufficient degree of confidence as to their efficacy.
Yellow are those where Natural England does not agree with the Applicant’s position or approach. We would ideally like this to be addressed but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process. However, we reserve the right to revise our opinion should further evidence be presented. It should be noted by interested parties that whilst these issues/comments are not raised as significant concerns in this instance, it should not be understood or inferred that Natural England would be of the same view in other cases or circumstances.
Green are those which have been successfully resolved (subject always to the appropriate requirements being adequately secured).
Additional information:
Key updates for D1 are primarily in column G.
The spreadsheet contains filters to enable ease of viewing.
Requested actions in our Relevant Representations are shown in Red Text.
NE's key updated advice at the current deadline is shown in Bold.

## R&I Log
Ref from Relevant Reps | Theme | Issue Summary | Current RAG Status | Taken from Natural England’s Relevant Representations - 28/08/2025 | RAG Status Rel Rep - 28/08/2025 | Consultation, actions, progression Prior to D1- 25/11/2025 | RAG Status D1 - 25/11/2025 | Consultation, actions, progression | RAG Status 11/11/2025 | Consultation, actions, progression | RAG Status D3 | Consultation, actions, progression | RAG Status D4 | Consultation, actions, progression | RAG Status D5 | Consultation, actions, progression | RAG Status D6 | Consultation, actions, progression | RAG Status D7
NE1 | Internationally Designated Sites | Screening Area & Identification of Sites | Green | The ES has used a 10km study area for all Internationally designated sites, along with a 30km study area for all SPA/Ramsar sites (ES paragraph 7.6.13). This has resulted in the following sites being screened in for assessment in the HRA: • Birklands and Bilhaugh SAC; • Hatfield Moor SAC; • Humber Estuary SPA; • Humber Estuary Ramsar; • Humber Estuary SAC; • Thorne and Hatfield Moors SPA; and, • Thorne Moor SAC NE consider all relevant sites have been considered. It was noted in our Section 42 consultation response that the Humber Estuary SPA lies beyond the 30km ‘screening distance’ used, whilst the Ramsar and SAC designations for the same site fall just within it. It was requested that the SPA was included in the screening assessment due to the mobile nature of it’s features. As such NE welcome the inclusion of the Humber Estuary SPA in the Information to Inform a Habitats Regulations Assessment (iHRA) (iHRA Table 2). | Green | No Update | Green
NE2 | Internationally Designated Sites | Survey Methods | Green | NE have reviewed appendix 7.4 and appendix 7.6 and are satisfied with the ornithology survey methods used. As stated in our EIA Scoping & S42 responses with regard to wintering birds: where there remains any doubt about the use of the site by species associated with international designations, further survey is likely to be required over a 2nd winter. In this scenario, due to the separation distance to relevant designations and numbers of qualifying species recorded to date, NE consider the single year’s wintering bird survey effort likely to be satisfactory to enable a robust assessment. NE have no further comments regarding survey methods in relation to Internationally designated Sites. | Green | No Update | Green
NE3 | Internationally Designated Sites | HRA Initial Scoping (iHRA Table 2) – Birklands and Bilhaugh SAC | Green | Natural England concur with the assessment set out in iHRA Table 2 that this site does not need to be considered further due to the nature of the Proposed Development, the location of the Site and its separation from the SAC. | Green | No Update | Green
NE4 | Internationally Designated Sites | HRA Potential impact pathways identified (iHRA Section 5) | Green | Natural England consider all relevant impact pathways have been considered at iHRA section 5. It is noted that impact from both air quality and water quality are ruled out for all sites. For air quality, Natural England consider this appropriate; the applicant has used the correct air quality screening thresholds (ES paragraph 14.34) to reach this conclusion. For water quality, Natural England also consider this appropriate, with the use of standard best practise construction management measures, via the CEMP, avoiding a likely significant effect. The distance from all sensitive international sites is also noted, adding further certainty that any pollution is unlikely to cause a perceptible effect (iHRA paragraph 5.23). | Green | No Update | Green
NE5 | Internationally Designated Sites | HRA Screening Assessment (iHRA Table 3) – All Sites | Green | A key impact considered is loss/disturbance to Functionally Linked Land (FLL). Natural England welcome the inclusion of survey results within Table 3, and concur that the order limits are unlikely to comprise important FLL for the qualifying features of each of the internationally designated sites due to both the physical separation, low numbers/frequency of use by relevant species, and the development design to include the enhancement of the most frequently used area of the site for biodiversity (Eastern Biodiversity Mitigation Area). It is also noted with regard to lamprey that the scheme design has avoided the creation of additional barriers to migration within the River Trent and it’s tributaries. Natural England have no further comments or concerns with the assessment provided in Table 3. | Green | No Update | Green
NE6 | Internationally Designated Sites | HRA Conclusions (including in-combination) | Green | HRA section 6 concludes that the project would not cause a likely significant effect upon any Internationally designated sites either alone or in-combination. It is noted that the project will not have any appreciable effect upon the qualifying features of any Internationally designated sites; thus, the project cannot combine with any other plans/projects to cause a significant effect. Upon review of the screening assessment provided, NE consider that in this scenario, this rationale is justified. | Green | No Update | Green
NE7 | Nationally Designated Sites | Study Area & Identification of Sites | Green | The ES has used a 5km search area for all Nationally designated sites, along with Natural England’s Impact Risk Zones (ES paragraph 7.6.12). Within the search areas, there are six biological Sites of Special Scientific Interest (SSSIs). Of which, the closest is Clarborough Tunnel SSSI, approximately 40m from the order limits. All other SSSIs have been scoped out of assessment (ES paragraph 7.6.29). Natural England agree that impacts to any other SSSIs are unlikely. | Green | No Update | Green
NE8 | Nationally Designated Sites | Impact Assessment – Clarborough Tunnel SSSI | Green | ES paragraph 7.8.19 clarifies that the nearest area of development to the SSSI is approximately 750m from the SSSI, with the intervening area being enhanced as species-rich grassland. As such, direct impacts are unlikely during construction and operation. Natural England welcome the consideration of impacts to the site from construction dust and traffic emissions: Traffic Emissions: - Table 14.4 addresses comments raised by Natural England at the Section 42 consultation stage. It confirms that all construction routes are over 200m away from the SSSI (Chapter 13: Transport and Access – Inset 13.3). As such, Natural England concur that impacts from this pathway can be ruled out (at both construction and decommissioning). Dust: - Table 14.4 confirms that the sensitivity of the SSSI has been raised to Medium following our Section 42 comments, which is welcomed. The ‘area sensitivity’ remains ‘low’ due to the distance to the SSSI (Table A14.8). Natural England note that the highest level of mitigation will be implemented regardless, due to the presence of human receptors. As such, Natural England are content that dust impacts will be avoided, subject to securing implementation of the dust mitigation measures set out in Appendix 14.1 (C). Non-Road Mobile Machinery: - Impacts from NRMM emissions have been screened out. ES Table 14.3 ID 3.9.2 states that further information on NRMM will be included in the oCEMP, however no information is included at this stage. It is assumed that this detail will be provided in the detailed CEMP. Nonetheless, Natural England consider where NRMM are not sited within 200m of any SSSIs, impacts are unlikely. Due to the enhancement area between the SSSI and developed areas of the order limits, impacts from NRMM are unlikely. Nonetheless, Natural England would welcome clarity regarding the type, duration and location of NRMM within the detailed CEMP, post-consent. Decommissioning impacts are considered likely to be similar to construction & as such Natural England concur that decommissioning impacts to Clarborough Tunnel SSSI are unlikely (ES Paragraph 7.8.24). | Green | No Update | Green
NE9 | Nationally Designated Sites | Conclusions | Green | In summary, Natural England concur that impacts to any SSSIs during construction, operation and decommissioning are unlikely. | Green | No Update | Green
NE10 | Designated Landscapes | Designated Landscapes | Green | The proposed development is not located within, or within the setting of any nationally designated landscapes. As a result, NE has no specific comments to make on landscape implications of this development. | Green | No Update | Green
NE11 | Protected Species Licencing | Protected Species Licencing | Yellow | The project design principles include the avoidance of impacts to protected species as far as possible, to avoid the need for mitigation & protected species licencing, which is welcomed. It is noted that since our Section 42 comments, licences for bats and great crested newts are not likely to be required. As a result, the only species licence requirement reported in the ES appears to be for Badger: ‘A badger development licence is likely to be required for temporary impacts to a small number of setts’ (ES paragraph 7.8.165 & P147 (Appendix 4: Table 7.9)). If avoidance and appropriate buffering of all setts is not possible, a licence will be required, and we would recommend that a draft protected species licence application is submitted to enable Natural England to issue a Letter of No Impediment (LoNI). This will provide the planning inspectorate with certainty during examination that impacts to badger can be mitigated. To date, Natural England have not received a draft protected species licence application for badger. A draft protected species licence application could be submitted to Natural England for Badgers. Cost incurred for this could be recouped from the existing DAS contract between Natural England and the Applicant. | Yellow | No Update | Yellow
NE12 | Soils and Best & Most Versatile Land | ALC Survey Methodology | Amber | Natural England welcome the completion of an ALC survey across the Solar PV areas (722ha), in line with the 1988 ALC Guidelines & at a detailed level (1 auger per hectare with representative pits). However, no ALC survey has been undertaken in the Cable Route or Enhancement Areas: A) Cable Route: Natural England advised in our Section 42 response that, whilst cable laying works are short term and temporary, they have the potential to damage the soil resource and soil profile, including the potential for degrading agricultural land quality. This advice remains relevant and Natural England consider any soil handling activities have potential to damage the soil resource. ES Table 15.4 also sets out the PINS request for the ALC survey to have sufficient coverage, including the cable route. ES paragraph 15.7.18 states that soils will be ‘checked’ prior to construction to inform the SMP. Natural England advise that a full ALC survey of the cable route will be required to inform the soil handling practises necessary to minimise potential damage and provide a baseline soil profile to which the restoration can be compared to demonstrate the land has been appropriately reinstated. B) Enhancement Areas: Paragraph 5.3.2 of Natural England’s Section 42 response discussed the potential impact of intrusive ecological enhancements on the soil resource, and advised a full ALC survey should be undertaken across the enhancement areas to inform both avoidance of BMV land and soil handling/re-use where required. ES paragraph 15.7.13 states that no soil disturbance will occur within the enhancement areas; as such, no ALC survey has been undertaken in these areas. Natural England note that the majority of the Enhancement Areas are to be used for skylark mitigation (including continued arable rotation) and grassland creation. As such, whilst a full ALC survey of these areas, and the full order limits, is always Natural England’s advice, the absence of survey in these areas is not raised as a significant concern. However, Figure 6.9 includes small areas of pond creation and woodland planting. These measures have the potential to damage the soil resource. Woodland creation is considered to remove the possibility for land to be returned to agricultural use, and pond areas are likely to involve a degree of soil stripping, so an ALC survey is essential to inform the depth of topsoil (and suitability of subsoil to support a pond). There will then also be the surplus soil to consider. Whilst the total volume will likely be small, it is still an important consideration to ensure there is a certainty of re-use of the soil (preferably on site), in line with NPS EN-1 paragraph 5.11.14. Natural England advise that ALC survey of the cable route is required to: a) Inform avoidance of BMV in the first instance via micro-siting. b) Provide a baseline soil profile to inform restoration. Natural England also advise that clarity should be provided with regard to the ecological enhancements (woodland creation, pond creation and other potentially damaging activities) proposed in the enhancement areas, specifically with regard to the statement that ‘None of the ecological mitigation requires the soils to be disturbed (beyond ordinary cultivation and management)’. ALC survey of the areas to be used for pond creation and woodland creation is likely to be required to ascertain the soil type (and ALC grade), which will then inform the suitability of the soil to support the planting / habitat proposed and the soil handling requirements. | Amber | No Update | Amber
NE13 | Soils and Best & Most Versatile Land | Development Design and Avoidance of BMV Land | Amber | ES Chapter 3 (Site Description, Site Selection and Iterative Design Process) includes BMV land as a consideration during site selection, which is welcomed, however, little information is provided with regard to ‘micro-siting’ infrastructure away from BMV, or the highest grade BMV land within Chapter 3 and Chapter 15. ES Table 15.4 states that Section 15.6-15.7 include further information regarding how options have been considered to avoid or minimise loss of BMV land and maximise use of poorer quality agricultural land, however, little reference is made in these sections regarding avoidance of BMV land. Natural England request further detail on steps taken to avoid BMV as far as reasonably practicable, in line with the NPPF mitigation hierarchy and NPS EN-1 paragraph 5.11.12. | Amber | No Update | Amber
NE14 | Soils and Best & Most Versatile Land | ALC Survey Results and Data Presentation | Yellow | The ALC survey was undertaken across 722ha, and found that 639ha was BMV. Of this, 467ha BMV land is proposed for Solar PV areas and 12.1ha BMV is proposed for base areas for fixed equipment (in particular power conversion unit systems), the internal access tracks, and the BESS compound (i.e. soils disturbed for the operational lifetime of the project). The areas of temporary construction compounds have not been measured as the ES notes impacts are temporary (15.7.19). Natural England advise that without appropriate soil management, these impacts could be permanent. Whilst natural England welcome the reference to the SMP ensuring temporary elements of the proposals (e.g. temporary construction compounds) are restored appropriately, we request details of the areas (in ha) to be impacted by temporary construction works (including construction compounds), to ensure PINS and the secretary of state fully understand the scale and likelihood of potential impacts. | Yellow | No Update | Yellow
NE15 | Soils and Best & Most Versatile Land | Assessment of impacts to BMV land | Green | The sensitivity and magnitude of effects on Best and Most Versatile Land are correctly defined in ES tables 15.1 and 15.2, respectively. Natural England consider that the proposed PV Areas, if temporary as described, are unlikely to lead to significant permanent loss of BMV agricultural land, as a resource for future generations. This is because the solar panels would be secured to the ground by steel piles with limited soil disturbance and could be removed in the future with no permanent loss of agricultural land quality likely to occur, provided the appropriate soil management is employed and the development is undertaken to high standards. The same principle applies with regard to other areas of fixed infrastructure, however due to the increased possibility of damage to the soil resource (i.e. through soil stripping and storage), further onus is placed on the soil management practised, secured by the oSMP. See Refs NE16, 17 and 18 regarding time limits, soil management and reinstatement, respectively. | Green | No Update | Green
NE16 | Soils and Best & Most Versatile Land | Time Limit | Green | A decommissioning timeline is specified in DCO Requirement 21, securing the 40-year lifespan of the project. Where a time limit is applied relevant impacts may be considered temporary, providing correct soil management & reinstatement, thus protecting the long-term potential of the agricultural land resource. | Green | No Update | Green
NE17 | Soils and Best & Most Versatile Land | Soil Management | Yellow | Natural England note the commitment to produce a Soil Management Plan, and welcome the principles set out in the oSMP, including separate soil handling methodologies for each element of the development (oSMP sections 7-12). Each element of the proposal may have a differing effect on the soil resource and must be managed appropriately. Of particular note, the oSMP discusses working in the wetter winter period. It is welcomed that winter working is to be avoided where possible, with works only occurring when soils are in a suitable condition. It is Natural England’s advice that soils should only be handled when they are dry and friable. Whilst the oSMP does not entirely prohibit works in the winter period, Natural England welcome the requirement for soil testing before working in this period – in line with the Institute of Quarrying Field Tests for Soil Suitability; oSMP paragraph 6.5 includes stop conditions where conditions are not suitable for soil handling. Natural England request the oSMP requirement is amended to include consultation with Natural England. | Yellow | No Update | Yellow
NE18 | Soils and Best & Most Versatile Land | Soil Reinstatement | Yellow | ES paragraph 15.11.6 notes mitigation is possible to ensure land is restored to a ‘comparable quality’ (i.e. ALC grade, in line with relevant guidance as discussed at ES paragraph 15.2.5). ES Chapter 15 discusses restoration of all elements of the proposals in various locations, and it is in the oSMP that the commitment is made clear that: ‘The objective is to remove panels and restore all fixed infrastructure areas to return the land to the same ALC grade and condition as it was when the construction phase commenced.’ (oSMP Paragraph 14.2). This is essential to allow consideration of a loss of BMV land to be temporary and is in line with NPS EN-5 paragraph 2.9.25. Whilst the intent to restore all areas to the same quality is clear, it is noted that this paragraph (oSMP Paragraph 14.2) refers specifically to reinstatement following decommissioning. Natural England recommend that a similar commitment should be made clear within the oSMP that all land disturbed temporarily during construction (Access tracks, construction compounds, cable routes etc) is also restored to the same ALC grade, informed by the ALC survey. Commitment should be made clear within the oSMP that all land disturbed temporarily during construction (Access tracks, construction compounds, cable routes etc) are also restored to the same ALC grade, informed by the ALC survey. | Yellow | No Update | Yellow
NE19 | Soils and Best & Most Versatile Land | Monitoring & Research | Yellow | At this stage, no soil monitoring or research is proposed through the project. Monitoring would enable any adverse soil conditions arising during the operational phase to be identified and rectified. In addition, the long-term effects of solar development on overall soil health are not yet fully understood. Whilst similarities are expected to the benefits provided to soil health by arable reversion, the effect of solar panels on this could be better understood with further monitoring & research over the longer term. There is also little evidence & understanding around the application of alternative solar technologies in England. Large scale solar proposals offer the opportunity to develop understanding & push forward the implementation of new, multi-benefit technologies & management practices. NE recommend that a scheme of soil health monitoring could be implemented across the scheme for the lifetime of the development. NE recommend that the scheme could include an area dedicated to research into future technologies and/or management practises (i.e. agrivoltaics). | Yellow | No Update | Yellow
NE20 | Biodiversity Net Gain (BNG) | Biodiversity Net Gain (BNG) | N/A | ES Paragraphs 7.8.80 – 83 set out that the project will result in a net gain of: - 54.93% in habitat units - 35.53% in hedgerow units - 14.66% in watercourse units It should be noted that Natural England have not reviewed the Biodiversity Metric in detail. Nonetheless, Natural England welcome this provision, which exceeds the intended mandate of 10% (Biodiversity net gain for nationally significant infrastructure projects). Despite the calculated biodiversity net gains being significantly in excess of 10%, DCO Requirement 6 is limited to securing a minimum of 10% Biodiversity Net Gain. Natural England would encourage the applicant to secure gains in excess of the minimum 10%, as demonstrated within the Biodiversity Metric Calculations. It is noted that similar projects Cottam Solar Project and West Burton Solar Project both included commitment to significant Biodiversity Net Gains (see Requirement 9 of the DCOs for these projects as made by the Secretary of State). | N/A | No Update | N/A
NE21 | Other Comments | Ancient Woodland | Green | There are two Ancient Woodlands (Ancient Semi Natural Woodland and Plantation on Ancient Woodland) site within 2km of the order limits. The closest ancient woodland is 1.3km to the east of the Site (Burton Wood) (ES paragraph 7.6.42). No direct habitat connectivity with the Site, via hedgerows, other semi-natural habitat corridors, or footpaths has been identified. In addition, no Ancient or Veteran trees have been identified within the order limits (Appendix 6.5). As a result, there will be no direct loss or damage to Ancient Woodland as a result of the development; thus NE have no specific comment to make in this regard and refer to Standing Advice. | Green | No Update | Green
NE22 | Other Comments | Connecting People with Nature | Yellow | ES Figure 3.3 (Public Rights of Way Plan) shows the significant number of Public Rights of Way (PRoW) in and around the order limits. Natural England welcome the inclusion of Appendix 6.6 (Assessment of Public Rights of Way) and oCTMP Section 7 (PRoW Management Plan) (Appendix 13.2). Whilst Natural England have no specific comment regarding the mitigation measures proposed, the principles of the PRoW Management Plan are welcomed. The PRoW Management Plan also sets out the commitment to retain all routes within the order limits for the full operational period, as well as the creation of two additional permissive footpaths, which is also welcomed. There may be further opportunity through the scheme to improve public knowledge and understanding of both the Solar Project and it’s impact on Biodiversity and Access, i.e. through the use of Signage and interpretation boards. | Yellow | No Update | Yellow