## Part 1 – Cat 1 (Owners)
PART 1
Ref | Landowner/ Affected Party | Agent/ Representative | BoR Category and Interest | Book of Ref. Plot No. | Plan Ref. No. | Description of Land | Description of Rights Requested | Works Number(s) and Description | Status of Objection | Notes | Last Updated | Summary of Negotiations | Status of Negotiations | Relevant Rep Ref No. | Written Rep Ref No. | Ref No. for any other docs submitted by IP/AP. | Ref No. for Applicant's Response
266498, 266503 | Alexander William Martin Mitchell, Burges Salmon Trustees Limited, James Fuller Bt | Georgina Bush | Cat 1 - Owner | 15-014 | 15 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400kV cable corridor | n/a |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent, issuing updated Heads of Terms on 21 October 2025. The Applicant wrote to the landowner 2 December 2025 and understands the landowner and their agent met on 10 December 2025 to discuss the Heads of Terms. The Applicant emailed the agent on 15 January 2026 and 18 February 2026 is currently awaiting feedback from the landowner and their agent. The Applicant will continue to engage and offer meetings and is hopeful the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to seek to engage with the landowner and their agent. Since Procedural Deadline A, the Applicant has extended the incentive deadline for signing the Heads of Terms. The Applicant remains committed to engaging with the landowner having issued them an updated response on 24 February 2026, to which The Applicant has not received any feedback. The Applicant will continue to engage and offer meetings and is hopeful the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to seek engage with the landowner and their agent, most recently emailing the agent on 19 May 2026. The Applicant is currently awaiting feedback and will continue to offer meetings to discuss the Heads of Terms. Deadline 3 The Applicant continues to seek engage with the landowner and their agent, most recently receving a response from the landowner's agent on 4 June 2026. The Applicant will continue to offer meetings to discuss the Heads of Terms.
285951 | Anna Smith | Ben Compton | Cat 1 - Owner | 04-048, 04-049, 04-050, 04-051, 04-052, 04-053, 04-054, 04-062, 04-063, 04-064, 04-065, 04-066, 04-067, 04-068 | 4 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1D, 5A, 5B, 6, 1 - Solar PV cabling, 400 kV cable corridor, 132kV cabling, General works, Solar PV area | n/a |  |  | Option Holder Following initial engagement, the Applicant negotiated Heads of Terms, which were agreed on 4 March 2024. The Parties then worked together to agree an option agreement which was signed and entered into on 8 August 2025 for the use of the land as part of the Scheme.
|  |  |  | 01-048, 01-049, 01-050, 04-040, 04-042, 04-044, 04-046 | 1, 4 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5B, 5A - 132 kV cabling, 400 kV cable corridor
266494, 266495 | Anne Elizabeth Mary Sawtell-Gist, Patricia Alexandra Sawtell | George King | Cat 1 - Owner | 15-021 | 15 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | n/a |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent, issuing updated Heads of Terms on 21 October 2025. The Applicant met with the landowner on 9 October 2025 to discuss the Heads of Terms. The Applicant wrote to the landowner on 2 December 2025 and most recently sent an email to the agent on 3 February 2026. The Applicant is currently awaiting further feedback from the landowner and their agent. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner and their agent. Since Procedural Deadline A, The Applicant wrote to the agent on 9 March with amended Heads of Terms, with the Landowners agent responding with requested changes. On the 23 March 2026 The Applicant responded with amended Heads of Terms, with only 5 clauses and commercials outstanding. The Applicant met with the Landowners agent on 10 April 2026 to discuss the Heads of Terms and finished the meeting with agreed commercials and only 2 clauses to be agreed in the Heads of Terms. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to engage with the landowner and their agent. Since Deadline 1, the Applicant has continued work towards resolving the final material clause of the voluntary agreement and most recently had a call with the landowner's agent on 19 May 2026. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant continues to engage with the landowner and their agent. Since Deadline 2, the Applicant has continued to work towards resolving the final material clausesof the voluntary agreement. The Applicant most recently emailed the landowner's agent on 11 June 2026 with updated Heads of Terms. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement.
278876, 278878 | Antony Philip Charles Creed, Sarah Margaret Creed |  | Cat 1 - Owner | 14-015 | 14 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A - Temporary access | n/a |  |  | Negotiations for temporary possession The Applicant intends to negotiate a temporary licence agreement for the temporary access rights prior to commencement of works post consent. The Applicant is endeavouring to progress negotiations with the landowner on this approach owing to the temporary use and has offered meetings to discuss the rights required. Procedural Deadline A The Applicant is seeking to negotiate a temporary licence agreement for the temporary access rights prior to commencement of works post consent. The Applicant is confident the temporary access rights can be agreed voluntarily. Deadline 1 The Applicant is seeking to negotiate a temporary licence agreement for temporary access rights prior to commencement of works post consent. Temporary access will be required for the three years of construction. The Applicant is confident the temporary access rights can be agreed voluntarily. Deadline 2 The Applicant is seeking to negotiate a temporary licence agreement for temporary access rights prior to commencement of works post consent. Temporary access will be required for the three years of construction. The Applicant is confident the temporary access rights can be agreed voluntarily. Deadline 3 The Applicant is seeking to negotiate a temporary licence agreement for temporary access rights prior to commencement of works post consent. Temporary access will be required for the three years of construction. The Applicant is confident the temporary access rights can be agreed voluntarily.
278813 | Ashton Robert Hawker |  | Cat 1 - Owner | 08-002, 08-003, 09-012, 09-016 | 8, 9 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | Open |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant issued updated Heads of Terms on 21 October 2025 and wrote to the landowner 2 December 2025. The Applicant is currently awaiting feedback on the Heads of Terms. The Applicant will continue to offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 Since Procedural Deadline A, the Applicant engaged with the landowner on the 30 March 2026. The landowner responded on 2 April confirming their position to not sign the Heads of Terms at this stage. The Applicant remains committed to engage with the landowner throughout Examination to progress a voluntary agreement. Deadline 2 Since Deadline 1, the landowner maintains their position to not sign the Heads of Terms at this stage. The Applicant remains committed to engage with the landowner throughout Examination to progress a voluntary agreement. Deadline 3 Since Deadline 2, the landowner maintains their position to not sign the Heads of Terms at this stage. The Applicant remains committed to engage with the landowner throughout Examination to progress a voluntary agreement. |  | RR-0431 - Ashton Hawker RR-1793 - Hawker Farms
76468 | Bristol Diocesan Board Of Finance Limited | Georgina Bush | Cat 1 - Owner | 04-028 | 4 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 5B - 400kV cable corridor, 132 kV cabling | n/a |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent, issuing updated Heads of Terms on 21 October 2025. The Applicant wrote to the landowner 2 December 2025 and sent emails to the agent on 15 January 2026 and 18 February 2026, and is currently awaiting feedback from the landowner and their agent. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to seek to engage with the landowner and their agent. Since Procedural Deadline A, the Applicant has extended the incentive deadline for signing the Heads of Terms. The Applicant remains committed to engaging with the landowner having issued them an updated response on 24 February 2026, to which The Applicant has not received any feedback. The Applicant will continue to engage and offer meetings and is hopeful the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to seek engage with the landowner and their agent, most recently emailing the agent on 19 May 2026. The Applicant is currently awaiting feedback and will continue to offer meetings to discuss the Heads of Terms. Deadline 3 The Applicant continues to seek engage with the landowner and their agent, most recently receving a response from the landowner's agent on 4 June 2026. The Applicant reissued Heads of Terms to the landowner for signing on 12 June 2026 and is confident the necessary land rights can be acquired by voluntary agreement.
278709, 278710 | Bryan Ashton Hawker, Michael Robert Edward Hawker | Toby Bateman | Cat 1 - Owner | 11-001 | 11 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | n/a |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner, meeting on 18 September 2025. The Applicant issued updated Heads of Terms on 21 October 2025 and wrote to the landowner on 2 December 2025. The Applicant sent an email on 16 February 2026 and is awaiting feedback from the landowner and agent. The Applicant will continue to offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner’s agent. Since Procedural Deadline A, the Applicant has had a phone call meeting on the 14 April 2026 and subsequent negotiations have continued to discuss the final material clause within the voluntary agreement. The Applicant will continue to engage and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to engage with the landowner's agent. Since Deadline 1, the Applicant has continued work towards resolving the final material clause of the voluntary agreement excluding specific commercial aspects. The Applicant will continue to engage and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant continues to engage with the landowner's agent. Since Deadline 2, the Applicant has continued work towards resolving the final material clause of the voluntary agreement excluding specific commercial aspects. The Applicant will continue to engage and is confident the necessary land rights can be acquired by voluntary agreement.
275396 | CERT Corsham Limited | Praxis Group | Cat 1 - Owner | 15-012 | 15 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | n/a |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant received signed Heads of Terms from the landowner on 17 December 2025. The Applicant is currently drafting an option agreement to be issued to the landowner’s solicitor in due course. The Applicant is confident the necessary land rights can be acquired by voluntary agreement.
278723 | Chippenham Golf Centre Limited |  | Cat 1 - Owner | 11-009 | 11 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | n/a |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant issued updated Heads of Terms on 21 October 2025. The Applicant continues to engage and offer meetings to discuss the Heads of Terms and is awaiting feedback from the landowner. Deadline 1 The Applicant continues attempts to engage with the landowner. Since Procedural Deadline A, the Applicant has continued attempts to engage with the landowner with the last communication being 9 April 2026 and 28 April 2026. The Applicant remains committed to engaging with the landowner to progress a voluntary agreement. Deadline 2 The Applicant continues to engage with the landowner. Since Deadline 1, the Applicant has received a response from the landowner on 15 May 2026 and is in the process of confirming an appropriate meeting date and time to discuss this holding further. The Applicant remains committed to engaging with the landowner to progress a voluntary agreement. Deadline 3 The Applicant continues to engage with the landowner. Since Deadline 2, the Applicant has had a meeting with the landowner on 05 June 2026 to discuss the voluntary agreement and negotiate specific terms. The Applicant has agreed the next steps with the landowner to progress a voluntary agreement and is commited to securing the relevant neccessary rights voluntarily.
278835, 278836 | Christine Burgess, Clyde Burgess | George King | Cat 1 - Owner | 09-010 | 9 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | Open |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent. The Applicant met with the agent on 9 October 2025 and issued updated Heads of Terms on 21 October 2025. The Applicant wrote to the landowner on 2 December 2025 and most recently sent an email to the agent on 3 February 2026. The Applicant is currently awaiting further feedback from the landowner and their agent. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner and their agent. Since Procedural Deadline A, The Applicant wrote to the agent on 9th March 2026 with amended Heads of Terms, with the Landowners agent responding with requested changes. On the 23 March 2026 The Applicant responded with amended Heads of Terms, with only 5 clauses and commercials outstanding. The Applicant met with the Landowners agent on 10 April 2026 to discuss the Heads of Terms and finished the meeting with agreed commercials and only 2 clauses to be agreed in the Heads of Terms. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to engage with the landowner and their agent. Since Deadline 1, the Applicant has continued work towards resolving the final material clause of the voluntary agreement and most recently had a call with the landowner's agent on 19 May 2026. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant continues to engage with the landowner and their agent. Since Deadline 2, the Applicant has continued to work towards resolving the final material clauses of the voluntary agreement. The Applicant most recently emailed the landowner's agent on 11 June 2026 with updated Heads of Terms. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement. |  | RR-0916 - Clyde Stanley Burgess
|  |  |  | 09-011 | 9 | As described in the Book of Reference | Land is subject to Temporary Possession | 5A(v) - Cable corridor temporary construction compound
278724, 278806 | Christopher Bernard Edwin Carpenter, Andrew Raymond James Carpenter | George King | Cat 1 - Owner | 15-008 | 15 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | n/a |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent. The Applicant met with the agent on 9 October 2025 and issued updated Heads of Terms on 21 October 2025. The Applicant wrote to the landowner on 2 December 2025 and most recently sent an email to the agent on 3 February 2026. The Applicant is currently awaiting further feedback from the landowner and their agent. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner and their agent. Since Procedural Deadline A, The Applicant wrote to the agent on 9 March 2026 with amended Heads of Terms, with the Landowners agent responding with requested changes. On the 23 March 2026 The Applicant responded with amended Heads of Terms, with only 5 clauses and commercials outstanding. The Applicant met with the Landowners agent on 10 April 2026 to discuss the Heads of Terms and finished the meeting with agreed commercials and only 2 clauses to be agreed in the Heads of Terms. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to engage with the landowner and their agent. Since Deadline 1, the Applicant has continued work towards resolving the final material clause of the voluntary agreement and most recently had a call with the landowner's agent on 19 May 2026. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The applicant continues to engage with the landowner and their agent. Since Deadline 2, the Applicant has continued to work towards resolving the final material clauses of the voluntary agreement. The Applicant most recently emailed the landowner's agent on 11 June 2026 with updated Heads of Terms. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement.
278764 | Christopher William Buss | Toby Bateman | Cat 1 - Owner | 11-003, 11-004, 11-005 | 11 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 8A, 5A(v) - 400 kV cable corridor, Temporary access, Cable corridor temporary construction compound | n/a |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent, issuing updated Heads of Terms on 21 October 2025. The Applicant met with the landowner on 24 October 2025 and wrote to the landowner on 2 December 2025. The Applicant sent an email on 16 February 2026 to the agent and is awaiting feedback from the landowner and agent. The Applicant will continue to offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner’s agent. Since Procedural Deadline A, the Applicant has had a phone call meeting on the 14 April 2026 and subsequent negotiations have continued to discuss the final material clause within the voluntary agreement. The Applicant will continue to engage and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to engage with the landowner's agent. Since Deadline 1, the Applicant has continued work towards resolving the final material clause of the voluntary agreement excluding specific commercial aspects. The Applicant will continue to engage and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant continues to engage with the landowner's agent. Since Deadline 2, the Applicant has continued work towards resolving the final material clause of the voluntary agreement excluding specific commercial aspects. The Applicant will continue to engage and is confident the necessary land rights can be acquired by voluntary agreement.
266480 | Clinton Ernest Dicks | Simon Male | Cat 1 - Owner | 16-006, 16-010 | 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | n/a |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent, issuing updated Heads of Terms on 21 October 2025. The Applicant wrote to the landowner on 2 December 2025, and most recently sent an email to the agent on 18 February 2026 and is currently awaiting further feedback from the landowner and their agent. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner and their agent. The Applicant most recently had meetings with the agent on 26 and 27 February 2026, during which the Applicant was advised by the landowner’s agent that their client does not wish to progress with negotiating a voluntary agreement owing to site specific aspirations. The Applicant will continue to seek to engage with the landowner and their agent to offer meetings if the landowner’s position changes. Deadline 2 The Applicant continues to engage with the landowner and their agent. The Applicant has attempted to contact the landowner's agent on 19 May 2026 via call and email to seek an update on the landowner's specific aspirations. The Applicant will continue to seek to engage with the landowner and their agent to offer meetings if the landowner's position changes. Deadline 3 The Applicant continues to engage with the landowner and their agent. The Applicant had a response from the landowner's agent on 26 May confirming the landowner does not wish to progress with negotiating a voluntary agreement. The Applicant will continue to seek to engage with the landowner and their agent if the landowner's position changes.
278750 | David Geoffrey Wilmott | Anthony Wright | Cat 1 - Owner | 11-011 | 11 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | n/a |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent. The Applicant met with the agent on 9 October 2025 and issued updated Heads of Terms on 21 October 2025. The Applicant wrote to the landowner on 2 December 2025, and most recently sent an email to the agent on 17 February 2026 and awaits feedback. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner and their agent. Since Procedural Deadline A, The Applicant wrote to the agent on 9th March 2026 with amended Heads of Terms, with the Landowners agent responding with requested changes. On the 23 March 2026 The Applicant responded with amended Heads of Terms, with only 5 clauses and commercials outstanding. The Applicant met with the Landowners agent on 10th April 2026 to discuss the Heads of Terms and finished the meeting with agreed commercials and only 2 clauses to be agreed in the Heads of Terms. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to engage with the landowner and their agent. Since Deadline 1, the Applicant has continued work towards resolving the final material clause of the voluntary agreement and most recently emailed the landowner's agent on 19 May 2025. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant continues to engage with the landowner and their agent. Since Deadline 2, the Applicant has continued to work towards resolving the final material clauses of the voluntary agreement. The Applicant most recently emailed the landowner's agent on 11 June 2026 with updated Heads of Terms. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement.
278801, 278803, 278805 | David Henry Spencer, Martin Douglas Spencer, Winston Francis Spencer, Timothy Reynolds, Paul Reynolds, Naomi Reynolds | Barry Meade | Cat 1 - Owner | 10-011 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | Open |  |  | Negotiations for rights The Applicant understands there has been a change of ownership and is undertaking further due diligence before issuing populated Heads of Terms. Procedural Deadline A The Applicant met with the landowner on 23 September 2025 and issued populated Heads of Terms on 21 October 2025. The Applicant continues to engage with the landowner and their agent to discuss the Heads of Terms. The Applicant is confident the necessary rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner’s agent. Since Procedural Deadline A, the Applicant has returned the latest set of comments on the voluntary agreement to the landowner’s agent on 10 April 2026. Prior to the receipt of comments, the Applicant chased the agent for comments on the 25 February 2026, 5 March 2026, 20 March 2026, 25 March 2026, 30 March 2026. The current position with the landowner's agent is that comments on the current agreement are to be distributed after engagement with other agents affected by the Project. The Applicant remains committed to engaging with the landowner and their agent to progress a voluntary agreement to secure the necessary land rights. Deadline 2 The Applicant continues to engage with the landowner. Since Deadline 1, the Applicant has continued attempts to secure a telephone meeting with the landoners agent to discuss the specific terms within the voluntary agreement. The Applicant remains committed to engaging with the landowner and their agent to progress a voluntary agreement to secure the necessary land rights. Deadline 3 The Applicant continues to engage with the landowner. Since Deadline 2, the Applicant has continued work towards finalising the specific commerical aspects to the voluntary agreement. The Applicant remains committed to engaging with the landowner and their agent to progress a voluntary agreement to secure the necessary land rights. |  | Naomi Reynolds - RR-3411, Tim Reynolds - RR-4707
241382 | David Matthew Irvine | Anthony Wright | Cat 1 - Owner | 04-039, 04-043, 04-045 | 4 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 5B - 400kV cable corridor, 132 kV cabling | Open |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent. The Applicant met with the agent on 9 October 2025 and issued updated Heads of Terms on 21 October 2025. The Applicant wrote to the landowner on 2 December 2025, and most recently sent an email to the agent on 17 February 2026. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner and their agent. Since Procedural Deadline A, The Applicant wrote to the agent on 9th March 2026 with amended Heads of Terms, with the Landowners agent responding with requested changes. On the 23 March 2026 The Applicant responded with amended Heads of Terms, with only 5 clauses and commercials outstanding. The Applicant met with the Landowners agent on 10th April to discuss the Heads of Terms and finished the meeting with agreed commercials and only 2 clauses to be agreed in the Heads of Terms. The Applicant most recently emailed the agent on the 29 April 2026 and is currently awaiting further feedback from the landowner and their agent. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to engage with the landowner and their agent. Since Deadline 1, the Applicant has continued work towards resolving the final material clause of the voluntary agreement and most recently emailed the landowner's agent on 19 May 2025. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant continues to engage with the landowner and their agent. Since Deadline 2, the Applicant has continued to work towards resolving the final material clauses of the voluntary agreement. The Applicant most recently emailed the landowner's agent on 11 June 2026 with updated Heads of Terms. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement. |  | RR-0981 - Dave Irvine
278796 | David Robert Walker | George King | Cat 1 - Owner | 14-051 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | n/a |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent. The Applicant met with the landowner and their agent on the 10 September 2025 and followed up with a meeting with their agent on 9 October 2025 to discuss the Heads of Terms. The Applicant issued updated Heads of Terms on 21 October 2025. The Applicant wrote to the landowner on 2 December 2025 and most recently sent an email to the agent on 3 February 2026. The Applicant is currently awaiting further feedback from the landowner and their agent. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner and their agent. Since Procedural Deadline A, The Applicant wrote to the agent on 9 March with amended Heads of Terms, with the Landowners agent responding with requested changes. On the 23 March 2026 The Applicant responded with amended Heads of Terms, with only 5 clauses and commercials outstanding. The Applicant met with the Landowners agent on 10th April 2026 to discuss the Heads of Terms and finished the meeting with agreed commercials and only 2 clauses to be agreed in the Heads of Terms. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to engage with the landowner and their agent. Since Deadline 1, the Applicant has continued work towards resolving the final material clause of the voluntary agreement and most recently had a call with the landowner's agent on 19 May 2025. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant continues to engage with the landowner and their agent. Since Deadline 2, the Applicant has continued to work towards resolving the final material clauses of the voluntary agreement. The Applicant most recently emailed the landowner's agent on 11 June 2026 with updated Heads of Terms. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement.
65954, 149532, 258289 | David Terence Digby Harrel, Matthew James Wakefield, Christopher Harold Smith |  | Cat 1 - Owner | 03-015, 03-016, 03-017, 03-018, 03-019, 03-020, 03-021, 03-022, 03-023, 03-024, 03-025, 03-026, 03-027, 03-028, 03-029, 03-030, 03-031, 03-032, 03-033, 03-034, 03-035, 03-036, 03-037, 03-038, 03-039, 03-040, 03-041, 03-042, 03-067, 03-068, 03-071, 03-072, 03-073, 03-074, 03-075, 03-077, 03-078, 03-079, 03-080 | 3 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1D, 6, 9, 10B, 5B, 3B - Solar PV area, Solar PV cabling, General works, Habitat management area, Permissive paths for pedestrian and equestrian users, 132 kV cabling, 132 kV substation | Open |  |  | Option Holder Following initial engagement, the Applicant negotiated Heads of Terms, which were agreed on 22 December 2022. The Parties then worked together to agree an option agreement which was entered into on 21 July 2023 and varied on 28 July 2025 for the use of the land as part of the Scheme.
|  |  |  | 03-014 | 3 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1D, 6 - Solar PV cabling, General works
278745, 278871 | De Vernon Ltd, De Vernon Trustees Inc | Georgina Bush | Cat 1 - Owner | 14-050 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | n/a |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent, issuing updated Heads of Terms on 21 October 2025. The Applicant wrote to the landowner 2 December 2025 and understands the landowner and their agent met on 10 December 2025 to discuss the Heads of Terms. The Applicant emailed the agent on 15 January 2026 and 18 February 2026 is currently awaiting feedback from the landowner and their agent. The Applicant will continue to engage and offer meetings and is hopeful the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to seek to engage with the landowner and their agent. Since Procedural Deadline A, the Applicant has extended the incentive deadline for signing the Heads of Terms. The Applicant remains committed to engaging with the landowner having issued them an updated response on 24 February 2026, to which The Applicant has not received any feedback. The Applicant will continue to engage and offer meetings and is hopeful the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to seek engage with the landowner and their agent, most recently emailing the agent on 19 May 2026. The Applicant is currently awaiting feedback and will continue to offer meetings to discuss the Heads of Terms. Deadline 3 The Applicant continues to seek engage with the landowner and their agent, most recently receving a response from the landowner's agent on 4 June 2026. The Applicant will continue to offer meetings to discuss the Heads of Terms.
275397, 275398, 275399 | Dorothy Elizabeth Robinson, Richard Luke Mander, Raymond Haslett | George King | Cat 1 - Owner | 15-009, 15-010, 15-011, 15-013 | 15 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | n/a |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent. The Applicant met with the landowner and their agent on 10 September 2025 and followed up with a meeting with their agent on 9 October 2025 to discuss the Heads of Terms. The Applicant issued updated Heads of Terms on 21 October 2025. The Applicant wrote to the landowner on 2 December 2025 and most recently sent an email to the agent on 3 February 2026. The Applicant is currently awaiting further feedback from the landowner and their agent. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner and their agent. Since Procedural Deadline A, The Applicant wrote to the agent on 9 March 2026 with amended Heads of Terms, with the Landowners agent responding with requested changes. On the 23 March 2026 The Applicant responded with amended Heads of Terms, with only 5 clauses and commercials outstanding. The Applicant met with the Landowners agent on 10 April 2026 to discuss the Heads of Terms and finished the meeting with agreed commercials and only 2 clauses to be agreed in the Heads of Terms. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to engage with the landowner and their agent. Since Deadline 1, the Applicant has continued work towards resolving the final material clause of the voluntary agreement and most recently had a call with the landowner's agent on 19 May 2026. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant continues to engage with the landowner and their agent. Since Deadline 2, the Applicant has continued to work towards resolving the final material clauses of the voluntary agreement. The Applicant most recently emailed the landowner's agent on 11 June 2026 with updated Heads of Terms. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement.
278833, 278834 | Elizabeth Mary England Cole, Peter Edward Cole |  | Cat 1 - Owner | 08-004 | 8 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | Open |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant issued updated Heads of Terms on 21 October 2025 and wrote to the landowner 2 December 2025. The Applicant is currently awaiting feedback on the Heads of Terms. The Applicant will continue to offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 Since Procedural Deadline A, the Applicant received correspondence from the landowner’s representative on 9 December 2025 confirming their position to not sign the Heads of Terms. The Applicant remains committed to engage with the landowner throughout Examination to progress a voluntary agreement. Deadline 2 Since Deadline 1, the landowner has maintained their position to not sign the Heads of Terms. The Applicant remains committed to engage with the landowner throughout Examination to progress a voluntary agreement. Deadline 3 Since Deadline 2, the landowner has maintained their position to not sign the Heads of Terms. The Applicant remains committed to engage with the landowner throughout Examination to progress a voluntary agreement. |  | RR-3056 - Mary Cole RR-3731 & RR 3732 - Peter Cole
278843, 278844 | Gabrielle Alice Corp, Graham John Corp | Rupert Bendell | Cat 1 - Owner | 11-021 | 11 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | n/a |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural deadline A The Applicant continues to engage with the landowner and their agent, issuing updated Heads of Terms on 21 October 2025. The Applicant met with the agent on 5 November 2025 to discuss the Heads of Terms. The Applicant wrote to the landowner on 2 December 2025 and most recently sent an email to the agent on 12 February 2026. The Applicant will continue to offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner and their agent. Since Procedural Deadline A, the Applicant has revised the commercial position offered. On 26 March 2026 and 13 April 2026 the Applicant requested feedback and is currently awaiting a response from the landowner and their agent. The Applicant has not received substantive feedback on non-commercial terms therefore considers outstanding matters to relate to the commercial offer within the Heads of Terms. The Applicant will continue to offer meetings to discuss the Heads of Terms and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to engage with the landowner and their agent. Since Deadline 1, the Applicant met with the agent on 15 May 2026 and reissued Heads of Terms on 19 May 2026. The Applicant is currently awaiting feedback on the Heads of Terms and is confident the necessary land rights can be aquired by voluntary agreement. Deadline 3 The Applicant continues to engage with the landowner and their agent. The Applicant and the landowner's agent have agreed updated clauses within the Heads of Terms relating to drainage and soil management. The Applicant will continue to offer meetings to discuss the Heads of Terms and is confident the necessary land rights can be acquired by voluntary agreement.
50968, 54640 | Jack Thomas Frank Nicholas, Thomas Howard Nicholas | George Tiley | Cat 1 - Owner | 16-011, 16-012, 16-013, 16-014, 16-015 | 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 5A(v) - 400 kV cable corridor, Cable corridor temporary construction compound | Open |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent. The Applicant met with the landowner’s their agent on the 8 October 2025. The Applicant wrote to the landowner on 2 December 2025, and most recently sent an email to the agent on 10 February 2026 and is currently awaiting further feedback from the landowner and their agent. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner’s professional representative. Since Procedural Deadline A, the Applicant has distributed clarification requests on 2 April 2026 to which a response has not been received. The Applicant is acknowledging of the Landowner's concerns relating to access and is appropriately seeking to engage with the professional representation. The Applicant remains committed to engaging with the landowner and their agent to progress a voluntary agreement however it cannot seek to progress a voluntary agreement in the absence of receiving substantive consistent feedback from the landowner and their agent. Deadline 2 The Applicant continues to engage with the landowners agent. Since Deadline 1, the Applicant has not yet recieved material comments on the voluntary agreementes from the landowners agent. The Applicant remains committed to engaging with the landowner and their agent to progress a voluntary agreement to secure the necessary land rights. Deadline 3 The Applicant continues to engage with the landowners agent. Since Deadline 2, the Applicant has amended the landowners book of refrence parcels in line with the assumption that they are an reputed occupier on parcel 16-014. The Applicant is awaiting appropiate evidence and has contacted the freeholder of the plot seeking this evidence. The Applicant remains committed to engaging with the landowner and their agent to progress a voluntary agreement to secure the necessary land rights. |  | RR-3146 - Messer Nicholas
258268, 258270 | James Keith Gay, Rebecca Jane Gay |  | Cat 1 - Owner | 01-039 | 1 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1D, 5B - Solar PV cabling, 132 kV cabling | Open |  |  | Option Holder Following a transfer of title to the stated party, the relevant terms of the option agreement were duly transferred to the new owner. The Transfer of part registered title(s) was signed by all parties on 19 August 2025. Accordingly, the Project retains all necessary rights over the land to facilitate the delivery of the Scheme. |  | RR-2041 - James Gay RR-3896 - Rebecca Gay
258268, 258311, 258313 | James Keith Gay, Sean Norman Richards, Ruth Richards |  | Cat 1 - Owner | 01-040 | 1 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1D, 5B - Solar PV cabling, 132 kV cabling | Open |  |  | Option Holder Following initial engagement, the Applicant negotiated Heads of Terms, which were agreed on 17 May 2022. The Parties then worked together to agree an option agreement which was entered into on 26 July 2023 and varied on 13 December 2024 for the use of the land as part of the Scheme. Procedural Deadline A There has been no substantive change to the negotiation position on the plot at Procedural Deadline A. For clarity, the Applicant confirms that it contains all the necessary rights over the land to deliver the Scheme on the basis of the option agreement of 13 December 2024. |  | RR-2041 - James Gay
278730 | James Paul Archibald Methuen-Campbell | Tom French | Cat 1 - Owner | 12-001, 12-002, 12-003, 12-004, 12-005, 12-006, 12-007, 12-011, 12-012, 12-013, 12-014, 12-018, 12-020, 13-001, 13-002, 13-017, 13-018, 13-020, 13-021, 13-022, 13-023, 13-025, 13-037, 14-001, 14-002, 14-003, 14-004, 14-005, 14-007, 14-018, 14-019, 14-020, 14-021, 14-022, 14-023, 14-026, 14-027, 14-028, 14-028a, 14-032, 14-035, 14-038, 14-042, 14-044, 14-044a, 14-045,14-045a, 14-046, 14-047 | 12, 13, 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 5A(v), 8A - 400 kV cable corridor, Cable corridor temporary construction compound, Temporary access, | n/a |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent, issuing updated Heads of Terms on 21 October 2025. The Applicant met with the agent on 5 November 2025, 27 November 2025 and 3 February 2026 to discuss the Heads of Terms. The Applicant will continue to offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner and their agent. Since Procedural Deadline A, the Applicant has revised the commercial position offered. On the 25 February 2026, the Applicant provided a revised commercial proposal to the landowner via their agent based on feedback on the Heads of Terms gathered in the meeting on 3 February 2026. This revised proposal was rejected by the agent on 18th March 2026, citing concerns, however no further tangible detail has been put forward since that date. The Applicant will continue to engage with the landowner via the agent in order to progress matters and reach a voluntary agreement. Deadline 2 The Applicant is still awaiting tangible detail from the landowner's agent regarding the commercial position offered. Deadline 3 The Applicant is awaiting tangible detail from the landowner's agent regarding the commercial position offered, and feedback surrounding the wider terms within the document.
|  |  |  | 12-019 | 12 | As described in the Book of Reference | Land is subject to Temporary Possession | 5A(v) - Cable corridor temporary construction compound
278755, 278756 | Janet Mary Tayler, Raymond John Tayler | Arthur Chambers | Cat 1 - Owner | 11-002 | 11 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | n/a |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent. The Applicant met with the landowner’s their agent on the 8 October 2025. The Applicant wrote to the landowner on 2 December 2025, and most recently sent an email to the agent on 12 February 2026 and is currently awaiting further feedback from the landowner and their agent. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the Landowner and their agent and most recently had a meeting with their agent on 10 April 2026 to discuss the final clauses outstanding within the voluntary agreement. Upon completion of the meeting, there are only two outstanding clauses to be agreed. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to engage with the landowner and their agent. Since Deadline 1, the Applicant has continued work towards resolving the final material clause of the voluntary agreement and most recently emailed the landowner's agent on 19 May 2025. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The applicant continues to engage with the landowner and their agent. Since Deadline 2, the Applicant has continued to work towards resolving the final material clauses of the voluntary agreement. The Applicant most recently emailed the landowner's agent on 11 June 2026 with updated Heads of Terms. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement.
328669 | Joden (Builders) Limited |  | Cat 1 - Owner | 17-003 | 17 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A - Temporary access | n/a |  |  | Negotiations for temporary possession The Applicant intends to negotiate a temporary licence agreement for the temporary access rights prior to commencement of works post consent. The Applicant is endeavouring to progress negotiations with the landowner on this approach owing to the temporary use and has offered meetings to discuss the rights required. Procedural Deadline A The Applicant is seeking to negotiate a temporary licence agreement for the temporary access rights prior to commencement of works post consent. The Applicant is confident the temporary access rights can be agreed voluntarily. Deadline 1 The Applicant is seeking to negotiate a temporary licence agreement for temporary access rights prior to commencement of works post consent. Temporary access will be required for the three years of construction. The Applicant is confident the temporary access rights can be agreed voluntarily. Deadline 2 The Applicant is seeking to negotiate a temporary licence agreement for temporary access rights prior to commencement of works post consent. Temporary access will be required for the three years of construction. The Applicant is confident the temporary access rights can be agreed voluntarily. Deadline 3 The Applicant is seeking to negotiate a temporary licence agreement for temporary access rights prior to commencement of works post consent. Temporary access will be required for the three years of construction. The Applicant is confident the temporary access rights can be agreed voluntarily.
258288 | John Alistair Baillie | Anthony Wright | Cat 1 - Owner | 05-033, 05-039, 05-042 | 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1D, 5B, 8A - Solar PV cabling, 132 kV cabling, Temporary access | Open |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent. The Applicant met with the agent on 9 October 2025 and issued updated Heads of Terms on 21 October 2025. The Applicant wrote to the landowner on 2 December 2025, and most recently met with the landowner and their agent on 23 February 2026 to discuss the Heads of Terms. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner and their agent. Since Procedural Deadline A, The Applicant had a meeting with the landowner and their agent on 23 February 2026 and wrote to the agent on 9 March 2026 with amended Heads of Terms, with the Landowners agent responding with requested changes. On the 23 March 2026 The Applicant responded with amended Heads of Terms, with only 5 clauses and commercials outstanding. The Applicant met with the Landowners agent on 10 April 2026 to discuss the Heads of Terms and finished the meeting with agreed commercials and only 2 clauses to be agreed in the Heads of Terms. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to engage with the landowner and their agent. Since Deadline 1, the Applicant has continued work towards resolving the final material clause of the voluntary agreement and most recently emailed the landowner's agent on 19 May 2026. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant continues to engage with the landowner and their agent. Since Deadline 2, the Applicant has continued to work towards resolving the final material clauses of the voluntary agreement. The Applicant most recently emailed the landowner's agent on 11 June 2026 with updated Heads of Terms. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement. |  | RR-2342 - John Baillie
72901, 72902 | John Eavis, Rosemarie Margaret Eavis | Keith Thomas & Richard Fearnall | Cat 1 - Owner | 05-043, 06-003, 06-004, 06-005, 06-006 | 5, 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5B, 8A, 8B - 132 kV cabling, Temporary access, Permanent access | Open |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 11 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent, issuing updated Heads of Terms on 21 October 2025. The Applicant met with the landowner on 17 November 2025 and 8 December 2025 to discuss the Heads of Terms and is currently awaiting feedback from the landowner and the agent. The Applicant will continue to offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner and their agents. The Applicant's agent met with the landowners agent on 1 April 2026 to discuss the Heads of Terms. Based on feedback, additional detail was provided by the Applicant on 20 April 2026. Feedback and comments on the Heads of Terms were received back to the Applicant's agent on 23 April 2026. A follow up meeting is scheduled for 5 May 2026, and the Applicant will continue to engage with the landowner via their agents in order to move negotiations forward towards a voluntary agreement. Deadline 2 The Applicant met with the landowner's agent on 5 May 2026 and is currently reviewing feedback subsequently received on the Heads of Terms. The Applicant will continue to engage with the landowner and their agent as is confident the necessary land rights can be aquired by voluntary agreement. Deadline 3 The Applicant is continuing to engage with the landowner's agent in relation to the Heads of Terms. A meeting is scheduled for 19 June 2026 between the Applicant and the landowner's agent to address the feedback received from the latest version of the Heads of Terms so as to progress negotiations. |  | RR-1963 - J Eavis RR-2358 - John Eavis
258283 | John Edward Branston |  | Cat 1 - Owner | 04-055, 04-056, 04-057, 04-058, 04-059, 04-060, 04-061, 05-001, 05-002, 05-003, 05-004, 05-005, 05-009, 05-010, 05-011, 05-012, 05-013, 05-014, 05-015, 05-016, 05-017, 05-018, 05-019, 05-020, 05-023, 05-024, 05-025 | 4, 5 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1D, 5A, 5B, 6, 1, 2, 10A, 7, 9 - Solar PV cabling, 400 kV cable corridor, 132kV cabling, General works, Solar PV area, BESS, Permissive path for pedestrians, Solar PV temporary construction compound, Habitat management area | n/a |  |  | Option Holder Following initial engagement, the Parties then worked together to agree an option agreement which was entered into on 9 November 2022 and varied on 9 October 2024 and again on 6 August 2025 for the use of the land as part of the Scheme.
|  |  |  | 04-025, 04-026, 04-027, 04-030, 04-034, 04-037 | 4 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 5B - 400kV cable corridor, 132 kV cabling
258260, 258311, 302278 | John Hart Richards, Sean Norman Richards, Patricia Richards |  | Cat 1 - Owner | 01-001, 01-002, 01-003, 01-004, 01-012, 01-013, 01-014, 01-015, 01-016, 01-017, 01-018, 01-019, 01-021, 01-022, 01-023, 01-024, 01-025, 01-027, 01-028, 01-029, 01-030, 01-031, 01-032, 01-033, 01-034, 01-035, 01-036, 01-037, 01-041, 01-042, 01-043, 01-045, 03-001, 03-002, 03-003, 03-004, 03-005, 03-006, 03-007, 03-008, 03-010, 03-012, 03-013, 04-002, 04-003 | 1, 3, 4 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 9, 10B, 1D, 6, 1, 3B, 5B, 7 - Habitat management area, Permissive paths for pedestrian and equestrian users, Solar PV cabling, General works, Solar PV area, 132 kV substation, 132 kV cabling, Solar PV temporary construction compound | n/a |  |  | Option Holder Following initial engagement, the Applicant negotiated Heads of Terms, which were agreed on 17 May 2022. The Parties then worked together to agree an option agreement which was entered into on 26 July 2023 and varied on 13 December 2024 for the use of the land as part of the Scheme.
|  |  |  | 01-020, 01-038, 01-039, 01-046, 01-053, 03-009, 03-050 | 1, 3 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1D, 5B, 6, 8B - Solar PV cabling, 132 kV cabling, General works, Permanent access
258261 | Jonathan William Walker | Grace Gardiner | Cat 1 - Owner | 03-045, 03-046, 03-047, 03-053, 04-004, 04-005, 04-006, 04-007, 04-016, 04-020, 04-021, 04-022 | 3, 4 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1D, 5B, 6, 1, 5A - Solar PV cabling, 132 kV cabling, General works, Solar PV area, 400 kV cable corridor | n/a |  |  | Option Holder Following initial engagement, the Applicant negotiated Heads of Terms, which were agreed on 16 October 2022. The Parties then worked together to agree an option agreement which was entered into on 4 April 2023 and varied on 20 January 2025 for the use of the land as part of the Scheme.
|  |  |  | 03-052, 03-054, 03-055, 03-061, 04-008, 04-009, 04-023, 09-017, 09-021, 10-003 | 3, 4, 9, 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1D, 5B, 6, 7, 5A, 5A(v) - Solar PV cabling, 132 kV cabling, General works, Solar PV temporary construction compound, 400 kV cable corridor, Cable corridor temporary construction compound |  |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent, meeting on 25 September 2025 to discuss the Heads of Terms. The Applicant issued updated Heads of Terms on 21 October 2025 and met with the agent on 18 December 2025 and 15 January 2026 to discuss the Heads of Terms. The Applicant will continue to offer meetings and remains confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner and their agent. Since Procedural Deadline A, The Applicant met with the landowner’s agent on 9 March 2026 to discuss the Heads of Terms. On 13 March 2026 the Applicant received an email from the landowner’s agent and understood revised Heads of Terms would be agreeable for signing. On 8 April 2026, the Applicant was advised by the landowner’s agent that their client would not be signing revised Heads of Terms. The Applicant reissued revised Heads of Terms on 9 April 2026 and as of 16 April 2026 the Applicant is awaiting feedback from the landowner and their agent. Deadline 2 The Applicant continues to seek to engage with the landowner and their agent, most recently requesting feedback on the 19 May 2026. The Applicant is still awaiting feedback from the landowner and their agent. Deadline 3 The Applicant received an email from the landowner's agent on 4 June 2026 advising the revised Heads of Terms would be agreeable. The Applicant reissued Heads of Terms to the landowner for signing on 5 June 2026 and is confident the necessary land rights can be acquired by voluntary agreement.
284069, 313382 | Julian Philip Edwin Brunt, Katherine Ruth Brunt |  | Cat 1 - Owner | 09-003 | 9 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A - Temporary access | Open |  |  | Negotiations for temporary possession The Applicant intends to negotiate a temporary licence agreement for the temporary access rights prior to commencement of works post consent. The Applicant is endeavouring to progress negotiations with the landowner on this approach owing to the temporary use and has offered meetings to discuss the rights required. Procedural Deadline A The Applicant is seeking to negotiate a temporary licence agreement for the temporary access rights prior to commencement of works post consent. The Applicant is confident the temporary access rights can be agreed voluntarily. Deadline 1 The Applicant engaged with the landowner to confirm a meeting will be arranged once the appropiate information is established, and intends to negotiate a temporary license agreement for temporary access rights prior to the commencement of works post consent. Temporary access will be required for the three years of construction. The Applicant is confident the temporary access rights can be agreed voluntarily. Deadline 2 The Applicant is seeking to negotiate a temporary licence agreement for temporary access rights prior to commencement of works post consent. Temporary access will be required for the three years of construction. The Applicant is confident the temporary access rights can be agreed voluntarily. Deadline 3 The Applicant is seeking to negotiate a temporary licence agreement for temporary access rights prior to commencement of works post consent. Temporary access will be required for the three years of construction. The Applicant is confident the temporary access rights can be agreed voluntarily. |  | RR-2517 - Julian Philip Edwin Brunt RR-2611 - Katherine Ruth Brunt
289118, 333598 | Matthew Newman, Alexandra Louise Newman | George Tiley | Cat 1 - Owner | 08-006 | 8 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | Open |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent. The Applicant met with the landowner’s their agent on the 8 October 2025. The Applicant wrote to the landowner on 2 December 2025, and most recently sent an email to the agent on 10 February 2026 and is currently awaiting further feedback from the landowner and their agent. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner’s professional representative. Since Procedural Deadline A, the Applicant has distributed clarification requests on 2 April 2026 to which a response has not been received. The Applicant remains committed to engaging with the landowner and their agent to progress a voluntary agreement however it cannot seek to progress a voluntary agreement in the absence of receiving substantive consistent feedback from the landowner and their agent. Deadline 2 The Applicant continues to engage with the landowners agent. Since Deadline 1, the Applicant has not yet recieved material comments on the voluntary agreementes from the landowners agent. The Applicant remains committed to engaging with the landowner and their agent to progress a voluntary agreement to secure the necessary land rights. Deadline 3 The Applicant continues to engage with the landowner's agent. Since Deadline 2, the Applicant has responded to the landowner's agents questions on 12 June 2026 relating to compensation provisions. The Applicant remains committed to engaging with the landowner and their agent to progress a voluntary agreement to secure the necessary land rights. |  | RR-3090 - Matthew Gerard Newman
284625 | Michael Badeni |  | Cat 1 - Owner | 01-054, 01-055 | 1 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5B, 8A, 7 - 132 kV cabling, Temporary access, Solar PV temporary construction compound | n/a |  |  | Option Holder Following initial engagement, the Applicant negotiated Heads of Terms, which were agreed on 26 May 2023. The Parties then worked together to agree an option agreement which was signed by both parties on 26 July 2023 and varied on 2 September 2025 for the use of the land as part of the Scheme.
258292 | Miriam Anne Stone |  | Cat 1 - Owner | 04-024 | 4 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 5B - 400kV cable corridor, 132 kV cabling | n/a |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant received signed Heads of Terms from the landowner on 5 December 2025. The Applicant has engaged with the landowner to establish their legal representation in order to progress an option agreement and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner, and wrote to them on the 23 January 2026. The Applicant has offered a meeting to the landowner and will continue to do so in order to move matters forward. Deadline 2 Since Deadline 1, The Applicant has not recieved any further from the landowner. The Applicant remains committed to engage with the landowner throughout Examination to progress a voluntary agreement. Deadline 3 Since Deadline 2, The Applicant has not recieved any further communication from the landowner. The Applicant remains committed to engage with the landowner throughout Examination to progress a voluntary agreement.
22381 | National Grid Electricity Transmission PLC | Tom Price | Cat 1 - Owner | 16-014, 16-016, 16-019 | 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 5A(v), 8A - 400 kV cable corridor, Cable corridor temporary construction compound, Temporary access, | Open |  |  | Negotiations for rights The Applicant met with NGET's representative on 1 July 2025 to understand NGET's six-stage process for acquiring land rights. The Applicant has submitted the Developer Enquiry Form with a view to proceeding to stage two prior to acceptance of the application. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent and is following the landowners process for acquiring land rights by voluntary agreement and is now at stage two. The Applicant remains confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 Since Procedural Deadline A, the Applicant has met with the landowner’s agent on the 27th April 2026 and is continuing to follow the landowners process for acquiring rights by voluntary agreement. The applicant remains confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 Since Deadline 1, The Applicant has continued to follow the landowners process for acquiring rights by voluntary agreement. The Applicant will continue to negotiate with the landowner and remains confident the necessary land rights can be acquired by voluntary agreement. |  | RR-3425 - National Grid Electricity Transmission Plc
|  |  |  | 16-017 | 16 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A - Temporary access
|  |  |  | 16-020 | 16 | As described in the Book of Reference | Land is subject to No Rights Sought | 4 - National Grid substation connection
278704 | National Highways Limited |  | Cat 1 - Owner | 09-018, 09-019, 09-020, 13-009 | 9 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | Open |  |  | Negotiations for rights The Applicant has commenced technical discussions with National Highways in respect of the strategic road network crossing. The Applicant is endeavouring to progress negotiations to acquire to necessary land rights. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner regarding the most appropriate method for acquiring land rights by voluntary agreement. The Applicant remains confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner regarding the most appropriate method for acquiring land rights by voluntary agreement. The Applicant held a meeting with National Highways and their representatives on 18 March 2026. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to engage with the landowner regarding the most appropriate method for acquiring land rights by voluntary agreement. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant continues to engage with the landowner regarding the most appropriate method for acquiring land rights by voluntary agreement. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement. |  | RR-3426 - National Highways
|  |  |  | 13-006, 13-013, 13-014, 13-016, 20-001, 20-002, 21-003, 21-006, 21-007 | 20, 21 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A - Temporary access
7310 | Network Rail Infrastructure Limited |  | Cat 1 - Owner | 03-051, 03-056, 03-057, 03-058, 03-066, 03-069, 03-070, 03-076, 04-017, 04-018, 04-032, 04-035, 05-037, 06-025, 06-026, 06-029, 14-009, 14-011, 14-012, 14-013, 14-014, 14-033, 14-040, 14-043 | 3, 4, 5, 6, 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5B, 1D, 5A, 8B - 132 kV cabling, Solar PV cabling, 400 kV cable corridor, Permanent access | n/a |  |  | Negotiations for rights The Applicant has commenced engagement and held technical discussions with Network Rail in respect of the strategic rail network crossing. The Applicant is endeavouring to progress negotiations to acquire the necessary land rights. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner regarding the most appropriate method for acquiring land rights by voluntary agreement. The Applicant remains confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner regarding the most appropriate method for acquiring land rights by voluntary agreement. The Applicant remains confident the necessary land rights can be acquired by voluntary agreement.
278663 | Peter Anthony Simon Stainer |  | Cat 1 - Owner | 10-007 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | n/a |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant issued updated Heads of Terms on 21 October 2025 and wrote to the landowner 2 December 2025. The Applicant is currently awaiting feedback on the Heads of Terms. The Applicant will continue to offer meetings and is confident the necessary land rights can be acquired by voluntary agreement.
266496, 266497 | Peter James Phillips, Anne Marie Phillips | George King | Cat 1 - Owner | 16-003 | 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | n/a |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent. The Applicant met with the landowner and their agent on the 19 September 2025 and followed up with a meeting with their agent on 9 October 2025 to discuss the Heads of Terms. The Applicant issued updated Heads of Terms on 21 October 2025. The Applicant wrote to the landowner on 2 December 2025 and most recently sent an email to the agent on 3 February 2026. The Applicant is currently awaiting further feedback from the landowner and their agent. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner and their agent. Since Procedural Deadline A, The Applicant wrote to the agent on 9 March 2026 with amended Heads of Terms, with the Landowners agent responding with requested changes. On the 23 March 2026 The Applicant responded with amended Heads of Terms, with only 5 clauses and commercials outstanding. The Applicant met with the Landowners agent on 10 April 2026 to discuss the Heads of Terms and finished the meeting with agreed commercials and only 2 clauses to be agreed in the Heads of Terms. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to engage with the landowner and their agent. Since Deadline 1, the Applicant has continued work towards resolving the final material clause of the voluntary agreement and most recently had a call with the landowner's agent on 19 May 2026. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The applicant continues to engage with the landowner and their agent, Since Deadline 2, The Applicant has continued to work towards resolving the final material cluasesof the voluntary agreement. The Applicant most recently emailed the landowner's agent on 11 June 2026 with updated Heads of Terms. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement.
278646 | Richard Charles Tanner | Arthur Chambers | Cat 1 - Owner | 10-004 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | Open |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent. The Applicant met with the landowner’s their agent on the 8 October 2025. The Applicant wrote to the landowner on 2 December 2025, and most recently sent an email to the agent on 12 February 2026 and is currently awaiting further feedback from the landowner and their agent. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the Landowner and their agent and most recently had a meeting with their agent on 10 April 2026 to discuss the final clauses outstanding within the voluntary agreement. Upon completion of the meeting, there are only two outstanding clauses to be agreed. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to engage with the landowner and their agent. Since Deadline 1, the Applicant has continued work towards resolving the final material clause of the voluntary agreement and most recently emailed the landowner's agent on 19 May 2026. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The applicant continues to engage with the landowner and their agent, Since Deadline 2, The Applicant has continued to work towards resolving the final material cluasesof the voluntary agreement. The Applicant most recently emailed the landowner's agent on 11 June 2026 with updated Heads of Terms. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement. |  | RR-3970 - Richard Tanner
258284 | Richard William Corbet Turnor | Guy Banham | Cat 1 - Owner | 02-004, 02-007, 02-008, 02-009, 02-011, 02-012, 02-013, 02-014 | 2 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 10B, 1D, 5B, 6 - Permissive paths for pedestrian and equestrian users, Solar PV cabling, 132 kV cabling, General works | n/a |  |  | Option Holder Following initial engagement, the Parties then worked together to agree an option agreement which was entered into on 24 February 2023 and varied on 22 January 2025 for the use of the land as part of the Scheme.
258284, 258285, 258286 | Richard William Corbet Turnor, Louisa Mary Turnor, William Michael Francis Turnor | Guy Banham | Cat 1 - Owner | 02-003, 02-005, 02-006, 02-015, 02-016, 02-017, 02-018, 02-019, 02-020, 02-021, 02-022, 02-023 | 2 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 10B, 1D, 5B, 6, 1, 9 - Permissive paths for pedestrian and equestrian users, Solar PV cabling, 132 kV cabling, General works, Solar PV area, Habitat management area | n/a |  |  | Option Holder Following initial engagement, the Parties then worked together to agree an option agreement which was entered into on 24 February 2023 and varied on 22 January 2025 for the use of the land as part of the Scheme.
278821 | Robert James Payne | Arthur Chambers | Cat 1 - Owner | 09-015 | 9 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | n/a |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner and their agent. The Applicant met with the landowner’s agent on the 8 October 2025. The Applicant wrote to the landowner on 2 December 2025, and most recently sent an email to the agent on 12 February 2026 and is currently awaiting further feedback from the landowner and their agent. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the Landowner and their agent and most recently had a meeting with their agent on 10 April 2026 to discuss the final clauses outstanding within the voluntary agreement. Upon completion of the meeting, there are only two oustanding clauses to be agreed. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to engage with the landowner and their agent. Since Deadline 1, the Applicant has continued work towards resolving the final material clause of the voluntary agreement and most recently emailed the landowner's agent on 19 May 2026. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant continues to engage with the landowner and their agent. Since Deadline 2, the Applicant has continued to work towards resolving the final material clauses of the voluntary agreement. The Applicant most recently emailed the landowner's agent on 11 June 2026 with updated Heads of Terms. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement.
258264 | Sarah Peta Badeni |  | Cat 1 - Owner | 01-054, 01-055 | 1 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5B, 8A, 7 - 132 kV cabling, Temporary access, Solar PV temporary construction compound | n/a |  |  | Option Holder Following initial engagement, the Applicant negotiated Heads of Terms, which were agreed on 26 May 2023. The Parties then worked together to agree an option agreement which was signed by both parties on 26 July 2023 and varied on 2 September 2025 for the use of the land as part of the Scheme.
|  |  |  | 01-056 | 1 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5B - 132 kV cabling |  |  |  | Negotiations for rights The Applicant will continue to engage with the landowner to acquire the necessary land rights by voluntary agreement. Procedural Deadline A The Applicant continues to engage with the landowner to acquire land rights by voluntary agreement and notes parcel 01-056 forms part of land potentially required for interconnecting cable routing.
258264, 284625 | Sarah Peta Badeni, Michael Badeni |  | Cat 1 - Owner | 02-001 | 2 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5B, 8A - 132 kV cabling, Temporary access | n/a |  |  | Option Holder Following initial engagement, the Applicant negotiated Heads of Terms, which were agreed on 26 May 2023. The Parties then worked together to agree an option agreement which was signed by both parties on 26 July 2023 and varied on 2 September 2025 for the use of the land as part of the Scheme.
258272 | Simon Laurence Grafftey-Smith |  | Cat 1 - Owner | 06-007, 06-008, 06-009, 06-010, 06-011, 06-012, 06-013, 06-020, 06-022, 06-023, 06-033, 06-034, 06-035, 06-036, 06-037, 07-001, 07-002, 07-003, 07-004, 07-005, 07-006, 07-007, 07-008, 07-009, 07-010, 07-011, 07-012, 07-013, 07-014, 07-015, 07-016, 07-017, 07-018, 07-019, 07-020, 07-021, 07-023, 07-024, 07-025, 07-026, 07-027, 07-028, 07-030, 07-031, 07-032, 07-036, 07-037, 07-038, 07-039, 07-040, 07-041, 07-042, 07-043, 07-044, 07-045 | 6, 7 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1D, 5B, 6, 1, 3B, 7, 10B, 10A, 8B - Solar PV cabling, 132 kV cabling, General works, Solar PV area, 132 kV substation, Solar PV temporary construction compound, Permissive paths for pedestrian and equestrian users, Permissive path for pedestrians, Permanent access | n/a |  |  | Option Holder Following initial engagement, the Applicant negotiated Heads of Terms, which were agreed on 18 November 2022. The Parties then worked together to agree an option agreement which was entered into on 21 February 2023 and varied on 9 October 2024 for the use of the land as part of the Scheme.
|  |  |  | 06-018, 06-019, 06-038, 06-039, 07-022, 07-029, 07-033 | 6, 7 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1D, 8B, 6 - Solar PV cabling, Permanent access, General works
324992, 324995 | Stephen Challis, John Brewster, Lindsay Minty, Roderick Pottow, Elizabeth J Waldron, Hannah C Minty, Jason P W Minty, Rachel White, The Executor of the Estate of the Late Ronald J Doherty | Raph Butt | Cat 1 - Owner | 10-013 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | Open |  |  | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 9 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant issued updated Heads of Terms on 21 October 2025 and met with the agent to discuss the Heads of Terms. The Applicant continues to engage with the landowner and met with the agent on 5 February 2026. The Applicant is confident the necessary rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner, and is confident that the necessary land rights can be acquired voluntarily. The Applicant has had extensive dialogue with the landowners agent in relation to the Heads of Terms. The Applicant's agent held meetings with the landowners agent on the 5 February and 19 March 2026, with finalised Heads of Terms being sent by the Applicant on 14 April 2026. Deadline 2 The Applicant continues to engage with the landowner and their agent. The Applicant has continued to negotiate with the landowner's agent on the Heads of Terms which are now at an advanced stage. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant continues to engage with the landowners agent, and the Heads of Terms are at an advanced stage. The Applicant is not aware of any outstanding clauses to negotiate, and so will continue to engage with the landowner's agent to secure a signed voluntary agreement. |  | RR-3301 - Mr Stephen Challis
311286, 311287 | Stephen Wardle, Gillian Wardle, Charlotte Tucker | George King | Cat 1 - Owner | 13-003 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | n/a |  |  | Negotiations for rights The Applicant understands there has been a change of ownership and is undertaking further due diligence before issuing populated Heads of Terms. Procedural Deadline A The Applicant met with the landowner and their agent on the 10 September 2025 and followed up with a meeting with their agent on 9 October 2025 to discuss the Heads of Terms. The Applicant issued populated Heads of Terms to the landowner on 21 October 2025. The Applicant wrote to the landowner on 2 December 2025 and most recently sent an email to the agent on 3 February 2026. The Applicant is currently awaiting further feedback from the landowner and their agent. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 1 The Applicant continues to engage with the landowner and their agent. Since Procedural Deadline A, The Applicant wrote to the agent on 9 March 2026 with amended Heads of Terms, to which the Landowners agent responded with requested changes. Following this, on the 23 March 2026 The Applicant responded with further amended Heads of Terms, with only 5 clauses and commercials outstanding. The Applicant met with the Landowners agent on 10 April 2026 to discuss the Heads of Terms and finished the meeting with agreed commercials and only 2 clauses to be agreed in the Heads of Terms. The Applicant will continue to engage and offer meetings and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to engage with the landowner and their agent. Since Deadline 1, the Applicant has continued work towards resolving the final material clause of the voluntary agreement and most recently had a call with the landowner's agent on 19 May 2026. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant continues to engage with the landowner and their agent. Since Deadline 2, the Applicant has continued to work towards resolving the final material clauses of the voluntary agreement. The Applicant most recently emailed the landowner's agent on 11 June 2026 with updated Heads of Terms. The Applicant will continue to engage with the landowner and their agent and is confident the necessary land rights can be acquired by voluntary agreement.
278625 | Templeville Limited |  | Cat 1 - Owner | 15-007 | 15 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A - Temporary access | n/a |  |  | Negotiations for temporary possession The Applicant intends to negotiate a temporary licence agreement for the temporary access rights prior to commencement of works post consent. The Applicant is endeavouring to progress negotiations with the landowner on this approach owing to the temporary use and has offered meetings to discuss the rights required. Procedural Deadline A The Applicant is seeking to negotiate a temporary licence agreement for the temporary access rights prior to commencement of works post consent. The Applicant is confident the temporary access rights can be agreed voluntarily. Deadline 1 The Applicant is seeking to negotiate a temporary licence agreement for temporary access rights prior to commencement of works post consent. Temporary access will be required for the three years of construction. The Applicant is confident the temporary access rights can be agreed voluntarily. Deadline 2 The Applicant is seeking to negotiate a temporary licence agreement for temporary access rights prior to commencement of works post consent. Temporary access will be required for the three years of construction. The Applicant is confident the temporary access rights can be agreed voluntarily. Deadline 3 The Applicant is seeking to negotiate a temporary licence agreement for temporary access rights prior to commencement of works post consent. Temporary access will be required for the three years of construction. The Applicant is confident the temporary access rights can be agreed voluntarily.
333344 | The Executor of the Estate of the Late Julian Richard Whately |  | Cat 1 - Owner | 03-014, 03-015, 03-016, 03-017, 03-018, 03-019, 03-020, 03-021, 03-022, 03-023, 03-024, 03-025, 03-026, 03-027, 03-028, 03-029, 03-030, 03-031, 03-032, 03-033, 03-034, 03-035, 03-036, 03-037, 03-038, 03-039, 03-040, 03-041, 03-042, 03-067, 03-068, 03-078 | 3 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1D, 6, 9, 10B, 5B - Solar PV area, Solar PV cabling, General works, Habitat management area, Permissive paths for pedestrian and equestrian users, 132 kV cabling | n/a |  |  | Option Holder Following initial engagement, the Applicant negotiated Heads of Terms, which were agreed on 22 December 2022. The Parties then worked together to agree an option agreement which was entered int on 21 July 2023 and varied on 28 July 2025 for the use of the land as part of the Scheme.
311076, 311077 | The Executor Of The Estate Of The Late Rex Charles Smith, The Executor Of The Estate Of The Late Sheila Ann Smith |  | Cat 1 - Owner | 04-033, 04-038 | 4 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 5B - 400kV cable corridor, 132 kV cabling | n/a |  |  | Option Holder Following initial engagement, the Applicant negotiated Heads of Terms, which were agreed on 4 March 2024. The Parties then worked together to agree an option agreement which was signed entered into on 8 August 2025 for the use of the land as part of the Scheme.
325138, 325140, 337812 | Thomas Lynch, Michael Cavalla, Jeremy Green, Manda Lisa Justine Green | Arthur Chambers | Cat 1 - Owner | 10-006 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | n/a |  |  | Negotiations for rights The Applicant understands the land was previously in probate and has now been sold. The Applicant is engaging with the prospective purchaser and undertaking further due diligence before issuing populated Heads of Terms. Procedural Deadline A The Applicant continues to engage with the landowner, meeting on 12 December 2025. The Applicant understands the landowner has since appointed an agent and will continue to offer meetings to discuss the Heads of Terms. The Applicant is confident the necessary rights can be acquired by voluntary agreement. Deadline 1 The Applicant is seeking to receive confirmation from an agent that they are appointed by the landowner to represent their interests in regards to the Project. The Applicant received notification from the agent on 11 February 2026 and has since requested written confirmation from the agent on the 25 February 2026, 11 March 2026 and 26 March 2026 respectively. The Applicant remains committed to engaging with the landowner and their agent to progress a voluntary agreement to secure the necessary lands rights. Deadline 2 Since Deadline 1, the Applicant has received notification that the landowner has sold the land that the Applicant is seeking an interest in. The Applicant has since requested confirmation evidence from the landowner. Deadline 3 Since Deadline 2, the Applicant has continued to ascertain the relevant evidence from the landowner confirming the sale of the land. The latest engagement was distributed on 15 June 2026.
258477, 258479 | Timothy James Butler, Reginald Mark Butler |  | Cat 1 - Owner | 05-021, 05-022, 05-026, 05-027, 05-028, 05-029, 05-030, 05-031, 05-032, 05-040, 05-041 | 5 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1D, 5B, 6, 9, 10A, 1, 7 - Solar PV cabling, 132 kV cabling, General works, Habitat management area, Permissive path for pedestrians, Solar PV area, Solar PV temporary construction compound | n/a |  |  | Option Holder Following initial engagement, the Parties then worked together to agree an option agreement which was entered into on 20 December 20222 and varied on 9 October 2024 for the use of the land as part of the Scheme.
|  |  |  | 05-034, 05-036 | 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1D, 5B, 8B, - Solar PV cabling, 132 kV cabling, Permanent access
349831 | Angus George Archibald Methuen-Campbell | Tom French | Cat 1 - Owner | 12-001, 12-002, 12-003, 12-004, 12-005, 12-006, 12-007, 12-011, 12-012, 12-013, 12-014, 13-017, 13-018a, 13-019, 13-020, 13-021, 13-022, 13-023, 13-025, 13-037, 14-001, 14-002, 14-003, 14-004, 14-005, 14-005a, 14-007a, 14-013, 14-018, 14-019, 14-020, 14-021, 14-022, 14-023, 14-026, 14-028, 14-035, 14-036 14-038, 14-042, 14-044, 14-045, 14-046, 14-047, 14-048 | 12, 13,14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | n/a |  |  | Deadline 1 The Applicant continues to engage with the landowner and their agent. Since Procedural Deadline A, the Applicant has revised the commercial position offered. On the 25 February 2026, the Applicant provided a revised commercial proposal to the landowner via their agent based on feedback on the Heads of Terms gathered in the meeting on 3 February 2026. This revised proposal was rejected by the agent on 18 March, citing concerns, however no further tangible detail has been put forward since that date. The Applicant will continue to engage with the landowner via the agent in order to progress matters and reach a voluntary agreement. Deadline 2 The Applicant is still awaiting tangible detail from the landowner's agent regarding the commercial position offered. Deadline 3 The Applicant is still awaiting tangible detail from the landowner's agent regarding the commercial position offered, and feedback surrounding the wider terms within the document.
278877 | Samuel Charles Creed |  | Cat 1 - Owner | 14-015a | 14 |  | Temp |  |  |  |  | Deadline 1 The Applicant is seeking to negotiate a temporary licence agreement for temporary access rights prior to commencement of works post consent. Temporary access will be required for the three years of construction. The Applicant is confident the temporary access rights can be agreed voluntarily. Deadline 2 The Applicant is seeking to negotiate a temporary licence agreement for temporary access rights prior to commencement of works post consent. Temporary access will be required for the three years of construction. The Applicant is confident the temporary access rights can be agreed voluntarily. Deadline 3 The Applicant is seeking to negotiate a temporary licence agreement for temporary access rights prior to commencement of works post consent. Temporary access will be required for the three years of construction. The Applicant is confident the temporary access rights can be agreed voluntarily.
54925 | Wessex Water Services Limited | Nick Routh | Cat 1 - Owner | 14-049 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | n/a |  |  | Negotiations for rights The Applicant met with Wessex Water Services on 11 August 2025 prior to issuing populated Heads of Terms on 8 September 2025. The Applicant will continue to engage with the landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline A The Applicant issued updated Heads of Terms on 21 October 2025 and met with the landowner on 10 November 2025 and 5 February 2026 to discuss the Heads of Terms. The Applicant continues to engage with the landowner and is currently awaiting feedback on the Heads of Terms. Deadline 1 The Applicant continues to engage with the landowner to discuss the Heads of Terms. The Applicant is currently awaiting feedback on the Heads of Terms from the landowners agent. Deadline 2 The Applicant continues to engage with the landowner to discuss the Heads of Terms. Since Deadline 1, the Applicant has requested a copy of the landowner's standard Heads of Terms document and is currently awaiting feedback. The Applicant will continue to offer meetings to discuss the Heads of Terms and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant requested the landowner to provide a copy of their standard Heads of Terms on 28 May 2026 and 5 June 2026. The Applicant is currently awaiting feedback and will continue to offer meetings to discuss the Heads of Terms and is confident the necessary land rights can be acquired by voluntary agreement.

## Part 2 - SU Crown
PART 2
Ref | Affected Party | Agent/ Representative | BoR Category and Interest | Book of Ref. Plot No. | Plan Ref. No. | Description of Land | Description of Rights Requested | Works Number(s) and Description | Interest Type | Is the relevant body a Statutory Undertaker and is the land operational? | Status of Objection | Notes | Last Updated | Summary of Negotiations | Protective Provision Status | Side Agreements Status | Complete | Relevant Rep Ref No. | Written Rep Ref No. | Ref No. for any other docs submitted by IP/AP. | Ref No. for Applicant's Response
335506 | C.A. Telecom UK Limited |  | Cat 2 | 20-002, 20-003 | 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A - Temporary access | Apparatus | Yes | n/a |  |  | n/a | Operators of electronic communications code networks will have the benefit of the protective provisions set out in Part 2 of Schedule 15 of the draft DCO. C.A. Telecom UK Limited has not requested bespoke protective provisions.
335507 | CityFibre Holdings Limited |  | Cat 2 | 20-002, 20-003 | 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A - Temporary access | Apparatus | Yes | n/a |  |  | n/a | Operators of electronic communications code networks will have the benefit of the protective provisions set out in Part 2 of Schedule 15 of the draft DCO. CityFibre Holdings Limited has not requested bespoke protective provisions.
108711 | EE Limited |  | Cat 2 | 03-014, 03-015, 03-016, 03-017, 03-018, 03-019, 03-020, 03-021, 03-022, 03-023, 03-024, 03-025, 03-026, 03-027, 03-028, 03-029, 03-030, 03-031, 03-032, 03-033, 03-034, 03-035, 03-036, 03-037, 03-038, 03-039, 03-040, 03-041, 03-042, 03-067, 03-068, 03-078 | 3 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1D, 6, 1, 9, 10B, 5B, 3B - Solar PV cabling, General works, Solar PV area, Habitat management area, Permissive paths for pedestrians and equestrian users, 132 kV cabling, 132 kV substation | Rights | Yes | n/a |  |  | n/a | Operators of electronic communications code networks will have the benefit of the protective provisions set out in Part 2 of Schedule 15 of the draft DCO. EE Limited has not requested bespoke protective provisions.
|  |  |  | 03-029 | 3 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1D, 5B, 6 - Solar PV cabling, 132 kV cabling, General works | Leaseholder
|  |  |  | 14-032, 14-043, 14-044, 14-045 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 8A - 400 kV cable corridor, Temporary access | Rights
288888 | EXA Infrastructure Limited |  | Cat 2 | 13-008, 13-010 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 8A - 400 kV cable corridor, Temporary access | Apparatus | Yes | n/a |  |  | n/a | Operators of electronic communications code networks will have the benefit of the protective provisions set out in Part 2 of Schedule 15 of the draft DCO. EXA Infrastructure Limited has not requested bespoke protective provisions.
|  |  |  | 13-004, 13-005, 13-007, 13-011, 13-012, 13-014, 13-015, 22-001, 22-002 | 13, 22 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A - Temporary access | Apparatus
192726 | Exolum Pipeline System Ltd | Maddy Ward | Cat 2 | 11-011 | 11 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | Apparatus | Yes | n/a |  |  | Technical discussions have taken place with Exolum. | Draft protective provisions for the benefit of Exolum are included in Part 8 of Schedule 15 of the draft DCO. Procedural Deadline A Discussions are ongoing between Exolum and the Applicant regarding the form of the Protective Provisions. Deadline 1 Discussions are ongoing with Exolum regarding the form of the Protective Provisions. Deadline 2 Exolum's solicitors have provided Exolum's standard protective provisions which the Applicant is reviewing and will provide justification as to any amendments required. Deadline 3 Negotiations in respect of the form of protective provisions required by Exolum are ongoing and the Applicant's solicitors provided comments on the most recent draft in circulation on 12 June 2026.
105595 | Gigaclear Limited |  | Cat 2 | 06-001, 06-002, 09-007, 10-009, 10-012, 11-010, 12-007, 12-016, 14-015, 14-016, 14-024, 14-031, 14-032, 14-033, 14-037, 14-039, 14-040, 14-043, 16-002a, 16-014, 16-016, 16-018 | 6, 9, 10, 11, 12, 14, 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5B, 8B, 5A, 8A - 132 kV cabling, Permanent access, 400 kV cable corridor, Temporary access | Apparatus | Yes | n/a |  |  | n/a | Operators of electronic communications code networks will have the benefit of the protective provisions set out in Part 2 of Schedule 15 of the draft DCO. Gigaclear Limited has not requested bespoke protective provisions.
|  |  |  | 09-001, 09-004, 09-006, 09-008, 10-008, 10-010, 11-006, 11-008, 11-020, 12-008, 12-015, 12-017, 12-019, 17-001, 17-002, 17-003, 17-004, 23-001, 23-002, 23-003 | 9, 10, 11, 12, 17, 23 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A, 5A(v) - Temporary access, Cable corridor temporary construction compound | Apparatus
7290 | Hutchison 3G UK Limited |  | Cat 2 | 14-032, 14-044, 14-045 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 8A - 400 kV cable corridor, Temporary access | Rights | Yes | n/a |  |  | n/a | Operators of electronic communications code networks will have the benefit of the protective provisions set out in Part 2 of Schedule 15 of the draft DCO. Hutchinson 3G UK Limited has not requested bespoke protective provisions.
333276 | Lumen Technologies UK Limited |  | Cat 2 | 03-078 | 3 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 6 - General works | Apparatus | Yes | n/a |  |  | n/a | Operators of electronic communications code networks will have the benefit of the protective provisions set out in Part 2 of Schedule 15 of the draft DCO. Lumen Technologies UK Limited has not requested bespoke protective provisions.
|  |  |  | 03-051, 03-058, 03-066, 03-069, 03-070, 03-076, 04-018, 04-019, 04-035, 06-021, 06-026, 06-027, 06-029, 06-030 | 3, 4, 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5B, 1D, 8B, 5A - 132 kV cabling, Solar PV cabling, Permanent access, 400 kV cabling | Apparatus
263873 | Melksham East Storage Limited |  | Cat 2 | 16-011, 16-012, 16-013, 16-014, 16-015, 16-016, 16-017, 16-019 | 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 5A(v), 8A - 400 kV cable corridor, Cable corridor temporary construction compound, Temporary access | Rights | Yes | n/a |  |  | n/a | Holders of an Electricity Act 1989 licence will have the benefit of the protective provisions set out in Part 1 of Schedule 2. Melksham Storage Limited has not requested bespoke protective provisions.
|  |  |  | 16-020 | 16 | As described in the Book of Reference | Land is subject to No Rights Sought | 4 - National Grid substation connection | Rights
86149 | National Gas Transmission PLC | Daniel Goulding | Cat 2 | 01-042, 01-045, 02-003, 02-005, 02-016, 03-001, 03-006, 03-014, 03-023, 03-025, 03-030, 03-035 | 1, 2, 3 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 10B, 1D, 5B, 6, 9 - Permissive paths for pedestrian and equestrian users, Solar PV cabling, 132 kV cabling, General works, Habitat management area | Apparatus | Yes | Open |  |  | Discussions are ongoing with National Gas Transmission plc regarding the form of protective provisions. | Draft protective provisions for the benefit of National Gas Transmission plc (NGT) are included in Part 4 of Schedule 15 of the draft DCO. Procedural Deadline A Discussions are ongoing between NGT and the Applicant regarding the form of the Protective Provisions. Deadline 1 Discussions are ongoing with NGT regarding the form of the Protective Provisions. Deadline 2 Bespoke protective provisions are currently being negotiated by the parties and the Applicant provided comments to NGT's solicitors on 18 May 2026 in respect of outstanding matters and is awaiting their response. Deadline 3 Negotiations between the Applicant and NGT are ongoing and focus on a select number of outstanding points to be agreed. A meeting between the parties is being arranged. |  |  | RR-3423 - National Gas Transmission PLC
|  |  |  | 01-045, 02-003, 02-005, 02-006, 02-015, 02-016, 02-017, 02-018, 02-019, 02-020, 02-021, 02-022, 02-023, 03-014, 03-015, 03-016, 03-017, 03-018, 03-019, 03-020, 03-021, 03-022, 03-023, 03-024, 03-025, 03-026, 03-027, 03-028, 03-029, 03-030, 03-031, 03-032, 03-033, 03-034, 03-035, 03-036, 03-037, 03-038, 03-039, 03-040, 03-041, 03-042, 03-067, 03-068, 03-078, 04-002, 04-003 | 1, 2, 3, 4 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 5B, 9, 10B, 1D, 6, 1 - 132 kV cabling, Habitat management area, Permissive paths for pedestrian and equestrian users, Solar PV cabling, General works, Solar PV area | Rights
|  |  |  | 01-039, 01-046, 01-053, 01-054, 01-055, 01-056, 03-050, 10-006, 10-007 | 1, 3, 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1D, 5B, 7, 8A, 5A - Solar PV cabling, 132 kV cabling, Solar PV temporary construction compound, Temporary access, 400 kV cable corridor | Rights
|  |  |  | 01-044, 01-046, 01-047, 01-048, 01-052, 01-054, 02-002, 02-010 | 1, 2 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5B, 8B - 132 kV cabling, Permanent access | Apparatus
310494 | National Grid Electricity Distribution (South West) PLC | Lauren Gardner | Cat 2 | 14-015 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | Rights | Yes | Open |  |  | n/a | Holders of an Electricity Act 1989 licence will have the benefit of the protective provisions set out in Part 1 of Schedule 2. National Grid Electricity Distribution (South West) plc has not requested bespoke protective provisions. Deadine 1 Protective Provisions with NGED have been incorporated into the draft DCO at Deadline 1. Discussions are ongoing in respect of a side agreement. Deadline 2 Following discussions in respect of the form of bespoke protective provisions, the Applicant provided NGED's solicitors with a draft side agreement and protective provisions on 27 April 2026 and is awaiting comment. Deadline 3 The protective provisions for the benefit of NGED included at DL1 are agreed and an engrossed Side Agreement is in circulation and awaiting signature as of 12 June 2026. |  |  | RR-3424 - National Grid Electricity Distribution (South West) plc
|  |  |  | 16-014 | 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | Apparatus
|  |  |  | 20-002, 20-003, 21-004, 21-005, 21-006, 21-007 | 20, 21 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A - Temporary access | Apparatus
22381 | National Grid Electricity Transmission PLC | Tom Price | Cat 2 | 11-011, 12-001, 12-002, 12-003, 12-004, 12-005, 12-006, 12-007, 13-037, 14-001, 14-002, 14-003, 14-004, 14-005, 14-007, 14-009, 14-012, 14-019, 14-020, 14-021, 14-022, 14-023, 16-003, 16-011, 16-012, 16-015 | 11, 12, 13, 14, 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 5A(v) - 400 kV cable corridor, Cable corridor temporary construction compound | Rights | Yes | Open |  |  | The Applicant will continue to engage with National Grid Electricity Transmission plc and is confident that any necessary land rights can be acquired by voluntary agreement. See Part 1 of this Land Rights Tracker for further details. | Draft protective provisions for the benefit of National Grid Electricity Transmission plc (NGET) are included in Part 3 of Schedule 15 of the draft DCO and are under discussion. Procedural Deadline A Discussions are ongoing between Exolum and the Applicant regarding the form of the Protective Provisions. Deadline 1 Discussions are ongoing with NGET regarding the form of the Protective Provisions. Deadline 2 As noted at Issue Specific Hearing 1 (see page 17 and 18 of the Written Summary of the Applicant’s Oral Submissions and Responses at Issue Specific Hearing 1 and Responses to Action Points [REP1A-012]), related entities of Island Green Power are promoting a number of other solar DCOs at varying stages of the consenting process, namely Green Hill Solar Farm. As the Applicant is a subsidiary of Island Green Power, where possible it is seeking a consistent approach with statutory undertakers to protective provisions across its projects. This includes protective provisions for the benefit of NGET. The Applicant understands that protective provisions are close to being agreed with NGET for Green Hill Solar Farm, and once agreed anticipates that agreement of protective provisions with NGET for the Scheme will follow soon thereafter. Once agreed, these will be incorporated into the draft DCO at a future deadline. The solicitors acting for the Applicant and NGET respectively have agreed this approach as per their email correspondence on 2 April 2026. Deadline 3 Negotiations between the parties continue to progress and the Applicant provided NGET's solicitors with a draft Side Agreement and form of protective provisions on 12 June 2026. |  |  | RR-3425 - National Grid Electricity Transmission Plc
|  |  |  | 13-001, 15-021, 16-002a, 16-003, 16-005, 16-006, 16-009, 16-011, 16-012, 16-014, 16-015, 16-016, 16-017, 16-018, 16-019 | 13, 15, 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 5A(v), 8A - 400 kV cable corridor, Cable corridor temporary construction compound, Temporary access | Apparatus
|  |  |  | 16-011, 16-012, 16-015 | 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 5A(v) - 400 kV cable corridor, Cable corridor temporary construction compound | Beneficiary
|  |  |  | 16-014, 16-016, 16-017, 16-019 | 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 5A(v), 8A - 400 kV cable corridor, Cable corridor temporary construction compound, Temporary access | Freeholder
|  |  |  | 13-012, 13-015, 13-016, 16-001, 16-002 | 13, 16 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A - Temporary access | Apparatus
|  |  |  | 16-020 | 16 | As described in the Book of Reference | Land is subject to No Rights Sought | 4 - National Grid substation connection | Freeholder
|  |  |  | 16-020 | 16 | As described in the Book of Reference | Land is subject to No Rights Sought | 4 - National Grid substation connection | Apparatus
278704 | National Highways Limited |  | Cat 2 | 09-018, 09-019, 09-020, 13-009 | 9, 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 8A - 400 kV cable corridor, Temporary access | Freeholder | Yes | Open |  |  | The Applicant is in discussions with National Highways over the technical aspects of the crossing of the strategic road network. The Applicant will continue to engage with National Highways and is confident that any necessary land rights can be acquired by voluntary agreement . See Part 1 of this Land Rights Tracker for further details. | Draft protective provisions for the benefit of National Highways Limited are included in Part 5 of Schedule 15 of the draft DCO. Deadline 1 An updated version of the protective provisions with National Highways have been incorporated into the draft DCO at Deadline 1. Discussions are ongoing regarding a side agreement. Deadline 2 The Applicant's solicitors provided National Highway's solicitors with a draft side agreement and protective provisions on 17 April 2026 and is awaiting comment. Deadline 3 National Highways' solicitors confirmed agreement in principle with the draft Side Agreement and form of protective provisions subject to further discussion between the parties on a select number of outstanding points. Negotiations in respect of these points remain ongoing. |  |  | RR-3426 - National Highways
|  |  |  | 09-018, 09-019, 09-020, 09-021 | 9 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | Apparatus
|  |  |  | 13-003 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | Rights
|  |  |  | 13-006, 13-013, 13-014, 13-016, 20-001, 20-002, 21-003, 21-006, 21-007 | 13, 20, 21 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A - Temporary access | Freeholder
72428 | NEOS Networks Limited |  | Cat 2 | 11-018, 11-019, 13-008, 13-010 | 11, 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 8A - 400 kV cable corridor, Temporary access | Apparatus | Yes | n/a |  |  | n/a | Operators of electronic communications code networks will have the benefit of the protective provisions set out in Part 2 of Schedule 15 of the draft DCO. NEOS Networks has not requested bespoke protective provisions.
|  |  |  | 11-015, 11-016, 11-020, 13-004, 13-005, 13-007, 13-011, 13-012, 13-014 | 11, 13 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A - Temporary access | Apparatus
7310 | Network Rail Infrastructure Limited |  | Cat 2 | 03-014, 03-015, 03-016, 03-017, 03-018, 03-019, 03-020, 03-021, 03-022, 03-023, 03-024, 03-025, 03-026, 03-027, 03-028, 03-029, 03-030, 03-031, 03-032, 03-033, 03-034, 03-035, 03-036, 03-037, 03-038, 03-039, 03-040, 03-041, 03-042, 03-049, 03-067, 03-068, 03-078 | 3 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1D, 6, 1, 9, 10B, 5B, 3B - Solar PV cabling, General works, Solar PV area, Habitat management area, Permissive paths for pedestrians and equestrian users, 132 kV cabling, 132 kV substation | Rights | Yes | n/a |  |  | The Applicant is in discussions with Network Rail over the technical aspects of the crossing of the railway. The Applicant will continue to engage with Network Rail and is confident that any necessary land rights can be acquired by voluntary agreement . See Part 1 of this Land Rights Tracker for further details. | Draft protective provisions for the benefit of Network Rail Infrastructure Limited (Network Rail) are included in Part 6 of Schedule 15 of the draft DCO. Procedural Deadline A Discussions are ongoing between Network Rail and the Applicant regarding the form of the Protective Provisions. Deadline 1 Discussions are ongoing with Network Rail regarding the form of the Protective Provisions. Deadline 2 Network Rail's solicitors have provided Network Rails's standard protective provisions which the Applicant is reviewing and will provide justification as to any amendments required. Deadline 3 As part of agreeing the form of protective provisions the parties have agreed to enter into a Framework Agreement regarding ongoing land agreement negotiations. Network Rail's solicitors have provided a draft Framework Agreement which the Applicant is currently reviewing.
|  |  |  | 03-023, 03-030, 03-049, 03-052, 03-067, 03-078, 04-004, 04-010, 04-016, 06-007, 06-009, 06-033 | 3, 4, 6 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 9, 1D, 5B, 6, 5A - Habitat management area, Solar PV cabling, 132 kV cabling, General works, 400 kV cable corridor | Apparatus
|  |  |  | 06-024 | 6 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 5A, 6 - 400 kV cable corridor, General works | Unregistered Freeholder
|  |  |  | 03-048, 03-050, 03-051, 03-056, 03-058, 03-066, 03-069, 03-070, 03-076, 04-017, 04-018, 04-019, 04-031, 04-032, 04-035, 04-038, 05-037, 06-029, 06-030, 14-011, 14-013, 14-014, 14-020, 14-031, 14-032, 14-033, 14-035, 14-043, 14-044, 14-045, 16-014 | 3, 4, 5, 6, 14, 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5B, 8B, 1D, 5A, 8A - 132 kV cabling, Permanent access, Solar PV cabling, 400 kV cable corridor, Temporary access | Apparatus
|  |  |  | 03-051, 03-056, 03-057, 03-058, 03-066, 03-069, 03-070, 03-076, 04-017, 04-018, 04-032, 04-035, 05-037, 06-025, 06-026, 06-029, 14-011, 14-013, 14-014, 14-033, 14-040 | 3, 4, 5, 6, 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5B, 8B, 1D, 5A - 132 kV cabling, Permanent access, Solar PV cabling, 400 kV cable corridor | Unregistered Freeholder
|  |  |  | 06-025, 14-032, 14-044, 14-045 | 6, 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 8A - 400 kV cable corridor, Temporary access | Rights
|  |  |  | 14-009, 14-012, 14-043 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | Freeholder
266588 | OCU Group Ltd |  | Cat 2 | 03-023, 03-025, 03-030, 03-034, 03-036, 03-044, 03-045, 03-078, 04-055, 04-056, 04-058, 04-059, 04-060, 06-007, 06-009, 06-020, 06-023, 06-024, 06-033 | 3, 6 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 9, 1D, 6, 5B, 1, 5A, 2, 3B, 7 - Habitat management area, Solar PV cabling, General works, 132 kV cabling, Solar PV area, 400 kV cable corridor, BESS, 132 kV substation, Solar PV temporary construction compound | Apparatus | Yes | n/a |  |  | n/a | Operators of electronic communications code networks will have the benefit of the protective provisions set out at Part 2 of Schedule 15 of the draft DCO. OCU Group has not requested bespoke protective provisions.
|  |  |  | 03-048, 03-050, 03-051, 03-058, 03-066, 03-069, 03-070, 03-076, 04-018, 04-019, 04-032, 04-035, 04-038, 05-035, 05-037, 06-015, 06-016, 06-017, 06-018, 06-021, 06-026, 06-027, 06-029, 06-030, 06-031, 11-011, 11-018, 11-019, 13-009, 13-017, 14-011, 14-013, 14-014, 14-033, 14-040, 16-002a, 16-014, 16-018 | 3, 4, 5, 6, 11, 13, 14, 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5B, 8B, 1D, 5A, 8A - 132 kV cabling, Permanent access, Solar PV cabling, 400 kV cable corridor, Temporary access | Apparatus
|  |  |  | 11-015, 11-016, 11-020, 13-012, 13-013, 13-015 | 11, 13 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A - Temporary access | Apparatus
181523 | On Tower UK Limited |  | Cat 2 | 03-014, 03-015, 03-016, 03-017, 03-018, 03-019, 03-020, 03-021, 03-022, 03-023, 03-024, 03-025, 03-026, 03-027, 03-028, 03-029, 03-030, 03-031, 03-032, 03-033, 03-034, 03-035, 03-036, 03-037, 03-038, 03-039, 03-040, 03-041, 03-042, 03-067, 03-068, 03-078 | 3 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1D, 6, 1, 9, 10B - Solar PV cabling, General works, Solar PV area, Habitat management area, Permissive paths for pedestrian and equestrian users | Rights | Yes | n/a |  |  | n/a | Operators of electronic communications code networks will have the benefit of the protective provisions set out at Part 2 of Schedule 15 of the draft DCO. On Tower UK Limited has not requested bespoke protective provisions.
|  |  |  | 03-039 | 3 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1D, 5B, 6 - Solar PV cabling, 132 kV cabling, General works | Leaseholder
156528 | Openreach Limited |  | Cat 2 | 01-003, 01-004, 01-020, 01-032, 02-016, 02-017, 04-067, 05-007 | 1, 2, 4, 5 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 9, 10B, 1D, 5B, 6, 10A, 8B - Habiat management area, Permissive paths for pedestrian and equestrian users, Solar PV cabling, 132 kV cabling, General works, Permissive path for pedestrians, Permanent access | Apparatus | Yes |  |  |  | n/a | Operators of electronic communications code networks will have the benefit of the protective provisions set out at Part 2 of Schedule 15 of the draft DCO. Openreach Limited has not requested bespoke protective provisions.
|  |  |  | 01-005, 01-010, 01-048, 01-050, 01-051, 01-052, 02-001, 02-002, 02-010, 04-045, 04-046, 04-047, 05-006, 05-008, 05-038, 06-001, 06-002, 06-004, 06-005, 06-017, 08-006, 09-007, 09-015, 10-001, 10-003, 10-011, 10-012, 11-005, 11-010, 11-011, 11-013, 11-014, 11-018, 11-019, 12-016, 13-003, 13-008, 13-010, 13-025, 13-031, 13-032, 14-004, 14-006, 14-009, 14-011, 14-012, 14-013, 14-015, 14-016, 14-017, 14-018, 14-024, 14-028, 14-031, 14-032, 14-033, 14-037, 14-038, 14-039, 14-040, 14-041, 14-042, 14-043, 14-049, 14-050, 15-003, 15-009, 15-011, 15-012, 16-002a, 16-007, 16-008, 16-009, 16-011, 16-012, 16-013, 16-014, 16-015, 16-016, 16-017, 16-018 | 1, 2, 4, 5, 6, 8, 9, 10, 11, 12, 13, 14, 15, 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B, 5B, 8A, 1D, 5A, 5A(v) - Permanent access, 132 kV cabling, Temporary access, Solar PV cabling, 400 kV cable corridor, Cable corridor temporary construction compound | Apparatus |  | n/a
|  |  |  | 01-006, 01-009, 09-001, 09-003, 09-004, 09-006, 09-008, 09-022, 10-002, 10-008, 11-006, 11-008, 11-012, 11-015, 11-016, 11-020, 12-015, 12-017, 12-019, 13-004, 13-005, 13-007, 13-011, 13-012, 13-014, 13-026, 13-027, 13-028, 13-034, 15-001, 15-006, 15-016, 16-002, 17-001, 17-002, 17-003, 17-004, 17-005, 19-001, 19-002, 20-001, 20-002, 20-003, 21-006, 21-007, 22-001, 22-002, 23-001, 23-003 | 1, 9, 10, 11, 12, 13, 15, 17, 19, 20, 21, 22, 23 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A, 5A(v) - Temporary access, Cable corridor temporary construction compound | Apparatus
|  |  |  | 16-020 | 16 | As described in the Book of Reference | Land is subject to No Rights Sought | 4 - National Grid substation connection | Apparatus
201221 | South West Water Limited |  | Cat 2 | 01-001, 01-002, 01-004, 01-012, 01-014, 01-020, 01-032, 03-021, 04-048, 04-049, 04-050, 04-051, 04-063, 04-064, 04-065, 04-066, 04-067, 04-068 | 1, 3, 4 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 9, 10B, 1D, 6, 5B, 5A - Habiat management area, Permissive paths for pedestrian and equestrian users, Solar PV cabling, General works, 132 kV cabling, 400 kV cable corridor | Apparatus | Yes | n/a |  |  | n/a | Water and sewerage undertakers will have the benefit of the protective provisions set out in Part 1 of Schedule 2. South West Water Limited has not requested bespoke protective provisions.
|  |  |  | 01-007, 01-010, 01-048, 04-044, 04-046 | 1, 4 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B, 5B - Permanent access, 132 kV cabling | Apparatus
|  |  |  | 01-006, 01-009, 20-002, 21-005 | 1, 20, 21 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A - Temporary access | Apparatus
278812 | Southern Electric Power Distribution PLC | James Archer | Cat 2 | 14-015 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | Rights | Yes | n/a |  |  | n/a | Holders of an Electricity Act 1989 licence will have the benefit of the protective provisions set out in Part 1 of Schedule 2. Southern Electric Power Distribution plc has not requested bespoke protective provisions.
119004 | SSE PLC |  | Cat 2 | 01-020, 01-029, 01-031, 01-036, 01-045, 02-016, 02-021, 02-022, 03-014, 03-015, 03-016, 03-023, 03-025, 03-030, 03-035, 03-038, 03-039, 03-040, 03-049, 04-003, 04-004, 04-016, 04-055, 04-058, 05-002, 05-009, 06-007, 06-012, 06-020, 06-033, 06-035, 07-036, 07-041 | 1, 2, 3, 4, 5, 6, 7 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1D, 5B, 6, 9, 1, 10B, 5A - Solar PV cabling, 132 kV cabling, General works, Habitat management area, Solar PV area, Permissive paths for pedestrian and equestrian users, 400 kV cable corridor | Apparatus | Yes | n/a |  |  | n/a | Holders of an Electricity Act 1989 licence will have the benefit of the protective provisions set out in Part 1 of Schedule 2. SSE plc has not requested bespoke protective provisions.
|  |  |  | 01-038, 01-046, 01-047, 01-048, 03-048, 03-050, 03-066, 03-069, 03-070, 04-009, 04-014, 04-024, 04-032, 04-035, 04-036, 04-037, 05-008, 05-042, 05-043, 06-002, 06-015, 06-016, 06-017, 06-029, 06-030, 06-039, 08-006, 09-021, 10-005, 10-006, 10-013, 11-001, 11-002, 11-003, 11-005, 11-010, 11-011, 11-018, 11-019, 11-021, 12-001, 12-002, 12-003, 12-011, 12-014, 12-016, 12-018, 13-002, 13-003, 13-024, 13-025, 14-006, 14-008, 14-010, 14-011, 14-013, 14-015, 14-016, 14-018, 14-019, 14-020, 14-024, 14-028, 14-029, 14-030, 14-051, 15-003, 15-008, 15-009, 15-014, 16-002a, 16-004, 16-009, 16-014, 16-015, 16-016, 16-018, 16-019 | 1, 3, 4, 5, 6, 8, 9, 10, 11, 12, 13, 14, 15, 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1D, 5B, 8B, 5A, 8A, 5A(v) - Solar PV cabling, 132 kV cabling, Permanent access, 400 kV cable corridor, Temporary access, Cable corridor temporary construction compound | Apparatus
|  |  |  | 05-043, 06-003, 06-004, 06-005, 08-006, 09-017, 11-011, 12-001, 12-002, 12-003, 12-004, 12-005, 12-006, 12-007, 12-011, 12-012, 12-013, 12-014, 12-018, 12-020, 13-001, 13-002, 13-017, 13-018, 13-020, 13-021, 13-022, 13-023, 13-025, 14-018, 14-026, 14-027, 14-028, 14-032, 14-035, 14-038, 14-042, 14-043, 14-044, 14-045, 14-046, 14-047 | 5, 6, 8, 9, 11, 12, 13, 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5B, 8A, 8B, 5A, 5A(v) - 132 kV cabling, Temporary access, Permanent access, 400 kV cable corridor, Cable corridor temporary construction compound | Rights
|  |  |  | 09-001, 09-003, 09-006, 10-008, 11-015, 11-016, 11-020, 12-008, 12-017, 12-019, 13-005, 13-006, 13-034, 15-001, 15-006, 15-015, 15-016, 15-018, 15-019, 16-002, 17-002, 17-003, 19-001, 19-002, 22-001, 22-002 | 9, 10, 11, 12, 13, 15, 16, 17, 19, 22 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A, 5A(v) - Temporary access, Cable corridor temporary construction compound | Apparatus
119004 | SSE PLC cont'd |  |  | 12-019 | 12 | As described in the Book of Reference | Land is subject to Temporary Possession | 5A(v) - Cable corridor temporary construction compound | Rights
|  |  |  | 16-020 | 16 | As described in the Book of Reference | Land is subject to No Rights Sought | 4 - National Grid substation connection | Apparatus
336274 | Telent Technology Services Limited |  | Cat 2 | 09-018, 09-019, 09-020 | 9 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | Apparatus | Yes | n/a |  |  | n/a | Operators of electronic communications code networks will have the benefit of the protective provisions set out at Part 2 of Schedule 15 of the draft DCO. Telent Technology Services Limited has not requested bespoke protective provisions.
63535 | Virgin Media Limited |  | Cat 2 | 11-018, 11-019 | 11 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 8A - 400 kV cable corridor, Temporary access | Apparatus | Yes | n/a |  |  | n/a | Operators of electronic communications code networks will have the benefit of the protective provisions set out at Part 2 of Schedule 15 of the draft DCO. Virgin Media Limited has not requested bespoke protective provisions.
|  |  |  | 11-015, 11-016, 11-020, 23-001, 23-003 | 11, 23 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A - Temporary access | Apparatus
182369 | Vodafone Limited |  | Cat 2 | 11-010, 11-018, 11-019, 12-016, 14-011, 14-013, 14-014, 14-033, 14-040, 16-002a, 16-014, 16-016, 16-017, 16-019 | 11, 12, 14, 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 8A, 5A(v) - 400 kV cable corridor, Temporary access, Cable corridor temporary construction compound | Apparatus | Yes | n/a |  |  | n/a | Operators of electronic communications code networks will have the benefit of the protective provisions set out at Part 2 of Schedule 15 of the draft DCO. Vodafone Limited has not requested bespoke protective provisions.
|  |  |  | 11-006, 11-015, 11-016, 11-020, 12-015, 12-017, 12-019 | 11, 12 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A, 5A(v) - Temporary access, Cable corridor temporary construction compound | Apparatus
|  |  |  | 16-020 | 16 | As described in the Book of Reference | Land is subject to No Rights Sought | 4 - National Grid substation connection | Apparatus
108800 | Wales and West Utilities Limited |  | Cat 2 | 10-004, 10-011 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | Rights | Yes | n/a |  |  | n/a | Gas undertakers will have the benefit of the protective provisions set out in Part 1 of Schedule 2. Wales and West Utilities Limited has not requested bespoke protective provisions.
|  |  |  | 10-006, 14-024, 14-031, 14-033, 14-037, 14-039 | 10, 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 8A - 400 kV cable corridor, Temporary access | Apparatus
|  |  |  | 10-010, 17-001, 17-002, 17-003, 17-005, 22-001, 22-002, 23-001, 23-003 | 10, 17, 22, 23 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A - Temporary access | Apparatus
54925 | Wessex Water Services Limited | Nick Routh | Cat 2 | 02-003, 02-005, 02-006, 02-015, 02-016, 02-017, 02-018, 02-019, 02-020, 02-021, 02-022, 02-023 | 2 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 10B, 1D, 5B, 6, 1, 9 - Permissive paths for pedestrian and equestrian users, Solar PV cabling, 132 kV cabling, General works, Solar PV area, Habitat management area | Rights | Yes | n/a |  |  | The Applicant will continue to engage with Wessex Water Services Limited and is confident that any necessary land rights can be acquired by voluntary agreement. See Part 1 of this Land Rights Tracker for further details. | Water and sewerage undertakers will have the benefit of the protective provisions set out in Part 1 of Schedule 2. Wessex Water Services Limited has not requested bespoke protective provisions.
|  |  |  | 05-021, 05-033, 06-024, 06-033, 07-032 | 5, 6, 7 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1D, 5B, 6, 5A, 8B - Solar PV cabling, 132 kV cabling, General works, 400 kV cable corridor, Permanent access | Apparatus
|  |  |  | 05-034, 05-035, 05-036, 05-038, 05-039, 06-005, 06-016, 06-017, 06-021, 06-026, 06-027, 06-029, 06-030, 06-031, 06-032, 07-022, 07-033, 07-034, 08-006, 09-007, 09-009, 09-010, 09-012, 09-015, 09-021, 10-005, 10-006, 10-011, 10-013, 11-003, 11-005, 11-009, 12-018, 12-020, 13-009, 13-031, 13-032, 14-004, 14-006, 14-011, 14-013, 14-016, 14-017, 14-018, 14-024, 14-031, 14-033, 14-037, 14-039, 14-041, 14-044, 14-045, 14-049, 14-050, 14-051, 15-003, 15-008, 15-009, 15-012, 15-013, 16-002a, 16-004, 16-005, 16-006, 16-009, 16-014, 16-016, 16-018 | 5, 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1D, 5B, 8B, 8A, 5A, 5A(v) - Solar PV cabling, 132 kV cabling, Permanent access, Temporary access, 400 kV cable corridor, Cable corridor temporary construction compound | Apparatus
|  |  |  | 09-010, 15-014, 16-006, 16-015 | 9, 15, 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | Rights
|  |  |  | 14-049 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | Freeholder
|  |  |  | 09-001, 09-003, 09-006, 09-011, 10-008, 11-006, 11-020, 12-019, 13-006, 13-012, 13-013, 13-016, 13-027, 13-028, 13-029, 13-030, 13-034, 15-001, 15-006, 15-016, 16-001, 16-002, 17-002, 17-003, 19-001, 22-002, 23-003 | 9, 10, 11, 12, 13, 15, 16, 17, 19, 22, 23 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A, 5A(v) - Temporary access, Cable corridor temporary construction compound | Apparatus
|  |  |  | 09-011 | 9 | As described in the Book of Reference | Land is subject to Temporary Possession | 5A(v) - Cable corridor temporary construction compound | Rights
178698 | Zayo Group UK Limited |  | Cat 2 | 01-042, 01-043, 01-045, 02-003, 02-005, 02-016, 03-001, 03-006, 03-007, 03-010, 03-014, 03-023, 03-024, 03-025, 03-030, 03-035, 03-037 | 1, 2, 3 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 10B, 1D, 5B, 6, 1, 9 - Permissive paths for pedestrian and equestrian users, Solar PV cabling, 132 kV cabling, General works, Solar PV area, Habitat management area | Apparatus | Yes | n/a |  |  | n/a | Operators of electronic communications code networks will have the benefit of the protective provisions set out at Part 2 of Schedule 15 of the draft DCO. Zayo Group UK Limited has not requested bespoke protective provisions.
|  |  |  | 01-045, 02-003, 02-005, 02-006, 02-015, 02-016, 02-017, 02-018, 02-019, 02-020, 02-021, 02-022, 02-023, 03-014, 03-015, 03-016, 03-017, 03-018, 03-019, 03-020, 03-021, 03-022, 03-023, 03-024, 03-025, 03-026, 03-027, 03-028, 03-029, 03-030, 03-031, 03-032, 03-033, 03-034, 03-035, 03-036, 03-037, 03-038, 03-039, 03-040, 03-041, 03-042, 03-067, 03-068, 03-078, 04-002, 04-003 | 1, 2, 3, 4 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 5B, 9, 10B, 1D, 6, 1 - 132 kV cabling, Habitat management area, Permissive paths for pedestrian and equestrian users, Solar PV cabling, General works, Solar PV area | Rights
|  |  |  | 01-044, 01-046, 01-047, 01-048, 01-052, 01-054, 02-002, 02-010, 03-076, 13-009 | 1, 2, 3, 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5B, 8B, 8A, 1D - 132 kV cabling, Permanent access, Temporary access, Solar PV cabling | Apparatus
|  |  |  | 01-046, 01-053, 03-050 | 1,3 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5B, 8B - 132 kV cabling, Permanent access | Rights
|  |  |  | 13-005, 13-006, 13-013, 13-016 | 13 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A - Temporary access | Apparatus
20042 | Secretary Of State For Defence |  | Cat 2 | 16-014, 16-016, 16-017, 16-019 | 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 5A(v), 8A - 400 kV cable corridor, Cable corridor temporary construction compound, Temporary access | Crown authority | No | n/a |  |  | If the DCO application is accepted for Examination, the Applicant will contact the Crown authority to confirm their interest in the land and obtain s135 consent. Deadline 2 The Applicant continues to seek to engage with the Crown Authority to confirm their interest in the land and obtain s135 consent. Deadline 3 The Applicant continues to seek to engage with the Crown Authority to confirm their interest in the land and obtain s135 consent and is still awaiting feedback.
|  |  |  | 16-020 | 16 | As described in the Book of Reference | Land is subject to No Rights Sought | 4 - National Grid substation connection | Crown authority | No
127751 | Secretary Of State For Work And Pensions |  | Cat 2 | 14-051 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | Crown authority | No | n/a |  |  | If the DCO application is accepted for Examination, the Applicant will contact the Crown authority to confirm their interest in the land and obtain s135 consent. Deadline 2 The Applicant continues to seek to engage with the Crown Authority to confirm their interest in the land and obtain s135 consent. Deadline 3 The Applicant continues to seek to engage with the Crown Authority to confirm their interest in the land and obtain s135 consent and is still awaiting feedback.
48051 | The Secretary of State for Environment, Food and Rural Affairs |  | Cat 2 | 09-012 | 9 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400 kV cable corridor | Crown authority | No | n/a |  |  | If the DCO application is accepted for Examination, the Applicant will contact the Crown authority to confirm their interest in the land and obtain s135 consent. Deadline 2 The Applicant continues to seek to engage with the Crown Authority to confirm their interest in the land and obtain s135 consent. Deadline 3 The Applicant continues to seek to engage with the Crown Authority to confirm their interest in the land and obtain s135 consent and is still awaiting feedback.

## Part 3 - Occupiers
Part 3
Ref | Landowner/ Affected Party | Agent/ Representative | BoR Category and Interest | Book of Ref. Plot No. | Plan Ref. No. | Description of Land | Description of Rights Requested | Works Number(s) and Description | Status of Objection | Notes | Last Updated | Summary of Negotiations | Status of Negotiations | Relevant Rep Ref No. | Written Rep Ref No. | Ref No. for any other docs submitted by IP/AP. | Ref No. for Applicant's Response
72901 | John Eavis | KMT Farming & Consultancy Limited | Cat 1 - Leasehold | 06-006 | 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5B, 8A - 132kV cabling, Temporary access |  |  |  | Deadline 3 The Applicant continues to negotiate and finalise the voluntary agreements with the respective landowner. Once the voluntary agreement is secured with the landowner, the Applicant will engage with the tenant and is confident the necessary land rights can be acquired by voluntary agreement.
72902 | Rosemarie Margaret Eavis | KMT Farming & Consultancy Limited | Cat 1 - Leasehold | 06-006 | 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5B, 8A - 132kV cabling, Temporary access |  |  |  | Deadline 3 The Applicant continues to negotiate and finalise the voluntary agreements with the respective landowner. Once the voluntary agreement is secured with the landowner, the Applicant will engage with the tenant and is confident the necessary land rights can be acquired by voluntary agreement.
137373 | David Mark Howard Giddings |  | Cat 1 - Tenant | 15-014 | 15 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400kV cable corridor |  |  |  | Deadline 3 The Applicant continues to negotiate and finalise the voluntary agreements with the respective landowner. Once the voluntary agreement is secured with the landowner, the Applicant will engage with the tenant and is confident the necessary land rights can be acquired by voluntary agreement.
237726 | Paul Trevor Gregory |  | Cat 1 - Tenant | 12-018, 12-020, 13-002, 13-025, 13-037, 14-001, 14-002, 14-003, 14-005, 14-005a, 14-023 | 12, 13, 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A(v), 5A - 400 kV cable corridor, Cable corridor temporary construction compound |  |  |  | Deadline 3 The Applicant continues to negotiate and finalise the voluntary agreements with the respective landowner. Once the voluntary agreement is secured with the landowner, the Applicant will engage with the tenant and is confident the necessary land rights can be acquired by voluntary agreement.
237726 | Paul Trevor Gregory |  | Cat 1 - Tenant | 12-019 | 12 | As described in the Book of Reference | Land is subject to Temporary Possession | 5A(v) - Cable corridor temporary construction compound |  |  |  | Deadline 3 The Applicant continues to negotiate and finalise the voluntary agreements with the respective landowner. Once the voluntary agreement is secured with the landowner, the Applicant will engage with the tenant and is confident the necessary land rights can be acquired by voluntary agreement.
241382 | David Matthew Irvine |  | Cat 1 - Tenant | 02-003, 02-005, 02-006, 02-015, 02-016, 02-017, 02-018, 02-019, 02-020, 02-021, 02-022, 02-023 | 2 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1D, 5B, 6, 9, 10B - Solar PV area, Solar PV cabling, 132 kV cabling, General works, Habitat management area, Permissive paths for pedestrian and equestrian users |  |  |  | Deadline 3 Option Agreements are between the Applicant and the Landowner and they deal with surrendor of tenancies as part of these contracts. Therefore the majority of these commercial discussions are between the landowner and their current tenant, with The Applicant offering assistance where applicable.
258316 | Jacqueline Joy Greenhill |  | Cat 1 - Leasehold | 07-041, 07-042, 07-043, 07-044, 07-045 | 7 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1D, 6 - Solar PV cabling, General works |  |  |  | Deadline 3 Option Agreements are between the Applicant and the Landowner and they deal with surrendor of tenancies as part of these contracts. Therefore the majority of these commercial discussions are between the landowner and their current tenant, with The Applicant offering assistance where applicable.
258317 | Andrew James Greenhill |  | Cat 1 - Leasehold | 07-041, 07-042, 07-043, 07-044, 07-045 | 7 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1D, 6 - Solar PV cabling, General works |  |  |  | Deadline 3 Option Agreements are between the Applicant and the Landowner and they deal with surrendor of tenancies as part of these contracts. Therefore the majority of these commercial discussions are between the landowner and their current tenant, with The Applicant offering assistance where applicable.
275395 | Octavian Wine Services Limited | Chris Threlfall | Cat 1 - Leasehold | 15-012 | 15 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400kV cable corridor |  |  |  | Deadline 3 The Applicant continues to negotiate and finalise the voluntary agreements with the respective landowner. Once the voluntary agreement is secured with the landowner, the Applicant will engage with the tenant and is confident the necessary land rights can be acquired by voluntary agreement.
278709 | Bryan Ashton Hawker |  | Cat 1 - Tenant | 11-003, 11-004, 11-005 | 11 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 5A(v), 8A - 400 kV cable corridor, Cable corridor temporary construction compound, Temporary access |  |  |  | Deadline 3 The Applicant continues to negotiate and finalise the voluntary agreements with the respective landowner. Once the voluntary agreement is secured with the landowner, the Applicant will engage with the tenant and is confident the necessary land rights can be acquired by voluntary agreement.
278710 | Michael Robert Edward Hawker | Toby Bateman | Cat 1 - Tenant | 11-003, 11-004, 11-005 | 11 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 5A(v), 8A - 400 kV cable corridor, Cable corridor temporary construction compound, Temporary access |  |  |  | Deadline 3 The Applicant continues to negotiate and finalise the voluntary agreements with the respective landowner. Once the voluntary agreement is secured with the landowner, the Applicant will engage with the tenant and is confident the necessary land rights can be acquired by voluntary agreement.
278724 | Christopher Bernard Edwin Carpenter | George King | Cat 1 - Tenant | 15-021 | 15 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400kV cable corridor |  |  |  | Deadline 3 The Applicant continues to negotiate and finalise the voluntary agreements with the respective landowner. Once the voluntary agreement is secured with the landowner, the Applicant will engage with the tenant and is confident the necessary land rights can be acquired by voluntary agreement.
278806 | Andrew Raymond James Carpenter | George King | Cat 1 - Tenant | 15-021 | 15 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400kV cable corridor |  |  |  | Deadline 3 The Applicant continues to negotiate and finalise the voluntary agreements with the respective landowner. Once the voluntary agreement is secured with the landowner, the Applicant will engage with the tenant and is confident the necessary land rights can be acquired by voluntary agreement.
278813 | Ashton Robert Hawker |  | Cat 1 - Tenant | 04-028, 09-015 | 4, 9 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 5B - 400kV cable corridor, 132 kV cabling |  |  |  | Deadline 3 The Applicant continues to negotiate and finalise the voluntary agreements with the respective landowner. Once the voluntary agreement is secured with the landowner, the Applicant will engage with the tenant and is confident the necessary land rights can be acquired by voluntary agreement.
278813 | Ashton Robert Hawker |  | Cat 1 - Tenant | 04-028 | 4 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 5B - 400kV cable corridor, 132 kV cabling |  |  |  | Deadline 3 The Applicant continues to negotiate and finalise the voluntary agreements with the respective landowner. Once the voluntary agreement is secured with the landowner, the Applicant will engage with the tenant and is confident the necessary land rights can be acquired by voluntary agreement.
278844 | Graham John Corp | Rupert Bendell | Cat 1 - Tenant | 12-001, 12-002, 12-003, 12-004, 12-005, 12-006, 12-007, 12-011, 12-012, 12-013, 12-014 | 12 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400kV cable corridor |  |  |  | Deadline 3 The Applicant continues to negotiate and finalise the voluntary agreements with the respective landowner. Once the voluntary agreement is secured with the landowner, the Applicant will engage with the tenant and is confident the necessary land rights can be acquired by voluntary agreement.
298916 | John Vincent | Graham Singer | Cat 1 - Tenant | 06-033, 06-034, 06-035, 06-036, 06-037, 07-001, 07-002, 07-003, 07-004, 07-005, 07-006, 07-007, 07-008, 07-009, 07-010, 07-011, 07-012, 07-013, 07-014, 07-015, 07-016, 07-017, 07-018, 07-019, 07-020, 07-021, 07-023, 07-024, 07-025, 07-027, 07-028, 07-029, 07-030, 07-031, 07-036, 07-037, 07-038, 07-039, 07-040 | 6, 7 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1D, 5B, 6, 7, 10A, 10B - Solar PV area, Solar PV cabling, 132 kV cabling, General works, Solar PV temporary construction compound, Permissive path for pedestrians, Permissive paths for pedestrian and equestrian users |  |  |  | Deadline 3 Option Agreements are between the Applicant and the Landowner and they deal with surrendor of tenancies as part of these contracts. Therefore the majority of these commercial discussions are between the landowner and their current tenant, with The Applicant offering assistance where applicable.
298916 | John Vincent | Graham Singer | Cat 1 - Tenant | 06-038, 06-039 | 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B - Permanent access |  |  |  | Deadline 3 Option Agreements are between the Applicant and the Landowner and they deal with surrendor of tenancies as part of these contracts. Therefore the majority of these commercial discussions are between the landowner and their current tenant, with The Applicant offering assistance where applicable.
303902 | Jacqueline Ann Collett |  | Cat 1 - Tenant | 04-024 | 4 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 5B - 400kV cable corridor, 132 kV cabling |  |  |  | Deadline 3 The Applicant continues to negotiate and finalise the voluntary agreements with the respective landowner. Once the voluntary agreement is secured with the landowner, the Applicant will engage with the tenant and is confident the necessary land rights can be acquired by voluntary agreement.
318397 | Bridget Marie Gregory |  | Cat 1 - Tenant | 13-025, 13-037, 14-001, 14-002, 14-003, 14-005, 14-005a, 14-023 | 13, 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400kV cable corridor |  |  |  | Deadline 3 The Applicant continues to negotiate and finalise the voluntary agreements with the respective landowner. Once the voluntary agreement is secured with the landowner, the Applicant will engage with the tenant and is confident the necessary land rights can be acquired by voluntary agreement.
318399 | Marcus Antony Gregory |  | Cat 1 - Tenant | 13-025, 13-037, 14-001, 14-002, 14-003, 14-005, 14-005a, 14-023 | 13, 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400kV cable corridor |  |  |  | Deadline 3 The Applicant continues to negotiate and finalise the voluntary agreements with the respective landowner. Once the voluntary agreement is secured with the landowner, the Applicant will engage with the tenant and is confident the necessary land rights can be acquired by voluntary agreement.
318401 | Dean Gary Sully |  | Cat 1 - Tenant | 13-001, 14-004, 14-019, 14-020, 14-021, 14-022, 14-026, 14-027, 14-028, 14-028a, 14-044, 14-044a, 14-045, 14-045a, 14-046, 14-047 | 13, 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A, 8A - 400kV cable corridor, Temporary access |  |  |  | Deadline 3 The Applicant continues to negotiate and finalise the voluntary agreements with the respective landowner. Once the voluntary agreement is secured with the landowner, the Applicant will engage with the tenant and is confident the necessary land rights can be acquired by voluntary agreement.
318402 | Easton Farm Ltd |  | Cat 1 - Tenant | 13-021, 13-022, 13-023 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400kV cable corridor |  |  |  | Deadline 3 The Applicant continues to negotiate and finalise the voluntary agreements with the respective landowner. Once the voluntary agreement is secured with the landowner, the Applicant will engage with the tenant and is confident the necessary land rights can be acquired by voluntary agreement.
318402 | Easton Farm Ltd |  | Cat 1 - General Licence | 12-001, 12-005, 12-004, 12-002, 12-003, 12-006, 12-007 | 12 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400kV cable corridor |  |  |  | Deadline 3 The Applicant continues to negotiate and finalise the voluntary agreements with the respective landowner. Once the voluntary agreement is secured with the landowner, the Applicant will engage with the tenant and is confident the necessary land rights can be acquired by voluntary agreement.
318403 | Kevin Candy |  | Cat 1 - Tenant | 13-017 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400kV cable corridor |  |  |  | Deadline 3 The Applicant continues to negotiate and finalise the voluntary agreements with the respective landowner. Once the voluntary agreement is secured with the landowner, the Applicant will engage with the tenant and is confident the necessary land rights can be acquired by voluntary agreement.
337481 | James Stafford |  | Cat 1 - Tenant | 14-050 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5A - 400kV cable corridor |  |  |  | Deadline 3 The Applicant continues to negotiate and finalise the voluntary agreements with the respective landowner. Once the voluntary agreement is secured with the landowner, the Applicant will engage with the tenant and is confident the necessary land rights can be acquired by voluntary agreement.
79937 | Leonard Irvine |  | Cat 1 - Tenant | 01-054, 01-055, 01-056, 02-001 | 1, 2 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5B, 8A - 132kV cabling, Temporary access |  |  |  | Deadline 3 Option Agreements are between the Applicant and the Landowner and they deal with surrendor of tenancies as part of these contracts. Therefore the majority of these commercial discussions are between the landowner and their current tenant, with The Applicant offering assistance where applicable.
379914 | Jeffrey Lionel Lippiatt |  | Cat 1 - Tenant | 03-014, 03-015, 03-016, 03-017, 03-018, 03-019, 03-020, 03-021, 03-022, 03-023, 03-024, 03-025, 03-026, 03-027, 03-028, 03-029, 03-030, 03-031, 03-032, 03-033, 03-034, 03-035, 03-036, 03-037, 03-038, 03-039, 03-040, 03-041, 03-042, 03-067, 03-068, 03-078 | 3 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1D, 3B, 5B, 6, 9, 10B - Solar PV area, Solar PV cabling, 132 kV substation, 132 kV cabling, General works, Habitat management area, Permissive paths for pedestrian and equestrian users |  |  |  | Deadline 3 Option Agreements are between the Applicant and the Landowner and they deal with surrendor of tenancies as part of these contracts. Therefore the majority of these commercial discussions are between the landowner and their current tenant, with The Applicant offering assistance where applicable.
302245 | Peter Alan Tutcher |  | Cat 1 - Tenant | 03-071, 03-072, 03-073, 03-074, 03-075, 03-077, 03-079, 03-080 | 3 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1D, 5B, 6, 9 - Solar PV area, Solar PV cabling, 132 kV cabling, General works, Habitat management area |  |  |  | Deadline 3 Option Agreements are between the Applicant and the Landowner and they deal with surrendor of tenancies as part of these contracts. Therefore the majority of these commercial discussions are between the landowner and their current tenant, with The Applicant offering assistance where applicable.
379908 | Martin Wooldridge |  | Cat 1 - Tenant | 04-048, 04-049, 04-050, 04-051, 04-052, 04-053, 04-054, 04-056, 04-062, 04-063, 04-064, 04-066, 04-067, 04-068 | 4 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1D, 3A, 5A, 5B, 6 - Solar PV area, Solar PV cabling, 400kV substation, 400kV cable corridor, 132 kV cabling, General works |  |  |  | Deadline 3 Option Agreements are between the Applicant and the Landowner and they deal with surrendor of tenancies as part of these contracts. Therefore the majority of these commercial discussions are between the landowner and their current tenant, with The Applicant offering assistance where applicable.

## Part 4 - Overview Table
Part 4
Land Type | Total Area | Total No. of Plots | Total No. of Aps |  |  |  | Assumptions
|  |  | Cat 1 | Cat 2 | Cat 3 | Total
CA of Land | 777 | 237 | 27 | 49 | 0 | 76 | Only counted individual once per plot interest i.e if they have cat 1 interest over 10 plots only counted once.
CA of Rights | 449 | 274 | 150 | 188 | 0 | 338 | Only counted individual once per plot interest i.e if they have cat 1 interest over 10 plots only counted once.
Temporary Possession | 20 | 85 | 155 | 15 | 0 | 170 | Only counted individual once per plot interest i.e if they have cat 1 interest over 10 plots only counted once.
Crown Land | 6 | 2 | 2 | 12 | 0 | 14 | In these plots the 2 CAT 1 interests are non Crown and of the 12 CAT 2 interests 2 are crown interests
Stat Undertaker Land | 70 | 29 | 2 | 23 | 0 | 25 | 2 Stat Undertaker with either registered or unregistered freehold 23 includes 7 Stat Undertakers with CAT2 Interest on Stat Undertaker registered or unregistered land
Agri Tenancies | 97 | 45 | 7 | 0 | 0 | 7 | Only Farm Business Tenancy, Farm Business Tenancy (7 years and above) and Agricultural Holdings Tenancy agreed before 1 September 1995 included
Entire Order Limits | 1237 | 597 | 242 | 205 | 0 | 447 | Category 3 interests are not within the order limits so not included in this table.