## Part 1 Category 1
Meridian Solar Farm Detailed Land and Rights Negotiations Tracker
Category 1
Book of Reference plot number¹ | Description of land and rights requested³ | Party Name | Nature of Interest | Agent / Representative⁶ | Summary of Negotiations | Heads of Terms agreed Summary Progress to Date Green = Likely to be completed Yellow = Potential Delay Red = Delay Blue = Completed or not required | Option agreed Summary Progress to Date Green = Likely to be completed Yellow = Potential Delay Red = Delay Blue = Completed or not required | Last Updated [DD/MM/YYYY]
B4-51, B4-52, B4-54, B4-55, B4-57, B4-58, B4-59, B4-60, B4-62, B4-63, B4-64, B4-65, B4-66, B4-67, B4-69, B4-70, B4-71, B4-72, B4-78, B4-84, B4-85, B5-3, B5-4, B5-8, B5-9, B5-10 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Albert Edwin Mark Slator, Howard Marshall Jones | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant has issued a chaser letter regarding the Heads of Terms to the Affected Person(s) in March 2026. | Ongoing | No | 2026-03-20
B5-26, B5-27 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure | Andrea Jane Rhodes, Stephen Frank Rhodes | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2026. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2026. The Applicant has issued a update letter in regard to those identified within the Order Limits but who are not subject to apparatus on or over their property, to discuss how the Scheme may impact the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
A7-13, A7-15, A7-25, A7-29, A7-30, A7-31, A7-32 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Andrew Martin King, Elizabeth Mary McRoberts, Frederick David King | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant has issued a chaser letter regarding the Heads of Terms to the Affected Person(s) in March 2026. | Ongoing | No | 2026-03-20
B2-117, B2-122, B2-123, B2-125, B2-126, B2-128 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Andrew Pearce | Occupier/Tenant | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since May 2025. The Applicant remains engaged with the freehold owner of the land for the rights required for the scheme. | N/A | N/A | 2026-03-20
A6-1 | Class 5 - Temporary Access for Construction | Anne Parker, John Malcolm Messenger | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information since February 2026. The Applicant has issued a update letter in regard to those identified within the Order Limits but who are not subject to apparatus on or over their property, to discuss how the Scheme may impact the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
B4-23, B4-27 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning | Beryl Holden, Tony Holden | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information since February 2026. The Applicant has issued a update letter in regard to those identified within the Order Limits but who are not subject to apparatus on or over their property, to discuss how the Scheme may impact the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
B5-10, B5-11 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure | Cameron Robert Whitworth, Jutta Whitworth-Biehler | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information since February 2025. The Applicant has issued a update letter in regard to those identified within the Order Limits but who are not subject to apparatus on or over their property, to discuss how the Scheme may impact the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
B3-91, B3-95, B3-96, B3-98, B3-99, B3-100, B3-101, B3-102, B3-103, B3-105, B3-107, B3-108, B3-110, B3-117 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Carlton James Lane | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant remains engaged with the Affected Person(s) on the Heads of Terms in January 2026. The Applicant remains engaged with the Affected Person(s) on the Head of Terms and is in discussion about how the scheme and its impacts in March 2026. | Ongoing | No | 2026-03-20
A5-24, A6-4, A7-2, A7-3, A7-4, A7-43, A7-5, A9-1, A9-9 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 5 - Temporary Access for Construction | Carol Rosemary Grundy | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant has issued a chaser letter regarding the Heads of Terms to the Affected Person(s) in March 2026. | Ongoing | No | 2026-03-20
B2-82, B2-83, B2-93 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Carole Ann Yule, John Andrew Yule | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant has issued a Request for Information (RFI) to capture any changes in land ownership information and an engagement letter to discuss how the Scheme impacts the Affected Person(s) in March 2026. The Applicant has issued a update letter in regard to those identified within the Order Limits but who are not subject to apparatus on or over their property, to discuss how the Scheme may impact the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
A6-4, A7-11 | Class 5 - Temporary Access for Construction | Catherine Mary Pease, Susan Elizabeth Shaw | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information since February 2026. The Applicant has issued a update letter in regard to those identified within the Order Limits but who are not subject to apparatus on or over their property, to discuss how the Scheme may impact the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
A1-10, A1-11, A1-3, A1-5, A1-7, A1-9 | Class 1 - Compulsory Acquisition of Land Class 3 - Compulsory Acquisition of Rights - Underground Cable System Class 5 - Temporary Access for Construction | Christine Elizabeth Branton, Walter David Branton | Owner | Rowley Barclay (Brown & Co) | The Applicant remains engaged with the Agent and the Affected Person(s) and negotiations of the Option agreement are advanced as of January 2026. | Agreed | Ongoing | 2026-03-20
B3-59, B3-102, B3-103, B3-104, B3-108, B3-109, B3-110, B3-111, B3-112, B3-113, B3-114, B3-115, B3-116, B3-117, B3-118, B3-119, B3-120, B3-121, B3-122, B3-124 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Christopher Stephen Dring, Stephen Walter Dring, W Dring And Sons Limited | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant has issued a chaser letter regarding the Heads of Terms to the Affected Person(s) in March 2026. | Ongoing | No | 2026-03-20
B3-2, B3-12, B3-16, B3-17, B3-20, B3-23, B3-24, B3-35, B3-37, B3-38, B3-39, B3-40, B3-41, B3-42, B3-43, B3-44, B3-45, B3-46 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Christopher William Wright, Holt William Myers | Owner | Richard Start ((R. Longstaff & Co LLP), (Chairman of Land Interest Group) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant is engaged with the Agent of the Affected Person(s) and as part of the Land Interest Group in March 2026. | Ongoing | No | 2026-03-20
A4-7, A4-8 | Class 1 - Compulsory Acquisition of Land Class 3 - Compulsory Acquisition of Rights - Underground Cable System | Clayton Hatton Banks | Owner | Tim Atkinson (Brown & Co) / Simon Thompson | Option for lease completed. | Agreed | Agreed | 2026-03-20
B2-63, B2-64 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 5 - Temporary Access for Construction | Clive Stewart Harvey, Tamra Louise Gadd | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant has received a response to their survey access request in March 2025. The Applicant has issued a update letter in regard to those identified within the Order Limits but who are not subject to apparatus on or over their property, to discuss how the Scheme may impact the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
A9-10, A9-21, A9-22, A9-25, A9-28, A9-33, A9-34, A9-35, A9-39, A9-40, A9-42 | Class 1 - Compulsory Acquisition of Land Class 3 - Compulsory Acquisition of Rights - Underground Cable System Class 5 - Temporary Access for Construction | Colin Boor | Owner | Tabner (Cheffins) | The Applicant remains engaged with the Agent and the Affected Person(s) and negotiations of the Option agreement are advanced as of January 2026. | Agreed | Ongoing | 2026-03-20
A1-5 | Class 1 - Compulsory Acquisition of Land | Crowland Charity Trustees | Owner | Robbie Longstaff (R. Longstaff & Co LLP) | The Applicant remains engaged with the Agent and the Affected Person(s) and negotiations of the Heads of Terms are advance as of January 2026. | Ongoing | No | 2026-03-20
B4-6, B4-7, B4-10, B4-12, B4-13, B4-14, B4-15, B4-16, B4-17, B4-18, B4-19, B4-20, B4-21 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | David Fletcher | Occupier/Tenant | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since April 2025. The Applicant has received a response to their Request for Information (RFI) and survey access request in April 2025. The Applicant remains engaged with the freehold owner of the land for the rights required for the scheme. | N/A | N/A | 2026-03-20
B3-85 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure | Dorothy Janet Bowers | Owner | Richard Start ((R. Longstaff & Co LLP), (Chairman of Land Interest Group) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant has issued a chaser letter regarding the Heads of Terms to the Affected Person(s) in March 2026. | Ongoing | No | 2026-03-20
B3-117, B3-121, B3-123, B3-124, B3-67, B3-70, B3-71, B3-72, B3-73, B3-74, B3-75, B3-76, B3-78, B3-79, B3-83, B3-84 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Dorothy Janet Bowers, Kenneth Reuben Bowers, Martin Bowers, Melvyn Kenneth Bowers | Owner | Richard Start ((R. Longstaff & Co LLP), (Chairman of Land Interest Group) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant is engaged with the Agent for Melvyn Kenneth Bowers in regards to the Heads of Terms and is awaiting feedback in March 2026. This agent is also part of the Land Interest Group. The Applicant has issued a chaser letter regarding the Heads of Terms to Dorothy Janet Bowers, Kenneth Reuben Bowers and Martin Bowers Affected Person(s) in March 2026. | Ongoing | No | 2026-03-20
B3-91, B3-93, B3-97 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Emily Rose Wint, Sam Mark Reeves | Owner | Richard Start ((R. Longstaff & Co LLP), (Chairman of Land Interest Group) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant is engaged with the Agent of the Affected Person(s) in regards to the Heads of Terms in March 2026. This agent is also part of the Land Interest Group. | Ongoing | No | 2026-03-20
A6-4, A7-1 | Class 5 - Temporary Access for Construction | Frances Mary Glendinning, Neil John Elisha | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information in March 2026. The Applicant has issued a update letter in regard to those identified within the Order Limits but who are not subject to apparatus on or over their property, to discuss how the Scheme may impact the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
B4-61, B4-63, B4-69, B4-71, B4-72, B4-73, B4-74, B4-77, B4-78, B4-80, B4-84 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Freshlinc Group Limited | Owner | Richard Start ((R. Longstaff & Co LLP), (Chairman of Land Interest Group) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant is engaged with the Agent of the Affected Person(s) in regards to the Heads of Terms in February 2026. This agent is also part of the Land Interest Group. | Ongoing | No | 2026-03-20
B2-109, B2-110, B2-111, B2-112, B2-114, B2-115, B2-116, B2-118, B2-119, B2-120, B3-31, B3-34, B5-5, B5-12, B5-13, B5-14, B5-16, B5-18, B5-19, B5-20, B5-21, B5-23, B5-27 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | G. H. Myers Limited | Owner | Richard Start ((R. Longstaff & Co LLP), (Chairman of Land Interest Group) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant is engaged with the Agent of the Affected Person(s) in regards to the Heads of Terms in February 2026. This agent is also part of the Land Interest Group. | Ongoing | No | 2026-03-20
A11-3, A11-4, A11-5, A11-7, A11-8, A11-9, A11-12, A11-13, A11-16, A11-19, A11-20, A11-21, A12-2, A12-6, A12-9, A12-14, A12-16, A12-21, A12-22, A12-23, A12-24, A9-10, A9-12, A9-15, A9-20, A9-21, A9-25, A9-26, A9-27, A9-29, A9-30, A9-31, A9-33, A9-34, A9-37, A9-38, A9-41 | Class 1 - Compulsory Acquisition of Land Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 3 - Compulsory Acquisition of Rights - Underground Cable System Class 5 - Temporary Access for Construction | George Frederick Sly, Malcolm Sly | Owner | Nick Green (Savills LLP) | Option for lease completed. | Agreed | Agreed | 2026-03-20
A7-5, A7-9, A7-12, A7-13, A7-15 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 5 - Temporary Access for Construction | George Goose | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant has issued a chaser letter regarding the Heads of Terms to the Affected Person(s) in March 2026. | Ongoing | No | 2026-03-20
B4-85 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 5 - Temporary Access for Construction | George Hay & Sons Limited | Occupier/Tenant | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant has been engaged regarding survey access since March 2025. The Applicant remains engaged with the freehold owner of the land for the rights required for the scheme. | N/A | N/A | 2026-03-20
B1-24, B1-25, B1-26, B1-27, B1-28, B1-30, B1-31, B1-32, B1-33, B1-34, B1-35, B1-36, B1-38, B1-39, B1-40, B1-43, B1-45, B1-46, B1-49, B1-50, B1-55, B1-56 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Gerald Arthur Biggs | Owner | Richard Start ((R. Longstaff & Co LLP), (Chairman of Land Interest Group) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant has issued Heads of Terms to the Agent and the Affected Person(s) in March 2026. The Applicant is engaged with the Agent of the Affected Person(s) in regards to the Heads of Terms in March 2026. This agent is also part of the Land Interest Group. | N/A | N/A | 2026-03-20
A9-6, A9-7, A9-9, A9-11, A9-13 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 5 - Temporary Access for Construction | Gloria Mary Read | Owner | Richard Start ((R. Longstaff & Co LLP), (Chairman of Land Interest Group) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant is engaged with the Agent of the Affected Person(s) in regards to the Heads of Terms in March 2026. This agent is also part of the Land Interest Group. The Applicant has been informed of a future change in Landownership and is seeking confirmation of the new owner and any tenants. | Ongoing | No | 2026-03-20
B4-85 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 5 - Temporary Access for Construction | GT4 Auto Repair Services | Occupier/Tenant | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information since May 2025. No response has been received. The Applicant remains engaged with the freehold owner of the land for the rights required for the scheme. | N/A | N/A | 2026-03-20
A11-3, A11-7, A11-12, A11-13, A11-19, A11-21, A12-6, A12-23, A9-12, A9-26, A9-27, A9-31, A9-37, A9-38 | Class 1 - Compulsory Acquisition of Land Class 5 - Temporary Access for Construction | H Sly and Sons Limited | Owner | N/A | The Applicant has been corresponding with the affected persons since May 2025. The Applicant has not entered into negotiations with the occupier of the identified plots, as an option agreement has been exchanged with the freeholders who are the owners of this company and occupy the land. The Applicant has completed an option agreement with the freehold owner of the land for the rights required for the scheme. | N/A | N/A | 2026-03-20
B2-50, B2-52, B2-54, B2-55, B2-56, B2-57, B2-58, B2-59, B2-60, B2-61, B2-62, B2-63, B2-65, B2-66, B2-67, B2-68, B2-69, B2-71, B2-72, B2-73, B2-75, B2-76, B2-77, B2-79, B2-80, B2-81, B2-84, B2-85, B2-86 | Class 1 - Compulsory Acquisition of Land Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 3 - Compulsory Acquisition of Rights - Underground Cable System Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Holmes And Hemmant Limited | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since April 2025. The Applicant has received a response to their Request for Information (RFI) and survey access request in March - May 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in February 2026. The Applicant has issued a chaser letter regarding the Heads of Terms to the Affected Person(s) in March 2026. | Ongoing | No | 2026-03-20
B3-31, B3-34, B4-83, B5-1, B5-5, B5-7, B5-11, B5-12, B5-13, B5-14, B5-15, B5-19, B5-27 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 5 - Temporary Access for Construction | Holt William Myers | Owner | Richard Start ((R. Longstaff & Co LLP), (Chairman of Land Interest Group) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant is engaged with the Agent of the Affected Person(s) and as part of the Land Interest Group in March 2026. | Ongoing | No | 2026-03-20
B5-26, B5-27, B5-28 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure | Ian Fred Pennington, Jennifer Anne Pennington | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2026. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in February 2026. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information in March 2026. The Applicant remains engaged with the Affected Person(s) in regards to the Head of Terms in March 2026. | Ongoing | No | 2026-03-20
A7-25, A7-26, A7-28, A7-30, A9-11 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | J. H. Grundy (Farms) Limited | Occupier/Tenant | Robbie Longstaff (R. Longstaff & Co LLP) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant remains engaged with the freehold owner of the land for the rights required for the scheme. | N/A | N/A | 2026-03-20
B4-1, B4-2, B4-3, B4-8, B4-9, B4-11 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | J. L. Farms Limited | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant has issued a chaser letter regarding the Heads of Terms to the Affected Person(s) in March 2026. | Ongoing | No | 2026-03-20
A1-12, A3-8, A3-9, A3-11, A3-15, A3-16, A3-17, A3-19, A3-21, A3-23, A3-24, A3-26, A3-27, A3-28, A4-1, A4-2, A4-3, A4-4, A4-8, A4-9, A4-10, A4-11, A5-1, A5-2, A5-6, A5-11, B1-6, B1-7, B1-9, B1-10, B1-11, B1-12, B1-13, B1-14, B1-15, B1-16, B1-18, B1-20 | Class 1 - Compulsory Acquisition of Land Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 3 - Compulsory Acquisition of Rights - Underground Cable System Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | J. W. E. Banks Limited | Owner | Tim Atkinson (Brown & Co) / Simon Thompson | Option for lease completed. | Agreed | Agreed | 2026-03-20
A3-11, A3-23, A3-25 | Class 3 - Compulsory Acquisition of Rights - Underground Cable System Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Jason Charles Thame | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information since February 2026. The Applicant has issued a update letter in regard to those identified within the Order Limits but who are not subject to apparatus on or over their property, to discuss how the Scheme may impact the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
A7-15, A7-18, A7-20, A7-21, A7-38, A7-39 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Jean Mary Cottam, Victor Ronald Cottam | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since Febbruary 2025. The Applicant has received a response to their Request for Information (RFI) and survey access request in March 2025. The Applicant has issued a update letter in regard to those identified within the Order Limits but who are not subject to apparatus on or over their property, to discuss how the Scheme may impact the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
B4-28, B4-37 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning | John Albert Gibson | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant has issued a update letter in regard to those identified within the Order Limits but who are not subject to apparatus on or over their property, to discuss how the Scheme may impact the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
B5-27, B5-30 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure | John Grant (Donington) | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2026. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2026. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in February 2026. The Applicant has issued a chaser letter regarding the Heads of Terms to the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
A9-28, A9-30, A9-39, A9-40 | Class 1 - Compulsory Acquisition of Land Class 5 - Temporary Access for Construction | Judith Anne Basford | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant has issued a update letter in regard to those identified within the Order Limits but who are not subject to apparatus on or over their property, to discuss how the Scheme may impact the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
B2-87, B2-88, B2-89, B2-90, B2-91, B2-92, B2-93, B2-94, B2-96, B2-97, B2-98, B2-100, B2-101, B2-102, B2-103, B2-105 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Julian Michael Smith, Leon Victor Smith | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant has issued a chaser letter regarding the Heads of Terms to the Affected Person(s) in March 2026. | Ongoing | No | 2026-03-20
A7-38, A7-39, A7-40, A7-42, A7-44, A7-45 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 5 - Temporary Access for Construction | Keith Hall | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant has issued a chaser letter regarding the Heads of Terms to the Affected Person(s) in March 2026. | Ongoing | No | 2026-03-20
A3-28, A4-12, A5-1, A5-2, A5-4, A5-6, A5-7, A5-8, A5-9, A5-10, A5-11, A5-12, A5-13, A5-14, A5-15, A5-16, A5-18, A5-19, A5-20 | Class 1 - Compulsory Acquisition of Land Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Kenneth Edward King, Michael Harold Speed Sly, Pamela Marigold Sly | Owner | Rowley Barclay (Brown & Co) | Option for lease completed. | Agreed | Agreed | 2026-03-20
B1-24, B1-26, B1-28, B1-31, B1-32, B1-33, B1-38, B1-39, B1-45, B1-55 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | L & D Flowers Limited | Occupier/Tenant | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant has been engaged regarding survey access since April 2025. The Applicant remains engaged with the freehold owner of the land for the rights required for the scheme. | N/A | N/A | 2026-03-20
A1-7, A3-1, A3-10, A3-11, A3-12, A3-13, A3-14, A3-15, A3-19, A3-2, A3-3, A3-4, A3-5, A3-6, A3-7, A3-23, A3-28, A4-1, A4-2, A4-3, A4-5, A5-2, A5-6, A5-11, A5-24, A6-3, A6-4, A7-3, A7-5, A7-13, A7-15, A7-21, A7-31, A7-32, A7-34, A7-38, A7-39, A7-40, A7-42, A7-43, A7-48, A7-49, A8-1, A8-5, A8-6, A8-8, A8-9, A9-1, A9-6, A9-7, A9-10, A9-20, A9-21, A9-25, A9-30, A9-34, A9-41, A10-1, A11-5, A11-8, A11-16, A12-9, A12-15, A12-16, A12-18, A12-19, A12-21, A12-25, B1-1, B1-2, B1-29, B1-37, B1-41, B1-47, B1-48, B1-61, B1-65, B1-66, B1-68, B1-69, B1-70, B1-71, B2-2, B2-5, B2-9, B2-11, B2-13, B2-18, B2-20, B2-23, B2-45, B2-52, B2-93, B2-94, B2-100, B2-114, B2-120, B2-121, B2-127, B2-135, B3-1, B3-2, B3-7, B3-8, B3-29, B3-30, B3-32, B3-33, B3-35, B3-36, B3-37, B3-39, B3-40, B3-46, B3-56, B3-68, B3-81, B3-82, B3-87, B3-88a, B3-91, B3-106, B3-111, B3-117, B3-124, B4-4, B4-5, B4-6, B4-7, B4-9, B4-10, B4-11, B4-12, B4-13, B4-14, B4-15, B4-16, B4-17, B4-18, B4-19, B4-20, B4-21, B4-22, B4-24, B4-26, B4-27, B4-29, B4-30, B4-31, B4-32, B4-33, B4-34, B4-35, B4-38, B4-39, B4-43, B4-57, B4-58, B4-59, B4-60, B4-63, B4-67, B4-83, B4-84, B4-85, B4-86, B5-2, B5-13, B5-19, B5-27 | Class 1 - Compulsory Acquisition of Land Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 3 - Compulsory Acquisition of Rights - Underground Cable System Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Lincolnshire County Council | Owner | Rebecca Mardall (Savills PLC) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant has issued a chaser letter regarding the Heads of Terms to the Affected Person(s) in March 2026. | Ongoing | No | 2026-03-20
B1-72, B1-73, B2-1, B2-3, B2-6, B2-8, B2-16, B2-17, B2-19, B2-21, B2-28, B4-27, B4-32, B4-33, B4-34, B4-36, B4-37, B4-40, B4-42, B4-44, B4-45, B4-49, B4-50, B4-55, B4-56, B4-69, B4-75, B4-76, B4-77, B4-79, B4-80, B4-81, B4-83, B4-86, B4-87, B5-1, B5-2, B5-7, B5-22 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Lincolnshire Field Products Limited | Owner | Richard Start ((R. Longstaff & Co LLP), (Chairman of Land Interest Group) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant is engaged with the Agent of the Affected Person(s) in regards to the Heads of Terms in February 2026. This agent is also part of the Land Interest Group. | Ongoing | No | 2026-03-20
B2-24, B2-27, B2-30, B2-31, B2-32, B2-33, B2-37, B2-38, B2-39, B2-41, B2-42, B2-43, B2-46, B2-47, B2-90, B2-96, B2-97, B2-98, B2-101, B2-102 | Class 1 - Compulsory Acquisition of Land Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 3 - Compulsory Acquisition of Rights - Underground Cable System Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | M L Smith & Sons Limited | Occupier/Tenant | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant has been engaged regarding survey access since February 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information in February 2026. The Applicant remains engaged with the freehold owner of the land for the rights required for the scheme. | N/A | N/A | 2026-03-20
A4-12, A5-19 | Class 1 - Compulsory Acquisition of Land | M. S. Smith Ltd | Owner | N/A | The Applicant has been corresponding with the affected persons since April 2025. The Applicant has not entered into negotiations with the occupier of the identified plots, as the option agreement with freeholder provides for vacant possession to be provided. The Applicant issued a Request for information (RFI) to capture any changes in land ownership information in February 2026. The Applicant has completed an option agreement with the freehold owner of the land for the rights required for the scheme. | N/A | N/A | 2026-03-20
A7-50, A9-6, A9-7 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 5 - Temporary Access for Construction | Marie Louise Cole, Richard Arhur Cole | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant has issued a chaser letter regarding the Heads of Terms to the Affected Person(s) in March 2026. | Ongoing | No | 2026-03-20
A3-25 | Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Markham Charles Barns Limited | Occupier/Tenant | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information in February 2026. The Applicant remains engaged with the freehold owner of the land for the rights required for the scheme. | N/A | N/A | 2026-03-20
B4-24, B4-27 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning | Martin Stewart Payne | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information in February 2026. The Applicant has issued a update letter in regard to those identified within the Order Limits but who are not subject to apparatus on or over their property, to discuss how the Scheme may impact the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
A7-41, A7-42, A7-45, A7-46 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Mary Rosalind Bull, Vincent Arthur James Bull | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant has issued a update letter in regard to those identified within the Order Limits but who are not subject to apparatus on or over their property, to discuss how the Scheme may impact the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
B1-51, B1-52, B1-53, B1-54, B1-57, B1-59, B1-60, B1-61, B1-62, B1-63, B1-64, B1-65, B1-66, B1-67, B1-69, B1-71 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Maureen Biggs, Roland Leslie Biggs | Owner | Robbie Longstaff (R. Longstaff & Co LLP) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant has issued a chaser letter regarding the Heads of Terms to the Affected Person(s) in March 2026. | Ongoing | No | 2026-03-20
B3-106, B3-61, B3-62, B3-63, B3-64, B3-65, B3-66, B3-85, B3-88, B3-88b, B3-89, B3-92 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Melvyn Kenneth Bowers | Owner | Richard Start ((R. Longstaff & Co LLP), (Chairman of Land Interest Group) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant is engaged with the Agent for Melvyn Kenneth Bowers in regards to the Heads of Terms and is awaiting feedback in March 2026. This agent is also part of the Land Interest Group. | Ongoing | No | 2026-03-20
B1-70, B2-10, B2-12, B2-13, B2-14, B2-15, B2-4, B2-7, B2-9, B2-44, B2-51 | Class 1 - Compulsory Acquisition of Land Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Michael Peter Truluck | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant has issued a update letter in regard to those identified within the Order Limits but who are not subject to apparatus on or over their property, to discuss how the Scheme may impact the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
B2-72, B2-73, B2-74, B2-75, B2-76, B2-77, B2-80, B2-81, B2-83, B2-85, B2-86, B2-87, B2-88, B2-89, B2-93, B2-116, B2-117, B2-119, B2-121, B2-122, B2-123, B2-124, B2-125, B2-126, B2-127, B2-128, B2-129, B2-130, B2-132, B2-133 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Moulton Harrox Educational Foundation (Thomas Henry Charlton, Dennis John Grimwood, William John Speechley, John Michael Atkin, Timothy Barker, Tom Bray, David Mawby, Rosemary Biggadyke, Robin Buck, Ann Willingham, Paul Winn) | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant has issued a chaser letter regarding the Heads of Terms to the Affected Person(s) in March 2026. | Ongoing | No | 2026-03-20
B2-20, B2-22, B2-23, B2-24, B2-25, B2-26, B2-27, B2-29, B2-30, B2-31, B2-32, B2-33, B2-34, B2-35, B2-36, B2-37, B2-38, B2-39, B2-41, B2-42, B2-43, B2-45, B2-46, B2-47, B2-72, B2-73, B2-75, B2-77, B2-81, B2-85, B2-86, B2-87, B2-88, B2-89, B2-93, B2-116, B2-117, B2-119, B2-121, B2-122, B2-123, B2-124, B2-125, B2-126, B2-127, B2-128, B2-129, B2-130, B2-132, B2-133 | Class 1 - Compulsory Acquisition of Land Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 3 - Compulsory Acquisition of Rights - Underground Cable System Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Moulton Poor Land Trust (Thomas Henry Charlton Jnr, Thomas Henry Charlton Snr, John Thomas Biggadike, Derek Thorpe, Harry Dean, Robert Oldershaw, Owen Thompson, David Buck, Alex Martin, Thomas Henry Charlton, Dennis John Grimwood, John Thomas Biggadyke) | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant has issued a chaser letter regarding the Heads of Terms to the Affected Person(s) in March 2026. | Ongoing | No | 2026-03-20
B4-85 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure | Mulini Exhibition Displays & Services Limited | Occupier/Tenant | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information since February 2025. The Applicant remains engaged with the freehold owner of the land for the rights required for the scheme. | N/A | N/A | 2026-03-20
A11-10, A11-8, A12-9 | Class 1 - Compulsory Acquisition of Land Class 3 - Compulsory Acquisition of Rights - Underground Cable System Class 5 - Temporary Access for Construction | Normon Grundy & Son Limited | Owner | Richard Start, Alice Peach (R. Longstaff & Co LLP) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant has issued an engagement letter to discuss how the Scheme impacts the Affected Person(s) in March 2026 | N/A | N/A | 2026-03-20
A1-3, A1-4, A1-12, A3-1, A3-3, A3-4, A3-5, A3-6, A3-7, A3-8, A3-9, A3-10, A3-14, A3-24, A3-26, A3-28, A4-5, A4-8, A4-9, A4-10, A4-11, A4-12, A5-1, A5-2, A5-4, A5-6, A5-8, A5-10, A5-11, A5-12, A5-15, A5-18, A5-19, A5-20 | Class 1 - Compulsory Acquisition of Land Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 3 - Compulsory Acquisition of Rights - Underground Cable System Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | North Level District Internal Drainage Board | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant has issued a chaser letter regarding the Heads of Terms to the Affected Person(s) in March 2026. | Ongoing | No | 2026-03-20
A7-50 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure | P K & M Grummitt | Occupier/Tenant | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since April - June 2025. The Applicant remains engaged with the freehold owner of the land for the rights required for the scheme. | N/A | N/A | 2026-03-20
B1-66, B1-68, B1-69, B1-71, B1-72, B1-73, B2-1, B2-2, B2-3, B2-5, B2-6, B2-8, B2-9, B2-10, B2-11, B2-12, B2-15, B2-16, B2-17, B2-18, B2-19, B2-20, B2-21, B2-22, B2-24, B2-25, B2-26, B2-27, B2-28, B2-29, B2-30, B2-31, B2-32, B2-33 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | P.E.D.C Limited | Owner | Caroline Wardle (CWC) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant is engaged with Agent and the Affected Person(s) in regards to the Heads of Terms in February 2026. | Ongoing | No | 2026-03-20
A7-15, A7-21, A7-25, A7-28, A7-30, A7-32, A7-34 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Richard Grundy, Susan Jennifer Grundy, Tom Richard Grundy, MK SSAS Trustees Limited | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant has issued a chaser letter regarding the Heads of Terms to the Affected Person(s) in March 2026. | Ongoing | No | 2026-03-20
A12-9, A12-13 | Class 1 - Compulsory Acquisition of Land Class 5 - Temporary Access for Construction | Robert Charles Laming | Owner | Mary Suttle (Roythornes) | The Applicant remains engaged with the Agent and the Affected Person(s) and negotiations of the Option agreement are advance as of January 2026. | Agreed | Ongoing | 2026-03-20
B2-127, B2-129, B2-130, B2-131, B2-132, B2-133, B2-134, B2-135, B2-136, B2-137, B3-1, B3-2, B3-3, B3-4, B3-5, B3-6, B3-8, B3-9, B3-10, B3-11, B3-13, B3-14, B3-15, B3-18, B3-19, B3-21, B3-22, B3-25, B3-26, B3-27, B3-29, B3-32, B3-35, B3-46, B3-47, B3-48, B3-49, B3-51, B3-52, B3-55, B3-56, B3-58, B3-68, B3-77, B3-89, B3-90, B3-94 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Robert Simon Earl | Owner | Elizabeth Allen (Elizabeth Allen Land Agents Limited) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant has issued a chaser letter regarding the Heads of Terms to the Affected Person(s) in March 2026. | Ongoing | No | 2026-03-20
B4-41, B4-46, B4-50, B4-56, B4-69, B4-73, B4-74, B4-79, B4-86 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Robin Hancox, Tessa Jane Hancox | Owner | Archie Read, Daniel Jobe (Brown & Co) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant has issued a update letter in regard to those identified within the Order Limits but who are not subject to apparatus on or over their property, to discuss how the Scheme may impact the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
B3-2, B3-12, B3-16, B3-17, B3-20, B3-23, B3-24, B3-35, B3-37, B3-38, B3-39, B3-40, B3-41, B3-42, B3-43, B3-44, B3-45, B3-46 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Roythornes Trustees Limited | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant has issued a chaser letter regarding the Heads of Terms to the Affected Person(s) in March 2026. | Ongoing | No | 2026-03-20
B1-15, B1-16, B1-17, B1-18, B1-19, B1-20, B1-22, B1-23, B1-28, B1-30, B1-31, B1-32, B1-33, B1-34, B1-35, B1-36, B1-38, B1-45, B1-46, B1-49, B1-50, B1-51, B1-53, B1-55, B1-56, B1-61, B2-103, B2-104, B2-105, B2-106, B2-107, B2-108, B2-109, B2-111, B2-114 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | S. Halgarth Limited | Owner | Richard Start ((R. Longstaff & Co LLP), (Chairman of Land Interest Group) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant is engaged with the Agent of the Affected Person(s) in regards to the Heads of Terms in March 2026. This agent is also part of the Land Interest Group. The Applicant has been informed of a future change in Landownership and is seeking confirmation of the new owner and any tenants. | Ongoing | No | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Shaun Bernard Robert Login, Stewart Rex Login | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information in February 2026. The Applicant has issued a update letter in regard to those identified within the Order Limits but who are not subject to apparatus on or over their property, to discuss how the Scheme may impact the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
B4-55, B4-62, B4-64, B4-65, B4-78, B4-84, B4-85, B5-3, B5-4, B5-6, B5-8, B5-9 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Slator Bros (Farms) Limited | Owner | Sam Booth (Hub Rural) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. | Ongoing | No | 2026-03-20
A7-43, A8-2 | Class 5 - Temporary Access for Construction | South Holland District Council | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information in March 2026. The Applicant has issued a update letter in regard to those identified within the Order Limits but who are not subject to apparatus on or over their property, to discuss how the Scheme may impact the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
A10-1, A11-2, A11-3, A11-4, A11-5, A11-7, A11-8, A11-9, A11-10, A11-13, A11-16, A11-18, A11-20, A12-4, A12-5, A12-6, A12-7, A12-8, A12-9, A12-10, A12-13, A12-14, A12-15, A12-16, A12-17, A12-18, A12-19, A12-21, A12-22, A12-23, A12-24, A12-25, A3-13, A3-15, A3-16, A3-21, A3-22, A5-24, A6-4, A7-3, A7-16, A7-17, A7-18, A7-19, A7-20, A7-27, A7-32, A7-35, A7-36, A7-43, A7-45, A7-47, A7-49, A7-5, A8-6, A8-9, A9-1, A9-5, A9-6, A9-7, A9-9, A9-10, A9-13, A9-14, A9-15, A9-18, A9-22, A9-25, A9-26, A9-28, A9-29, A9-30, A9-31, A9-32, A9-33, A9-34, A9-37, A9-38, A9-40, A9-41, B1-2, B1-15, B1-16, B1-18, B1-20, B1-21, B1-24, B1-25, B1-27, B1-3, B1-30, B1-34, B1-38, B1-4, B1-40, B1-42, B1-43, B1-44, B1-46, B1-5, B1-6, B1-7, B1-8, B1-9, B1-51, B1-53, B1-54, B1-59, B1-60, B1-61, B1-62, B1-66, B1-69, B1-70, B1-71, B1-73, B2-1, B2-2, B2-4, B2-9, B2-13, B2-14, B2-16, B2-18, B2-19, B2-20, B2-21, B2-22, B2-24, B2-25, B2-40, B2-44, B2-45, B2-5, B2-50, B2-51, B2-52, B2-56, B2-63, B2-65, B2-7, B2-70, B2-74, B2-78, B2-8, B2-83, B2-87, B2-88, B2-89, B2-93, B2-94, B2-95, B2-98, B2-99, B2-100, B2-103, B2-105, B2-109, B2-111, B2-113, B2-114, B2-116, B2-119, B2-120, B2-121, B2-124, B2-127, B2-129, B2-130, B2-132, B2-133, B2-135, B3-1, B3-2, B3-5, B3-6, B3-7, B3-8, B3-14, B3-16, B3-17, B3-20, B3-23, B3-24, B3-28, B3-29, B3-30, B3-38, B3-42, B3-46, B3-50, B3-53, B3-54, B3-56, B3-57, B3-58, B3-60, B3-62, B3-64, B3-65, B3-66, B3-67, B3-68, B3-69, B3-70, B3-71, B3-72, B3-73, B3-74, B3-75, B3-76, B3-77, B3-80, B3-81, B3-82, B3-86, B3-87, B3-89, B3-94, B3-102, B3-103, B3-104, B3-108, B3-109, B3-110, B3-111, B3-112, B3-113, B3-115, B3-117, B3-118, B3-119, B3-12, B3-120, B3-121, B3-124, B4-1, B4-3, B4-6, B4-8, B4-9, B4-11, B4-13, B4-14, B4-16, B4-17, B4-18, B4-27, B4-31, B4-33, B4-35, B4-37, B4-38, B4-39, B4-43, B4-44, B4-47, B4-52, B4-53, B4-59, B4-60, B4-61, B4-68, B4-69, B4-71, B4-72, B4-73, B4-74, B4-75, B4-76, B4-79, B4-81, B4-83, B4-85, B4-86, B4-87, B5-2, B5-3, B5-7, B5-8, B5-10, B5-11, B5-12, B5-13, B5-14, B5-19, B5-22, B5-27, B5-28 | Class 1 - Compulsory Acquisition of Land Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 3 - Compulsory Acquisition of Rights - Underground Cable System Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | South Holland Internal Drainage Board | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant remains engaged with the Agent and the Affected Person(s) in regards to the Head of Terms in March 2026. | Ongoing | No | 2026-03-20
B3-88, B3-88a, B3-88b, B3-89, B3-92, B3-94 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Spalding Rectory Feoffees | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information in February 2026. The Applicant has issued Heads of Terms to the Agent and the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
A7-18, A7-20 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Stancer Brothers Limited | Occupier/Tenant | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant has received a response to their Request for Information (RFI) confirming the affected person(s) Interest in March 2025. The Applicant remains engaged with the freehold owner of the land for the rights required for the scheme. | N/A | N/A | 2026-03-20
A9-7, A9-13, A9-14 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 5 - Temporary Access for Construction | The Executor for the Estate of Jonathan Henry Dean (Jonathan Henry Dean) | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued a Request for information (RFI) to capture any changes in land ownership information February 2026. A response was recieved from Mr Baker confirming that Jonathan Dean is now deceased. The Applicant is engaged in trying to find the successor to Mr Dean. | N/A | N/A | 2026-03-20
B3-2, B3-7, B3-8, B3-10, B3-11, B3-14, B3-15, B3-16, B3-18, B3-19, B3-21, B3-23, B3-26, B3-27, B3-28, B3-29, B3-30 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | The Master Fellows And Scholars Of The College Of Saint John The Evangelist In The University Of Cambridge | Owner | John Wootton, Felix Jebb (Savills) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant remains engaged with the Agent and the Affected Person(s) in regards to the Head of Terms in March 2026. | Ongoing | No | 2026-03-20
B3-61, B3-62, B3-63, B3-64, B3-65, B3-66 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | The Official Custodian For Charities | Owner | R. Longstaff & Co LLP | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant has issued a update letter in regard to those identified within the Order Limits but who are not subject to apparatus on or over their property, to discuss how the Scheme may impact the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
B2-20, B2-22, B2-23, B2-24, B2-25, B2-26, B2-27, B2-29, B2-30, B2-31, B2-32, B2-33, B2-34, B2-35, B2-36, B2-37, B2-38, B2-39, B2-41, B2-42, B2-43, B2-45, B2-46, B2-47, B2-72, B2-73, B2-75, B2-77, B2-81, B2-85, B2-86, B2-87, B2-88, B2-89 | Class 1 - Compulsory Acquisition of Land Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 3 - Compulsory Acquisition of Rights - Underground Cable System Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | The Poors Lands Moulton Charity (Thomas Henry Charlton Jnr, Thomas Henry Charlton Snr, Derek Thorpe, Robert Oldershaw, Owen Thompson, David Buck, Alex Martin, David John Grimwood, John Thomas Biggadike, John Thomas Biggadyke) | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant has issued a chaser letter regarding the Heads of Terms to the Affected Person(s) in March 2026. | Ongoing | No | 2026-03-20
A9-35, A9-39 | Class 1 - Compulsory Acquisition of Land | Timothy Boor, N.M. Boor and Sons | Occupier/Tenant | N/A | The Applicant has been corresponding with the affected persons since February 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant remains engaged with the freehold owner of the land for the rights required for the scheme. | N/A | N/A | 2026-03-20
B1-42 | Class 4 - Permanent Access for Construction, Operation and Decommissioning | Trevor John Tyrrell | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information in February 2026. The Applicant has issued a update letter in regard to those identified within the Order Limits but who are not subject to apparatus on or over their property, to discuss how the Scheme may impact the Affected Person(s) in March 2026. | N/A | N/A | 2026-03-20
B1-52, B1-57, B1-59, B1-60, B1-62, B1-63, B1-64, B1-67 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Walter David Branton | Occupier/Tenant | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant remains engaged with the Affected Person(s) around land the occupy in the grid connection corridor since February 2026. The Applicant remains engaged with the freehold owner of the land for the rights required for the scheme. | N/A | N/A | 2026-03-20
B4-35, B4-40, B4-49, B4-50, B4-52, B4-56, B4-69, B4-79, B4-86 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning | Wool Hall Investments Limited | Owner | N/A | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant issued Heads of Terms to the Agent and the Affected Person(s) in January 2026. The Applicant remains engaged with the Agent and the Affected Person(s) in regards to the Head of Terms in March 2026. | Ongoing | No | 2026-03-20
1 Plot number from the Book of Reference 2 Description of land and rights requested from the Book of Reference including restrictive covenants 2 (cont'd) Powers are also sought for the use of the subordinate rights to that principal right. This means, for example that where a plot refers to Class 1, powers to obtain all other classes of rights are also sought for that plot. This is to enable the undertaker to seek less extensive rights or interests where appropriate (such as the use of temporary possession powers for construction, or the use of easements or restrictive covenants instead of full acquisition of land). 3 & 4 A person is within category 1 if the applicant, after making diligent inquiry, knows that the person is an owner, lessee, tenant (whatever the tenancy period) or occupier of the land, see section 57 (1) of the Planning Act 2008 5 Person or organisation representing the interests of the affected person(s) - enter N/A if the affected person(s) are representing themselves 6 Narrative on negotiations to date 7 Status of Heads of Terms agreement(s) 8 Status of Option agreement(s) 9 Date of the last update

## Other Interests
Meridian Solar Farm Detailed Land and Rights Negotiations Tracker
Other Interests
Book of Reference plot number¹ | Description of land and rights requested³ | Party Name | Nature of Interest | Agent / Representative⁶ | Summary of Negotiations | Heads of Terms agreed Summary Progress to Date Green = Likely to be completed Yellow = Potential Delay Red = Delay Blue = Completed or not required | Option agreed Summary Progress to Date Green = Likely to be completed Yellow = Potential Delay Red = Delay Blue = Completed or not required | Last Updated [DD/MM/YYYY]
A6-4 | Class 5 - Temporary Access for Construction | Abnash Kaur Mcnally | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Adam Brand | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-9 | Class 5 - Temporary Access for Construction | Alison Paula Cooper, Gareth Stephen Cooper | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Amanda Heidi Worley, Melvyn Richard Worley | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4 | Class 5 - Temporary Access for Construction | Andrew John Cook, Kim Heather Coward | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Angela Margaret Brown, Clive Brown | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Anthony Curtis, Susan Ann Lantz | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4 | Class 5 - Temporary Access for Construction | Anthony John Harris, Janet Harris | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Anthony Leslie Brooks, Barbara Anne Brooks | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Arthur William David Ramm, Cressy Ann Ramm | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-39 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 5 - Temporary Access for Construction | Audrey May Ivatt | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4 | Class 5 - Temporary Access for Construction | Barry Mark Hodges, Jane Sybil Hodges | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-9 | Class 5 - Temporary Access for Construction | Ben Robert Gale, Carol Gale, Robert Stuart Gale | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Brian Frederick Stokes, Shirley Margaret Stokes | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A9-10 | Class 5 - Temporary Access for Construction | Brian Paul, Frederick Wakefield, George Johnson, John Loweth, Raymond Morris | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A9-10 | Class 5 - Temporary Access for Construction | Brian Samuel Scott Morton, Wendy Jane Morton | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-9 | Class 5 - Temporary Access for Construction | Bridgette-Diane Elston, Michael David Elston | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4 | Class 5 - Temporary Access for Construction | Carol Dorothy Hibbert | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Christine Brown | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4, A7-5 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 5 - Temporary Access for Construction | Colin Martin Gill | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Colin Richard Hatter, Margaret Benzie Hatter | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | David Graham Hitchens, Jacqueline Ann Hitchens | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | David Michael Hemmant | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4 | Class 5 - Temporary Access for Construction | Dawn-Marie Clarke, Simon David Clarke | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-9 | Class 5 - Temporary Access for Construction | Eileen Kelly, James Dennis Kelly | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4, A7-5 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 5 - Temporary Access for Construction | Elizabeth Ann Coles, Roger Michael Coles | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-5 | Class 5 - Temporary Access for Construction | Elizabeth Jane Picking, Gary Terence Picking | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4, A7-5 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 5 - Temporary Access for Construction | Emma Jayne Turczyn, Roger Jeffrey Matthews | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-9, A10-1 | Class 5 - Temporary Access for Construction | Emma Victoria Gale, Lee Leonard Horwood | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-5, A8-8, A8-9 | Class 5 - Temporary Access for Construction | Francis Herbert Fowler, Gerald Martin Fowler, Janet Mary Fowler | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Frederick Nathaniel Green | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-38 | Class 5 - Temporary Access for Construction | Frederick Stanley Watts, Laurence Drew Beeken | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-6 | Class 5 - Temporary Access for Construction | Gedney Hill Estate Charity | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Georgina Margaret Smith | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-49 | Class 5 - Temporary Access for Construction | Grace Loraine Young | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-9, A10-1 | Class 5 - Temporary Access for Construction | Helen Elizabeth Huyton | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-8 | Class 5 - Temporary Access for Construction | Hema Satdev Russell, Peter Robert Russell | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Hilary Clare Pavitt, Simon Lee Pavitt | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
B1-69, B1-70 | Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Hilary Hayes, Michael Alan Hayes | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-48, A7-49 | Class 5 - Temporary Access for Construction | Horizon Agricultural Machinery Limited | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-38 | Class 5 - Temporary Access for Construction | Ian Robert Morris, Leigh Morris | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4, A7-5 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 5 - Temporary Access for Construction | Ivan James Congreve | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Ivan Matthew Musgrove, Teresa Ann Musgrove | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-5 | Class 5 - Temporary Access for Construction | Jacqueline Anne Kastle, Paul Rolf Kastle | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4 | Class 5 - Temporary Access for Construction | James Alexander Donald, Lauren Elisse Neal | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-13 | Class 5 - Temporary Access for Construction | James Fennelow, Linda Hazel Wright | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4 | Class 5 - Temporary Access for Construction | James William Davis, Samantha Jane Howard | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-6, A8-8 | Class 5 - Temporary Access for Construction | Jane Winifred Geerlings, Petrus Maria Gysbertus Geerlings | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-5 | Class 5 - Temporary Access for Construction | Janet Pauline Harris | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Janet Susan Macdonald | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4, A7-5 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 5 - Temporary Access for Construction | Jean Margaret Coles, Maxwell John Coles, Robert Paul Mansfield, Trudy Mansfield | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A9-10 | Class 5 - Temporary Access for Construction | Jeffery Victor Ling, Kay Mary Ling | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Jennifer Suzanne Newton | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Jillian Carol Gavaghan, Neville Owen Gavaghan | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
B1-61 | Class 4 - Permanent Access for Construction, Operation and Decommissioning | Joanne Ball | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A9-10 | Class 5 - Temporary Access for Construction | Jonathan Boor | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-6, A8-8 | Class 5 - Temporary Access for Construction | Jules Vincent | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Kevin Andrew Cousins, Pamela Cathrine Bayly | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Komalar Vijayakumar | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4 | Class 5 - Temporary Access for Construction | Kristina Sophia Sturgeon, Terry Sturgeon | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4 | Class 5 - Temporary Access for Construction | Kyle Edward Gorf, Pauline Frances Harris Gorf | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-5, A8-6 | Class 5 - Temporary Access for Construction | Laurence Michael Tremayne, Malcolm Douglas Tremayne, Michael Douglas Tremayne, Oliver Thomas Tremayne | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4, A7-5 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 5 - Temporary Access for Construction | LG Design And Build Limited | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-34 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Linda Mary Wapples, Sydney Fred Wapples | Owner | Tracy Gillespie (Hix and Son) | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
B4-22 | Class 5 - Temporary Access for Construction | Lowlands Nursery Limited | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-8 | Class 5 - Temporary Access for Construction | Lynda Jane Meina | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4 | Class 5 - Temporary Access for Construction | Marek Clues, Stacey Clues | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A5-2 | Class 5 - Temporary Access for Construction | Mark Anthony Blackwell | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-9 | Class 5 - Temporary Access for Construction | Mark Robert Bingham, Peter William Bingham, Richard Paul Bingham | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4 | Class 5 - Temporary Access for Construction | Maureen Isabel Powley, Pamela Margaret Ivatt | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Michael Brian Crump, Sandra Crump | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4, A7-5 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 5 - Temporary Access for Construction | Michelle Louise Palmer, Troy Michael Palmer | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A9-10 | Class 5 - Temporary Access for Construction | Nicola Jane Singh, Stuart Christopher Winterton | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-42 | Class 5 - Temporary Access for Construction | Nicola Langley-Stevens, Richard Langley-Stevens | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-31 | Class 5 - Temporary Access for Construction | Patricia Anne Burchnall | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Patricia Johnson, Sidney Brian Johnson | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4 | Class 5 - Temporary Access for Construction | Paul Adrian Wilkinson, Rachel Mary Wilkinson | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-8 | Class 5 - Temporary Access for Construction | Paul Alexander Redgate, Samantha Jane Redgate | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-5 | Class 5 - Temporary Access for Construction | Paul Pulford | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4 | Class 5 - Temporary Access for Construction | Pauline Angela French, Tony Robert Goodwin | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Penelope Susanne Brown | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-9 | Class 5 - Temporary Access for Construction | Philip Whitwell | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Philippa Kim Mcguire | Owner | Alice Peach (R. Longstaff & Co LLP) | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A9-10 | Class 5 - Temporary Access for Construction | R J Wright (2006) Limited | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Renata Godlevskaja, Valerij Necipuruk | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-9, A10-1 | Class 5 - Temporary Access for Construction | Richard Lee O'Neill | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Richard Paul Tring, Sarah Louise James | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Richard Stokes | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Rosanna Maria Sly | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-6 | Class 5 - Temporary Access for Construction | Sally Jayne Malkin, Tony Malkin | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4 | Class 5 - Temporary Access for Construction | Sarah Louise Wright, Stephen Paul Wright | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Shaun Bernard Robert Login, Stewart Rex Login | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A12-16, A12-21, A12-22 | Class 1 - Compulsory Acquisition of Land Class 3 - Compulsory Acquisition of Rights - Underground Cable System Class 5 - Temporary Access for Construction | Sheila Alice Woodberry | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil and drain is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil and drain carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Simon Edward Wicks | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Simon Edward Wicks, Sylvia Joan Wicks | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
B1-61 | Class 4 - Permanent Access for Construction, Operation and Decommissioning | Simon James Ball | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4, A7-5 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 5 - Temporary Access for Construction | Stuart David Maurice Walters, Wendy Jean Walters | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-13 | Class 5 - Temporary Access for Construction | Sylvia Teresa Downer, Robin Sidney Joiner | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
B1-61 | Class 4 - Permanent Access for Construction, Operation and Decommissioning | T M Trustees Limited | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A6-4, A7-5 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 5 - Temporary Access for Construction | The Owner (Avalon, Green Bank, Whaplode Drove) | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-49 | Class 5 - Temporary Access for Construction | The Owner (Red Brick House, Holbeach Drove Gate, Holbeach Drove) | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A12-18 | Class 5 - Temporary Access for Construction | Thomas Christopher Robert Rose | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A9-21 | Class 5 - Temporary Access for Construction | Timothy Gyles Henderson | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
B3-39 | Class 5 - Temporary Access for Construction | Timothy Henry Hardy | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A9-10 | Class 5 - Temporary Access for Construction | Timothy Robert William Boor | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A7-43 | Class 5 - Temporary Access for Construction | Tomasz Marcin Biegaj | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-6 | Class 5 - Temporary Access for Construction | Tony Charles Rowell | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A9-10 | Class 5 - Temporary Access for Construction | William Peter Mills | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-5, A8-9 | Class 5 - Temporary Access for Construction | You Garden Limited | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
A8-9 | Class 5 - Temporary Access for Construction | Zoe Louise Cummings | Owner | N/A | The Applicant has not entered into negotiations for the acquisition of rights over the identified plots, as the interests have been determined under a legal presumption whereby ownership of the subsoil is attributed to the adjoining landowner. In light of this presumption, and given that the subsoil carries no market value, confers no use or enjoyment to the landowner, and is not prejudiced by the proposed development, the Applicant does not consider it necessary to engage in negotiations with these interests. | N/A | N/A | 2026-03-20
1 Plot number from the Book of Reference 2 Description of land and rights requested from the Book of Reference including restrictive covenants 2 (cont'd) Powers are also sought for the use of the subordinate rights to that principal right. This means, for example that where a plot refers to Class 1, powers to obtain all other classes of rights are also sought for that plot. This is to enable the undertaker to seek less extensive rights or interests where appropriate (such as the use of temporary possession powers for construction, or the use of easements or restrictive covenants instead of full acquisition of land). 3 & 4 A person is within category 1 if the applicant, after making diligent inquiry, knows that the person is an owner, lessee, tenant (whatever the tenancy period) or occupier of the land, see section 57 (1) of the Planning Act 2008 - For 'Other Interest' those identified as Category 1 are those who have been identified as owners of the ad medium filum (subsoil) or a riparian interest (half width of drain). 5 Person or organisation representing the interests of the affected person(s) - enter N/A if the affected person(s) are representing themselves 6 Narrative on negotiations to date 7 Status of Heads of Terms agreement(s) 8 Status of Option agreement(s) 9 Date of the last update

## Statutory Undertakers
Meridian Solar Farm Detailed Land and Rights Negotiations Tracker
Statutory Undertakers
Book of Reference plot number¹ | Description of land and rights requested³ | Party Name | Nature of Interest | Agent / Representative⁶ | Is the affected person a statutory undertaker and is the land operational (Select from drop down) | Protective provision status (Select from drop down list) | Side agreements (Select from drop down list) | Summary of Negotiations | Heads of Terms agreed Summary Progress to Date Green = Likely to be completed Yellow = Potential Delay Red = Delay Blue = Completed or not required | Option agreed Summary Progress to Date Green = Likely to be completed Yellow = Potential Delay Red = Delay Blue = Completed or not required | Last Updated [DD/MM/YYYY]
A1-4, A1-9, B1-61, B1-65, B1-66, B1-68, B1-69, B1-70, B1-71, B2-2, B2-5, B2-8, B2-9, B2-11, B2-16, B2-18, B2-19, B2-20, B2-21, B2-22, B2-23, B2-24, B2-30, B2-33, B2-34, B2-39, B2-41, B2-45, B2-48, B2-49, B2-50, B2-53, B2-56, B2-58, B2-61, B2-62, B2-83, B3-32, B3-33, B3-35, B3-36, B3-37, B3-39, B3-68, B3-81, B3-82, B3-87, B3-88a, B3-91, B3-117, B3-124, B4-22, B4-27, B4-29, B4-30, B4-32, B4-33, B4-38, B4-39, B4-40, B4-41, B4-42, B4-43, B4-44, B4-45, B4-46, B4-47, B4-49, B4-50, B4-51, B4-56, B4-58, B4-60, B4-63, B4-67, B4-85, B5-13, B5-19, B5-22, B5-26, B5-27 | Class 1 - Compulsory Acquisition of Land Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 3 - Compulsory Acquisition of Rights - Underground Cable System Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | Anglian Water Services Limited | Owner/Apparatus | N/A | ​​SU apparatus and operational rights​ | ​​PP Draft under discussion​ |  | The Applicant has been corresponding with Anglian Water ("AW") since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information in February 2025. The Applicant has received a response to their Request for Information (RFI) confirming AW's Interest in July 2025. The Applicant has reached out to discuss protective provisions with AW. AW have provided draft protective provisions to the Applicant's legal team for review and engagement is ongoing. | N/A | N/A | 2026-03-20
B1-59, B1-61, B1-69, B1-70, B2-2, B2-5, B2-9, B2-11, B2-18, B2-20, B2-23, B2-41, B2-58, B2-62, B2-83, B3-117, B3-120, B3-35, B3-37, B3-39, B3-40, B3-91, B4-22, B4-27, B4-28, B4-29, B4-30, B4-32, B4-33, B4-35, B4-38, B4-39, B4-43, B4-44, B4-56, B4-58, B4-60, B4-67, B5-13, B5-19, B5-22, B5-27, B5-28, B5-30 | Class 1 - Compulsory Acquisition of Land Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | BT Group plc | Rights/apparatus | N/A | ​​SU apparatus and operational rights​ | ​​PP Draft under discussion​ |  | The Applicant has been corresponding with BT Group plc ("BT") since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information in June 2025. The Applicant has reached out to discuss protective provisions with BT. BT have provided draft protective provisions to the Applicant's legal team for review and engagement is ongoing. | N/A | N/A | 2026-03-20
B4-22, B4-27, B4-29 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 5 - Temporary Access for Construction | Cadent Gas Limited | Rights/apparatus | N/A | ​​SU apparatus and operational rights​ | ​​PP Draft under discussion​ |  | The Applicant has been corresponding with Cadent Gas Limited ("Cadent Gas") since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information in April 2025. The Applicant has reached out to discuss protective provisions with Cadent Gas. Cadent Gas have provided draft protective provisions to the Applicant's legal team for review and engagement is ongoing. | N/A | N/A | 2026-03-20
A1-1, A1-2, A1-3, A1-9 | Class 1 - Compulsory Acquisition of Land | Environment Agency | Owner/Apparatus | N/A | SU land known operational | ​​PP Draft under discussion​ |  | The Applicant has been corresponding with Environment Agency ("EA") since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information in July 2025. The Applicant has reached out to discuss protective provisions with EA. EA have provided draft protective provisions to the Applicant's legal team for review and engagement is ongoing. | N/A | N/A | 2026-03-20
A12-23, A3-11, A3-19, A3-2, A3-23, A3-28, A3-3, A3-4, A3-5, A3-9, A4-10, A4-11, A4-12, A4-9, A5-11, A5-15, A5-16, A5-18, A5-19, A5-2, A5-20, A5-24, A5-6, A5-7, A5-8, A5-9, A6-4, A7-13, A7-16, A7-18, A7-20, A7-21, A7-26, A7-3, A7-31, A7-32, A7-34, A7-35, A7-37, A7-39, A7-40, A7-42, A7-43, A7-49, A7-5, A7-9, A8-9, A9-1, A9-10, A9-12, A9-20, A9-21, A9-26, A9-6, A9-7, B1-59, B1-65, B1-69, B1-73, B2-2, B2-4, B2-5, B2-12, B2-31, B2-33, B2-36, B2-37, B2-41, B2-43, B2-46, B2-47, B2-76, B2-78, B2-79, B2-81, B2-115, B2-116, B2-121, B2-125, B2-135, B2-136, B3-13, B3-14, B3-18, B3-19, B3-20, B3-23, B3-24, B3-25, B3-32, B3-35, B3-58, B3-62, B3-68, B3-69, B3-70, B3-88b, B3-89, B3-90, B3-93, B3-96, B3-99, B3-103, B3-107, B3-110, B3-112, B3-117, B3-118, B3-120, B3-121, B3-124, B4-22, B4-23, B4-25, B4-26, B4-27, B4-28, B4-30, B4-35, B4-37, B4-40, B4-41, B4-43, B4-44, B4-45, B4-46, B4-56, B4-85, B4-87, B5-3, B5-4, B5-6, B5-7, B5-8, B5-9, B5-10, B5-11, B5-12, B5-14, B5-28, B5-30 | Class 1 - Compulsory Acquisition of Land Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 3 - Compulsory Acquisition of Rights - Underground Cable System Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | National Grid Electricity Distribution (East Midlands) plc | Owner/Apparatus | N/A | SU land known operational, SU apparatus and operational rights | ​​PP Draft under discussion​ |  | The Applicant has been corresponding with National Grid Electricity Distribution (East Midlands) plc ("NGED East Midlands") since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information in March 2025. The Applicant has reached out to discuss protective provisions with NGED East Midlands. NGED East Midlands have provided draft protective provisions to the Applicant's legal team for review and engagement is ongoing. | N/A | N/A | 2026-03-20
B4-56, B4-77, B4-79, B4-80, B4-81, B4-84, B4-85, B4-86, B4-87, B5-5, B5-6, B5-8, B5-9, B5-12, B5-14, B5-15, B5-16, B5-20 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | National Grid Electricity Transmission plc | Owner/Apparatus | N/A | ​​SU apparatus and operational rights​ | ​​PP Draft under discussion​ |  | The Applicant has been corresponding with National Grid Electricity Distribution plc ("NGED") since 2025. The Applicant has reached out to discuss protective provisions with NGED. NGED have provided draft protective provisions to the Applicant's legal team for review and engagement is ongoing. | N/A | N/A | 2026-03-20
A1-3, A1-4, A1-12, A3-1, A3-3, A3-4, A3-5, A3-6, A3-7, A3-8, A3-9, A3-10, A3-14, A3-24, A3-26, A3-28, A4-5, A4-8, A4-9, A4-10, A4-11, A4-12, A5-1, A5-2, A5-4, A5-6, A5-8, A5-10, A5-11, A5-12, A5-15, A5-18, A5-19, A5-20 | Class 1 - Compulsory Acquisition of Land Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 3 - Compulsory Acquisition of Rights - Underground Cable System Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | North Level District Internal Drainage Board | Owner/Apparatus | N/A | SU land known operational, SU apparatus and operational rights | ​​PP Draft under discussion​ |  | The Applicant has been corresponding with North Level District Internal Drainage Board ("North Level") since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since March 2025. The Applicant has reached out to discuss protective provisions with North Level. North Level have provided draft protective provisions to the Applicant's legal team for review and engagement is ongoing. | N/A | N/A | 2026-03-20
A10-1, A11-2, A11-3, A11-4, A11-5, A11-7, A11-8, A11-9, A11-10, A11-13, A11-16, A11-18, A11-20, A12-4, A12-5, A12-6, A12-7, A12-8, A12-9, A12-10, A12-13, A12-14, A12-15, A12-16, A12-17, A12-18, A12-19, A12-21, A12-22, A12-23, A12-24, A12-25, A3-13, A3-15, A3-16, A3-21, A3-22, A5-24, A6-4, A7-3, A7-16, A7-17, A7-18, A7-19, A7-20, A7-27, A7-32, A7-35, A7-36, A7-43, A7-45, A7-47, A7-49, A7-5, A8-6, A8-9, A9-1, A9-5, A9-6, A9-7, A9-9, A9-10, A9-13, A9-14, A9-15, A9-18, A9-22, A9-25, A9-26, A9-28, A9-29, A9-30, A9-31, A9-32, A9-33, A9-34, A9-37, A9-38, A9-40, A9-41, B1-2, B1-15, B1-16, B1-18, B1-20, B1-21, B1-24, B1-25, B1-27, B1-3, B1-30, B1-34, B1-38, B1-4, B1-40, B1-42, B1-43, B1-44, B1-46, B1-5, B1-6, B1-7, B1-8, B1-9, B1-51, B1-53, B1-54, B1-59, B1-60, B1-61, B1-62, B1-66, B1-69, B1-70, B1-71, B1-73, B2-1, B2-2, B2-4, B2-9, B2-13, B2-14, B2-16, B2-18, B2-19, B2-20, B2-21, B2-22, B2-24, B2-25, B2-40, B2-44, B2-45, B2-5, B2-50, B2-51, B2-52, B2-56, B2-63, B2-65, B2-7, B2-70, B2-74, B2-78, B2-8, B2-83, B2-87, B2-88, B2-89, B2-93, B2-94, B2-95, B2-98, B2-99, B2-100, B2-103, B2-105, B2-109, B2-111, B2-113, B2-114, B2-116, B2-119, B2-120, B2-121, B2-124, B2-127, B2-129, B2-130, B2-132, B2-133, B2-135, B3-1, B3-2, B3-5, B3-6, B3-7, B3-8, B3-14, B3-16, B3-17, B3-20, B3-23, B3-24, B3-28, B3-29, B3-30, B3-38, B3-42, B3-46, B3-50, B3-53, B3-54, B3-56, B3-57, B3-58, B3-60, B3-62, B3-64, B3-65, B3-66, B3-67, B3-68, B3-69, B3-70, B3-71, B3-72, B3-73, B3-74, B3-75, B3-76, B3-77, B3-80, B3-81, B3-82, B3-86, B3-87, B3-89, B3-94, B3-102, B3-103, B3-104, B3-108, B3-109, B3-110, B3-111, B3-112, B3-113, B3-115, B3-117, B3-118, B3-119, B3-12, B3-120, B3-121, B3-124, B4-1, B4-3, B4-6, B4-8, B4-9, B4-11, B4-13, B4-14, B4-16, B4-17, B4-18, B4-27, B4-31, B4-33, B4-35, B4-37, B4-38, B4-39, B4-43, B4-44, B4-47, B4-52, B4-53, B4-59, B4-60, B4-61, B4-68, B4-69, B4-71, B4-72, B4-73, B4-74, B4-75, B4-76, B4-79, B4-81, B4-83, B4-85, B4-86, B4-87, B5-2, B5-3, B5-7, B5-8, B5-10, B5-11, B5-12, B5-13, B5-14, B5-19, B5-22, B5-27, B5-28 | Class 1 - Compulsory Acquisition of Land Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure Class 3 - Compulsory Acquisition of Rights - Underground Cable System Class 4 - Permanent Access for Construction, Operation and Decommissioning Class 5 - Temporary Access for Construction | South Holland Internal Drainage Board | Owner/Apparatus | N/A | SU land known operational, SU apparatus and operational rights | ​​PP Draft under discussion​ |  | The Applicant has been corresponding with South Holland Internal Drainage Board ("South Holland IDB") since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since March 2025. The Applicant has reached out to discuss protective provisions with South Holland IDB. South Holland IDB have provided draft protective provisions to the Applicant's legal team for review and engagement is ongoing. | N/A | N/A | 2026-03-20
B5-5, B5-14, B5-15, B5-16, B5-18, B5-19, B5-20, B5-21, B5-22 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure | Spalding Energy Company Limited | Owner/Apparatus | N/A | ​​SU apparatus and operational rights​ | ​​PP Draft under discussion​ |  | The Applicant has been corresponding with Spalding Energy Company Limited ("Spalding Energy") since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information since March 2025. The Applicant has received a response to their Request for Information (RFI) Spalding Energy in May 2025. The Applicant has reached out to discuss protective provisions with Spalding Energy. Spalding Energy have provided draft protective provisions to the Applicant's legal team for review and engagement is ongoing. | N/A | N/A | 2026-03-20
B5-5, B5-14, B5-16 | Class 2 - Compulsory Acquisition of Rights - Overhead Line and Associated Infrastructure | Spalding Energy Expansion Limited | Rights/apparatus | N/A | ​​SU apparatus and operational rights​ | ​​PP Draft under discussion​ |  | The Applicant has been corresponding with Spalding Energy Expansion Limited ("Spalding Energy Expansion") since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information since May 2025. The Applicant has reached out to discuss protective provisions with Spalding Energy Expansion. Spalding Energy Expansion have provided draft protective provisions to the Applicant's legal team for review and engagement is ongoing. | N/A | N/A | 2026-03-20
1 Plot number from the Book of Reference 2 Description of land and rights requested from the Book of Reference including restrictive covenants 2 (cont'd) Powers are also sought for the use of the subordinate rights to that principal right. This means, for example that where a plot refers to Class 1, powers to obtain all other classes of rights are also sought for that plot. This is to enable the undertaker to seek less extensive rights or interests where appropriate (such as the use of temporary possession powers for construction, or the use of easements or restrictive covenants instead of full acquisition of land). 3 & 4 A person is within category 1 if the applicant, after making diligent inquiry, knows that the person is an owner, lessee, tenant (whatever the tenancy period) or occupier of the land, see section 57 (1) of the Planning Act 2008 3 & 4 A person is within category 2 if the applicant, after making diligent inquiry knows that the person: interested in the land or has the power to sell or convey the land or to release the land, see section 57(20) of the Planning Act 2008 5 Person or organisation representing the interests of the affected person(s) - enter N/A if the affected person(s) are representing themselves 6 Narrative on negotiations to date 7 Status of Heads of Terms agreement(s) 8 Status of Option agreement(s) 9 Date of the last update

## Crown
Meridian Solar Farm Detailed Land and Rights Negotiations Tracker
Crown
Book of Reference plot number¹ | Description of land and rights requested³ | Party Name | Nature of Interest | Agent / Representative⁶ | Summary of Negotiations | Heads of Terms agreed Summary Progress to Date Green = Likely to be completed Yellow = Potential Delay Red = Delay Blue = Completed or not required | Option agreed Summary Progress to Date Green = Likely to be completed Yellow = Potential Delay Red = Delay Blue = Completed or not required | Last Updated [DD/MM/YYYY]
A11-10, A12-9 | Class 1 - Compulsory Acquisition of Land Class 5 - Temporary Access for Construction | The King's Most Excellent Majesty In Right Of His Crown | Owner | Alex Ireton (Carter Jonas) | The Applicant has been corresponding with the Affected Person since 2025. The Applicant issued a Request for Information (RFI) to capture any changes in land ownership information and has been engaged regarding survey access since February 2025. The Applicant remains engaged with the Agent and the Affected Person(s) to discuss the impact to their mine and minerals subsoil rights under the highway in the land and secure the necessary rights required for the scheme and confirm any concerns they may have in relation to the Scheme in February 2026. The Applicant has chased for a response regarding their interest and to discuss the necessary rights regard with the Crown in March 2026. | No | No | 2026-03-20
1 Plot number from the Book of Reference 2 Description of land and rights requested from the Book of Reference including restrictive covenants 2 (cont'd) Powers are also sought for the use of the subordinate rights to that principal right. This means, for example that where a plot refers to Class 1, powers to obtain all other classes of rights are also sought for that plot. This is to enable the undertaker to seek less extensive rights or interests where appropriate (such as the use of temporary possession powers for construction, or the use of easements or restrictive covenants instead of full acquisition of land). 3 & 4 A person is within category 1 if the applicant, after making diligent inquiry, knows that the person is an owner, lessee, tenant (whatever the tenancy period) or occupier of the land, see section 57 (1) of the Planning Act 2008 3 & 4 A person is within category 2 if the applicant, after making diligent inquiry knows that the person: interested in the land or has the power to sell or convey the land or to release the land, see section 57(20) of the Planning Act 2008 5 Person or organisation representing the interests of the affected person(s) - enter N/A if the affected person(s) are representing themselves 6 Narrative on negotiations to date 7 Status of Heads of Terms agreement(s) 8 Status of Option agreement(s) 9 Date of the last update