## Guide to the R&I Log
Introduction:
Natural England have created this Risk and Issues Spreadsheet to track progress of issues raised throughout the Examination for the Meridian Solar Project. Each issue has been assigned a Red, Amber, Yellow or Green risk rating, as defined below. This Risk and Issues Spreadsheet can be updated through Examination, with the rating updated at each deadline to clearly show progress made.
Risk Rating:
Red are those where there are fundamental concerns which it may not be possible to overcome in their current form.
Amber are those where further information is required to determine the effects of the project and allow the Examining Authority to properly undertake its task and or advise that further information is required on mitigation/compensation proposals in order to provide a sufficient degree of confidence as to their efficacy.
Yellow are those where Natural England does not agree with the Applicant’s position or approach. We would ideally like this to be addressed but are satisfied that for this particular project it is unlikely to make a material difference to our advice or the outcome of the decision-making process. However, we reserve the right to revise our opinion should further evidence be presented. It should be noted by interested parties that whilst these issues/comments are not raised as significant concerns in this instance, it should not be understood or inferred that Natural England would be of the same view in other cases or circumstances.
Green are those which have been successfully resolved (subject always to the appropriate requirements being adequately secured).
Additional information:
Natural England's key updated advice or requests for action are shown in Bold.
The spreadsheet contains filters to enable ease of viewing. For example, filtering column D1 ('Current RAG Status') allows the user to view only those issues which are marked as yellow, amber or red.

## R&I Log
Pre- App Ref | Relevant Reps Ref | Theme | Issue Summary | Current RAG Status | Natural England Comments - Relevant Representations (30/06/2026) | RAG Status Relevant Reps | Consultation, actions, progression at deadline 1 (22/09/2026) | RAG Status | Consultation, actions, progression | RAG Status | Consultation, actions, progression | RAG Status | Consultation, actions, progression | RAG Status
n/a | NE1 | Internationally Designated Sites | Identification of sites | Green | HRA Report [APP-217] section 3.3 sets out the screening area used and relevant sites identified for the assessment. NE considers that all relevant European Sites have been identified; agrees that consideration of Barnack Hills and Holes SAC and Orton Pit SAC is not necessary. | Green
NE1 | NE2 | Internationally Designated Sites | Baseline Data | Green | NE has agreed an evidence plan for the project’s HRA via our Discretionary Advice Service (DAS). This evidence plan is included in HRA Report [APP-217] Appendix 2. NE considers relevant desk data and survey has been carried out in order to inform the HRA. | Green
NE2 | NE3 | Internationally Designated Sites | IIWS Qualifying Species | Yellow | It is important to note that any wetland bird species would be considered to qualify for the Waterbird Assemblage (non-breeding) for The Wash. The HRA has included consideration for the overall waterbird assemblage feature; so NE raise no major concerns on this point. Ensure that any table listing species (eg primary Focal Species or Tables 3.2 of both Wintering Bird Survey Reports) acknowledges that any wetland bird would be considered an IIWS qualifying species for The Wash (especially if it is a record/observation from within typical range for The Wash). | Yellow | The Applicant has stated that the wintering bird report appendices will be updated for D1 to acknowledge that any wetland bird species would be considered an IIWS qualifying species for the wash. NE will review and provide an update on our position following a review of documents submitted by the Applicant at Deadline 1. | Yellow
NE4 | NE4 | Internationally Designated Sites | Impact Pathways Considered | Yellow | HRA Report [APP-217] Table 4, identifies relevant impact pathways based on the Site Improvement Plans, IRZ criteria and other known sensitivities. NE considers that all relevant impacts from the proposed development have been identified for further consideration in the screening assessment: - Impacts on Functionally Linked Land (FLL) - Direct impacts on individuals of qualifying species - Air pollution - Water pollution Whilst impacts to FLL have been considered, Table 4 should specifically reference noise and visual disturbance on birds using FLL; NE has made further comment on this at NE7. NE’s comments on the Stage 1 Screening Assessment for each impact pathway are set out below. | Yellow | The Applicant has stated that the HRA Report will be updated for Deadline 1 to address relevant points, including additional detail in Table 4 regarding impact pathways on FLL. NE will review and provide an update on our position following a review of documents submitted by the Applicant at Deadline 1. | Yellow
NE5 | NE5 | Internationally Designated Sites | Stage 1 – Impacts on Functionally Linked Land (FLL) – Ornithology Identification of FLL | Amber | HRA Report [APP-217] 4.4.3 to 4.4.10 discusses four areas the applicant has identified as FLL. These are also illustrated at HRA Figure 3. Whilst NE concurs that the 4 areas identified are likely to constitute functionally linked land, the method used to reach this conclusion, and to rule out any other areas of FLL within the order limits or in close proximity, is unclear. NE’s Section 42 Response stated: ‘NE advise that a clear assessment of potential functionally linked land within and adjacent to the site (within relevant disturbance distances, such as those set out by NatureScot3) should be presented in the ES. NE advise that where any SPA birds are recorded, this area should be considered as functionally linked land. It should then be assessed for the value of this land to the relevant SPA/Ramsar site(s). Key considerations include: • Is the number of birds recorded during survey or in desk study measurable against the SPA population (i.e. 1%)? Whilst NE have generally advised a 1% threshold, this is dependent on a number of factors and cannot be considered in isolation. • How regularly did this species use the area? • What is the conservation status and population trend for those species within the SPA? • How mobile are the species? • How much alternative habitat is available? • Did the birds use the site as refuge during harsh weather/high water events? • Can effective mitigation be provided to ensure the relevant populations are still adequately supported?' It is unclear where this assessment has taken place. Further information should be provided regarding the process used to identify areas of Functionally Linked Land. Justification should be provided as to why none of the order limits have been considered as FLL; where this is not possible, additional FLL should be included for assessment. | Amber | The Applicant has stated that the HRA Report will be updated for Deadline 1, including significant further information regarding the identification of FLL. NE will review and provide an update on our position following a review of documents submitted by the Applicant at Deadline 1. | Amber
NE9 | NE6 | Internationally Designated Sites | Stage 1 – Impacts on Functionally Linked Land (FLL) – Ornithology Direct Loss of FLL | Amber | HRA Report [APP-217] Paragraph 4.4.13 states: ‘The Scheme has been designed to take account of baseline ecological data and avoids loss of habitats within these potential areas of FLL, and incorporates buffer zones to minimise the risk of damage or disturbance. On the basis of the nature, scale and location of the Scheme, and noting that the Scheme would not result in direct land take within areas identified as potential functionally linked land (FLL), there is no plausible impact pathway by which the Scheme could result in a likely significant effect on qualifying features of The Wash and North Norfolk Coast SAC, The Wash SPA and Ramsar, or the Nene Washes SPA and Ramsar as a result of loss of FLL.’ The surveys and desk study results appear to indicate species of importance to the nearby designated sites within the proposed development area and so it is difficult to understand how there is no land-take in those areas that would affect FLL. Vantage Point Survey Report (APP-213) paragraph 4.4 states low numbers of Golden Plover were noted during nocturnal surveys. It is important to note that golden plover regularly split into smaller flocks during the night even when pre roosting behaviour involves a larger flock. As such a ‘core’ roosting area may be spread over several fields/ locations. This is similarly true for lapwing. It is also stated that that scheme design has been designed to take account of potential areas of FLL, but little further information is provided to explain where this has taken place. Alongside the information requested at NE5, further reasoning should be provided to justify the statement that there will be no direct land-take within FLL. Further information should be provided to demonstrate how survey results have been used to inform scheme design to avoid impacts to FLL. | Amber | The Applicant has stated that the HRA Report will be updated for Deadline 1, including significant further information regarding the identification & loss of FLL. NE will review and provide an update on our position following a review of documents submitted by the Applicant at Deadline 1. | Amber
NE10 | NE7 | Internationally Designated Sites | Stage 1 – Impacts on Functionally Linked Land (FLL) – Ornithology Noise and Visual Disturbance to FLL | Amber | There is no assessment of noise or visual disturbance impacts within the HRA. Regardless of any potential additional functionally linked land (See NE5), it is unclear how noise/disturbance impacts to the four identified areas of FLL have been screened out. Three of the four areas lie directly adjacent to the order limits; so noise and visual disturbance in these areas would be expected during construction and decommissioning. NE notes that Chapter 13, Noise and Vibration, ‘does not include the assessment of noise and vibration on ecological or heritage receptors’ (APP-064, paragraph 13.1.5). Where FLL is identified in proximity to the order limits, it may be appropriate to include this as a receptor in the Noise chapter, and/or for noise contours to be provided to inform the HRA. Chapter 9, Ecology and Biodiversity (APP-060) also makes limited assessment of noise and visual impacts to SPA birds. Little information is provided with regard to the buffer zones referenced at paragraph 4.4.13, for example, where they are, how large they are and what mitigating effect they may have concerning noise. Minor reference is made to the ‘further precautionary controls’ that are embedded within the CEMP and DEMP to mitigate impacts from noise and visual disturbance, however, these measures are limited to best practice construction measures, which are welcomed, but may not address impacts to specific sensitive ecological receptors (i.e. areas of functionally linked land directly adjacent to the order limits). No consideration has been given to the avoidance of the wintering period for the most disturbing construction activities. NE advises that Likely Significant Effects from disturbance to FLL should be screened in, with further assessment of noise and visual disturbance being provided within the Appropriate Assessment. Further information should also be provided regarding the embedded measures being relied upon to reduce impacts from Noise and Visual Disturbance. Any additional mitigation measures required to avoid noise/visual disturbance effects during construction and decommisisoning must be detailed in the oCEMP/oDEMP. | Amber | The Applicant has stated that the HRA Report will be updated for Deadline 1, including noise and Visual Disturbance being taken through to Appropriate Assessment stage, with further information on noise & visual disturbance & mitigation. NE will review and provide an update on our position following a review of documents submitted by the Applicant at Deadline 1. | Amber
n/a | NE8 | Internationally Designated Sites | Stage 1 – Impacts on Functionally Linked Land (FLL) – Ornithology Predator Shadows | Amber | HRA Report [APP-217] 4.4.17 discusses potential impacts from a perceived predator shadow. NE generally concurs with the rationale provided, although it should also be noted that species such as Golden Plover are known to avoid prominant field edges such as hedges (of any height) and avoid being within 100m or more of such features. This is likely to include the edges of fields containing solar panels, however, as the Solar PV is located within existing field boundaries, with existing boundary features, significant effects from a predator shadow effect are considered unlikely. NE note the routing of the cable route and OHL 200-300m from the Northern-most area of identified FLL, which is likely to avoid any such effects in this area. Nonetheless, further consideration of impacts from a predator shadow effect may be necessary should any additional FLL be identified in closer proximity to the Order Limits (see NE5). Further consideration of impacts via a predator shadow effect should be made where any additional FLL is identified. See NE5. | Amber | The Applicant has stated that the HRA Report will be updated for Deadline 1, including significant further information regarding the identification of FLL. NE will review and provide an update on our position following a review of documents submitted by the Applicant at Deadline 1. | Amber
n/a | NE9 | Internationally Designated Sites | Stage 1 – Impacts on FLL - Otter | Green | HRA Report [APP-217] 4.4.11 to 4.4.16 Discuss the use of the site and it’s surrounds by Otter, a qualifying feature of The Wash & North Norfolk Coast SAC. NE notes the identification of the River Welland and South Holland Main as part of Otter territories, but concurs with the applicant’s assessment that a likely significant effect on this species as a result of impacts to functionally linked land can be ruled out. The scheme design has ensured there is no direct loss of key functionally linked habitats along these watercourses, and embedded measures, such as those set out in CEMP Table 3-5 (APP-275, p40-41) for Otter and Water Vole, are likely to avoid any significant disturbance to the species. These include, buffering of watercourses, avoidance of night works & pre-construction survey. It is also acknowledged that the intervening distance between the SAC and the order limits is also significant; there is availability of alternative habitat within the catchment, which copudl be utilised during any temporary disturbance. NE welcomes acknowledgement that should any pre-construction survey show significant new evidence of Otter in areas required for the scheme, that a protected species licence would be required to proceed; and must be applied for in the usual way. This legislative requirement provides further certainty that significant effects could be avoided and/or mititgated effectively through the licencing regime. The CEMP & DEMP, containing embedded measures which will ensure avoidance of effects to Otter, are secured by DCO Requirements 12 and 21, respectively. | Green
NE8(a) | NE10 | Internationally Designated Sites | Stage 1 – Direct impacts to species – Ornithology (collision) | Green | HRA Report [APP-217] paragraphs 4.4.19 to 4.4.30 discuss the potential effects of collision. The data presented at Figure 4 and discussed at paragraph 4.4.22 is helpful, relating to desk study hotspots and movement corridors, however, with this figure being based solely upon desk based data, it does have significant limitations and should not be relied upon to draw any conclusions in isolation. The applicant has considered this data appropriately; it does provide helpful context, indicating that the grid connection route does not cross any major flight lines. It is welcomed that our previous advice has been taken on board with regard to collision risk modelling; understanding the limitations of this. It is welcomed that modelled outputs are not relied on in isolation to screen for likely significant effects (paragraph 4.4.23). A screening threshold of a modelled 1% change in baseline mortality is discussed at paragraph 4.4.24; NE would like to clarify that we do not endorse the use of any such screening thresholds. Our pre-app advice on this matter noted historic use of this threshold, but was clear that reliance on a threshold approach to screening out LSE is not recommended, owing to the uncertainties around modelling, particularly when concerning OHLs. Nonetheless, the applicant does go on to state that this ‘should not be relied on alone, given the limitations of using the collision risk model, but will be taken in the context of wider qualitative assessment’, which is welcomed. Table 5 sets out the modelling results, identifying Golden Plover as the only species with a predicted increase in mortality of over 1%. The Golden Plover population that over-winters on The Wash is of international importance and as such is considered to be a main component species within the Waterbird Assemblage.The Conservation Objective to maintain the population of this species therefore applies. NE therefore welcomes the consideration of Golden Plover and the statement that ‘it is reasonable to treat as a qualifying feature for consideration of likely significant effects’ at paragraph 4.4.26. Table 5 also illustrates a 0.79% increase in mortality for Whooper Swan. This species is not discussed at Stage 1 of the HRA. With this modelled risk, alongside significant flight durations of Whooper Swan being observed in the 10-25m range in the Vantage Point Surveys (APP-213), NE considers this to indicate Whooper Swan are at risk of collision from the scheme. As the collision risk impact pathway has been screened in due to the risk to Golden Plover, further consideration of Whooper Swan is unlikely to change the outcome of the stage 1 screening assessment, so NE raises no significant concern at this stage. It is also welcomed that Common Crane have been considered within the assessment. Despite an absence of survey data indicating Crane flights at collision height, Cranes were recorded in the area of the OHL, and the species is known to be able to fly at collision height and be susceptible to collision. They also fly in groups and there is potential for a whole group to collide at once. As such we welcome recognition that, a single collision would constitute a significant effect to this recently established population. Overall, NE concurs with the conclusion that LSE cannot be ruled out for Collision risk in relation to the Wash SPA/Ramsar and Nene Washes Ramsar. | Green
NE8(b) | NE11 | Internationally Designated Sites | Stage 1 – Direct impacts to species - Otter | Green | HRA Report [APP-217] 4.4.18 states that as a result of embedded measures within the CEMP & DEMP, no direct impacts are predicted for Otter. NE concurs with this conclusion & as set out at NE9, the general mitigation measures in the CEMP are considered suitable to avoid a significant effect on Otter associated with the Wash and North Norfolk Coast SAC. The CEMP & DEMP, containing embedded measures which will ensure avoidance of effects to Otter, are secured by DCO Requirements 12 and 21, respectively. | Green
NE8(c) | NE12 | Internationally Designated Sites | Stage 1 – Air Pollution | Unrated | Natural England has produced ‘Standard Advice for Air Quality Impacts in Nationally Significant Infrastructure Projects’ and have no bespoke comment to provide with regard to air quality impacts. | Unrated
NE8(d) | NE13 | Internationally Designated Sites | Stage 1 – Water Pollution | Green | HRA Report [APP-217] 4.4.39 to 4.4.42 discusses potential impacts from water pollution. It is concluded that due to the nature of the proposed works, and standard construction practices, no LSE is predicted. Both the oCEMP [APP-275] and oDEMP [APP-277] tables 3-6 and 3-7 include numerous best practice pollution prevention measures which are to be implemented during construction and decommissioning. Where these measures are implemented as planned, NE concurs with the conclusion that significant effects from water pollution during construction and decommissioning can be ruled out on this basis. It is also noted that these measures are considered best practice, and thus would not constitute mitigation measures specifically used to avoid an impacts upon a European site. NE also concurs that water pollution effects during operation are unlikely. The CEMP & DEMP, containing embedded measures which will ensure avoidance of effects via water pollution, are secured by DCO Requirements 12 and 21, respectively | Green
NE8(e) | NE14 | Internationally Designated Sites | Stage 1 - Screening Conclusions | Amber | NE concurs with all of the applicant’s stage 1 screening conclusions, with the exception of impacts on FLL for Ornithology (See items NE5-8). A summary of NE’s agreement with the Stage 1 Screening and Stage 2 Appropriate Assessment is included at Annex A of NE's Relevant Reps. | Amber | NE will review and provide an update on our position following a review of documents submitted by the Applicant at Deadline 1. | Amber
NE8(f) | NE15 | Internationally Designated Sites | Stage 2 - Direct impacts to species – Ornithology (collision) | Amber | HRA Report [APP-217] paragraphs 5.2.1 to 5.2.10 discuss collisison risk and mitigation considerations. The potential for undergrounding of the cable route has been considered by the applicant at Chapter 3. HRA paragraph 5.2.6 states that undergrounding of the route may have greater impacts to wintering birds foraging and roosting in the area. NE disagrees with this, and notes that whilst temporary impacts to wintering birds would be anticipated during construction of an underground cable, the overhead line introduces a permanent collision risk. Ultimately, the decision to use overhead cables instead of underground cables for the grid connection must be considered by the Secretary of State in line with NPS EN-5 paragraphs 2.9.25-26. Consideration has been given to the routing of the Overhead Cables, being sited to the east of the corridor to somewhat avoid the surveyed hotspots for Golden Plover (paragraph 5.2.5), but it is acknowledged this will not avoid the risk altogether and further mitigation is proposed in the form of line markers. The use of Line Markers to reduce collision risk is welcomed. NE concurs with the applicant’s conclusion regarding the two areas identified as having increased risk of collision for both Golden Plover and other higher collision risk for cranes, geese and swans, and that these areas should be fitted with line markers (illustrated at HRA Figure 5). Nonetheless, as the section between these two areas has not been subject to Vantage Point survey, NE recommends that a scheme of monitoring for collision should be undertaken once the scheme becomes operational. Should collision be reported, additional line markers should be considered. The monitoring scheme could be designed to mimic the VP survey effort undertaken. This would provide a direct comparison between the modelled collision risk and the actual collision risk, which would provide invaluable information to inform future projects’ collision risk assessments and modelling. The change line markers are likely to have on the modelling outputs has been shown at paragraph 5.2.8. It is acknowledged that the exact model of line marker to be used is yet to be determined. As a result, the use of the lowest (worst performing) risk reduction rate in the figures presented here is welcomed, in line with the precautionary approach. The detailed design of line markers, including model, frequency of use and exact locations, must be undertaken in consultation with Natural England. Commitment must be made for the detailed design of line markers, including choice of model, frequency of use and exact locations, to be undertaken in consultation with Natural England. Commitment should be made for a scheme of monitoring for collision along the length of the OHL to be undertaken during operation. NE recommends the detailed design of line marker deployment is secured within the DCO, including requirement for consultation with NE. For example at DCO Requirement 5 (Detailed Design Approval). Similarly, NE recommends a scheme of monitoring for collision is secured within the DCO. | Amber | The Applicant has stated that consultation with NE on the detailed design of Bird Diverters will be secured via an update to the Design Parameters Document at D1. NE will review and provide an update on our position following a review of documents submitted by the Applicant at Deadline 1. | Amber
NE12 | NE16 | Internationally Designated Sites | Stage 2 – Direct impacts to species – Ornithology (collision) Collision Risk Modelling | Yellow | Further detail regarding the collision risk modelling conducted has been provided by the applicant at Appendix 9-15 (APP-218). It is acknowledged that specific guidance on modelling of collision risk for onshore Overhead Lines is not currently available. The applicant has engaged positively with NE to inform their approach to this model. The general approach to the model, following the principles of the NatureScot onshore wind turbine model, is considered suitable; NE generally agrees with the approach taken to the overall assessment of collision risk, which has considered desk data, survey results, local expertise and modelling outputs. NE’s advice specific to the model is set out below: NE does not agree with the rationale provided for the use of the ‘Alignment Factor’, set out at paragraph 2.2.12 to 2.2.13 (APP-218). It is unclear how the discussed model has been parameterised to be made comparable with the scheme, nor de we consider there to be sufficient reason to assume that one model can inform the other to justify such a significant lowering of collision risk. Nonetheless, given the significant uncertainties inherent in the whole process, the model outputs have served their primary purpose to identify the high-risk species and locations. This information has then been considered ‘in the context of wider qualitative assessment’ within the HRA and mitigation applied appropriately. Thus, whilst Natural England does not agree with this alignment factor, we do not consider it would alter the outcome of the assessment in this instance. NE notes the use of species specific Avoidance Factors based on guidance published for onshore wind farms (paragraph 2.2.14), with an assumption of the lowest avoidance factor where data is limited. It is worth noting these factors are not purely estimates of the proportion of birds that will avoid an obstacle, but instead model correction factors that are specific to the wind turbine Band Collision Risk Model. Nonetheless, NE considers the approach taken to be suitable and based on the best available evidence. The Alignment Factor used in the model should be omitted, or further rationale and information regarding the parameters used in the model used to inform it could be provided. | Yellow | No Change. | Yellow
| NE17 | Internationally Designated Sites | Stage 2 – Incombination Assessment | Green | NE specifically notes the potential for additionality of impacts through collision risk with the Grimsby to Walpole and Weston Marsh to East Leicestershire (WMEL) projects, which both propose additional Overhead Lines in proximity to this scheme. It is acknowledged that both of these projects are yet to reach a stage in design where significant collision risk assessment or modelling has been undertaken, so a quantitative in-combination assessment is not possible at this stage. In-combination effects from collision from both the Meridian Solar Project and these two additional schemes will need to be considered quantitavely by these projects as they come forward. NE recommends that collision risk data associated with the Meridian project should be made available to the Grimsby to Walpole and WMEL projects to ensure they are able to carry out a full quantitative in-combination assessment. | Green
NE20 | NE18 | Internationally Designated Sites | Appropriate Assessment Conclusions | Amber | Overall, subject to the detailed design of line markers and monitoring of collision, NE concurs with the conclusions reached regarding Collision risk. However, it is advised that impacts to functionally linked land are considered within the Appropriate Assessment. A summary of NE’s agreement with the Stage 1 Screening and Stage 2 Appropriate Assessment is included at Annex A of NE's Relevant Reps. | Amber | NE will review and provide an update on our position following a review of documents submitted by the Applicant at Deadline 1. | Amber
n/a | NE19 | Nationally Designated Sites | Identification of Sites | Green | NE welcomes the extensive use of our Impact Risk Zones (IRZs) to identify potential impacts and considers all relevant SSSIs have been identified. NE welcomes the identification of all SSSIs as being of National Importance (Table 9-6). | Green
NE21 | NE20 | Nationally Designated Sites | Impact Assessment – Underpinning SSSIs | Green | NE welcomes that all relevant SSSIs which underpin European designations, even where these are beyond the relevant SSSI IRZs, have been identified and noted in Table 9-6 and scoped into further assessment in Table 9-13. NE has no further advice regarding potential impacts to The Wash SSSI, the Nene Washes SSSI and Baston Fen SSSI. The assessment of impacts to the qualifying features of the overlapping European designations is considered to cover any relevant impacts to the SSSIs’ notified features. See our advice regarding these sites at NE1-18. It is welcomed that impacts to the Unattributed IRZ (centroid TF 3499 1700) have been considered in the ES. As stated, this IRZ relates to potential Functionally Linked Land for features of The Wash and/or Nene Washes designations. Impacts to Functionally linked land have been captured for these designations within the assessment of impacts to the qualifying features of the overlapping European designations. No further sites or impacts pathways need to be reviewed as a result of this IRZ. | Green
n/a | NE21 | Nationally Designated Sites | Impact Assessment – Cowbit Wash | Green | NE concurs with the assessment of impacts to Cowbit Wash SSSI in Table 9-14 that there is no potential for effects beyond those via Air Quality. As noted at NE12, NE refers to our standard advice (See Annex B of NE's Relevant Reps) regarding Air Quality impacts from Traffic emissions and has no further comment at this stage. The CEMP is secured by DCO requirement 12; specifies the need for a dust management plan to be produced post-consent. | Green
NE22 | NE22 | Designated Landscapes | Designated Landscapes | Green | The proposed development is not located within, or within the setting of, any nationally designated landscapes. As a result, NE has no specific comments to make on the landscape implications of this development. For advice on wider landscape issues, NE refers to the local planning authorities and other local bodies. | Green
NE13 | NE23 | Protected Species Licencing | Water Vole Licencing Approach | Green | The Otter and Water Vole Report [APP-210] discusses the likely need for a protected species licence for impacts to ditches where water voles are present. This is due to the need for both improvements to existing crossing points and one new crossing point (PV-A-03). As set out at paragraph 5.4 of the Otter and Water Vole Report, NE has been in discussion with the applicant with regard to the licencing approach for Water Vole, and is in agreement with the proposal as it stands. Due to the nature of the CL31 licence , which is issued to an ecologist to act under a pre-approved set of rules, the proposed approach would not require an individual (site specific) A11 licence to be applied for. Hence, it was not considered necessary for the applicant to submit a draft licence application to NE or request a LoNI during the Pre-App period. Should pre-construction surveys indicate that the CL31 licence approach is no longer viable, then it may be necessary for a full A11 licence, to be applied for and issued prior to works starting. | Green
NE14 | NE24 | Protected Species Licencing | Other Protected Species Licencing | Green | No further licence need has been identified by the applicant. NE welcomes the approach taken to avoid impacts as much as possible in line with the mitigation hierarchy. As stated, where further pre-construction survey or detailed design reveals the need for any protected species licences from NE, further consultation will be required and these licences will need to be applied for in the usual manner. | Green
NE15 | NE25 | Protected Species Licencing | Disapplication of Legislation | Green | Draft DCO Part 2, section 4 (2) is clear that ‘this article does not relieve the undertaker of any requirement to obtain any permit or licence under any other legislation that may be required from time to time to authorise the operation of an electricity generating station or overhead electric lines’. NE welcomes this clarity and notes it will apply to any requirement for a protected species licence during operation of the scheme. | Green
NE16 | BMV1 | Soils and Best & Most Versatile Land | Scheme design and avoidance of BMV land | Green | It is welcomed that Chapter 3, Alternatives and Design Evolution (APP-054) includes Design Principle 6, to avoid infrastructure within Best and most versatile (BMV) land, with a preference for the lowest grade available for areas likely to host hard standing infrastructure, where practicable. This approach is in line with NPS EN3, paragraph 2.10.21. Agricultural Land Classification and type have also been considered by the applicant during site selection. The Site Selection Report (APP-264) paragraph 3.3.26 states ‘that there is no land of sufficient scale for a 750MW solar farm that is located within proximity to the PoC which does not have a high likelihood of BMV land, making complete avoidance of BMV agricultural land impossible for the Scheme’, which is noted. The Site Selection Report, paragraphs 3.4.5 to 3.4.14 then set out how the initial reconnaissance ALC survey, and then subsequent detailed level ALC suiveys, have been used to avoid infrastructure on the highest grade agricultural land. It is noted that areas initially graded as Grade 1 were removed from the development and proposed for ecological enhancements which retain the soil resource, however, following subsequent detailed ALC survey, large areas have been downgraded from grade 1 and infrastructure has been re-introduced. See items BMV2-8 for NE’s comments on the final ALC survey methods and findings. Nonetheless, it is noted in Chapter 5 (APP-056), paragraph 5.7.3 that over 69ha of Grade 1 and 2 agricultural land within Habitat Management Area 6 has been excluded from physical development and will be kept in arable use and managed to provide biodiversity benefits. This is welcomed. The intent to avoid the highest grade agricultural land for permanent elements of the development is clear within the ES, however it is noted that small areas of Grade 1 and 2 land are to be used for the Substation/BESS. Justification for this has been provided at paragraph 3.4.10 of the site selection report (APP-264): due to constraints relating to the routing of the cable corridor and competing constraints with alternative solutions. The Secretary of State should ensure that the applicant has put forward appropriate mitigation measures to minimise impacts on soils or soil resources and, as set out at NPS EN-3 paragraph 2.10.137, take into account the economic and other benefits of the best and most versatile agricultural land in their decision making. | Green
NE17 | BMV2 | Soils and Best & Most Versatile Land | ALC Survey Methodology – PV Area | Green | NE has worked with the applicant during the pre-application period to agree an ALC survey methodology for the project. Whilst NE always advises that the ALC survey be undertaken at a density of 1 auger boring per hectare across the full order limits, during discussions with the applicant it was agreed that their survey effort could be reduced to 1 auger boring per 2 hectares in areas to be used solely for environmental enhancements, which did not require any soil handling activities. It is welcomed that the remaining PV area was subject to ALC survey at a density of 1 auger boring per hectare. | Green
| BMV3 | Soils and Best & Most Versatile Land | ALC Survey Methodology – Cable Corridor | Yellow | It is always NE’s advice that an ALC survey of the full order limits should be carried out pre-consent, to inform avoidance of the highest quality land as far as practicable, ensure the ES assessment is based on robust evidence, and to inform the Soil Management Plan. The applicant has not undertaken ALC survey of the Grid Connection Corridor; in the absence of survey data, the applicant’s ability to avoid the highest quality land through scheme design has been limited. However, they have instead: - Committed to undertaking ALC survey of the cable route post-consent, to inform the final Soil Management Plan, and - Taken a worst-case scenario approach for the cable route within the ES, considering them to be entirely ALC Grades 1 and 2. Whilst NE’s advice remains that an ALC survey of the full order limits should be carried out pre-consent, in this instance it is considered unlikely to make a material difference to our advice or the outcome of the decision-making process. oSMP Section 3.1 discusses the requirement for post-consent ALC survey of the cable route. DCO Requirement 19 subsequently secures the development of the final Soil Management Plan substantially in accordance with the outline soil management plan. NE considers this to be suitably secured. | Yellow | No Change | Yellow
| BMV4 | Soils and Best & Most Versatile Land | ALC Survey Methodology – Incomplete Survey | Amber | Whilst it is appreciated a detailed ALC survey has now been completed across the PV areas. It is noted that 27.95ha of parcels A and D were inaccessible due to dense crops and vegetation (APP-172) and have not been resurveyed. In similar instances for Parcels C and D, these areas were subsequently re-surveyed (APP-173, para 3.3.2). NE understands that access restrictions mean 100% coverage is not always possible, however, further discussion is expected with regard to the exprapolation of data to inform the ES. In addition, 75.47ha of Parcels A & D have not been surveyed as a result of unexploded ordnance (UXO) risk. NE acknowledges the potential risks associated with UXO, however, with appropriate mitigation measures in place, we do not consider the potential for UXO to be a constraint to carrying out ALC surveys. Where there is an identified risk from UXO, the auger core and soil profile pit locations should be first cleared by a UXO specialist prior to the commencement of any intrusive works. Where there are indications that a location is unsuitable due to perceived UXO risk, auger and pit locations should be adjusted to a nearby suitable location. Unsurveyed areas should be subject to ALC survey where accessibility allows, even if this must be post-consent, to ensure the evidence is available to inform the final Soil Management Plan. Rationale should be provided for any remaining un-surveyed areas across the site. The oSMP, secured by DCO Requirement 19, must make clear commitment for the completion of the ALC dataset. | Amber | The Applicant has stated that a series of updates will be made to the oSMP and ES Chapter 5 regarding a commitment to ensure additional ALC survey is undertaken post-consent in areas that were inaccessible perviously. NE will review and provide an update on our position following a review of documents submitted by the Applicant at Deadline 1. | Amber
| BMV5 | Soils and Best & Most Versatile Land | ALC Survey Findings - Mapping | Amber | Following our comments with regard to Mapping of ALC grades at pre-application stage (APP-056, Table 5-3, 9th September 2025), the Applicant has presented both auger-by-auger point analysis and field average. NE continues to have concerns with the mapping of ALC grades across the order limits. As set out in the ALC Guidelines , ‘Land is graded and mapped without regard to present field boundaries, except where they coincide with permanent physical features’. NE notes the presentation of both auger point and field average ALC grading; acknowledges that a worst case scenario has been used to determine the significance of effects in table 5-15. However, whilst NE agrees that there may be isolated augers of differing ALC grades which would not be reasonably practicable to be managed in an isolated way (APP-173, para 3.5.2-3.5.4), and as such, it is not helpful to map isolated auger cores of differing ALC grades, we do not agree that a field average approach should be taken when mapping ALC grade. No attempt has been made to use or integrate existing data from the semi-detailed survey undertaken by Land Research Associates, nor is there any discussion regarding the Post 1988 ALC survey available for part of the site. It is acknowledged that the previous Post 1988 survey is referenced within the Methodology; that this area was re-surveyed as no point by point data was available (APP-056, para 5.4.5), however, NE would expect discussion to be provided regarding the discrepancies between the results. This would be particularly useful where detailed survey was not undertaken (i.e. inaccessible areas). NE advises that, following updates to soil wetness calculations and ALC gradings (see item BMV6) an updated ALC map should be prepared in line with the requirements of the BSSS Working with soil competencies (WWS-Complete-Competencies.pdf), which sets out the expectation for mapping soil units and ALC grades. Further discussion should also be provided regarding the Semi-detailed survey undertaken by Land Research Associates and the Post 1988 ALC survey available for part of the site, particularly where detailed survey was not undertaken, or where grading differs significantly. | Amber | The Applicant has stated that further information regarding their ALC mapping will be provided in their Response to relevant Representations submitted at D1. NE will review and provide an update on our position following a review of documents submitted by the Applicant at Deadline 1. | Amber
| BMV6 | Soils and Best & Most Versatile Land | ALC Survey Findings – Wetness Class Calculation | Amber | Although Para 3.5.1. of both ALC reports (APP-172 & APP-173) state that ‘ALC grade has been calculated on a point-by-point basis, with features of wetness class (Slowly Permeable Layer and Gleying) analysed from each auger sample’. Para 5.1.2 in both reports contradicts this by stating, ‘The general profiles for the soil types identified on the Site has been used to assess the Wetness Class (WC) for the Soil.’ The Grade of each overarching soil type according to soil wetness has been determined in sections 5.2 and 5.3 fo each ALC report. In particular, Para 5.2.1 on ALC report for parcels A and D (APP-172) states that ‘The majority of Area 1 and 2 has been identified with the combination of the topsoil texture (Heavy Silty Clay Loam), Wetness Class (III) and the number of Field Capacity Days (<126), together with the topsoil being calcareous results in ALC Grade 3b for Type 1 soils.’ However, as per ALC guidelines Table 6 , if the soils exhibit a Calcium carbonate content greater than 1%, a clay content greater than 18% in the top 25 cm, and the number of field capacity days below 150, the Soil Wetness should be relaxed by 1 grade. This distinction should be made in this case, reducing the Wetness Class to WCII. This is significant as it would improve the ALC Grade for HZCL and MZCL from 3b to 3a or from 3a to 2 in this instance. Wetness Class Calculations should be updated across both of the ALC reports to reflect the calcareous soils, with ALC gradings subsequently amended to reflect this and remapped as per item BMV5. The Assessment of Effects to BMV land at ES Chapter 5 must then be updated to reflect any changes in ALC grading. | Amber | The Applicant has stated that testing for calcium carbonate was undertaken in accordance with the ALC guidelines, and the ALC survey reports will be updated at D1 to clarify this. NE will review and provide an update on our position following a review of documents submitted by the Applicant at Deadline 1. | Amber
(1) | BMV7 | Soils and Best & Most Versatile Land | ALC Survey Findings – Soil Auger Records | Yellow | Soil bore logs provide a detailed log of soil properties. However, it is unexpected to see the same soil properties, including soil horizon depths; and soil colours across large swathes of land as shown in Appendix II. Particularly as it has been previously acknowledged both in the ALC report (APP-172 para 3.5.2 & APP-173 para 3.5.2) "a degree of variability in physical characteristics within a discrete area is to be expected", and in a previous reconnaissance survey of the site, that the soils are variable over short distances ‘[fine silty] soils occur in a complex pattern throughout the site’; ‘[coarse silty] soils occur mainly in the east of Land Parcel C and in large areas through Land Parcel B, although they also occur in a complex pattern on higher ground within the clay soils described below’; and ‘ [clay] soils are the most common across the survey area…. Variation occurs within these soils, where fine silty and coarse silty soils are formed along former creek channels.’ Furthermore, the soil pit photograph appended to the ALC report for parcels A and D (APP-172) ‘soil type 2 PIT’, clearly shows a high topsoil depth variability across a relatively small area, suggesting topsoil depths across the wider sites would also be more variable than suggested by the auger bore log. The photographs, whilst welcome, lack the information required to make them useful. There are no co-ordinates or direction shown for the photos, nor soil bore numbers. Whilst only two soil types were identified across the 2 sites, it would be expected that due to the size of these sites, and the fact they are spatially isolated from each other, more than 2 pits would be explored to confirm soil structural properties. NE does not request any further action on this point, however, would like to note this for PINS’ consideration as a further concern regarding the robustness of the ALC survey. | Yellow | The Applicant has stated that full soil pit logs will be included in the updated ALC survey reports at Deadline 1. NE will review and provide an update on our position following a review of documents submitted by the Applicant at Deadline 1. | Yellow
| BMV8 | Soils and Best & Most Versatile Land | ALC Survey Findings – Soil Lab Analysis | Amber | NE welcomes the lab analysis undertaken. Although, it is noted that the depth and texture measurements listed in the soil bore log do not align with the depths and textures provided in the lab analysis, which raises some concern. The percent calcareousness has also not been determined. Therefore, it cannot be confirmed which soils should be considered calcareous. This is a significant omission, as this will impact the Wetness Class, and therefore the ALC Grade. The soils have been tested according to the British Standard for topsoil, which is designed for imported soils. This is not the appropriate soil test in this instance. NE would generally only expect particle size distribution (Texture) and calcareous content to be tested. As per item BMV6, NE requests that the wetness class is recalculated considering the calcareous soils. Based on the available literature and contextual information, NE considers it necessary to take a worst case scenario approach in the absence of complete lab testing to assume all relevant soils have a CaCO3 content of more than 1%. This assumption would need to be noted in the SMP, as restoration to the same grade, should the soils not be calcareous, would not be possible. | Amber | The Applicant has stated that the ALC Survey Reports will eb updated at Deadline 1 to include further information regarding the Soil Lab Analysis. NE will review and provide an update on our position following a review of documents submitted by the Applicant at Deadline 1. | Amber
| BMV9 | Soils and Best & Most Versatile Land | Assessment Methodology | Green | NE generally welcomes the ES assessment methodology, which follows ISEP (formerly IEMA) guidance (‘A New Perspective on Land and Soil in Environmental Impact Assessment’). The sensitivity and magnitude criteria attributed to BMV land in Tables 5-5 and 5-6 are all suitable. | Green
| BMV10 | Soils and Best & Most Versatile Land | Assessment of impacts to BMV land within the ES: ALC Results | Amber | As set out in Table 5-9, 375.4ha of the total 1067.4ha Solar Development Area is classified as BMV, based on grades averaged by soil type. Table 5-10 indicates a greater proportion of BMV, at 418.6ha, when mapped by individual auger point. See item BMV5 for NE’s comments with regard to the ALC mapping. Table 5-11 sets out the provisional ALC grades of each of the inter-array connections and grid connection route. 100% of these areas are BMV, a total of 542.1ha. NE would like to reference the recently published Predictive ALC map for England, which has now replaced the Provisional ALC mapping as the primary strategic dataset. The mapping is available via the Defra Data Services Platform and has now also been incorporated into MAGIC. This updated mapping is unlikely to alter the outcome of the assessment to show any additional effects, as 100% of the inter-array areas and grid connection corridor have already been considered either grade 1 or 2 land. It must be acknowledged that the applicants’ assessment of effects to Best and Most Versatile Land is based upon ALC survey results that NE has significant concerns around (see items BMV5 to BMV8). As such, the following advice at items BMV11 to BMV15 may need to be superseded following any amendment to the survey results. The Assessment at ES Chapter 5 should be updated following amendments to ALC grading. See item BMV6. | Amber | NE will review and provide an update on our position following a review of documents submitted by the Applicant at Deadline 1. | Amber
| BMV11 | Soils and Best & Most Versatile Land | Assessment of impacts to BMV land within the ES: Permanent Loss of BMV Land for Hardstanding | Amber | Paragraph 5.8.2 (APP-056) sets out that On-Site Substation and BESS Compounds, Solar Stations and CSEC Compounds will involve the creation of hardstanding, which will be in situ for the lifetime of the development, and removed at decommissioning. Despite the removal at decommissioning, the Applicant has considered, for the purpose of the ES, that the land will be permanently lost where these are sited on Grade 1 and 2 BMV land. Whilst the rationale for this being due to the very high sensitivity of Grade 1 and 2 land is noted, NE considers it may not be possible to re-establish the standard of BMV land for lower grades; particularly Grade 3a, which is still classified as BMV. NE references the recent precedent from the Springwell Solar project, where the SoS stated in their decision letter (EN010149-001062-Springwell Solar Farm - Secretary of State for Energy Security and Net Zero Decision Letter.pdf Para 4.49): ‘In respect of BMV land, the Secretary of State notes that the ExA disagreed with the Applicant’s assessment of BMV land and instead agreed with NKDC that sealed over hard standing areas of the Proposed Development should be treated on a precautionary basis as ‘permanently lost’ [ER 8.4.16]. The Secretary of State notes that this approach has been followed on other similar solar farm developments to provide a worst-case scenario where such areas cannot be returned to the same Agricultural Land Classification (“ALC”) grade and considers it appropriate to use this approach in this case too.’ On-Site Substation and BESS Compounds, Solar Stations and CSEC Compounds requiring hardstanding for the lifetime of the development are sited on BMV land, including Grade 3a, should be considered permanently lost as part of the ‘worst case scenario’ in the ES. | Amber | The Applicant has stated that ES Chapter 5 will be updated for Deadline 1 to consider a permanent effect on Grade 3a land from the creation of hardstanding. NE will review and provide an update on our position following a review of documents submitted by the Applicant at Deadline 1. | Amber
| BMV12 | Soils and Best & Most Versatile Land | Assessment of impacts to BMV land within the ES: Downgrading of effect magnitude | Amber | Paragraph 5.8.3 (APP-056) discusses the downgrading of the magnitude of effect (from medium to low) of permanent tree and shrub planting as a result of these features being sited along field boundaries. It should be noted that impacts of these elements of habitat creation would be major adverse (loss of 8.3ha Grade 1 and 2 BMV) and moderate adverse (loss of 10.8ha Grade 3a BMV) if the standard medium magnitude of effect was applied; so this split from the ISEP guideline is significant. It is noted that the ISEP Guidance states: ‘in all cases these tables should not replace professional judgement by experienced professionals based on the specifics and context of the EIA being undertaken’, however, NE considers this amendment should be omitted. Whilst this impact on the BMV resource differs to that of soil stripping and hardstanding, and siting of these features on field boundaries will reduce the project’s lasting effect on the agricultural use of the site, which is a relevant consideration in the decision making process, these enhancements will nonetheless result in a permanent loss of BMV land, which should not be understated within the ES. It is also noted that Table 5-15 shows that the permanent loss of 8.3ha of Grade 1 & 2 land for Trees and Shrubs as a minor, insignificant effect (after considering the downgraded magnitude of effect). However, in line with Table 5-7, this minor effect on a very high sensitivity receptor should result in a moderate, significant adverse effect. The downgrading of magnitude of impact of tree and shrub planting along field boundaries should be omitted. Should this amendment not be made, the significance of the effect of permanent loss of Grade 1 & 2 BMV land for trees and shrubs should as a minimum be amended to moderate, significant. | Amber | The Applicant has stated that further information regarding the application of professional judgement in modifying the assessment of magnitude of this effect will be probided in ES Chapter 5 for deadline 1. NE will review and provide an update on our position following a review of documents submitted by the Applicant at Deadline 1. | Amber
| BMV13 | Soils and Best & Most Versatile Land | Assessment of impacts to BMV land within the ES: Overall Permanent Loss of BMV Land | Amber | Table 5-15 and 5-16 set out the significance of effects to agriculture and soils from each element of the development. NE considers that all permanent losses of Grade 1 & 2 land (as a very high sensitivity receptor) should be assessed together. The same applies for Grade 3a land (as a high sensitivity receptor). Whilst the permanent losses presented are from different elements of the project (and it’s still helpful to present this, which is welcomed) without then considering the total permanent losses from all elements of the development, this is an omission in terms of cumulative assessment of intra-project effects. It is pertinent to understand the total permanent loss of BMV land as a result of the proposal. The ES should present the total permanent losses of Grade 1 & 2 land, and Grade 3a land when determining the overall significant of effects. | Amber | The Applicant has stated that an additional table and associated commentary reflecting the total permanent loss of BMV land will be included in ES Chapter 5 for deadline 1. NE will review and provide an update on our position following a review of documents submitted by the Applicant at Deadline 1. | Amber
| BMV14 | Soils and Best & Most Versatile Land | Assessment of impacts to BMV land within the ES: Other Matters | Green | Aside from the advice provided above, NE considers the assessment at Chapter 5 to be suitable. The Soil Management Plan (SMP) remains essential mitigation to ensure effects are temporary as described. See NE’s comment on oSMP at item BMV15. | Green
| BMV15 | Soils and Best & Most Versatile Land | Soil Management | Amber | NE welcomes the commitment to produce a SMP post-consent. Our advice regarding the oSMP is set out below. The following items must be updated in the oSMP (APP-280) pre-consent: - It is welcomed that ALC survey of the Cable route areas is secured in the SMP (paragraph 3.1.2.). However, ALC survey of other unsurveyed areas (including inaccessible areas and areas of high UXO risk) must be carried out post-consent; the oSMP should be updated to reflect this. - Despite being discussed within the ES Chapter 5, no firm commitment is made within the SMP to restore agricultural land to the same ALC grade. This applies to both temporary impacts during construction (i.e. access tracks and construction compounds) and operational impacts (i.e. Substations). The oSMP should be updated to ensure this commitment is secured. - Paragraph 5.7.2 says ‘An aftercare period will not be necessary for the majority area where soil has remained in situ as the extended period of time under grass should leave the soil profile in better structural condition than that found under the current arable production’. Aftercare will be necessary where soils have been stripped, stored, moved and reinstated. The oSMP should be updated to ensure ths is included. The following items should be included in the oSMP pre-consent, but must be included in the final SMP post-consent: - No Soil Budget has been provided in the oSMP. - No reference is made to the need for soil bunds to be in place for more than six months to be grassed and regularly cut to avoid excessive weed growth. Requirement 19 should be updated to include consultation with NE on the final SMP. The SMP is secured by DCO requirement 19; must be substantially in accordance with the oSMP. | Amber | The Applicant has stated that the requesnted amendments to the oSMP will be made for Deadline 1. NE will review and provide an update on our position following a review of documents submitted by the Applicant at Deadline 1. | Amber
| NE26 | Biodiversity Net Gain | Biodiversity Net Gain | Green | NE has not reviewed the BNG metric in detail, but notes that the Biodiversity Net Gain report [APP-274] sets out that based on the current development plans for the site, biodiversity gains of +14.60% for area-based habitats, +477.94% for hedgerows, and +11.42% for watercourses are achievable on site, whilst satisfying all trading rules. Draft DCO [APP-028] Requirement 8 includes commitment to the delivery of a minimum of 10%, 400% and 10% net gains for Habitat, hedgerow and watercourses, respectively, which is welcomed. | Green
| NE27 | Other | Ancient Woodland | Green | ES Chapter 7 [APP-060] paragraph 9.6.9 states that no Ancient Woodland is mapped within 2km of the site; no Ancient Woodland was identified during site surveys. As such, no impacts to this irreplaceable habitat are expected. Inidividual ancient/veteran trees have been identified on site (APP-242 Table 5-3), however, development design has avoided any direct effects, and indirect effects during construction are to be managed via the Arboricultural Method Statement, secured via the oCEMP. Draft DCO [APP-028] Requirement 12 secures the provision of the Construction Environment Management Plan, substantially in accordance with the outline CEMP [APP-275]. It is clearly noted in the oCEMP that an ‘Arboricultural Method Statement and Tree Protection Plan’ will be drafted as part of the CEMP (oCEMP paragraph 4.1.2). | Green