## Status
Green Hill Solar Farm Detailed Land and Rights Negotiations Tracker
Notes:
1. All interests which are not already acquired at the point of submission should be entered in this tracker and marked as complete (column 'w') when agreement with known interests is reached
2. Any non-agreement is also counted as an objection by an affected person(s) for the purpose of this tracker
3. An entry should also be made where the interest (or potential interest) holder is not known, to allow the relevant information to be added following diligent inquiry, negotiation etc
4. An editable version of this tracker must be submitted to The Planning Inspectorate with the application as an appendix to the Statement of Reasons
Book of Reference plot number 1 | Plan reference number 2 | Description of land and rights requested 3 | Party Name | Category | Agent/ representative 6 | When available Interested party/ affected person reference number 7 | When available Relevant representation reference number 8 | When available Written representation reference number 9 | Other document reference number 10 | Applicant's response references 11 | Duration of temporary rights 12 | Special category (Crown, allotment, National Trust etc) (Select from drop down list) | Special category - other information including confirmation of status 13 | Is the affected person a statutory undertaker and is the land operational? (Select from drop down list) | Protective provision status (Select from drop down list) | Side agreements (Select from drop down list) | Status of objection 14 | Heads of Terms (Select from drop down list) | Complete (Select from drop down list) | Last Updated [DD/MM/YYYY]
01–022, 02–023, 02–024 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Painesend Farm LLP | CAT 1 | Andrew Jenkinson (Robinson & Hall) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing | Draft under discussion | No | 2025-11-07
05-052 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Sywell Aerodrome Limited | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Discussions with the landowner to address glint and glare concerns have resulted in the removal of solar panels from relevant areas. Deadline 1 update: Positive Negotiations ongoing | Draft under discussion | No | 2025-11-07
07-076 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | James William Mills | CAT 1 | Tom Arthey (Arthey Associates) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing | Draft under discussion | No | 2025-11-07
07–077, 07–079, 07–080, 07–082, 07–083-a, 07–083-b, 08–084, 08–086, 08–089, 08–096-a, 08–096-b, 08–096-c | APP/GH2.2 | Freehold Acquisition Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | TOF Corporate Trustee Limited | CAT 1 | Giles Wordsworth (Savills) | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land within plots 07-082, 08-086 and 08-089 as part of the Scheme In relation to the remaining plots over which Acquisition of Rights and Imposition of Restrictive Covenants are required, draft HOTs sent to landowner 15/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing | Draft under discussion | No | 2025-11-07
08–094-a, 08–094-b | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Robert George Partridge | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing | Draft under discussion | No | 2025-11-07
08–094-a, 08–094-b | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Serien Partridge | CAT 1 | Guy Banham (Berrys) |  | RR-1061 |  |  |  |  | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Negotiations ongoing although a few concerns in regard to badgers in the area / disruption from the works | Draft under discussion | No | 2025-11-07
10–099-a, 10–099-b, 10–100, 10–101, 12–140, 12–142, 12–158 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Judith Thompson | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/25 Option negotiations with solicitors now ongoing | Agreed | No | 2025-11-07
10-102 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Timothy David Allinson | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Negotiations ongoing | Draft under discussion | No | 2025-11-07
10-102 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Alison Jocelyn Fitzhugh | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Negotiations ongoing although a concerns in regard to payment values | Draft under discussion | No | 2025-11-07
03–033, 04–041-a, 04–041-b, 05–051, 05–055-b, 06–058-a, 06–058-b, 06–058-c, 07–066-a, 07–066-b, 07–066-c, 07–066-d, 07–066-e, 08–087, 09–091, 08–092, 08–093-a, 08–093-b, 08–093-c, 10–103-a, 10–103-b, 10–103-c, 10–104-a, 10–104-b, 10–104-c, 10–105, 10-106-a, 10-106-b, 10-107, 11–110-a, 11–110-b, 11–110-c, 11–111, 11–112, 11–114, 11–116-a, 11–116-b, 11–116-c, 12–125, 12–131-a, 12–131-b, 12–131-c, 12–132, 12–133, 12–134, 12–135, 12-138, 12–151, 12–152, 12–153, 12–154, 12–155-a, 12–155-b, 12–156, 12-158, 12–159, 12–162, 13–172, 13–174, 13–177-a, 13–177-b, 14–187-a, 14–187-b, 14–193, 14–195, 15–202, 15–204-a, 15–204-b, 15–204-c, 16–211 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | North Northamptonshire Council | CAT 1 | Robert Keeves (Underwoods) |  | RR-1243 |  |  |  |  | Crown Land | 15–202 The King's Most Excellent Majesty in the right of his Duchy Of Lancaster - in respect of presumed subsoil interest to the centreline of the highway | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 in respect of plots 10-104-b, 10-105, 11-110-a, 11-110-b, 11-110-c, 11-111, 11-112, 11-114, 12-131-a, 12-131-b, 12-131-c, 12-132, 12-133, 12-134, 12-135, 12-151, 12-152, 12-153, 12-154, 16-211. Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into HOT's for the remaining plots are not required as these plots relate to land that is public highway Deadline 1 update: Council have instructed a Surveyor to review and undertake HOTs negotiations - 06/11/25 | Draft under discussion | No | 2025-11-07
10–107 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Elizabeth Lee | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/25 Option negotiations with solicitors now ongoing | Agreed | No | 2025-11-07
10–106-a, 10–106-b, 10–107 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Julie Mary Thompson | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/25 Option negotiations with solicitors now ongoing | Agreed | No | 2025-11-07
10–106-a, 10–106-b, 10–107 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Barbara Jean Thompson | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/25 Option negotiations with solicitors now ongoing | Agreed | No | 2025-11-07
10–106-a, 10–106-b, 10–107 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Caroline Margaret Thompson | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/25 Option negotiations with solicitors now ongoing | Agreed | No | 2025-11-07
10–106-a, 10–106-b, 10–107 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Susan Emma Everton | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/25 Option negotiations with solicitors now ongoing | Agreed | No | 2025-11-07
10-108 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Melvyn John Mallard | CAT 1 | Andrew Middleditch (Bletsoes) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing | Draft under discussion | No | 2025-11-07
11–109-a, 11–109-b, 12–141 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Stephen Elderton | CAT 1 | Chris Templar (Bletsoes) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing | Draft under discussion | No | 2025-11-07
11–109-a, 11–109-b, 11–119-a, 11–119-b, 11–121-a, 11–121-b, 12–141 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Trescella Claudette Elderton | CAT 1 | Chris Templar (Bletsoes) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing | Draft under discussion | No | 2025-11-07
03-028 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Alison Kate Linkletter | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/25 Option negotiations with solicitors now ongoing | Agreed | No | 2025-11-07
03-028 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Karen Elizabeth Linkletter | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/25 Option negotiations with solicitors now ongoing | Agreed | No | 2025-11-07
11–121-a, 11–121-b | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Michael Roy Elderton | CAT 1 | Chris Templar (Bletsoes) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing | Draft under discussion | No | 2025-11-07
11–122, 12–123, 12–124 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Isobel Sarah Clarke | CAT 1 | Peter Moore (Bletsoes) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing | Draft under discussion | No | 2025-11-07
12–126, 12–136-a, 12–136-b, 12–137 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Lavinia Mary De-Vere Padbury | CAT 1 | Kate Andrew (Hamlins) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into. Deadline 1 update: Interaction with CAT 1 legal representative but no negotiations to-date nor instruction of a surveyor. | Draft under discussion | No | 2025-11-07
12-138 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Deborah Joanne Skinner | CAT 1 | Burges Salmon | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Negotiations ongoing with Landowner whilst other discussions onging to facilitate HOTS negotiations | Draft under discussion | No | 2025-11-07
12–138, 12–148, 12–163-a, 12-163-b, 12–164, 12–165-a, 12–165-b, 13–169, 13–170, 13–171-a, 13–171-b | APP/GH2.2 | Freehold Acquisition Acquisition of Rights and Imposition of Restrictive Covenants | John William Banks Skinner | CAT 1 | Burges Salmon | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land within plots 12-164, 12-165-a, 12-165-b, 13-169, 13-170, 13-171-a and 13-171-b as part of the Scheme In relation to the remaining plots over which Acquisition of Rights and Imposition of Restrictive Covenants are required, draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Negotiations ongoing with Landowner whilst other discussions onging to facilitate HOTS negotiations | Draft under discussion | No | 2025-11-07
12–143, 12–144, 12–145, 12–146, 13–184-a, 14–185, 14–186, 14–188, 14–189-a, 14–189-b, 15–200, 15–201, | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants Temporary Possession Freehold Acquisition | Spencer Douglas David Compton Marquess of Northampton | CAT 1 | Mark Henderson (In-House Estates) | [6 empty] | Crown Land | 12-143, 12-144, 12-145, 12-146 British Railways Board Limited hold CAT 2 interest in respect of rights contained in a conveyance dated 6 March 1972. | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land within plots 15-200 and 15-201 as part of the Scheme In relation to the remaining plots over which Acquisition of Rights and Imposition of Restrictive Covenants are required, terms have been discussed and agreed in principle with formal HOTs to be issued shortly. Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into. Deadline 1 Update : Positive negotiations on-going. | Draft under discussion | No | 2025-11-07
12–138, 12–143, 12–144, 12–145, 12–146, 12–147, 12–156 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Heidelberg Materials UK Limited | CAT 1 | Pawel Zlocki (Heidelberg) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Owner of mines and minerals in respect of plot 12-138. The minerals code has been included in the draft DCO. HOT's not required in respect of plot 12-156 as it relates to land that is public highway. Deadline 1 update: Positive Negotiations ongoing and an external surveyor is being assigned to the HOTS | Draft under discussion | No | 2025-11-07
13–181, 13–182, 13–183 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Trinity Land Limited | CAT 1 | Guy Banham (Berrys) |  | RR-1254 |  |  |  |  | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Negotiations ongoing but Landowner has a number of concerns raised in Relevant Representation reference RR-1254, which are being reviewed and actioned. | Draft under discussion | No | 2025-11-07
03-031 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Brian Richard Knight | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: The agent has signed HOTs and legal teams have been instructed. | Draft under discussion | No | 2025-11-07
03-031 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | David Anthony Knight | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: The agent has signed HOTs and legal teams have been instructed. | Agreed | No | 2025-11-07
03-031 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Jennifer Rosemary Knight | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: The agent has signed HOTs and legal teams have been instructed. | Agreed | No | 2025-11-07
17–215-b, 17–215-a, 16–214, 16–213, 16–212, 16–210-a, 16-210-b, 15–207, 15–203-b, 15–203-a, 15–199, 15–198, 14–197, 14–194, 14–191 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants Freehold Acquisition | Compton Family Trust Corporation Limited | CAT 1 | Mark Henderson (In-House Estates) | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land within plots 14-191, 14-194, 15-198, 15-199, 15-203-a, 15-203-b, 15-207, 16-212, 16-213 and 16-214 as part of the Scheme In relation to the remaining plots over which Acquisition of Rights and Imposition of Restrictive Covenants are required, terms have been discussed and agreed in principle with formal HOTs to be issued shortly. Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing. | Draft under discussion | No | 2025-11-07
04–044, 04–045, 04–046, 04–048 | APP/GH2.2 | Temporary Possession | Benjamin Keith Muttock | CAT 1 | Nick Denman (SDF) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing. | Draft under discussion | No | 2025-11-07
04–044, 04–045, 04–046, 04–048 | APP/GH2.2 | Temporary Possession | Nanette Muttock | CAT 1 | Nick Denman (SDF) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing. | Draft under discussion | No | 2025-11-07
03–032, 03–033 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | David John Beesley | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/25 Option negotiations with solicitors now ongoing | Agreed | No | 2025-11-07
03–032, 03–033 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Joanna Mary Beesley | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/25 Option negotiations with solicitors now ongoing | Agreed | No | 2025-11-07
03–035, 03–036 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Anthony James Middleton | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/25 Option negotiations with solicitors now ongoing | Agreed | No | 2025-11-07
03–035, 03–036 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Anthony Mark Middleton | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/25 Option negotiations with solicitors now ongoing | Agreed | No | 2025-11-07
04–037, 04–043 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Fiona Mary Smith | CAT 1 | Andrew Middleditch (Bletsoes) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing | Draft under discussion | No | 2025-11-07
04–037, 04–043 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | P.S. Smith & Son | CAT 1 | Andrew Middleditch (Bletsoes) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing | Draft under discussion | No | 2025-11-07
04-042 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Andrew Clive Middleditch | CAT 1 | Andrew Middleditch (Bletsoes) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing | Draft under discussion | No | 2025-11-07
04-042 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Christopher Thomas Bletsoe | CAT 1 | Andrew Middleditch (Bletsoes) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing | Draft under discussion | No | 2025-11-07
04–042, 04–043 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Tristan Baxter-Smith | CAT 1 | Andrew Middleditch (Bletsoes) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing | Draft under discussion | No | 2025-11-07
04–047, 04–049, 04–050 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Frederick Richard Harris | CAT 1 | Gilbert Watchorn | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing | Draft under discussion | No | 2025-11-07
05-054 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Philip Lionel Smith | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | Owner of mines and minerals. The minerals code has been included in the draft DCO. | None drafted | No | 2025-05-21
05–056, 05–057, 06–059, 06–060, 06–061, 06–062, 06–063, 06–065 | APP/GH2.2 | Freehold Acquisition Acquisition of Rights and Imposition of Restrictive Covenants | The Trustees of the G T Wilson Will Trust (Trustees of Holcot Estates LLP) | CAT 1 | Harry Edwards (Fisher German) | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land within plots 06-062 and 06-063 and 06-065 as part of the Scheme In relation to the remaining plots over which Acquisition of Rights and Imposition of Restrictive Covenants are required, draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: HOTs have been signed and are with legal instruction | Agreed | Yes | 2025-11-07
01–001, 01–007, 01–012-a, 01–012-b, 01–019, 01–020, 02–025-a, 02–025-b, 02–025-c, 03–034-a, 03–034-b, 03–034-c, 12-127, 12-128, 12-129, 12-130, 04-038, 04-039-b | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | West Northamptonshire Council | CAT 1 | In house Property Team |  | RR-1251 |  |  |  |  | N/A | N/A | Not SU |  |  | HOT's for these plots are not required as these plots relate to land that is public highway Deadline 1 update: Two titles are being transferred to North Northamptonshire Council as they are outside WNC juristiction and WNC do not wish to engage with HOTS. Negotiatiions are ongoing with NNC as per the entry for North Northamptonshire Council in this tracker | None drafted | No | 2025-11-07
01-002 | APP/GH2.2 | Freehold Acquisition | Matthew Arnold Knight | CAT 1 | HCR Legal LLP | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
01–002, 01–003, 01–004, 01–005, 01–006, 01–011, 01–013, 01–015, 01–017 | APP/GH2.2 | Freehold Acquisition | John Arnold Knight | CAT 1 | HCR Legal LLP | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land in plots 01–002, 01–004, 01–005, 01–006, 01–011, 01–013, 01–015 and 01–017 as part of the Scheme. HOTs are not required in respect of plot 01-003; negotiations for the use of this land are being conducted with the owner of the freehold interest | Agreed | Yes | 2025-05-21
01–002, 01–003, 01–018 | APP/GH2.2 | Freehold Acquisition | Pamela Jane Knight | CAT 1 | HCR Legal LLP | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land in plots 01–002 and 01–018 as part of the Scheme. HOTs are not required in respect of plot 01-003; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | Yes | 2025-05-21
01-003 | APP/GH2.2 | Freehold Acquisition | Mark William Knight | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
01–008, 01–009, 01–010, 01–014, 01–016, 01–022, 02–023, 02–024 | APP/GH2.2 | Freehold Acquisition Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | J A Knight & Son (Farmers) Limited | CAT 1 | HCR Legal LLP | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land in plots 01-008, 01-009, 01-010, 01-014 and 01-016 as part of the Scheme HOTs are not required in respect of the remainder; negotiations for the use of this land are being conducted with the owner of the freehold interest | Agreed | Yes | 2025-05-21
02–029, 03–030 | APP/GH2.2 | Freehold Acquisition Acquisition of Rights and Imposition of Restrictive Covenants | Julian Lindsay Care | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land in plot 02-029 as part of the Scheme. To be confirmed if rights over plot 03-030 are required. | Agreed | Yes | 2025-05-21
02–029, 03–030 | APP/GH2.2 | Freehold Acquisition Acquisition of Rights and Imposition of Restrictive Covenants | Timothy Adrian Care | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land in plot 02-029 as part of the Scheme. To be confirmed if rights over plot 03-030 are required. | Agreed | Yes | 2025-05-21
05–053, 07–069, 07–070, 07–071, 07–072, 07–073, 07–074, 07–075, 07–077, 07–079, 07–080, 07–082, 08–083-a, 08–073-b, 08–084, 08–086, 08–089, 08–096-a, 08–096-b, 08–096-c | APP/GH2.2 | Freehold Acquisition Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | William John Pitts | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land in plots 05-053, 07-069, 07-070, 07-071 and 07-072 as part of the Scheme. To be confirmed if rights over plots 07-073, 07-074 and 07-075 are required. HOTs are not required in respect of the remainder; negotiations for the use of this land are being conducted with the owner of the freehold interest | Agreed | Yes | 2025-05-21
07–069, 07–070, 07–071 | APP/GH2.2 | Freehold Acquistion | Catherine Elizabeth Pitts | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
06-059 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Merrick John Russell Pinny | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted |  | 2025-05-21
06-064 | APP/GH2.2 | Freehold Acquisition | Henry Charles Michael Gurney | CAT 1 | HCR Legal LLP | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
06-064 | APP/GH2.2 | Freehold Acquisition | Jane Ann Gurney | CAT 1 | HCR Legal LLP | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
07–072, 07–073, 07–074, 07–075 | APP/GH2.2 | Freehold Acquisition Acquisition of Rights and Imposition of Restrictive Covenants | CERES (Northampton) Limited | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A |  |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No | 2025-05-21
07-073, 07-075 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Sywell Solar Limited | CAT 1 | [7 empty] | N/A | N/A |  |  |  | To be confirmed if rights over this plot are required Deadline 1 update The Applicant is in discussions with Sywell Solar Farm regarding the Scheme's interaction with their operational asset including shared access to these plots and has proposed a cooperation agreement. | None drafted | No | 2025-05-21
07–077, 07–079, 07–080, 07–082, 08–083-a, 08–083-b, 08–084, 08–086, 08–089, 08–094-a, 08–094-b, 08–096-a, 08–096-b, 08–096-c | APP/GH2.2 | Freehold Acquisition Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | J. W. Pitts & Son | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A | Not SU |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | Agreed | Yes | 2025-05-21
08-090 | APP/GH2.2 | Freehold Acquisition | Robert Charles Minshull Stockdale | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
08-090 | APP/GH2.2 | Freehold Acquisition | Henry Robert Minshull Stockdale | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
11–109-a, 11–109-b, 11–119-a, 11–119-b, 11–121-a, 11–121-b, 12–141 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Ben Elderton | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No | 2025-05-21
11–122, 12–123, 12–124 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Tim Frost | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No | 2025-05-21
12-141 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Storeland Aggregates Limited | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | Owner of mines and minerals. The minerals code has been included in the draft DCO. | None drafted |  | 2025-05-21
12-156 | APP/GH2.2 | Temporary Possession | Stanley John Bond | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | HOT's are not required as these plots relate to land that is public highway | None drafted | No | 2025-05-21
13–181, 13–183 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | John Hope | CAT 1 |  |  | RR-0560 |  |  |  |  | N/A | N/A | Not SU |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No | 2025-05-21
14–185, 14–186, 14–188 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Jodie Finch | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No | 2025-05-21
13–184-a, 13–184-b, 14–185, 14–186, 14–188, 14–189-a, 14–189-b | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Robert Jakeman | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No | 2025-05-21
16-210-a, 16-210-b | APP/GH2.2 | Temporary Possession | Abigail West | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No | 2025-05-21
14–191, 14–194, 14–197, 15–203-a, 15–203-b, 16–212 | APP/GH2.2 | Freehold Acquisition | Tim Allebone | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | Negotiations for the use of this land are being conducted in parallel with the owner of the freehold interest and a draft Agreement is under review | Agreed | No | 2025-05-21
16–214, 16–213, 15–207 | APP/GH2.2 | Freehold Acquisition | Castle Ashby Farms | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No | 2025-05-21
17–215-b, 17–215-a | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Philip Skinner | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No | 2025-05-21
17–215-b, 17–215-a | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | William Skinner | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No | 2025-05-21
18-219 | APP/GH2.2 | Freehold Acquisition | Meikle Farming Limited | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
18–222, 18–221, 18–220, 18–218, 17–217 | APP/GH2.2 | Freehold Acquisition Acquisition of Rights and Imposition of Restrictive Covenants | Ian James Meikle | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
18–222, 18–221, 18–220, 18–218, 17–217 | APP/GH2.2 | Freehold Acquisition Acquisition of Rights and Imposition of Restrictive Covenants | Andrew Meikle | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
18–222, 18–221, 18–220, 18–218, 17–217 | APP/GH2.2 | Freehold Acquisition Acquisition of Rights and Imposition of Restrictive Covenants Temporary Possession | Ruth Lesley Meikle | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
18–223, 18–220, 17–216-c, 17–216-b, 17–216-a | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Milton Keynes Council | CAT 1 |  |  | RR-1233 |  |  |  |  | N/A | N/A | Not SU |  |  | HOT's are not required as these plots relate to land that is public highway | None drafted | No | 2025-05-21
12-141 |  | Acquisition of Rights and Imposition of Restrictive Covenants | Ecton Estates Commercial Company Limited | CAT 1 | [12 empty] | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No
08-089 |  | Freehold Acquisition | Ian Clegg | CAT 1 | [12 empty] | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No
08-089 |  | Freehold Acquisition | Mandy Clegg | CAT 1 | [12 empty] | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No
05-054 |  | Acquisition of Rights and Imposition of Restrictive Covenants | Frederick Thomas Harris | CAT 1 | Gilbert Watchorn | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing | Draft under discussion | No | 2025-11-07
05-054 |  | Acquisition of Rights and Imposition of Restrictive Covenants | Peter Andrew Harris | CAT 1 | Gilbert Watchorn | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing | Draft under discussion | No | 2025-11-07
Add new lines as required…
1 Plot number from the Book of Reference
2 Plan reference number from the Book of Reference and Examination Library reference
3 Description of land and rights requested from the Book of Reference including restrictive covenants
4 A person is within category 1 if the applicant, after making diligent inquiry, knows that the person is an owner, lessee, tenant (whatever the tenancy period) or occupier of the land, see section 57 (1) of the Planning Act 2008
5 A person is within category 2 if the applicant, after making diligent inquiry knows that the person: interested in the land or has the power to sell or convey the land or to release the land, see section 57(20) of the Planning Act 2008
6 Person or organisation representing the interests of the affected person(s) - enter N/A if the affected person(s) are representing themselves
7 Reference number assigned to each interested party and affected person - for Planning Inspectorate use only
8 Reference number assigned to each relevant representation in the Examination Library
9 Reference number assigned to each written representation in the Examination Library
10 Reference number assigned to any other document in the Examination Library
11 Reference numbers assigned to all of the applicant's responses in the Examination Library including specific reference to relevant sections within documents
12 Likely duration of any temporary rights such as temporary possesion
13 Where crown land is affected, this column should include the anticipated date of consent from the crown authority
14 Narrative on negotiations to date

## Statutory Undertakers
Green Hill Solar Farm Detailed Land and Rights Negotiations Tracker
Notes:
1. All interests which are not already acquired at the point of submission should be entered in this tracker and marked as complete (column 'w') when agreement with known interests is reached
2. Any non-agreement is also counted as an objection by an affected person(s) for the purpose of this tracker
3. An entry should also be made where the interest (or potential interest) holder is not known, to allow the relevant information to be added following diligent inquiry, negotiation etc
4. An editable version of this tracker must be submitted to The Planning Inspectorate with the application as an appendix to the Statement of Reasons
Book of Reference plot number 1 | Plan reference number 2 | Description of land and rights requested 3 | Party Name | Category | Agent/ representative 6 | When available Interested party/ affected person reference number 7 | When available Relevant representation reference number 8 | When available Written representation reference number 9 | Other document reference number 10 | Applicant's response references 11 | Special category (Crown, allotment, National Trust etc) (Select from drop down list) | Special category - other information including confirmation of status 13 | Is the affected person a statutory undertaker and is the land operational? (Select from drop down list) | Protective provision status (Select from drop down list) | Side agreements (Select from drop down list) | Status of objection 14 | Heads of Terms (Select from drop down list) | Complete (Select from drop down list) | Last Updated [DD/MM/YYYY]
08–094-b, 08–096-c, 10–099-b, 10–102, 10–103-b, 10–103-c, 11-111, 11-116-c, 11-119-a, 12–166, 12–167, 13–169, 13–171-b, 13–173, 13–176, 13–177-b, 13–184-a, 13–184-b, 14–186, 14–187-b, 16–212, 16–214, 17–215-b, 17–216-a, 17–217, 18–219, 18–220, 18–221, 18–223 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | National Grid Electricity Transmission plc | CAT 1/CAT 2 |  |  | RR-1240 |  |  |  | N/A | N/A | SU and known operational | Draft under discussion | Draft under discussion | The Applicant has engaged with National Grid in respect of the process to obtain the necessary easement and will be progressing this alongside the DCO application. Protective provisions for the benefit of National Grid are under negotiation and a draft version has been included in Schedule 15 to the draft DCO. It is anticipated that a side agreement may be required. Deadline 1 update: The Applicant has contacted National Grid's solicitors and is in discussions as to the form of PPs and a side agreement. | Draft under discussion |  | 2025-11-07
03–030, 08–088 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | On Tower UK 1 Limited | CAT 1 | [6 empty] | N/A | N/A | SU and known operational | Draft under discussion | Not required | To be confirmed if rights over this plot are required Protective provisions for the benefit of electronic communications code operators have been included in Schedule 15 to the draft DCO Deadline 1 Update: On Tower UK 1 Limited has not requested bespoke protective provisions. Accordingly, the Applicant has not progressed any bespoke form of protective provisions or side agreement with On Tower UK 1 Limited. | None drafted |  | 2025-11-07
04–039-a, 04–039-b, 05-055-b, 11–112, 11–114, 12–127, 12–128, 12–134, 12–135, 12–149, 12–150 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | National Highways Limited | CAT 1 |  |  | RR-1241 |  |  |  | N/A | N/A | SU and known operational | Draft under discussion | Draft under discussion | Protective provisions for the benefit of National Highways are under negotiation and a draft version has been included in Schedule 15 to the draft DCO. It is anticipated that a side agreement may be required. Deadline 1 update: The Applicant is currently negotiating bespoke protective provisions with National Highways. The Applicant has returned a revised draft to National Highways and awaits further comments. Negotiations are progressing positively and the Applicant anticipates that the parties will be able to reach agreement before the end of Examination. | Draft under discussion |  | 2025-11-07
01–008, 01–010, 01-013, 01–014, 02-025-a, 02-025-c, 02-029, 03-032, 03-034-c, 04–042, 04–045, 04-046, 04–048, 04-049, 04-050, 05-054, 06-058-a, 06-058-b, 06-058-c, 06-065, 07-066-a, 07-066-b, 07-066-c, 07-066-d, 07-066-e, 07–070, 07–071, 07–072, 07–073, 07–074, 07–075, 07–076, 07–077, 07–079, 07–080, 07–082, 08–083-a, 08–083-b, 08–084, 08–086, 08-088, 08-089, 08–090, 09-091, 08-093-c, 08-094-a 08–094-b, 10-103-a, 10-104-c, 11-109-a, 11-110-a, 11-110-b, 11-110-c, 11-112, 11-116-a, 11–119-a, 11-119-b, 11-120-a, 11-120-b, 12-131-a, 12-131-b, 12-131-c, 12-132, 12-138, 12–143, 12–144, 12–145, 12–146, 12-147, 12-148, 12-151, 12-152, 12-153, 12-154, 12-155-a, 12-155-b, 12-156, 12-159, 12-162, 12-163-a, 12–165-a, 12–165-b, 12–167, 13–169, 13–184-b, 14–186, 14-188, 14-194, 14-195, 15-200, 15–201, 15-202, 15–203-a, 15-204-a, 15-207, 17-215-a, 17-216-b, 17-216-c | APP/GH2.2 | Freehold Acquisition Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants No Compulsory Acquisition or Temporary Possession Powers Being Sought | National Grid Electricity Distribution (East Midlands) plc | CAT 2 | [6 empty] | N/A | N/A | SU and known operational | Draft under discussion | Draft under discussion | Protective provisions for the benefit of National Grid Electricity Distribution are under negotiation and a draft version has been included in Schedule 15 to the draft DCO. It is anticipated that a side agreement may be required. Deadline 1 update: National Grid Electricity Distribution (East Midlands) plc has not requested bespoke protective provisions. The Applicant is seeking confirmation from National Grid Electricity Distribution that it is content with the protective provisions for its benefit included in the draft DCO. | Draft under discussion |  | 2025-11-07
08-088, 07-066-a, 07-082, 08-086, 08-087, 08-089, 08-090. 10-099-a, 10-100, 10-103-a, 10-103-b, 10-103-c, 10-104-a, 11-110-a, 11-110-b, 11-110-c, 11-111, 11-112, 11-116-a, 13-177-b, 15-201, 15-202 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Cadent Gas Limited | CAT 1/CAT 2 | [6 empty] | N/A | N/A | SU and known operational | Draft under discussion | Draft under discussion | To be confirmed if rights over this plot are required Protective provisions for the benefit of Cadent Gas are under negotiation and a draft version has been included in Schedule 15 to the draft DCO. It is anticipated that a side agreement may be required. Deadline 1 update: Cadent has not requested bespoke protective provisions. The Applicant is seeking confirmation from Cadent that it is content with the protective provisions for its benefit included in the draft DCO. | None drafted |  | 2025-11-07
12-138, 12–139, 12–160, 12–161 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | The Environment Agency | CAT 1 |  |  | RR-1224 |  |  |  | N/A | N/A | SU and known operational | Draft under discussion | Not required | Protective provisions for the benefit of the Environment Agency are under negotiation and a draft version has been included in Schedule 15 to the draft DCO. Deadline 1 update: Draft protective provisions have been provided to the EA for consideration and the Applicant awaits comments. The Applicant is confident that the parties will be able to reach agreement before the end of Examination. | Draft under discussion |  | 2025-11-07
06–058-a, 06–058-b, 06–058-c, 09–091, 12–131-a, 12–131-b, 12–131-c, 12–132, 12-133, 12–134, 12-135, 12–149, 12–150, 12–151, 12–152, 12–153, 12–154, 12–155-a, 12–155-b, 12–156, 12–161, 13–177-a, 13–184-a, 13–184-b, 14–187-b | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Zayo Group UK Limited | CAT 2 | [6 empty] | N/A | N/A | SU and known operational | Draft under discussion | Not required | Protective provisions for the benefit of electronic communications code operators have been included in Schedule 15 to the draft DCO | None drafted |  | 2025-11-07
02–025-a, 02–025-b, 02–025-c, 03–034-a, 03–034-b, 03–034-c, 05–055-a, 05-055-b, 06–058-a, 06–058-b, 06–058-c, 06–065, 07–066-e, 08-087, 08–093-a, 08–093-b, 08–093-c, 12-155-b, 12-164, 13-173, 13–176, 13–177-a, 13–177-b, 14–193, 14–195, 15–201, 15–202, 15–204-b, 15–204-c | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants Freehold Acquisition | Gigaclear Limited | CAT 2 | [6 empty] | N/A | N/A | SU and known operational | Draft under discussion | Not required | Protective provisions for the benefit of electronic communications code operators have been included in Schedule 15 to the draft DCO Deadline 1 update: Gigaclear Limited have not requested bespoke protective proovisions. Accordingly, the Applicant has not progressed any bespoke form of protective provisions or side agreement with Gigaclear Limited. | None drafted |  | 2025-11-07
02-025-c, 02–029, 03–036, 04–037, 04–041-a, 04–042, 04–049, 04–050, 05–052, 05–053, 05–054, 06–058-a, 06–058-b, 06–058-c, 06–065, 07–066-a, 07–066-d, 07–066-e, 07–069, 08–090, 09–091, 10–107, 10–108, 11–109-a, 11–110-c, 11-111, 11-112, 11-116-a, 11–119-a, 11–119-b, 11–120-a, 11–122, 12–123, 12–124, 12–125, 12–131-a, 12–131-b, 12–131-c, 12–151, 12–152, 12–153, 12–154, 12–155-a, 13-173, 13–176, 13–177-a, 13–177-b, 14–187-a, 14–187-b, 14-191, 14–193, 14–195, 14–197, 15–202, 15–203-b, 15–204-a, 15-204-c, 15–207, 16–212, 16-213, 16–214, 17–215-a, 17–216-a, 17–216-b, 17–216-c | APP/GH2.2 | Freehold Acquisition Acquisition of Rights and Imposition of Restrictive Covenants Temporary Possession | Anglian Water Services Limited | CAT 2 |  |  | RR-1214 |  |  |  | N/A | N/A | SU and known operational | Draft under discussion | Not required | Protective provisions for the benefit of Anglian Water are under negotiation and a draft version has been included in Schedule 16 to the draft DCO Deadline 1 update: The Applicant is currently negotiating bespoke protective provisions with Anglian Water and a revised draft is currently being considered by Anglian Water. The Applicant is confident that the parties will be able to reach agreement before the end of Examination. | Draft under discussion |  | 2025-11-07
18-223 | APP/GH2.2 | Temporary Possession | Vodafone Limited | CAT 2 | [6 empty] | N/A | N/A | SU and known operational | Draft under discussion | Not required | Protective provisions for the benefit of electronic communications code operators have been included in Schedule 15 to the draft DCO Deadline 1 update: Vodafone Limited have not requested bespoke protective proovisions. Accordingly, the Applicant has not progressed any bespoke form of protective provisions or side agreement with Vodafone Limited. | None drafted |  | 2025-11-07
18–223, 11-116-a, 10–103-c, 10–103-b, 10–103-a, 05-055-b, 05–055-a, 05–051, 04-042, 04–041-a, 04–039-b, 04–039-a, 04–038, 04–037 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants Temporary Possession | Virgin Media Limited | CAT 2 | [6 empty] | N/A | N/A | SU and known operational | Draft under discussion | Not required | Protective provisions for the benefit of electronic communications code operators have been included in Schedule 15 to the draft DCO Deadline 1 update: Virgin Media Limited have not requested bespoke protective proovisions. Accordingly, the Applicant has not progressed any bespoke form of protective provisions or side agreement with Virgin Media Limited. | None drafted |  | 2025-11-07
18–223, 18–219, 15–207, 15–204-c, 15–204-b, 15–204-a, 15–202, 15–201, 14–195, 14–193, 14-191, 13–177-b, 13–177-a, 13–176, 13–174, 13–173, 12-166, 12-165-b, 12-165-a, 12–164, 12–163, 12–159, 12–158, 12–155-b, 12–155-a, 12–154, 12–153, 12–152, 12–151, 12-132, 12–131-c, 12–131-b, 12–131-a, 12–125, 11-121-b, 11–120-b, 11–120-a, 11-119-b, 11-116-c, 11-116-b, 11-116-a, 11-112, 11-111, 11–110-c, 11–110-b, 11–110-a, 10–104-c, 10–104-b, 10–104-a, 10–103-c, 10–103-b, 10–103-a, 09–091, 08-089, 08-088, 08-087, 08-086, 07–066-e, 07–066-d, 07–066-c, 07–066-a, 06–065, 06–058-c, 06–058-b, 06–058-a, 05-055-b, 05–055-a, 05–051, 04–046, 04–041-b, 04–041-a, 04-39-b, 04-038, 04–037, 03–035, 03–034-c, 03–034-b , 03–034-a, 03-033, 02–025-c, 02–025-b, 02–025-a, 01–012-b, 01–012-a, 01–008, 01–004, 01–002, 01–001 | APP/GH2.2 | Temporary Possession Freehold Acquisition Acquisition of Rights and Imposition of Restrictive Covenants | British Telecommunications Public Limited Company | CAT 2 | [6 empty] | N/A | N/A | SU and known operational | Draft under discussion | Not required | Protective provisions for the benefit of electronic communications code operators have been included in Schedule 15 to the draft DCO Deadline 1 update: British Telecommunications has not requested bespoke protective proovisions. Accordingly, the Applicant has not progressed any bespoke form of protective provisions or side agreement with British Telecommunications | None drafted |  | 2025-11-07
12-143, 12-144, 12-145, 12-146 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | British Railways Board Limited | CAT2 | [6 empty] | Crown Land |  |  |  |  | Discussions are ongoing with the Department for Transport to establish if this interest is Crown Land or has been transferred into the Historic Railways Estate Deadline 1 update: The Applicant continues to await confirmation as to the status of this land. | None drafted |  | 2025-11-07
09-091 |  | Temporary Possession | EXA Networks Limited | CAT2 | [11 empty] | Deadline 1 update: A newly identified interest, the Applicant awaits confirmation from EXA Networks Limited for whether bespoke protective provisions are required | None drafted |  | 2025-11-07
10-100 |  | Acquisition of Rights and Imposition of Restrictive Covenants | British Gas Limited | CAT 2 | [11 empty] | Deadline 1 update: A newly identified interest, the Applicant awaits confirmation from British Gas Limited for whether bespoke protective provisions are required | None drafted |  | 2025-11-07
11-116-a |  | Temporary Possession | ESP Electricity Limited | CAT 2 | [11 empty] | Deadline 1 update: A newly identified interest, the Applicant awaits confirmation from ESP Electricity Limited for whether bespoke protective provisions are required | None drafted |  | 2025-11-07
Add new lines as required…
1 Plot number from the Book of Reference
2 Plan reference number from the Book of Reference and Examination Library reference
3 Description of land and rights requested from the Book of Reference including restrictive covenants
4 A person is within category 1 if the applicant, after making diligent inquiry, knows that the person is an owner, lessee, tenant (whatever the tenancy period) or occupier of the land, see section 57 (1) of the Planning Act 2008
5 A person is within category 2 if the applicant, after making diligent inquiry knows that the person: interested in the land or has the power to sell or convey the land or to release the land, see section 57(20) of the Planning Act 2008
6 Person or organisation representing the interests of the affected person(s) - enter N/A if the affected person(s) are representing themselves
7 Reference number assigned to each interested party and affected person - for Planning Inspectorate use only
8 Reference number assigned to each relevant representation in the Examination Library
9 Reference number assigned to each written representation in the Examination Library
10 Reference number assigned to any other document in the Examination Library
11 Reference numbers assigned to all of the applicant's responses in the Examination Library including specific reference to relevant sections within documents
12 Likely duration of any temporary rights such as temporary possesion
13 Where crown land is affected, this column should include the anticipated date of consent from the crown authority
14 Narrative on negotiations to date

## Data types
Data types | Special category | Statutory undertaker (SU) and operational land status | Protective provisions status | Side agreements | Heads of Terms | Complete
Options | Crown land | Not SU | Not required | Not required | None drafted | Yes
| National Trust | SU and known operational | Draft under discussion | Draft under discussion | Draft under discussion | No
| Allotment | SU and unknown operational | Agreed | Agreed | Agreed
| Commons | SU and disputed operational | Agreed and in latest version of DCO
| Open space |  | No agreement on final version
Other