## Status
Green Hill Solar Farm Detailed Land and Rights Negotiations Tracker
Notes:
1. All interests which are not already acquired at the point of submission should be entered in this tracker and marked as complete (column 'w') when agreement with known interests is reached
2. Any non-agreement is also counted as an objection by an affected person(s) for the purpose of this tracker
3. An entry should also be made where the interest (or potential interest) holder is not known, to allow the relevant information to be added following diligent inquiry, negotiation etc
4. An editable version of this tracker must be submitted to The Planning Inspectorate with the application as an appendix to the Statement of Reasons
Book of Reference plot number 1 | Plan reference number 2 | Description of land and rights requested 3 | Party Name | Category | Agent/ representative 6 | When available Interested party/ affected person reference number 7 | When available Relevant representation reference number 8 | When available Written representation reference number 9 | Other document reference number 10 | Applicant's response references 11 | Duration of temporary rights 12 | Special category (Crown, allotment, National Trust etc) (Select from drop down list) | Special category - other information including confirmation of status 13 | Is the affected person a statutory undertaker and is the land operational? (Select from drop down list) | Protective provision status (Select from drop down list) | Side agreements (Select from drop down list) | Status of objection 14 | Heads of Terms (Select from drop down list) | Complete (Select from drop down list) | Last Updated [DD/MM/YYYY]
01–022, 02–023, 02–024 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Painesend Farm LLP | CAT 1 | Polly Sewell (Robinson & Hall) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing Deadline 3 update: HOT's are currently with the landowner's agent. There are only a couple of outstanding points remaining to be resolved. Deadline 5 update: HOT's discussions have progressed and are close to being agreed Deadline 7 update: HOTs have final few terms to be agreed. | Draft under discussion | No | 2026-04-08
05-052 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Sywell Aerodrome Limited | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Discussions with the landowner to address glint and glare concerns have resulted in the removal of solar panels from relevant areas. Deadline 1 update: Positive Negotiations ongoing Deadline 3 update: HOT's are currently with landowner for signature. Deadline 5 update: HOTs are in an agreed form and out for signing by landowner. Deadline 7 update: HOTs signed | Agreed | No | 2026-04-08
07-076 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | James William Mills | CAT 1 | Tom Arthey (Arthey Associates) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing Deadline 3 update: HOT's are currently with the landowner's agent for review. The agent is expecting to provide comments before the end of December. Deadline 5 update: HOTs with landowner's agent with no response to-date. Deadline 7 update: Meeting with agent agreed to review HOTs | Draft under discussion | No | 2026-04-08
07–077, 07–079, 07–080, 07–082, 07–083-a, 07–083-b, 08–084, 08–086, 08–089, 08–096-a, 08–096-b, 08–096-c | APP/GH2.2 | Freehold Acquisition Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | TOF Corporate Trustee Limited | CAT 1 | Giles Wordsworth (Savills) | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land within plots 07-082, 08-086 and 08-089 as part of the Scheme In relation to the remaining plots over which Acquisition of Rights and Imposition of Restrictive Covenants are required, draft HOTs sent to landowner 15/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing Deadline 3 update: HOT's have been signed. The Option agreement is currently being negotiated. Deadline 5 update: Option agreement ongoing Deadline 7 update: Option agreement ongoing | Agreed | No | 2026-04-08
08–094-a, 08–094-b | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Robert George Partridge | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing Deadline 3 update: HOT's have been agreed in principle with this landowner, however discussions are ongoing with the associated landowner of plot(s) 08–094-a and 08–094-b, who has also submitted representations into Examination. HOTs are being discussed further to reach an agreement with all landowners. Deadline 5 update: HOTs are with Mrs Partridge for review. The landowner has been advised to utilise a third party professional advisor to help represent the family in regard to the HOTs at the Applicant's cost. Deadline 7 update: Numerous correspondence with the Partridges and a site visit to discuss the cable route corridor between the Spinney and pylons. Landowners are reviewing possible options for professional representation to engage with HOTs. | Draft under discussion | No | 2026-04-08
08–094-a, 08–094-b | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Serien Partridge | CAT 1 |  |  | RR-1061 |  |  |  |  | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Negotiations ongoing although a few concerns in regard to badgers in the area / disruption from the works Deadline 3 update: Discussions with this landowner are ongoing. This landowner has made submissions into the Examination, including speaking at the Compulsory Acquisition Hearing on 10 December. The Applicant is seeking to address this landowner's concerns about the Scheme alongside seeking to agree HOTs in principle. Deadline 5 update: HOTs are with Mrs Partridge. The Applicant held a Teams meeting with Mr M Partridge 06/02/2026 to discuss their concerns regarding the land around the Spinney. Mr M Partridge has been advised to utilise a third party professional advisor to help represent the family in regard to the HOTs. Deadline 7 update: Numerous correspondence with the Partridges and a site visit to discuss the cable route corridor between the Spinney and pylons. Landowners are reviewing possible options for professional representation to engage with HOTs. | Draft under discussion | No | 2026-04-08
10–099-a, 10–099-b, 10–100, 10–101, 12–140, 12–142, 12–158 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Judith Thompson | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/2025 Option negotiations with solicitors now ongoing Deadline 3 update: Option negotiations with solicitors ongoing Deadline 5 update: Option negotiations with solicitors ongoing Deadline 7 update: Option Negotiations with solicitors ongoing | Agreed | No | 2026-04-08
10-102 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Timothy David Allinson | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Negotiations ongoing Deadline 3 update: Discussions are ongoing to agree HOTs with other landowner of plot 10-102 Deadline 5 update: See other landowner for same plot Deadline 7 updated: Please see comments for this plot, below. | Draft under discussion | No | 2026-04-08
10-102 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Alison Jocelyn Fitzhugh | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Negotiations ongoing although a concerns in regard to payment values Deadline 3 update: Discussions with this landowner are currently stalled due to differences in payment values Deadline 5 update: Agent has been provided new terms to inform landowner - awaiting return Deadline 7 update: Landowner has refused change of terms and does not wish to engage with HOTs. | Draft under discussion | No | 2026-04-08
03–033, 04–041-a, 04–041-b, 05–051, 05–055-b, 06–058-a, 06–058-b, 06–058-c, 07–066-a, 07–066-b, 07–066-c, 07–066-d, 07–066-e, 08–087, 09–091, 08–092, 08–093-a, 08–093-b, 08–093-c, 10–103-a, 10–103-b, 10–103-c, 10–104-a, 10–104-b, 10–104-c, 10–105, 10-106-a, 10-106-b, 10-107, 11–110-a, 11–110-b, 11–110-c, 11–111, 11–112, 11–114, 11–116-a, 11–116-b, 11–116-c, 12–125, 12–131-a, 12–131-b, 12–131-c, 12–132, 12–133, 12–134, 12–135, 12-138, 12–151, 12–152, 12–153, 12–154, 12–155-a, 12–155-b, 12–156, 12-158, 12–159, 12–162, 13–172, 13–174, 13–177-a, 13–177-b, 14–187-a, 14–187-b, 14–193, 14–195, 15–202, 15–204-a, 15–204-b, 15–204-c, 16–211 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | North Northamptonshire Council | CAT 1 | Robert Keeves (Underwoods) |  | RR-1243 |  |  |  |  | Crown Land | 15–202 The King's Most Excellent Majesty in the right of his Duchy Of Lancaster - in respect of presumed subsoil interest to the centreline of the highway | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 in respect of plots 10-104-b, 10-105, 11-110-a, 11-110-b, 11-110-c, 11-111, 11-112, 11-114, 12-131-a, 12-131-b, 12-131-c, 12-132, 12-133, 12-134, 12-135, 12-151, 12-152, 12-153, 12-154, 16-211. Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into HOT's for the remaining plots are not required as these plots relate to land that is public highway Deadline 1 update: Council have instructed a Surveyor to review and undertake HOTs negotiations - 06/11/2025 Deadline 3 update: Positive meeting was held with the Council's third party representing surveyor. The Council is reviewing terms and commercials with the intention to return these to the Applicant in December. Deadline 5 update: Agent reviewing HOTs. Chasing WNC for land transfer to NNC For Crown Plot 15-202 has been removed from the Book of Reference and the Land and Rights Negotiation Tracker as the Crown agents have returned to inform that there are no sub soil rights for this Plot. Deadline 7 update: Agent has responded and is reviewing HOTs | Draft under discussion | No | 2026-04-08
10–107 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Elizabeth Lee | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/2025 Option negotiations with solicitors now ongoing Deadline 3 update: Option negotiations with solicitors ongoing Deadline 5 update: Option negotiations with solicitors ongoing Deadline 7 update: Option Negotiations with solicitors ongoing | Agreed | No | 2026-04-08
10–106-a, 10–106-b, 10–107 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Julie Mary Thompson | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/2025 Option negotiations with solicitors now ongoing Deadline 3 update: Option negotiations with solicitors ongoing Deadline 5 update: Option negotiations with solicitors ongoing Deadline 7 update: Option Negotiations with solicitors ongoing | Agreed | No | 2026-04-08
10–106-a, 10–106-b, 10–107 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Barbara Jean Thompson | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/2025 Option negotiations with solicitors now ongoing Deadline 3 update: Option negotiations with solicitors ongoing Deadline 5 update: Option negotiations with solicitors ongoing Deadline 7 update: Option Negotiations with solicitors ongoing | Agreed | No | 2026-04-08
10–106-a, 10–106-b, 10–107 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Caroline Margaret Thompson | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/2025 Option negotiations with solicitors now ongoing Deadline 3 update: Option negotiations with solicitors ongoing Deadline 5 update: Option negotiations with solicitors ongoing Deadline 7 update: Option Negotiations with solicitors ongoing | Agreed | No | 2026-04-08
10–106-a, 10–106-b, 10–107 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Susan Emma Everton | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/2025 Option negotiations with solicitors now ongoing Deadline 3 update: Option negotiations with solicitors ongoing Deadline 5 update: Option negotiations with solicitors ongoing Deadline 7 update: Option Negotiations with solicitors ongoing | Agreed | No | 2026-04-08
10-108 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Melvyn John Mallard | CAT 1 | Andrew Middleditch (Bletsoes) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing Deadline 3 update: A number of landowners have instructed the same agent to negotiate HOTs. A template is being drafted which will be updated to incorporate individual's specific terms. The latest iteration has been with the agent for 6 weeks. Deadline 5 update: HOTs being advanced by landowner agent with positive progress Deadline 7 update: HOTs signed. | Draft under discussion | No | 2026-04-08
11–109-a, 11–109-b, 12–141 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Stephen Elderton | CAT 1 | Chris Templar (Bletsoes) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing Deadline 3 update: HOT's were sent to this PIL directly as they were not represented by the agent for the landowner on the same plots 11-109-a and 11-109-b. Deadline 5 update: HOTs being advanced by landowner agent with positive progress Deadline 7 update: HOTs template near to completion with final terms to be agreed. Representations made by the Eldertons into Examination are being addressed in parallel. | Draft under discussion | No | 2026-04-08
11–109-a, 11–109-b, 11–119-a, 11–119-b, 11–121-a, 11–121-b, 12–141 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Trescella Claudette Elderton | CAT 1 | Chris Templar (Bletsoes) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing Deadline 3 update: A number of landowners have instructed the same agent to negotiate HOTs. A template is being drafted which will be updated to incorporate individual's specific terms. The latest iteration has been with the agent for 6 weeks. Deadline 5 update: HOTs being advanced by landowner agent with positive progress Deadline 7 update: HOTs template near to completion with final terms to be agreed. Representations made by the Eldertons into Examination are being addressed in parallel. | Draft under discussion | No | 2026-04-08
03-028 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Alison Kate Linkletter | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/2025 Option negotiations with solicitors now ongoing Deadline 3 update: Option negotiations with solicitors ongoing Deadline 5 update: Option negotiations with solicitors ongoing Deadline 7 update: Option Negotiations with solicitors ongoing | Agreed | No | 2026-04-08
03-028 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Karen Elizabeth Linkletter | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/2025 Option negotiations with solicitors now ongoing Deadline 3 update: Option negotiations with solicitors ongoing Deadline 5 update: Option negotiations with solicitors ongoing Deadline 7 update: Option Negotiations with solicitors ongoing | Agreed | No | 2026-04-08
11–121-a, 11–121-b | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Michael Roy Elderton | CAT 1 | Chris Templar (Bletsoes) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing Deadline 3 update: A number of landowners have instructed the same agent to negotiate HOTs. A template is being drafted which will be updated to incorporate individual's specific terms. The latest iteration has been with the agent for 6 weeks. Deadline 5 update: HOTs being advanced by landowner agent with positive progress Deadline 7 update: HOTs template near to completion with final terms to be agreed. Representations made by the Eldertons into Examination are being addressed in parallel. | Draft under discussion | No | 2026-04-08
11–122, 12–123, 12–124 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Isobel Sarah Clarke | CAT 1 | Peter Moore (Bletsoes) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing Deadline 3 update: A number of landowners have instructed the same agent to negotiate HOTs. A template is being drafted which will be updated to incorporate individual's specific terms. The latest iteration has been with the agent for 6 weeks Deadline 5 update: HOTs being advanced by landowner agent with positive progress Deadline 7 update: HOTs template being addressed by agent and agreed in principle subject to residential developer review | Draft under discussion | No | 2026-04-08
12–126, 12–136-a, 12–136-b, 12–137 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Lavinia Mary De-Vere Padbury | CAT 1 | Kate Andrew (Hamlins) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into. Deadline 1 update: Interaction with CAT 1 legal representative but no negotiations to-date nor instruction of a surveyor. Deadline 3 update: The landowner's legal representative dealing with this matter is waiting for instructions from her client. The Applicant has offered to pay for the cost of the representing land agent for the landowner. Deadline 5 update: Awaiting landowner solicitor to respond regarding HOTs meeting Deadline 7 update: Agent has been allocated and discussions are progressing. Agents to review HOTs and respond | Draft under discussion | No | 2026-04-08
12-138 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Deborah Joanne Skinner | CAT 1 | Burges Salmon | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Negotiations ongoing with Landowner whilst other discussions ongoing to facilitate HOTS negotiations Deadline 3 update: Negotiations ongoing whilst other elements are under discussion with the same landowner. Deadline 5 update: Negotiations ongoing - Same situation as above Deadline 7 update: Negotiations ongoing - Same as Deadline 3 update | Draft under discussion | No | 2026-04-08
12–138, 12–148, 12–163-a, 12-163-b, 12–164, 12–165-a, 12–165-b, 13–169, 13–170, 13–171-a, 13–171-b | APP/GH2.2 | Freehold Acquisition Acquisition of Rights and Imposition of Restrictive Covenants | John William Banks Skinner | CAT 1 | Burges Salmon | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land within plots 12-164, 12-165-a, 12-165-b, 13-169, 13-170, 13-171-a and 13-171-b as part of the Scheme In relation to the remaining plots over which Acquisition of Rights and Imposition of Restrictive Covenants are required, draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Negotiations ongoing with Landowner whilst other discussions ongoing to facilitate HOTS negotiations Deadline 3 update: Negotiations ongoing whilst other elements are under discussion with the same landowner. Deadline 5 update: Negotiations ongoing - Same situation as above Deadline 7 update: Negotiations ongoing - Same as Deadline 3 update | Draft under discussion | No | 2026-04-08
12–143, 12–144, 12–145, 12–146, 13–184-a, 14–185, 14–186, 14–188, 14–189-a, 14–189-b, 15–200, 15–201, | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants Temporary Possession Freehold Acquisition | Spencer Douglas David Compton Marquess of Northampton | CAT 1 | Mark Henderson (In-House Estates) | [6 empty] | Crown Land | 12-143, 12-144, 12-145, 12-146 British Railways Board Limited hold CAT 2 interest in respect of rights contained in a conveyance dated 6 March 1972. | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land within plots 15-200 and 15-201 as part of the Scheme In relation to the remaining plots over which Acquisition of Rights and Imposition of Restrictive Covenants are required, terms have been discussed and agreed in principle with formal HOTs to be issued shortly. Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into. Deadline 1 Update : Positive negotiations on-going. Deadline 3 update: Positive negotiations on-going. HoTs issued with iterations in circulation. It is expected that terms will be agreed imminently. Deadline 5 update: There are two agreements in this landowners name one of which is signed and in legals being processed. The outstanding part is over land which Heidelberg have a leasehold interest in. The negotiations over that part are on-going, pending engagement with Heidelberg on their freehold land. Deadline 7 update: Option Negotiations with solicitors ongoing for two agreements. Awaiting Heidleberg to respond to HOTs and enter into negotiations for outstanding agreement. | Draft under discussion | No | 2026-04-08
12–138, 12–143, 12–144, 12–145, 12–146, 12–147, 12–156 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Heidelberg Materials UK Limited | CAT 1 | Pawel Zlocki (Heidelberg) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Owner of mines and minerals in respect of plot 12-138. The minerals code has been included in the draft DCO. HOT's not required in respect of plot 12-156 as it relates to land that is public highway. Deadline 1 update: Positive Negotiations ongoing and an external surveyor is being assigned to the HOTS Deadline 3 update: Awaiting landowner to instruct third party surveyor. HOT's are with landowner for consideration. Deadline 5 update: Awaiting response to instruct agent to advise Deadline 7 update: Awaiting response to instruct surveyor to represent Party for Leasehold Titles and also Freehold Title for Plot 12-147 | Draft under discussion | No | 2026-04-08
13–181, 13–182, 13–183 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Trinity Land Limited | CAT 1 | Guy Banham (Berrys) |  | RR-1254 |  |  |  |  | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Negotiations ongoing but Landowner has a number of concerns raised in Relevant Representation reference RR-1254, which are being reviewed and actioned. Deadline 3 update: Landowner requested to join the accompanied site visit on 11 December and make representations at the Compulsory Acquisition Hearing on 10 December. HOT's reside with the landowner for consideration. Deadline 5 update: Landowner now does not wish to progress at this time. It has been suggested the landowner utilises a third party agent to help represent them at the applicant's cost. Deadline 7 update: Landowner has not responded to latest correspondence so in the same scenario as per Deadline 5. | Draft under discussion | No | 2026-04-08
03-031 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Brian Richard Knight | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: The agent has signed HOTs and legal teams have been instructed. Deadline 3 update: Option negotiations with solicitors ongoing Deadline 5 update: Option negotiations with solicitors ongoing Deadline 7 update: Option negotiations with solicitors ongoing | Agreed | No | 2026-04-08
03-031 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | David Anthony Knight | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: The agent has signed HOTs and legal teams have been instructed. Deadline 3 update: Option negotiations with solicitors ongoing Deadline 5 update: Option negotiations with solicitors ongoing Deadline 7 update: Option negotiations with solicitors ongoing | Agreed | No | 2026-04-08
03-031 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Jennifer Rosemary Knight | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: The agent has signed HOTs and legal teams have been instructed. Deadline 3 update: Option negotiations with solicitors ongoing Deadline 5 update: Option negotiations with solicitors ongoing Deadline 7 update: Option negotiations with solicitors ongoing | Agreed | No | 2026-04-08
17–215-b, 17–215-a, 16–214, 16–213, 16–212, 16–210-a, 16-210-b, 15–207, 15–203-b, 15–203-a, 15–199, 15–198, 14–197, 14–194, 14–191 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants Freehold Acquisition | Compton Family Trust Corporation Limited | CAT 1 | Mark Henderson (In-House Estates) | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land within plots 14-191, 14-194, 15-198, 15-199, 15-203-a, 15-203-b, 15-207, 16-212, 16-213 and 16-214 as part of the Scheme In relation to the remaining plots over which Acquisition of Rights and Imposition of Restrictive Covenants are required, terms have been discussed and agreed in principle with formal HOTs to be issued shortly. Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing. Deadline 3 update: Positive negotiations on-going. HoTs issued with iterations in circulation. It is expected that terms will be agreed imminently. Deadline 5 update: The HoTs have been signed and the Option is being drafted by legals. Deadline 7 update: Option negotiations with solicitors ongoing | Agreed | No | 2026-04-08
04–044, 04–045, 04–046, 04–048 | APP/GH2.2 | Temporary Possession | Benjamin Keith Muttock | CAT 1 | Nick Denman (SDF) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing. Deadline 3 update: Third party access licence only. Ongoing negotiations are taking place with the landowner's instructed agent. Deadline 5 update: Terms in discussion with agent for third party access Deadline 7 update: Awaiting response from agent | Draft under discussion | No | 2026-04-08
04–044, 04–045, 04–046, 04–048 | APP/GH2.2 | Temporary Possession | Nanette Muttock | CAT 1 | Nick Denman (SDF) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing. Deadline 3 update: Third party access licence only. Ongoing negotiations are taking place with the landowner's instructed agent. Deadline 5 update: Terms in discussion with agent for third party access Deadline 7 update: Awaiting response from agent | Draft under discussion | No | 2026-04-08
03–032, 03–033 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | David John Beesley | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/2025 Option negotiations with solicitors now ongoing Deadline 3 update: Option negotiations with solicitors ongoing Deadline 5 update: Option negotiations with solicitors ongoing Deadline 7 update: Option negotiations with solicitors ongoing | Agreed | No | 2026-04-08
03–032, 03–033 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Joanna Mary Beesley | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/2025 Option negotiations with solicitors now ongoing Deadline 3 update: Option negotiations with solicitors ongoing Deadline 5 update: Option negotiations with solicitors ongoing Deadline 7 update: Option negotiations with solicitors ongoing | Agreed | No | 2026-04-08
03–035, 03–036 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Anthony James Middleton | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/2025 Option negotiations with solicitors now ongoing Deadline 3 update: Option negotiations with solicitors ongoing Deadline 5 update: Option negotiations with solicitors ongoing Deadline 7 update: Option negotiations with solicitors ongoing | Agreed | No | 2026-04-08
03–035, 03–036 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Anthony Mark Middleton | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Signed HOTs 15/08/2025 Option negotiations with solicitors now ongoing Deadline 3 update: Option negotiations with solicitors ongoing Deadline 5 update: Option negotiations with solicitors ongoing Deadline 7 update: Option negotiations with solicitors ongoing | Agreed | No | 2026-04-08
04–037, 04-042, 04–043 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Fiona Mary Smith | CAT 1 | Andrew Middleditch (Bletsoes) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing Deadline 3 update: Ongoing discussions with agent and landowner regarding BNG, directional drilling under ponds and woodland grants on preferred cable route for plot 04-037. A number of landowners have instructed the same agent to negotiate HOTs. A template is being drafted which will be updated to incorporate individual's specific terms. The latest iteration has been with the agent for 6 weeks Deadline 5 update: HOTs being advanced by landowner agent with positive progress - willing to enter into option subject to terms Deadline 7 update: HOTs signed | Agreed | No | 2026-04-08
04–037, 04-042, 04–043 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | P.S. Smith & Son | CAT 1 | Andrew Middleditch (Bletsoes) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing Deadline 3 update: Ongoing discussions with agent and landowner regarding BNG, directional drilling under ponds and woodland grants on preferred cable route for plot 04-037. A number of landowners have the same agent so a template is being devised to then incorporate individuals specifics. The latest iteration as been with the agents for 6 weeks. Deadline 5 update: HOTs being advanced by landowner agent with positive progress - willing to enter into option subject to terms Deadline 7 update: HOTs signed | Agreed | No | 2026-04-08
04-042 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Andrew Clive Middleditch | CAT 1 | Andrew Middleditch (Bletsoes) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing Deadline 3 update: A number of landowners have instructed the same agent to negotiate HOTs. A template is being drafted which will be updated to incorporate individual's specific terms. The latest iteration has been with the agent for 6 weeks Deadline 5 update: HOTs being advanced by landowner agent with positive progress - willing to enter into option subject to terms Deadline 7 update: HOTs signed | Agreed | No | 2026-04-08
04-042 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Christopher Thomas Bletsoe | CAT 1 | Andrew Middleditch (Bletsoes) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing Deadline 3 update: A number of landowners have instructed the same agent to negotiate HOTs. A template is being drafted which will be updated to incorporate individual's specific terms. The latest iteration has been with the agent for 6 weeks Deadline 5 update: HOTs being advanced by landowner agent with positive progress - willing to enter into option subject to terms Deadline 7 update: HOTs signed | Agreed | No | 2026-04-08
04–037, 04-042, 04–043 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Tristan Baxter-Smith | CAT 1 | Andrew Middleditch (Bletsoes) | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing Deadline 3 update: Ongoing discussions with agent and landowner regarding BNG, directional drilling under ponds and woodland grants on preferred cable route for plot 04-037. A number of landowners have instructed the same agent to negotiate HOTs. A template is being drafted which will be updated to incorporate individual's specific terms. The latest iteration has been with the agent for 6 weeks. Deadline 5 update: HOTs being advanced by landowner agent with positive progress - willing to enter into option subject to terms Deadline 7 update: HOTs signed | Agreed | No | 2026-04-08
04–047, 04–049, 04–050 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Frederick Richard Harris | CAT 1 | Gilbert Watchorn | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing Deadline 3 update: HOT's are currently with landowners agent. There are only a few terms left under discussion before negotiation of the agreement can commence. Deadline 5 update: Negotiations are positive and minimal points remaining to agree Deadline 7 update: HOTs signed | Agreed | No | 2026-04-08
05-054 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Philip Lionel Smith | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | Owner of mines and minerals. The minerals code has been included in the draft DCO. | None drafted | No | 2026-01-07
05–056, 05–057, 06–059, 06–060, 06–061, 06–062, 06–063, 06–065 | APP/GH2.2 | Freehold Acquisition Acquisition of Rights and Imposition of Restrictive Covenants | The Trustees of the G T Wilson Will Trust (Trustees of Holcot Estates LLP) | CAT 1 | Harry Edwards (Fisher German) | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land within plots 06-062 and 06-063 and 06-065 as part of the Scheme In relation to the remaining plots over which Acquisition of Rights and Imposition of Restrictive Covenants are required, draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: HOTs have been signed and are with legal instruction Deadline 3 update: Legal representatives are progressing the documents as per the commercials. It is expected that the Option will exchange soon. Deadline 5 update: Legally Complete | Agreed | Yes | 2026-02-18
01–001, 01–007, 01–012-a, 01–012-b, 01–019, 01–020, 02–025-a, 02–025-b, 02–025-c, 03–034-a, 03–034-b, 03–034-c, 12-127, 12-128, 12-129, 12-130, 04-038, 04-039-b | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | West Northamptonshire Council | CAT 1 | In house Property Team |  | RR-1251 |  |  |  |  | N/A | N/A | Not SU |  |  | HOT's for these plots are not required as these plots relate to land that is public highway Deadline 1 update: Two titles are being transferred to North Northamptonshire Council as they are outside WNC jurisdiction and WNC do not wish to engage with HOTS. Negotiations are ongoing with NNC as per the entry for North Northamptonshire Council in this tracker Deadline 3 update: Transfer of land between WNC to NNC is ongoing to allow HOT's to proceed with NNC. A third party agent has been instructed and is in negotiations with the Applicant. Deadline 5 update: Negotiations ongoing with North Northamptonshire's third party agent. Awaiting West Northamptonshire to remove Title to transfer Title to NNC Deadline 7 update: Transfer ongoing. Council agent facilitating. | None drafted | No | 2026-04-08
01-002 | APP/GH2.2 | Freehold Acquisition | Matthew Arnold Knight | CAT 1 | HCR Legal LLP | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
01–002, 01–003, 01–004, 01–005, 01–006, 01–011, 01–013, 01–015, 01–017 | APP/GH2.2 | Freehold Acquisition | John Arnold Knight | CAT 1 | HCR Legal LLP | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land in plots 01–002, 01–004, 01–005, 01–006, 01–011, 01–013, 01–015 and 01–017 as part of the Scheme. HOTs are not required in respect of plot 01-003; negotiations for the use of this land are being conducted with the owner of the freehold interest | Agreed | Yes | 2025-05-21
01–002, 01–003, 01–018 | APP/GH2.2 | Freehold Acquisition | Pamela Jane Knight | CAT 1 | HCR Legal LLP | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land in plots 01–002 and 01–018 as part of the Scheme. HOTs are not required in respect of plot 01-003; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | Yes | 2025-05-21
01-003 | APP/GH2.2 | Freehold Acquisition | Mark William Knight | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
01–008, 01–009, 01–010, 01–014, 01–016, 01–022, 02–023, 02–024 | APP/GH2.2 | Freehold Acquisition Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | J A Knight & Son (Farmers) Limited | CAT 1 | HCR Legal LLP | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land in plots 01-008, 01-009, 01-010, 01-014 and 01-016 as part of the Scheme HOTs are not required in respect of the remainder; negotiations for the use of this land are being conducted with the owner of the freehold interest | Agreed | Yes | 2025-05-21
02–029, 03–030 | APP/GH2.2 | Freehold Acquisition Acquisition of Rights and Imposition of Restrictive Covenants | Julian Lindsay Care | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land in plot 02-029 as part of the Scheme. To be confirmed if temporary access over plot 03-030 is required. | Agreed | Yes | 2025-05-21
02–029, 03–030 | APP/GH2.2 | Freehold Acquisition Acquisition of Rights and Imposition of Restrictive Covenants | Timothy Adrian Care | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land in plot 02-029 as part of the Scheme. To be confirmed if temporary access over plot 03-030 is required. | Agreed | Yes | 2025-05-21
05–053, 07–069, 07–070, 07–071, 07–072, 07–073, 07–074, 07–075, 07–077, 07–079, 07–080, 07–082, 08–083-a, 08–073-b, 08–084, 08–086, 08–089, 08–096-a, 08–096-b, 08–096-c | APP/GH2.2 | Freehold Acquisition Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | William John Pitts | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land in plots 05-053, 07-069, 07-070, 07-071 and 07-072 as part of the Scheme. To be confirmed if rights over plots 07-073, 07-074 and 07-075 are required. HOTs are not required in respect of the remainder; negotiations for the use of this land are being conducted with the owner of the freehold interest | Agreed | Yes | 2025-05-21
07–069, 07–070, 07–071 | APP/GH2.2 | Freehold Acquisition | Catherine Elizabeth Pitts | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
06-059 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Merrick John Russell Pinny | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | Deadline 5 update: The Interest is a tenant on this plot and therefore doesn't require a direct cable easement agreement | None drafted |  | 2026-02-25
06-064 | APP/GH2.2 | Freehold Acquisition | Henry Charles Michael Gurney | CAT 1 | HCR Legal LLP | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
06-064 | APP/GH2.2 | Freehold Acquisition | Jane Ann Gurney | CAT 1 | HCR Legal LLP | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
07–072, 07–073, 07–074, 07–075 | APP/GH2.2 | Freehold Acquisition Acquisition of Rights and Imposition of Restrictive Covenants | CERES (Northampton) Limited | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A |  |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No | 2025-05-21
07-069-c, 07-070-b, 07-072-a, 07-072-b, 07-072-c, 07-072-d, 07-073, 07-074 & 07-075 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Sywell Solar Limited | CAT 1 | [7 empty] | N/A | N/A |  |  |  | To be confirmed if rights over this plot are required Deadline 1 update The Applicant is in discussions with Sywell Solar Farm regarding the Scheme's interaction with their operational asset including shared access to these plots and has proposed a cooperation agreement. Deadline 5 update The Applicant has provided the first draft of the cooperation agreement for Sywell Solar Ltd to review. Deadline 7 update: Cooperation agreement ongoing | None drafted | No | 2026-04-08
07–077, 07–079, 07–080, 07–082, 08–083-a, 08–083-b, 08–084, 08–086, 08–089, 08–094-a, 08–094-b, 08–096-a, 08–096-b, 08–096-c | APP/GH2.2 | Freehold Acquisition Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | J. W. Pitts & Son | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A | Not SU |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | Agreed | Yes | 2025-05-21
08-090 | APP/GH2.2 | Freehold Acquisition | Robert Charles Minshull Stockdale | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
08-090 | APP/GH2.2 | Freehold Acquisition | Henry Robert Minshull Stockdale | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
11–109-a, 11–109-b, 11–119-a, 11–119-b, 11–121-a, 11–121-b, 12–141 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Ben Elderton | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No | 2025-05-21
11–122, 12–123, 12–124 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Tim Frost | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No | 2025-05-21
12-141 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Storefield Aggregates Limited | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | Licence to work mines and minerals. The minerals code has been included in the draft DCO. Deadline 3 update: The applicant is awaiting the agent for Storefield to engage and provide further information regarding the agreements between freeholder, M&M freeholder and licence holder. Deadline 5 update: Awaiting landowner's agent's response following the Applicant's numerous attempts to engage. Deadline 7 update: Meeting held between the Applicant and Storefield and coordination of works to avoid mineral sterilisation discussed. | None drafted | No | 2026-04-08
12-156 | APP/GH2.2 | Temporary Possession | Stanley John Bond | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | HOT's are not required as these plots relate to land that is public highway | None drafted | No | 2025-05-21
13–181, 13–183 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | John Hope | CAT 1 |  |  | RR-0560 |  |  |  |  | N/A | N/A | Not SU |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest. John Hope is a director of Trinity Land Limited. | None drafted | No | 2025-05-21
14–185, 14–186, 14–188 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Jodie Finch | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No | 2025-05-21
13–184-a, 13–184-b, 14–185, 14–186, 14–188, 14–189-a, 14–189-b | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Robert Jakeman | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No | 2025-05-21
16-210-a, 16-210-b | APP/GH2.2 | Temporary Possession | Abigail West | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | Yes | 2026-02-25
14–191, 14–194, 14–197, 15–203-a, 15–203-b, 16–212 | APP/GH2.2 | Freehold Acquisition | Tim Allebone | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | Negotiations for the use of this land are being conducted in parallel with the owner of the freehold interest and a draft Agreement is under review | Agreed | Yes | 25/02/2026
16–214, 16–213, 15–207 | APP/GH2.2 | Freehold Acquisition | Castle Ashby Farms | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No | 2025-05-21
17–215-b, 17–215-a | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Philip Skinner | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No | 2025-05-21
17–215-b, 17–215-a | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | William Skinner | CAT 1 | [7 empty] | N/A | N/A | Not SU |  |  | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No | 2025-05-21
18-219 | APP/GH2.2 | Freehold Acquisition | Meikle Farming Limited | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
18–222, 18–221, 18–220, 18–218, 17–217 | APP/GH2.2 | Freehold Acquisition Acquisition of Rights and Imposition of Restrictive Covenants | Ian James Meikle | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
18–222, 18–221, 18–220, 18–218, 17–217 | APP/GH2.2 | Freehold Acquisition Acquisition of Rights and Imposition of Restrictive Covenants | Andrew Meikle | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
18–222, 18–221, 18–220, 18–218, 17–217 | APP/GH2.2 | Freehold Acquisition Acquisition of Rights and Imposition of Restrictive Covenants Temporary Possession | Ruth Lesley Meikle | CAT 1 | Arnold Thomson Solicitors | [6 empty] | N/A | N/A | Not SU |  |  | An option agreement has been entered into with this landowner for the use of the land as part of the Scheme | Agreed | Yes | 2025-05-21
18–223, 18–220, 17–216-c, 17–216-b, 17–216-a | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Milton Keynes Council | CAT 1 |  |  | RR-1233 |  |  |  |  | N/A | N/A | Not SU |  |  | HOT's are not required as these plots relate to land that is public highway | None drafted | No | 2025-05-21
12-141 |  | Acquisition of Rights and Imposition of Restrictive Covenants | Ecton Estates Commercial Company Limited | CAT 1 | [12 empty] | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest Deadline 3 update: The applicant is awaiting the agent for Storefield to engage and provide further information regarding the agreements between freeholder, M&M freeholder and licence holder. Deadline 5 update: Awaiting landowner's agent's response following the Applicant's numerous attempts to engage. Deadline 7 update: Awaiting landowner's agent's response following the Applicant's numerous attempts to engage. | None drafted | No | 2026-04-08
08-089 |  | Freehold Acquisition | Ian Clegg | CAT 1 | [12 empty] | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No | 2025-05-21
08-089 |  | Freehold Acquisition | Mandy Clegg | CAT 1 | [12 empty] | HOTs are not required; negotiations for the use of this land are being conducted with the owner of the freehold interest | None drafted | No | 2025-05-21
05-054 |  | Acquisition of Rights and Imposition of Restrictive Covenants | Frederick Thomas Harris | CAT 1 | Gilbert Watchorn | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing Deadline 3 update: HOT's are currently with the landowners agent for consideration. There are only a few terms left under discussion before negotiation of the agreement can commence. Deadline 7 update: HOTs signed | Draft under discussion | No | 2026-04-08
05-054 |  | Acquisition of Rights and Imposition of Restrictive Covenants | Peter Andrew Harris | CAT 1 | Gilbert Watchorn | [6 empty] | N/A | N/A | Not SU |  |  | Draft HOTs sent to landowner 14/05/2025 Landowner has worked with the Applicant to complete survey works and the Applicant is hopeful that an agreement for the use of their land will be entered into Deadline 1 update: Positive Negotiations ongoing Deadline 3 update: HOT's are currently with the landowners agent for consideration. There are only a few terms left under discussion before negotiation of the Option agreement can commence. Deadline 5 update: Negotiations are positive and minimal points to agree Deadline 7 update: HOTs signed | Agreed | No | 2026-04-08
02-029-b |  | Freehold Acquisition | Acan Developments Limited | CAT 1 | Guy Banham (Berrys) | [6 empty] | N/A | N/A | Not SU |  |  | Deadline 3 update: For the material change a gate in the hedge is required for the movement of the public into the A3 right of way. ACAN are the owner of the hedgerow and have been contacted. Discussions are ongoing for an easement and mitigating requirements involving a new fence on the property. Deadline 5 update: Awaiting signature as HOTs all agreed Deadline 7 update: HOTs signed | Agreed | No | 2026-04-08
Add new lines as required…
1 Plot number from the Book of Reference
2 Plan reference number from the Book of Reference and Examination Library reference
3 Description of land and rights requested from the Book of Reference including restrictive covenants
4 A person is within category 1 if the applicant, after making diligent inquiry, knows that the person is an owner, lessee, tenant (whatever the tenancy period) or occupier of the land, see section 57 (1) of the Planning Act 2008
5 A person is within category 2 if the applicant, after making diligent inquiry knows that the person: interested in the land or has the power to sell or convey the land or to release the land, see section 57(20) of the Planning Act 2008
6 Person or organisation representing the interests of the affected person(s) - enter N/A if the affected person(s) are representing themselves
7 Reference number assigned to each interested party and affected person - for Planning Inspectorate use only
8 Reference number assigned to each relevant representation in the Examination Library
9 Reference number assigned to each written representation in the Examination Library
10 Reference number assigned to any other document in the Examination Library
11 Reference numbers assigned to all of the applicant's responses in the Examination Library including specific reference to relevant sections within documents
12 Likely duration of any temporary rights such as temporary possession
13 Where crown land is affected, this column should include the anticipated date of consent from the crown authority
14 Narrative on negotiations to date

## Statutory Undertakers
Green Hill Solar Farm Detailed Land and Rights Negotiations Tracker
Notes:
1. All interests which are not already acquired at the point of submission should be entered in this tracker and marked as complete (column 'w') when agreement with known interests is reached
2. Any non-agreement is also counted as an objection by an affected person(s) for the purpose of this tracker
3. An entry should also be made where the interest (or potential interest) holder is not known, to allow the relevant information to be added following diligent inquiry, negotiation etc
4. An editable version of this tracker must be submitted to The Planning Inspectorate with the application as an appendix to the Statement of Reasons
Book of Reference plot number 1 | Plan reference number 2 | Description of land and rights requested 3 | Party Name | Category | Agent/ representative 6 | When available Interested party/ affected person reference number 7 | When available Relevant representation reference number 8 | When available Written representation reference number 9 | Other document reference number 10 | Applicant's response references 11 | Special category (Crown, allotment, National Trust etc) (Select from drop down list) | Special category - other information including confirmation of status 13 | Is the affected person a statutory undertaker and is the land operational? (Select from drop down list) | Protective provision status (Select from drop down list) | Side agreements (Select from drop down list) | Status of objection 14 | Heads of Terms (Select from drop down list) | Complete (Select from drop down list) | Last Updated [DD/MM/YYYY]
08-093-c, 08–094-b, 08–096-c, 10-099-b, 10-102, 10-103-c, 10-104-c, 10–102, 10–103-b, 11-110-c, 11-112, 11-116-c, 12–166, 12–167, 13–173, 13–176, 13-177-a | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | National Grid Electricity Transmission plc | CAT 1/CAT 2 |  |  | RR-1240 |  |  |  | N/A | N/A | SU and known operational | Draft under discussion | Draft under discussion | The Applicant has engaged with National Grid in respect of the process to obtain the necessary easement and will be progressing this alongside the DCO application. Protective provisions for the benefit of National Grid are under negotiation and a draft version has been included in Schedule 15 to the draft DCO. It is anticipated that a side agreement may be required. Deadline 1 update: The Applicant has contacted National Grid's solicitors and is in discussions as to the form of PPs and a side agreement. Deadline 3 update: The Applicant has agreed with NGET the approach to be taken in relation to an agreement and PPs for existing NGET infrastructure. NGET are proposing two projects that include future works at or near the Grendon Substation – the Weston Marsh to East Lincolnshire Project and the Sundon to Grendon Reconductoring Project. The Applicant is seeking further technical information from NGET to understand how these projects will interact with the Scheme, which will help to inform discussions on how the PPs will be drafted to provide the necessary protections for NGET’s future projects and certainty for the Scheme. Deadline 5 updated: NGET's solicitors have shared a draft agreement for consideration. The Applicant is seeking a meeting with NGET to better understand its future projects in the area. Deadline 7 update: The Applicant is continuing discussions on the form of protective provisions and a side agreement, with the intention that the form can be agreed and included in the DCO when made by the Secretary of State. | Draft under discussion |  | 2025-11-07
03–030, 08–088 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | On Tower UK 1 Limited | CAT 1 | [6 empty] | N/A | N/A | SU and known operational | Draft under discussion | Not required | To be confirmed if rights over this plot are required Protective provisions for the benefit of electronic communications code operators have been included in Schedule 15 to the draft DCO Deadline 1 Update: On Tower UK 1 Limited has not requested bespoke protective provisions. Accordingly, the Applicant has not progressed any bespoke form of protective provisions or side agreement with On Tower UK 1 Limited. Deadline 7 update: No request for bespoke protective provisions has been received. | None drafted |  | 2026-04-08
04–039-a, 04–039-b, 05-055-b, 11–112, 11–114, 12–127, 12–128, 12–134, 12–135, 12–149, 12–150 | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | National Highways Limited | CAT 1 |  |  | RR-1241 |  |  |  | N/A | N/A | SU and known operational | Draft under discussion | Draft under discussion | Protective provisions for the benefit of National Highways are under negotiation and a draft version has been included in Schedule 15 to the draft DCO. It is anticipated that a side agreement may be required. Deadline 1 update: The Applicant is currently negotiating bespoke protective provisions with National Highways. The Applicant has returned a revised draft to National Highways and awaits further comments. Negotiations are progressing positively and the Applicant anticipates that the parties will be able to reach agreement before the end of Examination. Deadline 3 update: Solicitors for the Applicant and for National Highways met on 16 December 2025 to discuss the protective provisions. Discussions are progressing and a revised draft of the PPs will be shared with National Highways in early January for consideration. Deadline 5 update: Draft PPs and agreement are with National Highways for consideration. The Applicant awaits comments. Deadline 7 update: Protective provisions are agreed and included in the draft DCO. A side agreement has been entered into. | Agreed | Yes | 2026-04-08
01–008, 01–010, 01-013, 01–014, 02-025-a, 02-025-c, 02-029, 03-032, 03-034-c, 04–042, 04–045, 04-046, 04–048, 04-049, 04-050, 05-054, 06-058-a, 06-058-b, 06-058-c, 06-065, 07-066-a, 07-066-b, 07-066-c, 07-066-d, 07-066-e, 07–070, 07–071, 07–072, 07–073, 07–074, 07–075, 07–076, 07–077, 07–079, 07–080, 07–082, 08–083-a, 08–083-b, 08–084, 08–086, 08-088, 08-089, 08–090, 09-091, 08-093-c, 08-094-a 08–094-b, 10-099-b, 10-103-a, 10–103-c 10-104-c, 11-109-a, 11-110-a, 11-110-b, 11-110-c, 11-111, 11-112, 11-116-a, 11–119-a, 11-119-b, 11-120-a, 11-120-b, 12-131-a, 12-131-b, 12-131-c, 12-132, 12-138, 12–143, 12–144, 12–145, 12–146, 12-147, 12-148, 12-151, 12-152, 12-153, 12-154, 12-155-a, 12-155-b, 12-156, 12-159, 12-162, 12-163-a, 12–165-a, 12–165-b, 12–167, 13–169, 13–171-b, 13–177-b, 13–184-a, 13–184-b, 14–186, 14-187-b, 14-188, 14-194, 14-195, 15-200, 15–201, 15-202, 15–203-a, 15-204-a, 15-207, 16–212, 16–214, 17-215-a, 17-215-b, 17-216-a, 17-216-b, 17-216-c, 17-217, 18-219, 18-220, 18-221, 18-223 | APP/GH2.2 | Freehold Acquisition Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants No Compulsory Acquisition or Temporary Possession Powers Being Sought | National Grid Electricity Distribution (East Midlands) plc | CAT 2 | [6 empty] | N/A | N/A | SU and known operational | Draft under discussion | Draft under discussion | Protective provisions for the benefit of National Grid Electricity Distribution are under negotiation and a draft version has been included in Schedule 15 to the draft DCO. It is anticipated that a side agreement may be required. Deadline 1 update: National Grid Electricity Distribution (East Midlands) plc has not requested bespoke protective provisions. The Applicant is seeking confirmation from National Grid Electricity Distribution that it is content with the protective provisions for its benefit included in the draft DCO. Deadline 3 update: The Applicant has received data from NGED as to the location of its assets, which has informed a number of amendments to the Book of Reference. A markup of the PPs and a draft side agreement have been received from NGED. The Applicant is currently reviewing these and will shortly be providing comments to NGED. Deadline 5 update: NGED have provided further comments on the PPs and side agreement which the Applicant is currently considering. Deadline 7 update: Protective provisions are agreed and included in the draft DCO. A side agreement has been entered into. | Agreed | Yes | 2026-04-08
08-088, 07-066-a, 07-082, 08-086, 08-087, 08-089, 08-090. 10-099-a, 10-100, 10-103-a, 10-103-b, 10-103-c, 10-104-a, 11-110-a, 11-110-b, 11-110-c, 11-111, 11-112, 11-116-a, 13-177-b, 15-201, 15-202 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | Cadent Gas Limited | CAT 1/CAT 2 | [6 empty] | N/A | N/A | SU and known operational | Draft under discussion | Draft under discussion | To be confirmed if rights over this plot are required Protective provisions for the benefit of Cadent Gas are under negotiation and a draft version has been included in Schedule 15 to the draft DCO. It is anticipated that a side agreement may be required. Deadline 1 update: Cadent has not requested bespoke protective provisions. The Applicant is seeking confirmation from Cadent that it is content with the protective provisions for its benefit included in the draft DCO. Deadline 5 updated: The Applicant has contacted Cadent and is negotiating PPs and a side agreement with its solicitor. The PPs and agreement are currently with Cadent's solicitor for consideration. Deadline 7 update: Protective provisions are agreed and included in the draft DCO. A side agreement has been agreed. | Agreed | Yes | 2026-04-08
12-138, 12–139, 12–160, 12–161 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | The Environment Agency | CAT 1 |  |  | RR-1224 |  |  |  | N/A | N/A | SU and known operational | Draft under discussion | Not required | Protective provisions for the benefit of the Environment Agency are under negotiation and a draft version has been included in Schedule 15 to the draft DCO. Deadline 1 update: Draft protective provisions have been provided to the EA for consideration and the Applicant awaits comments. The Applicant is confident that the parties will be able to reach agreement before the end of Examination. Deadline 3 update: The Applicant provided detail of potential flood risk activities to the EA on 9 December. The EA is currently considering the proposed PPs alongside the technical data. Deadline 5 update: The EA has confirmed it is content to disapply the need to obtain flood risk activity provided its standard PPs are contained in the DCO. The Applicant is considering the standard form of PPs. Deadline 7 update: The EA's standard form of protective provisions are included in the draft DCO. | Agreed | Yes | 2026-04-08
06–058-a, 06–058-b, 06–058-c, 09–091, 12–131-a, 12–131-b, 12–131-c, 12–132, 12-133, 12–134, 12-135, 12–149, 12–150, 12–151, 12–152, 12–153, 12–154, 12–155-a, 12–155-b, 12–156, 12–161, 13–177-a, 13–184-a, 13–184-b, 14–187-b | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants | Zayo Group UK Limited | CAT 2 | [6 empty] | N/A | N/A | SU and known operational | Draft under discussion | Not required | Protective provisions for the benefit of electronic communications code operators have been included in Schedule 15 to the draft DCO Deadline 7 update: No request for bespoke protective provisions has been received. | None drafted |  | 2026-04-08
02–025-a, 02–025-b, 02–025-c, 03–034-a, 03–034-b, 03–034-c, 05–055-a, 05-055-b, 06–058-a, 06–058-b, 06–058-c, 06–065, 07–066-e, 08-087, 08–093-a, 08–093-b, 08–093-c, 12-155-b, 12-164, 13-173, 13–176, 13–177-a, 13–177-b, 14–193, 14–195, 15–201, 15–202, 15–204-b, 15–204-c | APP/GH2.2 | Temporary Possession Acquisition of Rights and Imposition of Restrictive Covenants Freehold Acquisition | Gigaclear Limited | CAT 2 | [6 empty] | N/A | N/A | SU and known operational | Draft under discussion | Not required | Protective provisions for the benefit of electronic communications code operators have been included in Schedule 15 to the draft DCO Deadline 1 update: Gigaclear Limited have not requested bespoke protective proovisions. Accordingly, the Applicant has not progressed any bespoke form of protective provisions or side agreement with Gigaclear Limited. Deadline 7 update: No request for bespoke protective provisions has been received. | None drafted |  | 2026-04-08
02-025-c, 02–029, 03–036, 04–037, 04–041-a, 04–042, 04–049, 04–050, 05–052, 05–053, 05–054, 06–058-a, 06–058-b, 06–058-c, 06–065, 07–066-a, 07–066-d, 07–066-e, 07–069, 08–090, 09–091, 10–107, 10–108, 11–109-a, 11–110-c, 11-111, 11-112, 11-116-a, 11–119-a, 11–119-b, 11–120-a, 11–122, 12–123, 12–124, 12–125, 12–131-a, 12–131-b, 12–131-c, 12–151, 12–152, 12–153, 12–154, 12–155-a, 13-173, 13–176, 13–177-a, 13–177-b, 14–187-a, 14–187-b, 14-191, 14–193, 14–195, 14–197, 15–202, 15–203-b, 15–204-a, 15-204-c, 15–207, 16–212, 16-213, 16–214, 17–215-a, 17–216-a, 17–216-b, 17–216-c | APP/GH2.2 | Freehold Acquisition Acquisition of Rights and Imposition of Restrictive Covenants Temporary Possession | Anglian Water Services Limited | CAT 2 |  |  | RR-1214 |  |  |  | N/A | N/A | SU and known operational | Draft under discussion | Not required | Protective provisions for the benefit of Anglian Water are under negotiation and a draft version has been included in Schedule 16 to the draft DCO Deadline 1 update: The Applicant is currently negotiating bespoke protective provisions with Anglian Water and a revised draft is currently being considered by Anglian Water. The Applicant is confident that the parties will be able to reach agreement before the end of Examination. Deadline 3 update: The form of PPs included in Revision A of the draft DCO has been agreed with Anglian Water. | Agreed | Yes | 2025-11-07
18-223 | APP/GH2.2 | Temporary Possession | Vodafone Limited | CAT 2 | [6 empty] | N/A | N/A | SU and known operational | Draft under discussion | Not required | Protective provisions for the benefit of electronic communications code operators have been included in Schedule 15 to the draft DCO Deadline 1 update: Vodafone Limited have not requested bespoke protective proovisions. Accordingly, the Applicant has not progressed any bespoke form of protective provisions or side agreement with Vodafone Limited. Deadline 7 update: No request for bespoke protective provisions has been received. | None drafted |  | 2026-04-08
18–223, 11-116-a, 10–103-c, 10–103-b, 10–103-a, 05-055-b, 05–055-a, 05–051, 04-042, 04–041-a, 04–039-b, 04–039-a, 04–038, 04–037 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants Temporary Possession | Virgin Media Limited | CAT 2 | [6 empty] | N/A | N/A | SU and known operational | Draft under discussion | Not required | Protective provisions for the benefit of electronic communications code operators have been included in Schedule 15 to the draft DCO Deadline 1 update: Virgin Media Limited have not requested bespoke protective proovisions. Accordingly, the Applicant has not progressed any bespoke form of protective provisions or side agreement with Virgin Media Limited. Deadline 7 update: No request for bespoke protective provisions has been received. | None drafted |  | 2026-04-08
18–223, 18–219, 15–207, 15–204-c, 15–204-b, 15–204-a, 15–202, 15–201, 14–195, 14–193, 14-191, 13–177-b, 13–177-a, 13–176, 13–174, 13–173, 12-166, 12-165-b, 12-165-a, 12–164, 12–163, 12–159, 12–158, 12–155-b, 12–155-a, 12–154, 12–153, 12–152, 12–151, 12-132, 12–131-c, 12–131-b, 12–131-a, 12–125, 11-121-b, 11–120-b, 11–120-a, 11-119-b, 11-116-c, 11-116-b, 11-116-a, 11-112, 11-111, 11–110-c, 11–110-b, 11–110-a, 10–104-c, 10–104-b, 10–104-a, 10–103-c, 10–103-b, 10–103-a, 09–091, 08-089, 08-088, 08-087, 08-086, 07–066-e, 07–066-d, 07–066-c, 07–066-a, 06–065, 06–058-c, 06–058-b, 06–058-a, 05-055-b, 05–055-a, 05–051, 04–046, 04–041-b, 04–041-a, 04-39-b, 04-038, 04–037, 03–035, 03–034-c, 03–034-b , 03–034-a, 03-033, 02–025-c, 02–025-b, 02–025-a, 01–012-b, 01–012-a, 01–008, 01–004, 01–002, 01–001 | APP/GH2.2 | Temporary Possession Freehold Acquisition Acquisition of Rights and Imposition of Restrictive Covenants | British Telecommunications Public Limited Company | CAT 2 | [6 empty] | N/A | N/A | SU and known operational | Draft under discussion | Not required | Protective provisions for the benefit of electronic communications code operators have been included in Schedule 15 to the draft DCO Deadline 1 update: British Telecommunications has not requested bespoke protective proovisions. Accordingly, the Applicant has not progressed any bespoke form of protective provisions or side agreement with British Telecommunications Deadline 7 update: No request for bespoke protective provisions has been received. | None drafted |  | 2026-04-08
12-143, 12-144, 12-145, 12-146 | APP/GH2.2 | Acquisition of Rights and Imposition of Restrictive Covenants | British Railways Board Limited | CAT2 | [6 empty] | Crown Land |  |  |  |  | Discussions are ongoing with the Department for Transport to establish if this interest is Crown Land or has been transferred into the Historic Railways Estate Deadline 1 update: The Applicant continues to await confirmation as to the status of this land. Deadline 3 update: The Applicant continues to await confirmation as to the status of this land. Deadline 5 update: The Applicant continues to await confirmation as to the status of this land. Deadline 7 update: The Applicant has received confirmation that the British Railways Board do not hold an interest in this land. | None drafted |  | 2025-11-07
09-091 |  | Temporary Possession | EXA Networks Limited | CAT 2 | [11 empty] | Deadline 1 update: A newly identified interest, the Applicant awaits confirmation from EXA Networks Limited for whether bespoke protective provisions are required Deadline 7 update: This party has been confirmed as not holding an interest in this land | None drafted |  | 2025-11-07
10-100 |  | Acquisition of Rights and Imposition of Restrictive Covenants | British Gas Limited | CAT 2 | [11 empty] | Deadline 1 update: A newly identified interest, the Applicant awaits confirmation from British Gas Limited for whether bespoke protective provisions are required Deadline 7 update: No request for bespoke protective provisions has been received. | None drafted |  | 2026-04-08
11-116-a |  | Temporary Possession | ESP Electricity Limited | CAT 2 | [11 empty] | Deadline 1 update: A newly identified interest, the Applicant awaits confirmation from ESP Electricity Limited for whether bespoke protective provisions are required Deadline 7 update: No request for bespoke protective provisions has been received. | None drafted |  | 2026-04-08
09-091 |  | Temporary Possession | EXA Infrastructure Limited | CAT 2 | [11 empty] | Deadline 7 update: The Applicant has confirmed the extent of EXA Infrastructure Limited's assets within the Order Limits. No bespoke protective provisions have been requested. | None drafted |  | 2026-04-08
Add new lines as required…
1 Plot number from the Book of Reference
2 Plan reference number from the Book of Reference and Examination Library reference
3 Description of land and rights requested from the Book of Reference including restrictive covenants
4 A person is within category 1 if the applicant, after making diligent inquiry, knows that the person is an owner, lessee, tenant (whatever the tenancy period) or occupier of the land, see section 57 (1) of the Planning Act 2008
5 A person is within category 2 if the applicant, after making diligent inquiry knows that the person: interested in the land or has the power to sell or convey the land or to release the land, see section 57(20) of the Planning Act 2008
6 Person or organisation representing the interests of the affected person(s) - enter N/A if the affected person(s) are representing themselves
7 Reference number assigned to each interested party and affected person - for Planning Inspectorate use only
8 Reference number assigned to each relevant representation in the Examination Library
9 Reference number assigned to each written representation in the Examination Library
10 Reference number assigned to any other document in the Examination Library
11 Reference numbers assigned to all of the applicant's responses in the Examination Library including specific reference to relevant sections within documents
12 Likely duration of any temporary rights such as temporary possesion
13 Where crown land is affected, this column should include the anticipated date of consent from the crown authority
14 Narrative on negotiations to date

## Data types
Data types | Special category | Statutory undertaker (SU) and operational land status | Protective provisions status | Side agreements | Heads of Terms | Complete
Options | Crown land | Not SU | Not required | Not required | None drafted | Yes
| National Trust | SU and known operational | Draft under discussion | Draft under discussion | Draft under discussion | No
| Allotment | SU and unknown operational | Agreed | Agreed | Agreed
| Commons | SU and disputed operational | Agreed and in latest version of DCO
| Open space |  | No agreement on final version
Other