## Current Position
Affected Person / Party | BoR Plot Numbers in which Party has an interest arranged by applicable Work No | Work No (purpose for which acquisition of freehold interest or rights in plots are sought) | Interest Held by Party | Brief Summary of Powers Sought in each Plot | Current Status of Negotiations | Summary Progress to Date | Objections Made to Compulsory Purchase Powers and the Applicant's Responses | Has Voluntary Agreement been Reached? | Progress made since last update
Albans, Julie Ellen | 3-217, 3-218, 3- 219 | 6 - Cooling & Wastewater discharge pipeline | Freehold - 3- 218 Riparian Owner - 3-217, 3-219 Occupiers - 3-218 | New Rights - 3-217, 3-218, 3-219 | The terms of an Option agreement for variation of existing easement to enable the Applicant to benefit from the existing water discharge pipes and cathodic protection are agreed but legal completion is awaiting approval of the Alban’s lenders. Applicant chasing. Intention to complete prior to end 2025. | With solicitors
Albans, Nigel David | 3-217, 3-218, 3-219 | 6 - Cooling & Wastewater discharge pipeline | Freehold - 3-218 Riparian Owner - 3-217, 3-219 Occupiers - 3-218 | New Rights - 3-217, 3-218, 3-219 | The terms of an Option agreement for variation of existing easement to enable the Applicant to benefit from the existing water discharge pipes and cathodic protection are agreed but legal completion is awaiting approval of the Alban’s lenders. Applicant chasing. Intention to complete prior to end 2025. | With solicitors
Associated Waterway Services Limited | 3-127 | 5 - Cooling Water Abstraction | Leasehold - 3-195, 3-199, 3-200, 3-202, 3-203, 3-204 Occupiers - 3-127, 3-195, 3-199, 3-200, 3-202, 3-203, 3-204 | Temporary Use - 3-195, 3-199, 3-200, 3-202, 3-203, 3-204 New Rights - 3-127 | PD Ports connected company. CA powers sought as a backup in case it becomes necessary for the Applicant to take control in order to moor and unload boats and then transport through PD Ports' yard. See comments in respect of PD Ports below. | See PD Ports
| 3-195 | 9D - Temporary Haul Route
| 3-199, 3-200, 3-202, 3-203, 3-204 | 9E - Jetty & crane offloading for waterborne transport and river barges
Barclays Security Trustee Limited | 3-209 | 6 - Cooling & Wastewater discharge pipeline | Category 2 - 3-209 | New Rights -3-209 | Former lender to Maclean - no current interest in the DCO land | See Maclean
Belton Wright, Jonathan | 1-07, 1-12, 1-13, 1-14, 1-16, 1-17, 1-18, 1-19, 1-20, 1-21, 1-23, 1-24, 1-25, 1-28, 2-29 | 8A - Vehicular Site Access | Freehold - 1-22, 1-26 Occupiers - 1-07, 1-10, 1-11, 1-13, 1-17, 1-20, 1-24, 1-26, 1-28 Category 2 - 1-12, 1-13, 1-14, 1-15, 1-16, 1-17, 1-18, 1-19, 1-20, 1-21, 1-23, 1-24, 1-25, 1-27, 1-28, 2-29, 2-42, 2-43, 2-44, 2-47, 2-48, 2-49, 2-52, 2-54, 2-55, 2-56, 2-57, 2-58, 2-60, 2-61, 2-62, 2-66 | Temporary Use - 1-10, 1-11, 1-22, 1-26, 2-55 New Rights - 1-07, 1-12, 1-13, 1-14, 1-15, 1-16, 1-17, 1-18, 1-20, 1-23, 1-24, 1-25, 1-27, 1-28, 2-29, 2-42, 2-43, 2-44, 2-48, 2-49, 2-52, 2-54, 2-56, 2-57, 2-58, 2-60, 2-61, 2-62, 2-66 Freehold Acquisition - 1-19, 1-21, 2-47 | Option agreement for access to A18 via Skew Bridge completed 1st April 2025. Negotiations in respect of updating previous Heads of Terms concerning the temporary laydown area on Plot 1-26 picked up again - Heads of Terms are ready for issue but awaiting some technical detail. The freehold acquisition powers are required in case the restrictive covenants could be enforced - the Applicant considers that the prospects of successful enforcement are remote but wishes to protect against any potential action by the beneficiary that might delay implementation of the project. | Skew Bridge Deed completed. Heads of Terms in respect of Laydown Area under negotiation
| 1-19, 1-20, 1-21 | 8B - Gatehouse & Layby
| 1-07, 1-12, 1-13, 1-14, 1-15, 1-16, 1-17, 1-18, 1-19, 1-20, 1-21 | 8C - Gatehouse Services
| 2-42, 2-43, 2-44, 2-47, 2-48, 2-49, 2-52, 2-54, 2-55, 2-56, 2-57, 2-58, 2-60, 2-61, 2-62, 2-66 | 8D - Emergency Operational Access
| 1-26, 1-27 | 9A - Construction & Temporary Laydown
| 1-10, 1-11, 1-12, 1-13, 1-14, 1-16, 1-17, 1-18, 1-19, 1-20, 1-21, 1-22, 1-23, 1-24, 1-25, 1-28, 2-29 | 9B - Temporary Access Area to Construction & laydown area
| 1-07, 1-12, 1-13, 1-14, 1-15 | 9C - Temporary Construction and Laydown Area for Replacement of Private Bridge
| 1-12, 1-14, 1-15, 1-16, 1-18, 1-19, 1-21, 1-23, 1-25, 1-27 | 10 - Potential Landscaping and Planting Area
British Telecommunications Public Limited Company | 2-102, 3-112, 3-120, 3-121, 3-122, 3-123 | 1C - Power station staff support facilities | Occupiers - 1-03a, 1-03b, 1-03c , 2-37, 2-39, 2-67, 2-83, 2-90, 2-92, 2-100, 2-102, 2-104, 2-106, 2-110, 3-111, 3-112, 3-120, 3-121, 3-122, 3-123, 3-128, 3-129, 3-130, 3-131, 3-132, 3-133, 3-134, 3-135, 3-136, 3-137, 3-138, 3-139, 3-143, 3-145, 3-146, 3-147, 3-153, 3-154, 3-156, 3-157, 3-171, 3-173, 3-174, 3-176, 3-177, 3-178, 3-179, 3-180, 3-181, 3-182, 3-183, 3-187, 3-191, 3-192, 3-210, 3-211, 3-220, 3-225 | Temporary Use - 2-100, 3-171 New Rights - 1-03a, 1-03b, 1-03c , 2-37, 2-39, 2-67, 2-104, 3-111, 3-128, 3-129, 3-130, 3-131, 3-132, 3-133, 3-134, 3-135, 3-136, 3-137, 3-138, 3-139, 3-143, 3-145, 3-146, 3-147, 3-153, 3-154, 3-156, 3-157, 3-173, 3-174, 3-176, 3-177, 3-178, 3-179, 3-180, 3-181, 3-182, 3-183, 3-187, 3-191, 3-192, 3-210, 3-211, 3-220, 3-225 Freehold Acquisition - 2-83, 2-90, 2-92, 2-102, 2-106, 2-110, 3-112, 3-120, 3-121, 3-122, 3-123 | BT hold equipment in the plots identified in the Book of Reference. The Applicant does not intend to extinguish, vary, or otherwise impact upon that equipment. To the extent that the Applicant's works have any potential to impact upon such equipment, this is a matter for engineer engagement and Protective Provisions. The CA powers for title acquisition are required in case it is necessary to remove restrictions on title. | No land rights or interests required from BT
| 2-83 | 3A - National Grid NG Compound
| 2-102, 2-104, 3-120, 3-123, 3-143, 3-145, 3-153, 3-154, 3-156 | 4A - Primary Electrical connection & Distribution facilities
| 2-104 | 4B - Alternative Electrical connection & Distribution facilities
| 2-102, 2-106, 2-110, 3-111, 3-112, 3-128, 3-129, 3-130, 3-131, 3-132, 3-133, 3-134, 3-157 | 5 - Cooling Water Abstraction
| 2-102, 3-120, 3-122, 3-123, 3-135, 3-136, 3-137, 3-138, 3-139, 3-143, 3-146, 3-147, 3-153, 3-173, 3-174, 3-176, 3-177, 3-178, 3-179, 3-180, 3-183, 3-210, 3-211, 3-220, 3-225 | 6 - Cooling & Wastewater discharge pipeline
| 2-102, 3-120, 3-121, 3-122, 3-123, 3-135, 3-136, 3-137, 3-138, 3-139, 3-143, 3-147, 3-153 | 7 - Public Water
| 1-03b, 2-37, 2-39, 2-83, 2-90, 2-92, 2-106 | 8A - Vehicular Site Access
| 1-03a, 1-03b, 1-03c | 8C - Gatehouse Services
| 2-83, 2-67 | 8D - Emergency Operational Access
| 2-100, 2-102, 2-110 | 9A - Construction & Temporary Laydown
| 2-37, 2-39, 2-83, 2-90, 2-92 | 9B - Temporary Access Area to Construction & laydown area
| 2-106, 3-112, 3-128, 3-129, 3-130, 3-131, 3-132, 3-133, 3-134, 3-171 | 9D - Temporary Haul Route
| 3-181, 3-182, 3-187, 3-191, 3-192 | 10 - Potential Landscaping and Planting Area
Canal & River Trust | 3-124, 3-125, 3-126, 3-127, 3-128, 3-158, 3-159, 3-160, 3-161, 3-162, 3-163, 3-164, 3-165, 3-166, 3-167, 3-168 | 5 - Cooling Water Abstraction | Freehold - 2-30, 2-31, 2-32, 2-33, 3-159, 3-160, 3-161, 3-162, 3-163, 3-164, 3-165, 3-166, 3-167, 3-168, 3-200, 3-201, 3-202, 3-204 Occupiers - 2-30, 2-31, 2-32, 2-33, 3-124, 3-125, 3-126, 3-127, 3-128, 3-158, 3-159, 3-160, 3-161, 3-162, 3-163, 3-164, 3-165, 3-166, 3-167, 3-168, 3-199, 3-201 Category 2 - 3-193, 3-194, 3-195, 3-203 | Temporary Use for Haul Road - 3-193, 3-194, 3-195, 3-199, 3-200, 3-201, 3-202, 3-203, 3-204 Temporary use for construction of pumping station - 3-163, 3-164 Benefit of existing lease in respect of North Pilfrey Bridge - 2-30, 2-31, 2-32, 2-33 Interests in Public Highway - 3-124, 3-125, 3-126, 3-127, 3-128 Freehold Acquisition - 3-166, 3-168 Easement rights for water connection pipe and power cable - 3-158, 3-159, 3-160, 3-161, 3-162, 3-165, 3-167 | Deed of variation in respect of North Pilfrey Bridge air easement completed. Agreement was previously reached in principle for the permanent acquisition of land for the pumping station together with easements for the canal water abstraction pipe and temporary licence for the construction thereof. However, the position of the pumping station has had to be amended for the purposes of this DCO due to an existing siphon coming to light. It is therefore necessary to amend the terms to reflect the change in circumstances. In the meantime, the point of contact at CRT has changed as have their agents hence there has been a period of time during which they have been brought up to speed. To this end, a meeting took place on 4 November with CRT and their agents and updated/revised Heads of Terms will be issued by 27 November at the latest. These negotiations are being conducted in parallel with the Canal Improvement Study which is due to be completed in December 2025. The current expectation is that agreement will be reached early in the examination process. The CRT interests in the Haul Road route will not be directly affected nor restrict use thereof but are included for completeness | North Pilfrey Bridge Air Easement completed. Agreements in respect of new pumping station and pipe easement progressing in parallel with the Canal Improvement Study
| 2-30, 2-31, 2-32, 2-33 | 8A - Vehicular Site Access
| 2-30, 2-31, 2-32, 2-33 | 9B - Temporary Access Area to Construction & laydown area
| 3-193, 3-195 | 9D - Temporary Haul Route
| 3-199, 3-200, 3-201, 3-202, 3-203, 3-204 | 9E - Jetty & crane offloading for waterborne transport and river barges
| 3-194 | 10 - Potential Landscaping and Planting Area
Environment Agency | 2-80, 2-81, 2-82 | 3A - National Grid NG Compound | Freehold - 1-02, 1-04a, 1-04b, 1-06, 1-07, 1-08, 1-09, 1-10, 1-11, 2-36, 2-80 (reputed), 2-81, 2-82, 2-89 (reputed), 2-90, 2-91 Freehold (subsoil) - 1-03a, 1-03b, 1-03c Occupiers - 1-02, 1-04, 1-06, 1-07, 1-08, 1-09, 1-10, 1-11, 2-30, 2-35, 2-36, 2-80, 2-81, 2-82, 2-89, 2-90, 2-91, 3-124, 3-125, 3-126, 3-127, 3-128, 3-205, 3-206, 3-229, 3-230 Category 2 - 3-158, 3-159, 3-160, 3-161, 3-162, 3-163, 3-164, 3-165, 3-166, 3-167, 3-168, 3-169 | Temporary Use - 1-10, 1-11, 2-80, 2-81, 2-82, 3-163, 3-164, 3-205, 3-206 New Rights - 1-02, 1-03a, 1-03b, 1-03c, 1-04a, 1-04b, 1-06, 1-07, 1-08, 1-09, 2-30, 2-35, 2-36, 3-124, 3-125, 3-126, 3-127, 3-128, 3-158, 3-159, 3-160, 3-161, 3-162, 3-229, 3-230 Freehold Acquisition - 2-89, 2-90, 2-91 Acquisition of restrictions on Third Party Title 3-165, 3-166, 3-167, 3-168, 3-169 | The following agreements have been reached in principle: 1. Mabey Bridge - option agreement for Deed of Variation in respect of existing air easement rights 2. North Pilfrey Bridge - Deed of Variation to existing lease for air rights 3. Canal Abstraction Pipe - draft Deed agreed 4. Skew Bridge - variation to existing 125 year lease agreed Minor delay due to change of relevant personnel at EA. It is intended that completion of all 4 agreements will occur simultaneously with the aim to complete before end 2025. | With solicitors
| 3-124, 3-125, 3-126, 3-127, 3-128, 3-158, 3-159, 3-160, 3-161, 3-162, 3-163, 3-164, 3-165, 3-166, 3-167, 3-168, 3-169 | 5 - Cooling Water Abstraction
| 3-229, 3-230 | 6 - Cooling & Wastewater discharge pipeline
| 1-03b, 1-04b, 1-06, 1-07, 1-08, 2-30, 2-35, 2-36, 2-80, 2-81, 2-82, 2-89, 2-90, 2-91 | 8A - Vehicular Site Access
| 1-02, 1-03a, 1-03b, 1-03c, 1-04a, 1-04b, 1-06, 1-07, 1-08, 1-09 | 8C - Gatehouse Services
| 1-10, 1-11, 2-30, 2-35, 2-36, 2-80, 2-81, 2-82, 2-89, 2-90, 2-91 | 9B - Temporary Access Area to Construction & laydown area
| 1-06, 1-07, 1-08 | 9C - Temporary Construction and Laydown Area in Association with Replacement of Private Bridge
| 3-205, 3-206 | 9E - Jetty & crane offloading for waterborne transport and river barges
Glew J R Junior & Co Limited | 3-212, 3-216, 3-222 | 6 - Cooling & Wastewater discharge pipeline | Leasehold - 3-212, 3-216, 3-222 Occupiers - 3-212, 3-216, 3-222 | New Rights - 3-212, 3-216, 3-222 | Agricultural tenants of the Glew Land and are a consenting party to the Option agreement for variation of the existing easement to benefit from the existing water discharge pipes and cathodic protection | With solicitors
Glew, David | 3-211, 3-212, 3-213, 3-215, 3-216, 3-217, 3-221, 3-222 | 6 - Cooling & Wastewater discharge pipeline | Freehold - 3-212, 3-216, 3-222 Freehold (subsoil) - 3-211 Riparian Owner - 3-213, 3-215, 3-217, 3-221 Occupiers - 3-212, 3-216, 3-222 | New Rights - 3-211, 3-212, 3-213, 3-215, 3-216, 3-217, 3-221, 3-222 | The terms of an Option agreement for variation of existing easement to enable the Applicant to benefit from the existing water discharge pipes and cathodic protection are agreed in principle. Exchange and completion are expected by end 2025. | With solicitors
Glew, Richard | 3-211, 3-212, 3-213, 3-215, 3-216, 3-217, 3-221, 3-222 | 6 - Cooling & Wastewater discharge pipeline | Freehold - 3-212, 3-216, 3-222 Freehold (subsoil) - 3-211 Riparian Owner - 3-213, 3-215, 3-217, 3-221 Occupiers - 3-212, 3-216, 3-222 | New Rights - 3-211, 3-212, 3-213, 3-215, 3-216, 3-217, 3-221, 3-222 | The terms of an Option agreement for variation of existing easement to enable the Applicant to benefit from the existing water discharge pipes and cathodic protection are agreed in principle. Exchange and completion are expected by end 2025. | With solicitors
Glew, Stephen | 3-211, 3-212, 3-213, 3-215, 3-216, 3-217, 3-221, 3-222 | 6 - Cooling & Wastewater discharge pipeline | Freehold - 3-212, 3-216, 3-222 Freehold (subsoil) - 3-211 Riparian Owner - 3-213, 3-215, 3-217, 3-221 Occupiers - 3-212, 3-216, 3-222 | New Rights - 3-211, 3-212, 3-213, 3-215, 3-216, 3-217, 3-221, 3-222 | The terms of an Option agreement for variation of existing easement to enable the Applicant to benefit from the existing water discharge pipes and cathodic protection are agreed in principle. Exchange and completion are expected by end 2025. | With solicitors
Harmony KB Limited | 3-212, 3-216, 3-222 | 6 - Cooling & Wastewater discharge pipeline | Category 2 - 3-212, 3-216, 3-222 | New Rights - 3-212, 3-216, 3-222 | HKB Ltd have the benefit of an option agreement only and do not therefore have a compensatable interest in the land. | No impact
Humphrey, Ruth Pauline | 3-213, 3-214, 3-215 | 6 - Cooling & Wastewater discharge pipeline | Freehold - 3-214 Riparian Owner - 3-213, 3-215 Occupiers - 214 | New Rights - 3-213, 3-214, 3-215 | The terms of an Option agreement agreed for variation of existing easement to enable the Applicant to benefit from the existing water discharge pipes and cathodic protection are agreed in principle. Exchange and completion expected by end 2025. | In legals
KCOM Group Plc | 1-03b | 8A - Vehicular Site Access | Occupiers - 1-03a, 1-03b, 1-03c | New Rights - 1-03a, 1-03b, 1-03c | KCOM Group Plc hold equipment in the plots identified in the Book of Reference. The Applicant does not intend to extinguish, vary, or otherwise impact upon existing rights. To the extent that the Applicant's works have any potential to impact upon such equipment, this is a matter for engineer engagement. | No land rights or interests required
| 1-03a, 1-03b, 1-03c | 8C - Gatehouse Services
Keadby Developments Limited | 2-73a, 2-73b, 2-73c, 2-74, 2-77, 2-103 | 1A - CCGT Plant | Freehold - 2-38, 2-40, 2-45, 2-50, 2-68a, 2-68b, 2-68c, 2-69, 2-70, 2-71a, 2-71b, 2-71c, 2-72a, 2-72b, 2-73a, 2-73b, 2-73c, 2-74, 2-75, 2-76, 2-77, 2-78, 2-79, 2-86, 2-87a, 2-87b, 2-88, 2-96, 2-99, 2-100, 2-101, 2-102, 2-103, 2-109, 2-110, 3-116, 3-118, 3-119, 3-120, 3-134, 3-137, 3-157, 3-171, 3-173, 3-188, 3-189, 3-190 Freehold (subsoil) - 1-59, 3-127, 3-130, 3-136 Riparian Owner - 2-41, 2-46, 2-51, 2-53, 2-59 Occupiers - 2-38, 2-40, 2-45, 2-50, 2-68a, 2-68b, 2-68c, 2-69, 2-70, 2-71a, 2-71b, 2-71c, 2-72a, 2-72b, 2-73a, 2-73b, 2-73c, 2-74, 2-75, 2-76, 2-77, 2-78, 2-79, 2-86, 2-87a, 2-87b, 2-88, 2-96, 2-99, 2-100, 2-101, 2-102, 2-103, 2-109, 2-110, 3-116, 3-118, 3-119, 3-120, 3-134, 3-137, 3-157, 3-170, 3-173, 3-188, 3-189, 3-190 Category 2 - 3-117, 3-121, 3-122, 3-123, 3-138, 3-141, 3-142, 3-144, 3-148, 3-149, 3-150, 3-155, 3-170, 3-172, 3-176, 3-177, 3-179, 3-180, 3-181, 3-191, 3-192, 3-224 | Temporary Use - 2-100, 3-170, 3-171, 3-172, 3-188, 3-189 New Rights - 2-38, 2-40, 2-41, 2-50, 2-51, 2-53, 2-59, 3-127, 3-130, 3-134, 3-136, 3-137, 3-138, 3-141, 3-142, 3-144, 3-148, 3-149, 3-150, 3-155, 3-157, 3-170, 3-173, 3-176, 3-177, 3-179, 3-180, 3-181, 3-190, 3-191, 3-192, 3-224 Freehold Acquisition - 2-45, 2-46, 2-68a, 2-68b, 2-68c, 2-69, 2-70, 2-71a, 2-71b, 2-71c, 2-72a, 2-72b, 2-73a, 2-73b, 2-73c, 2-74, 2-75, 2-76, 2-77, 2-78, 2-79, 2-86, 2-87a, 2-87b, 2-88, 2-96, 2-99, 2-101, 2-102, 2-103, 2-109, 2-110, 3-116, 3-117, 3-118, 3-119, 3-120, 3-121, 3-122, 3-123 | This is a SSE plc Group Company. Heads of terms are being progressed for agreement with the relevant SSE plc entities. | Intercompany Heads of Terms under discussion
| 2-68a, 2-69, 2-70, 2-71a, 2-71b, 2-71c, 2-73a, 2-73b, 2-73c, 2-74, 2-75, 2-76, 2-77, 2-78, 2-79, 2-103 | 1B - CCGT Cooling Infrastructure
| 2-88, 2-101, 2-102, 3-116, 3-117, 3-118, 3-119, 3-120, 3-121, 3-122, 3-123 | 1C - Power station staff support facilities
| 2-68a, 2-68b, 2-68c, 2-69, 2-70, 2-71b, 2-71c | 2A - Suppler H2 Compound
| 2-68c, 2-71b, 2-71c, 2-72a, 2-72b, 2-73a, 2-73b | 2B - Undertaker (SSE) H2 Compound
| 2-86, 2-87a, 2-87b, | 3A - National Grid NG Compound
| 2-72b, 2-73b, 2-73c, 2-87a, 2-88 | 3B - Undertaker (SSE) NG Compound
| 2-102, 2-103, 3-120, 3-123, 3-141, 3-142, 3-144, 3-149, 3-150, 3-155 | 4A - Primary Electrical connection & Distribution facilities
| 2-103 | 4B - Alternative Electrical connection & Distribution facilities
| 2-68a, 2-69, 2-70, 2-71a, 2-71b, 2-71c, 2-73a, 2-73b, 2-73c, 2-74, 2-75, 2-76, 2-77, 2-78, 2-79, 2-102, 2-103, 2-109, 2-110, 3-116, 3-117, 3-127, 3-130, 3-134, 3-157, 3-170 | 5 - Cooling Water Abstraction
| 2-68a, 2-69, 2-70, 2-71a, 2-71b, 2-71c, 2-73a, 2-73b, 2-73c, 2-74, 2-75, 2-76, 2-77, 2-78, 2-79, 2-102, 2-103, 3-119, 3-120, 3-122, 3-123, 3-136, 3-137, 3-138, 3-141, 3-142, 3-148, 3-149, 3-150, 3-173, 3-176, 3-177, 3-179, 3-180, 3-224 | 6 - Cooling & Wastewater discharge pipeline
| 2-73a, 2-73b, 2-73c, 2-74, 2-75, 2-77, 2-78, 2-101, 2-102, 2-103, 3-118, 3-119, 3-120, 3-121, 3-122, 3-123, 3-136, 2-137, 3-138, 3-141, 3-142, 3-148, 3-149, 3-150 | 7 - Public Water
| 2-38, 2-86, 2-96, 2-99, 2-109 | 8A - Vehicular Site Access
| 2-40, 2-41, 2-45, 2-46, 2-50, 2-51, 2-53, 2-59 | 8D - Emergency Operational Access
| 2-68a, 2-68b, 2-68c, 2-71a, 2-71b, 2-71c, 2-72a, 2-72b, 2-74, 2-75, 2-76, 2-100, 2-101, 2-102, 2-110 | 9A - Construction & Temporary Laydown
| 2-38, 2-86, 2-96 | 9B - Temporary Access Area to Construction & laydown area
| 2-86, 2-87a, 2-87b, 2-88, 2-96, 2-99, 2-109, 3-116, 3-117, 3-127, 3-130, 3-134, 3-171, 3-172, 3-188 | 9D - Temporary Haul Route
| 3-181, 3-189, 3-190, 3-191, 3-192 | 10 - Potential Landscaping and Planting Area
| 2-68a, 2-68b, 2-68c, 2-69, 2-71a, 2-71b, 2-71c, 2-72a, 2-72b | 11 - Reserved Area for CCP
Keadby Generation Limited | 3-112, 3-113, 3-114, 3-115, 3-117, 3-121, 3-122, 3-123 | 1C - Power station staff support facilities | Freehold - 3-117, 3-121, 3-122, 3-123, 3-138, 3-141, 3-142, 3-144, 3-158, 3-169, 3-170, 3-172, 3-176, 3-180, 3-181, 3-184, 3-187, 3-191, 3-192, 3-224 Freehold (subsoil) - 3-124, 3-135, 3-143, 3-225, 3-226 Leasehold - 3-160, 3-161, 3-177, 3-179, 3-182, 3-183 Occupiers - 2-104, 3-117, 3-121, 3-122, 3-123, 3-137, 3-138, 3-139, 3-141, 3-142, 3-144, 3-152, 3-156, 3-158, 3-160, 3-161, 3-169, 3-170, 3-172, 3-173, 3-176, 3-177, 3-178, 3-179, 3-180, 3-181, 3-182, 3-183, 3-184, 3-185, 3-186, 3-187, 3-191, 3-192, 3-209, 3-210, 3-211, 3-212, 3-213, 3-214, 3-215, 3-216, 3-217, 3-218, 3-219, 3-220, 3-221, 3-222, 3-223, 3-224, 3-226, 3-227, 3-228 Category 2 - 3-111, 3-112, 3-113, 3-114, 3-115, 3-125, 3-127, 3-157, 3-159 | Temporary Use - 3-172 New Rights - 2-104, 3-111, 3-113, 3-124, 3-125, 3-127, 3-135, 3-137, 3-138, 3-139, 3-141, 3-142, 3-143, 3-144, 3-152, 3-156, 3-157, 3-158, 3-159, 3-160, 3-161, 3-170, 3-173, 3-176, 3-177, 3-178, 3-179, 3-180, 3-181, 3-182, 3-183, 3-184, 3-185, 3-186, 3-187, 3-191, 3-192, 3-209, 3-210, 3-211, 3-212, 3-213, 3-214, 3-215, 3-216, 3-217, 3-218, 3-219, 3-220, 3-221, 3-222, 3-223, 3-224, 3-225, 3-226,3-227, 3-228 Use of existing rights - 3-112, 3-114, 3-115, Potential extinguishment of restrictions on title - 3-117, 3-121, 3-122, 3-123, 3-169 | This is a SSE plc Group Company. Heads of terms are being progressed for agreement with the relevant SSE plc entities. | Intercompany Heads of Terms under discussion
| 2-104, 3-123, 3-141, 3-142, 3-143, 3-144, 3-152, 3-156 | 4A - Primary Electrical connection & Distribution facilities
| 2-104 | 4B - Alternative Electrical connection & Distribution facilities
| 3-111, 3-112, 3-113, 3-114, 3-115, 3-117, 3-124, 3-125, 3-127, 3-157, 3-158, 3-159, 3-160, 3-161, 3-169, 3-170 | 5 - Cooling Water Abstraction
| 3-122, 3-123, 3-135, 3-137, 3-138, 3-139, 3-141, 3-142, 3-143, 3-173, 3-176, 3-177, 3-178, 3-179, 3-180, 3-183, 3-184, 3-185, 3-186, 3-209, 3-210, 3-211, 3-212, 3-213, 3-214, 3-215, 3-216, 3-217, 3-218, 3-219, 3-220, 3-221, 3-222, 3-223, 3-224, 3-225, 3-226, 3-227, 3-228 | 6 - Cooling & Wastewater discharge pipeline
| 3-121, 3-122, 3-123, 3-135, 3-137, 3-138, 3-139, 3-141, 3-142, 3-143 | 7 - Public Water
| 3-112, 3-113, 3-114, 3-115, 3-117, 3-172 | 9D - Temporary Haul Route
| 3-181, 3-182, 3-187, 3-191, 3-192 | 10 - Potential Landscaping and Planting Area
Keadby Wind Farm Limited | 1-07, 1-13, 1-17, 1-20, 1-24, 1-28, 2-30, 2-31, 2-32, 2-33, 2-34, 2-35, 2-36, 2-37, 2-38 | 8A - Vehicular Site Access | Leasehold - 1-26 Occupiers - 1-07, 1-13, 1-17, 1-20, 1-24, 1-26, 1-28, 2-30, 2-31, 2-32, 2-33, 2-34, 2-35, 2-36, 2-37, 2-38, 2-49, 2-56, 2-57, 2-58 Category 2 - 2-42, 2-43, 2-44, 2-47, 2-48, 2-52, 2-54, 2-60, 2-66 | Temporary Use - 1-26 New Rights - 1-07, 1-13, 1-17, 1-20, 1-24, 1-28, 2-30, 2-31, 2-32, 2-33, 2-34, 2-35, 2-36, 2-37, 2-38, 2-42, 2-43, 2-44, 2-48, 2-49, 2-52, 2-54, 2-56, 2-57, 2-58, 2-60, 2-66 Acquisition of restriction on title - 2-47 | This is a SSE plc Group Company. Heads of terms are being progressed for agreement with the relevant SSE plc entities. | Intercompany Heads of Terms under discussion
| 1-20 | 8B - Gatehouse & Layby
| 1-07, 1-13, 1-17, 1-20 | 8C - Gatehouse Services
| 2-42, 2-43, 2-44, 2-47, 2-48, 2-49, 2-52, 2-54, 2-56, 2-57, 2-58, 2-60, 2-66 | 8D - Emergency Operational Access
| 1-26 | 9A - Construction & Temporary Laydown
| 1-13, 1-17, 1-20, 1-24, 1-28, 2-30, 2-31, 2-32, 2-33, 2-34, 2-35, 2-36, 2-37, 2-38 | 9B - Temporary Access Area to Construction & laydown area
| 1-07, 1-13 | 9C - Temporary Construction and Laydown Area in Association with Replacement of Private Bridge
Lidsey Renewables Limited | 2-42, 2-43, 2-44, 2-47, 2-48, 2-49, 2-52, 2-54, 2-60, 2-66 | 8D - Emergency Operational Access | Category 2 - 2-42, 2-43, 2-44, 2-47, 2-48, 2-49, 2-52, 2-54, 2-60, 2-66 | New Rights - 2-42, 2-43, 2-44, 2-48, 2-49, 2-52, 2-54, 2-60, 2-66 Acquisition of Option over Third Party Freehold interest - 2-47 | Lidsey Renewables Limited have the benefit of an option agreement only and do not therefore have a compensatable interest in the land. | No discernible impact
Maclean, Amy Sarah | 3-186, 3-209, 3-210 | 6 - Cooling & Wastewater discharge pipeline | Freehold - 3-209 Freehold (subsoil) - 3-210 Riparian Owner - 3-186 Occupiers - 3-209 | New Rights - 3-186, 3-209, 3-210 | The terms of an Option agreement for variation of existing easement to enable the Applicant to benefit from the existing water discharge pipes and cathodic protection are agreed in principle. Lendor approval not required. Exchange and completion expected by end of 2025 | With solicitors
Maclean, Simon Alistair | 3-186, 3-209, 3-210 | 6 - Cooling & Wastewater discharge pipeline | Freehold - 3-209 Freehold (subsoil) - 3-210 Riparian Owner - 3-186 Occupiers - 3-209 | New Rights - 3-186, 3-209, 3-210 | The terms of an Option agreement for variation of existing easement to enable the Applicant to benefit from the existing water discharge pipes and cathodic protection are agreed in principle. Lendor approval not required. Exchange and completion expected by end of 2025 | With solicitors
Nat West | 3-218 | 6 - Cooling & Wastewater discharge pipeline | Category 2 - 3-218 | New Rights - 3-218 | Natwest acquired Metrobank. Mortgagee for Albans. See comments in respect of Albans above. | See "Albans"
National Gas Transmission Plc | 3-112, 3-113, 3-114 | 1C - Power station staff support facilities | Occupiers - 2-36, 2-39, 2-90, 2-92, 2-93, 2-95, 2-98, 2-105, 2-106, 2-107, 2-108, 3-111, 3-112, 3-113, 3-114, 3-156, 3-157, 3-220 | New Rights - 2-36, 2-39, 2-93, 2-107, 3-111, 3-113, 3-156, 3-157, 3-220 Freehold Acquisition - 2-90, 2-92, 2-95, 2-98, 2-105, 2-106, 2-108, 3-112, 3-114 | National Gas hold equipment in the plots identified in the Book of Reference for temporary or permanent use or creation of new rights. The Applicant does not intend to extinguish, vary, or otherwise impact upon existing rights benefitting NG. To the extent that the Applicant's works have any potential to impact upon such equipment, this is a matter for engineer engagement. | No land rights or interests required
| 3-156 | 4A - Primary Electrical connection & Distribution facilities
| 2-106, 2-107, 2-108, 3-111, 3-112, 3-113, 3-114, 3-157 | 5 - Cooling Water Abstraction
| 3-220 | 6 - Cooling & Wastewater discharge pipeline
| 2-36, 2-39, 2-90, 2-92, 2-93, 2-95, 2-98, 2-105, 2-106, 2-107, 2-108 | 8A - Vehicular Site Access
| 2-36, 2-39, 2-90, 2-92, 2-93, 2-95 | 9B - Temporary Access Area to Construction & laydown area
| 2-93, 2-95, 2-98, 2-105, 2-106, 2-107, 2-108, 2-112, 2-113, 2-114 | 9D - Temporary Haul Route
National Grid Electricity Transmission PLC | 2-73a, 2-73b, 2-73c, 2-74, 2-77, 2-103 | 1A - CCGT Plant | Freehold - 2-63, 2-64, 2-65, 2-104, 3-146, 3-147, 3-148, 3-149, 3-150, 3-151, 3-152, 3-155, 3-174, 3-175, 3-177, 3-178, 3-179 Freehold (subsoil) - 3-139, 3-140, 3-145, 3-153, 3-156 Occupiers - 2-38, 2-39, 2-44, 2-63, 2-64, 2-65, 2-67, 2-81, 2-82, 2-83, 2-84, 2-88, 2-90, 2-92, 2-93, 2-97, 2-98, 2-99, 2-100, 2-101, 2-102, 2-103, 2-104, 2-107, 3-111, 3-112, 3-113, 3-114, 3-115, 3-117, 3-121, 3-122, 3-123, 3-124, 3-125, 3-128, 3-134, 3-142, 3-143, 3-144, 3-146, 3-147, 3-148, 3-149, 3-150, 3-151, 3-152, 3-153, 3-155, 3-157, 3-158, 3-159, 3-170, 3-171, 3-172, 3-174, 3-175, 3-177, 3-178, 3-179, 3-180, 3-181, 3-185, 3-186, 3-191, 3-192, 3-208, 3-209, 3-210, 3-211, 3-212, 3-213, 3-214, 3-215, 3-216, 3-217, 3-218, 3-219, 3-221, 3-222, 3-223, 3-224, 3-225, 3-226, 3-227, 3-228 Category 2 - 2-37, 2-39, 2-40, 2-42, 2-43, 2-45, 2-47, 2-48, 2-49, 2-50, 2-52, 2-54, 2-55, 2-56, 2-57, 2-58, 2-60, 2-61, 2-62, 2-66, 2-68a, 2-68b, 2-68c, 2-69, 2-70, 2-71a, 2-71b, 2-71c, 2-72a, 2-72b, 2-73a, 2-73b, 2-73c, 2-74, 2-75, 2-76, 2-77, 2-78, 2-79, 2-83, 2-84, 2-85, 2-86, 2-87a, 2-87b, 2-92, 2-93, 2-94, 2-95, 2-96, 2-97, 2-98, 2-103, 2-105, 2-106, 2-107, 2-108, 2-109, 2-110, 3-111, 3-112, 3-113, 3-114, 3-116, 3-118, 3-119, 3-120, 3-137, 3-141, 3-173, 3-188, 3-189, 3-190, 3-208 | Temporary Use - 2-55, 2-100, 3-171, 3-172, 3-189 New Rights - 2-37, 2-38, 2-39, 2-40, 2-42, 2-43, 2-44, 2-48, 2-49, 2-50, 2-52, 2-54, 2-56, 2-57, 2-58, 2-60, 2-61, 2-62, 2-64, 2-65, 2-66, 2-67, 2-84, 2-93, 2-97, 2-104, 2-107, 3-111, 3-113, 3-124, 3-125, 3-128, 3-134, 3-137,3-139, 3-140, 3-141, 3-142, 3-143, 3-144, 3-145, 3-146, 3-147, 3-148, 3-149, 3-150, 3-151, 3-152, 3-153, 3-155, 3-156, 3-157, 3-158, 3-159, 3-170, 3-173, 3-174, 3-175, 3-177, 3-178, 3-179, 3-180, 3-181, 3-185,3-186, 3-188, 3-190, 3-191, 3-192, 3-208, 3-209, 3-210, 3-211, 3-212, 3-213, 3-214, 3-215, 3-216, 3-217, 3-218, 3-219, 3-221, 3-222, 3-223, 3-224, 3-225, 3-226, 3-227, 3-228 Freehold Acquisition - 2-45, 2-47, 2-63, 2-68a, 2-68b, 2-68c, 2-69, 2-70, 2-71a, 2-71b, 2-71c, 2-72a, 2-72b, 2-73a, 2-73b, 2-73c, 2-74, 2-75, 2-76, 2-77, 2-78, 2-79, 2-81, 2-82, 2-83, 2-85, 2-86, 2-87a, 2-87b, 2-88, 2-90, 2-92, 2-94, 2-95, 2-96, 2-98, 2-99, 2-101, 2-102, 2-103, 2-105, 2-106, 2-108, 2-109, 2-110, 3-112, 3-114, 3-115, 3-116, 3-117, 3-118, 3-119, 3-120, 3-121, 3-122, 3-123 | The Applicant does not intend to extinguish, vary, or otherwise impact upon existing rights by NGET in respect of the installation, maintenance and operation of equipment. To the extent that the Applicant's works have any potential to impact upon such equipment, this is a matter for engineer engagement. The Applicant requires a new cable easement to connect into the PowerGrid. In addition whilst the Applicant already benefits from a Lease in respect of water discharge pipes, this will expire in 2032 such that it is of insufficient length. The Applicant therefore needs to secure an extension of that lease to benefit the DCO scheme failing which it will seek an easement. The Applicant has already engaged with NGET in respect of statutory consultation and progression of PPs. However, NGET are requiring the Applicant to make separate submissions for clearance before land agreement terms can be progressed. Certain technical information has been requested by NGET which is being progressed. | The Applicant has approached NGET to commence negotiations.
| 2-63, 2-68a, 2-69, 2-70, 2-71a, 2-71b, 2-71c, 2-73a, 2-73b, 2-73c, 2-74, 2-75, 2-76, 2-77, 2-78, 2-79, 2-103 | 1B - CCGT Cooling Infrastructure
| 2-88, 2-101, 2-102, 3-112, 3-113, 3-114, 3-115, 3-116, 3-117, 3-118, 3-119, 3-120, 3-121, 3-122, 3-123 | 1C - Power station staff support facilities
| 2-68a, 2-68b, 2-68c, 2-69, 2-70, 2-71b, 2-71c | 2A - Suppler H2 Compound
| 2-68c, 2-71b, 2-71c, 2-72a, 2-72b, 2-73a, 2-73b | 2B - Undertaker (SSE) H2 Compound
| 2-81, 2-82, 2-83, 2-84, 2-85, 2-86, 2-87a, 2-87b, | 3A - National Grid NG Compound
| 2-72b, 2-73b, 2-73c, 2-87a, 2-88 | 3B - Undertaker (SSE) NG Compound
| 2-102, 2-103, 2-104, 3-120, 3-123, 3-141, 3-142, 3-143, 3-144, 3-145, 3-149, 3-150, 3-151, 3-152, 3-153, 3-155, 3-156 | 4A - Primary Electrical connection & Distribution facilities
| 2-103, 2-104 | 4B - Alternative Electrical connection & Distribution facilities
| 2-63, 2-68a, 2-69, 2-70, 2-71a, 2-71b, 2-71c, 2-73a, 2-73b, 2-73c,2-74, 2-75, 2-76, 2-77, 2-78, 2-79, 2-102, 2-103, 2-106, 2-107, 2-108, 2-109, 2-110, 3-111, 3-112, 3-113, 3-114, 3-115, 3-116, 3-117, 3-124, 3-125, 3-128, 3-134, 3-157, 3-158, 3-159, 3-170 | 5 - Cooling Water Abstraction
| 2-63, 2-68a, 2-69, 2-70, 2-71a, 2-71b, 2-71c, 2-73a, 2-73b, 2-73c, 2-74, 2-75, 2-76, 2-77, 2-78, 2-79, 2-102, 2-103, 3-119, 3-120, 3-122, 3-123, 3-137, 3-139, 3-140, 3-141, 3-142, 3-143, 3-146, 3-147, 3-148, 3-149, 3-150, 3-151, 3-153, 3-173, 3-174, 3-175, 3-177, 3-178, 3-179, 3-180, 3-185, 3-186, 3-208, 3-209, 3-210, 3-211, 3-212, 3-213, 3-214, 3-215, 3-216, 3-217, 3-218, 3-219, 3-221, 3-222, 3-223, 3-224, 3-225, 3-226, 3-227, 3-228 | 6 - Cooling & Wastewater discharge pipeline
| 2-73a, 2-73b, 2-73c, 2-74, 2-75, 2-77, 2-78, 2-101, 2-102, 2-103, 3-118, 3-119, 3-120, 3-121, 3-122, 3-123, 3-137, 3-139, 3-140, 3-141, 3-143, 3-142, 3-147, 3-148, 3-149, 3-150, 3-151, 3-153 | 7 - Public Water
| 2-37, 2-38, 2-39, 2-81, 2-82, 2-83, 2-84, 2-85, 2-86, 2-90, 2-92, 2-93, 2-94, 2-95, 2-96, 2-97, 2-98, 2-99, 2-105, 2-106, 2-107, 2-108, 2-109 | 8A - Vehicular Site Access
| 2-40, 2-42, 2-43, 2-44, 2-45, 2-47, 2-48, 2-49, 2-50, 2-52, 2-54, 2-55, 2-56, 2-57, 2-58, 2-60, 2-61, 2-62, 2-64, 2-65, 2-66, 2-67 | 8D - Emergency Operational Access
| 2-68a, 2-68b, 2-68c, 2-71a, 2-71b, 2-71c, 2-72a, 2-72b, 2-74, 2-75, 2-76, 2-100, 2-101, 2-102, 2-110 | 9A - Construction & Temporary Laydown
| 2-37, 2-38, 2-39, 2-81, 2-82, 2-83, 2-84, 2-85, 2-86, 2-90, 2-92, 2-93, 2-94, 2-95, 2-96 | 9B - Temporary Access Area to Construction & laydown area
| 2-84, 2-85, 2-86, 2-87a, 2-87b, 2-88, 2-93, 2-94, 2-95, 2-96, 2-97, 2-98, 2-99, 2-105, 2-106, 2-107, 2-108, 2-109, 3-112, 3-113, 3-114, 3-115, 3-116, 3-117, 3-134, 3-171, 3-172, 3-188 | 9D - Temporary Haul Route
| 3-181, 3-189, 3-190, 3-191, 3-192 | 10 - Potential Landscaping and Planting Area
| 2-68a, 2-68b, 2-68c, 2-69, 2-71a, 2-71b, 2-71c, 2-72a, 2-72b | 11 - Reserved Area for CCP
Network Rail Infrastructure Limited | 3-159, 3-161, 3-168 | 5 - Cooling Water Abstraction | Freehold - 2-34 Occupiers - 2-34, 3-195 Category 2 - 3-159, 3-161, 3-168, 3-193, 3-194 | Temporary Use of Third Party Land which is subject to restrictions in favour of NR - 3-193, 3-194, 3-195 New Rights over Third Party land which is subject to restrictions in favour of NR - 3-159, 3-161 Variation of existing lease with NR - 2-34 Acquisition of Third Party land over which NR claims restrictions - 3-168 | There will be no impact on NR's claimed restrictions on Third Party titles which will be acquired (03-168) or subject to temporary occupation or subject to new rights of easement. Terms have been agreed in respect of the variation of the existing lease and Licence of Alterations over land owned by NR in the vicinity of North Pilfrey Bridge (02-34) and is awaiting exchange and completion which is expected imminently. | With solicitors
| 2-34 | 8A - Vehicular Site Access
| 2-34 | 9B - Temporary Access Area to Construction & laydown area
| 3-193, 3-195 | 9D - Temporary Haul Route
| 3-194 | 10 - Potential Landscaping and Planting Area
North Lincolnshire Council | 3-143, 3-145, 3-153, 3-156 | 4A - Primary Electrical connection & Distribution facilities | Freehold (Public Highway) - 1-03a, 1-03b, 1-03c, 3-129, 3-130, 3-131, 3-132, 3-133, 3-135, 3-136, 3-139, 3-140, 3-143, 3-145, 3-153, 3-156, 3-196, 3-197, 3-210, 3-211, 3-225 Occupiers - 1-03a, 1-03b, 1-03c, 3-129, 3-130, 3-131, 3-132, 3-133, 3-135, 3-136, 3-139, 3-140, 3-143, 3-145, 3-153, 3-156, 3-195, 3-196, 3-197, 3-199, 3-210, 3-211, 3-225, 3-227 Category 2 - 3-193, 3-194 | Temporary Use - 3-193, 3-194, 3-195, 3-196, 3-197, 3-199 New Rights - 1-03a, 1-03b, 1-03c, 3-129, 3-130, 3-131, 3-132, 3-133, 3-135, 3-136, 3-139, 3-140, 3-143, 3-145, 3-153, 3-156, 3-210, 3-211, 3-225, 3-227 | The Applicant understand that all the identified plots comprise adopted highway. The Council Estates Team have been contacted but no response received to suggest that the Applicant's understanding is incorrect. | No land rights or interests required
| 3-129, 3-130, 3-131, 3-132, 3-133 | 5 - Cooling Water Abstraction
| 3-135, 3-136, 3-139, 3-140, 3-143, 3-153, 3-210, 3-211, 3-225, 3-227 | 6 - Cooling & Wastewater discharge pipeline
| 3-135, 3-136, 3-139, 3-140, 3-143, 3-153 | 7 - Public Water
| 1-03b | 8A - Vehicular Site Access
| 1-03a, 1-03b, 1-03c | 8C - Gatehouse Services
| 3-129, 3-130, 3-131, 3-132, 3-133, 3-193, 3-195, 3-196, 3-197 | 9D - Temporary Haul Route
| 3-199 | 9E - Jetty & crane offloading for waterborne transport and river barges
| 3-194 | 10 - Potential Landscaping and Planting Area
Northern Powergrid (Yorkshire) plc | 2-73a, 2-73b, 2-73c, 2-74, 2-77, 2-103 | 1A - CCGT Plant | Freehold - 3-154 (caution against first registration), 3-185 (caution) Riparian Owner - 3-186 Occupiers - 1-04a, 1-05, 2-37, 2-67, 2-81, 2-82, 2-83, 2-90, 2-91, 2-92, 2-93, 2-95, 2-96, 2-98, 2-99, 2-106, 2-107, 2-108, 3-111, 3-112, 3-115, 3-117, 3-121, 3-122, 3-123, 3-127, 3-128, 3-129, 3-131, 3-133, 3-134, 3-135, 3-138, 3-142, 3-143, 3-144, 3-151, 3-153, 3-156, 3-157, 3-158, 3-159, 3-169, 3-176, 3-177, 3-178, 3-179, 3-180, 3-181, 3-182, 3-183, 3-185, 3-187, 3-188, 3-189, 3-190, 3-192, 3-195, 3-197, 3-198, 3-208, 3-210, 3-211, 3-212, 3-222, 3-228, 3-230 Category 2 - 2-39, 2-40, 2-44, 2-45, 2-50, 2-68a, 2-68b, 2-68c, 2-69, 2-70, 2-71a, 2-71b, 2-71c, 2-72a, 2-72b, 2-73a, 2-73b, 2-73c, 2-74, 2-75, 2-76, 2-77, 2-78, 2-79, 2-84, 2-85, 2-86, 2-87a, 2-87b, 2-88, 2-97, 2-100, 2-101, 2-102, 2-103, 2-105, 2-109, 2-110, 3-116, 3-118, 3-119, 3-120 | Temporary Use - 2-100, 3-188, 3-189, 3-195, 3-197, 3-198 New Rights - 1-04a, 1-05, 2-37, 2-39, 2-40, 2-44, 2-50, 2-67, 2-84, 2-93, 2-97, 2-107, 3-111, 3-113, 3-127, 3-128, 3-129, 3-131, 3-133, 3-134, 3-135, 3-138, 3-142, 3-143, 3-144, 3-151, 3-153, 3-154, 3-156, 3-157, 3-158, 3-159, 3-176, 3-177, 3-178, 3-179, 3-180, 3-181, 3-182, 3-183, 3-185, 3-186, 3-187, 3-190, 3-192, 3-208, 3-210, 3-211, 3-212, 3-222, 3-228, 3-230 Freehold Acquisition - 2-45, 2-68a, 2-68b, 2-68c, 2-69, 2-70, 2-71a, 2-71b, 2-71c, 2-72a, 2-72b, 2-73a, 2-73b, 2-73c, 2-74, 2-75, 2-76, 2-77, 2-78, 2-79, 2-81, 2-82, 2-83, 2-85, 2-86, 2-87a, 2-87b, 2-88, 2-90, 2-91, 2-92, 2-95, 2-96, 2-98, 2-99, 2-101, 2-102, 2-103, 2-105, 2-106, 2-108, 2-109, 2-110, 3-112, 3-114, 3-115, 3-116, 3-117, 3-118, 3-119, 3-120, 3-121, 3-122, 3-123, 3-169 | Northern Powergrid hold equipment in the plots identified in the Book of Reference. The Applicant does not intend to extinguish, vary, or otherwise impact upon existing rights. To the extent that the Applicant's works have any potential to impact upon such equipment, this is a matter for engineer engagement. | No land rights or interests required
| 2-68a, 2-69, 2-70, 2-71a, 2-71b, 2-71c, 2-73a, 2-73b, 2-73c, 2-74, 2-75, 2-76, 2-77, 2-78, 2-79, 2-103 | 1B - CCGT Cooling Infrastructure
| 2-88, 2-101, 2-102, 3-112, 3-113, 3-114, 3-115, 3-116, 3-117, 3-118, 3-119, 3-120, 3-121, 3-122, 3-123 | 1C - Power station staff support facilities
| 2-68a, 2-68b, 2-68c, 2-69, 2-70, 2-71b, 2-71c | 2A - Suppler H2 Compound
| 2-68c, 2-71b, 2-71c, 2-72a, 2-72b, 2-73a, 2-73b | 2B - Undertaker (SSE) H2 Compound
| 2-81, 2-82, 2-83, 2-84, 2-85, 2-86, 2-87a, 2-87b | 3A - National Grid NG Compound
| 2-72b, 2-73b, 2-73c, 2-87a, 2-88 | 3B - Undertaker (SSE) NG Compound
| 2-102, 2-103, 3-120, 3-123, 3-142, 3-143, 3-144, 3-151, 3-153, 3-154, 3-156 | 4A - Primary Electrical connection & Distribution facilities
| 2-103 | 4B - Alternative Electrical connection & Distribution facilities
| 2-68a, 2-69, 2-70, 2-71a, 2-71b, 2-71c, 2-73a, 2-73b, 2-73c, 2-74, 2-75, 2-76, 2-77, 2-78, 2-79, 2-102, 2-103, 2-106, 2-107, 2-108, 2-109, 2-110, 3-111, 3-112, 3-113, 3-114, 3-115, 3-116, 3-117, 3-127, 3-128, 3-129, 3-131, 3-133, 3-134, 3-157, 3-158, 3-159, 3-169 | 5 - Cooling Water Abstraction
| 2-68a, 2-69, 2-70, 2-71a, 2-71b, 2-71c, 2-73a, 2-73b, 2-73c, 2-74, 2-75, 2-76, 2-77, 2-78, 2-79, 2-102, 2-103, 3-119, 3-120, 3-122, 3-123, 3-135, 3-138, 3-142, 3-143, 3-151, 3-153, 3-176, 3-177, 3-178, 3-179, 3-180, 3-183, 3-185, 3-186, 3-208, 3-210, 3-211, 3-212, 3-222, 3-228, 3-230 | 6 - Cooling & Wastewater discharge pipeline
| 2-73a, 2-73b, 2-73c, 2-74, 2-75, 2-77, 2-78, 2-101, 2-102, 2-103, 3-118, 3-119, 3-120, 3-121, 3-122, 3-123, 3-135, 3-138, 3-142, 3-143, 3-151, 3-153 | 7 - Public Water
| 2-37, 2-39, 2-81, 2-82, 2-83, 2-84, 2-85, 2-86, 2-90, 2-91, 2-92, 2-93, 2-95, 2-96, 2-97, 2-98, 2-99, 2-105, 2-106, 2-107, 2-108, 2-109 | 8A - Vehicular Site Access
| 1-04a, 1-05 | 8C - Gatehouse Services
| 2-40, 2-44, 2-45, 2-50, 2-67 | 8D - Emergency Operational Access
| 2-68a, 2-68b, 2-68c, 2-71a, 2-71b, 2-71c, 2-72a, 2-72b, 2-74, 2-75, 2-76, 2-100, 2-101, 2-102, 2-110 | 9A - Construction & Temporary Laydown
| 2-37, 2-39, 2-81, 2-82, 2-83, 2-84, 2-85, 2-86, 2-90, 2-91, 2-92, 2-93, 2-95, 2-96 | 9B - Temporary Access Area to Construction & laydown area
| 2-84, 2-85, 2-86, 2-87a, 2-87b, 2-88, 2-93, 2-95, 2-96, 2-97, 2-98, 2-99, 2-105, 2-106, 2-107, 2-108, 2-109, 3-112, 3-113, 3-114, 3-115, 3-116, 3-117, 3-129, 3-131, 3-133, 3-134, 3-188, 3-195, 3-197 | 9D - Temporary Haul Route
| 3-198 | 9E - Jetty & crane offloading for waterborne transport and river barges
| 3-181, 3-182, 3-187, 3-189, 3-190, 3-192 | 10 - Potential Landscaping and Planting Area
| 2-68a, 2-68b, 2-68c, 2-69, 2-71a, 2-71b, 2-71c, 2-72a, 2-72b | 11 - Reserved Area for CCP
Openreach Limited | 2-102, 3-112, 3-120, 3-121, 3-122, 3-123 | 1C - Power station staff support facilities | Occupiers - 1-03a, 1-03b, 1-03c, 2-37, 2-39, 2-67, 2-83, 2-90, 2-92, 2-100, 2-102, 2-104, 2-106, 2-110, 3-111, 3-112, 3-120, 3-121, 3-122, 3-123, 3-128, 3-129, 3-130, 3-131, 3-132, 3-133, 3-134, 3-135, 3-136, 3-137, 3-138, 3-139, 3-143, 3-145, 3-146, 3-147, 3-153, 3-154, 3-156, 3-157, 3-171, 3-173, 3-174, 3-176, 3-177, 3-178, 3-179, 3-180, 3-181, 3-182, 3-183, 3-187, 3-191, 3-192, 3-210, 3-211, 3-220, 3-225 | Temporary Use - 2-100, 3-171 New Rights - 1-03a, 1-03b, 1-03c, 2-37, 2-39, 2-67, 2-104, 3-111, 3-128, 3-129, 3-130, 3-131, 3-132, 3-133, 3-134, 3-135, 3-136, 3-137, 3-138, 3-139, 3-143, 3-145, 3-146, 3-147, 3-153, 3-154, 3-156, 3-157, 3-173, 3-174, 3-176, 3-177, 3-178, 3-179, 3-180, 3-181, 3-182, 3-183, 3-187, 3-191, 3-192, 3-210, 3-211, 3-220, 3-225 Freehold Acquisition - 2-83, 2-90, 2-92, 2-102, 2-106, 2-110, 3-112, 3-120, 3-121, 3-122, 3-123 | Openreach hold equipment in the plots identified in the Book of Reference. The Applicant does not intend to extinguish, vary, or otherwise impact upon existing rights. To the extent that the Applicant's works have any potential to impact upon such equipment, this is a matter for engineer engagement. | No land rights or interests required
| 2-83 | 3A - National Grid NG Compound
| 2-102, 2-104, 3-120, 3-123,3-143, 3-145, 3-153, 3-154, 3-156 | 4A - Primary Electrical connection & Distribution facilities
| 2-104 | 4B - Alternative Electrical connection & Distribution facilities
| 2-102, 2-106, 2-110, 3-111, 3-112, 3-128, 3-129, 3-130, 3-131, 3-132, 3-133, 3-134, 3-157 | 5 - Cooling Water Abstraction
| 2-102, 3-120, 3-122, 3-123, 3-135, 3-136, 3-137, 3-138, 3-139, 3-143, 3-146, 3-147, 3-153, 3-173, 3-174, 3-176, 3-177, 3-178, 3-179, 3-180, 3-183, 3-210, 3-211, 3-220, 3-225 | 6 - Cooling & Wastewater discharge pipeline
| 2-102, 3-120, 3-121, 3-122, 3-123, 3-135, 3-136, 3-137, 3-138, 3-139, 3-143, 3-147, 3-153 | 7 - Public Water
| 1-03b, 2-37, 2-39, 2-83, 2-90, 2-92, 2-106 | 8A - Vehicular Site Access
| 1-03a, 1-03b, 1-03c | 8C - Gatehouse Services
| 2-67 | 8D - Emergency Operational Access
| 2-100, 2-102, 2-110 | 9A - Construction & Temporary Laydown
| 2-37, 2-39, 2-83, 2-90, 2-92 | 9B - Temporary Access Area to Construction & laydown area
| 2-106, 3-112, 3-129, 3-130, 3-131, 3-132, 3-133, 3-134, 3-171 | 9D - Temporary Haul Route
| 3-181, 3-182, 3-187, 3-191, 3-192 | 10 - Potential Landscaping and Planting Area
PD Ports Properties Limited | 3-193, 3-195, 3-196 | 9D - Temporary Haul Route | Freehold - 3-193, 3-194, 3-195, 3-199, 3-203 Freehold (subsoil) - 3-196 Leasehold - 3-200 Occupiers - 3-193, 3-194, 3-200 Category 2 - 3-201, 3-202, 3-204 | Temporary Use - 3-193, 3-194, 3-195, 3-196, 3-199, 3-200, 3-201, 3-202, 3-203, 3-204 | The Applicant requires the ability to moor boats to Railway Wharf that will necessitate the need to use the northern mooring on the PD Ports wharf. In addition, the Applicant will need to take HGV access from Railway Wharf and through PD Ports yard. It is intended to reach agreement on a commercial Vehicle and Boat Management Agreement basis whereby PD Ports provide Banksman and Ships Agent services to moor and unload boats then guide HGV's through PD Port's yard. The principles of this are agreed between the Parties but the precise details cannot be finalised until contractors appointed. It is therefore necessary to include these rights to protect against the possibility of PD Ports being unable or unwilling to act as a Ships Agent at the point when delivery will be scheduled. | Management Agreement for PD Ports to provide Banks persons to manage HGV traffic through the Yard and act as Ships Agent in respect of the mooring of boats under discussion
| 3-199, 3-200, 3-201, 3-202, 3-203, 3-204 | 9E - Jetty & crane offloading for waterborne transport and river barges
| 3-194 | 10 - Potential Landscaping and Planting Area
Radford, Ann Ida Madge | 3-124, 3-125, 3-126, 3-127, 3-128 | 5 - Cooling Water Abstraction | Occupiers - 3-124, 3-125, 3-126, 3-127, 3-128 | New Rights - 3-124, 3-125, 3-126, 3-127, 3-128 | The landowner's property is outside of the DCO redline boundary. However, they take vehicular and pedestrian access over Vazon Bridge and across Chapel Lane which will be subject to disruption and use by construction traffic during the development works. DWD wrote on 8th July 2025 to provide assurance that access and egress will be maintained at all times. | No land rights or interests required
Radford, Raymond | 3-124, 3-125, 3-126, 3-127, 3-128 | 5 - Cooling Water Abstraction | Occupiers - 3-124, 3-125, 3-126, 3-127, 3-128 | New Rights - 3-124, 3-125, 3-126, 3-127, 3-128 | The landowner's property is outside of the DCO redline boundary. However, they take vehicular and pedestrian access over Vazon Bridge and across Chapel Lane which will be subject to disruption and use by construction traffic during the development works. DWD wrote on 8th July 2025 to provide assurance that access and egress will be maintained at all times. | No land rights or interests required
Railway Wharf (Keadby) Limited | 3-197 | 9D - Temporary Haul Route | Freehold - 3-198 Freehold (subsoil) - 3-197 Leasehold - 3-205, 3-207 Occupiers - 3-198, 3-205, 3-207 | Temporary Use - 3-197, 3-198, 3-205, 3-207 | Keadby Generation Limited has completed the acquisition of the freehold and leasehold interest from Railway Wharf Ltd. Keadby Generation Limited is a SSE plc Group Company. A formal understanding is being worked up between the SSE plc entities regarding the land arrangements to facilitate the Proposed Development. Heads of terms are being progressed for agreement with the relevant SSE plc entities. | Already owned by KGL |  | Yes
| 3-198, 3-205, 3-207 | 9E - Jetty & crane offloading for waterborne transport and river barges
RES Developments Limited | 1-05 | 8C - Gatehouse Services | Category 2 -1-05 | New Rights - 1-05 | The Applicant understands that RES Developments only has an option and does not hold a compensatable interest. No evidence has been provided to indicate otherwise | No land rights or interests required
Sea Cadets Scunthorpe (Peter Jenkin & Dale Andrew Smith) | 3-124, 3-125, 3-126, 3-127, 3-128 | 5 - Cooling Water Abstraction | Occupiers - 3-124, 3-125, 3-126, 3-127, 3-128 | New Rights - 3-124, 3-125, 3-126, 3-127, 3-128 | The landowner's property is outside of the DCO redline boundary. However, they take vehicular and pedestrian access over Vazon Bridge and across Chapel Lane which will be subject to disruption and use by construction traffic during the development works. DWD wrote on 8th July 2025 to provide assurance that access and egress will be maintained at all times. | No land rights or interests required
Severn Trent Water | 3-170 | 5 - Cooling Water Abstraction | Occupiers - 3-177, 3-178, 3-179, 3-180, 3-181, 3-185, 3-186, 3-192, 3-195, 3-198, 3-205, 3-207, 3-230 Category 2 - 1-02, 1-04a, 1-04b, 1-06, 1-07, 1-08, 1-11, 3-170, 3-172 | Temporary Use - 1-11, 3-172, 3-195, 3-198, 3-205, 3-207 New Rights - 1-02, 1-04a, 1-04b, 1-06, 1-07, 1-08, 3-170, 3-177, 3-178, 3-179, 3-180, 3-181, 3-185, 3-186, 3-192, 3-230 | Severn Trent Water hold equipment in the plots identified in the Book of Reference. The Applicant does not intend to extinguish, vary, or otherwise impact upon existing rights. To the extent that the Applicant's works have any potential to impact upon such equipment, this is a matter for engineer engagement. | No land rights or interests required
| 3-177, 3-178, 3-179, 3-180, 3-185, 3-186, 3-230 | 6 - Cooling & Wastewater discharge pipeline
| 1-04b, 1-06, 1-07, 1-08 | 8A - Vehicular Site Access
| 1-02, 1-04a, 1-04b, 1-06, 1-07, 1-08 | 8C - Gatehouse Services
| 1-11 | 9B - Temporary Access Area to Construction & laydown area
| 1-06, 1-07, 1-08 | 9C - Temporary Construction and Laydown Area in Association with Replacement of Private Bridge
| 3-172, 3-195 | 9D - Temporary Haul Route
| 3-198, 3-205, 3-207 | 9E - Jetty & crane offloading for waterborne transport and river barges
| 3-181, 3-192 | 10 - Potential Landscaping and Planting Area
Severn, Andrew Clive | 2-44, 2-49, 2-55, 2-56, 2-57, 2-58, 2-61, 2-62, 2-66, 2-67 | 8D - Emergency Operational Access | Freehold - 2-55, 2-56, 2-57, 2-58, 2-61, 2-62 Occupiers - 2-44, 2-49, 2-55, 2-56, 2-57, 2-58, 2-61, 2-62, 2-66, 2-67 | Temporary Use - 2-55 New Rights - 2-44, 2-49, 2-56, 2-57, 2-58, 2-61, 2-62, 2-66, 2-67 | The Applicant requires the ability to construct and retain a bridge together with a taking of emergency access over the existing track. It is considered that the emergency access will be required to be widened. Negotiations have taken place and the landowner's agent has requested the provision of culverts under the access to accommodate solar farm power cables. Proposals are being worked up on this basis to be issued to the landowner's agent together with updated Heads of Terms as a matter of priority. | Negotiations underway and the proposals being redesigned to allow for the provision of electricity cable culverts for the benefit of the landowner.
SSE Generation Limited | 3-112, 3-113, 3-114 | 1C - Power station staff support facilities | Freehold - 2-37, 2-39, 2-83, 2-84, 2-85, 2-92, 2-93, 2-94, 2-95, 2-97, 2-98, 2-105, 2-106, 2-107, 2-108, 3-111, 3-112, 3-113, 3-114 Freehold (subsoil) - 2-67, 3-128, 3-129, 3-131 Leasehold - 2-31, 2-32, 2-33 Occupiers - 1-07, 1-10, 1-11, 2-30, 2-31, 2-32, 2-33, 2-34, 2-35, 2-36, 2-37, 2-39, 2-83, 2-84, 2-85, 2-92, 2-93, 2-94, 2-95, 2-97, 2-98, 2-105, 2-106, 2-107, 2-108, 3-111, 3-112, 3-113, 3-114 | Temporary Use - 1-10, 1-11 New Rights - 1-07, 2-30, 2-31, 2-32, 2-33, 2-34, 2-35, 2-36, 2-37, 2-39, 2-67, 2-84, 2-93, 2-97, 2-107, 3-111, 3-113, 3-128, 3-129, 3-131 Freehold Acquisition - 2-83, 2-85, 2-92, 2-94, 2-95, 2-98, 2-105, 2-106, 2-108, 3-112, 3-114 | This is a SSE plc Group Company. Heads of terms are being progressed for agreement with the relevant SSE plc entities. | Intercompany Heads of Terms under discussion
| 2-83, 2-84, 2-85 | 3A - National Grid NG Compound
| 2-106, 2-107, 2-108, 3-111, 3-112, 3-113, 3-114, 3-128, 3-129, 3-131 | 5 - Cooling Water Abstraction
| 1-07, 2-30, 2-31, 2-32, 2-33, 2-34, 2-35, 2-36, 2-37, 2-39, 2-83, 2-84, 2-85, 2-92, 2-93, 2-94, 2-95, 2-97, 2-98, 2-105, 2-106, 2-107, 2-108 | 8A - Vehicular Site Access
| 1-07 | 8C - Gatehouse Services
| 2-67 | 8D - Emergency Operational Access
| 1-10, 1-11, 2-30, 2-31, 2-32, 2-33, 2-34, 2-35, 2-36, 2-37, 2-39, 2-83, 2-84, 2-85, 2-92, 2-93, 2-94, 2-95 | 9B - Temporary Access Area to Construction & laydown area
| 1-07 | 9C - Temporary Construction and Laydown Area in Association with Replacement of Private Bridge
| 2-84, 2-85, 2-93, 2-94, 2-95, 2-97, 2-98, 2-105, 2-106, 2-107, 2-108, 3-112, 3-113, 3-114, 3-129, 3-131 | 9D - Temporary Haul Route
SSE Plc | 3-218 | 6 - Cooling & Wastewater discharge pipeline | Freehold - 1-12, 1-13, 1-14, 1-15, 1-16, 1-17, 1-18, 1-19, 1-20, 1-21, 1-23, 1-24, 1-25, 1-27, 1-28, 2-29 Occupiers - 1-06, 1-12, 1-13, 1-14, 1-15, 1-16, 1-17, 1-18, 1-19, 1-20, 1-21, 1-22, 1-23, 1-24, 1- 25, 1-26, 1- 27, 1-28, 2-29 Category 2 - 3-218 | Temporary Use - 1-15, 1-22, 1-26 New Rights - 1-12, 1-13, 1-14, 1,-15, 1-16, 1-17, 1-18, 1-20, 1-23, 1-24, 1-25, 1-27, 1-28, 2-29, 3-218 Freehold Acquisition - 1-19, 1-21 | This is a SSE plc Group Company. Heads of terms are being progressed for agreement with the relevant SSE plc entities. | Intercompany Heads of Terms under discussion
| 1-12, 1-13, 1-14, 1-16, 1-17, 1-18, 1-19, 1-20, 1-21, 1-23, 1-24, 1-25, 1-28, 2-29 | 8A - Vehicular Site Access
| 1-19, 1-20, 1-21 | 8B - Gatehouse & Layby
| 1-12, 1-13, 1-14, 1-15, 1-16, 1-17, 1-18, 1-19, 1-20, 1-21 | 8C - Gatehouse Services
| 1-26, 1-27 | 9A - Construction & Temporary Laydown
| 1-12, 1-13, 1-14, 1-16, 1-17, 1-18, 1-19, 1-20, 1-21, 1-22, 1-23, 1-24, 1-25, 1-28, 2-29 | 9B - Temporary Access Area to Construction & laydown area
| 1-12, 1-13, 1-14, 1-15 | 9C - Temporary Construction and Laydown Area in Association with Replacement of Private Bridge
| 1-12, 1-14, 1-15, 1-16, 1-18, 1-19, 1-21, 1-23, 1-25, 1-27 | 10 - Potential Landscaping and Planting Area
Strawson, Richard Henry | 2-41, 2-42, 2-43, 2-44, 2-46, 2-47, 2-48, 2-49, 2-51, 2-52, 2-53, 2-54, 2-55, 2-56, 2-57, 2-58, 2-59, 2-60, 2-61, 2-62, 2-66 | 8D - Emergency Operational Access | Freehold - 2-42, 2-43, 2-44, 2-47, 2-48, 2-49, 2-52, 2-54, 2-55, 2-56, 2-57, 2-58, 2-60, 2-61, 2-62, 2-66 Riparian Owner - 2-41, 2-46, 2-51, 2-53, 2-59 Occupiers - 2-42, 2-43, 2-44, 2-47, 2-48, 2-49, 2-52, 2-54, 2-55, 2-56, 2-57, 2-58, 2-60, 2-61, 2-62, 2-66 | Temporary Use - 2-55 New Rights - 2-41, 2-42, 2-43, 2-44, 2-48, 2-49, 2-51, 2-52, 2-53, 2-54, 2-56, 2-57, 2-58, 2-59, 2-60, 2-61, 2-62, 2-66 Freehold Acquisition - 2-46, 2-47, | See comments in respect of Severn, Andrew Clive. | Negotiations underway
The Isle of Oxholm and North Nottinghamshire Water Level Management Board | 3-143, 3-145, 3-156 | 4A - Primary Electrical connection & Distribution facilities | Freehold - 3-220 Riparian Owner - 3-219, 3-221 Occupiers - 1-05, 1-26, 1-27, 2-41, 2-46, 2-51, 2-53, 2-59, 2-65, 3-143, 3-145, 3-156, 3-186, 3-213, 3-215, 3-216, 3-217, 3-219, 3-220, 3-221, 3-223 | Temporary Use - 1-26, 1-27 New Rights - 1-05, 2-41, 2-51, 2-53, 2-59, 2-65, 3-143, 3-145, 3-156, 3-186, 3-213, 3-215, 3-216, 3-217, 3-219, 3-220, 3-221, 3-223 Freehold Acquisition - 2-46 | The Applicant is seeking to vary the existing Deeds in respect of the water discharge pipe together with cathodic protection easements. Headline Terms have been agreed that are consistent with other landowners (set out above). Isle of Axeholme waiting for Charities Act Report recommendation that the proposed agreement is in the best interests of the charity. Applicant is chasing for an update. | All matters save for the level of compensation are agreed
| 3-143, 3-186, 3-213, 3-215, 3-216, 3-217, 3-219, 3-220, 3-221, 3-223 | 6 - Cooling & Wastewater discharge pipeline
| 3-143 | 7 - Public Water
| 1-05 | 8C - Gatehouse Services
| 2-41, 2-46, 2-51, 2-53, 2-59, 2-65 | 8D - Emergency Operational Access
| 1-26, 1-27 | 9A - Construction & Temporary Laydown
The King's Most Excellent Majesty In Right Of His Crown | 3-229, 3-230 | 6 - Cooling & Wastewater discharge pipeline | Freehold - 3-205, 3-206, 3-207, 3-229, 3-230 Occupiers - 3-206, 3-229, 3-230 | Temporary Use - 3-205, 3-206, 3-207 New Rights - 3-229, 3-230 | The Applicant requires the use of the Jetty which is leased from the Crown in order to unload construction materials from barges. The barges would be unloaded by PD Ports, acting as Ships Agent, and the construction materials transported across Railway Wharf, which is owned by SSE, over the highway and through the PD Ports warehouse yard. As such, the Jetty is only one of a number of interests required in order to bring large construction items onto site. The Jetty has previously been used for this purpose without any opposition by the Crown or demands for significant payments. With regard to the proposed DCO, the Crown would not engage in negotiations until after the DCO was submitted and, prior to a meeting on 14 November 2025, no progress had been made despite the Crown benefitting from a fee undertaking. Whilst KNGL already benefit from a lease over the jetty, the Crown dispute that the jetty can be used for the purposes of this development. In addition, the Crown has taken the stance that, as it is not subject to compulsory acquisition powers, neither the Compensation Code nor the RICS definition of Market Value apply to it. It therefore considers that it is entitled to a share of the turnover generated by the completed development or, alternatively, a share of the alleged savings that arise through the use of the jetty irrespective of the fact that the jetty can only be used in conjunction with the adjoining land. The Applicant has proposed the grant of a new lease on three alternative approaches: 1) An agreed rent for the unchallenged use of the jetty on the same approach that would apply if the Crown was unable to exploit its exemption from CA powers 2) A Third-Party determination of the rent to be paid 3) A price per boat delivery | The Crown has yet to set out its proposed financial terms despite repeated chasing by the Applicant.
| 3-205, 3-206, 3-207 | 9E - Jetty & crane offloading for waterborne transport and river barges
Vodafone Limited | 2-104 | 4A - Primary Electrical connection & Distribution facilities | Occupiers - 2-104 | New Rights - 2-104 | Vodafone hold equipment in the plots identified in the Book of Reference. The Applicant does not intend to extinguish, vary, or otherwise impact upon existing rights. To the extent that the Applicant's works have any potential to impact upon such equipment, this is a matter for engineer engagement. | No land rights or interests required
| 2-104 | 4B - Alternative Electrical connection & Distribution facilities
Wall, Andrew (personal representative of) | 3-208 | 6 - Cooling & Wastewater discharge pipeline | Freehold - 3-208 Occupiers - 3-208 | New Rights - 3-208 | The original terms of an Option agreement for variation of existing easement to enable the Applicant to benefit from the existing water discharge pipes and cathodic protection were agreed in principle. Further amendments are being discussed with the landowner's solicitors to account for the change of beneficiary. The Applicant is hopeful that exchange and completion will be achieved prior to end 2025. | With solicitors
Wall, Donna | 3-208 | 6 - Cooling & Wastewater discharge pipeline | Occupiers - 3-208 | New Rights - 3-208 | The original terms of an Option agreement for variation of existing easement to enable the Applicant to benefit from the existing water discharge pipes and cathodic protection were agreed in principle. Further amendments are being discussed with the landowner's solicitors to account for the change of beneficiary. The Applicant is hopeful that exchange and completion will be achieved prior to end 2025. | With solicitors
Wall, Vivien Anne | 3-186, 3-208 | 6 - Cooling & Wastewater discharge pipeline | Freehold - 3-208 Riparian Owner - 3-186 Occupiers - 3-208 | New Rights - 3-186, 3-208 | The original terms of an Option agreement for variation of existing easement to enable the Applicant to benefit from the existing water discharge pipes and cathodic protection were agreed in principle. Further amendments are being discussed with the landowner's solicitors to account for the change of beneficiary. The Applicant is hopeful that exchange and completion will be achieved prior to end 2025. | With solicitors
Way, Angela | 3-125 | 5 - Cooling Water Abstraction | Freehold (subsoil) - 3-125 | New Rights - 3-125 | This comprises an unregistered plot of subsoil under Chapel Lane. It is not proven beyond reasonable doubt that Ms Way owns the subsoil such that compulsory purchase powers will need to be exercised in any event. | Compulsory acquisition powers will be required due to uncertainty as to ownership
Yorkshire Water Limited | 3-145, 3-153, 3-154, 3-156 | 4A - Primary Electrical connection & Distribution facilities | Occupiers - 3-127, 3-130, 3-136, 3-139, 3-140, 3-145, 3-153, 3-154, 3-156, 3-195, 3-198, 3-210 | Temporary Use - 3-195, 3-198 New Rights - 3-127, 3-130, 3-136, 3-139, 3-140, 3-145, 3-153, 3-154, 3-156, 3-210 | Yorkshire Water Ltd hold equipment in the plots identified in the Book of Reference. The Applicant does not intend to extinguish, vary, or otherwise impact upon existing rights. To the extent that the Applicant's works have any potential to impact upon such equipment, this is a matter for engineer engagement. | No land rights or interests required
| 3-127, 3-130 | 5 - Cooling Water Abstraction
| 3-136, 3-139, 3-140, 3-153, 3-210 | 6 - Cooling & Wastewater discharge pipeline
| 3-136, 3-139, 3-140, 3-153 | 7 - Public Water
| 3-130, 3-195 | 9D - Temporary Haul Route
| 3-198 | 9E - Jetty & crane offloading for waterborne transport and river barges
W. H. Strawson (Notts) Limited | 1-05 | 8C - Gatehouse Services | Freehold - 1-05 Occupiers - 1-05 | New Rights - 1-05 | The Applicant wishes to install a cable to take power across a field from the network to the gatehouse. Negotiations have taken place and it is intended that Heads of Terms together with technical design details will be issued at the earliest opportunity. | Negotiations underway.
Unknown/Unregistered | 3-115 | 1C - Power station staff support facilities | Freehold - 1-01, 1-03a, 1-03b, 1-03c, 2-35, 2-41, 2-46, 2-51, 2-53, 2-59, 2-67, 3-115, 3-124, 3-125, 3-126, 3-127, 3-128, 3-129, 3-130, 3-131, 3-132, 3-133, 3-135, 3-136, 3-139, 3-140, 3-143, 3-145, 3-153, 3-154, 3-156, 3-182, 3-183, 3-185, 3-186, 3-196, 3-197, 3-210, 3-211, 3-213, 3-215, 3-217, 3-219, 3-221, 3-223, 3-225, 3-226, 3-227, 3-228 Freehold (subsoil) - 3-227 | Temporary Use - 3-196, 3-197 New Rights - 1-01, 1-03a, 1-03b, 1-03c, 2-35, 2-41, 2-51, 2-53, 2-59, 2-67, 3-124, 3-125, 3-126, 3-127, 3-128, 3-129, 3-130, 3-131, 3-132, 3-133, 3-135, 3-136, 3-139, 3-140, 3-143, 3-145, 3-153, 3-154, 3-156, 3-182, 3-183, 3-185, 3-186, 3-210, 3-211, 3-213, 3-215, 3-217, 3-219, 3-221, 3-223, 3-225, 3-226, 3-227, 3-228 Freehold Acquisition - 2-46, 3-115 | In the absence of being able to identify actual owners, the Applicant will need to rely on compulsory purchase powers. These plots predominantly comprise highway subsoil. | Compulsory acquisition powers will be required due to uncertainty as to ownership
| 3-143, 3-145, 3-153, 3-154, 3-156 | 4A - Primary Electrical connection & Distribution facilities
| 3-115, 3-124, 3-125, 3-126, 3-127, 3-128, 3-129, 3-130, 3-131, 3-132, 3-133 | 5 - Cooling Water Abstraction
| 3-135, 3-136, 3-139, 3-140, 3-143, 3-153, 3-183, 3-185, 3-186, 3-210, 3-211, 3-213, 3-215, 3-217, 3-219, 3-221, 3-223, 3-225, 3-226, 3-227, 3-228 | 6 - Cooling & Wastewater discharge pipeline
| 3-135, 3-136, 3-139, 3-140, 3-143, 3-153 | 7 - Public Water
| 1-03b, 2-35 | 8A - Vehicular Site Access
| 1-01, 1-03a, 1-03b, 1-03c | 8C - Gatehouse Services
| 2-41, 2-46, 2-51, 2-53, 2-59, 2-67 | 8D - Emergency Operational Access
| 2-35 | 9B - Temporary Access Area to Construction & laydown area
| 3-115, 3-129, 3-130, 3-131, 3-132, 3-133, 3-196, 3-197 | 9D - Temporary Haul Route
| 3-182 | 10 - Potential Landscaping and Planting Area
Note on F31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Add year for November dates and clarify that the Canal Improvement Study is a CRT piece of work
Note on F98: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Refers to the existing lease for water discharge pipes as being ‘of insufficient length’ – suggest amending to ‘duration’ as 'length' could be misinterpreted
Note on F184: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Is it worth adding “the emergency access track will be required to be widened to ensure suitable access for fire engines.”