## Part 1 LO
PART 1
Ref | Landowner/ Affected Party | Agent/ Representative | Book of Ref. Plot No. | Plan Ref. No. | Description of Land | Description of Rights Requested | Works Number(s) | Status of Objection | Notes | Last Updated | Summary of Negotiations | Status of Negotiations | Relevant Rep Ref No. | Written Rep Ref No. | Ref No. for any other docs submitted by IP/AP. | Ref No. for Applicant's Response
304655 | Alan Leslie Pearse | Brian Bartle | 10-003, 16-008, 16-011 | 10, 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8B |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 8 September 2025 and 1 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent met with the Landowner's appointed land agent on 22 May 2026 to discuss and progress the Heads of Terms. It was made clear to the Applicant's land agent in that meeting that the Landowner was unwilling to enter into negotiations. Notwithstanding the position reported by the Landowners appointed land agent, the Applicant will continue to engage with them with the intention to progress the Heads of Terms. |  | Alan Pearse - RR-0014
|  |  | 08-005, 08-006, 08-009, 08-021, 08-022, 08-024, 10-004, 10-012 | 8, 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 8 September 2025 and 1 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent met with the Landowner's appointed land agent on 22 May 2026 to discuss and progress the Heads of Terms. It was made clear to the Applicant's land agent in that meeting that the Landowner was unwilling to enter into negotiations. Notwithstanding the position reported by the Landowners appointed land agent, the Applicant will continue to engage with them with the intention to progress the Heads of Terms.
305115, 305144, 305340, 318156 | Alison Joan Bramley, Brigita Fionait Bramley, Richard Andrew Bramley, The Executor of the Estate of the Late John Richard Bramley | Stephen Burley | 05-003, 05-006 | 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 19 August 2025 and 10 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B There has been extensive dialogue between the Landowner's appointed land agent and the Applicant. The Landowner's appointed land agent has reported to the Applicant that the Heads of Terms are agreed, however a signed document has, at the time of updating this tracker, not been received. The Applicant will continue to engage with the Landowner's appointed land agent to arrange for signed documents to be provided.
331926, 331971 | Andrew David McCloy, Sarah Jane Foster | Mary Foster | 21-037, 21-038, 21-039 | 21 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant consulted with the Landowners as part of the pre-application consultation processes. The Applicant is commencing negotiations with these Landowners following confirmation of the nature of the requirements and rights sought for this land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B Heads of Terms were issued on 16 March 2026. The Applicant's appointed land agent has engaged with the Landowner's appointed land agent and most recently held a meeting on 15 June 2026. The route proposed remains the outstanding issue and the Applicants is reviewing this and remains confident a voluntary agreement can be acquired.
322665 | Andrew James Cawood | Johnny Cordingley | 13-051, 14-001, 14-002, 14-003, 14-004, 14-017, 14-022, 15-002 | 13, 14, 15 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 5, 6, 7, 8B, 10B |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
|  |  | 16-002 | 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
311856, 339988 | Andrew William Headley, Richard Mark Headley |  | 03-007 | 3 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for this land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B A populated licence agreement was issued to the Landowners on 3 June 2026. The Applicant's appointed land agent held a meeting with the Landowners' appointed land agent on 15 June 2026 to progress negotiations. The Applicant will continue to engage with the Landowners and their land agent and is confident the necessary land rights can be acquired by voluntary agreement.
305122, 305310, 305331, 339681 | Angela Fiona Smith, Neil James Cawthorne, Phyllis Margaret Cawthorne, The Executor of the Estate of the Late James Cawthorne | Johnny Cordingley | 11-037, 11-038 | 11 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legal documents are progressing.
304644 | Anne Colette Harrison | Mary Foster | 11-025, 11-035 | 11 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives Procedural Deadline B Legal representatives have been instructed and negotiations of the legal documents are progressing.
|  |  | 11-008 | 11 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing.
304608, 304609 | Anne Vincent, George Edward Vincent | Chris Thyer | 13-036, 13-040 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 24 November 2025, 27 and 28 January 2026 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent has engaged regularly with the Applicant's appointed land agent. The principle issue with the Heads of Terms Document is regarding land agents fees, for which the Applicant's land agent and the Landowners land agent are working together to resolve this matter. The Applicant will continue to engage with the Landowners and their agent and is confident that the necessary land rights can be acquired by voluntary agreement. |  | George Edward Vincent - RR-0474
305134, 305304, 305335 | Barbara Wilson, Michael Edwin Wilson, Rachel Elizabeth Wilson | Michael Townend | 10-007, 10-008, 10-013, 10-014, 10-023 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. |  | Rachael Wilson - RR-1137
305138, 305175 | Brian Anthony Richardson, Elaine Caroline Richardson | Ben Wills | 12-075, 19-005, 19-006, 19-010, 19-011, 19-012 | 12, 19 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on the 12 January 2026 to progress landowner specific aspects of the HoTs. The Applicant is aware Hillam Solar Limited have a beneficiary interest in the land by way of an option agreement and is working with the Landowners, their appointed land agent and Hillam Solar Limited to obtain the necessary consents. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 5 May 2026. The principal surrounding route optionality was agreed in relation to the Hillam Solar Limited development. Revised Heads or Terms reflecting this are due to be re-issued to the Landowners' appointed land agent shortly. The Applicant will continue to engage with the Landowners and their land agent and is confident the necessary land rights can be acquired by voluntary agreement. |  | Elaine Caroline Richardson - RR-0382
305140, 305217, 305266 | Brian Dennis Heselwood, Ian George Heselwood, Keith Alan Heselwood | Michael Townend | 09-003 | 9 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this.
356225, 332776, 356199 | Caroline Seiler, Pamela Austwick, William Harry Johnson |  | 20-045 | 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant consulted with the Landowners as part of the pre-application consultation processes. The Applicants agent are working with the Landowners to understand an ownership query. Once the ownership query is established, the Applicant will commence negotiations with this Landowners following confirmation of the nature of the requirements and rights sought for this land. A draft licence agreement is being prepared and is due to be issued shortly. Procedural Deadline B A licence agreement was issued to the Landowners on 3 June 2026. The Landowner has emailed the Applicant's land agent advising they are unwilling to enter into negotiations. Notwithstanding the position reported by the Landowner, the Applicant is committed to continuing to engage with them and understand their concerns with the intention to progressing a voluntary position.
305148, 305195 | Charles Andrew John Tindall, Geoffrey Tindall |  | 08-020 | 8 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant consulted with the Landowners as part of the pre-application consultation processes. The Applicant is commencing negotiations with the Landowners following confirmation of the nature of the requirements and rights sought for this land. A draft licence agreement is being prepared and is due to be issued shortly. Procedural Deadline B A licence agreement was issued to the Landowners on 3 June 2026. The Applicant's appointed land agent received a signed licence on 22 June 2026.
305149, 305263 | Charles Angus William Gowthorpe, Kathleen Margaret Gowthorpe | Stephen Burley | 05-046, 05-047, 05-048, 06-002, 06-004, 06-007 | 5, 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant has received signed Heads of Terms on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing.
305149, 305263, 326739 | Charles Angus William Gowthorpe, Kathleen Margaret Gowthorpe, The Executor of the Estate of the Late Peter Ward Gowthorpe | Stephen Burley | 05-043 | 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant has received signed Heads of Terms on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing.
|  |  | 05-042 | 5 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant has received signed HoTs on 29th January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing.
304585 | Charles David Forbes Adam | Giles Johnson | 01-004, 01-009, 01-012, 01-019, 01-023, 01-030, 01-033 | 1 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 3, 5, 6, 7, 9A, 10A |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
|  |  | 01-002, 01-003, 01-005, 01-006, 01-010, 01-011, 01-031, 02-002, 03-002, 03-004, 03-005, 03-011, 03-015, 03-019, 03-020, 03-023, 03-024, 03-025, 03-026, 03-027, 03-028, 03-050, 03-051 | 1, 2, 3 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 8B, 10A |  |  | 2026-07-01 | Option Holder An option for lease with this Landowner exists for the majority of these plots. Following confirmation of the Order limits, some plots are not covered by that option. The Applicant is therefore working with the Landowner to regularise the position in respect of those remaining plots and is confident that this will be able to be resolved. Procedural Deadline B The Applicant is working with the Landowner to complete a variation to the existing option for lease to ensure all plots are cover by that option.
|  |  | 03-001, 05-005 | 3, 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 3, 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this.
|  |  | 03-006, 03-012, 03-016, 03-054 | 3 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this.
304585, 305162 | Charles David Forbes Adam, Crispin Beilby Forbes Adam | Giles Johnson | 03-062 | 3 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their agent to achieve this.
304585, 328172, 328179, 328186 | Charles David Forbes Adam, Frederick Michael Martin Woodhead, Lettice Hunter Bell, Nicholas David Cuthbert Hopkinson | Giles Johnson | 03-021 | 3 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowners' appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this.
322656 | Charles Ian Farrar | Johnny Cordingley | 14-014 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d) |  |  | 2026-07-01 | Negotiations for rights The Applicant has received signed Heads of Terms on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing.
304652 | Christopher Philip Yewdall | Stephen Burley | 16-003, 16-005, 16-006, 16-007 | 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B |  |  | 2026-07-01 | Negotiations for rights The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for this land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B Heads of Terms were issued by the Applicant to the Landowner on 16 March 2026. The Applicant will continue to work with the landowners appointed land agent to progress the Heads of Terms.
305157, 305203, 305300 | Clifford Ian Roy Watson, Gillian Heather Walmsley, Melanie Jane Brown | Giles Bilton | 10-026 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 22 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowners' appointed land agent and is confident the necessary land rights can be acquired by voluntary agreement.
|  |  | 10-027 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 22 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowners' appointed land agent and is confident the necessary land rights can be acquired by voluntary agreement.
304676 | Colin Smith | Johnny Cordingley | 09-004 | 9 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 and 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed agent continues to engage with the Landowner's appointed land agent and most recently held a meeting on 15 June 2026. The Applicant will continue to engage with the Landowner and their land agent and is confident the necessary land rights can be acquired by voluntary agreement. |  | Colin Smith - RR-0283
|  |  | 09-006, 09-009 | 9 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 and 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowner's appointed agent and most recently held a meeting on 15 June 2026. The Applicant will continue to engage with the Landowner and their land agent and is confident the necessary land rights can be acquired by voluntary agreement.
305162 | Crispin Beilby Forbes Adam | Giles Johnson | 01-008, 01-013, 01-014, 01-016, 01-017, 01-018, 01-020, 01-021, 01-025, 01-027, 01-029, 01-034, 02-006, 02-005 | 1, 2 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 5, 6, 7, 9A, 9B, 10A |  |  | 2026-07-01 | Option Holder An option for lease with this Landowner exists for the majority of these plots. Following confirmation of the Order limits, some plots are not covered by that option. The Applicant is therefore working with the Landowner to regularise the position in respect of those remaining plots and is confident that this will be able to be resolved. Procedural Deadline B The Applicant is working with the Landowner to complete a variation to the existing option for lease to ensure all plots are cover by that option.
|  |  | 01-015, 01-022, 01-024, 01-026, 01-028, 01-032, 02-003 | 1, 2 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 8B |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
|  |  | 02-011, 03-017, 03-018, 03-046, 03-049, 03-059, 05-002, 05-004 | 2, 3, 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this.
|  |  | 02-008, 03-033, 03-034, 03-035, 03-036, 03-040, 03-041, 03-043, 03-044, 03-045, 03-047, 03-048,04-003 | 2, 3, 4 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this.
305081 | Crosshills Pigs Limited | Michael Townend | 08-037, 09-001, 09-002 | 8, 9 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this.
66248 | David Arnold Platt | Thomas Cooper | 12-002, 12-012, 19-013, 19-014 | 12, 19 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 and 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent has attempted to contacted the Landowner's appointed land agent regularly, most recently on 19 June 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement.
356719, 340089 | The Executor of the Estate of the Late David Coates, Jane Coates |  | 21-007 | 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant has received signed Heads of Terms on 18th December 2025 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives Procedural Deadline B The Applicant's appointed land agent has contacted the landowner regularly, most recently on 1 July 2026, to obtain confirmation of the Landowner's legal representative. The Applicant's appointed land agent will continue to attempt to engage with the Landowner to progress the legal documents.
304647, 304648 | David Michael Hall, Elizabeth Hall | Giles Johnson | 13-001 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowners' appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22nd May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this.
|  |  | 15-001, 15-013 | 15 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowners' appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this.
162803, 162804, 289862 | Diane Lawrie Hey, Timothy Brian Hey, Mark Alan Hey | Matthew Watson / Andrew Holden | 11-018, 11-030, 11-031, 11-033, 15-004, 15-005, 15-006, 15-009, 15-010 | 11, 15 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 7, 8A, 8B |  |  | 2026-07-01 | Negotiations for rights The Applicant's appointed land agent received verbal confirmation the Heads of Terms are in an agreed format on 29 January 2026 from the Landowners' appointed land agent and is awaiting signed copies of the Heads of Terms. Procedural Deadline B The Applicant received signed Heads of Terms on the 16 March 2026. The Applicant is awaiting confirmation of the Landowner's legal representative from the Landowner. The Applicant's land agent has contacted the Landowner's appointed agent regularly to obtain these details, most recently on the 30 June 2026. |  | Tim Hey - RR-1391
|  |  | 11-003, 11-010, 11-019, 11-020, 11-034 | 11 | As described in the Book of Reference | Land is subject to Temporary Possession | 7, 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant's appointed land agent received verbal confirmation the Heads of Terms are in an agreed format on 29 January 2026 from the Landowners' appointed land agent and is awaiting signed copies of the Heads of Terms. Procedural Deadline B The Applicant received signed Heads of Terms on the 16 March 2026. The Applicant is awaiting confirmation of the Landowner's legal representative from the Landowner. The Applicant's land agent has contacted the Landowner's appointed agent regularly to obtain these details, most recently on the 30 June 2026.
305182 | Emma Vaughn Clark | Thomas Hind | 06-033 | 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 to progress Landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent has attempted to contact the Landowner's appointed land agent regularly, most recently on 19 June 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement.
20333 | Environment Agency |  | 06-009, 06-011, 06-012, 06-016 | 7 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on the 28 November 2025, 8 December 2025 and 7 January 2026 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant received signed Heads of Terms on 26 June 2026 and will now progress negotiations of the legal documents through the Landowner's respective legal representatives. |  | Environment Agency - RR-0528 and RR-0419
305188, 305222 | Francesca Elizabeth Young, James Edward Hartley | Giles Johnson/ Brian Bartle | 12-050, 12-051, 12-053, 12-054 | 12 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 5, 6, 7, 8B, 10B |  |  | 2026-07-01 | Option Holder An option for lease with these Landowners exists for the majority of these plots. Following confirmation of the Order limits, some plots are not covered by that option. The Applicant is therefore working with the Landowners to regularise the position in respect of those remaining plots and is confident that this will be able to be resolved. Procedural Deadline B The Applicant is working with the Landowner to complete a variation to the existing option for lease to ensure all plots are cover by that option.
|  |  | 12-049 | 12 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 8 September 2025 and 1 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant met with the landowners appointed land agent on the 22nd May 2026 in order to progress the Heads of Terms. There remains several matters within the terms that are to be agreed, and there has been limited substantive feedback received from the Landowner's appointed land agent. The Applicant will continue to engage with the Landowner's appointed land agent to progress Heads of Terms, and is confident that the necessary land rights can be agreed on a voluntary basis.
305199 | George Louis Outhwaite | Johnny Cordingley | 05-049, 06-006 | 5, 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 and 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowner's appointed land agent and most recently held a meeting on 15 June 2026 to progress negotiations. The Applicant will continue to engage with the Landowners and their land agent and is confident the necessary land rights can be acquired by voluntary agreement. |  | George Outhwaite - RR-0475
328644 | Gillian Francis Parkin | Tori Heaton | 13-008 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this.
|  |  | 13-006, 15-014 | 13, 15 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed agent on 22nd May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their agent to achieve this.
305085 | Hartley Farming (Yorkshire) Limited | Brian Bartle | 12-035, 12-073, 12-074, 19-003 | 12, 19 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 3, 5, 6, 8B, 10B |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
|  |  | 19-004 | 19 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d) |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
|  |  | 17-006, 17-008,17-010, 17-012 | 17 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B |  |  | 2026-07-01 | Negotiations for rights The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for this land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B Heads of Terms were issued by the Applicant to the Landowner on 3 July 2026. The Applicant will continue to work with the landowners appointed land agent to progress the Heads of Terms.
305211, 305385 | Heather Victoria Verity, Tom Edwin Verity | Giles Johnson / Brian Bartle | 13-021, 13-035 | 13 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 2, 3, 5, 6, 7 |  |  | 2026-07-01 | Option Holder An option for lease with these Landowners exists for the majority of these plots. Following confirmation of the Order limits, some plots are not covered by that option. The Applicant is therefore working with the Landowners to regularise the position in respect of those remaining plots and is confident that this will be able to be resolved. Procedural Deadline B The Applicant is working with the Landowner to complete a variation to the existing option for lease to ensure all plots are cover by that option.
|  |  | 13-020, 13-022, 13-029, 13-030 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 8A, 8B |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
|  |  | 13-019, 13-031 | 13 | As described in the Book of Reference | Land is subject to Temporary Possession | 1(d), 8A, 8B |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
330221 | Helen Elizabeth Platt | Thomas Cooper | 12-005 | 12 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for this land. A draft licence agreement is being prepared and is due to be issued shortly. Procedural Deadline B A populated licence agreement was issued to the Landowners on 3 June 2026. The Applicant's appointed land agent has contacted the Landowner's appointed agent on 19 June 2026 to progress negotiations. The Applicant will continue to engage with the Landowners and their land agent and is confident the necessary land rights can be acquired by voluntary agreement.
305212, 305262 | Helen Michaela Scholey, Karen Elizabeth Scholey | Michael Townend | 20-025 | 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowners' appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this.
|  |  | 20-040, 20-041 | 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowners' appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this.
305212, 305262, 341991 | Helen Michaela Scholey, Karen Elizabeth Scholey, The Executor of the Estate of the Late Paul Sherrard Scholey | Michael Townend | 20-021 | 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their agent to achieve this.
334252 | Hey Holdings Limited | Matthew Watson | 11-036 | 11 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant's appointed land agent received verbal confirmation the Heads of Terms are in an agreed format on 29 January 2026 from the Landowner's appointed land agent and is awaiting signed copies of the Heads of Terms. Procedural Deadline B The Applicant received signed Heads of Terms on the 16 March 2026. The Applicant is awaiting confirmation of the Landowner's legal representative from the Landowner. The Applicant's land agent has contacted the Landowner's appointed agent regularly to obtain these details, most recently on the 30 June 2026.
305089 | J.H. McCloy & Co Limited | Mary Foster | 19-017, 19-018, 20-003, 20-004, 20-007, 20-008, 20-011, 20-012, 20-026, 20-031, 20-032 | 19, 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 7, 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 and 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant understands the Heads of Terms are in an agreed format apart from an outstanding query on an operational access route. The Applicant's land agent is working with the Landowner's land agent to resolve this issue and is confident the necessary land rights can be acquired by voluntary agreement. The Applicant understands that UK Power Associates Ltd have a beneficiary interest in the land by way of an option agreement and is working with the Landowners to obtain the necessary consents. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowners' appointed land agent and most recently held a meeting on 15 June 2026. The route proposed remains the outstanding issue and the Applicants is reviewing this and remains confident a voluntary agreement can be acquired.
|  |  | 19-016, 20-005, 20-029, 20-033, 20-034, 20-039 | 19, 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 7, 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 and 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant understands the Heads of Terms are in an agreed format apart from an outstanding query on an operational access route. The Applicant's land agent is working with the Landowner's land agent to resolve this issue and is confident the necessary land rights can be acquired by voluntary agreement. The Applicant understands that UK Power Associates Ltd have a beneficiary interest in the land by way of an option agreement and is working with the Landowners to obtain the necessary consents. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowners' appointed land agent and most recently held a meeting on 15 June 2026. The route proposed remains the outstanding issue and the Applicants is reviewing this and remains confident a voluntary agreement can be acquired.
305219 | Jacqueline Daphne Bradshaw | Thomas Hind | 06-015, 06-017, 06-018, 06-019, 06-022, 06-023 | 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent has attempted to contact the Landowner's appointed land agent regularly, most recently on 19 June 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement.
244072 | James Edward Clark | Thomas Hind | 06-020, 06-021, 06-024, 06-025, 06-028, 06-038, 06-042, 06-043, 06-044, 06-045, 07-023, 07-024, 07-025, 07-026, 08-014 | 6, 7, 8 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent has attempted to contact the Landowner's appointed land agent regularly, most recently on 19 June 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement. |  | C E CJ E Clark - RR-0175
|  |  | 06-031, 06-032, 06-034, 06-035, 06-036, 06-039, 07-012, 07-013, 07-027, 08-002, 08-003, 08-004, 08-007, 08-016, 08-017, 08-018 | 6, 7, 8 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed agent has attempted to contact the Landowner's appointed land agent regularly, most recently on 19 June 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement.
305222 | James Edward Hartley | Giles Johnson/ Brian Bartle | 12-034, 12-052, 12-055, 12-060, 12-071, 12-072, 18-008, 18-013, 18-014, 18-015 | 12, 18 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 3, 5, 6, 7, 8A, 8B, 10B |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
|  |  | 18-001, 18-002, 18-011 | 18 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 8B, 10B |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
305234, 305287, 305344 | Joan Mary Smith, Margaret Hirst, Richard John Pratt | Stephen Burley | 05-030 | 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 19 August 2025 and 10 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant received signed Heads of Terms on 27 February 2026. The Applicant is awaiting confirmation of the Landowner's legal representative from the Landowner. The Applicant's land agent has contacted the Landowner's appointed agent regularly to obtain these details, most recently on the 02 July 2026.
305237, 305245, 305346, 305363 | John Charles Cox, John Richard Hall, Richard Thomas Batty, Sarah Batty | Johnny Cordingley | 20-023, 20-024 | 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing.
305238, 305248 | John Cook, Jonathan Cook | Richard Waring | 09-016 | 9 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B The Applicant's appointed land agent has contacted the Landowner's appointed land agent regularly, most recently on 1 July 2026, to obtain confirmation of the Landowner's legal representative. The Applicant's appointed land agent understands legal representatives have been confirmed and awaits the detail of these. |  | John Stuart Cook - RR-0686
304673, 305168, 305269 | John Miles Sherwood, David Kenneth Sherwood, Kevin Andrew Sherwood |  | 08-008 | 8 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant consulted with the Landowners as part of the pre-application consultation processes. The Applicant is commencing negotiations with the Landowners following confirmation of the nature of the requirements and rights sought for this land. A draft licence agreement is being prepared and is due to be issued shortly. Procedural Deadline B A populated licence agreement was issued to the Landowners on 3 June 2026. The Applicant remains open to engagement with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement.
325410 | John Nicholas Stoker | Eliza Raine | 13-038, 13-041 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 10 December to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant met with the Landowner and his appointed land agent on the 22 April 2026 whereby progress was made on the Heads of Terms. The Applicant’s land agent understands that the Landowner’s land agent is no longer instructed. The Applicant will continue to engage directly with the Landowner and is confident that the necessary land rights can be acquired by voluntary agreement |  | John Nicholas Stoker - RR-0684
|  |  | 13-042 | 13 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 10 December to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B the Applicant met with the Landowner and his appointed land agent on the 22 April 2026 to progress the Heads of Terms, the Applicant had good engagement from the Landowner's agent, the landowners land agent has been subsequently disinstructed by the landowner. The Applicant will continue to engage directly with the landowner and is confident that the necessary land rights can be acquired by voluntary agreement.
304717 | Joseph Rex Pocklington | Thomas Hind | 06-013 | 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent has attempted to contact the Landowner's appointed land agent regularly, most recently on 19 June 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement.
304672 | Judith Ann Pearse | Brian Bartle | 09-021, 09-022 | 9 | As described in the Book of Reference | Land is subject to Temporary Possession | 7, 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for this land. A draft licence agreement is being prepared and is due to be issued shortly. Procedural Deadline B The Applicant issued Licences to the Landowner on 3 June 2026. The Applicant had met with the Landowners appointed land agent on the 22 May 2026 to discuss the overarching rights being sought by the Applicant. The land agent made it clear in the meeting that the Landowner was unwilling to progress the Heads of Terms. Notwithstanding the position reported by the Landowner's appointed land agent, the Applicant will continue to engage with them with the intention to progress the Heads of Terms.
305260, 358611 | June Elisabeth Romans, The Executor of the Estate of the Late Michael Robert Romans | Mary Foster | 05-017, 05-018, 05-020 | 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant's appointed land agent received written confirmation the Heads of Terms are in an agreed format on 29 January 2026 from the Landowner's appointed land agent and is awaiting signed copies of the Heads of Terms once an ownership query has been resolved. Procedural Deadline B The Applicant understands the ownership query has been resolved and the Heads of Terms are with the Landowner's representative for signature and are expected to be returned shortly.
305261, 334240, 334244 | June Harris, Alison Victoria Laskey, Sarah Joanne Thompson | Michael Townend | 12-014, 12-048 | 12 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowners' appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. |  | Sarah Thompson - RR-1262
349123 | Keith Winsor |  | 13-047 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for the land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B Heads of Terms were issued on 16 March 2026. The Applicant wrote to the Landowner again on 5 May 2026 and remains open to engagement with Landowner. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement.
305273, 305320 | Kt Jodie Allen, Paul Adam Watson | Thomas Hind | 07-019, 07-020 | 7 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 2 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent has attempted to contact the Landowner's appointed land agent regularly, most recently on 19 June 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement.
304641, 304642, 304643 | Margaret Anne Parkin, Andrew Kenneth Parkin, Jonathan William Parkin | Mary Foster | 13-009, 13-010 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing.
|  |  | 13-011 | 13 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing.
304606 | Marlene Thompson |  | 20-027, 20-032 | 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant has made attempts of engagement most recently 21 January 2026 . The Applicant will continue to attempt to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant re issued Heads of Terms to the Landowner's daughter on 24 June 2026 following a phone call to discuss the Heads of Terms document. The Applicant remains confident that all required land rights can be acquired by voluntary agreement.
|  |  | 20-028, 20-033 | 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025.The Applicant has made multiple attempts of engagement most recently 21 January 2026 . The Applicant will continue to attempt to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant re issued Heads of Terms to the Landowner's daughter on 24 June 2026 following a phone call to discuss the Heads of Terms document.
332764 | Martin James Bramley |  | 14-005 | 14 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 8B, 10B |  |  | 2026-07-01 | Option Holder The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for this land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B Heads of Terms were issued by the Applicant to the landowner on 16 March 2026. The Applicant will continue to work with the Landowner's appointed land agent to progress the Heads of Terms.
|  |  | 14-006 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B |  |  | 2026-07-01 | Option Holder The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for the land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B Heads of Terms were issued by the Applicant to the Landowner on 16 March 2026. The Applicant will continue to work with the landowners appointed land agent to progress the Heads of Terms.
|  |  | 14-007 | 14 | As described in the Book of Reference | Land is subject to Temporary Possession | 8B |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for this land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B There has been extensive dialogue between the Applicant and the Landowner's appointed land agent in relation to the Heads of Terms. It is understood by the Applicant that the Heads of Terms are agreed, however a signed document has not been received. The Applicant will continue to liaise with the landowners appointed land agent to progress the Heads of Terms and is confident that signed documents can be provided in due course.
305301 | Michael Anthony Bowker |  | 05-029 | 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant has received signed HoTs on 12 January 2026 and will now progress negotiations of the legal documents through the Landowner's respective legal representatives. Procedural Deadline B The Applicant is awaiting confirmation of the Landowner's legal representative from the Landowner. The Applicant's land agent has contacted the Landowner's regularly to obtain these details, most recently on the 30 June 2026.
305304, 305335, 340482 | Michael Edwin Wilson, Rachel Elizabeth Wilson, Sara Fox |  | 10-019 | 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant consulted with the interest as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Interest following confirmation of the nature of the requirements and rights sought for this party’s land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B A populated licence agreement was issued to the Landowners on 3 June 2026. The Applicant remains open to engagement with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. |  | Rachael Wilson - RR-1137
305093 | National Grid Electricity Transmission PLC |  | 21-008, 21-009, 21-011, 21-015, 21-016, 21-017, 21-018, 21-021, 21-024, 21-025, 21-026, 21-031, 21-035, 21-040 | 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 12th January 2026 . The Applicants land agent has made further attempts to engage. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent is continuing to engage with the Landowner and is working with the Landowner to complete the required forms to progress Heads of Terms. The Applicant will continue to engage with the Landowner and is confident that the necessary land rights can be reached by voluntary agreement. |  | National Grid Electricity Transmission PLC - RR-1037 and RR-0437
|  |  | 21-013, 21-019, 21-032, 21-033, 21-034 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5, 8A |  |  | 2026-02-04 | N/A
22908 | National Highways Limited |  | 05-019, 05-021, 05-024, 05-026, 05-028, 05-034, 05-035, 05-037, 10-052, 10-053, 10-054, 10-056, 10-059, 10-060, 10-062 | 5, 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 12 January 2026. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 24 November 2025. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant has been in discussion with National Highways and the representative of North Yorkshire Council to confirm the ownership of the land within the Heads of Terms. The Applicant is awaiting a response from North Yorkshire Council as to the Heads of Terms and the land ownership. The Applicant is confident that all land rights required can be agreed via voluntary agreement. |  | National Highways - RR-0177 and RR-1038
|  |  | 05-036, 05-038, 05-039, 05-041, 10-045, 10-047, 10-050, 10-051, 10-069 | 5, 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 12 January 2026. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 24 November 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant has been in discussion with National Highways and the representative of North Yorkshire Council to confirm the ownership of the land within the Heads of Terms. The Applicant is awaiting a response from North Yorkshire Council as to the Heads of Terms and the land ownership. The Applicant is confident that all land rights required can be agreed via voluntary agreement.
304738, 304739 | Neil Stainthorpe, Julie Fiona Stainthorpe |  | 08-025, 08-026 | 8 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for this land. A draft licence agreement is being prepared and is due to be issued shortly. Procedural Deadline B A populated licence agreement was issued to the Landowners on 3 June 2026. The Applicant's appointed agent held a meeting with the Landowners' appointed agent on 15 June 2026. The Applicant will continue to engage with the Landowners and their agent and is confident the necessary land rights can be acquired by voluntary agreement.
7310 | Network Rail Infrastructure Limited |  | 10-073, 10-074, 16-001 | 10, 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's land agent has made attempts to engage the landowner, most recently on 4 February 2026. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowner and held a meeting on 13 May 2026 to progress negotiations. The Applicant's appointed land agent continues to have productive dialogue with the landowner, most recently on 22 June 2026 and remains confident the necessary land rights can be acquired by voluntary agreement. |  | Network Rail Infrastructure Limited - RR-1298 and RR-1045
249688 | North Yorkshire Council |  | 03-033, 03-053, 08-038, 22-004 | 3, 8, 22 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 27 January 2026. The Applicant's land agent has made further attempts to engage. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent continues to have productive dialogue with the landowner, most recently on 1 July 2026 and remains confident the necessary land rights can be acquired by voluntary agreement. |  | North Yorkshire Council - RR-1075
325424 | Martin Bramley |  | 14-028 | 14 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 6 |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
|  |  | 14-024 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 8B |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
53140, 53214 | Paul Robert Swales, Peter David Swales | Robert Hamilton | 21-001, 21-003, 21-004, 21-005, 21-006 | 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 24 November 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowner's appointed land agent and has last emailed on thge 30th Jun 2026 . The Applicant is not aware of any outstanding matters to agree, and will therefore continue to work with the appointed land agent to progress towards a signed set of terms.
305326 | Peter Darley Stockdale | Mary Foster | 05-045, 06-001, 06-008 | 5, 7 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowner's respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing.
305327 | Peter James Richardson |  | 07-005, 07-006, 07-007, 07-010, 07-011 | 7 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with the Landowner following confirmation of the nature of the requirements and rights sought for this land. A draft licence agreement is being prepared and is due to be issued shortly. Procedural Deadline B A populated licence agreement was issued to the Landowner on 3 June 2026. The Applicant's land agent received a signed licence from the Landowner on 22 June 2026.
304613, 304619 | Richard Stephen Atkinson, Joanne Atkinson | Philip Bartle | 12-001 | 12 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners on 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant met with the Landowners appointed land agent on 22 May 2026 to discuss the Heads of Terms. The Applicant is not aware of any outstanding matters to agree, and will therefore continue to work with the appointed land agent to progress towards a signed set of terms. |  | Joanne Atkinson - RR-0662
304613, 304622 | Richard Stephen Atkinson, Julie Caroline Tye | Philip Bartle | 13-028 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners on 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant met with the Landowners appointed land agent on 22 May 2026 to discuss the Heads of Terms. The Applicant is not aware of any outstanding matters to agree, and will therefore continue to work with the appointed land agent to progress towards a signed set of terms.
305346, 305363 | Richard Thomas Batty, Sarah Batty | Johnny Cordingley | 13-049, 13-050, 14-021 | 13, 14 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 5, 6, 7, 10B |  |  | 2026-07-01 | Option Holder An option for lease with these Landowners exists for the majority of these plots. Following confirmation of the Order limits, some plots are not covered by that option. The Applicant is therefore working with the Landowners to regularise the position in respect of those remaining plots and is confident that this will be able to be resolved. Procedural Deadline B The Applicant is working with the Landowner to complete a variation to the existing option for lease to ensure all plots are cover by that option.
|  |  | 14-020 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 6 |  |  | 2026-07-01 | Option Holder An option for lease with the Landowners exists for the majority of plots within their ownership. Following confirmation of the Order limits, this plot is not covered by that option. The Applicant is therefore working with the Landowners to regularise the position in respect of this remaining plot and is confident that this will be able to be resolved. Procedural Deadline B The Applicant is working with the Landowner to complete a variation to the existing option for lease to ensure all plots are cover by that option.
304657, 304658 | Robert Frederick Stoker, Mark Edmund Stoker | Brian Bartle | 16-004 | 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B |  |  | 2026-07-01 | Negotiations for rights The Applicant consulted with the Landowners as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowners following confirmation of the nature of the requirements and rights sought for this land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B Heads of Terms were issued by the Applicant to the landowner on 16 March 2026. The Applicant will continue to engage with the Landowner's appointed land agent in order to progress these Heads of Terms.
305356 | Rosemarie Claire Tait | James Thompson | 20-014, 20-020 | 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 16 December 2025 and 21 January 2026 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B Revised Heads of Terms were issued to the Landowner's appointed land agent on 12 May 2026. The Applicant's appointed land agent will continue to engage with the Landowner and their appointed land agent and remains confident the necessary land rights can be acquired by voluntary agreement. |  | Rosie Tait - RR-1215
|  |  | 20-017, 20-019 | 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 16 December 2025 and 21 January 2026 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B Revised Heads of Terms were issued to the Landowner's appointed land agent on 12 May 2026. The Applicant's appointed land agent will continue to engage with the Landowner and their appointed land agent and remains confident the necessary land rights can be acquired by voluntary agreement.
325414, 325415 | Stephen Batty, Joyce Batty | Alexander Ireton | 13-048 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 10B |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 20 January 2026 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's land agent has continued to engage with the Landowner's appointed land agent most recently on 1 July 2026 to progress voluntary negotiations. The Applicant will continue to engage with the Landowner and their appointment land agent and is confident the necessary land rights can be acquired by voluntary agreement.
304697 | Stephen Mark Stockdale | Johnny Cordingley | 06-014, 07-022, 08-028, 08-035 | 6, 7, 8 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 7 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 and 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowner's appointed land agent and most recently held a meeting on 15 June 2026. The Applicant will continue to engage with the Landowner and their land agent and is confident the necessary land rights can be acquired by voluntary agreement.
|  |  | 07-009, 08-030, 08-032, 08-034, 08-036 | 7, 8 | As described in the Book of Reference | Land is subject to Temporary Possession | 7, 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 and 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed agent continues to engage with the Landowner's appointed land agent and most recently held a meeting on 15 June 2026. The Applicant will continue to engage with the Landowner and their land agent and is confident the necessary land rights can be acquired by voluntary agreement.
329022, 329023 | Stephen Michael Thompson, Mark Stuart Thompson | Mary Foster | 10-072, 11-024, 11-028, 11-032, 15-011, 16-019 | 10, 11, 15, 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A, 8B |  |  | 2026-07-01 | Negotiations for rights The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowner's respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing.
|  |  | 11-009, 11-012 | 11 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowner's respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing.
153114 | Sybil Elizabeth Platt | Thomas Cooper | 12-003, 12-061, 12-076, 13-027, 18-006, 19-015, 19-019, 19-020 | 12, 13, 18, 19 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 8A, 8B, 10B |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 16 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent has attempted to contact the Landowner's appointed land agent regularly, most recently on 19 June 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement.
|  |  | 12-004, 18-004, 18-005 | 12, 18 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 16 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed agent has attempted to contact the Landowner's appointed land agent regularly, most recently on 19 June 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement.
305349, 309440, 312902, 318071, 324933, 335608, 335610 | Robert Ian Pratt, The Executor of the Estate of the Late Christine Elizabeth Dobson, The Executor of the Estate of the Late Phyllis Revis, Keith William Revis, Janet Schofield, Louise Dobson, Timothy Dobson | Johnny Cordingley | 05-025 | 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant has received signed Heads of Terms on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing.
289871, 305132, 325051, 353699 | Michael Donald Parkin, Antony Hebden Walter Parkin, The Executor of the Estate of the Late Donald Parkin, The Executor of the Estate of the Late Rosemary Wendy Parkin | Mary Foster | 12-033 | 12 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 2 December 2025 and 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B Signed Heads of Terms were received on 29 January 2026. Legal representatives have been instructed and negotiations of the legals documents are progressing.
324871, 328607, 328608, 330846 | The Executor of the Estate of the Late Gilbert Firth, The Executor of the Estate of the Late Roland Firth, Julie Horner, Tim Gaskell | Michael Townend | 05-012, 05-013, 05-014 | 5 | As described in the Book of Reference | Land is subject to Temporary Possession | 7 |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowners' appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this.
305340, 318156 | Richard Andrew Bramley, The Executor of the Estate of the Late John Richard Bramley | Stephen Burley | 05-007 | 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 19 August 2025 and 10 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B There has been extensive dialogue between the Landowner's appointed land agent and the Applicant. The Landowner's appointed land agent has reported to the Applicant that the Heads of Terms are agreed, however a signed document has, at the time of updating this tracker, not been received. The Applicant will continue to engage with the Landowner's appointed land agent to arrange for signed documents to be provided.
|  |  | 05-010 | 5 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 19 August 2025 and 10 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B There has been extensive dialogue between the Landowner's appointed land agent and the Applicant. The Landowner's appointed land agent has reported to the Applicant that the Heads of Terms are agreed, however a signed document has, at the time of updating this tracker, not been received. The Applicant will continue to engage with the Landowner's appointed land agent to arrange for signed documents to be provided.
322852 | The Executor of the Estate of the Late Reginald Geoffrey Makin | Brian Bartle | 20-001, 20-002, 21-030, 21-036 | 20, 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 8 September 2025 and 1 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant is continuing to engage with the landowners land agent to fully understand the current status of the land ownership. The Applicant will continue to work with the land agent to establish those ownership details, and if any rights are required from the landowner.
322852, 339936 | The Executor of the Estate of the Late Reginald Geoffrey Makin, Stephen Geoffrey Makin | Brian Bartle | 21-029 | 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 8 September 2025 and 1 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant is continuing to engage with the landowners land agent to fully understand the current status of the land ownership. The Applicant will continue to work with the land agent to establish those ownership details, and if any rights are required from the landowner.
305102 | The King's Most Excellent Majesty in Right of His Crown | Ellie Brown | 06-010 | 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent continues to engage with the Interest's appointment agent and has a meeting scheduled for 2 February 2026. The Applicant will continue to engage with the Landowner's appointment agent and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent held a meeting with the Landowner's appointed land agent on 13 February 2026. Further responses were provided to the Landowner's agent on 9 April 2026 and most recently followed up on 26 June 2026. The Applicant will continue to engage with the Landowner's appointment land agent and is confident the necessary land rights can be acquired by voluntary agreement.
213890, 305105 | The Official Custodian For Charities, Hambleton United Charities | Mary Foster | 11-027 | 11 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing.
305108 | The York Diocesan Board of Finance Limited |  | 10-029, 12-059 | 10, 12 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 8A, 8B, 10B |  |  | 2026-07-02 | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 3 February 2026. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowner and most recently corresponded on 2 July 2026. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement.
|  |  | 10-021, 10-030 | 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-02 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the landowner on 3 February 2026. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowner and most recently corresponded on 2 July 2026. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement.
244074, 305258, 305319 | Thomas Swan Thirsk, Julian Richard Thirsk, Patricia Thirsk | Johnny Cordingley | 10-001 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-07-01 | Negotiations for rights The Applicant has received signed Heads of Terms on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing.
|  |  | 09-023 | 9 | As described in the Book of Reference | Land is subject to Temporary Possession | 7, 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant has received signed HoTs on 29th January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing.
244074, 305319 | Thomas Swan Thirsk, Patricia Thirsk | Johnny Cordingley | 09-012, 09-014 | 9 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant has received signed Heads of Terms on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing.
|  |  | 09-008, 09-011 | 9 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing.
162804 | Timothy Brian Hey | Matthew Watson | 12-047 | 12 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant's appointed land agent received verbal confirmation the Heads of Terms are in an agreed format on 29 January 2026 from the Landowner's appointed land agent and is awaiting signed copies of the Heads of Terms. Procedural Deadline B The Applicant received signed Heads of Terms on the 16 March 2026. The Applicant is awaiting confirmation of the Landowner's legal representative from the Landowner. The Applicant's land agent has contacted the Landowner's appointed agent regularly to obtain these details, most recently on the 30 June 2026. |  | Tim Hey - RR-1391
|  |  | 12-045, 12-046 | 12 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant's appointed land agent received verbal confirmation the Heads of Terms are in an agreed format on 29 January 2026 from the Landowner's appointed land agent and is awaiting signed copies of the Heads of Terms Procedural Deadline B The Applicant received signed Heads of Terms on the 16 March 2026. The Applicant is awaiting confirmation of the Landowner's legal representative from the Landowner. The Applicant's land agent has contacted the Landowner's appointed agent regularly to obtain these details, most recently on the 30 June 2026.
304610, 304611, 304612 | Trevor Ernest Millington, Graham Tune Millington, Frank William Millington | Mary Foster | 10-031, 10-036, 10-064, 10-071, 10-081, 10-082, 10-083, 11-022, 16-015, 16-016 | 10, 11, 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A, 8B |  |  | 2026-07-01 | Negotiations for rights The Applicant has received signed Heads of Terms on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing.
|  |  | 10-032, 10-033, 10-035, 10-037, 11-017, 11-021 | 10, 11 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing.
339901 | Wendy Terezia Tomlinson | Chris Tyther / Joe Bonsor | 03-009, 03-010 | 3 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for this land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B The Applicant's land agent continues to have productive dialogue with the Landowner's appointed land agent regarding the Heads of Terms. Land Agent fees remain outstanding and the Applicant's land agent and the Landowner's land agent are working together to resolve this matter. The Applicant will continue to engage with the Landowner and their land agent and is confident that the necessary land rights can be acquired by voluntary agreement. |  | Wendy Tomlinson - RR-1444
305109 | Yorkshire Water Services Limited |  | 03-003, 05-001, 05-033 | 3, 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-07-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 3 February 2026. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent has attempted to contact the Landowner, will continue to engage and is confident the necessary land rights can be acquired by voluntary agreement.

## Part 2 SU Crown
PART 2
Ref | Affected Party | Agent/ Representative | Book of Ref. Plot No. | Plan Ref. No. | Description of Land | Description of Rights Requested | Works Number(s) | Interest Type | Is the relevant body a Statutory Undertaker and is the land operational? | Status of Objection | Notes | Last Updated | Summary of Negotiations | Protective Provision (PPs) Status | Commercial Agreement Status (if required) | Complete | Relevant Rep Ref No. | Written Rep Ref No. | Ref No. for any other docs submitted by IP/AP. | Ref No. for Applicant's Response
119431 | Canal & River Trust |  | 06-010 | 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Rights | Yes |  |  | 2026-07-07 | The Applicant has agreed bespoke PPs with the Canal and River Trust and negotiations are complete. | Bespoke PPs for the benefit of the Canal and River Trust are now agreed and are included in Schedule 15 of the dDCO at Procedural Deadline B | N/A |  | Canal and River Trust - RR-0177
139920 | Centrica PLC |  | 05-046, 05-047, 05-049, 07-026, 10-064, 11-022, 11-025, 11-030 | 5, 7, 10, 11 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A | Rights | Yes |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Gas undertakers will have the benefit of the generic protective provisions for gas undertakers in the draft DCO | N/A
|  |  | 07-027, 11-008, 11-010, 11-021 | 7, 11 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights
7261 | Cornerstone Telecommunications Infrastructure Limited |  | 05-029 | 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Rights | No |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Operators of electronic communications code networks will have the benefit of the protective provisions for electronic communications code operators set out in the draft DCO. | N/A
331938 | EE Limited |  | 10-036 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Rights | No |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Operators of electronic communications code networks will have the benefit of the protective provisions for electronic communications code operators set out in the draft DCO. | N/A
|  |  | 10-037 | 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights
20333 | Environment Agency |  | 06-009, 06-011, 06-012, 06-016 | 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Freehold | Yes |  |  | 2026-07-07 | The Applicant will continue to engage with the Environment Agency and is confident that any necessary land rights can be acquired by voluntary agreement. See Part 1 of this Land Rights Tracker for further details. Procedural Deadline B The Applicant received signed Heads of Terms on 26 June 2026 and will now progress negotiations on the voluntary property agreement with the EA. This does not need to be completed prior to the end of Examination. | Bespoke PPs for the benefit of the Environment Agency are now agreed and are included at Part 4 of Schedule 15 of the dDCO at Procedural Deadline B. The Applicant is therefore seeking confirmation from the EA that they can give their s150 consent. | N/A |  | Environment Agency - RR-0528 and RR-0419
|  |  | 06-004, 06-007, 06-010, 06-015, 06-017, 06-018, 06-019, 06-022, 06-023 | 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Rights | Yes
105595 | Gigaclear Limited |  | 10-039, 10-041, 13-023 | 10, 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A, 8B | Apparatus | No |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Operators of electronic communications code networks will have the benefit of the protective provisions for electronic communications code operators set out in the draft DCO. | N/A
|  |  | 10-018, 10-022, 10-046, 10-047, 10-050, 10-085, 11-001, 13-016, 13-018, 13-024, 13-025, 20-044 | 10, 11, 13, 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 5, 8A, 8B | Apparatus
|  |  | 10-048 | 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights
325427 | HD777FRY Ltd |  | 21-035 | 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Leasehold | Yes |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Electricity undertakers will benefit from the Protective Provisions for electricity undertakers included in the draft DCO | N/A |  | HD777FRY Limited - RR-1380 and RR-0528
|  |  | 20-001, 20-002, 21-030, 21-031, 21-036, 21-040 | 20, 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Rights
|  |  | 21-033, 21-034 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5 | Leasehold
|  |  | 21-032 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5 | Rights
104483 | KCOM Group Limited |  | 10-036, 10-039, 10-041, 10-043, 10-044 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A | Apparatus | No |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Operators of electronic communications code networks will have the benefit of the protective provisions for electronic communications code operators set out in the draft DCO. | N/A
|  |  | 08-039, 10-046, 10-047, 10-048, 10-050 | 8, 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Apparatus
331952 | Kelda Group Limited |  | 05-030, 06-011,13-047 | 5, 6, 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A | Rights | Yes |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Water and sewerage undertakers will have the benefit of the protective provisions set out in the draft DCO | N/A
51929 | Leeds City Council |  | 11-035, 11-036, 12-047 | 11, 12 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A | Rights | Yes |  |  | 2026-02-04 | N/A | As street/highways authority, the Council will have the benefit of having approvals under the relevant DCO articles. No Protective Provisions are proposed at this time | N/A
|  |  | 12-045, 12-046, 13-047 | 12, 13 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights | Yes
198340 | National Gas Transmission PLC |  | 12-034, 12-052, 12-053, 12-055, 12-060, 12-071, 12-072, 18-008, 18-013, 18-014, 18-015 | 12, 18 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 3, 5, 6, 7, 8B, 10B | Rights | Yes |  |  | 2026-07-07 | Discussions are ongoing with National Gas Transmission plc regarding the form of protective provisions. | Draft protective provisions for the benefit of National Gas Transmission plc are included in the draft DCO and are under discussion. |  |  | National Gas Transmission PLC - RR-1036 and RR-1039
|  |  | 05-048, 06-001, 05-049, 06-002, 06-003, 11-036, 15-009, 16-003, 16-004 | 5, 6, 11, 15, 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8B | Apparatus | Yes
|  |  | 05-046, 05-047, 10-064, 10-072, 11-018, 11-022, 11-024, 11-028, 11-030, 11-031, 11-032, 11-033, 11-036, 18-001, 13-008, 13-009, 13-010, 15-005, 15-006, 15-011, 15-004, 15-009, 15-010, 16-003, 16-004, 16-007, 16-008, 16-011, 18-002, 18-011 | 5, 10, 11, 12, 13, 15, 16, 18 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 7, 8A, 8B, 10B | Rights | Yes
|  |  | 11-003, 11-009, 11-010, 11-012, 11-020, 11-021, 11-034, 13-006, 13-011, 15-014 | 11, 13, 15 | As described in the Book of Reference | Land is subject to Temporary Possession | 7, 8A | Rights | Yes
305093 | National Grid Electricity Transmission PLC |  | 12-034, 12-053, 12-054, 12-055, 12-074, 18-013 | 12, 18 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 3, 5, 6, 7, 8B, 10B | Apparatus | Yes |  |  | 2026-07-07 | The Applicant will continue to engage with National Grid Electricity Transmission plc and is confident that any necessary land rights can be acquired by voluntary agreement. See Part 1 of this Land Rights Tracker for further details. | Draft protective provisions for the benefit of National Grid Electricity Transmission plc are included in the draft DCO and are under discussion. |  |  | National Grid Electricity Transmission PLC - RR-1037 and RR-0437
|  |  | 12-034, 12-052, 12-055, 12-060, 12-071, 12-072, 13-021, 13-035, 14-028, 18-013, 18-014, 18-015 | 12, 13, 14, 18 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 2, 3, 5, 6, 7, 8B, 10B | Rights | Yes
|  |  | 18-006, 18-011, 20-001, 21-002, 21-006, 21-008, 21-009, 21-016, 21-017, 21-022, 21-027, 21-031, 21-035, 21-040 | 18, 20, 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 4, 5, 8A, 10B | Apparatus | Yes
|  |  | 21-031, 21-035, 21-040 | 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Freehold | Yes
|  |  | 18-001, 13-020, 13-022, 13-029, 13-030, 18-002, 18-011, 19-011, 19-013, 20-001, 20-002, 21-006, 21-030, 21-036 | 12, 13, 18, 19, 20, 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 8A, 8B, 10B | Rights | Yes
|  |  | 18-003, 18-004, 18-005, 20-005, 20-044, 21-037 | 18, 20, 21 | As described in the Book of Reference | Land is subject to Temporary Possession | 5, 8A | Apparatus | Yes
|  |  | 13-019, 20-045 | 13, 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 5, 8A | Rights | Yes
|  |  | 21-013, 21-019, 21-032, 21-033, 21-034 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5, 8A | Apparatus | Yes
|  |  | 21-013, 21-019, 21-032, 21-033, 21-034 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5, 8A | Freehold | Yes
22908 | National Highways Limited |  | 05-019, 05-021, 05-024, 05-026, 05-028, 05-034, 05-035, 05-037, 10-052, 10-053, 10-054, 10-056, 10-059, 10-060, 10-062 | 5, 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A | Freehold | Yes |  |  | 2026-07-07 | The Applicant is in discussions with National Highways over the technical aspects of the crossing of the strategic road network. The Applicant will continue to engage with National Highways and is confident that any necessary land rights can be acquired by voluntary agreement . See Part 1 of this Land Rights Tracker for further details. | Draft protective provisions for the benefit of National Highways Limited are included in the draft DCO and are under discussion. |  |  | National Highways - RR-0177 and RR-1038
|  |  | 10-063, 10-064, 10-065, 10-067, 10-071, 10-083, 20-014, 20-020, 20-025 | 10, 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A | Rights | Yes
|  |  | 05-036, 05-038, 05-039, 05-041, 10-045, 10-047, 10-050, 10-051, 10-069 | 5, 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Freehold | Yes
|  |  | 11-017, 20-017, 20-019, 20-040, 20-041 | 11, 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights | Yes
309564 | Netomnia Limited |  | 10-043 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A | Apparatus | No |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Operators of electronic communications code networks will have the benefit of the protective provisions for electronic communications code operators set out in the draft DCO.
|  |  | 10-018, 10-021, 10-022, 11-001 | 10, 11 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Apparatus
7310 | Network Rail Infrastructure Limited |  | 14-002, 14-003, 14-004 | 14 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 6, 10B | Apparatus | Yes |  |  | 2026-07-07 | The Applicant is in discussions with Network Rail over the technical aspects of the crossing of the railway. The Applicant will continue to engage with Network Rail and is confident that any necessary land rights can be acquired by voluntary agreement . See Part 1 of this Land Rights Tracker for further details. | Draft protective provisions for the benefit of Network Rail Infrastructure Limited are included in the draft DCO and are under discussion. |  |  | Network Rail Infrastructure Limited - RR-1298 and RR-1045
|  |  | 14-001, 14-002, 14-003, 14-004, 14-017, 15-002 | 14, 15 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 6, 7, 8B, 10B | Rights | Yes
|  |  | 10-016, 10-023, 10-025, 10-063, 10-070, 10-072, 10-076, 10-078, 15-003, 15-007, 20-013 | 10, 15, 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A, 8B | Apparatus | Yes
|  |  | 16-001, 10-073, 10-074 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B | Freehold | Yes
|  |  | 10-052, 10-053, 10-071, 10-083, 11-024, 11-028, 11-032, 14-014, 15-004, 15-005, 16-003, 16-019, 17-006, 17-010, 17-012 | 10, 11, 14, 15, 16, 17 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 8A, 8B | Rights | Yes
|  |  | 10-015, 10-016, 10-017; 10-025, 10-052, 10-053, 10-070, 14-014, 15-003, 16-019, 20-013 | 10, 14, 15, 16, 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 8A, 8B | Unregistered Freeholder | Yes
|  |  | 10-032, 10-033, 10-034 | 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Apparatus | Yes
|  |  | 11-009, 11-012, 11-017, 17-008 | 10, 11, 17 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A, 8B | Rights | Yes
249688 | North Yorkshire Council |  | 01-030, 13-021, 13-035 | 1, 13 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 2, 3, 5, 6, 7, 9A | Rights | Yes |  |  | 2026-02-04 | N/A | As street/highways authority, the Council will have the benefit of having approvals under the relevant DCO articles. No Protective Provisions are proposed at this time |  |  | North Yorkshire Council - RR-1075
|  |  | 05-027, 05-028, 05-029, 10-059, 10-083 | 5, 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A | Apparatus | Yes
|  |  | 05-002, 05-003, 05-005, 05-006, 05-018, 05-020, 05-025, 05-029, 06-010, 08-037, 09-001, 09-002, 09-003, 09-004, 10-031, 13-020, 13-022, 13-029, 13-030 | 5, 6, 8, 9, 10, 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 8A, 8B | Rights | Yes
|  |  | 03-061, 04-004, 05-038, 05-040, 05-041, 07-002, 07-003, 10-022, 10-046, 10-069, 11-001 | 3, 5, 7, 10, 11 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Apparatus | Yes
|  |  | 03-053, 08-038, 22-004 | 3, 8, 22 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Freehold | Yes
|  |  | 09-006, 09-009, 10-012, 10-047, 10-050, 13-019 | 9, 10, 13 | As described in the Book of Reference | Land is subject to Temporary Possession | 5, 8A | Rights | Yes
7317 | Northern Gas Networks Limited |  | 12-034, 12-053, 12-054, 12-055, 18-008, 18-013 | 12, 18 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 5, 6, 7, 8B, 10B | Apparatus | Yes |  |  | 2026-07-07 | The Applicant is in discussions with Northern Gas Networks Limited | Draft protective provisions for the benefit of Northern Gas Network Ltd are included in the draft DCO and are under discussion.
|  |  | 12-034, 12-052, 12-053, 12-055, 12-060, 12-071, 12-072, 18-008, 18-013, 18-014, 18-015 | 12, 18 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 3, 5, 6, 7, 8B, 10B | Rights | Yes
|  |  | 05-027, 05-028, 11-022, 18-011 | 5, 11, 18 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 8A, 10B | Apparatus | Yes
|  |  | 18-001, 18-002, 18-011 | 12, 18 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 8B, 10B | Rights | Yes
|  |  | 05-036, 05-038, 05-039, 05-040, 05-041, 08-039, 10-009, 11-001, 11-010, 11-011, 11-012, 20-010 | 5, 8, 10, 11, 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Apparatus | Yes
183942 | Northern Powergrid (Yorkshire) PLC |  | 01-012, 01-014, 01-017, 01-019, 01-021, 01-027, 01-033, 01-034, 02-005, 12-034, 12-035, 12-054, 12-060, 12-074, 13-021, 13-035, 13-050, 14-017, 14-018, 14-028, 15-002, 18-008, 18-020 | 1, 12, 13, 14, 15, 18 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 2, 3, 5, 6, 7, 8B, 9A, 9B, 10A, 10B | Apparatus | Yes |  |  | 2026-07-07 | The Applicant is in discussions with Northern Powergrid (Yorkshire) PLC over the technical aspects of the crossing of the strategic road network. The Applicant will continue to engage with Northern Powergrid (Yorkshire) PLC and is confident that any necessary land rights can be acquired by voluntary agreement . See Part 1 of this Land Rights Tracker for further details. | Draft protective provisions for the benefit of Northern Powergrid (Yorkshire) PLC are included in the dDCO at Schedule 15 and are under discussion. |  |  | Northern Powergrid (Yorkshire) PLC and (North East) PLC - RR-1037 Weightmans LLP on behalf of Northern Powergrid (Yorkshire) PLC and (North East) PLC - RR-1440
|  |  | 01-004, 01-014, 01-016, 01-017, 01-018, 01-019, 01-020, 01-021, 01-023, 01-025, 01-027, 01-029, 01-030, 01-033, 12-053 | 1, 12 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 6, 7, 9A, 10A, 10B | Rights | Yes
|  |  | 01-010, 01-015, 01-022, 01-031, 01-032, 02-003, 03-011, 03-019, 03-020, 03-023, 03-026, 03-027, 05-022, 05-023, 05-024, 05-025, 05-026, 05-027, 05-028, 05-029, 05-032, 05-033 05-044, 06-033, 08-028, 08-035, 09-012, 09-016, 10-003, 10-064, 10-070, 10-071, 10-072, 10-075, 10-077, 10-081, 11-026, 11-027, 11-037, 12-001, 12-002, 12-003, 12-033, 18-001, 13-009, 13-010, 13-014, 13-015, 13-029, 13-030, 13-032, 14-019, 16-002, 15-004, 15-005, 15-009, 15-010, 15-011, 16-003, 16-004, 16-005, 16-006, 16-007, 16-008, 16-015, 16-016, 16-019, 17-009, 17-010, 17-012, 18-011, 18-016, 18-017, 19-017, 20-015, 20-020, 20-021, 21-002, 21-004, 21-008, 21-009, 21-023, 21-024, 21-025, 21-027 | 1, 3, 5, 6, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 4, 5, 6, 7, 8A, 8B, 10B | Apparatus | Yes
|  |  | 01-003, 01-005, 01-006 01-015, 01-022, 01-024, 01-026, 01-028, 01-031, 21-009, 21-015, 21-016, 21-017, 21-018, 21-021, 21-024, 21-025, 21-026, 21-035 | 1, 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 4, 5, 6, 8B, 10A | Rights | Yes
|  |  | 02-004, 03-008, 03-013, 03-014, 03-030, 03-031, 03-032, 03-035, 03-038, 03-039, 03-040, 04-001, 03-042, 03-044, 03-045, 03-047, 03-061, 04-002, 04-004, 05-040, 05-041, 06-030, 06-032, 07-001, 07-002, 07-003, 07-004, 07-005, 07-008, 07-009, 07-011, 08-001, 08-002, 08-010, 08-012, 08-019, 08-020, 08-021, 08-022, 08-031, 08-033, 08-036, 10-004, 10-005, 10-018, 10-021, 10-022, 10-033, 10-035, 10-037, 10-038, 10-040, 11-001, 11-004, 11-007, 11-008, 11-009, 11-013, 12-036, 12-037, 13-018, 13-019, 13-024, 14-012, 18-018, 18-019, 18-021, 19-001, 20-016, 20-018, 20-044 | 2, 3, 4, 5, 6, 7, 8, 10, 11, 12, 13, 14, 18, 19, 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 5, 7, 8A, 8B, 10B | Apparatus | Yes
|  |  | 03-037 | 3, 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights | Yes
|  |  | 21-013, 21-032 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5, 8A | Apparatus | Yes
|  |  | 21-034 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5 | Rights | Yes
356665 | Noventum Power Limited |  | 12-075, 19-005, 19-011, 19-012 | 12, 19 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Beneficiary | Yes |  |  | 2026-02-04 | Technical discussions have taken place and will continue | Bespoke PPs not required. Electricity undertakers will benefit from the Protective Provisions for electricity undertakers included in the draft DCO
266588 | OCU Group Ltd |  | 14-002, 14-028, 15-002 | 14, 15 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 6, 7, 8B, 10B | Apparatus | No |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Operators of electronic communications code networks will have the benefit of the protective provisions for electronic communications code operators set out in the draft DCO.
|  |  | 10-015, 10-023, 10-024, 10-071, 10-075, 10-076, 10-077, 14-014, 15-004, 15-007, 15-011, 17-009, 17-010, 17-012, 20-012 | 10, 14, 15, 17, 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 8A, 8B | Apparatus
156528 | Openreach Limited |  | 01-009, 12-054, 12-060, 12-074, 13-021, 14-002, 14-005, 14-009, 14-010, 18-013, 18-020 | 1, 12, 13, 14, 18 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 2, 3, 5, 6, 7, 8B, 10A, 10B | Apparatus | No |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Operators of electronic communications code networks will have the benefit of the protective provisions for electronic communications code operators set out in the draft DCO.
|  |  | 01-003, 01-011, 01-032, 02-009, 03-015, 03-026, 03-027, 03-028, 03-029, 03-046, 03-059, 05-007, 05-008, 05-009, 05-027, 05-028, 05-031, 05-032, 05-037, 06-020, 06-021, 06-023, 06-025, 08-029, 09-002, 09-004, 09-013, 09-014, 09-016, 10-008, 10-036, 10-039, 10-041, 10-043, 10-044, 10-075, 10-078, 10-079, 10-083, 11-029, 12-001, 12-002, 12-026, 12-033, 12-041, 12-043, 12-059, 12-062, 12-063, 12-065, 13-001, 13-002, 13-005, 13-023, 13-028, 13-030, 13-033, 13-044, 14-006, 14-011, 14-013, 14-025, 14-026, 17-004, 17-009, 18-016, 18-017, 20-006, 20-012, 20-014, 20-015, 21-001, 21-002, 21-003, 21-005, 21-006, 21-008, 21-009, 21-010, 21-012, 21-020, 21-021, 21-023, 21-024, 21-027, 21-028, 21-029, 21-030, 21-031, 21-035, 21-040 | 1, 2, 5, 6, 8, 9, 10, 11, 12, 13, 14, 17, 18, 20, 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 4, 5, 6, 8A, 8B, 10A, 10B | Apparatus
|  |  | 01-001, 01-007, 02-001, 02-004, 02-007, 02-010, 03-013, 03-016, 03-030, 03-031, 03-032, 03-038, 03-039, 03-040, 03-042, 03-043, 03-047, 03-053, 03-054, 03-055, 03-060, 03-061, 04-002, 04-003, 04-004, 05-011, 05-036, 05-038, 05-039, 05-040, 05-041, 07-001, 07-002, 07-003, 07-004, 07-005, 07-006, 07-007, 07-008, 07-009, 07-010, 07-011, 08-001, 08-010, 08-012, 08-023, 08-031, 08-033, 08-038, 08-039, 10-005, 10-009, 10-010, 10-012, 10-018, 10-022, 10-034, 10-037, 10-038, 10-040, 10-046, 10-047, 10-050, 10-083, 10-085, 11-001, 11-011, 11-013, 12-007, 12-008, 12-010, 12-029, 12-037, 12-039, 12-040, 12-042, 15-001, 13-007, 13-016, 13-018, 13-024, 13-025, 13-032, 13-043, 13-045, 14-007, 14-008, 14-012, 15-012, 17-001, 17-002, 17-003, 17-007, 18-003, 18-004, 18-007, 18-018, 18-019, 18-021, 20-009, 20-010, 20-016, 20-018, 20-038, 20-044, 20-045, 22-001, 22-002, 22-003, 22-004 | 1, 2, 3, 4, 5, 7, 8, 10, 11, 12, 13, 14, 15, 17, 18, 20, 22 | As described in the Book of Reference | Land is subject to Temporary Possession | 1(d), 5, 6, 8A, 8B, 10A, 10B | Apparatus
|  |  | 10-048 | 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights
|  |  | 21-013, 21-032, 21-033 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5, 8A | Apparatus
333641 | Ouse & Derwent Internal Drainage Board |  | 01-009, 01-012, 01-030, 01-033, 01-034, 02-006, 02-005 | 1 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 3, 5, 6, 7, 9A, 9B, 10A | Rights | Yes |  |  | 2026-07-07 | Negotiations complete | Agreed protective provisions for the benefit of Ouse & Derwent Internal Drainage Board (and the other relevant drainage authorities) are included in the draft DCO. |  |  | Ouse & Derwent Internal Drainage Board - RR-1083 and RR-1440
|  |  | 01-010, 01-011, 01-031, 02-003, 02-002, 02-011, 03-001, 03-002, 03-004, 03-005, 03-017, 03-019, 03-021, 03-025, 03-027, 03-049, 03-062, 05-002, 05-003, 05-004, 05-006, 05-007, 05-026, 05-028, 05-029, 05-030, 05-044, 05-045, 05-046, 05-047, 05-048, 06-001, 05-049, 06-002, 06-004, 06-005, 06-006, 06-008, 06-010 | 1, 2, 3, 5, 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 8A, 8B, 10A | Rights | Yes
|  |  | 02-008, 05-010, 05-041 | 2, 5 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights | Yes
331961 | Prowind Hambleton Windfarm GmbH & Co. KG |  | 16-004 | 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B | Rights | Yes |  |  | 2026-02-04 | The Applicant received the following response within a Land Interest Questionnaire from the Interest: 'We would like to inform you that the projects in question have been suspended and no longer belong to us. Therefore, there is nothing on our part that would prevent earthworks from being carried out on the land in question'. | No Protective Provisions required given LIQ response
|  |  | 09-021, 09-022 | 9 | As described in the Book of Reference | Land is subject to Temporary Possession | 7, 8A | Rights | Yes
355902 | Quickline Communications Limited |  | 03-032, 03-038, 03-039, 03-041, 04-002 | 3, 4 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Apparatus | No |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Operators of electronic communications code networks will have the benefit of the protective provisions for electronic communications code operators set out in the draft DCO.
187230 | Secretary Of State For Defence |  | 09-021, 09-022 | 9 | As described in the Book of Reference | Land is subject to Temporary Possession | 7, 8A | Rights | No |  |  | 2026-02-04 | The Applicant will be seeking s135 consent from this party. | N/A
305096 | Secretary of State for Transport |  | 03-003, 10-063, 10-065, 10-067, 10-068 | 3, 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Rights | No |  |  | 2026-02-04 | The Applicant will be seeking s135 consent from this party. | N/A
|  |  | 10-048 | 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights | No |  |  | 2026-02-04
331972 | Selby Area Internal Drainage Board |  | 12-034, 12-050, 12-051, 12-052, 12-053, 12-055, 12-056, 12-071, 12-072, 13-021, 13-049, 13-050, 13-051, 14-001, 14-002, 14-004, 14-005, 14-017, 14-018, 14-021, 14-021, 14-022, 14-028, 15-002, 18-009, 18-012, 18-013, 18-014, 18-015, 19-003 | 12, 13, 14, 15, 18, 19 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 2, 3, 5, 6, 7, 8B, 10B | Rights | Yes |  |  | 2026-07-07 | Negotiations complete | Agreed protective provisions for the benefit of Selby Area Internal Drainage Board (and the other relevant drainage authorities) are included in the draft DCO at Procedural Deadline B.
|  |  | 06-011, 06-012, 06-013, 06-014, 06-015, 06-016, 06-017, 06-018, 06-019, 06-020, 06-024, 06-028, 06-039, 06-033, 06-037, 06-038, 06-041, 06-042, 06-043, 06-044, 06-045, 07-019, 07-020, 08-027, 08-028, 08-037, 09-001, 09-002, 09-005, 09-012, 09-013, 09-014, 09-015, 09-016, 09-018, 10-001, 10-003, 10-007, 10-008, 10-015, 10-016, 10-017, 10-023, 10-028, 10-031, 10-044, 10-055, 10-059, 10-060, 10-061, 10-062, 10-063, 10-065, 10-066, 10-070, 10-071, 10-072, 10-082, 11-015, 11-018, 11-022, 11-023, 11-025, 11-026, 11-030, 11-031, 11-033, 11-036, 12-001, 12-002, 12-003, 18-001, 12-047, 12-048, 12-049, 12-076, 13-009, 13-010, 13-014, 13-015, 13-017, 13-020, 13-022, 13-027, 13-029, 13-030, 13-036, 13-037, 13-038, 13-040, 13-046, 13-048, 14-006, 14-014, 14-015, 14-020, 14-024, 14-029, 16-002, 15-004, 15-005, 15-006, 15-009, 15-010, 15-011, 16-003, 16-004, 16-005, 16-006, 16-007, 16-008, 16-011, 16-015, 16-016, 17-011, 17-012, 18-002, 18-006, 18-010, 18-011, 19-002, 19-004, 19-005, 19-006, 19-013, 19-017, 19-018, 19-019, 19-020, 20-021, 20-024, 20-026, 20-031, 20-032 | 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 7, 8A, 8B, 10B | Rights | Yes
|  |  | 06-027, 06-030, 06-031, 06-032, 06-034, 06-035, 06-036, 06-039, 07-008, 07-009, 07-011, 07-012, 07-013, 08-001, 08-002, 08-003, 08-004, 08-005, 08-006, 08-007, 08-009, 08-010, 08-011, 08-012, 08-013, 08-020, 08-021, 08-022, 08-024, 08-030, 08-032, 08-038, 08-039, 09-007, 09-008, 09-010, 09-011, 09-017, 09-019, 09-020, 09-021, 09-022, 09-023, 10-002, 10-004, 10-012, 10-018, 10-019, 10-020, 10-032, 10-033, 10-034, 10-045, 10-046, 11-010, 11-016, 11-019, 11-020, 11-021, 11-034, 12-004, 12-045, 12-046, 13-011, 13-016, 13-018, 13-019, 14-007, 18-004, 18-005, 18-021, 19-001, 19-016, 20-029, 20-033, 20-034, 20-038, 20-039, 20-040, 20-041 | 6, 7, 8, 9, 10, 11, 12, 13, 14, 18, 19, 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 5, 7, 8A, 8B, 10B | Rights | Yes
53952 | Sheffield City Council |  | 01-034, 02-006, 02-005 | 1 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 5, 6, 9A, 9B | Rights | Yes |  |  | 2025-02-04 | The Applicant is undertaking further due diligence as it is believed the listed rights are historic. If it transpires that the rights are not historic the Applicant will seek appropriate Protective Provisions. | As street/highways authority, the Council will have the benefit of having approvals under the relevant DCO articles. No Protective Provisions are proposed at this time
|  |  | 02-003, 05-001, 05-002, 05-003, 05-005, 05-006, 06-010 | 1, 5, 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6 | Rights | Yes
|  |  | 08-005, 08-006, 08-009, 08-021, 08-022, 08-024 | 8 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights | Yes
331977 | SSE Battery Monk Fryston Limited |  | 20-003, 20-004, 20-007, 20-008, 20-011, 20-012 | 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A | Beneficiary | Yes |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Electricity undertakers will benefit from the Protective Provisions for electricity undertakers included in the draft DCO |  |  | SSE Hydrogen Developments Ltd - RR-1036 and RR-1298
|  |  | 20-005 | 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Beneficiary | Yes
55087 | Telefonica UK Limited |  | 05-029 | 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Rights | No |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Operators of electronic communications code networks will have the benefit of the protective provisions for electronic communications code operators set out in the draft DCO.
305102 | The King's Most Excellent Majesty in Right of His Crown |  | 06-010 | 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Freehold | No |  |  | 2026-02-04 | The Applicant will be seeking s135 consent from this party.
20098 | Vodafone Limited |  | 16-004, 17-009, 17-010, 17-011, 17-012 | 16, 17 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B | Rights | No |  |  | 2026-02-04 | Discussions have taken place with Vodafone Limited to confirm that bespoke PPs are not required. | Bespoke PPs not required. Operators of electronic communications code networks will have the benefit of the protective provisions for electronic communications code operators set out in the draft DCO.
|  |  | 21-032 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5 | Apparatus
55035 | Yorkshire Electricity Group PLC |  | 14-028 | 14 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 6 | Rights | Yes |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Electricity undertakers will benefit from the Protective Provisions for electricity undertakers included in the draft DCO
|  |  | 21-031, 21-035, 21-040 | 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Rights | Yes
|  |  | 21-032, 21-033, 21-034 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5 | Rights | Yes
305109 | Yorkshire Water Services Limited |  | 01-008, 01-009, 01-012, 01-030, 01-034, 02-005, 12-034, 13-021, 13-035 | 1, 12, 13 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 2, 3, 5,6, 7, 8B, 9A, 9B, 10A, 10B | Apparatus | Yes |  |  | 2026-07-07 | Discussions are ongoing with Yorkshire Water Services Limited regarding the form of protective provisions. | The water and sewerage undertaker protective provisions in the DCO will protect Yorkshire Water and have been adjusted to give additional protection specifically for them. This is under discussion with Yorkshire Water.
|  |  | 01-004, 01-009, 01-012, 01-019, 01-023, 01-030, 01-033, 13-021 | 1, 13 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 2, 3, 5, 7, 9A, 10A | Rights | Yes
|  |  | 01-011, 02-003, 02-002, 02-011, 03-002, 03-004, 03-017, 03-019, 05-007, 05-008, 05-009, 05-016, 05-027, 05-028, 05-029, 05-030, 05-043, 05-047, 06-023, 06-025, 06-039, 06-033, 08-029, 09-002, 09-005, 09-013, 09-018, 10-026, 10-031, 11-015, 11-018, 11-022, 11-029, 12-026, 18-001, 12-065, 12-067, 13-002, 13-005, 13-009, 13-010, 13-014, 13-015, 13-030, 13-032, 13-033, 13-038, 13-041, 13-048, 16-004, 17-009, 17-010, 17-012, 18-002, 19-018, 20-001, 20-002, 20-015, 20-026, 21-001, 21-002, 21-008, 21-010, 21-012, 21-015, 21-016, 21-017, 21-018, 21-022, 21-023, 21-024, 21-025, 21-026, 21-027, 21-028, 21-035, 21-040 | 1, 2, 3, 5, 6, 8, 9, 10, 11, 12, 13, 16, 17, 18, 19, 20, 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 4, 5, 6, 7, 8A, 8B, 10A, 10B | Apparatus | Yes
|  |  | 03-003, 05-001, 05-033 | 3, 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A | Freehold | Yes
|  |  | 01-003, 01-005, 01-006, 01-010, 01-011, 01-031, 02-002, 05-025, 05-029, 05-031, 05-043, 06-009, 06-015, 06-016, 06-017, 06-018, 06-019, 06-022, 06-023, 06-038, 06-042, 06-043, 06-044, 06-045, 11-022, 11-025, 11-027, 11-030, 11-031, 11-035, 13-009, 13-010, 13-041, 13-048, 19-018, 20-026, 20-031, 20-032 | 1, 2, 5, 6, 11, 13, 19, 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 8A , 8B, 10A, 10B | Rights | Yes
|  |  | 07-007, 01-007, 02-001, 02-004, 02-007, 02-008, 03-012, 03-014, 03-015, 03-016, 03-029, 03-030, 03-031, 03-032, 03-033, 03-038, 03-039, 03-042, 03-053, 03-054, 03-055, 03-056, 03-060, 03-061, 04-002, 04-003, 04-004, 04-005, 05-011, 05-032, 05-033, 05-034, 05-035, 05-036, 05-037, 05-038, 05-039, 05-040, 05-041, 05-042, 06-026, 06-027, 06-030, 07-001, 07-002, 07-003, 07-004, 07-005, 07-006, 07-008, 07-009, 08-001, 08-004, 08-005, 08-006, 08-007, 08-008, 08-009, 08-010, 08-012, 08-019, 08-020, 08-021, 08-023, 08-031, 08-033, 08-038, 08-039, 09-007, 09-010, 09-017, 09-019, 09-020, 10-002, 10-005, 10-009, 10-018, 10-022, 10-027, 10-077, 10-078, 10-079, 10-081, 11-001, 11-010, 11-011, 11-012, 11-013, 11-016, 11-019, 11-020, 11-021, 12-008, 12-009, 12-010, 12-029, 12-064, 13-007, 13-011, 13-012, 13-046, 15-012, 17-001, 17-002, 17-003, 17-007, 18-003, 18-007, 18-018, 18-019, 19-016, 20-016, 20-018, 20-037, 20-038, 20-039, 20-044, 21-037, 21-038, 21-039, 22-001, 22-003, 22-004 | 7, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 15, 17, 18, 19, 20, 21, 22 | As described in the Book of Reference | Land is subject to Temporary Possession | 1(d), 5, 6, 7, 8A, 8B, 10A | Apparatus | Yes
|  |  | 03-028, 05-032, 05-034, 05-035, 05-042, 06-035, 06-036, 06-039, 07-009, 08-002, 08-003, 08-004, 08-007, 11-008, 11-010, 11-012, 13-011, 13-042, 20-029, 20-033, 20-034 | 11, 3, 5, 6, 7, 8, 11, 13, 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights | Yes
|  |  | 21-013, 21-019, 21-032 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5, 8A | Apparatus | Yes