## Part 1 LO
PART 1
Ref | Landowner/ Affected Party | Agent/ Representative | Book of Ref. Plot No. | Plan Ref. No. | Description of Land | Description of Rights Requested | Works Number(s) | Status of Objection | Notes | Last Updated | Summary of Negotiations | Status of Negotiations | Relevant Rep Ref No. | Written Rep Ref No. | Ref No. for any other docs submitted by IP/AP. | Ref No. for Applicant's Response
304655 | Alan Leslie Pearse | Brian Bartle | 10-003, 16-008, 16-011 | 10, 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8B |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 8 September 2025 and 1 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent met with the Landowner's appointed land agent on 22 May 2026 to discuss and progress the Heads of Terms. It was made clear to the Applicant's land agent in that meeting that the Landowner was unwilling to enter into negotiations. Notwithstanding the position reported by the Landowners appointed land agent, the Applicant will continue to engage with them with the intention to progress the Heads of Terms. Deadline 2 The Applicant's appointed land agent met with the Landowner's appointed land agent on 27 July 2026 to discuss and progress the Heads of Terms. There were several actions resulting from the meeting, and progress has been made. The Applicant has will be reissuing updated Heads of Terms in due course so that the Landowners land agent can report to their client. Deadline 3 The Applicant reissued Heads of Terms to the Landowners land agent on 2 September 2026. The Applicant called the Landowners land agent for an update on 15 September 2026, 18 September 2026, and 21 September 2026. The Applicant also followed up with emails on 9 September 2026, and 24 September 2026. As of this Land and Rights Negotiation Tracker update, the Applicant has not received any update from the Landowners land agent in relation to his clients Heads of Terms. The Applicant will continue to engage with the Landowners land agent so as to move Heads of Terms forward. |  | Alan Pearse - RR-0014
|  |  | 08-005, 08-006, 08-009, 08-021, 08-022, 08-024, 10-004, 10-012 | 8, 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 8 September 2025 and 1 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent met with the Landowner's appointed land agent on 22 May 2026 to discuss and progress the Heads of Terms. It was made clear to the Applicant's land agent in that meeting that the Landowner was unwilling to enter into negotiations. Notwithstanding the position reported by the Landowners appointed land agent, the Applicant will continue to engage with them with the intention to progress the Heads of Terms. Deadline 2 The Applicant's appointed land agent met with the Landowner's appointed land agent on 27 July 2026 to discuss and progress the Heads of Terms. There were several actions resulting from the meeting, and progress has been made. The Applicant has will be reissuing updated Heads of Terms in due course so that the Landowners land agent can report to their client. Deadline 3 The Applicant reissued Heads of Terms to the Landowners land agent on 2 September 2026. The Applicant called the Landowners land agent for an update on 15 September 2026, 18 September 2026, and 21 September 2026. The Applicant also followed up with emails on 9 September 2026, and 24 September 2026. As of this Land and Rights Negotiation Tracker update, the Applicant has not received any update from the Landowners land agent in relation to his clients Heads of Terms. The Applicant will continue to engage with the Landowners land agent so as to move Heads of Terms forward.
305115, 305144, 305340, 318156 | Alison Joan Bramley, Brigita Fionait Bramley, Richard Andrew Bramley, The Executor of the Estate of the Late John Richard Bramley | Stephen Burley | 05-003, 05-006 | 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 19 August 2025 and 10 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B There has been extensive dialogue between the Landowner's appointed land agent and the Applicant. The Landowner's appointed land agent has reported to the Applicant that the Heads of Terms are agreed, however a signed document has, at the time of updating this tracker, not been received. The Applicant will continue to engage with the Landowner's appointed land agent to arrange for signed documents to be provided. Deadline 2 The Applicant's appointed land agent met with the Landowner's land agent on 27 July 2026. The Purpose of the meeting was to update on the status of the Heads of Terms. As far as the Applicant is aware, there are no outstanding matters and awaits an update from the Landowner's land agent to update on whether the Heads of Terms are in a position to be signed. Deadline 3 Further to the Applicant's appointed land agent's meeting with the Landowner's appointed land agent, the Applicant's land agent followed up on 25 August 2026, and on 9 September 2026 via email. The Applicant's land agent followed up via telephone call on 15 September 2026, where the Landowner's land agent requested that the Applicant contact his client directly. The Applicant's land agent spoke to the Landowner on 28 September 2026 to discuss the Heads of Terms, and to offer a meeting in person. The Landowner expressed their frustration at the scheme, and suggested that he and the Applicant's land agent speak in a months' time. The Applicant's land agent followed up with the landowners land agent on 28 September 2026 in a bid to move Heads of Terms negotiations forward.
331926, 389455 | Andrew David McCloy, DSJM Property Ltd | Mary Foster | 21-037, 21-038, 21-039 | 21 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant consulted with the Landowners as part of the pre-application consultation processes. The Applicant is commencing negotiations with these Landowners following confirmation of the nature of the requirements and rights sought for this land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B Heads of Terms were issued on 16 March 2026. The Applicant's appointed land agent has engaged with the Landowner's appointed land agent and most recently held a meeting on 15 June 2026. The route proposed remains the outstanding issue and the Applicants is reviewing this and remains confident a voluntary agreement can be acquired. Deadline 2 The Applicant's appointed land agent responded to the outstanding point of difference of 9 July 2026 and is awaiting a response from the Landowners' appointed land agent. This was followed up most recently on 20 August 2026. The Applicant remains confident a voluntary agreement can be agreed. Deadline 3 The Applicant's appointed land agent continues to engage with the Landowner's appointed land agent, most recently on 29 September 2026. The Applicant's appointed land agent has provided the requested information to the Landowner's appointed agent and is awaiting a response. The Applicant remains confident a voluntary agreement can be reached.
322665 | Andrew James Cawood | Johnny Cordingley | 13-051, 14-001, 14-002, 14-003, 14-004, 14-017, 14-022, 15-002 | 13, 14, 15 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 5, 6, 7, 8B, 10B |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
|  |  | 16-002 | 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
311856, 339988 | Andrew William Headley, Richard Mark Headley |  | 03-007 | 3 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for rights The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for this land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B A populated licence agreement was issued to the Landowners on 3 June 2026. The Applicant's appointed land agent held a meeting with the Landowners' appointed land agent on 15 June 2026 to progress negotiations. The Applicant will continue to engage with the Landowners and their land agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to engage regularly with the Landowner's appointed agent in respect of the licence agreement. The Applicant is awaiting on comments from the Landowner's appointed agent as to the outstanding matters of difference and most recently followed this up on 20 August 2026. Deadline 3 The Applicant's appointed land agent requested an update from the Landowner's appointed land agent via telephone and email, most recently on 29 September 2026. As of this Land and Rights Negotiation Tracker update, the Applicant has not received any update from the Landowner's land agent in relation to the Licence Agreement. The Applicant will continue to engage with the Landowners land agent so as to move the agreement forward.
305122, 305310 | Angela Fiona Smith, Neil James Cawthorne | Johnny Cordingley | 11-037, 11-038 | 11 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-09-29 | Negotiations for rights The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legal documents are progressing. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
304644 | Anne Colette Harrison | Mary Foster | 11-025, 11-035 | 11 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives Procedural Deadline B Legal representatives have been instructed and negotiations of the legal documents are progressing. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
|  |  | 11-008 | 11 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
304608, 304609 | Anne Vincent, George Edward Vincent | Chris Thyer / Joe Bonsor | 13-036, 13-040 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-10-05 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 24 November 2025, 27 and 28 January 2026 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent has engaged regularly with the Applicant's appointed land agent. The principle issue with the Heads of Terms Document is regarding land agents fees, for which the Applicant's land agent and the Landowners land agent are working together to resolve this matter. The Applicant will continue to engage with the Landowners and their agent and is confident that the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant has corresponded with the Landowner and their appointed land agent and has offered a meeting to progress the voluntary agreement. Following correspondence from the Landowners' appointed land agent, the Applicant understands the Landowner' appointed agent is in dialogue with the Landowner and will revert to the Applicant shortly with a response on the voluntary agreement. The Applicant will continue to engage with the Landowners and their appointed agent and is confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant continues to try to engage the Landowner's land agent, most recently via email on 5 October 2026. As of this Land and Rights Negotiation Tracker update, the Applicant has not received any update from the Landowner's land agent in relation to his clients Heads of Terms. The Applicant will continue to engage with the Landowners land agent so as to move Heads of Terms forward. |  | George Edward Vincent - RR-0474 | George Edward Vincent - REP1-036
305134, 305304, 305335 | Barbara Wilson, Michael Edwin Wilson, Rachel Elizabeth Wilson | Michael Townend | 10-007, 10-008, 10-013, 10-014, 10-023 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. Deadline 2 The Applicant and the Applicant's appointed agent met with the Landowner's appointed land agent on 7 August 2026 to discuss the remaining outstanding items within the Heads of Terms. The parties agreed the final amendments required to the Heads of Terms and revised Heads of Terms are due to be issued to the Landowner shortly. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowners and their appointed land agent to achieve this. Deadline 3 The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 25 September 2026 following engagement with the Landowner's appointed land agent. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this. |  | Rachael Wilson - RR-1137
305138, 305175 | Brian Anthony Richardson, Elaine Caroline Richardson | Ben Wills | 12-075, 19-005, 19-006, 19-010, 19-011, 19-012 | 12, 19 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on the 12 January 2026 to progress landowner specific aspects of the HoTs. The Applicant is aware Hillam Solar Limited have a beneficiary interest in the land by way of an option agreement and is working with the Landowners, their appointed land agent and Hillam Solar Limited to obtain the necessary consents. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 5 May 2026. The principal surrounding route optionality was agreed in relation to the Hillam Solar Limited development. Revised Heads or Terms reflecting this are due to be re-issued to the Landowners' appointed land agent shortly. The Applicant will continue to engage with the Landowners and their land agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant held a further meeting with Hillam Solar Limited on 14 August 2026. The Applicant continues to correspond with the Landowner' appointed agent, most recently on 14 August 2026. The Applicant understands that the Landowner' appointed land agent and Hillam Solar Limited are meeting w/c 17 August 2026 following which the Landowner' appointed land agent will revert to the Applicant with a response on the voluntary agreement. The Applicant will continue to engage with the Landowners and their appointed land agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant held a further meeting with Hillam Solar Limited on 9 September 2026. The Applicant has correspondence with the Landowner's appointed agent regularly since the previous update. The main outstanding point of difference is the route optionality. The Applicant is engaging with Hillam Solar Limited is respect of this and remains confident the necessary land rights can be acquired by voluntary agreement without prejudice to either project. |  | Elaine Caroline Richardson - RR-0382
305140, 305217, 305266 | Brian Dennis Heselwood, Ian George Heselwood, Keith Alan Heselwood | Michael Townend | 09-003 | 9 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. Deadline 2 The Applicant and the Applicant's appointed agent met with the Landowner's appointed land agent on 7 August 2026 to discuss the remaining outstanding items within the Heads of Terms. The parties agreed the final amendments required to the Heads of Terms and revised Heads of Terms are due to be issued to the Landowner shortly. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their appointed land agent to achieve this. Deadline 3 The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 25 September 2026 following engagement with the Landowner's appointed land agent. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this.
356225, 356199 | Caroline Seiler, William Harry Johnson |  | 20-045 | 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant consulted with the Landowners as part of the pre-application consultation processes. The Applicants agent are working with the Landowners to understand an ownership query. Once the ownership query is established, the Applicant will commence negotiations with this Landowners following confirmation of the nature of the requirements and rights sought for this land. A draft licence agreement is being prepared and is due to be issued shortly. Procedural Deadline B A licence agreement was issued to the Landowners on 3 June 2026. The Landowner has emailed the Applicant's land agent advising they are unwilling to enter into negotiations. Notwithstanding the position reported by the Landowner, the Applicant is committed to continuing to engage with them and understand their concerns with the intention to progressing a voluntary position. Deadline 2 The Applicant's appointed land agent continues to offer a meeting with the Landowner, most recently on the 20 August 2026, to better understand their concerns and to facilitate progress towards a voluntary agreement. Deadline 3 The Applicant's appointed land agent has continued efforts to engage with the Landowner and, most recently on 21 September 2026, offered a meeting to better understand their concerns and facilitate progress towards securing a voluntary agreement.
305148, 305195 | Charles Andrew John Tindall, Geoffrey Tindall |  | 08-020 | 8 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant consulted with the Landowners as part of the pre-application consultation processes. The Applicant is commencing negotiations with the Landowners following confirmation of the nature of the requirements and rights sought for this land. A draft licence agreement is being prepared and is due to be issued shortly. Procedural Deadline B A licence agreement was issued to the Landowners on 3 June 2026. The Applicant's appointed land agent received a signed licence on 22 June 2026.
305149, 305263 | Charles Angus William Gowthorpe, Kathleen Margaret Gowthorpe | Stephen Burley | 05-046, 05-047, 05-048, 06-002, 06-004, 06-007 | 5, 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant has received signed Heads of Terms on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
305149, 305263, 326739 | Charles Angus William Gowthorpe, Kathleen Margaret Gowthorpe, The Executor of the Estate of the Late Peter Ward Gowthorpe | Stephen Burley | 05-043 | 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-09-29 | Negotiations for rights The Applicant has received signed Heads of Terms on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
|  |  | 05-042 | 5 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant has received signed HoTs on 29th January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
304585 | Charles David Forbes Adam | Giles Johnson | 01-004, 01-009, 01-012, 01-019, 01-023, 01-030, 01-033 | 1 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 3, 5, 6, 7, 9A, 10A |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
|  |  | 01-002, 01-003, 01-005, 01-006, 01-010, 01-011, 01-031, 02-002, 03-002, 03-004, 03-005, 03-019, 03-020, 03-023, 03-024, 03-025, 03-026, 03-027, 03-028, 03-050, 03-051 | 1, 2, 3 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 8B, 10A |  |  | 2026-09-29 | Option Holder An option for lease with this Landowner exists for the majority of these plots. Following confirmation of the Order limits, some plots are not covered by that option. The Applicant is therefore working with the Landowner to regularise the position in respect of those remaining plots and is confident that this will be able to be resolved. Procedural Deadline B The Applicant is working with the Landowner to complete a variation to the existing option for lease to ensure all plots are cover by that option. Deadline 2 A small area of Plot 01-006 is not covered by the existing option. The Applicant is working with the Landowner to complete a variation to the existing option and is confident this will be agreed shortly. Deadline 3 The Applicant is continuing to work with the Landowner to complete a variation to the existing option and is confident this will be agreed shortly.
|  |  | 05-005 | 3, 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 3, 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. Deadline 2 The Applicant and the Applicant's Agent met with the Landowner's appointed land agent on 7 August 2026 to discuss the remaining outstanding items within the Heads of Terms. The parties agreed the final amendments required to the Heads of Terms, following which the revised document will be issued to the Landowner. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. Deadline 3 The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 25 September 2026 following engagement with the Landowner's appointed land agent. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this.
|  |  | 03-006, 03-011, 03-012, 03-015, 03-016, 03-054 | 3 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. Deadline 2 The Applicant and the Applicant's Agent met with the Landowner's appointed land agent on 7 August 2026 to discuss the remaining outstanding items within the Heads of Terms. The parties agreed the final amendments required to the Heads of Terms, following which the revised document will be issued to the Landowner. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. Deadline 3 The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 25 September 2026 following engagement with the Landowner's appointed land agent. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this.
304585, 305162 | Charles David Forbes Adam, Crispin Beilby Forbes Adam | Giles Johnson | 03-062 | 3 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their agent to achieve this. Deadline 2 The Applicant and the Applicant's Agent met with the Landowner's appointed land agent on 7 August 2026 to discuss the remaining outstanding items within the Heads of Terms. The parties agreed the final amendments required to the Heads of Terms, following which the revised document will be issued to the Landowner. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. Deadline 3 The Applicant reissued Heads of Terms to the Landowners land agent on 25 September 2026. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowners and their appointed land agent to achieve this.
304585 | Charles David Fobes Adam | Giles Johnson | 03-021 | 3 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowners' appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. Deadline 2 The Applicant and the Applicant's appointed agent met with the Landowner's appointed land agent on 7 August 2026 to discuss the remaining outstanding items within the Heads of Terms. The parties agreed the final amendments required to the Heads of Terms and revised Heads of Terms are due to be issued to the Landowner shortly. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their appointed land agent to achieve this. Deadline 3 The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 25 September 2026 following engagement with the Landowner's appointed land agent. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this.
|  |  | 03-005a, 03-017f, 03-017i | 3 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-10-13 | Change Application The Applicant's appointed Land Agent called the Landowner's appointed Land Agent to advise of the submission of the Change Application. This was followed up in writing via a letter issued directly to the Landowner. The Applicant will continue to seek to engage with the Landowner in respect of the Change Application and ensure when appropriate, the Heads of Terms will be updated to reflect any changes to the voluntary agreement sought. The updates provided for this Landowner at Deadline 2 and Deadline 3 are applicable to plot 03-005a.
322656 | Charles Ian Farrar | Johnny Cordingley | 14-014 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d) |  |  | 2026-08-20 | Negotiations for rights The Applicant has received signed Heads of Terms on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing. Deadline 2 An option for easement has been exchanged in respect of these plots.
304652 | Christopher Philip Yewdall | Stephen Burley | 16-003, 16-005, 16-006, 16-007 | 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B |  |  | 2026-09-29 | Negotiations for rights The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for this land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B Heads of Terms were issued by the Applicant to the Landowner on 16 March 2026. The Applicant will continue to work with the landowners appointed land agent to progress the Heads of Terms. Deadline 2 The Applicant's appointed land agent met with the Landowner's land agent on 27 July 2026. The purpose of the meeting was to update on the status of the Heads of Terms. As far as the Applicant is aware, there are no outstanding matters and awaits an update from the Landowner's land agent to update on whether the Heads of Terms are in a position to be signed. Deadline 3 Further to the Applicant's appointed land agent meeting with the Landowner's appointed land agent, the Applicant's land agent followed up on 25 August 2026, and on 9 September 2026 via email. The Applicant's land agent followed up via telephone call on 15 September 2026 to obtain an update. The Landowner's agent explained that discussions were ongoing, however due to unforeseen circumstances there was likely to be a delay. The Applicant will continue to engage with the Landowner's agent to progress the Heads of Terms.
305157, 305203, 305300 | Clifford Ian Roy Watson, Gillian Heather Walmsley, Melanie Jane Brown | Giles Bilton | 10-026 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-10-02 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 22 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowners' appointed land agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent continues to engage with the Landowners' appointed land agent and has offered to meet to discuss the outstanding clauses within the Heads of Terms. The Applicant remains confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicants appointed land agent held a meeting with the Landoner's appointed agent on the 15 September 2026 to discuss landowner specific aspects of the HoTs. The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 2 October 2026.The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement.
|  |  | 10-027 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8A |  |  | 2026-10-02 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 22 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowners' appointed land agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent continues to engage with the Landowners' appointed land agent, most recently on the 24 August 2026 and has offered to meet to discuss the outstanding clauses within the Heads of Terms. The Applicant remains confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicants appointed land agent held a meeting with the Landoner's appointed agent on the 15 September 2026 to discuss landowner specific aspects of the HoTs. The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 2 October 2026.The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement.
304676 | Colin Smith | Johnny Cordingley | 09-004 | 9 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 and 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed agent continues to engage with the Landowner's appointed land agent and most recently held a meeting on 15 June 2026. The Applicant will continue to engage with the Landowner and their land agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed agent continues to engage with the Landowner's appointed land agent and most recently corresponded on 20 August 2026 re-iterating the offer to meet with the Landowner in order to understand the outstanding points of difference and progress the voluntary agreement. The Applicant will continue to engage with the Landowner and their appointed land agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant's appointed land agent requested an update from the Landowner's appointed land agent via telephone and email, most recently on 29 September 2026. As of this Land and Rights Negotiation Tracker update, the Applicant has not received any update from the Landowner's land agent in relation to the Heads of Terms. The Applicant will continue to engage with the Landowners land agent so as to move the Heads of Terms forward. |  | Colin Smith - RR-0283
|  |  | 09-006, 09-009 | 9 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 and 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowner's appointed agent and most recently held a meeting on 15 June 2026. The Applicant will continue to engage with the Landowner and their land agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed agent continues to engage with the Landowner's appointed land agent and most recently corresponded on 20 August 2026 re-iterating the offer to meet with the Landowner in order to understand the outstanding points of difference and progress the voluntary agreement. The Applicant will continue to engage with the Landowner and their appointed land agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant's appointed land agent requested an update from the Landowner's appointed land agent via telephone and email, most recently on 29 September 2026. As of this Land and Rights Negotiation Tracker update, the Applicant has not received any update from the Landowner's land agent in relation to the Heads of Terms. The Applicant will continue to engage with the Landowners land agent so as to move the Heads of Terms forward.
305162 | Crispin Beilby Forbes Adam | Giles Johnson | 01-008, 01-013, 01-014, 01-016, 01-017, 01-018, 01-020, 01-021, 01-025, 01-027, 01-029, 01-034, 02-006, 02-005 | 1, 2 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 5, 6, 7, 9A, 9B, 10A |  |  | 2026-08-20 | Option Holder An option for lease with this Landowner exists for the majority of these plots. Following confirmation of the Order limits, some plots are not covered by that option. The Applicant is therefore working with the Landowner to regularise the position in respect of those remaining plots and is confident that this will be able to be resolved. Procedural Deadline B The Applicant is working with the Landowner to complete a variation to the existing option for lease to ensure all plots are cover by that option. Option Holder An option for lease has been exchanged in respect of these plots.
|  |  | 01-015, 01-022, 01-024, 01-026, 01-028, 01-032, 02-003 | 1, 2 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 8B |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
|  |  | 02-011, 03-001, 03-017, 03-018, 03-046, 03-049, 03-059, 05-002, 05-004 | 2, 3, 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-10-13 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. Deadline 2 The Applicant and the Applicant's Agent met with the Landowner's appointed land agent on 7 August 2026 to discuss the remaining outstanding items within the Heads of Terms. The parties agreed the final amendments required to the Heads of Terms, following which the revised document will be issued to the Landowner. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. Deadline 3 The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 25 September 2026 following engagement with the Landowner's appointed land agent. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this. Change Application The Applicant's appointed Land Agent called the Landowner's appointed Land Agent to advise of the submission of the Change Application. This was followed up in writing via a letter issued directly to the Landowner. The Applicant will continue to seek to engage with the Landowner in respect of the Change Application and ensure when appropriate, the Heads of Terms will be updated to reflect any changes to the voluntary agreement sought.
|  |  | 02-008, 03-005a, 03-017a, 03-017b, 03-017c, 03-017e, 03-033, 03-034, 03-035, 03-036, 03-040, 03-041, 03-043, 03-044, 03-045, 03-047, 03-048,04-003 | 2, 3, 4 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-10-13 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. Deadline 2 The Applicant and the Applicant's Agent met with the Landowner's appointed land agent on 7 August 2026 to discuss the remaining outstanding items within the Heads of Terms. The parties agreed the final amendments required to the Heads of Terms, following which the revised document will be issued to the Landowner. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. Deadline 3 The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 25 September 2026 following engagement with the Landowner's appointed land agent. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this. Change Application The Applicant's appointed Land Agent called the Landowner's appointed Land Agent to advise of the submission of the Change Application. This was followed up in writing via a letter issued directly to the Landowner. The Applicant will continue to seek to engage with the Landowner in respect of the Change Application and ensure when appropriate, the Heads of Terms will be updated to reflect any changes to the voluntary agreement sought.
305081 | Crosshills Pigs Limited | Michael Townend | 08-037, 09-001, 09-002 | 8, 9 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. Deadline 2 The Applicant and the Applicant's appointed agent met with the Landowner's appointed land agent on 7 August 2026 to discuss the remaining outstanding items within the Heads of Terms. The parties agreed the final amendments required to the Heads of Terms and revised Heads of Terms are due to be issued to the Landowner shortly. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their appointed land agent to achieve this. Deadline 3 The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 25 September 2026 following engagement with the Landowner's appointed land agent. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this.
66248 | David Arnold Platt | Thomas Cooper | 12-002, 12-012, 19-013, 19-014 | 12, 19 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-10-01 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 and 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent has attempted to contacted the Landowner's appointed land agent regularly, most recently on 19 June 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent has attempted to contacted the Landowner's appointed land agent regularly, most recently on 18 August 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant's appointed land agent held a meeting with the Landowner's appointed Land Agent on 1 October 2026 to progress negotiations of the Heads of Terms. Commercials are the main outstanding point of difference. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement.
356719, 340089 | The Executor of the Estate of the Late David Coates, Jane Coates |  | 21-007 | 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant has received signed Heads of Terms on 18th December 2025 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives Procedural Deadline B The Applicant's appointed land agent has contacted the landowner regularly, most recently on 1 July 2026, to obtain confirmation of the Landowner's legal representative. The Applicant's appointed land agent will continue to attempt to engage with the Landowner to progress the legal documents. Deadline 2 The Applicant's appointed land agent continues to attempt to contact the Landowner to obtain confirmation of the Landowner's legal representative and most recently wrote to the Landowner on 19 August 2026. Once legal representatives are confirmed, the legal documents can progress. Deadline 3 The Applicant's appointed land agent continue to attempt to contact the Landowner to obtain confirmation of the Landowner's legal representative and most recently door knocked the Landowner on 9 September 2026. The Landowner advised they would confirm their legal representative shortly. As of this Land and Rights Negotiation Tracker update, the Applicant has not received any update from the Landowner. The Applicant will continue to attempt to confirm the legal representatives with Landowner.
304647, 304648 | David Michael Hall, Elizabeth Hall | Giles Johnson | 13-001 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowners' appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22nd May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. Deadline 2 The Applicant and the Applicant's appointed agent met with the Landowner's appointed land agent on 7 August 2026 to discuss the remaining outstanding items within the Heads of Terms. The parties agreed the final amendments required to the Heads of Terms and revised Heads of Terms are due to be issued to the Landowner shortly. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their appointed land agent to achieve this. Deadline 3 The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 25 September 2026 following engagement with the Landowner's appointed land agent. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this.
|  |  | 15-001, 15-013 | 15 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowners' appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. Deadline 2 The Applicant and the Applicant's appointed agent met with the Landowner's appointed land agent on 7 August 2026 to discuss the remaining outstanding items within the Heads of Terms. The parties agreed the final amendments required to the Heads of Terms and revised Heads of Terms are due to be issued to the Landowner shortly. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their appointed land agent to achieve this. Deadline 3 The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 25 September 2026 following engagement with the Landowner's appointed land agent. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this.
162803, 162804, 289862 | Diane Lawrie Hey, Timothy Brian Hey, Mark Alan Hey | Matthew Watson / Andrew Holden | 11-018, 11-030, 11-031, 11-033, 15-004, 15-005, 15-006, 15-009, 15-010 | 11, 15 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 7, 8A, 8B |  |  | 2026-09-29 | Negotiations for rights The Applicant's appointed land agent received verbal confirmation the Heads of Terms are in an agreed format on 29 January 2026 from the Landowners' appointed land agent and is awaiting signed copies of the Heads of Terms. Procedural Deadline B The Applicant received signed Heads of Terms on the 16 March 2026. The Applicant is awaiting confirmation of the Landowner's legal representative from the Landowner. The Applicant's land agent has contacted the Landowner's appointed agent regularly to obtain these details, most recently on the 30 June 2026. Deadline 2 The Applicant's appointed land agent has contacted the landowner to obtain confirmation regarding the Landowner's legal representative. Legal representatives are to start progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents. |  | Tim Hey - RR-1391
|  |  | 11-003, 11-010, 11-019, 11-020, 11-034 | 11 | As described in the Book of Reference | Land is subject to Temporary Possession | 7, 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant's appointed land agent received verbal confirmation the Heads of Terms are in an agreed format on 29 January 2026 from the Landowners' appointed land agent and is awaiting signed copies of the Heads of Terms. Procedural Deadline B The Applicant received signed Heads of Terms on the 16 March 2026. The Applicant is awaiting confirmation of the Landowner's legal representative from the Landowner. The Applicant's land agent has contacted the Landowner's appointed agent regularly to obtain these details, most recently on the 30 June 2026. Deadline 2 The Applicant's appointed land agent has contacted the landowner to obtain confirmation regarding the Landowner's legal representative. Legal representatives are to start progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
305182 | Emma Vaughn Clark | Alexander Ireton | 06-033 | 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-10-02 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 to progress Landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent has attempted to contact the Landowner's appointed land agent regularly, most recently on 19 June 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent held a meeting with the Landowner's appointed land agent on 18 August 2026. The Applicant understands the Landowner's appointed agent is in dialogue with the Landowner and will revert to the Applicant shortly with a response on the voluntary agreement. The Applicant's appointed land agent has a further meeting scheduled for 26 August 2026 with the Landowner's appointed land agent to progress the voluntary agreement. The Applicant will continue to engage with the Landowners and their agent and is confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant has progressed Heads of Terms negotiations with the Landowner’s appointed land agent. The Applicant received comments on the Heads of Terms from Landowner’s appointed land agent on 23rd September 2026. The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 2 October 2026. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this.
|  |  | 06-033a | 6 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-10-13 | Change Application The Applicant's appointed Land Agent called the Landowner's appointed Land Agent to advise of the submission of the Change Application. This was followed up in writing via a letter issued directly to the Landowner. The Applicant will continue to seek to engage with the Landowner in respect of the Change Application and ensure when appropriate, the Heads of Terms will be updated to reflect any changes to the voluntary agreement sought.
20333 | Environment Agency |  | 06-009, 06-011, 06-012, 06-016 | 7 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on the 28 November 2025, 8 December 2025 and 7 January 2026 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant received signed Heads of Terms on 26 June 2026 and will now progress negotiations of the legal documents through the Landowner's respective legal representatives. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents. |  | Environment Agency - RR-0528 and RR-0419 | Environment Agency -REP1-019 and REP1-018
305188, 305222 | Francesca Elizabeth Young, James Edward Hartley | Giles Johnson/ Brian Bartle | 12-050, 12-051, 12-053, 12-054 | 12 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 5, 6, 7, 8B, 10B |  |  | 2026-08-20 | Option Holder An option for lease with these Landowners exists for the majority of these plots. Following confirmation of the Order limits, some plots are not covered by that option. The Applicant is therefore working with the Landowners to regularise the position in respect of those remaining plots and is confident that this will be able to be resolved. Procedural Deadline B The Applicant is working with the Landowner to complete a variation to the existing option for lease to ensure all plots are cover by that option. Deadline 2 A variation to the existing option for lease completed on 27 July 2026.
|  |  | 12-049 | 12 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 8 September 2025 and 1 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant met with the landowners appointed land agent on the 22nd May 2026 in order to progress the Heads of Terms. There remains several matters within the terms that are to be agreed, and there has been limited substantive feedback received from the Landowner's appointed land agent. The Applicant will continue to engage with the Landowner's appointed land agent to progress Heads of Terms, and is confident that the necessary land rights can be agreed on a voluntary basis. Deadline 2 The Applicant's appointed land agent met with the Landowner's appointed land agent on 27 July 2026 to discuss and progress the Heads of Terms. There were several actions resulting from the meeting, and progress has been made. The Applicant has will be reissuing updated Heads of Terms in due course so that the Landowners land agent can report to their client. Deadline 3 The Applicant reissued Heads of Terms to the Landowners land agent on 2 September 2026. The Applicant called the Landowners land agent for an update on 15 September 2026, 18 September 2026, and 21 September 2026. The Applicant also followed up with emails on 9 September 2026, and 24 September 2026. As of this Land and Rights Negotiation Tracker update, the Applicant has not received any update from the Landowners land agent in relation to his clients Heads of Terms. The Applicant will continue to engage with the Landowners land agent so as to move Heads of Terms forward.
305199 | George Louis Outhwaite | Johnny Cordingley | 05-049, 06-006 | 5, 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 and 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowner's appointed land agent and most recently held a meeting on 15 June 2026 to progress negotiations. The Applicant will continue to engage with the Landowners and their land agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed agent continues to engage with the Landowner's appointed land agent and most recently corresponded on 20 August 2026 re-iterating the offer to meet with the Landowner in order to understand the outstanding points of difference and progress the voluntary agreement. The Applicant will continue to engage with the Landowner and their appointed land agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant's appointed land agent requested an update from the Landowner's appointed land agent via telephone and email, most recently on 29 September 2026. As of this Land and Rights Negotiation Tracker update, the Applicant has not received any update from the Landowner's land agent in relation to the Heads of Terms. The Applicant will continue to engage with the Landowners land agent so as to move the Heads of Terms forward. |  | George Outhwaite - RR-0475
328644 | Gillian Francis Parkin | Tori Heaton | 13-008 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. Deadline 2 The Applicant and the Applicant's appointed agent met with the Landowner's appointed land agent on 7 August 2026 to discuss the remaining outstanding items within the Heads of Terms. The parties agreed the final amendments required to the Heads of Terms and revised Heads of Terms are due to be issued to the Landowner shortly. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their appointed land agent to achieve this. Deadline 3 The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 25 September 2026 following engagement with the Landowner's appointed land agent. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this.
|  |  | 13-006, 15-014 | 13, 15 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed agent on 22nd May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their agent to achieve this. Deadline 2 The Applicant and the Applicant's appointed agent met with the Landowner's appointed land agent on 7 August 2026 to discuss the remaining outstanding items within the Heads of Terms. The parties agreed the final amendments required to the Heads of Terms and revised Heads of Terms are due to be issued to the Landowner shortly. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their appointed land agent to achieve this. Deadline 3 The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 25 September 2026 following engagement with the Landowner's appointed land agent. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this.
305085 | Hartley Farming (Yorkshire) Limited | Brian Bartle | 12-035, 12-073, 12-074, 19-003 | 12, 19 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 3, 5, 6, 8B, 10B |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
|  |  | 19-004 | 19 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d) |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
|  |  | 17-006, 17-008,17-010, 17-012 | 17 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B |  |  | 2026-09-29 | Negotiations for rights The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for this land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B Heads of Terms were issued by the Applicant to the Landowner on 3 July 2026. The Applicant will continue to work with the landowners appointed land agent to progress the Heads of Terms. Deadline 2 The Applicant's appointed land agent met with the Landowner's appointed land agent on 27 July 2026 to discuss and progress the Heads of Terms. There were several actions resulting from the meeting, and progress has been made. The Applicant has will be reissuing updated Heads of Terms in due course so that the Landowners land agent can report to their client. Deadline 3 The Applicant reissued Heads of Terms to the Landowners land agent on 2 September 2026. The Applicant called the Landowners land agent for an update on 15 September 2026, 18 September 2026, and 21 September 2026. The Applicant also followed up with emails on 9 September 2026, and 24 September 2026. As of this Land and Rights Negotiation Tracker update, the Applicant has not received any update from the Landowners land agent in relation to his clients Heads of Terms. The Applicant will continue to engage with the Landowners land agent so as to move Heads of Terms forward.
305211, 305385 | Heather Victoria Verity, Tom Edwin Verity | Giles Johnson / Brian Bartle | 13-021, 13-035 | 13 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 2, 3, 5, 6, 7 |  |  | 2026-08-20 | Option Holder An option for lease with these Landowners exists for the majority of these plots. Following confirmation of the Order limits, some plots are not covered by that option. The Applicant is therefore working with the Landowners to regularise the position in respect of those remaining plots and is confident that this will be able to be resolved. Procedural Deadline B The Applicant is working with the Landowner to complete a variation to the existing option for lease to ensure all plots are cover by that option. Deadline 2 A variation to the existing option for lease completed on 27 July 2026.
|  |  | 13-020, 13-022, 13-029, 13-030 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 8A, 8B |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
|  |  | 13-019, 13-031 | 13 | As described in the Book of Reference | Land is subject to Temporary Possession | 1(d), 8A, 8B |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
330221 | Helen Elizabeth Platt | Thomas Cooper | 12-005 | 12 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-23 | Negotiations for temporary possession The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for this land. A draft licence agreement is being prepared and is due to be issued shortly. Procedural Deadline B A populated licence agreement was issued to the Landowners on 3 June 2026. The Applicant's appointed land agent has contacted the Landowner's appointed agent on 19 June 2026 to progress negotiations. The Applicant will continue to engage with the Landowners and their land agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent has attempted to contacted the Landowner's appointed land agent regularly, most recently on 18 August 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant's appointed land agent held a meeting with the Landowner's appointed Land Agent on 1 October 2026 to progress negotiations of the Heads of Terms. Commercials are the main outstanding point of difference. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement.
305212, 305262 | Helen Michaela Scholey, Karen Elizabeth Scholey | Michael Townend | 20-025 | 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowners' appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. Deadline 2 The Applicant and the Applicant's appointed agent met with the Landowner's appointed land agent on 7 August 2026 to discuss the remaining outstanding items within the Heads of Terms. The parties agreed the final amendments required to the Heads of Terms and revised Heads of Terms are due to be issued to the Landowner shortly. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their appointed land agent to achieve this. Deadline 3 The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 25 September 2026 following engagement with the Landowner's appointed land agent. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this.
|  |  | 20-040, 20-041 | 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowners' appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. Deadline 2 The Applicant and the Applicant's appointed agent met with the Landowner's appointed land agent on 7 August 2026 to discuss the remaining outstanding items within the Heads of Terms. The parties agreed the final amendments required to the Heads of Terms and revised Heads of Terms are due to be issued to the Landowner shortly. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their appointed land agent to achieve this. Deadline 3 The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 25 September 2026 following engagement with the Landowner's appointed land agent. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this.
305212, 305262, 341991 | Helen Michaela Scholey, Karen Elizabeth Scholey, The Executor of the Estate of the Late Paul Sherrard Scholey | Michael Townend | 20-021 | 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowner's appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their agent to achieve this. Deadline 2 The Applicant and the Applicant's appointed agent met with the Landowner's appointed land agent on 7 August 2026 to discuss the remaining outstanding items within the Heads of Terms. The parties agreed the final amendments required to the Heads of Terms and revised Heads of Terms are due to be issued to the Landowner shortly. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their appointed land agent to achieve this. Deadline 3 The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 25 September 2026 following engagement with the Landowner's appointed land agent. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this.
334252 | Hey Holdings Limited | Matthew Watson | 11-036 | 11 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant's appointed land agent received verbal confirmation the Heads of Terms are in an agreed format on 29 January 2026 from the Landowner's appointed land agent and is awaiting signed copies of the Heads of Terms. Procedural Deadline B The Applicant received signed Heads of Terms on the 16 March 2026. The Applicant is awaiting confirmation of the Landowner's legal representative from the Landowner. The Applicant's land agent has contacted the Landowner's appointed agent regularly to obtain these details, most recently on the 30 June 2026. Deadline 2 The Applicant's appointed land agent has contacted the landowner to obtain confirmation regarding the Landowner's legal representative. Legal representatives are to start progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
305089 | J.H. McCloy & Co Limited | Mary Foster | 19-017, 19-018, 20-003, 20-004, 20-007, 20-008, 20-011, 20-012, 20-026, 20-031, 20-032 | 19, 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 7, 8A |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 and 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant understands the Heads of Terms are in an agreed format apart from an outstanding query on an operational access route. The Applicant's land agent is working with the Landowner's land agent to resolve this issue and is confident the necessary land rights can be acquired by voluntary agreement. The Applicant understands that UK Power Associates Ltd have a beneficiary interest in the land by way of an option agreement and is working with the Landowners to obtain the necessary consents. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowners' appointed land agent and most recently held a meeting on 15 June 2026. The route proposed remains the outstanding issue and the Applicants is reviewing this and remains confident a voluntary agreement can be acquired. Deadline 2 The Applicant's appointed land agent responded to the outstanding point of difference of 9 July 2026 and is awaiting a response from the Landowners' appointed land agent. This was followed up most recently on 20 August 2026. The Applicant remains confident a voluntary agreement can be agreed. Deadline 3 The Applicant's appointed land agent continues to engage with the Landowner's appointed land agent, most recently on 29 September 2026. The Applicant's appointed land agent has provided the requested information to the Landowner's appointed agent and is awaiting a response. The Applicant remains confident a voluntary agreement can be reached.
|  |  | 19-016, 20-005, 20-029, 20-033, 20-034, 20-039 | 19, 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 7, 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 and 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant understands the Heads of Terms are in an agreed format apart from an outstanding query on an operational access route. The Applicant's land agent is working with the Landowner's land agent to resolve this issue and is confident the necessary land rights can be acquired by voluntary agreement. The Applicant understands that UK Power Associates Ltd have a beneficiary interest in the land by way of an option agreement and is working with the Landowners to obtain the necessary consents. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowners' appointed land agent and most recently held a meeting on 15 June 2026. The route proposed remains the outstanding issue and the Applicants is reviewing this and remains confident a voluntary agreement can be acquired. Deadline 2 The Applicant's appointed land agent responded to the outstanding point of difference of 9 July 2026 and is awaiting a response from the Landowners' appointed land agent. This was followed up most recently on 20 August 2026. The Applicant remains confident a voluntary agreement can be agreed. Deadline 3 The Applicant's appointed land agent continues to engage with the Landowner's appointed land agent, most recently on 29 September 2026. The Applicant's appointed land agent has provided the requested information to the Landowner's appointed agent and is awaiting a response. The Applicant remains confident a voluntary agreement can be reached.
305219 | Jacqueline Daphne Bradshaw | Alexander Ireton | 06-015, 06-017, 06-018, 06-019, 06-022, 06-023 | 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-10-02 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent has attempted to contact the Landowner's appointed land agent regularly, most recently on 19 June 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement Deadline 2 The Applicant's appointed land agent held a meeting with the Landowner's appointed land agent on 18 August 2026. The Applicant understands the Landowner's appointed agent is in dialogue with the Landowner and will revert to the Applicant shortly with a response on the voluntary agreement. The Applicant's appointed land agent has a further meeting scheduled for 26 August 2026 with the Landowner's appointed land agent to progress the voluntary agreement. The Applicant will continue to engage with the Landowners and their agent and is confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant has progressed Heads of Terms negotiations with the Landowner’s appointed land agent. The Applicant received comments on the Heads of Terms from Landowner’s appointed land agent on 23rd September 2026. The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 2 October 2026. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this.
244072 | James Edward Clark | Alexander Ireton | 06-020, 06-021, 06-024, 06-025, 06-028, 07-023, 07-024, 07-025, 07-026, 08-014 | 6, 7, 8 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-10-02 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent has attempted to contact the Landowner's appointed land agent regularly, most recently on 19 June 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent held a meeting with the Landowner's appointed land agent on 18 August 2026. The Applicant understands the Landowner's appointed agent is in dialogue with the Landowner and will revert to the Applicant shortly with a response on the voluntary agreement. The Applicant's appointed land agent has a further meeting scheduled for 26 August 2026 with the Landowner's appointed land agent to progress the voluntary agreement. The Applicant will continue to engage with the Landowners and their agent and is confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant has progressed Heads of Terms negotiations with the Landowner’s appointed land agent. The Applicant received comments on the Heads of Terms from Landowner’s appointed land agent on 23rd September 2026. The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 2 October 2026. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this. |  | C E CJ E Clark - RR-0175
|  |  | 06-031, 06-032, 06-034, 07-012, 07-013, 07-027, 08-016, 08-017, 08-018 | 6, 7, 8 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-10-02 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed agent has attempted to contact the Landowner's appointed land agent regularly, most recently on 19 June 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent held a meeting with the Landowner's appointed land agent on 18 August 2026. The Applicant understands the Landowner's appointed agent is in dialogue with the Landowner and will revert to the Applicant shortly with a response on the voluntary agreement. The Applicant's appointed land agent has a further meeting scheduled for 26 August 2026 with the Landowner's appointed land agent to progress the voluntary agreement. The Applicant will continue to engage with the Landowners and their agent and is confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant has progressed Heads of Terms negotiations with the Landowner’s appointed land agent. The Applicant received comments on the Heads of Terms from Landowner’s appointed land agent on 23rd September 2026. The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 2 October 2026. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this.
322674, 244072 | James Edward Clark, Charles Clark | Alexander Ireton | 06-038, 06-042, 06-043, 06-044, 06-045 | 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  |  | Deadline 3 The Applicant has progressed Heads of Terms negotiations with the Landowner’s appointed land agent. The Applicant received comments on the Heads of Terms from Landowner’s appointed land agent on 23rd September 2026. The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 2 October 2026. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this. |  | C E CJ E Clark - RR-0175
|  |  | 06-035, 06-036, 06-039, 08-002, 08-003, 08-004, 08-007, 08-008 | 6, 8 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  |  | Deadline 3 The Applicant has progressed Heads of Terms negotiations with the Landowner’s appointed land agent. The Applicant received comments on the Heads of Terms from Landowner’s appointed land agent on 23rd September 2026. The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 2 October 2026. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this.
305222 | James Edward Hartley | Giles Johnson/ Brian Bartle | 12-034, 12-052, 12-055, 12-060, 12-071, 12-072, 18-008, 18-013, 18-014, 18-015 | 12, 18 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 3, 5, 6, 7, 8A, 8B, 10B |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
|  |  | 18-001, 18-001a, 18-001d, 18-002, 18-002a, 18-002b, 18-011 | 18 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 8B, 10B |  |  | 2026-10-13 | Option Holder An option for lease has been exchanged in respect of these plots. Change Application The Applicant's appointed Land Agent called the Landowner's appointed Land Agent to advise of the submission of the Change Application. This was followed up in writing via a letter issued directly to the Landowner. The Applicant will continue to seek to engage with the Landowner in respect of the Change Application and ensure when appropriate, the Heads of Terms will be updated to reflect any changes to the voluntary agreement sought.
305234, 305287, 305344 | Joan Mary Smith, Margaret Hirst, Richard John Pratt | Stephen Burley | 05-030 | 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 19 August 2025 and 10 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant received signed Heads of Terms on 27 February 2026. The Applicant is awaiting confirmation of the Landowner's legal representative from the Landowner. The Applicant's land agent has contacted the Landowner's appointed agent regularly to obtain these details, most recently on the 02 July 2026. Deadline 2 The Applicant's appointed land agent met with the Landowner's land agent on 27 July 2026. The purpose of the meeting was to update on the status of the Heads of Terms. The Heads of Terms document has been signed, however their legal representatives have not yet been confirmed. The Landowners land agent has been contacted for this information and the Applicant awaits a response. Deadline 3 Further to the Applicant's appointed land agent meeting with the Landowner's appointed land agent, the Applicant's land agent followed up on 25 August 2026, and on 9 September 2026 via email. The Applicant's land agent followed up via telephone call on 15 September 2026 to obtain an update and they were able to confirm the occupier details, and committed to following up with their client to obtain the details necessary to progress the Heads of Terms to Option. As of providing this Land and Rights Negotiations Tracker update, no further details have been submitted by the Landowner's land agent.
305237, 305245, 305346, 305363 | John Charles Cox, John Richard Hall, Richard Thomas Batty, Sarah Batty | Johnny Cordingley | 20-023, 20-024 | 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 An option for easement has been exchanged in respect of these plots.
305238, 305248 | John Cook, Jonathan Cook | Richard Waring | 09-016 | 9 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B The Applicant's appointed land agent has contacted the Landowner's appointed land agent regularly, most recently on 1 July 2026, to obtain confirmation of the Landowner's legal representative. The Applicant's appointed land agent understands legal representatives have been confirmed and awaits the detail of these. Deadline 2 The Applicant's appointed land agent has received confirmation of the Landowner's legal representative and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Deadline 3 Legal representatives are progressing the legal documents. |  | John Stuart Cook - RR-0686
325410 | John Nicholas Stoker |  | 13-038, 13-041 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-09-22 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 10 December to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant met with the Landowner and his appointed land agent on the 22 April 2026 whereby progress was made on the Heads of Terms. The Applicant’s land agent understands that the Landowner’s land agent is no longer instructed. The Applicant will continue to engage directly with the Landowner and is confident that the necessary land rights can be acquired by voluntary agreement Deadline 2 The Applicant continues to engage with the Landowner and held a meeting on 20 August 2026 to understand the outstanding points of difference and progress the voluntary agreement. The Applicant will continue to engage with the Landowner and is confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant's appointed land agent provided further information to the Landowner on 24 September 2026 regarding the outstanding points of difference. The Landowner advised they would review the information provided as well as the commercial arrangement within the Heads of Terms and revert to the Applicant's appointed agent shortly. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement. |  | John Nicholas Stoker - RR-0684 | John Nicholas Stoker - REP1-040
|  |  | 13-042 | 13 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-22 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 10 December to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B the Applicant met with the Landowner and his appointed land agent on the 22 April 2026 to progress the Heads of Terms, the Applicant had good engagement from the Landowner's agent, the landowners land agent has been subsequently disinstructed by the landowner. The Applicant will continue to engage directly with the landowner and is confident that the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to engage with the Landowner and held a meeting on 20 August 2026 to understand the outstanding points of difference and progress the voluntary agreement. The Applicant will continue to engage with the Landowner and is confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant's appointed land agent provided further information to the Landowner on 24 September 2026 regarding the outstanding points of difference. The Landowner advised they would review the information provided as well as the commercial arrangement within the Heads of Terms and revert to the Applicant's appointed agent shortly. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement.
304717 | Joseph Rex Pocklington | Alexander Ireton | 06-013 | 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-10-02 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent has attempted to contact the Landowner's appointed land agent regularly, most recently on 19 June 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent held a meeting with the Landowner's appointed land agent on 18 August 2026. The Applicant understands the Landowner's appointed agent is in dialogue with the Landowner and will revert to the Applicant shortly with a response on the voluntary agreement. The Applicant's appointed land agent has a further meeting scheduled for 26 August 2026 with the Landowner's appointed land agent to progress the voluntary agreement. The Applicant will continue to engage with the Landowners and their agent and is confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant has progressed Heads of Terms negotiations with the Landowner’s appointed land agent. The Applicant received comments on the Heads of Terms from Landowner’s appointed land agent on 23rd September 2026. The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 2 October 2026. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this.
304672 | Judith Ann Pearse | Brian Bartle | 09-021, 09-022 | 9 | As described in the Book of Reference | Land is subject to Temporary Possession | 7, 8A |  |  | 29/09/026 | Negotiations for temporary possession The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for this land. A draft licence agreement is being prepared and is due to be issued shortly. Procedural Deadline B The Applicant issued Licences to the Landowner on 3 June 2026. The Applicant had met with the Landowners appointed land agent on the 22 May 2026 to discuss the overarching rights being sought by the Applicant. The land agent made it clear in the meeting that the Landowner was unwilling to progress the Heads of Terms. Notwithstanding the position reported by the Landowner's appointed land agent, the Applicant will continue to engage with them with the intention to progress the Heads of Terms. Deadline 2 The Applicant's appointed land agent met with the Landowner's appointed land agent on 27 July 2026 to discuss and progress the Heads of Terms. There were several actions resulting from the meeting, and progress has been made. The Applicant has will be reissuing updated Heads of Terms in due course so that the Landowners land agent can report to their client. Deadline 3 The Applicant continues to engage, and most recently called the Landowners land agent for an update on 15 September 2026, 18 September 2026, and 21 September 2026. The Applicant also followed up with emails on 9 September 2026, and 24 September 2026. As of this Land and Rights Negotiation Tracker update, the Applicant has not received any update from the Landowners land agent.
305260, 358611 | June Elisabeth Romans, The Executor of the Estate of the Late Michael Robert Romans | Mary Foster | 05-017, 05-018, 05-020 | 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 29/09/026 | Negotiations for rights The Applicant's appointed land agent received written confirmation the Heads of Terms are in an agreed format on 29 January 2026 from the Landowner's appointed land agent and is awaiting signed copies of the Heads of Terms once an ownership query has been resolved. Procedural Deadline B The Applicant understands the ownership query has been resolved and the Heads of Terms are with the Landowner's representative for signature and are expected to be returned shortly. Deadline 2 The Applicant has received signed HoTs on 31 July 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Deadline 3 Legal representatives are progressing the legal documents.
305261, 334240, 334244 | June Harris, Alison Victoria Laskey, Sarah Joanne Thompson | Michael Townend | 12-014, 12-048 | 12 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 29/09/026 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowners' appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. Deadline 2 The Applicant and the Applicant's appointed agent met with the Landowner's appointed land agent on 7 August 2026 to discuss the remaining outstanding items within the Heads of Terms. The parties agreed the final amendments required to the Heads of Terms and revised Heads of Terms are due to be issued to the Landowner shortly. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their appointed land agent to achieve this. Deadline 3 The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 25 September 2026 following engagement with the Landowner's appointed land agent. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this. |  | Sarah Thompson - RR-1262
349123 | Keith Winsor |  | 13-047 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8A |  |  | 2026-09-24 | Negotiations for rights The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for the land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B Heads of Terms were issued on 16 March 2026. The Applicant wrote to the Landowner again on 5 May 2026 and remains open to engagement with Landowner. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent continues to engage with the Landowner, most recently on 25 August 2026 and has scheduled a meeting for 9 September 2026 to progress the voluntary agreement. Applicant is confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant has received signed HoTs on 24 September 2026 and will now progress negotiations of the legal documents through the Landowner's respective legal representatives.
305273, 305320 | Kt Jodie Allen, Paul Adam Watson | Alexander Ireton | 07-019, 07-020 | 7 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-10-02 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 2 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent has attempted to contact the Landowner's appointed land agent regularly, most recently on 19 June 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent held a meeting with the Landowner's appointed land agent on 18 August 2026. The Applicant understands the Landowner's appointed agent is in dialogue with the Landowner and will revert to the Applicant shortly with a response on the voluntary agreement. The Applicant's appointed land agent has a further meeting scheduled for 26 August 2026 with the Landowner's appointed land agent to progress the voluntary agreement. The Applicant will continue to engage with the Landowners and their agent and is confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant has progressed Heads of Terms negotiations with the Landowner’s appointed land agent. The Applicant received comments on the Heads of Terms from Landowner’s appointed land agent on 23rd September 2026. The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 2 October 2026. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this.
304641, 304642, 304643 | Margaret Anne Parkin, Andrew Kenneth Parkin, Jonathan William Parkin | Mary Foster | 13-009, 13-010 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-09-29 | Negotiations for rights The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
|  |  | 13-011 | 13 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
304606 | Marlene Thompson |  | 20-027, 20-032 | 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-10-02 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant has made attempts of engagement most recently 21 January 2026 . The Applicant will continue to attempt to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant re issued Heads of Terms to the Landowner's daughter on 24 June 2026 following a phone call to discuss the Heads of Terms document. The Applicant remains confident that all required land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent continues to attempt to engage with the Landowner's daughter who is acting on the Landowner's behalf and last emailed on 20 August 2026 to progress Heads of Terms negotiations. The Applicant remains confident that all required land rights can be acquired by voluntary agreement. Deadline 3 The Applicant continues to attempt to engage with the Landowner, and has called the Landowner’s representative on 24 September 2026, 8 September 2026, and 20 August 2026. The Applicant also followed up with emails on 8 September 2026, and 24 September 2026. As of this Land and Rights Negotiation Tracker update, the Applicant has not received an update from the Landowner or their representative. The Applicant will continue to seek engagement with the Landowner so as to move Heads of Terms forward.
|  |  | 20-028, 20-033 | 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-10-02 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025.The Applicant has made multiple attempts of engagement most recently 21 January 2026 . The Applicant will continue to attempt to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant re issued Heads of Terms to the Landowner's daughter on 24 June 2026 following a phone call to discuss the Heads of Terms document. Deadline 2 The Applicant's appointed land agent continues to attempt to engage with the Landowner's daughter who is acting on the Landowner's behalf and last emailed on 20 August 2026 to progress Heads of Terms negotiations. The Applicant remains confident that all required land rights can be acquired by voluntary agreement. Deadline 3 The Applicant continues to attempt to engage with the Landowner, and has called the Landowner’s representative on 24 September 2026, 8 September 2026, and 20 August 2026. The Applicant also followed up with emails on 8 September 2026, and 24 September 2026. As of this Land and Rights Negotiation Tracker update, the Applicant has not received an update from the Landowner or their representative. The Applicant will continue to seek engagement with the Landowner so as to move Heads of Terms forward.
332764 | Martin James Bramley |  | 14-005 | 14 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 8B, 10B |  |  | 2026-09-29 | Option Holder The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for this land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B Heads of Terms were issued by the Applicant to the landowner on 16 March 2026. The Applicant will continue to work with the Landowner's appointed land agent to progress the Heads of Terms. Deadline 2 The Applicant's appointed land agent has arranged to meet with the Landowner on the 2 September 2026 to progress Heads of Terms. The Applicant remains confident that all required land rights can be acquired by voluntary agreement. Deadline 3 The Applicant has received signed HoTs on 2 September 2026 and will now progress negotiations of the legal documents through the Landowner's respective legal representatives.
|  |  | 14-006 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B |  |  | 2026-09-29 | Option Holder The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for the land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B Heads of Terms were issued by the Applicant to the Landowner on 16 March 2026. The Applicant will continue to work with the landowners appointed land agent to progress the Heads of Terms. Deadline 2 The Applicant's appointed land agent has arranged to meet with the Landowner on the 2 September 2026 to progress Heads of Terms. The Applicant remains confident that all required land rights can be acquired by voluntary agreement. Deadline 3 The Applicant has received signed HoTs on 2 September 2026 and will now progress negotiations of the legal documents through the Landowner's respective legal representatives.
|  |  | 14-007 | 14 | As described in the Book of Reference | Land is subject to Temporary Possession | 8B |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for this land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B There has been extensive dialogue between the Applicant and the Landowner's appointed land agent in relation to the Heads of Terms. It is understood by the Applicant that the Heads of Terms are agreed, however a signed document has not been received. The Applicant will continue to liaise with the landowners appointed land agent to progress the Heads of Terms and is confident that signed documents can be provided in due course. Deadline 2 The Applicant's appointed land agent has arranged to meet with the Landowner on the 2 September 2026 to progress Heads of Terms. The Applicant remains confident that all required land rights can be acquired by voluntary agreement. Deadline 3 The Applicant has received signed HoTs on 2 September 2026 and will now progress negotiations of the legal documents through the Landowner's respective legal representatives.
305301 | Michael Anthony Bowker |  | 05-029 | 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant has received signed HoTs on 12 January 2026 and will now progress negotiations of the legal documents through the Landowner's respective legal representatives. Procedural Deadline B The Applicant is awaiting confirmation of the Landowner's legal representative from the Landowner. The Applicant's land agent has contacted the Landowner's regularly to obtain these details, most recently on the 30 June 2026. Deadline 2 The Applicant is awaiting confirmation of the Landowner's legal representative from the Landowner. The Applicant's land agent has contacted the Landowner's regularly to obtain these details, most recently on the 18 August 2026. Deadline 3 The Applicant is awaiting confirmation of the Landowner's legal representative from the Landowner. The Applicant's land agent has contacted the Landowner's regularly to obtain these details, most recently on the 17 September 2026.
305304, 305335, 340482, 390114 | Michael Edwin Wilson, Rachel Elizabeth Wilson, Sara Fox, Rosie Allsopp | Michael Townend | 10-018b, 10-019, 10-019a, 10-019b | 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-10-13 | Negotiations for temporary possession The Applicant consulted with the interest as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Interest following confirmation of the nature of the requirements and rights sought for this party’s land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B A populated licence agreement was issued to the Landowners on 3 June 2026. The Applicant remains open to engagement with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant and the Applicant's Agent met with the Landowner's appointed land agent on 7 August 2026 to discuss the remaining outstanding items within the licence agreement. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. Deadline 3 The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 25 September 2026 following engagement with the Landowner's appointed land agent. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this. Change Application The Applicant's appointed Land Agent called the Landowner's appointed Land Agent to advise of the submission of the Change Application. This was followed up in writing via a letter issued directly to the Landowner. The Applicant will continue to seek to engage with the Landowner in respect of the Change Application and ensure when appropriate, the Heads of Terms will be updated to reflect any changes to the voluntary agreement sought. |  | Rachael Wilson - RR-1137
305093 | National Grid Electricity Transmission PLC |  | 21-008, 21-009, 21-011, 21-015, 21-016, 21-017, 21-018, 21-021, 21-024, 21-025, 21-026, 21-029, 21-031a, 21-031, 21-035, 21-040, 21-040a, 21-040b | 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 12th January 2026 . The Applicants land agent has made further attempts to engage. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent is continuing to engage with the Landowner and is working with the Landowner to complete the required forms to progress Heads of Terms. The Applicant will continue to engage with the Landowner and is confident that the necessary land rights can be reached by voluntary agreement. Deadline 2 The Applicant's appointed land agent is continuing to engage with the Landowner and is working with the Landowner to complete the required forms to progress Heads of Terms. The Applicant will continue to engage with the Landowner and is confident that the necessary land rights can be reached by voluntary agreement Deadline 3 The Applicant's appointed land agent has worked with the Landowner to complete the required forms to facilitate progress towards Heads of Terms. With the necessary information now provided, the Applicant's appointed land agent will continue engagement with the Landowner and progress negotiations with a view to securing a voluntary agreement. The Applicant remains confident that the necessary land rights can be acquired by voluntary agreement. |  | National Grid Electricity Transmission PLC - RR-1037 and RR-0437 | National Grid Electricity Transmission Plc - REP1-022
|  |  | 21-013, 21-019, 21-032, 21-032a, 21-032b, 21-033, 21-034 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5, 8A |  |  | 2026-02-04 | N/A
22908 | National Highways Limited |  | 05-019, 05-021, 05-024, 05-026, 05-028, 05-034, 05-035, 05-037, 10-052, 10-053, 10-054, 10-056, 10-059, 10-060, 10-062 | 5, 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 12 January 2026. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 24 November 2025. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant has been in discussion with National Highways and the representative of North Yorkshire Council to confirm the ownership of the land within the Heads of Terms. The Applicant is awaiting a response from North Yorkshire Council as to the Heads of Terms and the land ownership. The Applicant is confident that all land rights required can be agreed via voluntary agreement. Deadline 2 The Applicant's appointed land agent continues to contact North Yorkshire Council, most recently on 20 August 2026, and awaits a response regarding the Heads of Terms and land ownership. The Applicant is confident that all land rights required can be secured through voluntary agreement. Deadline 3 The Applicant's appointed land agent has continued to seek engagement with North Yorkshire Council and, most recently on 21 September 2026, requested an update regarding the Heads of Terms and confirmation of land ownership. The Applicant remains confident that all land rights required can be secured through voluntary agreement. |  | National Highways - RR-0177 and RR-1038 | National Highways Limited - REP1-023
|  |  | 05-036, 05-038, 05-039, 05-041, 10-045, 10-047, 10-050, 10-051, 10-069 | 5, 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 12 January 2026. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 24 November 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant has been in discussion with National Highways and the representative of North Yorkshire Council to confirm the ownership of the land within the Heads of Terms. The Applicant is awaiting a response from North Yorkshire Council as to the Heads of Terms and the land ownership. The Applicant is confident that all land rights required can be agreed via voluntary agreement. Deadline 2 The Applicant's appointed land agent continues to contact North Yorkshire Council, most recently on 20 August 2026, and awaits a response regarding the Heads of Terms and land ownership. The Applicant is confident that all land rights required can be secured through voluntary agreement. Deadline 3 The Applicant's appointed land agent has continued to seek engagement with North Yorkshire Council and, most recently on 21 September 2026, requested an update regarding the Heads of Terms and confirmation of land ownership. The Applicant remains confident that all land rights required can be secured through voluntary agreement.
304738, 304739 | Neil Stainthorpe, Julie Fiona Stainthorpe |  | 08-025, 08-026 | 8 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for this land. A draft licence agreement is being prepared and is due to be issued shortly. Procedural Deadline B A populated licence agreement was issued to the Landowners on 3 June 2026. The Applicant's appointed agent held a meeting with the Landowners' appointed agent on 15 June 2026. The Applicant will continue to engage with the Landowners and their agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant continues to engage regularly with the Landowner's appointed agent in respect of the licence agreement. The Applicant is awaiting on comments from the Landowner's appointed agent as to the outstanding matters of difference and most recently followed this up on 20 August 2026. Deadline 3 The Applicant's appointed requested an update from the Landowner's appointed land agent via telephone and email, most recently on 29 September 2026. As of this Land and Rights Negotiation Tracker update, the Applicant has not received any update from the Landowner's land agent in relation to the Licence Agreement. The Applicant will continue to engage with the Landowners land agent so as to move the agreement forward.
7310 | Network Rail Infrastructure Limited |  | 10-073, 10-074, 16-001 | 10, 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's land agent has made attempts to engage the landowner, most recently on 4 February 2026. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowner and held a meeting on 13 May 2026 to progress negotiations. The Applicant's appointed land agent continues to have productive dialogue with the landowner, most recently on 22 June 2026 and remains confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent continues to have productive dialogue with the Landowner, most recently on 19 August 2026. The Applicant's appointed land agent is expecting revised Heads of Terms from the Landowner shortly and remains confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant's appointed land agent continue to corresponded with the Landowner and has provided the Landowner with all requested information. The Applicant is still awaiting revised HoTs from the Landowner but it is understood these are expected to be issued shortly. The Applicant remains confident the necessary land rights can be acquired by voluntary agreement. |  | Network Rail Infrastructure Limited - RR-1298 and RR-1045 | Network Rail Infrastructure Limited - REP2-122
249688 | North Yorkshire Council |  | 03-033, 03-053, 08-038, 22-004 | 3, 8, 22 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 27 January 2026. The Applicant's land agent has made further attempts to engage. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent continues to have productive dialogue with the landowner, most recently on 1 July 2026 and remains confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent continues to contact North Yorkshire Council, most recently on 20 August 2026, and awaits a response regarding the Heads of Terms and land ownership. The Applicant is confident that all land rights required can be secured through voluntary agreement. Deadline 3 The Applicant's appointed land agent continues to contact North Yorkshire Council, most recently on 21 September 2026. A meeting is being arranged to receive feedback on Heads of Terms and land ownership. The Applicant is confident that all land rights required can be secured through voluntary agreement. |  | North Yorkshire Council - RR-1075 | North Yorkshire Council - REP 1-006 REP 1-007 REP 1-008 REP 2-121
325424 | Martin Bramley |  | 14-028 | 14 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 6 |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
|  |  | 14-024 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 8B |  |  | 2026-02-04 | Option Holder An option for lease has been exchanged in respect of these plots.
53140, 53214 | Paul Robert Swales, Peter David Swales | Robert Hamilton | 21-001, 21-003, 21-004, 21-005, 21-006 | 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 24 November 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowner's appointed land agent and has last emailed on the 30th Jun 2026 . The Applicant is not aware of any outstanding matters to agree, and will therefore continue to work with the appointed land agent to progress towards a signed set of terms. Deadline 2 The Applicant's appointed land agent continues to engage with the Landowners appointed land agent, most recently on 18 August 2026 and has scheduled a meeting for 2 September to progress the voluntary agreement. Applicant is confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant's appointed land agent continues to engage with the Landowners appointed land agent, most recently on 22 September 2026 to arrange a meeting. Applicant is confident that the necessary land rights can be acquired by voluntary agreement.
305326 | Peter Darley Stockdale | Mary Foster | 05-045, 06-001, 06-008 | 5, 7 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowner's respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
305327 | Peter James Richardson |  | 07-005, 07-006, 07-007, 07-010, 07-011 | 7 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-07-01 | Negotiations for temporary possession The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with the Landowner following confirmation of the nature of the requirements and rights sought for this land. A draft licence agreement is being prepared and is due to be issued shortly. Procedural Deadline B A populated licence agreement was issued to the Landowner on 3 June 2026. The Applicant's land agent received a signed licence from the Landowner on 22 June 2026.
304613, 304619 | Richard Stephen Atkinson, Joanne Atkinson | Philip Bartle | 12-001 | 12 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners on 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant met with the Landowners appointed land agent on 22 May 2026 to discuss the Heads of Terms. The Applicant is not aware of any outstanding matters to agree, and will therefore continue to work with the appointed land agent to progress towards a signed set of terms. Deadline 2 The Applicant's appointed land agent met with the Landowner's appointed land agent on 27 July 2026. The Heads of Terms were reviewed and the rights being sought were confirmed. Clean documents are to be issued by the Applicant in due course, and as far as the Applicant is concerned, there are no outstanding points. Deadline 3 The Applicant's land agent emailed finalised Heads of Terms documents to the Landowner's appointed land agent on 2 September 2026. The Applicant's land agent followed up with the landowner's agent on 9 September 2026 and 15 September 2026 via email. The Applicant also followed up with the landowner's agent on 15 September by way of telephone call. As of writing this update to the Land and Rights Negotiation Tracker, no update has been received from the landowner's agent. The Applicant will continue to engage with the landowner's agent and progress the Heads of Terms. |  | Joanne Atkinson - RR-0662
304613, 304622 | Richard Stephen Atkinson, Julie Caroline Tye | Philip Bartle | 13-028 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners on 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant met with the Landowners appointed land agent on 22 May 2026 to discuss the Heads of Terms. The Applicant is not aware of any outstanding matters to agree, and will therefore continue to work with the appointed land agent to progress towards a signed set of terms. Deadline 2 The Applicant's appointed land agent met with the Landowner's appointed land agent on 27 July 2026. The Heads of Terms were reviewed and the rights being sought were confirmed. Clean documents are to be issued by the Applicant in due course, and as far as the Applicant is concerned, there are no outstanding points. Deadline 3 The Applicant's land agent emailed finalised Heads of Terms documents to the Landowner's appointed land agent on 2 September 2026. The Applicant's land agent followed up with the landowner's agent on 9 September 2026 and 15 September 2026 via email. The Applicant also followed up with the landowner's agent on 15 September by way of telephone call. As of writing this update to the Land and Rights Negotiation Tracker, no update has been received from the landowner's agent. The Applicant will continue to engage with the landowner's agent and progress the Heads of Terms.
305346, 305363 | Richard Thomas Batty, Sarah Batty | Johnny Cordingley | 13-049, 13-050, 14-021 | 13, 14 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 5, 6, 7, 10B |  |  | 2026-09-29 | Option Holder An option for lease with these Landowners exists for the majority of these plots. Following confirmation of the Order limits, some plots are not covered by that option. The Applicant is therefore working with the Landowners to regularise the position in respect of those remaining plots and is confident that this will be able to be resolved. Procedural Deadline B The Applicant is working with the Landowner to complete a variation to the existing option for lease to ensure all plots are cover by that option. Deadline 2 A small area of Plot 14-021 is not covered by the existing option. The Applicant is working with the Landowner to complete a variation to the existing option and is confident this will be agreed shortly. Deadline 3 The Applicant is continuing to work with the Landowner to complete a variation to the existing option and is confident this will be agreed shortly.
|  |  | 14-020 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 6 |  |  | 2026-08-20 | Option Holder An option for lease with the Landowners exists for the majority of plots within their ownership. Following confirmation of the Order limits, this plot is not covered by that option. The Applicant is therefore working with the Landowners to regularise the position in respect of this remaining plot and is confident that this will be able to be resolved. Procedural Deadline B The Applicant is working with the Landowner to complete a variation to the existing option for lease to ensure all plots are cover by that option. Deadline 2 An option for lease has been exchanged in respect of these plots.
304657, 304658 | Robert Frederick Stoker, Mark Edmund Stoker | Brian Bartle | 16-004 | 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B |  |  | 2026-09-29 | Negotiations for rights The Applicant consulted with the Landowners as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowners following confirmation of the nature of the requirements and rights sought for this land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B Heads of Terms were issued by the Applicant to the landowner on 16 March 2026. The Applicant will continue to engage with the Landowner's appointed land agent in order to progress these Heads of Terms. Deadline 2 The Applicant's appointed land agent met with the Landowner's appointed land agent on 27 July 2026 to discuss and progress the Heads of Terms. There were several actions resulting from the meeting, and progress has been made. The Applicant has will be reissuing updated Heads of Terms in due course so that the Landowners land agent can report to their client. Deadline 3 The Applicant reissued Heads of Terms to the Landowners land agent on 2 September 2026. The Applicant called the Landowners land agent for an update on 15 September 2026, 18 September 2026, and 21 September 2026. The Applicant also followed up with emails on 9 September 2026, and 24 September 2026. As of this Land and Rights Negotiation Tracker update, the Applicant has not received any update from the Landowners land agent in relation to his clients Heads of Terms. The Applicant will continue to engage with the Landowners land agent so as to move Heads of Terms forward.
305356 | Rosemarie Claire Tait | James Thompson | 20-014, 20-020 | 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 16 December 2025 and 21 January 2026 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B Revised Heads of Terms were issued to the Landowner's appointed land agent on 12 May 2026. The Applicant's appointed land agent will continue to engage with the Landowner and their appointed land agent and remains confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent is continuing to engage with the Landowner and their appointed land agent, most recently on 18 August 2026 regarding Heads of Terms. The Applicant's appointed land agent has offered to meet with the Landowner's appointed land agent to address the outstanding clauses within the Heads of Terms. The Applicant remains confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant's appointed land agent continues to engage with the Landowner and their appointed land agent regarding the Heads of Terms. Most recently, on 21 September 2026 and again on 29 September 2026, the Applicant's appointed land agent contacted the Landowner's appointed land agent to request a meeting to discuss the outstanding provisions of the Heads of Terms and progress negotiations. The Applicant remains confident that the necessary land rights can be acquired by voluntary agreement. |  | Rosie Tait - RR-1215
|  |  | 20-017, 20-019 | 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 16 December 2025 and 21 January 2026 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B Revised Heads of Terms were issued to the Landowner's appointed land agent on 12 May 2026. The Applicant's appointed land agent will continue to engage with the Landowner and their appointed land agent and remains confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent is continuing to engage with the Landowner and their appointed land agent, most recently on 18 August 2026 regarding Heads of Terms. The Applicant's appointed land agent has offered to meet with the Landowner's appointed land agent to address the outstanding clauses within the Heads of Terms. The Applicant remains confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant's appointed land agent continues to engage with the Landowner and their appointed land agent regarding the Heads of Terms. Most recently, on 21 September 2026 and again on 29 September 2026, the Applicant's appointed land agent contacted the Landowner's appointed land agent to request a meeting to discuss the outstanding provisions of the Heads of Terms and progress negotiations. The Applicant remains confident that the necessary land rights can be acquired by voluntary agreement.
325414, 325415 | Stephen Batty, Joyce Batty | Alexander Ireton | 13-048 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 10B |  |  | 2026-10-02 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 20 January 2026 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's land agent has continued to engage with the Landowner's appointed land agent most recently on 1 July 2026 to progress voluntary negotiations. The Applicant will continue to engage with the Landowner and their appointment land agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent held a meeting with the Landowner's appointed land agent on 18 August 2026. The Applicant understands the Landowner's appointed agent is in dialogue with the Landowner and will revert to the Applicant shortly with a response on the voluntary agreement. The Applicant's appointed land agent has a further meeting scheduled for 26 August 2026 with the Landowner's appointed land agent to progress the voluntary agreement. The Applicant will continue to engage with the Landowners and their agent and is confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant has progressed Heads of Terms negotiations with the Landowner’s appointed land agent. The Applicant received comments on the Heads of Terms from Landowner’s appointed land agent on 23rd September 2026. The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 2 October 2026. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this.
304697 | Stephen Mark Stockdale | Johnny Cordingley | 06-014, 07-022, 08-028, 08-035 | 6, 7, 8 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 7 |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 and 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowner's appointed land agent and most recently held a meeting on 15 June 2026. The Applicant will continue to engage with the Landowner and their land agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed agent continues to engage with the Landowner's appointed land agent and most recently corresponded on 20 August 2026 re-iterating the offer to meet with the Landowner in order to understand the outstanding points of difference and progress the voluntary agreement. The Applicant will continue to engage with the Landowner and their appointed land agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant's appointed land agent requested an update from the Landowner's appointed land agent via telephone and email, most recently on 29 September 2026. As of this Land and Rights Negotiation Tracker update, the Applicant has not received any update from the Landowner's land agent in relation to the Heads of Terms. The Applicant will continue to engage with the Landowners land agent so as to move the Heads of Terms forward.
|  |  | 07-009, 08-030, 08-032, 08-034, 08-036 | 7, 8 | As described in the Book of Reference | Land is subject to Temporary Possession | 7, 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 2 December 2025 and 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed agent continues to engage with the Landowner's appointed land agent and most recently held a meeting on 15 June 2026. The Applicant will continue to engage with the Landowner and their land agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed agent continues to engage with the Landowner's appointed land agent and most recently corresponded on 20 August 2026 re-iterating the offer to meet with the Landowner in order to understand the outstanding points of difference and progress the voluntary agreement. The Applicant will continue to engage with the Landowner and their appointed land agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant's appointed land agent requested an update from the Landowner's appointed land agent via telephone and email, most recently on 29 September 2026. As of this Land and Rights Negotiation Tracker update, the Applicant has not received any update from the Landowner's land agent in relation to the Heads of Terms. The Applicant will continue to engage with the Landowners land agent so as to move the Heads of Terms forward.
329022, 329023 | Stephen Michael Thompson, Mark Stuart Thompson | Mary Foster | 10-072, 11-024, 11-028, 11-032, 15-011, 16-019 | 10, 11, 15, 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A, 8B |  |  | 2026-09-29 | Negotiations for rights The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowner's respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
|  |  | 11-009, 11-012 | 11 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowner's respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
369623 | Steve Shepard |  | 06-003 | 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Deadline 2 Following a refresh of HM Land Registry data, landownership of this plot has been confirmed. Heads of Terms are in the process of being drafted and the Applicant's appointed land agent has attempted to make contact with the Landowner, most recently on 20 August 2026. Deadline 3 The Applicant’s appointed land agent has drafted Heads of Terms and has made multiple attempts to arrange a meeting to discuss the proposed terms prior to issuing. Most recently, the Landowner was contacted on 24 September 2026 in an effort to arrange a meeting and facilitate progress towards a voluntary agreement. The Applicant remains confident that the necessary land rights can be secured through voluntary agreement.
153114 | Sybil Elizabeth Platt | Thomas Cooper | 12-003, 12-061, 12-061a, 12-061b, 12-076, 13-027, 18-001b, 18-001c, 18-004, 18-005a, 18-006, 19-015, 19-019, 19-020 | 12, 13, 18, 19 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 8A, 8B, 10B |  |  | 2026-10-13 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 16 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent has attempted to contact the Landowner's appointed land agent regularly, most recently on 19 June 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent has attempted to contacted the Landowner's appointed land agent regularly, most recently on 18 August 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant's appointed land agent held a meeting with the Landowner's appointed Land Agent on 1 October 2026 to progress negotiations of the Heads of Terms. Commercials are the main outstanding point of difference. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement. Change Application The Applicant's appointed Land Agent called the Landowner's appointed Land Agent to advise of the submission of the Change Application. This was followed up in writing via a letter issued directly to the Landowner. The Applicant will continue to seek to engage with the Landowner in respect of the Change Application and ensure when appropriate, the Heads of Terms will be updated to reflect any changes to the voluntary agreement sought.
|  |  | 12-004, 18-005 | 12, 18 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-10-13 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 16 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed agent has attempted to contact the Landowner's appointed land agent regularly, most recently on 19 June 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent has attempted to contacted the Landowner's appointed land agent regularly, most recently on 18 August 2026, to progress the Heads of Terms. The Applicant remains committed to engaging with the Landowner's and their land agent and remains confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant's appointed land agent held a meeting with the Landowner's appointed Land Agent on 1 October 2026 to progress negotiations of the Heads of Terms. Commercials are the main outstanding point of difference. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement. Change Application The Applicant's appointed Land Agent called the Landowner's appointed Land Agent to advise of the submission of the Change Application. This was followed up in writing via a letter issued directly to the Landowner. The Applicant will continue to seek to engage with the Landowner in respect of the Change Application and ensure when appropriate, the Heads of Terms will be updated to reflect any changes to the voluntary agreement sought.
389464, 305349, 318071, 324933 | Alan Frank Mitchell, Robert Ian Pratt, Keith William Revis, Janet Schofield | Johnny Cordingley | 05-025 | 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant has received signed Heads of Terms on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
289871, 305132, 325051, 353699 | Michael Donald Parkin, Antony Hebden Walter Parkin, The Executor of the Estate of the Late Donald Parkin, The Executor of the Estate of the Late Rosemary Wendy Parkin | Mary Foster | 12-033 | 12 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 2 December 2025 and 18 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B Signed Heads of Terms were received on 29 January 2026. Legal representatives have been instructed and negotiations of the legals documents are progressing. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
324871, 328607, 328608, 330846 | The Executor of the Estate of the Late Gilbert Firth, The Executor of the Estate of the Late Roland Firth, Julie Horner, Tim Gaskell | Michael Townend | 05-012, 05-013, 05-014 | 5 | As described in the Book of Reference | Land is subject to Temporary Possession | 7 |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 4 December 2025 and the Applicant held a meeting with the Landowners' appointed agent 28 January 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant held a meeting with the Landowners' appointed land agent on 22 May 2026, which has led to agreement on a number of outstanding items within the Heads of Terms. Revised Heads of Terms are due to be issued shortly, and the Applicant remains confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their land agent to achieve this. Deadline 2 The Applicant and the Applicant's appointed agent met with the Landowner's appointed land agent on 7 August 2026 to discuss the remaining outstanding items within the Heads of Terms. The parties agreed the final amendments required to the Heads of Terms and revised Heads of Terms are due to be issued to the Landowner shortly. The Applicant is confident that the necessary land rights can be acquired by voluntary agreement and will continue to engage with the Landowners and their appointed land agent to achieve this. Deadline 3 The Applicant issued revised Heads of Terms to the Landowner's appointed land agent on 25 September 2026 following engagement with the Landowner's appointed land agent. The Applicant is confident that voluntary agreement can be reached and will continue to engage with the Landowner's appointed land agent to achieve this.
305340, 318156 | Richard Andrew Bramley, The Executor of the Estate of the Late John Richard Bramley | Stephen Burley | 05-007 | 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 19 August 2025 and 10 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B There has been extensive dialogue between the Landowner's appointed land agent and the Applicant. The Landowner's appointed land agent has reported to the Applicant that the Heads of Terms are agreed, however a signed document has, at the time of updating this tracker, not been received. The Applicant will continue to engage with the Landowner's appointed land agent to arrange for signed documents to be provided. Deadline 2 The Applicant's appointed land agent met with the Landowner's land agent on 27 July 2026. The purpose of the meeting was to update on the status of the Heads of Terms. The Heads of Terms document has not been signed, and as far as the Applicant is aware, there are no outstanding points. The Landowners land agent has been asked to obtain and update and the Applicant is waiting on this, and is hopeful the Heads of Terms can progress to signature. Deadline 3 Further to the Applicant's appointed land agent's meeting with the Landowner's appointed land agent, the Applicant's land agent followed up on 25 August 2026, and on 9 September 2026 via email. The Applicant's land agent followed up via telephone call on 15 September 2026, where the Landowner's land agent requested that the Applicant contact his client directly. The Applicant's land agent spoke to the Landowner on 28 September 2026 to discuss the Heads of Terms, and to offer a meeting in person. The Landowner expressed their frustration at the scheme, and suggested that he and the Applicant's land agent speak in a months' time. The Applicant's land agent followed up with the landowners land agent on 28 September 2026 in a bid to move Heads of Terms negotiations forward.
|  |  | 05-010 | 5 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant issued populated Heads of Terms to the Landowners on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowners' appointed agent on 19 August 2025 and 10 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowners and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B There has been extensive dialogue between the Landowner's appointed land agent and the Applicant. The Landowner's appointed land agent has reported to the Applicant that the Heads of Terms are agreed, however a signed document has, at the time of updating this tracker, not been received. The Applicant will continue to engage with the Landowner's appointed land agent to arrange for signed documents to be provided. Deadline 2 The Applicant's appointed land agent met with the Landowner's land agent on 27 July 2026. The purpose of the meeting was to update on the status of the Heads of Terms. The Heads of Terms document has not been signed, and as far as the Applicant is aware, there are no outstanding points. The Landowners land agent has been asked to obtain and update and the Applicant is waiting on this, and is hopeful the Heads of Terms can progress to signature. Deadline 3 Further to the Applicant's appointed land agent's meeting with the Landowner's appointed land agent, the Applicant's land agent followed up on 25 August 2026, and on 9 September 2026 via email. The Applicant's land agent followed up via telephone call on 15 September 2026, where the Landowner's land agent requested that the Applicant contact his client directly. The Applicant's land agent spoke to the Landowner on 28 September 2026 to discuss the Heads of Terms, and to offer a meeting in person. The Landowner expressed their frustration at the scheme, and suggested that he and the Applicant's land agent speak in a months' time. The Applicant's land agent followed up with the landowners land agent on 28 September 2026 in a bid to move Heads of Terms negotiations forward.
322852 | The Executor of the Estate of the Late Reginald Geoffrey Makin | Brian Bartle | 20-001, 21-030, 21-036 | 20, 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent held a meeting with the Landowner's appointed agent on 8 September 2025 and 1 December 2025 to progress landowner specific aspects of the HoTs. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant is continuing to engage with the landowners land agent to fully understand the current status of the land ownership. The Applicant will continue to work with the land agent to establish those ownership details, and if any rights are required from the landowner. Deadline 2 The Applicant's appointed land agent met with the Landowner's land agent on 27 July 2026. The purpose of the meeting was to clarify the ownership information for the landowner. The Heads of Terms document has not been signed, and as far as the Applicant is aware, there are no outstanding points. The Landowners land agent has been asked to obtain and update and the Applicant is waiting on this, and is hopeful the Heads of Terms can progress to signature. Deadline 3 The Applicant has continued to engage with the landowner's appointed land agent, most recently receiving email correspondence from the land agent confirming the ownership boundary. The Applicant will continue to work with the appointed land agent to progress the Heads of Terms.
305102 | The King's Most Excellent Majesty in Right of His Crown | Ellie Brown | 06-010 | 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-10-05 | Negotiations for rights The Applicant issued populated Heads of Terms to the Landowner on 6 November 2025. The Applicant's appointed land agent continues to engage with the Interest's appointment agent and has a meeting scheduled for 2 February 2026. The Applicant will continue to engage with the Landowner's appointment agent and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent held a meeting with the Landowner's appointed land agent on 13 February 2026. Further responses were provided to the Landowner's agent on 9 April 2026 and most recently followed up on 26 June 2026. The Applicant will continue to engage with the Landowner's appointment land agent and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent continues to engage with the Landowner's appointed land agent and understands the only outstanding point of difference is commercials. The Applicant's appointed land agent most recently followed this up with the Landowner's appointed land agent on 18 August 2026 and remains confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant's appointed land agent continues attempt to contact the Landowner's appointed agent, most recently on 29 September 2026. The Landowner's agent confirmed a response would be provided shortly. As of this Land and Rights Negotiation Tracker update, the Applicant has not received any update from the Landowner's land agent since 6 July 2026 in relation to the Heads of Terms. The Applicant will continue to engage with the Landowners land agent so as to move Heads of Terms forward.
213890, 305105 | The Official Custodian For Charities, Hambleton United Charities | Mary Foster | 11-027 | 11 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
305108 | The York Diocesan Board of Finance Limited | Susannah Pick | 10-029, 12-059 | 10, 12 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 8A, 8B, 10B |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 3 February 2026. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowner and most recently corresponded on 2 July 2026. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent continues to engage with the landowner and last emailed on 18 August 2026 to arrange a meeting. The Applicant remains confident that all required land rights can be acquired by voluntary agreement. Deadline 3 The Applicant's appointed land agent held a meeting with the Landowner's appointed land agent on 3 September 2026. The Applicant understands the Landowner's appointed agent is in dialogue with the Landowner and will revert to the Applicant shortly with a response on the voluntary agreement. The Applicant will continue to engage with the Landowner and their agent and is confident that the necessary land rights can be acquired by voluntary agreement.
|  |  | 10-021, 10-030 | 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 3 February 2026. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent continues to engage with the Landowner and most recently corresponded on 2 July 2026. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent continues to engage with the landowner and last emailed on 18 August 2026 to arrange a meeting. The Applicant remains confident that all required land rights can be acquired by voluntary agreement. Deadline 3 The Applicant's appointed land agent held a meeting with the Landowner's appointed land agent on 3 September 2026. The Applicant understands the Landowner's appointed agent is in dialogue with the Landowner and will revert to the Applicant shortly with a response on the voluntary agreement. The Applicant will continue to engage with the Landowners and their agent and is confident that the necessary land rights can be acquired by voluntary agreement.
244074, 305258, 305319 | Thomas Swan Thirsk, Julian Richard Thirsk, Patricia Thirsk | Johnny Cordingley | 10-001 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-09-29 | Negotiations for rights The Applicant has received signed Heads of Terms on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
|  |  | 09-023 | 9 | As described in the Book of Reference | Land is subject to Temporary Possession | 7, 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant has received signed HoTs on 29th January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
244074, 305319 | Thomas Swan Thirsk, Patricia Thirsk | Johnny Cordingley | 09-012, 09-014 | 9 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-09-29 | Negotiations for rights The Applicant has received signed Heads of Terms on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
|  |  | 09-008, 09-011 | 9 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
162804 | Timothy Brian Hey | Matthew Watson | 12-047 | 12 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-09-29 | Negotiations for rights The Applicant's appointed land agent received verbal confirmation the Heads of Terms are in an agreed format on 29 January 2026 from the Landowner's appointed land agent and is awaiting signed copies of the Heads of Terms. Procedural Deadline B The Applicant received signed Heads of Terms on the 16 March 2026. The Applicant is awaiting confirmation of the Landowner's legal representative from the Landowner. The Applicant's land agent has contacted the Landowner's appointed agent regularly to obtain these details, most recently on the 30 June 2026. Deadline 2 The Applicant's appointed land agent has contacted the landowner to obtain confirmation regarding the Landowner's legal representative. Legal representatives are to start progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents. |  | Tim Hey - RR-1391
|  |  | 12-045, 12-046 | 12 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant's appointed land agent received verbal confirmation the Heads of Terms are in an agreed format on 29 January 2026 from the Landowner's appointed land agent and is awaiting signed copies of the Heads of Terms Procedural Deadline B The Applicant received signed Heads of Terms on the 16 March 2026. The Applicant is awaiting confirmation of the Landowner's legal representative from the Landowner. The Applicant's land agent has contacted the Landowner's appointed agent regularly to obtain these details, most recently on the 30 June 2026. Deadline 2 The Applicant's appointed land agent has contacted the landowner to obtain confirmation regarding the Landowner's legal representative. Legal representatives are to start progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
304610, 304611, 304612 | Trevor Ernest Millington, Graham Tune Millington, Frank William Millington | Mary Foster | 10-031, 10-036, 10-064, 10-071, 10-081, 10-082, 10-083, 11-022, 16-015, 16-016 | 10, 11, 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A, 8B |  |  | 2026-09-29 | Negotiations for rights The Applicant has received signed Heads of Terms on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives. Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
|  |  | 10-032, 10-033, 10-035, 10-037, 11-017, 11-021 | 10, 11 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-09-29 | Negotiations for temporary possession The Applicant has received signed HoTs on 29 January 2026 and will now progress negotiations of the legal documents through the Landowners' respective legal representatives Procedural Deadline B Legal representatives have been instructed and negotiations of the legals documents are progressing. Deadline 2 Legal representatives are progressing the legal documents. Deadline 3 Legal representatives are progressing the legal documents.
339901 | Wendy Terezia Tomlinson | Chris Tyther / Joe Bonsor | 03-009, 03-010, 03-017h | 3 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-10-13 | Negotiations for rights The Applicant consulted with the Landowner as part of the pre-application consultation processes. The Applicant is commencing negotiations with this Landowner following confirmation of the nature of the requirements and rights sought for this land. Heads of Terms are being prepared and are due to be issued shortly. Procedural Deadline B The Applicant's land agent continues to have productive dialogue with the Landowner's appointed land agent regarding the Heads of Terms. Land Agent fees remain outstanding and the Applicant's land agent and the Landowner's land agent are working together to resolve this matter. The Applicant will continue to engage with the Landowner and their land agent and is confident that the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant has corresponded with the Landowner and their appointed land agent and has offered a meeting to progress the voluntary agreement. Following correspondence from the Landowners' appointed land agent, the Applicant understands the Landowner' appointed agent is in dialogue with the Landowner and will revert to the Applicant shortly with a response on the voluntary agreement. The Applicant will continue to engage with the Landowners and their appointed agent and is confident that the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant received correspondence from the Landowner on 1 September 2026 requesting the issues raised be responded to through the examination process before arranging a site meeting with the Applicant. The Applicant responded further re-iterating their willingness to reach a voluntary agreement and resolve outstanding matters. Change Application The Applicant's appointed Land Agent called the Landowner's appointed Land Agent to advise of the submission of the Change Application. This was followed up in writing via a letter issued directly to the Landowner. The Applicant will continue to seek to engage with the Landowner in respect of the Change Application and ensure when appropriate, the Heads of Terms will be updated to reflect any changes to the voluntary agreement sought. |  | Wendy Tomlinson - RR-1444 | Wendy Tomlinson - REP1-053 and REP1-054
305109 | Yorkshire Water Services Limited |  | 03-003, 05-001, 05-033 | 3, 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-09-29 | Negotiations for rights The Applicant issued populated Heads of Terms to the landowner on 3 February 2026. The Applicant will continue to engage with the Landowner and is confident the necessary land rights can be acquired by voluntary agreement. Procedural Deadline B The Applicant's appointed land agent has attempted to contact the Landowner, will continue to engage and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 2 The Applicant's appointed land agent continues to make attempts to contact the Landowner most recently on the 20 August 2026. The Applicant's appointed land agent will continue to engage and is confident the necessary land rights can be acquired by voluntary agreement. Deadline 3 The Applicant's appointed land agent continues to make attempts to contact the Landowner most recently on the 21 September 2026. As of this Land and Rights Negotiation Tracker update, the Applicant has not received any update from the Landowners land agent in relation to the Heads of Terms. The Applicant will continue to engage with the Landowners land agent so as to move Heads of Terms forward.

## Part 2 SU Crown
PART 2
Ref | Affected Party | Agent/ Representative | Book of Ref. Plot No. | Plan Ref. No. | Description of Land | Description of Rights Requested | Works Number(s) | Interest Type | Is the relevant body a Statutory Undertaker and is the land operational? | Status of Objection | Notes | Last Updated | Summary of Negotiations | Protective Provision (PPs) Status | Commercial Agreement Status (if required) | Complete | Relevant Rep Ref No. | Written Rep Ref No. | Ref No. for any other docs submitted by IP/AP. | Ref No. for Applicant's Response
119431 | Canal & River Trust |  | 06-010 | 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Rights | Yes |  |  | 2026-08-26 | The Applicant has agreed bespoke PPs with the Canal and River Trust and negotiations are complete. | Bespoke PPs for the benefit of the Canal and River Trust are now agreed and are included in Schedule 15 of the dDCO at Deadline 2 | N/A |  | Canal and River Trust - RR-0177
139920 | Centrica PLC |  | 05-046, 05-047, 05-049, 07-026, 10-064, 11-022, 11-025, 11-030, 18-001b, 18-001c | 5, 7, 10, 11 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A | Rights | Yes |  |  | 2026-10-13 | Change Application The Applicant sent a letter to Centrica PLC setting out information regarding the relevant proposed changes on 9 October 2026 | Bespoke PPs not required. Gas undertakers will have the benefit of the generic protective provisions for gas undertakers in the draft DCO | N/A
|  |  | 07-027, 11-008, 11-010, 11-021 | 7, 11 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights
370091 | Constantine Energy Storage |  | 21-032, 21-032a, 21-032b, 21-033 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5 | Rights | No |  |  | 2026-09-30 | The Applicant met with Constantine Energy Storage (parent company of HD777FRY Limited) on 27 April 2026 to discuss the potential interface between the Proposed Deevelopment and the Affected Party's BESS. The Applicant's current position is that bespoke PPs are not required as HD777FRY Ltd (as the generation licence holder) will have the benefit of the protective provisions for electronic communications code operators included in the dDCO. The Applicant emailed Constantine Energy on 23 September 2026 | Bespoke PPs not required. Operators of electronic communications code networks will have the benefit of the protective provisions for electronic communications code operators set out in the draft DCO. |  |  | HD777FRY Limited - RR-0538
|  |  | 21-034 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5 | Leasehold
|  |  | 21-035 | 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Leasehold
7261 | Cornerstone Telecommunications Infrastructure Limited |  | 05-029, 16-004 | 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Rights | No |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Operators of electronic communications code networks will have the benefit of the protective provisions for electronic communications code operators set out in the draft DCO. | N/A
331938 | EE Limited |  | 10-036 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Rights | No |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Operators of electronic communications code networks will have the benefit of the protective provisions for electronic communications code operators set out in the draft DCO. | N/A
|  |  | 10-037 | 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights
20333 | Environment Agency |  | 06-009, 06-011, 06-012, 06-016 | 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Freehold | Yes |  |  | 2026-09-30 | The Applicant will continue to engage with the Environment Agency and is confident that any necessary land rights can be acquired by voluntary agreement. See Part 1 of this Land Rights Tracker for further details. Procedural Deadline B The Applicant received signed Heads of Terms on 26 June 2026 and will now progress negotiations on the voluntary property agreement with the EA. This does not need to be completed prior to the end of Examination. The Applicant has submitted a SoCG at Deadline 3 recording the latest position between the parties. | Bespoke PPs for the benefit of the Environment Agency are now agreed and are included at Part 4 of Schedule 15 of the dDCO. At Deadline 2, minor amednments were made to these PPs at the EA's request. As the PPs are agreed, the EA has provided its consent under section 150 of the Planning Act 2008 in article 6 of the draft DCO. This consent is recorded in the SoCG with the EA submitted at Deadline 3. | N/A |  | Environment Agency - RR-0528 and RR-0419 | REP1-018, REP1-019
|  |  | 05-048, 06-004, 06-007, 06-010, 06-015, 06-017, 06-018, 06-019, 06-022, 06-023 | 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Rights | Yes
105595 | Gigaclear Limited |  | 10-039, 10-041, 13-023 | 10, 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A, 8B | Apparatus | No |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Operators of electronic communications code networks will have the benefit of the protective provisions for electronic communications code operators set out in the draft DCO. | N/A
|  |  | 10-018, 10-022, 10-046, 10-047, 10-050, 10-085, 11-001, 13-016, 13-018, 13-024, 13-025, 20-044 | 10, 11, 13, 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 5, 8A, 8B | Apparatus
|  |  | 10-048 | 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights
325427 | HD777FRY Ltd |  | 21-035 | 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Leasehold | Yes |  |  | 2026-08-27 | The Applicant met with Constantine Energy Storage (parent company of HD777FRY Limited) on 27 April 2026 to discuss the potential interface between the Proposed Development and the Affected Party's BESS. The Applicant's current position is that bespoke PPs are not required as HD777FRY Ltd (as the generation licence holder) will have the benefit of the protective provisions for electronic communications code operators included in the dDCO. | Bespoke PPs not required. Electricity undertakers will benefit from the Protective Provisions for electricity undertakers included in the draft DCO | N/A |  | HD777FRY Limited - RR-1380 and RR-0528
|  |  | 20-001, 20-002, 21-030, 21-031, 21-036, 21-040 | 20, 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Rights
|  |  | 21-033, 21-034 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5 | Leasehold
|  |  | 21-032, 21-032a, 21-032b | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5 | Rights
104483 | KCOM Group Limited |  | 10-036, 10-039, 10-041, 10-043, 10-044 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A | Apparatus | No |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Operators of electronic communications code networks will have the benefit of the protective provisions for electronic communications code operators set out in the draft DCO. | N/A
|  |  | 08-039, 10-046, 10-047, 10-048, 10-050 | 8, 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Apparatus
331952 | Kelda Group Limited |  | 05-030, 06-011,13-047 | 5, 6, 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A | Rights | Yes |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Water and sewerage undertakers will have the benefit of the protective provisions set out in the draft DCO | N/A
51929 | Leeds City Council |  | 11-035, 11-036, 12-047 | 11, 12 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A | Rights | Yes |  |  | 2026-02-04 | N/A | As street/highways authority, the Council will have the benefit of having approvals under the relevant DCO articles. No Protective Provisions are proposed at this time | N/A
|  |  | 12-045, 12-046, 13-047 | 12, 13 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights | Yes
333276 | Lumen Technologies UK Limited |  | 10-015a | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8A | Rights | Yes |  |  | 2026-10-13 | Change Application The Applicant sent a letter to Lumen Technologies UK Limited setting out information regarding the relevant proposed changes on 9 October 2026
198340 | National Gas Transmission PLC |  | 12-034, 12-052, 12-053, 12-055, 12-060, 12-071, 12-072, 18-008, 18-013, 18-014, 18-015 | 12, 18 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 3, 5, 6, 7, 8B, 10B | Rights | Yes |  |  | 2026-10-13 | Discussions are ongoing with National Gas Transmission plc regarding the form of protective provisions. The Applicant has submitted a SoCG at Deadline 3 recording the latest position between the parties. Change Application The Applicant sent a letter to National Gas Transmission PLC setting out information regarding the relevant proposed changes on 9 October 2026 | Draft protective provisions for the benefit of National Gas Transmission plc are included in the draft DCO and are under discussion. The Applicant is aware that the Protective Provisions currently drafted and included at Part 7 of Schedule15 of the Draft DCO depart from NGT’s standard Protective Provisions. The Applicant will continue to negotiate bespoke protections and any commercial agreement necessary with NGT, in the context of the broader Island Green Power (IGP) portfolio/NGT negotiations. |  |  | National Gas Transmission PLC - RR-1036 and RR-1039 | REP1-021
|  |  | 05-048, 06-001, 05-049, 06-002, 06-003, 11-036, 15-009, 16-003, 16-004 | 5, 6, 11, 15, 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8B | Apparatus | Yes
|  |  | 05-046, 05-047, 10-064, 10-072, 11-018, 11-022, 11-024, 11-028, 11-030, 11-031, 11-032, 11-033, 11-036, 18-001, 13-008, 13-009, 13-010, 15-005, 15-006, 15-011, 15-004, 15-009, 15-010, 16-003, 16-004, 16-007, 16-008, 16-011, 18-001a, 18-001d, 18-002, 18-002a,18-002b, 18-011 | 5, 10, 11, 12, 13, 15, 16, 18 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 7, 8A, 8B, 10B | Rights | Yes
|  |  | 11-003, 11-009, 11-010, 11-012, 11-020, 11-021, 11-034, 13-006, 13-011, 15-014 | 11, 13, 15 | As described in the Book of Reference | Land is subject to Temporary Possession | 7, 8A | Rights | Yes
305093 | National Grid Electricity Transmission PLC |  | 12-034, 12-053, 12-054, 12-055, 12-074, 18-013 | 12, 18 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 3, 5, 6, 7, 8B, 10B | Apparatus | Yes |  |  | 2026-10-13 | The Applicant will continue to engage with National Grid Electricity Transmission plc and is confident that any necessary land rights can be acquired by voluntary agreement. See Part 1 of this Land Rights Tracker for further details. The Applicant has submitted a SoCG at Deadline 3 recording the latest position between the parties. Change Application The Applicant sent a letter to National Grid Electricity Transmission PLC setting out information regarding the relevant proposed changes on 9 October 2026 | Draft protective provisions for the benefit of National Grid Electricity Transmission plc are included in the draft DCO and are under discussion. The Applicant is aware that the Protective Provisions currently drafted and included at Part 9 of Schedule15 of the Draft DCO are not in a form acceptable to NGET. The Applicant will continue to negotiate bespoke protections and any commercial agreement necessary with NGET, in the context of the broader Island Green Power (IGP) portfolio/NGET negotiations |  |  | National Grid Electricity Transmission PLC - RR-1037 and RR-0437 | REP1-022
|  |  | 12-034, 12-052, 12-055, 12-060, 12-071, 12-072, 13-021, 13-035, 14-028, 18-013, 18-014, 18-015 | 12, 13, 14, 18 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 2, 3, 5, 6, 7, 8B, 10B | Rights | Yes
|  |  | 18-006, 18-011, 20-001, 21-002, 21-006, 21-008, 21-009, 21-016, 21-017, 21-022, 21-027, 21-031, 21-035, 21-040 | 18, 20, 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 4, 5, 8A, 10B | Apparatus | Yes
|  |  | 21-029, 21-031, 21-035, 21-040 | 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Freehold | Yes
|  |  | 18-001, 18-001a, 18-001d, 18-003, 18-004, 13-020, 13-022, 13-029, 13-030, 18-002, 18-002a, 18-002b, 18-011, 19-011, 19-013, 20-001, 20-002, 21-006, 21-030, 21-036 | 12, 13, 18, 19, 20, 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 8A, 8B, 10B | Rights | Yes
|  |  | 13-019, 18-005, 20-005, 20-044, 20-045, 21-037, 21-038, 21-039 | 18, 20, 21 | As described in the Book of Reference | Land is subject to Temporary Possession | 5, 8A | Apparatus | Yes
|  |  | 21-013, 21-019, 21-032, 21-033, 21-034 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5, 8A | Apparatus | Yes
|  |  | 21-013, 21-019, 21-032, 21-033, 21-034 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5, 8A | Freehold | Yes
22908 | National Highways Limited |  | 05-019, 05-021, 05-024, 05-026, 05-028, 05-034, 05-035, 05-037, 10-052, 10-053, 10-054, 10-056, 10-059, 10-060, 10-062 | 5, 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A | Freehold | Yes |  |  | 2026-09-30 | The Applicant is in discussions with National Highways over the technical aspects of the crossing of the strategic road network. The Applicant provided NH with requested data on 30 July 2026 and further information about the nature of the works in the various plots where NH has a subsoil interest on 2 October 2026. Updated draft PPs have been with NH for review since 7 September 2026. The Applicant will continue to engage with National Highways and is confident that any necessary land rights can be acquired by voluntary agreement . See Part 1 of this Land Rights Tracker for further details. The Applicant has submitted a SoCG at Deadline 3 recording the latest position between the parties. | Draft protective provisions for the benefit of National Highways Limited are included in the draft DCO and are under discussion. |  |  | National Highways - RR-0177 and RR-1038 | REP1-023, REP1-024
|  |  | 10-063, 10-064, 10-065, 10-067, 10-071, 10-083, 20-014, 20-020, 20-025 | 10, 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A | Rights | Yes
|  |  | 05-036, 05-038, 05-039, 05-041, 10-045, 10-047, 10-050, 10-051, 10-069 | 5, 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Freehold | Yes
|  |  | 11-017, 20-017, 20-019, 20-040, 20-041 | 11, 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights | Yes
309564 | Netomnia Limited |  | 10-043 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A | Apparatus | No |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Operators of electronic communications code networks will have the benefit of the protective provisions for electronic communications code operators set out in the draft DCO.
|  |  | 10-018, 10-021, 10-022, 11-001 | 10, 11 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Apparatus
7310 | Network Rail Infrastructure Limited |  | 14-002, 14-003, 14-004 | 14 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 6, 10B | Apparatus | Yes |  |  | 2026-10-13 | The Applicant is in discussions with Network Rail over the technical aspects of the crossing of the railway. The Applicant will continue to engage with Network Rail and is confident that any necessary land rights can be acquired by voluntary agreement. Draft Protective Provisions have been with NRIL's solicitors for review since 10 July 2026. The Applicant has checked in regularly since then, and most recently on 28 September 2026. See Part 1 of this Land Rights Tracker for further details. The Applicant has submitted a SoCG at Deadline 3 recording the latest position between the parties. Change Application The Applicant sent a letter to Network Rail Infrastructure Limited setting out information regarding the relevant proposed changes on 9 October 2026 | Draft protective provisions for the benefit of Network Rail Infrastructure Limited are included in the draft DCO and are under discussion. |  |  | Network Rail Infrastructure Limited - RR-1298 and RR-1045 | REP2-122
|  |  | 14-001, 14-002, 14-003, 14-004, 14-017, 15-002 | 14, 15 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 6, 7, 8B, 10B | Rights | Yes
|  |  | 10-016, 10-016a, 10-016b, 10-023, 10-025, 10-063, 10-070, 10-072, 10-076, 10-078, 15-003, 15-007, 20-013 | 10, 15, 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A, 8B | Apparatus | Yes
|  |  | 16-001, 10-073, 10-074 | 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B | Freehold | Yes
|  |  | 10-052, 10-053, 10-071, 10-083, 11-024, 11-028, 11-032, 14-014, 15-004, 15-005, 16-003, 16-019, 17-006, 17-010, 17-012 | 10, 11, 14, 15, 16, 17 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 8A, 8B | Rights | Yes
|  |  | 10-015, 10-016, 10-017; 10-025, 10-052, 10-053, 10-070, 14-014, 15-003, 16-019, 20-013 | 10, 14, 15, 16, 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 8A, 8B | Unregistered Freeholder | Yes
|  |  | 10-032, 10-033, 10-034 | 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Apparatus | Yes
|  |  | 11-009, 11-012, 11-017, 17-008 | 10, 11, 17 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A, 8B | Rights | Yes
249688 | North Yorkshire Council |  | 01-030, 13-021, 13-035 | 1, 13 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 2, 3, 5, 6, 7, 9A | Rights | Yes |  |  | 2026-02-04 | N/A | As street/highways authority, the Council will have the benefit of having approvals under the relevant DCO articles. No Protective Provisions are proposed at this time |  |  | North Yorkshire Council - RR-1075 | North Yorkshire Council - REP1-006, REP1-007 and REP1-008
|  |  | 05-027, 05-028, 05-029, 10-059, 10-083 | 5, 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A | Apparatus | Yes
|  |  | 05-002, 05-003, 05-005, 05-006, 05-018, 05-020, 05-025, 05-029, 06-010, 08-037, 09-001, 09-002, 09-003, 09-004, 10-031, 13-020, 13-022, 13-029, 13-030 | 5, 6, 8, 9, 10, 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 8A, 8B | Rights | Yes
|  |  | 03-061, 04-004, 05-038, 05-040, 05-041, 07-002, 07-003, 10-022, 10-046, 10-069, 11-001 | 3, 5, 7, 10, 11 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Apparatus | Yes
|  |  | 03-053, 08-038, 22-004 | 3, 8, 22 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Freehold | Yes
|  |  | 09-006, 09-009, 10-012, 10-047, 10-050, 13-019 | 9, 10, 13 | As described in the Book of Reference | Land is subject to Temporary Possession | 5, 8A | Rights | Yes
7317 | Northern Gas Networks Limited |  | 12-034, 12-053, 12-054, 12-055, 18-008, 18-013 | 12, 18 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 5, 6, 7, 8B, 10B | Apparatus | Yes |  |  | 2026-10-13 | The Applicant is in discussions with Northern Gas Networks Limited. Draft Protective Provisions have been with NGN for review since 29 April 2026. The Applicant has checked in regularly since then, and most recently on 28 September 2026. Change Application The Applicant sent a letter to Northern Gas Networks Limited setting out information regarding the relevant proposed changes on 9 October 2026 | Draft protective provisions for the benefit of Northern Gas Network Ltd are included in the draft DCO and are under discussion.
|  |  | 12-034, 12-052, 12-053, 12-055, 12-060, 12-071, 12-072, 18-008, 18-013, 18-014, 18-015 | 12, 18 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 3, 5, 6, 7, 8B, 10B | Rights | Yes
|  |  | 05-027, 05-028, 11-022, 18-001d, 18-011 | 5, 11, 18 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 8A, 10B | Apparatus | Yes
|  |  | 18-001, 18-001a, 18-001d, 18-002, 18-002a, 18-002b, 18-011 | 12, 18 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 8B, 10B | Rights | Yes
|  |  | 05-036, 05-038, 05-039, 05-040, 05-041, 08-039, 10-009, 11-001, 11-010, 11-011, 11-012, 20-010 | 5, 8, 10, 11, 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Apparatus | Yes
183942 | Northern Powergrid (Yorkshire) PLC |  | 01-012, 01-014, 01-017, 01-019, 01-021, 01-027, 01-033, 01-034, 02-005, 12-034, 12-035, 12-054, 12-060, 12-074, 13-021, 13-035, 13-050, 14-017, 14-018, 14-028, 15-002, 18-008, 18-020 | 1, 12, 13, 14, 15, 18 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 2, 3, 5, 6, 7, 8B, 9A, 9B, 10A, 10B | Apparatus | Yes |  |  | 2026-10-13 | The Applicant is in discussions with Northern Powergrid (Yorkshire) PLC over the technical aspects of the crossing of the strategic road network. The Applicant will continue to engage with Northern Powergrid (Yorkshire) PLC and is confident that any necessary land rights can be acquired by voluntary agreement . See Part 1 of this Land Rights Tracker for further details. Change Application The Applicant sent a letter to Northern Powergrid (Yorkshire) PLC setting out information regarding the relevant proposed changes on 9 October 2026. | Draft protective provisions for the benefit of Northern Powergrid (Yorkshire) PLC are included in the dDCO at Deadline 2 at Schedule 15 and are under discussion. The Applicant returned comments on the Draft PPs and Side Agreement to NPG's solicitors on 25 August 2026. The Applicant has checked in regularly since then, and most recently on 28 September 2026. | The Applicant returned comments on the Side Agreement to NPg's solicitors on 25 August 2026. |  | Northern Powergrid (Yorkshire) PLC and (North East) PLC - RR-1037 Weightmans LLP on behalf of Northern Powergrid (Yorkshire) PLC and (North East) PLC - RR-1440
|  |  | 01-004, 01-014, 01-016, 01-017, 01-018, 01-019, 01-020, 01-021, 01-023, 01-025, 01-027, 01-029, 01-030, 01-033, 12-053 | 1, 12 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 6, 7, 9A, 10A, 10B | Rights | Yes
|  |  | 01-010, 01-015, 01-022, 01-031, 01-032, 02-003, 03-019, 03-020, 03-023, 03-026, 03-027, 05-022, 05-023, 05-024, 05-025, 05-026, 05-027, 05-028, 05-029, 05-032, 05-033 05-044, 06-033, 08-028, 08-035, 09-012, 09-016, 10-003, 10-064, 10-070, 10-071, 10-072, 10-075, 10-077, 10-081, 11-026, 11-027, 11-037, 12-001, 12-002, 12-003, 12-033, 18-001, 18-001a, 13-009, 13-010, 13-014, 13-015, 13-029, 13-030, 13-032, 14-019, 16-002, 15-004, 15-005, 15-009, 15-010, 15-011, 16-003, 16-004, 16-005, 16-006, 16-007, 16-008, 16-015, 16-016, 16-019, 17-009, 17-010, 17-012, 18-011, 18-016, 18-017, 19-017, 20-015, 20-020, 20-021, 21-002, 21-004, 21-008, 21-009, 21-023, 21-024, 21-025, 21-027 | 1, 3, 5, 6, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20, 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 4, 5, 6, 7, 8A, 8B, 10B | Apparatus | Yes
|  |  | 01-003, 01-005, 01-006 01-015, 01-022, 01-024, 01-026, 01-028, 01-031, 21-009, 21-015, 21-016, 21-017, 21-018, 21-021, 21-024, 21-025, 21-026, 21-035 | 1, 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 4, 5, 6, 8B, 10A | Rights | Yes
|  |  | 02-004, 03-008, 03-011, 03-013, 03-014, 03-030, 03-031, 03-032, 03-035, 03-038, 03-039, 03-040, 04-001, 03-042, 03-044, 03-045, 03-047, 03-061, 04-002, 04-004, 05-040, 05-041, 06-030, 06-032, 06-033a, 07-001, 07-002, 07-003, 07-004, 07-005, 07-008, 07-009, 07-011, 08-001, 08-002, 08-010, 08-012, 08-019, 08-020, 08-021, 08-022, 08-031, 08-033, 08-036, 10-004, 10-005, 10-018, 10-021, 10-022, 10-033, 10-035, 10-037, 10-038, 10-040, 11-001, 11-004, 11-007, 11-008, 11-009, 11-013, 12-036, 12-037, 13-018, 13-019, 13-024, 14-012, 18-018, 18-019, 18-021, 19-001, 20-016, 20-018, 20-044 | 2, 3, 4, 5, 6, 7, 8, 10, 11, 12, 13, 14, 18, 19, 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 5, 7, 8A, 8B, 10B | Apparatus | Yes
|  |  | 03-037 | 3, 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights | Yes
|  |  | 21-013, 21-032 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5, 8A | Apparatus | Yes
|  |  | 21-034 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5 | Rights | Yes
356665 | Noventum Power Limited |  | 12-075, 19-005, 19-011, 19-012 | 12, 19 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Beneficiary | Yes |  |  | 2026-02-04 | Technical discussions have taken place and will continue | Bespoke PPs not required. Electricity undertakers will benefit from the Protective Provisions for electricity undertakers included in the draft DCO
266588 | OCU Group Ltd |  | 14-002, 14-028, 15-002 | 14, 15 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 6, 7, 8B, 10B | Apparatus | No |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Operators of electronic communications code networks will have the benefit of the protective provisions for electronic communications code operators set out in the draft DCO.
|  |  | 10-015, 10-023, 10-024, 10-071, 10-075, 10-076, 10-077, 14-014, 15-004, 15-007, 15-011, 17-009, 17-010, 17-012, 20-012 | 10, 14, 15, 17, 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 8A, 8B | Apparatus
156528 | Openreach Limited |  | 01-009, 12-054, 12-060, 12-074, 13-021, 14-002, 14-005, 14-009, 14-010, 18-013, 18-020 | 1, 12, 13, 14, 18 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 2, 3, 5, 6, 7, 8B, 10A, 10B | Apparatus | No |  |  | 2026-10-13 | Change Application The Applicant sent a letter to Openreach Limited setting out information regarding the relevant proposed changes on 9 October 2026. | Bespoke PPs not required. Operators of electronic communications code networks will have the benefit of the protective provisions for electronic communications code operators set out in the draft DCO.
|  |  | 01-003, 01-011, 01-032, 02-009, 03-026, 03-027, 03-028, 03-029, 03-046, 03-059, 05-007, 05-008, 05-009, 05-027, 05-028, 05-031, 05-032, 05-037, 06-020, 06-021, 06-023, 06-025, 08-029, 09-002, 09-004, 09-013, 09-014, 09-016, 10-008, 10-036, 10-039, 10-041, 10-043, 10-044, 10-075, 10-078, 10-079, 10-083, 11-029, 12-001, 12-002, 12-026, 12-033, 12-041, 12-043, 12-059, 12-062, 12-063, 12-065, 13-001, 13-002, 13-005, 13-023, 13-028, 13-030, 13-033, 13-044, 14-006, 14-011, 14-013, 14-025, 14-026, 17-004, 17-009, 18-003, 18-004, 18-016, 18-017, 20-006, 20-012, 20-014, 20-015, 21-001, 21-002, 21-003, 21-005, 21-006, 21-008, 21-009, 21-010, 21-012, 21-020, 21-021, 21-023, 21-024, 21-027, 21-028, 21-029, 21-030, 21-031, 21-035, 21-040 | 1, 2, 5, 6, 8, 9, 10, 11, 12, 13, 14, 17, 18, 20, 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 4, 5, 6, 8A, 8B, 10A, 10B | Apparatus
|  |  | 01-001, 01-007, 02-001, 02-004, 02-007, 02-010, 03-013, 03-015, 03-016, 03-017i, 03-017j, 03-030, 03-031, 03-032, 03-038, 03-039, 03-040, 03-042, 03-043, 03-047, 03-053, 03-054, 03-055, 03-060, 03-061, 04-002, 04-003, 04-004, 05-011, 05-036, 05-038, 05-039, 05-040, 05-041, 07-001, 07-002, 07-003, 07-004, 07-005, 07-006, 07-007, 07-008, 07-009, 07-010, 07-011, 08-001, 08-010, 08-012, 08-023, 08-031, 08-033, 08-038, 08-039, 10-005, 10-009, 10-010, 10-012, 10-018, 10-019a, 10-022, 10-034, 10-037, 10-038, 10-040, 10-046, 10-047, 10-050, 10-083, 10-085, 11-001, 11-011, 11-013, 12-007, 12-008, 12-010, 12-029, 12-037, 12-039, 12-040, 12-042, 15-001, 13-007, 13-016, 13-018, 13-024, 13-025, 13-032, 13-043, 13-045, 14-007, 14-008, 14-012, 15-012, 17-001, 17-002, 17-003, 17-007, 18-007, 18-018, 18-019, 18-021, 20-009, 20-010, 20-016, 20-018, 20-038, 20-044, 20-045, 22-001, 22-002, 22-003, 22-004 | 1, 2, 3, 4, 5, 7, 8, 10, 11, 12, 13, 14, 15, 17, 18, 20, 22 | As described in the Book of Reference | Land is subject to Temporary Possession | 1(d), 5, 6, 8A, 8B, 10A, 10B | Apparatus
|  |  | 10-048 | 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights
|  |  | 21-013, 21-032, 21-032a, 21-033 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5, 8A | Apparatus
333641 | Ouse & Derwent Internal Drainage Board |  | 01-012, 01-030, 01-034 | 1 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 3, 5, 6, 7, 9A, 9B, 10A | Rights | Yes |  |  | 2026-07-07 | Negotiations complete. Given Protective Provisions are agreed, the Applicant has received the Ouse and Derwent IDB's consent to the disapplication of relevant provisions in Article 6 of the Draft DCO and has submitted this consent into the Examination at Deadline 2. | Agreed protective provisions for the benefit of Ouse & Derwent Internal Drainage Board (and the other relevant drainage authorities) are included in the draft DCO. |  |  | Ouse & Derwent Internal Drainage Board - RR-1083 and RR-1440 | Ouse & Derwent Internal Drainage Board - REP 1-027
|  |  | 02-003, 02-011, 03-001, 03-002, 03-004, 03-017, 03-062, 05-002, 05-049, 06-002, 06-003, 06-004, 06-005, 06-006, 06-007, 06-008 | 1, 2, 3, 5, 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 8A, 8B, 10A | Rights | Yes
|  |  | 02-008, 05-010, 05-041 | 2, 5 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights | Yes
331961 | Prowind Hambleton Windfarm GmbH & Co. KG |  | 16-004 | 16 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B | Rights | Yes |  |  | 2026-02-04 | The Applicant received the following response within a Land Interest Questionnaire from the Interest: 'We would like to inform you that the projects in question have been suspended and no longer belong to us. Therefore, there is nothing on our part that would prevent earthworks from being carried out on the land in question'. | No Protective Provisions required given LIQ response
|  |  | 09-021, 09-022 | 9 | As described in the Book of Reference | Land is subject to Temporary Possession | 7, 8A | Rights | Yes
355902 | Quickline Communications Limited |  | 03-017f, 03-017i, 03-017j, 03-032, 03-038, 03-039, 03-041, 04-002 | 3, 4 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Apparatus | No |  |  | 2026-10-13 | Change Application The Applicant sent a letter to Quickline Communications Limited setting out information regarding the relevant proposed changes on 9 October 2026. | Bespoke PPs not required. Operators of electronic communications code networks will have the benefit of the protective provisions for electronic communications code operators set out in the draft DCO.
187230 | Secretary Of State For Defence |  | 09-021, 09-022 | 9 | As described in the Book of Reference | Land is subject to Temporary Possession | 7, 8A | Rights | No |  |  | 2026-09-30 | The Applicant has sought s135 consent from this party. The Applicant will submit a copy of the consent into the Examination once received. | N/A
305096 | Secretary of State for Transport |  | 03-003, 10-063, 10-065, 10-067, 10-068 | 3, 10 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Rights | No |  |  | 2026-09-30 | The Applicant has sought s135 consent from this party. The Applicant will submit a copy of the consent into the Examination once received. | N/A
|  |  | 10-048 | 10 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights | No |  |  | 2026-09-30
331972 | Selby Area Internal Drainage Board |  | 12-034, 12-050, 12-052, 12-053, 12-055, 12-056, 12-071, 12-072, 13-021, 13-049, 13-050, 13-051, 14-001, 14-002, 14-004, 14-005, 14-017, 14-018, 14-021, 14-022, 14-028, 15-002, 18-009, 18-012, 18-013, 19-003 | 12, 13, 14, 15, 18, 19 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 2, 3, 5, 6, 7, 8B, 10B | Rights | Yes |  |  | 2026-10-13 | Negotiations complete. Given Protective Provisions are agreed, the Applicant has received Selby Area IDB's consent to the disapplication of relevant provisions in Article 6 of the Draft DCO and has submitted this consent into the Examination at Deadline 2. Change Application The Applicant sent a letter to Selby Area Internal Drainage Board setting out information regarding the relevant proposed changes on 9 October 2026. | Agreed protective provisions for the benefit of Selby Area Internal Drainage Board (and the other relevant drainage authorities) are included in the draft DCO at Deadline 2.
|  |  | 06-015, 06-039, 06-033, 06-037, 06-038, 07-019, 07-020, 08-027, 09-015, 10-008, 10-031, 10-044, 10-055, 10-059, 10-061, 10-062, 10-063, 10-065, 10-066, 10-070, 10-071, 10-072, 10-082, 11-015, 11-022, 12-002, 12-003, 12-048, 13-009, 13-014, 13-015, 13-017, 13-036, 13-037, 13-046, 13-048, 14-006, 14-014, 15-011, 16-007, 16-008, 18-005a, 18-006, 18-010, 19-002 | 6, 7, 8, 9, 10, 11, 12, 13, 14, 15, 16, 17, 18, 19, 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 7, 8A, 8B, 10B | Rights | Yes
|  |  | 06-030, 06-034, 06-036, 06-039, 07-008, 07-009, 08-001, 08-002, 08-010, 08-012, 08-038, 08-039, 10-018, 10-019a, 10-032, 10-033, 10-034, 10-045, 10-046, 12-004, 13-016, 13-018, 18-005, 20-038, 20-040 | 6, 7, 8, 9, 10, 11, 12, 13, 14, 18, 19, 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 5, 7, 8A, 8B, 10B | Rights | Yes
53952 | Sheffield City Council |  | 01-034, 02-006, 02-005 | 1 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 5, 6, 9A, 9B | Rights | Yes |  |  | 2025-02-04 | The Applicant is undertaking further due diligence as it is believed the listed rights are historic. If it transpires that the rights are not historic the Applicant will seek appropriate Protective Provisions. | As street/highways authority, the Council will have the benefit of having approvals under the relevant DCO articles. No Protective Provisions are proposed at this time
|  |  | 02-003, 05-001, 05-002, 05-003, 05-005, 05-006, 06-010 | 1, 5, 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6 | Rights | Yes
|  |  | 08-005, 08-006, 08-009, 08-021, 08-022, 08-024 | 8 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights | Yes
331977 | SSE Battery Monk Fryston Limited |  | 20-003, 20-004, 20-007, 20-008, 20-011, 20-012 | 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A | Beneficiary | Yes |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Electricity undertakers will benefit from the Protective Provisions for electricity undertakers included in the draft DCO |  |  | SSE Hydrogen Developments Ltd - RR-1036 and RR-1298
|  |  | 20-005 | 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Beneficiary | Yes
55087 | Telefonica UK Limited |  | 05-029 | 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Rights | No |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Operators of electronic communications code networks will have the benefit of the protective provisions for electronic communications code operators set out in the draft DCO.
305102 | The King's Most Excellent Majesty in Right of His Crown |  | 06-010 | 6 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Freehold | No |  |  | 2026-09-30 | The Applicant is in the process of seeking s135 consent from this party. The Applicant will submit a copy of the consent into the Examination once received.
20098 | Vodafone Limited |  | 17-009, 17-010, 17-011, 17-012 | 16, 17 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B | Rights | No |  |  | 2026-02-04 | Discussions have taken place with Vodafone Limited to confirm that bespoke PPs are not required. | Bespoke PPs not required. Operators of electronic communications code networks will have the benefit of the protective provisions for electronic communications code operators set out in the draft DCO.
|  |  | 21-032 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5 | Apparatus
55035 | Yorkshire Electricity Group PLC |  | 14-028 | 14 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 6 | Rights | Yes |  |  | 2026-02-04 | N/A | Bespoke PPs not required. Electricity undertakers will benefit from the Protective Provisions for electricity undertakers included in the draft DCO
|  |  | 21-031, 21-035, 21-040 | 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 | Rights | Yes
|  |  | 21-032, 21-032a, 21-033, 21-034 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5 | Rights | Yes
305109 | Yorkshire Water Services Limited |  | 01-008, 01-009, 01-012, 01-030, 01-034, 02-005, 12-034, 13-021, 13-035 | 1, 12, 13 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 2, 3, 5,6, 7, 8B, 9A, 9B, 10A, 10B | Apparatus | Yes |  |  | 2026-10-13 | Discussions are ongoing with Yorkshire Water Services Limited regarding the form of protective provisions. Draft Protective Provisions have been with Yorkshire Water for review since 9 January 2026. The Applicant has checked in regularly since then, and most recently on 28 September 2026. Change Application The Applicant sent a letter to Yorkshire Water Services Limited setting out information regarding the relevant proposed changes on 9 October 2026. | The water and sewerage undertaker protective provisions in the DCO will protect Yorkshire Water and have been adjusted to give additional protection specifically for them. This is under discussion with Yorkshire Water.
|  |  | 01-004, 01-009, 01-012, 01-019, 01-023, 01-030, 01-033, 13-021 | 1, 13 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 2, 3, 5, 7, 9A, 10A | Rights | Yes
|  |  | 01-011, 02-003, 02-002, 02-011, 03-002, 03-004, 03-017, 03-019, 05-007, 05-008, 05-009, 05-016, 05-027, 05-028, 05-029, 05-030, 05-043, 05-047, 06-023, 06-025, 06-039, 06-033, 08-029, 09-002, 09-005, 09-013, 09-018, 10-026, 10-031, 11-015, 11-018, 11-022, 11-029, 12-026, 18-001, 18-001a, 18-001b, 18-001c, 18-001d, 12-065, 12-067, 13-002, 13-005, 13-009, 13-010, 13-014, 13-015, 13-030, 13-032, 13-033, 13-038, 13-041, 13-048, 16-004, 17-009, 17-010, 17-012, 18-002, 18-002a, 19-018, 20-001, 20-002, 20-015, 20-026, 21-001, 21-002, 21-008, 21-010, 21-012, 21-015, 21-016, 21-017, 21-018, 21-022, 21-023, 21-024, 21-025, 21-026, 21-027, 21-028, 21-035, 21-040 | 1, 2, 3, 5, 6, 8, 9, 10, 11, 12, 13, 16, 17, 18, 19, 20, 21 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 4, 5, 6, 7, 8A, 8B, 10A, 10B | Apparatus | Yes
|  |  | 03-003, 05-001, 05-033 | 3, 5 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A | Freehold | Yes
|  |  | 01-003, 01-005, 01-006, 01-010, 01-011, 01-031, 02-002, 05-025, 05-029, 05-031, 05-043, 06-009, 06-015, 06-016, 06-017, 06-018, 06-019, 06-022, 06-023, 06-038, 06-042, 06-043, 06-044, 06-045, 11-022, 11-025, 11-027, 11-030, 11-031, 11-035, 13-009, 13-010, 13-041, 13-048, 18-003, 19-018, 20-026, 20-031, 20-032 | 1, 2, 5, 6, 11, 13, 19, 20 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 5, 6, 8A , 8B, 10A, 10B | Rights | Yes
|  |  | 07-007, 01-007, 02-001, 02-004, 02-007, 02-008, 03-011, 03-012, 03-014, 03-015, 03-016, 03-017i, 03-017j, 03-029, 03-030, 03-031, 03-032, 03-033, 03-038, 03-039, 03-042, 03-053, 03-054, 03-055, 03-056, 03-060, 03-061, 04-002, 04-003, 04-004, 04-005, 05-011, 05-032, 05-033, 05-034, 05-035, 05-036, 05-037, 05-038, 05-039, 05-040, 05-041, 05-042, 06-026, 06-027, 06-030, 07-001, 07-002, 07-003, 07-004, 07-005, 07-006, 07-008, 07-009, 08-001, 08-004, 08-005, 08-006, 08-007, 08-008, 08-009, 08-010, 08-012, 08-019, 08-020, 08-021, 08-023, 08-031, 08-033, 08-038, 08-039, 09-007, 09-010, 09-017, 09-019, 09-020, 10-002, 10-005, 10-009, 10-018, 10-022, 10-027, 10-077, 10-078, 10-079, 10-081, 11-001, 11-010, 11-011, 11-012, 11-013, 11-016, 11-019, 11-020, 11-021, 12-008, 12-009, 12-010, 12-029, 12-063a, 12-064, 13-007, 13-011, 13-012, 13-046, 15-012, 17-001, 17-002, 17-003, 17-007, 18-007, 18-018, 18-019, 19-016, 20-016, 20-018, 20-037, 20-038, 20-039, 20-044, 21-037, 21-038, 21-039, 22-001, 22-003, 22-004 | 7, 1, 2, 3, 4, 5, 6, 7, 8, 9, 10, 11, 12, 13, 15, 17, 18, 19, 20, 21, 22 | As described in the Book of Reference | Land is subject to Temporary Possession | 1(d), 5, 6, 7, 8A, 8B, 10A | Apparatus | Yes
|  |  | 03-017i, 03-017j, 03-028, 05-032, 05-034, 05-035, 05-042, 06-035, 06-036, 06-039, 07-009, 08-002, 08-003, 08-004, 08-007, 11-008, 11-010, 11-012, 13-011, 13-042, 20-029, 20-033, 20-034 | 11, 3, 5, 6, 7, 8, 11, 13, 20 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A | Rights | Yes
|  |  | 21-013, 21-019, 21-032 | 21 | As described in the Book of Reference | Land is subject to No Rights Sought | 4, 5, 8A | Apparatus | Yes

## Part 3 Cat 2s RRs only
PART 3
Ref | Affected Party | Agent/ Representative | Book of Ref. Plot No. | Plan Ref. No. | Description of Land | Description of Rights Requested | Works Number(s) | Status of Objection | Notes | Last Updated | Summary of Negotiations | Status of Negotiations | Relevant Rep Ref No. | Written Rep Ref No. | Ref No. for any other docs submitted by IP/AP. | Ref No. for Applicant's Response
332771 | John Nathan Blackburn |  | 14-016, 14-019, 14-020 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 6 |  |  | 2026-08-27 | The Applicant is not in negotiation with the Affected Party regarding their interests as it is not anticipated that their interest will be affected by the Proposed Development. |  | RR-0674
318706 | Richard James Worsley Hardy |  | 03-001, 03-002, 03-004, 03-005, 03-006, 03-050, 03-051 | 3 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5, 8A |  |  | 2026-08-27 | The Applicant is not in negotiation with the Affected Party regarding their interests as it is not anticipated that their interest will be affected by the Proposed Development. |  | RR-1174
|  |  | 03-011, 03-012, 03-015, 03-016, 03-054 | 3 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-08-27 | The Applicant is not in negotiation with the Affected Party regarding their interests as it is not anticipated that their interest will be affected by the Proposed Development.
325101 | Terence Bernard Hewson |  | 14-016, 14-019 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 6 |  |  | 2026-08-27 | The Applicant is not in negotiation with the Affected Party regarding their interests as it is not anticipated that their interest will be affected by the Proposed Development. |  | RR-1374
325099 | Roger Hilton Hodgkiss and Clare Hodgkiss |  | 13-050 | 13 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 10B, 5, 6, 7 |  |  | 2026-08-27 | The Applicant is not in negotiation with the Affected Party regarding their interests as it is not anticipated that their interest will be affected by the Proposed Development. |  | RR-1207 RR-0277
| Roger Hilton Hodgkiss and Clare Hodgkiss and Elizabeth Anne Hewson |  | 14-016, 14-019 | 14 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 6 |  |  | 2026-08-27 | The Applicant is not in negotiation with the Affected Party regarding their interests as it is not anticipated that their interest will be affected by the Proposed Development. |  | RR-1207 RR-0277 RR-0384
331934 | Clive Robert Hoyland |  | 13-028 | 13 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-08-27 | The Applicant is not in negotiation with the Affected Party regarding their interests as it is not anticipated that their interest will be affected by the Proposed Development. |  | RR-0282
352989 | Sarah Jackson |  | 01-009, 01-012, 01-030, 01-033 | 1 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 10A, 3, 5, 6, 7, 9A, 10A |  |  | 2026-08-27 | The Applicant is not in negotiation with the Affected Party regarding their interests as it is not anticipated that their interest will be affected by the Proposed Development. |  | RR-1251
|  |  | 01-010, 01-011, 01-031 | 1 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 1(d), 8B, 10A, 5, 6 |  |  | 2026-08-27 | The Applicant is not in negotiation with the Affected Party regarding their interests as it is not anticipated that their interest will be affected by the Proposed Development.
328272 | Jonathan Daniel Marks and Emma Louis Smith |  | 16-003, 16-005, 16-006, 16-007, 17-009, 17-011 | 16, 17 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 8B |  |  | 2026-08-27 | The Applicant is not in negotiation with the Affected Party regarding their interests as it is not anticipated that their interest will be affected by the Proposed Development. |  | RR-0691 RR-0413
330355 | Simon Monkhouse |  | 09-002 | 9 | As described in the Book of Reference | Land is subject to Acquisition of Rights | 5 |  |  | 2026-08-27 | The Applicant is not in negotiation with the Affected Party regarding their interests as it is not anticipated that their interest will be affected by the Proposed Development. |  | RR-0992
374308 | Hannah Preston and Stuart Preston |  | 03-008, 03-008a | 3 | As described in the Book of Reference | Land is subject to Temporary Possession | 8A |  |  | 2026-08-27 | The Applicant is not in negotiation with the Affected Party regarding their interests as it is not anticipated that their interest will be affected by the Proposed Development. |  | RR-0521 RR-1337
325096 | Christopher David Whyke and Christine Tracy Whyke |  | 13-051, 14-017, 14-022 | 13, 14 | As described in the Book of Reference | Land is subject to Freehold Acquisition | 1, 1(d), 10B, 5, 6 |  |  | 2026-08-27 | The Applicant is not in negotiation with the Affected Party regarding their interests at this time as it is either not anticipated that their interest will be affected by the Proposed Development or the extent of any interference will be dependent on detailed design and construction methodologies which would then confirm how their interest would need to be dealt with and so a position cannot be negotiated at this time. |  | RR-0271 RR-1008
|  |  | 14-029 | 14 | As described in the Book of Reference | Land is subject to No Rights Sought | No Rights Sought |  |  | 2026-08-27 | The Applicant is not in negotiation with the Affected Party regarding their interests as it is not anticipated that their interest will be affected by the Proposed Development.