## Category 1
South East Anglia Link: Detailed Land and Rights Negotiations Tracker - Category 1 interests
Notes:
1. All interests which are not already acquired at the point of submission should be entered in this tracker and marked as complete (column 'w') when agreement with known interests is reached
2. Any non-agreement is also counted as an objection by an affected person(s) for the purpose of this tracker
Book of Reference plot number | Plan reference number | Description of land and rights requested | Class of Rights and Type of Acquisition | PIL Name | PIL Reference/Land Referencing PartyID | Title Number(s) | Interest Type | Interest Description | Party Interest capacity | Category | Agent/ representative (if any) | Relevant Representation | When available Relevant representation reference number | When available Written representation reference number | Other document reference number | Applicant's response references | Special category (allotment, National Trust etc) (Select from drop down list) | Crown | Special category - other information including confirmation of status | Is the affected person a statutory undertaker and is the land operational? (Select from drop down list) | Protective provision status (Select from drop down list) | Side agreements (Select from drop down list) | Summary of Negotiation Status | Heads of Terms (Select from drop down list) | Complete (Select from drop down list) | Last Updated [DD/MM/YYYY]
2/30 | Kent Sheet 2 | 6,023 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | John Robert Collins | 698 | K56551 | Freehold |  | excluding mines and minerals | Category 1 | Martin Allen, Elgars | Yes | RR-1465 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 04 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 6th November 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - On 19th November 2025 Dalcour Maclaren wrote to the landowner to confirm that their agent continues to be instructed in relation to the Heads of Terms. No response has been received. On 7th January 2026 Dalcour Maclaren attempted to contact the landowner by phone call to discuss Heads of Terms further and have not had a response to their voicemail. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/30 | Kent Sheet 3 | 735 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south east of Sevenscore Crossing, Kent, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Kent County Council | 97 | TT104661 | Freehold |  | excluding mines and minerals | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/30 | Kent Sheet 3 | 735 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south east of Sevenscore Crossing, Kent, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/30 | Kent Sheet 5 | 10,705 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporate the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/30 | Kent Sheet 5 | 10,705 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | RR-5371 | [6 empty] | SU and unknown operational | Not required |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
3/31 | Kent Sheet 3 | 5,195 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Oast, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ebbsfleet Minster (Kent) Limited | 341 | K808893 | Freehold |  | excluding mines and minerals | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/31 | Kent Sheet 3 | 5,195 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Oast, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ebbsfleet Minster (Kent) Limited | 341 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/31 | Kent Sheet 5 | 16,280 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporate the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/31 | Kent Sheet 5 | 16,280 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | RR-5371 | [6 empty] | SU and unknown operational | Not required |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
2/32 | Kent Sheet 2 | 316 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | John Robert Collins | 698 | K56551 | Freehold |  | excluding mines and minerals | Category 1 | Martin Allen, Elgars | Yes | RR-1465 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 04 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 6th November 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - On 19th November 2025 Dalcour Maclaren wrote to the landowner to confirm that their agent continues to be instructed in relation to the Heads of Terms. No response has been received. On 7th January 2026 Dalcour Maclaren attempted to contact the landowner by phone call to discuss Heads of Terms further and have not had a response to their voicemail. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/32 | Kent Sheet 3 | 818 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Ebbsfleet Minster (Kent) Limited | 341 | K808893 | Freehold |  | excluding mines and minerals | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/32 | Kent Sheet 3 | 818 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Ebbsfleet Minster (Kent) Limited | 341 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/32 | Kent Sheet 5 | 105,621 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporate the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/32 | Kent Sheet 5 | 105,621 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | RR-5371 | [6 empty] | SU and unknown operational | Not required |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
5/32 | Kent Sheet 5 | 105,621 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Ventures Limited | 3292 |  | Occupation | underground electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/33 | Kent Sheet 3 | 3,845 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south east of Sevenscore Crossing, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | TT104661 | Freehold |  | excluding mines and minerals | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/33 | Kent Sheet 3 | 3,845 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south east of Sevenscore Crossing, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/33 | Kent Sheet 5 | 14,518 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporate the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/33 | Kent Sheet 5 | 14,518 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | RR-5371 | [6 empty] | SU and unknown operational | Not required |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
3/34 | Kent Sheet 3 | 371 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Oast, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 | TT104661 | Freehold |  | excluding mines and minerals | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/34 | Kent Sheet 3 | 371 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Oast, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/34 | Kent Sheet 5 | 1,129 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | N/A Mark Warnett, Ardent | Yes | RR-5384 |  |  |  | National Trust |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025 and are arranging a meeting with the landowner’s agent in January. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/34 | Kent Sheet 5 | 1,129 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent Wildlife Trust | 498 | TT41175 | Leasehold |  |  | Category 1 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/34 | Kent Sheet 5 | 1,129 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Ventures Limited | 3292 |  | Occupation | underground electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/35 | Kent Sheet 2 | 87 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/35 | Kent Sheet 3 | 1,084 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/35 | Kent Sheet 3 | 1,084 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ebbsfleet Minster (Kent) Limited | 341 | K808893 | Freehold | subsoil fronting land to the south west of Cottington Hill, Ebbsfleet Lane North |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/35 | Kent Sheet 3 | 1,084 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Struan Gordon Robertson | 494 | K755310 | Freehold | subsoil fronting land to the south of Sevenscore Crossing, Ebbsfleet Lane North |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/35 | Kent Sheet 3 | 1,084 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/35 | Kent Sheet 3 | 1,084 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/35 | Kent Sheet 5 | 191,908 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporate the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/35 | Kent Sheet 5 | 191,908 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | RR-5371 | [6 empty] | SU and unknown operational | Not required |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
2/36 | Kent Sheet 2 | 1,470 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | John Robert Collins | 698 | K458450 | Freehold |  |  | Category 1 | Martin Allen, Elgars | Yes | RR-1465 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 04 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 6th November 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - On 19th November 2025 Dalcour Maclaren wrote to the landowner to confirm that their agent continues to be instructed in relation to the Heads of Terms. No response has been received. On 7th January 2026 Dalcour Maclaren attempted to contact the landowner by phone call to discuss Heads of Terms further and have not had a response to their voicemail. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/36 | Kent Sheet 2 | 1,470 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/36 | Kent Sheet 3 | 16 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Oast, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 | TT104661 | Freehold |  | excluding mines and minerals | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/36 | Kent Sheet 3 | 16 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Oast, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/36 | Kent Sheet 5 | 9,869 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporate the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/36 | Kent Sheet 5 | 9,869 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | RR-5371 | [6 empty] | SU and unknown operational | Not required |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
3/37 | Kent Sheet 3 | 306 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Oast, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | TT104661 | Freehold |  | excluding mines and minerals | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/37 | Kent Sheet 3 | 306 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Oast, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/37 | Kent Sheet 5 | 1,220 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | N/A Mark Warnett, Ardent | Yes | RR-5384 |  |  |  | National Trust |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025 and are arranging a meeting with the landowner’s agent in January. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/37 | Kent Sheet 5 | 1,220 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent Wildlife Trust | 498 | TT41175 | Leasehold |  |  | Category 1 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/38 | Kent Sheet 2 | 60 square metres, or thereabouts, of drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/38 | Kent Sheet 3 | 28,006 square metres, or thereabouts, of agricultural land situated to the west of St. Augustine`s Golf Course, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ebbsfleet Minster (Kent) Limited | 341 | K808893 | Freehold |  | excluding mines and minerals | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/38 | Kent Sheet 3 | 28,006 square metres, or thereabouts, of agricultural land situated to the west of St. Augustine`s Golf Course, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ebbsfleet Minster (Kent) Limited | 341 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/38 | Kent Sheet 5 | 82 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent Wildlife Trust | 498 | K410629 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/39 | Kent Sheet 2 | 27,228 square metres, or thereabouts, of grassland, drains and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | John Robert Collins | 698 | K458450 | Freehold |  |  | Category 1 | Martin Allen, Elgars | Yes | RR-1465 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 04 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 6th November 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - On 19th November 2025 Dalcour Maclaren wrote to the landowner to confirm that their agent continues to be instructed in relation to the Heads of Terms. No response has been received. On 7th January 2026 Dalcour Maclaren attempted to contact the landowner by phone call to discuss Heads of Terms further and have not had a response to their voicemail. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/39 | Kent Sheet 2 | 27,228 square metres, or thereabouts, of grassland, drains and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/39 | Kent Sheet 2 | 27,228 square metres, or thereabouts, of grassland, drains and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/39 | Kent Sheet 3 | 5,301 square metres, or thereabouts, of agricultural land situated to the south east of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ebbsfleet Minster (Kent) Limited | 341 | K808893 | Freehold |  | excluding mines and minerals | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/39 | Kent Sheet 3 | 5,301 square metres, or thereabouts, of agricultural land situated to the south east of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ebbsfleet Minster (Kent) Limited | 341 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/39 | Kent Sheet 5 | 317,744 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporate the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/39 | Kent Sheet 5 | 317,744 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | RR-5371 | [6 empty] | SU and unknown operational | Not required |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
5/39 | Kent Sheet 5 | 317,744 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Ventures Limited | 3292 |  | Occupation | underground electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/40 | Kent Sheet 2 | 2,835 square metres, or thereabouts, of grassland, track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | John Robert Collins | 698 | K458450 | Freehold |  |  | Category 1 | Martin Allen, Elgars | Yes | RR-1465 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 04 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 6th November 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - On 19th November 2025 Dalcour Maclaren wrote to the landowner to confirm that their agent continues to be instructed in relation to the Heads of Terms. No response has been received. On 7th January 2026 Dalcour Maclaren attempted to contact the landowner by phone call to discuss Heads of Terms further and have not had a response to their voicemail. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/40 | Kent Sheet 2 | 2,835 square metres, or thereabouts, of grassland, track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/40 | Kent Sheet 2 | 2,835 square metres, or thereabouts, of grassland, track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/40 | Kent Sheet 3 | 6,289 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south east of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent County Council | 97 | TT104661 | Freehold |  | excluding mines and minerals | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/40 | Kent Sheet 3 | 6,289 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south east of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/40 | Kent Sheet 5 | 8,496 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | N/A Mark Warnett, Ardent | Yes | RR-5384 |  |  |  | National Trust |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025 and are arranging a meeting with the landowner’s agent in January. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/40 | Kent Sheet 5 | 8,496 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent Wildlife Trust | 498 | TT41175 | Leasehold |  |  | Category 1 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/41 | Kent Sheet 2 | 5,222 square metres, or thereabouts, of agricultural land, electricity transmission pylon and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | John Robert Collins | 698 | K458450 | Freehold |  |  | Category 1 | Martin Allen, Elgars | Yes | RR-1465 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 04 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 6th November 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - On 19th November 2025 Dalcour Maclaren wrote to the landowner to confirm that their agent continues to be instructed in relation to the Heads of Terms. No response has been received. On 7th January 2026 Dalcour Maclaren attempted to contact the landowner by phone call to discuss Heads of Terms further and have not had a response to their voicemail. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/41 | Kent Sheet 2 | 5,222 square metres, or thereabouts, of agricultural land, electricity transmission pylon and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/41 | Kent Sheet 2 | 5,222 square metres, or thereabouts, of agricultural land, electricity transmission pylon and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/41 | Kent Sheet 3 | 8,369 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ebbsfleet Minster (Kent) Limited | 341 | K808893 | Freehold |  | excluding mines and minerals | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/41 | Kent Sheet 3 | 8,369 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ebbsfleet Minster (Kent) Limited | 341 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/41 | Kent Sheet 3 | 8,369 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
5/41 | Kent Sheet 5 | 23 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | N/A Mark Warnett, Ardent | Yes | RR-5384 |  |  |  | National Trust |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025 and are arranging a meeting with the landowner’s agent in January. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/41 | Kent Sheet 5 | 23 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent Wildlife Trust | 498 | TT41175 | Leasehold |  |  | Category 1 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/42 | Kent Sheet 2 | 5,319 square metres, or thereabouts, of grassland, track, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | John Robert Collins | 698 | K458450 | Freehold |  |  | Category 1 | Martin Allen, Elgars | Yes | RR-1465 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 04 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 6th November 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - On 19th November 2025 Dalcour Maclaren wrote to the landowner to confirm that their agent continues to be instructed in relation to the Heads of Terms. No response has been received. On 7th January 2026 Dalcour Maclaren attempted to contact the landowner by phone call to discuss Heads of Terms further and have not had a response to their voicemail. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/42 | Kent Sheet 2 | 5,319 square metres, or thereabouts, of grassland, track, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/42 | Kent Sheet 2 | 5,319 square metres, or thereabouts, of grassland, track, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/42 | Kent Sheet 3 | 78 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/42 | Kent Sheet 5 | 144 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | N/A Mark Warnett, Ardent | Yes | RR-5384 |  |  |  | National Trust |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025 and are arranging a meeting with the landowner’s agent in January. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/42 | Kent Sheet 5 | 144 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent Wildlife Trust | 498 | TT41175 | Leasehold |  |  | Category 1 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/43 | Kent Sheet 3 | 248 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/43 | Kent Sheet 5 | 4 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | N/A Mark Warnett, Ardent | Yes | RR-5384 |  |  |  | National Trust |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025 and are arranging a meeting with the landowner’s agent in January. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/43 | Kent Sheet 5 | 4 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent Wildlife Trust | 498 | TT41175 | Leasehold |  |  | Category 1 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/44 | Kent Sheet 2 | 50 square metres, or thereabouts, of drain under bridge carrying track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/44 | Kent Sheet 3 | 11,247 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Edward Martin Spanton | 154 | K960682 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/44 | Kent Sheet 3 | 11,247 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Edward Martin Spanton | 154 | K960682 | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/44 | Kent Sheet 3 | 11,247 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
5/44 | Kent Sheet 5 | 2 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | N/A Mark Warnett, Ardent | Yes | RR-5384 |  |  |  | National Trust |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025 and are arranging a meeting with the landowner’s agent in January. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/44 | Kent Sheet 5 | 2 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent Wildlife Trust | 498 | TT41175 | Leasehold |  |  | Category 1 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/45 | Kent Sheet 2 | 968 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/45 | Kent Sheet 3 | 7,705 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Edward Martin Spanton | 154 | K960682 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/45 | Kent Sheet 3 | 7,705 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Edward Martin Spanton | 154 | K960682 | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
5/45 | Kent Sheet 5 | 6,544 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporate the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/45 | Kent Sheet 5 | 6,544 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | RR-5371 | [6 empty] | SU and unknown operational | Not required |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
3/46 | Kent Sheet 3 | 2,942 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ebbsfleet Minster (Kent) Limited | 341 | K808893 | Freehold |  | excluding mines and minerals | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/46 | Kent Sheet 3 | 2,942 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ebbsfleet Minster (Kent) Limited | 341 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/46 | Kent Sheet 3 | 2,942 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
5/46 | Kent Sheet 5 | 14,098 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporate the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/46 | Kent Sheet 5 | 14,098 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | RR-5371 | [6 empty] | SU and unknown operational | Not required |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
2/47 | Kent Sheet 2 | 50 square metres, or thereabouts, of drain under bridge carrying track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/47 | Kent Sheet 2 | 50 square metres, or thereabouts, of drain under bridge carrying track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Ian Stewart Chandler | 49 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/47 | Kent Sheet 2 | 50 square metres, or thereabouts, of drain under bridge carrying track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Chandler & Dunn Limited | 2581 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/47 | Kent Sheet 3 | 17,155 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ebbsfleet Minster (Kent) Limited | 341 | K808893 | Freehold |  | excluding mines and minerals | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/47 | Kent Sheet 3 | 17,155 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ebbsfleet Minster (Kent) Limited | 341 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/47 | Kent Sheet 3 | 17,155 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/47 | Kent Sheet 3 | 17,155 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/47 | Kent Sheet 3 | 17,155 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/47 | Kent Sheet 5 | 1,166 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporate the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/47 | Kent Sheet 5 | 1,166 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | RR-5371 | [6 empty] | SU and unknown operational | Not required |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
3/48 | Kent Sheet 3 | 189 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/48 | Kent Sheet 5 | 9,902 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporate the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/48 | Kent Sheet 5 | 9,902 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | RR-5371 | [6 empty] | SU and unknown operational | Not required |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
2/49 | Kent Sheet 2 | 108 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/49 | Kent Sheet 3 | 683 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Edward Martin Spanton | 154 | K960682 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/49 | Kent Sheet 3 | 683 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Edward Martin Spanton | 154 | K960682 | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/49 | Kent Sheet 3 | 683 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
2/50 | Kent Sheet 2 | 3,952 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Stewart Chandler | 49 | K57595 | Freehold |  | as freeholder and as Personal Representative to Robert Stewart Chandler) (excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/50 | Kent Sheet 2 | 3,952 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Stewart Dunn | 219 | K57595 | Freehold |  | excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/50 | Kent Sheet 2 | 3,952 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Stewart Chandler | 49 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/50 | Kent Sheet 2 | 3,952 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/50 | Kent Sheet 2 | 3,952 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Chandler & Dunn Limited | 2581 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/50 | Kent Sheet 3 | 1,186 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Edward Martin Spanton | 154 | K960682 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/50 | Kent Sheet 3 | 1,186 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Edward Martin Spanton | 154 | K960682 | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
2/51 | Kent Sheet 2 | 3,852 square metres, or thereabouts, of agricultural land, track, drain and overhead electricity distribution lines situated to the south and south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Stewart Chandler | 49 | K57595 | Freehold |  | as freeholder and as Personal Representative to Robert Stewart Chandler) (excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/51 | Kent Sheet 2 | 3,852 square metres, or thereabouts, of agricultural land, track, drain and overhead electricity distribution lines situated to the south and south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul Stewart Dunn | 219 | K57595 | Freehold |  | excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/51 | Kent Sheet 2 | 3,852 square metres, or thereabouts, of agricultural land, track, drain and overhead electricity distribution lines situated to the south and south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Stewart Chandler | 49 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/51 | Kent Sheet 2 | 3,852 square metres, or thereabouts, of agricultural land, track, drain and overhead electricity distribution lines situated to the south and south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/51 | Kent Sheet 2 | 3,852 square metres, or thereabouts, of agricultural land, track, drain and overhead electricity distribution lines situated to the south and south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Chandler & Dunn Limited | 2581 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/51 | Kent Sheet 3 | 1,518 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | Edward Martin Spanton | 154 | K960682 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/51 | Kent Sheet 3 | 1,518 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | Edward Martin Spanton | 154 | K960682 | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
2/52 | Kent Sheet 2 | 3,701 square metres, or thereabouts, of grassland and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Stewart Chandler | 49 | K57595 | Freehold |  | as freeholder and as Personal Representative to Robert Stewart Chandler) (excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/52 | Kent Sheet 2 | 3,701 square metres, or thereabouts, of grassland and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Stewart Dunn | 219 | K57595 | Freehold |  | excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/52 | Kent Sheet 2 | 3,701 square metres, or thereabouts, of grassland and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Stewart Chandler | 49 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/52 | Kent Sheet 2 | 3,701 square metres, or thereabouts, of grassland and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Chandler & Dunn Limited | 2581 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/52 | Kent Sheet 3 | 1,079 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/52 | Kent Sheet 3 | 1,079 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/52 | Kent Sheet 3 | 1,079 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/53 | Kent Sheet 2 | 12,613 square metres, or thereabouts, of grassland, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Ian Stewart Chandler | 49 | K57595 | Freehold |  | as freeholder and as Personal Representative to Robert Stewart Chandler) (excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/53 | Kent Sheet 2 | 12,613 square metres, or thereabouts, of grassland, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Paul Stewart Dunn | 219 | K57595 | Freehold |  | excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/53 | Kent Sheet 2 | 12,613 square metres, or thereabouts, of grassland, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/53 | Kent Sheet 2 | 12,613 square metres, or thereabouts, of grassland, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Ian Stewart Chandler | 49 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/53 | Kent Sheet 2 | 12,613 square metres, or thereabouts, of grassland, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Chandler & Dunn Limited | 2581 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/53 | Kent Sheet 3 | 16 square metres, or thereabouts, of track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Edward Martin Spanton | 154 |  | Freehold |  | as reputed owner | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/53 | Kent Sheet 3 | 16 square metres, or thereabouts, of track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/53 | Kent Sheet 3 | 16 square metres, or thereabouts, of track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/54 | Kent Sheet 2 | 40,844 square metres, or thereabouts, of grassland, track, drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Stewart Chandler | 49 | K57595 | Freehold |  | as freeholder and as Personal Representative to Robert Stewart Chandler) (excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/54 | Kent Sheet 2 | 40,844 square metres, or thereabouts, of grassland, track, drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Stewart Dunn | 219 | K57595 | Freehold |  | excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/54 | Kent Sheet 2 | 40,844 square metres, or thereabouts, of grassland, track, drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Stewart Chandler | 49 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/54 | Kent Sheet 2 | 40,844 square metres, or thereabouts, of grassland, track, drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/54 | Kent Sheet 2 | 40,844 square metres, or thereabouts, of grassland, track, drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Chandler & Dunn Limited | 2581 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/54 | Kent Sheet 3 | 17,794 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Edward Martin Spanton | 154 | K960682 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/54 | Kent Sheet 3 | 17,794 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Edward Martin Spanton | 154 | K960682 | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/54 | Kent Sheet 3 | 17,794 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/54 | Kent Sheet 3 | 17,794 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | St. Augustine`s Golf Club (Ramsgate) Limited | 553 |  | Occupation |  |  | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/54 | Kent Sheet 3 | 17,794 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/54 | Kent Sheet 3 | 17,794 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/55 | Kent Sheet 2 | 4,844 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Stewart Chandler | 49 | K57595 | Freehold |  | as freeholder and as Personal Representative to Robert Stewart Chandler) (excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/55 | Kent Sheet 2 | 4,844 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Stewart Dunn | 219 | K57595 | Freehold |  | excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/55 | Kent Sheet 2 | 4,844 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Stewart Chandler | 49 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/55 | Kent Sheet 2 | 4,844 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/55 | Kent Sheet 2 | 4,844 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Chandler & Dunn Limited | 2581 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/55 | Kent Sheet 3 | 3,331 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Edward Martin Spanton | 154 | K960682 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/55 | Kent Sheet 3 | 3,331 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Edward Martin Spanton | 154 | K960682 | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/55 | Kent Sheet 3 | 3,331 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/55 | Kent Sheet 3 | 3,331 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/56 | Kent Sheet 2 | 28 square metres, or thereabouts, of grassland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/56 | Kent Sheet 2 | 28 square metres, or thereabouts, of grassland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/56 | Kent Sheet 2 | 28 square metres, or thereabouts, of grassland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/56 | Kent Sheet 2 | 28 square metres, or thereabouts, of grassland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
3/56 | Kent Sheet 3 | 7,939 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Edward Martin Spanton | 154 | K960682 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/56 | Kent Sheet 3 | 7,939 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Edward Martin Spanton | 154 | K960682 | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/56 | Kent Sheet 3 | 7,939 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/57 | Kent Sheet 2 | 343 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Marquess Conyngham | 2591 |  | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
2/57 | Kent Sheet 2 | 343 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/57 | Kent Sheet 3 | 762 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Edward Martin Spanton | 154 | K960682 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/57 | Kent Sheet 3 | 762 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Edward Martin Spanton | 154 | K960682 | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/57 | Kent Sheet 3 | 762 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/57 | Kent Sheet 3 | 762 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/58 | Kent Sheet 2 | 434 square metres, or thereabouts, of river, bed and bank (River Stour), overhead electricity distribution lines and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line: Open Space (River Stour Navigation) | Class 2. Compulsory Acquisition of Rights - Overhead Line: Open Space (River Stour Navigation) | The King`s Most Excellent Majesty in Right of His Crown | 458 | K933847,Crown Land Query - River Stour | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 |  |  |  | Open Space | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage.In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. 09.01.2026 – Dalcour Maclaren exchanged emails with the landowner’s agent on 5th December 2025 in relation to outstanding principles in the commercial agreements. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/58 | Kent Sheet 2 | 434 square metres, or thereabouts, of river, bed and bank (River Stour), overhead electricity distribution lines and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line: Open Space (River Stour Navigation) | Class 2. Compulsory Acquisition of Rights - Overhead Line: Open Space (River Stour Navigation) | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/58 | Kent Sheet 3 | 337 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/58 | Kent Sheet 3 | 337 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/58 | Kent Sheet 3 | 337 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [6 empty] | SU and disputed operational | Not required |  | 09.01.2026 - Discussions ongoing | No Heads of Terms Required |  | 2026-01-09
2/59 | Kent Sheet 2 | 620 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights – Overhead Line | Class 2. Compulsory Acquisition of Rights – Overhead Line | Ian Stewart Chandler | 49 | K57595 | Freehold |  | as freeholder and as Personal Representative to Robert Stewart Chandler) (excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/59 | Kent Sheet 2 | 620 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights – Overhead Line | Class 2. Compulsory Acquisition of Rights – Overhead Line | Paul Stewart Dunn | 219 | K57595 | Freehold |  | excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/59 | Kent Sheet 2 | 620 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights – Overhead Line | Class 2. Compulsory Acquisition of Rights – Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/59 | Kent Sheet 2 | 620 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights – Overhead Line | Class 2. Compulsory Acquisition of Rights – Overhead Line | Ian Stewart Chandler | 49 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/59 | Kent Sheet 2 | 620 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights – Overhead Line | Class 2. Compulsory Acquisition of Rights – Overhead Line | Chandler & Dunn Limited | 2581 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert John Chapman | 654 | K651171 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Stonelees Golf Centre | 3413 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/60 | Kent Sheet 2 | 8,781 square metres, or thereabouts, of grassland, drains, sluices, track, electricity transmission pylon and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Stewart Chandler | 49 | K57595 | Freehold |  | as freeholder and as Personal Representative to Robert Stewart Chandler) (excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/60 | Kent Sheet 2 | 8,781 square metres, or thereabouts, of grassland, drains, sluices, track, electricity transmission pylon and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Stewart Dunn | 219 | K57595 | Freehold |  | excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/60 | Kent Sheet 2 | 8,781 square metres, or thereabouts, of grassland, drains, sluices, track, electricity transmission pylon and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Stewart Chandler | 49 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/60 | Kent Sheet 2 | 8,781 square metres, or thereabouts, of grassland, drains, sluices, track, electricity transmission pylon and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/60 | Kent Sheet 2 | 8,781 square metres, or thereabouts, of grassland, drains, sluices, track, electricity transmission pylon and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Chandler & Dunn Limited | 2581 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert John Chapman | 654 | K651171 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Stonelees Golf Centre | 3413 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/61 | Kent Sheet 2 | 122 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 2591 |  | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert John Chapman | 654 | K651171 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Stonelees Golf Centre | 3413 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/62 | Kent Sheet 2 | 2,242 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The King`s Most Excellent Majesty in Right of His Crown | 458 | K933847,Crown Land Query - River Stour | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 |  |  |  | Open Space | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage.In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. 09.01.2026 – Dalcour Maclaren exchanged emails with the landowner’s agent on 5th December 2025 in relation to outstanding principles in the commercial agreements. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/62 | Kent Sheet 2 | 2,242 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/62 | Kent Sheet 3 | 162 square metres, or thereabouts, of drain situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/62 | Kent Sheet 3 | 162 square metres, or thereabouts, of drain situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [6 empty] | SU and disputed operational | Not required |  | 09.01.2026 - Discussions ongoing | No Heads of Terms Required |  | 2026-01-09
2/63 | Kent Sheet 2 | 2,701 square metres, or thereabouts, of grassland, sluice, drain and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Stewart Chandler | 49 | K57595 | Freehold |  | as freeholder and as Personal Representative to Robert Stewart Chandler) (excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/63 | Kent Sheet 2 | 2,701 square metres, or thereabouts, of grassland, sluice, drain and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul Stewart Dunn | 219 | K57595 | Freehold |  | excluding mines and minerals below a depth of 500 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/63 | Kent Sheet 2 | 2,701 square metres, or thereabouts, of grassland, sluice, drain and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Stewart Chandler | 49 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/63 | Kent Sheet 2 | 2,701 square metres, or thereabouts, of grassland, sluice, drain and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/63 | Kent Sheet 2 | 2,701 square metres, or thereabouts, of grassland, sluice, drain and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Chandler & Dunn Limited | 2581 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/63 | Kent Sheet 3 | 456 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Edward Martin Spanton | 154 | K960682 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/63 | Kent Sheet 3 | 456 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Edward Martin Spanton | 154 | K960682 | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
2/64 | Kent Sheet 2 | 1,771 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 2591 |  | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
2/64 | Kent Sheet 2 | 1,771 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/64 | Kent Sheet 3 | 996 square metres, or thereabouts, of drain situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Timothy John Deakin | 313 | TT40208 | Leasehold |  | as trustee to St. Augustines Golf Club (Ramsgate) Limited | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/64 | Kent Sheet 3 | 996 square metres, or thereabouts, of drain situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Thomas | 559 | TT40208 | Leasehold |  | as trustee to St. Augustines Golf Club (Ramsgate) Limited | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/64 | Kent Sheet 3 | 996 square metres, or thereabouts, of drain situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Gary Snell | 642 | TT40208 | Leasehold |  | as trustee to St. Augustines Golf Club (Ramsgate) Limited | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/64 | Kent Sheet 3 | 996 square metres, or thereabouts, of drain situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [6 empty] | SU and disputed operational | Not required |  | 09.01.2026 - Discussions ongoing | No Heads of Terms Required |  | 2026-01-09
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Church Commissioners for England | 378 | K535742 | Freehold |  |  | Category 1 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert John Chapman | 654 | K651171 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | St. Augustine`s Golf Club (Ramsgate) Limited | 553 |  | Occupation |  |  | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/66 | Kent Sheet 2 | 28 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 2591 |  | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
2/66 | Kent Sheet 2 | 28 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/66 | Kent Sheet 2 | 28 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/66 | Kent Sheet 2 | 28 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/66 | Kent Sheet 2 | 28 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
3/66 | Kent Sheet 3 | 22,214 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | St. Augustine`s Golf Club (Ramsgate) Limited | 553 |  | Freehold |  | as reputed owner | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/66 | Kent Sheet 3 | 22,214 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Timothy John Deakin | 313 | TT40208 | Leasehold |  | as trustee to St. Augustines Golf Club (Ramsgate) Limited | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/66 | Kent Sheet 3 | 22,214 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Thomas | 559 | TT40208 | Leasehold |  | as trustee to St. Augustines Golf Club (Ramsgate) Limited | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/66 | Kent Sheet 3 | 22,214 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Gary Snell | 642 | TT40208 | Leasehold |  | as trustee to St. Augustines Golf Club (Ramsgate) Limited | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/66 | Kent Sheet 3 | 22,214 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | St. Augustine`s Golf Club (Ramsgate) Limited | 553 |  | Occupation |  |  | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/66 | Kent Sheet 3 | 22,214 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [6 empty] | SU and disputed operational | Not required |  | 09.01.2026 - Discussions ongoing | No Heads of Terms Required |  | 2026-01-09
2/67 | Kent Sheet 2 | 76 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Marquess Conyngham | 2591 |  | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
2/67 | Kent Sheet 2 | 76 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/67 | Kent Sheet 2 | 76 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/67 | Kent Sheet 2 | 76 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/67 | Kent Sheet 2 | 76 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/67 | Kent Sheet 2 | 76 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | James Southorn | 3137 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/68 | Kent Sheet 2 | 123 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 2591 |  | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
2/69 | Kent Sheet 2 | 108 square metres, or thereabouts, of agricultural land and track situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Church Commissioners for England | 378 | K535742 | Freehold |  |  | Category 1 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/69 | Kent Sheet 2 | 108 square metres, or thereabouts, of agricultural land and track situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/69 | Kent Sheet 2 | 108 square metres, or thereabouts, of agricultural land and track situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/69 | Kent Sheet 2 | 108 square metres, or thereabouts, of agricultural land and track situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/69 | Kent Sheet 2 | 108 square metres, or thereabouts, of agricultural land and track situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/70 | Kent Sheet 2 | 2,290 square metres, or thereabouts, of scrubland, track and drain situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Church Commissioners for England | 378 | K535742 | Freehold |  |  | Category 1 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/70 | Kent Sheet 2 | 2,290 square metres, or thereabouts, of scrubland, track and drain situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/70 | Kent Sheet 2 | 2,290 square metres, or thereabouts, of scrubland, track and drain situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/70 | Kent Sheet 2 | 2,290 square metres, or thereabouts, of scrubland, track and drain situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/70 | Kent Sheet 2 | 2,290 square metres, or thereabouts, of scrubland, track and drain situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/71 | Kent Sheet 2 | 460 square metres, or thereabouts, of scrubland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Church Commissioners for England | 378 | K535742 | Freehold |  |  | Category 1 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/71 | Kent Sheet 2 | 460 square metres, or thereabouts, of scrubland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/71 | Kent Sheet 2 | 460 square metres, or thereabouts, of scrubland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/71 | Kent Sheet 2 | 460 square metres, or thereabouts, of scrubland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/71 | Kent Sheet 2 | 460 square metres, or thereabouts, of scrubland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/72 | Kent Sheet 2 | 5,521 square metres, or thereabouts, of agricultural land and drain situated to the south west of Boxlees, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Church Commissioners for England | 378 | K535742 | Freehold |  |  | Category 1 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/72 | Kent Sheet 2 | 5,521 square metres, or thereabouts, of agricultural land and drain situated to the south west of Boxlees, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/72 | Kent Sheet 2 | 5,521 square metres, or thereabouts, of agricultural land and drain situated to the south west of Boxlees, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/72 | Kent Sheet 2 | 5,521 square metres, or thereabouts, of agricultural land and drain situated to the south west of Boxlees, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/73 | Kent Sheet 2 | 11,831 square metres, or thereabouts, of agricultural land, track, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Church Commissioners for England | 378 | K535742 | Freehold |  |  | Category 1 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/73 | Kent Sheet 2 | 11,831 square metres, or thereabouts, of agricultural land, track, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/73 | Kent Sheet 2 | 11,831 square metres, or thereabouts, of agricultural land, track, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/73 | Kent Sheet 2 | 11,831 square metres, or thereabouts, of agricultural land, track, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/73 | Kent Sheet 2 | 11,831 square metres, or thereabouts, of agricultural land, track, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/73 | Kent Sheet 2 | 11,831 square metres, or thereabouts, of agricultural land, track, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/73 | Kent Sheet 2 | 11,831 square metres, or thereabouts, of agricultural land, track, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | James Southorn | 3137 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/74 | Kent Sheet 2 | 832 square metres, or thereabouts, of track and scrubland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Church Commissioners for England | 378 | K535742 | Freehold |  |  | Category 1 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/74 | Kent Sheet 2 | 832 square metres, or thereabouts, of track and scrubland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/74 | Kent Sheet 2 | 832 square metres, or thereabouts, of track and scrubland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/74 | Kent Sheet 2 | 832 square metres, or thereabouts, of track and scrubland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/74 | Kent Sheet 2 | 832 square metres, or thereabouts, of track and scrubland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
3/74 | Kent Sheet 3 | 601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ebbsfleet Minster (Kent) Limited | 341 | K808893 | Freehold |  | excluding mines and minerals | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/74 | Kent Sheet 3 | 601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ebbsfleet Minster (Kent) Limited | 341 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/74 | Kent Sheet 3 | 601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/74 | Kent Sheet 3 | 601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/74 | Kent Sheet 3 | 601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/74 | Kent Sheet 3 | 601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/75 | Kent Sheet 2 | 12,129 square metres, or thereabouts, of agricultural land situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Church Commissioners for England | 378 | K535742 | Freehold |  |  | Category 1 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/75 | Kent Sheet 2 | 12,129 square metres, or thereabouts, of agricultural land situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/75 | Kent Sheet 2 | 12,129 square metres, or thereabouts, of agricultural land situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/75 | Kent Sheet 2 | 12,129 square metres, or thereabouts, of agricultural land situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/75 | Kent Sheet 2 | 12,129 square metres, or thereabouts, of agricultural land situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
3/75 | Kent Sheet 3 | 6,551 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ebbsfleet Minster (Kent) Limited | 341 | K808893 | Freehold |  | excluding mines and minerals | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/75 | Kent Sheet 3 | 6,551 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ebbsfleet Minster (Kent) Limited | 341 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/75 | Kent Sheet 3 | 6,551 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/75 | Kent Sheet 3 | 6,551 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/76 | Kent Sheet 2 | 2,173 square metres, or thereabouts, of agricultural land and track situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Church Commissioners for England | 378 | K535742 | Freehold |  |  | Category 1 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/76 | Kent Sheet 2 | 2,173 square metres, or thereabouts, of agricultural land and track situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/76 | Kent Sheet 2 | 2,173 square metres, or thereabouts, of agricultural land and track situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/76 | Kent Sheet 2 | 2,173 square metres, or thereabouts, of agricultural land and track situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/76 | Kent Sheet 2 | 2,173 square metres, or thereabouts, of agricultural land and track situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James Southorn | 3137 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
3/76 | Kent Sheet 3 | 3,447 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ebbsfleet Minster (Kent) Limited | 341 | K808893 | Freehold |  | excluding mines and minerals | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/76 | Kent Sheet 3 | 3,447 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ebbsfleet Minster (Kent) Limited | 341 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/77 | Kent Sheet 3 | 7,380 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Edward Martin Spanton | 154 | K960682 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/77 | Kent Sheet 3 | 7,380 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Edward Martin Spanton | 154 | K960682 | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/77 | Kent Sheet 3 | 7,380 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/77 | Kent Sheet 3 | 7,380 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/78 | Kent Sheet 2 | 1,396 square metres, or thereabouts, of agricultural land, track and drain situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Church Commissioners for England | 378 | K535742 | Freehold |  |  | Category 1 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/78 | Kent Sheet 2 | 1,396 square metres, or thereabouts, of agricultural land, track and drain situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/78 | Kent Sheet 2 | 1,396 square metres, or thereabouts, of agricultural land, track and drain situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/78 | Kent Sheet 2 | 1,396 square metres, or thereabouts, of agricultural land, track and drain situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/78 | Kent Sheet 2 | 1,396 square metres, or thereabouts, of agricultural land, track and drain situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
3/78 | Kent Sheet 3 | 2,612 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Edward Martin Spanton | 154 | K960682 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/78 | Kent Sheet 3 | 2,612 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Edward Martin Spanton | 154 | K960682 | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/78 | Kent Sheet 3 | 2,612 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/79 | Kent Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Church Commissioners for England | 378 | K535742 | Freehold |  |  | Category 1 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/79 | Kent Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/79 | Kent Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/79 | Kent Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/79 | Kent Sheet 2 | 1,334 square metres, or thereabouts, of agricultural land situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
3/79 | Kent Sheet 3 | 2,027 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Edward Martin Spanton | 154 | K960682 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/79 | Kent Sheet 3 | 2,027 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Edward Martin Spanton | 154 | K960682 | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/79 | Kent Sheet 3 | 2,027 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/79 | Kent Sheet 3 | 2,027 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/80 | Kent Sheet 3 | 1,637 square metres, or thereabouts, of scrubland, agricultural land and track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Edward Martin Spanton | 154 |  | Freehold |  | as reputed owner | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/80 | Kent Sheet 3 | 1,637 square metres, or thereabouts, of scrubland, agricultural land and track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/80 | Kent Sheet 3 | 1,637 square metres, or thereabouts, of scrubland, agricultural land and track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Gas Networks plc | 547 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-5066 REP1-180 | [6 empty] | SU kit and apparatus | Draft under discussion |  | 09.01.2025 - Draft PPs issued on the 10th of Decemebr 2025. | No Heads of Terms Required |  | 2026-01-09
3/80 | Kent Sheet 3 | 1,637 square metres, or thereabouts, of scrubland, agricultural land and track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/80 | Kent Sheet 3 | 1,637 square metres, or thereabouts, of scrubland, agricultural land and track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/81 | Kent Sheet 2 | 921 square metres, or thereabouts, of agricultural land and private road situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
2/81 | Kent Sheet 2 | 921 square metres, or thereabouts, of agricultural land and private road situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/81 | Kent Sheet 3 | 430 square metres, or thereabouts, of scrubland situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | TT121856 | Freehold |  |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/81 | Kent Sheet 3 | 430 square metres, or thereabouts, of scrubland situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
2/82 | Kent Sheet 2 | 569 square metres, or thereabouts, of scrubland situated to the north west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
2/82 | Kent Sheet 2 | 569 square metres, or thereabouts, of scrubland situated to the north west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/82 | Kent Sheet 3 | 68 square metres, or thereabouts, of track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Edward Martin Spanton | 154 | K960682 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/82 | Kent Sheet 3 | 68 square metres, or thereabouts, of track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Edward Martin Spanton | 154 | K960682 | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/82 | Kent Sheet 3 | 68 square metres, or thereabouts, of track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/83 | Kent Sheet 2 | 2,958 square metres, or thereabouts, of public adopted highway (Marsh Farm Road), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/83 | Kent Sheet 2 | 2,958 square metres, or thereabouts, of public adopted highway (Marsh Farm Road), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Church Commissioners for England | 378 | K535742 | Freehold | subsoil fronting land to the south of Minster Station, Marsh Farm Road |  | Category 1 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/83 | Kent Sheet 2 | 2,958 square metres, or thereabouts, of public adopted highway (Marsh Farm Road), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | David John Fuller | 1335 | K280164 | Freehold | subsoil fronting land to the north of Marsh Farm, Marsh Farm Road |  | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-10-08
2/83 | Kent Sheet 2 | 2,958 square metres, or thereabouts, of public adopted highway (Marsh Farm Road), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Denton & Co Trustees Limited | 1336 | K280164 | Freehold | subsoil fronting land to the north of Marsh Farm, Marsh Farm Road | as trustee to The Dentons Self Invested Personal Pension | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-10-08
2/83 | Kent Sheet 2 | 2,958 square metres, or thereabouts, of public adopted highway (Marsh Farm Road), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/83 | Kent Sheet 2 | 2,958 square metres, or thereabouts, of public adopted highway (Marsh Farm Road), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
2/83 | Kent Sheet 2 | 2,958 square metres, or thereabouts, of public adopted highway (Marsh Farm Road), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/83 | Kent Sheet 2 | 2,958 square metres, or thereabouts, of public adopted highway (Marsh Farm Road), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/83 | Kent Sheet 2 | 2,958 square metres, or thereabouts, of public adopted highway (Marsh Farm Road), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/83 | Kent Sheet 3 | 12 square metres, or thereabouts, of scrubland situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Edward Martin Spanton | 154 | K960682 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/83 | Kent Sheet 3 | 12 square metres, or thereabouts, of scrubland situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Edward Martin Spanton | 154 | K960682 | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Church Commissioners for England | 378 | K535742 | Freehold |  |  | Category 1 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [6 empty] | SU and disputed operational | Not required |  | 09.01.2026 - Discussions ongoing | No Heads of Terms Required |  | 2026-01-09
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/84 | Kent Sheet 2 | 51,090 square metres, or thereabouts, of agricultural land, pond, track, drains, sluice and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
3/84 | Kent Sheet 3 | 19 square metres, or thereabouts, of scrubland situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | TT121856 | Freehold |  |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/84 | Kent Sheet 3 | 19 square metres, or thereabouts, of scrubland situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/85 | Kent Sheet 2 | 7,282 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The King`s Most Excellent Majesty in Right of His Crown | 458 | K933847,Crown Land Query - River Stour | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 |  |  |  | Open Space | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage.In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. 09.01.2026 – Dalcour Maclaren exchanged emails with the landowner’s agent on 5th December 2025 in relation to outstanding principles in the commercial agreements. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/85 | Kent Sheet 2 | 7,282 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/85 | Kent Sheet 3 | 2,026 square metres, or thereabouts, of scrubland, electricity distribution pole and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Kent County Council | 97 | TT121856 | Freehold |  |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/85 | Kent Sheet 3 | 2,026 square metres, or thereabouts, of scrubland, electricity distribution pole and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/85 | Kent Sheet 3 | 2,026 square metres, or thereabouts, of scrubland, electricity distribution pole and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/85 | Kent Sheet 3 | 2,026 square metres, or thereabouts, of scrubland, electricity distribution pole and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/85 | Kent Sheet 3 | 2,026 square metres, or thereabouts, of scrubland, electricity distribution pole and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/86 | Kent Sheet 2 | 6,648 square metres, or thereabouts, of river, bed, bank (River Stour), drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 2591 |  | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
2/86 | Kent Sheet 2 | 6,648 square metres, or thereabouts, of river, bed, bank (River Stour), drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/86 | Kent Sheet 3 | 33 square metres, or thereabouts, of scrubland and track (Cottington Lane) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Freehold |  | as reputed owner | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/86 | Kent Sheet 3 | 33 square metres, or thereabouts, of scrubland and track (Cottington Lane) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/87 | Kent Sheet 3 | 106 square metres, or thereabouts, of public adopted highway (Cottington Road) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/87 | Kent Sheet 3 | 106 square metres, or thereabouts, of public adopted highway (Cottington Road) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Edward Martin Spanton | 154 | K960680 | Freehold | subsoil fronting land to the north of Club House, Cottington Road |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR- 1410 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
3/87 | Kent Sheet 3 | 106 square metres, or thereabouts, of public adopted highway (Cottington Road) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Freehold | subsoil fronting railway land to the west of Great Cliffsend Farm House, Cottington Road | as reputed owner | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/87 | Kent Sheet 3 | 106 square metres, or thereabouts, of public adopted highway (Cottington Road) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/87 | Kent Sheet 3 | 106 square metres, or thereabouts, of public adopted highway (Cottington Road) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/87 | Kent Sheet 3 | 106 square metres, or thereabouts, of public adopted highway (Cottington Road) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Gas Networks plc | 547 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-5066 REP1-180 | [6 empty] | SU kit and apparatus | Draft under discussion |  | 09.01.2025 - Draft PPs issued on the 10th of Decemebr 2025. | No Heads of Terms Required |  | 2026-01-09
3/87 | Kent Sheet 3 | 106 square metres, or thereabouts, of public adopted highway (Cottington Road) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/87 | Kent Sheet 3 | 106 square metres, or thereabouts, of public adopted highway (Cottington Road) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/88 | Kent Sheet 2 | 2,138 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | John Robert Collins | 698 | K458450 | Freehold |  |  | Category 1 | Martin Allen, Elgars | Yes | RR-1465 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 04 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 6th November 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - On 19th November 2025 Dalcour Maclaren wrote to the landowner to confirm that their agent continues to be instructed in relation to the Heads of Terms. No response has been received. On 7th January 2026 Dalcour Maclaren attempted to contact the landowner by phone call to discuss Heads of Terms further and have not had a response to their voicemail. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/88 | Kent Sheet 3 | 1,220 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | St. Augustine`s Golf Club (Ramsgate) Limited | 553 |  | Freehold |  | as reputed owner | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/88 | Kent Sheet 3 | 1,220 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Timothy John Deakin | 313 | TT40208 | Leasehold |  | as trustee to St. Augustines Golf Club (Ramsgate) Limited | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/88 | Kent Sheet 3 | 1,220 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Thomas | 559 | TT40208 | Leasehold |  | as trustee to St. Augustines Golf Club (Ramsgate) Limited | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/88 | Kent Sheet 3 | 1,220 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gary Snell | 642 | TT40208 | Leasehold |  | as trustee to St. Augustines Golf Club (Ramsgate) Limited | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/88 | Kent Sheet 3 | 1,220 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Gas Networks plc | 547 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-5066 REP1-180 | [6 empty] | SU kit and apparatus | Draft under discussion |  | 09.01.2025 - Draft PPs issued on the 10th of Decemebr 2025. | No Heads of Terms Required |  | 2026-01-09
3/88 | Kent Sheet 3 | 1,220 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | St. Augustine`s Golf Club (Ramsgate) Limited | 553 |  | Occupation |  |  | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/88 | Kent Sheet 3 | 1,220 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/88 | Kent Sheet 3 | 1,220 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/88 | Kent Sheet 3 | 1,220 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/89 | Kent Sheet 3 | 404 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path and footbridge over drain situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | St. Augustine`s Golf Club (Ramsgate) Limited | 553 |  | Freehold |  | as reputed owner | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/89 | Kent Sheet 3 | 404 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path and footbridge over drain situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Timothy John Deakin | 313 | TT40208 | Leasehold |  | as trustee to St. Augustines Golf Club (Ramsgate) Limited | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/89 | Kent Sheet 3 | 404 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path and footbridge over drain situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Thomas | 559 | TT40208 | Leasehold |  | as trustee to St. Augustines Golf Club (Ramsgate) Limited | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/89 | Kent Sheet 3 | 404 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path and footbridge over drain situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gary Snell | 642 | TT40208 | Leasehold |  | as trustee to St. Augustines Golf Club (Ramsgate) Limited | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/89 | Kent Sheet 3 | 404 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path and footbridge over drain situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | St. Augustine`s Golf Club (Ramsgate) Limited | 553 |  | Occupation |  |  | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/90 | Kent Sheet 2 | 579 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/90 | Kent Sheet 2 | 579 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/90 | Kent Sheet 2 | 579 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/90 | Kent Sheet 2 | 579 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/90 | Kent Sheet 3 | 5,728 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet District Council | 167 | K628577 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporate the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/90 | Kent Sheet 3 | 5,728 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | RR-5371 | [6 empty] | SU and unknown operational | Not required |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
3/90 | Kent Sheet 3 | 5,728 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/90 | Kent Sheet 3 | 5,728 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/91 | Kent Sheet 2 | 114 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The King`s Most Excellent Majesty in Right of His Crown | 458 | K933847,Crown Land Query - River Stour | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 |  |  |  | Open Space | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage.In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. 09.01.2026 – Dalcour Maclaren exchanged emails with the landowner’s agent on 5th December 2025 in relation to outstanding principles in the commercial agreements. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/91 | Kent Sheet 3 | 355 square metres, or thereabouts, of agricultural land situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/91 | Kent Sheet 3 | 355 square metres, or thereabouts, of agricultural land situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Gas Networks plc | 547 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-5066 REP1-180 | [6 empty] | SU kit and apparatus | Draft under discussion |  | 09.01.2025 - Draft PPs issued on the 10th of Decemebr 2025. | No Heads of Terms Required |  | 2026-01-09
3/91 | Kent Sheet 3 | 355 square metres, or thereabouts, of agricultural land situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/91 | Kent Sheet 3 | 355 square metres, or thereabouts, of agricultural land situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/92 | Kent Sheet 2 | 109 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 2591 |  | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Ian Peter Alan Smith | 2669 | K564173 | Freehold |  |  | Category 1 | Stuart Mair, George Webb Finn | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 10th October 2025 to discuss the Sea Link project and the landowners proposed use for the land. Engagement is ongoing with the landowner’s agent following the meeting. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 7th January 2026. Engagement is ongoing in relation to overlapping development proposals. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Gas Networks plc | 547 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-5066 REP1-180 | [6 empty] | SU kit and apparatus | Draft under discussion |  | 09.01.2025 - Draft PPs issued on the 10th of Decemebr 2025. | No Heads of Terms Required |  | 2026-01-09
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Ian Peter Alan Smith | 2669 | K564173 | Occupation |  |  | Category 1 | Stuart Mair, George Webb Finn | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 10th October 2025 to discuss the Sea Link project and the landowners proposed use for the land. Engagement is ongoing with the landowner’s agent following the meeting. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 7th January 2026. Engagement is ongoing in relation to overlapping development proposals. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/92 | Kent Sheet 3 | 2,199 square metres, or thereabouts, of agricultural land, track and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/93 | Kent Sheet 2 | 138 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/93 | Kent Sheet 2 | 138 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/93 | Kent Sheet 2 | 138 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/93 | Kent Sheet 2 | 138 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/93 | Kent Sheet 3 | 118 square metres, or thereabouts, of scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Kent County Council | 97 | K745070 | Freehold |  |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/93 | Kent Sheet 3 | 118 square metres, or thereabouts, of scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Kent County Council | 97 | K745070 | Occupation |  |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/93 | Kent Sheet 3 | 118 square metres, or thereabouts, of scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/93 | Kent Sheet 3 | 118 square metres, or thereabouts, of scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Gas Networks plc | 547 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-5066 REP1-180 | [6 empty] | SU kit and apparatus | Draft under discussion |  | 09.01.2025 - Draft PPs issued on the 10th of Decemebr 2025. | No Heads of Terms Required |  | 2026-01-09
2/94 | Kent Sheet 2 | 7,226 square metres, or thereabouts, of grassland, drain and track situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/94 | Kent Sheet 2 | 7,226 square metres, or thereabouts, of grassland, drain and track situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/94 | Kent Sheet 2 | 7,226 square metres, or thereabouts, of grassland, drain and track situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/94 | Kent Sheet 2 | 7,226 square metres, or thereabouts, of grassland, drain and track situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Peter Alan Smith | 2669 | K564173 | Freehold |  |  | Category 1 | Stuart Mair, George Webb Finn | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 10th October 2025 to discuss the Sea Link project and the landowners proposed use for the land. Engagement is ongoing with the landowner’s agent following the meeting. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 7th January 2026. Engagement is ongoing in relation to overlapping development proposals. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/94 | Kent Sheet 3 | 8,600 square metres, or thereabouts, of agricultural land and scrubland situated to the north east of Cliffsend Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Peter Alan Smith | 2669 | K564173 | Occupation |  |  | Category 1 | Stuart Mair, George Webb Finn | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 10th October 2025 to discuss the Sea Link project and the landowners proposed use for the land. Engagement is ongoing with the landowner’s agent following the meeting. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 7th January 2026. Engagement is ongoing in relation to overlapping development proposals. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/95 | Kent Sheet 2 | 1,900 square metres, or thereabouts, of agricultural land, grassland and drain situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/95 | Kent Sheet 2 | 1,900 square metres, or thereabouts, of agricultural land, grassland and drain situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/95 | Kent Sheet 2 | 1,900 square metres, or thereabouts, of agricultural land, grassland and drain situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/95 | Kent Sheet 2 | 1,900 square metres, or thereabouts, of agricultural land, grassland and drain situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/95 | Kent Sheet 3 | 3 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/95 | Kent Sheet 3 | 3 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/96 | Kent Sheet 2 | 81 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/96 | Kent Sheet 2 | 81 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/96 | Kent Sheet 2 | 81 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/96 | Kent Sheet 2 | 81 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/96 | Kent Sheet 3 | 105 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the north east of Cliffsend Farm Cottages, Kent, ﻿Class 9. ﻿Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ﻿Class 9. ﻿Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/96 | Kent Sheet 3 | 105 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the north east of Cliffsend Farm Cottages, Kent, ﻿Class 9. ﻿Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ﻿Class 9. ﻿Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Peter Alan Smith | 2669 | K564173 | Freehold | subsoil fronting land to the north west of Little Cliffsend Farm, Sandwich Road |  | Category 1 | Stuart Mair, George Webb Finn | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 10th October 2025 to discuss the Sea Link project and the landowners proposed use for the land. Engagement is ongoing with the landowner’s agent following the meeting. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 7th January 2026. Engagement is ongoing in relation to overlapping development proposals. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/96 | Kent Sheet 3 | 105 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the north east of Cliffsend Farm Cottages, Kent, ﻿Class 9. ﻿Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ﻿Class 9. ﻿Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/96 | Kent Sheet 3 | 105 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the north east of Cliffsend Farm Cottages, Kent, ﻿Class 9. ﻿Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ﻿Class 9. ﻿Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/96 | Kent Sheet 3 | 105 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the north east of Cliffsend Farm Cottages, Kent, ﻿Class 9. ﻿Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ﻿Class 9. ﻿Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Gas Networks plc | 547 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-5066 REP1-180 | [6 empty] | SU kit and apparatus | Draft under discussion |  | 09.01.2025 - Draft PPs issued on the 10th of Decemebr 2025. | No Heads of Terms Required |  | 2026-01-09
3/96 | Kent Sheet 3 | 105 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the north east of Cliffsend Farm Cottages, Kent, ﻿Class 9. ﻿Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ﻿Class 9. ﻿Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/97 | Kent Sheet 3 | 251 square metres, or thereabouts, of public adopted highway (Sandwich Road), cycle way and footpath situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/97 | Kent Sheet 3 | 251 square metres, or thereabouts, of public adopted highway (Sandwich Road), cycle way and footpath situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet District Council | 167 | K628577 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporate the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/97 | Kent Sheet 3 | 251 square metres, or thereabouts, of public adopted highway (Sandwich Road), cycle way and footpath situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/97 | Kent Sheet 3 | 251 square metres, or thereabouts, of public adopted highway (Sandwich Road), cycle way and footpath situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/97 | Kent Sheet 3 | 251 square metres, or thereabouts, of public adopted highway (Sandwich Road), cycle way and footpath situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/97 | Kent Sheet 3 | 251 square metres, or thereabouts, of public adopted highway (Sandwich Road), cycle way and footpath situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/97 | Kent Sheet 3 | 251 square metres, or thereabouts, of public adopted highway (Sandwich Road), cycle way and footpath situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/98 | Kent Sheet 2 | 889 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The King`s Most Excellent Majesty in Right of His Crown | 458 | K933847,Crown Land Query - River Stour | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 |  |  |  | Open Space | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage.In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. 09.01.2026 – Dalcour Maclaren exchanged emails with the landowner’s agent on 5th December 2025 in relation to outstanding principles in the commercial agreements. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/98 | Kent Sheet 3 | 218 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/98 | Kent Sheet 3 | 218 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/98 | Kent Sheet 3 | 218 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown Occupier of Caravan | 3546 |  | Occupation |  |  | Category 1 |  | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/99 | Kent Sheet 2 | 1,113 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/99 | Kent Sheet 2 | 1,113 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/99 | Kent Sheet 2 | 1,113 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/99 | Kent Sheet 2 | 1,113 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/99 | Kent Sheet 3 | 14,375 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | St. Augustine`s Golf Club (Ramsgate) Limited | 553 |  | Freehold |  | as reputed owner | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/99 | Kent Sheet 3 | 14,375 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Timothy John Deakin | 313 | TT40208 | Leasehold |  | as trustee to St. Augustines Golf Club (Ramsgate) Limited | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/99 | Kent Sheet 3 | 14,375 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Thomas | 559 | TT40208 | Leasehold |  | as trustee to St. Augustines Golf Club (Ramsgate) Limited | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/99 | Kent Sheet 3 | 14,375 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Gary Snell | 642 | TT40208 | Leasehold |  | as trustee to St. Augustines Golf Club (Ramsgate) Limited | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/99 | Kent Sheet 3 | 14,375 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/99 | Kent Sheet 3 | 14,375 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | St. Augustine`s Golf Club (Ramsgate) Limited | 553 |  | Occupation |  |  | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/99 | Kent Sheet 3 | 14,375 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [6 empty] | SU and disputed operational | Not required |  | 09.01.2026 - Discussions ongoing | No Heads of Terms Required |  | 2026-01-09
1/13 | Kent Sheet 1 | 455 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/13 | Kent Sheet 1 | 455 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
1/13 | Kent Sheet 1 | 455 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
1/13 | Kent Sheet 1 | 455 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/13 | Kent Sheet 2 | 3,834 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/13 | Kent Sheet 2 | 3,834 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/13 | Kent Sheet 2 | 3,834 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/13 | Kent Sheet 2 | 3,834 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/13 | Kent Sheet 3 | 1,219 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 | TT29616 | Freehold |  |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/13 | Kent Sheet 3 | 1,219 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/13 | Kent Sheet 3 | 1,219 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/13 | Kent Sheet 4 | 1,156 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/13 | Kent Sheet 4 | 1,156 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Kent County Council | 97 | K377523 | Freehold | subsoil fronting land to the west of Ebbsfleet Farm Cottages, Ebbsfleet Lane |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/13 | Kent Sheet 4 | 1,156 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/13 | Kent Sheet 4 | 1,156 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
4/13 | Kent Sheet 4 | 1,156 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/13 | Kent Sheet 4 | 1,156 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/13 | Kent Sheet 4 | 1,156 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/13 | Kent Sheet 5 | 92,778 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent Wildlife Trust | 498 | K410629 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/13 | Kent Sheet 5 | 92,778 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent Wildlife Trust | 498 |  | Occupation |  |  | Category 1 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/14 | Kent Sheet 1 | 8,833 square metres, or thereabouts, of grassland, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/14 | Kent Sheet 1 | 8,833 square metres, or thereabouts, of grassland, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
1/14 | Kent Sheet 1 | 8,833 square metres, or thereabouts, of grassland, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
1/14 | Kent Sheet 1 | 8,833 square metres, or thereabouts, of grassland, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/14 | Kent Sheet 1 | 8,833 square metres, or thereabouts, of grassland, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/14 | Kent Sheet 2 | 2,555 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/14 | Kent Sheet 2 | 2,555 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/14 | Kent Sheet 2 | 2,555 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/14 | Kent Sheet 2 | 2,555 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/14 | Kent Sheet 3 | 429 square metres, or thereabouts, of agricultural land and private road (Jutes Lane), situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 | TT29616 | Freehold |  |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/14 | Kent Sheet 4 | 18 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/14 | Kent Sheet 4 | 18 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/14 | Kent Sheet 5 | 4,138 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The King`s Most Excellent Majesty in Right of His Crown | 458 | Pegwell Bay & Crown | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 |  |  |  | Open Space | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage.In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. 09.01.2026 – Dalcour Maclaren exchanged emails with the landowner’s agent on 5th December 2025 in relation to outstanding principles in the commercial agreements. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/15 | Kent Sheet 1 | 894 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/15 | Kent Sheet 1 | 894 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
1/15 | Kent Sheet 1 | 894 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
1/15 | Kent Sheet 1 | 894 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/15 | Kent Sheet 2 | 204 square metres, or thereabouts, of drain, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/15 | Kent Sheet 2 | 204 square metres, or thereabouts, of drain, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/15 | Kent Sheet 3 | 1,652 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | TT29616 | Freehold |  |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/15 | Kent Sheet 3 | 1,652 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/15 | Kent Sheet 3 | 1,652 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/15 | Kent Sheet 4 | 166 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/15 | Kent Sheet 4 | 166 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/15 | Kent Sheet 5 | 94,015 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The King`s Most Excellent Majesty in Right of His Crown | 458 | Pegwell Bay & Crown | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 |  |  |  | Open Space | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage.In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. 09.01.2026 – Dalcour Maclaren exchanged emails with the landowner’s agent on 5th December 2025 in relation to outstanding principles in the commercial agreements. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/16 | Kent Sheet 1 | 754 square metres, or thereabouts, of agricultural land, track and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/16 | Kent Sheet 1 | 754 square metres, or thereabouts, of agricultural land, track and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
1/16 | Kent Sheet 1 | 754 square metres, or thereabouts, of agricultural land, track and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
1/16 | Kent Sheet 1 | 754 square metres, or thereabouts, of agricultural land, track and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/16 | Kent Sheet 2 | 75 square metres, or thereabouts, of drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/16 | Kent Sheet 3 | 247 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/16 | Kent Sheet 3 | 247 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | TT104661 | Freehold | subsoil fronting land to the north of Ebbsfleet Farm Cottages, Ebbsfleet Lane |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/16 | Kent Sheet 3 | 247 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | TT29616 | Freehold | subsoil fronting land to the north west of Ebbsfleet Farm Cottages, Ebbsfleet Lane |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/16 | Kent Sheet 3 | 247 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/16 | Kent Sheet 3 | 247 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/16 | Kent Sheet 4 | 72 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K868267 | Freehold |  |  | Category 1 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/16 | Kent Sheet 5 | 2,940 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The King`s Most Excellent Majesty in Right of His Crown | 458 | Pegwell Bay & Crown | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 |  |  |  | Open Space | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage.In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. 09.01.2026 – Dalcour Maclaren exchanged emails with the landowner’s agent on 5th December 2025 in relation to outstanding principles in the commercial agreements. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/17 | Kent Sheet 1 | 1,129 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/17 | Kent Sheet 1 | 1,129 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
1/17 | Kent Sheet 1 | 1,129 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
1/17 | Kent Sheet 1 | 1,129 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/17 | Kent Sheet 3 | 3,830 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/17 | Kent Sheet 3 | 3,830 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/17 | Kent Sheet 4 | 719 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K868267 | Freehold |  |  | Category 1 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/17 | Kent Sheet 5 | 470 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporate the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/17 | Kent Sheet 5 | 470 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | RR-5371 | [6 empty] | SU and unknown operational | Not required |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
1/18 | Kent Sheet 1 | 8,477 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/18 | Kent Sheet 1 | 8,477 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
1/18 | Kent Sheet 1 | 8,477 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
1/18 | Kent Sheet 1 | 8,477 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/18 | Kent Sheet 1 | 8,477 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/18 | Kent Sheet 3 | 104 square metres, or thereabouts, of private road (Jutes Lane) situated to the south of Sevenscore Oast, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/18 | Kent Sheet 4 | 2,404 square metres, or thereabouts, of wooded area, private road, track and overhead electricity distribution lines situated to the south west of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K838442 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/18 | Kent Sheet 4 | 2,404 square metres, or thereabouts, of wooded area, private road, track and overhead electricity distribution lines situated to the south west of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K838442 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/18 | Kent Sheet 4 | 2,404 square metres, or thereabouts, of wooded area, private road, track and overhead electricity distribution lines situated to the south west of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/18 | Kent Sheet 4 | 2,404 square metres, or thereabouts, of wooded area, private road, track and overhead electricity distribution lines situated to the south west of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/18 | Kent Sheet 5 | 25,439 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent Wildlife Trust | 498 | K410629 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/18 | Kent Sheet 5 | 25,439 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent Wildlife Trust | 498 |  | Occupation |  |  | Category 1 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/19 | Kent Sheet 1 | 8 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/19 | Kent Sheet 1 | 8 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
1/19 | Kent Sheet 1 | 8 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
1/19 | Kent Sheet 1 | 8 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/19 | Kent Sheet 1 | 8 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/19 | Kent Sheet 3 | 123 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/19 | Kent Sheet 3 | 123 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 | TT104661 | Freehold | subsoil fronting land to the north of Ebbsfleet Farm Cottages, Ebbsfleet Lane |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/19 | Kent Sheet 3 | 123 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 | TT29616 | Freehold | subsoil fronting land to the north west of Ebbsfleet Farm Cottages, Ebbsfleet Lane |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/19 | Kent Sheet 3 | 123 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/19 | Kent Sheet 3 | 123 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | TT165118 | Freehold |  |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 |  | Occupation |  |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU and disputed operational | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/19 | Kent Sheet 4 | 2,781 square metres, or thereabouts, of private road (Jutes Lane), scrubland and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/20 | Kent Sheet 1 | 2,896 square metres, or thereabouts, of agricultural land, track and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/20 | Kent Sheet 1 | 2,896 square metres, or thereabouts, of agricultural land, track and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
1/20 | Kent Sheet 1 | 2,896 square metres, or thereabouts, of agricultural land, track and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
1/20 | Kent Sheet 1 | 2,896 square metres, or thereabouts, of agricultural land, track and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/20 | Kent Sheet 3 | 75 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/20 | Kent Sheet 3 | 75 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/20 | Kent Sheet 4 | 26 square metres, or thereabouts, of private road (Jutes Lane) and scrubland situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | TT10526 | Freehold |  |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/20 | Kent Sheet 4 | 26 square metres, or thereabouts, of private road (Jutes Lane) and scrubland situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | TT10526 | Occupation |  |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/21 | Kent Sheet 1 | 6,595 square metres, or thereabouts, of agricultural land, track, drain, electricity transmission pylon and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/21 | Kent Sheet 1 | 6,595 square metres, or thereabouts, of agricultural land, track, drain, electricity transmission pylon and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
1/21 | Kent Sheet 1 | 6,595 square metres, or thereabouts, of agricultural land, track, drain, electricity transmission pylon and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
1/21 | Kent Sheet 1 | 6,595 square metres, or thereabouts, of agricultural land, track, drain, electricity transmission pylon and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/21 | Kent Sheet 1 | 6,595 square metres, or thereabouts, of agricultural land, track, drain, electricity transmission pylon and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/21 | Kent Sheet 2 | 1,322 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/21 | Kent Sheet 2 | 1,322 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/21 | Kent Sheet 2 | 1,322 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/21 | Kent Sheet 2 | 1,322 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/21 | Kent Sheet 3 | 55 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/21 | Kent Sheet 3 | 55 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/21 | Kent Sheet 4 | 777 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the south of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Kent County Council | 97 | K811125 | Freehold |  |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/21 | Kent Sheet 4 | 777 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the south of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/21 | Kent Sheet 4 | 777 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the south of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/21 | Kent Sheet 4 | 777 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the south of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/21 | Kent Sheet 4 | 777 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the south of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/22 | Kent Sheet 1 | 4,461 square metres, or thereabouts, of agricultural land situated to the north west of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/22 | Kent Sheet 1 | 4,461 square metres, or thereabouts, of agricultural land situated to the north west of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
1/22 | Kent Sheet 1 | 4,461 square metres, or thereabouts, of agricultural land situated to the north west of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
1/22 | Kent Sheet 1 | 4,461 square metres, or thereabouts, of agricultural land situated to the north west of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/22 | Kent Sheet 3 | 258 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/22 | Kent Sheet 3 | 258 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/22 | Kent Sheet 3 | 258 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/22 | Kent Sheet 4 | 700 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/22 | Kent Sheet 4 | 700 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | James Bedford Pace | 184 | K716057 | Freehold | subsoil fronting land to the north west of Stoneless Farm Bungalow, Ebbsfleet Lane |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/22 | Kent Sheet 4 | 700 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Alexandra Ruth Pace | 637 | K716057 | Freehold | subsoil fronting land to the north west of Stoneless Farm Bungalow, Ebbsfleet Lane |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/22 | Kent Sheet 4 | 700 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Robert John Chapman | 654 | K651171 | Freehold | subsoil fronting land to the north of Stonelees Farm Bungalow, Ebbsfleet Lane |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/22 | Kent Sheet 4 | 700 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/22 | Kent Sheet 4 | 700 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
4/22 | Kent Sheet 4 | 700 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
4/22 | Kent Sheet 4 | 700 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/22 | Kent Sheet 4 | 700 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/22 | Kent Sheet 4 | 700 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/23 | Kent Sheet 2 | 1,908 square metres, or thereabouts, of grassland and drain situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | John Robert Collins | 698 | K458450 | Freehold |  |  | Category 1 | Martin Allen, Elgars | Yes | RR-1465 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 04 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 6th November 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - On 19th November 2025 Dalcour Maclaren wrote to the landowner to confirm that their agent continues to be instructed in relation to the Heads of Terms. No response has been received. On 7th January 2026 Dalcour Maclaren attempted to contact the landowner by phone call to discuss Heads of Terms further and have not had a response to their voicemail. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/23 | Kent Sheet 3 | 53 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/23 | Kent Sheet 3 | 53 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold | subsoil fronting land to the south of Sevenscore Crossing, Ebbsfleet Lane North |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/23 | Kent Sheet 3 | 53 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/23 | Kent Sheet 3 | 53 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/23 | Kent Sheet 4 | 129 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/23 | Kent Sheet 4 | 129 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James Bedford Pace | 184 | K716057 | Freehold | subsoil fronting land to the north west of Stoneless Farm Bungalow, Ebbsfleet Lane |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/23 | Kent Sheet 4 | 129 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Alexandra Ruth Pace | 637 | K716057 | Freehold | subsoil fronting land to the north west of Stoneless Farm Bungalow, Ebbsfleet Lane |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/23 | Kent Sheet 4 | 129 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert John Chapman | 654 | K651171 | Freehold | subsoil fronting land to the north of Stonelees Farm Bungalow, Ebbsfleet Lane |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/23 | Kent Sheet 4 | 129 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert John Chapman | 654 | K651171 | Freehold | subsoil fronting land to the north of Stonelees House, Ebbsfleet Lane |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/23 | Kent Sheet 4 | 129 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/23 | Kent Sheet 4 | 129 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
4/23 | Kent Sheet 4 | 129 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/23 | Kent Sheet 4 | 129 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/24 | Kent Sheet 2 | 711 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | John Robert Collins | 698 | K56551 | Freehold |  | excluding mines and minerals | Category 1 | Martin Allen, Elgars | Yes | RR-1465 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 04 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 6th November 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - On 19th November 2025 Dalcour Maclaren wrote to the landowner to confirm that their agent continues to be instructed in relation to the Heads of Terms. No response has been received. On 7th January 2026 Dalcour Maclaren attempted to contact the landowner by phone call to discuss Heads of Terms further and have not had a response to their voicemail. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/24 | Kent Sheet 3 | 25 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/24 | Kent Sheet 3 | 25 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Ebbsfleet Minster (Kent) Limited | 341 | K808893 | Freehold | subsoil fronting land to the south west of Cottington Hill, Ebbsfleet Lane North |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/24 | Kent Sheet 3 | 25 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Struan Gordon Robertson | 494 | K755310 | Freehold | subsoil fronting land to the south of Sevenscore Crossing, Ebbsfleet Lane North |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/24 | Kent Sheet 3 | 25 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/24 | Kent Sheet 4 | 18 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/24 | Kent Sheet 4 | 18 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert John Chapman | 654 | K651171 | Freehold | subsoil fronting land to the north of Stonelees Farm Bungalow, Ebbsfleet Lane |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/24 | Kent Sheet 4 | 18 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert John Chapman | 654 | K651171 | Freehold | subsoil fronting land to the north of Stonelees House, Ebbsfleet Lane |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/24 | Kent Sheet 4 | 18 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/24 | Kent Sheet 4 | 18 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/25 | Kent Sheet 3 | 6 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/25 | Kent Sheet 3 | 6 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold | subsoil fronting land to the south of Sevenscore Crossing, Ebbsfleet Lane North |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/25 | Kent Sheet 3 | 6 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/25 | Kent Sheet 3 | 6 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Robert John Chapman | 654 | K651171,K985109 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/25 | Kent Sheet 4 | 3,119 square metres, or thereabouts, of golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Stonelees Golf Centre | 3413 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/25 | Kent Sheet 5 | 71,976 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporate the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/25 | Kent Sheet 5 | 71,976 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | RR-5371 | [6 empty] | SU and unknown operational | Not required |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | TT103427 | Freehold | subsoil fronting land to the south west of Kings End Cottage, Richborough Road |  | Category 1 | No Agent Known | No | [7 empty] | SU and disputed operational | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Nigel Stewart Daw | 1015 | K77907 | Freehold | subsoil fronting land to the south of Kings End Cottage, Richborough Road |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-10-08
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Dorcas Muriel Daw | 2370 | K77907 | Freehold | subsoil fronting land to the south of Kings End Cottage, Richborough Road |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-10-08
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Samuel David Price | 2386 | K90346 | Freehold | subsoil fronting land at King`s End Farm, Richborough Road |  | Category 1 | N/A | Yes | RR-4767 | [6 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-01-09
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Amy Elizabeth Price | 2387 | K90346 | Freehold | subsoil fronting land at King`s End Farm, Richborough Road |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-10-08
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/1 | Kent Sheet 2 | 5,962 square metres, or thereabouts, of agricultural land and drain situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/1 | Kent Sheet 2 | 5,962 square metres, or thereabouts, of agricultural land and drain situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/1 | Kent Sheet 2 | 5,962 square metres, or thereabouts, of agricultural land and drain situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/1 | Kent Sheet 2 | 5,962 square metres, or thereabouts, of agricultural land and drain situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
4/1 | Kent Sheet 4 | 363 square metres, or thereabouts, of agricultural land situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/1 | Kent Sheet 4 | 363 square metres, or thereabouts, of agricultural land situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/1 | Kent Sheet 5 | 11,625 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | N/A Mark Warnett, Ardent | Yes | RR-5384 |  |  |  | National Trust |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025 and are arranging a meeting with the landowner’s agent in January. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/1 | Kent Sheet 5 | 11,625 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent Wildlife Trust | 498 | TT41175 | Leasehold |  |  | Category 1 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/1 | Kent Sheet 6 | 127,268 square metres, or thereabouts, of agricultural land, drains and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Wallace John Wilson-Haffenden | 3258 | K273192 | Freehold |  |  | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting on the 14th November 2025 with the landowner's agent to discuss the proposed terms in more detail. 09.01.2026 – On 3rd December 2025, Dalcour Maclaren re-issued the Heads of Terms to the landowner’s agent to seek their feedback. A follow up email was sent on the 18th December 2025. Engagement continues in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/1 | Kent Sheet 6 | 127,268 square metres, or thereabouts, of agricultural land, drains and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
6/1 | Kent Sheet 6 | 127,268 square metres, or thereabouts, of agricultural land, drains and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
6/1 | Kent Sheet 6 | 127,268 square metres, or thereabouts, of agricultural land, drains and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
6/1 | Kent Sheet 6 | 127,268 square metres, or thereabouts, of agricultural land, drains and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Wallace John Wilson-Haffenden | 3258 | K273192 | Occupation |  |  | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting on the 14th November 2025 with the landowner's agent to discuss the proposed terms in more detail. 09.01.2026 – On 3rd December 2025, Dalcour Maclaren re-issued the Heads of Terms to the landowner’s agent to seek their feedback. A follow up email was sent on the 18th December 2025. Engagement continues in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/1 | Kent Sheet 6 | 127,268 square metres, or thereabouts, of agricultural land, drains and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/2 | Kent Sheet 1 | 2,988 square metres, or thereabouts, of private road (Whitehouse Drove), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Castle Farm, Kent, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Andrew William Johnson | 3566 | K839921 | Freehold |  | excluding mines and minerals | Category 1 |  | No | [11 empty] | No Heads of Terms Required |  | 2026-01-09
1/2 | Kent Sheet 1 | 2,988 square metres, or thereabouts, of private road (Whitehouse Drove), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Castle Farm, Kent, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/2 | Kent Sheet 1 | 2,988 square metres, or thereabouts, of private road (Whitehouse Drove), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Castle Farm, Kent, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/2 | Kent Sheet 2 | 41,204 square metres, or thereabouts, of agricultural land, drain and sluice situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/2 | Kent Sheet 2 | 41,204 square metres, or thereabouts, of agricultural land, drain and sluice situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/2 | Kent Sheet 2 | 41,204 square metres, or thereabouts, of agricultural land, drain and sluice situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/2 | Kent Sheet 2 | 41,204 square metres, or thereabouts, of agricultural land, drain and sluice situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/2 | Kent Sheet 3 | 531 square metres, or thereabouts, of private road (Brook Lane), overhead telecommunication lines and overhead electricity distribution lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/2 | Kent Sheet 3 | 531 square metres, or thereabouts, of private road (Brook Lane), overhead telecommunication lines and overhead electricity distribution lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/2 | Kent Sheet 3 | 531 square metres, or thereabouts, of private road (Brook Lane), overhead telecommunication lines and overhead electricity distribution lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/2 | Kent Sheet 3 | 531 square metres, or thereabouts, of private road (Brook Lane), overhead telecommunication lines and overhead electricity distribution lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/2 | Kent Sheet 4 | 37 square metres, or thereabouts, of agricultural land situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 | TT29616 | Freehold |  |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/2 | Kent Sheet 6 | 104 square metres, or thereabouts, of scrubland and track situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Wallace John Wilson-Haffenden | 3258 | K273192 | Freehold |  |  | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting on the 14th November 2025 with the landowner's agent to discuss the proposed terms in more detail. 09.01.2026 – On 3rd December 2025, Dalcour Maclaren re-issued the Heads of Terms to the landowner’s agent to seek their feedback. A follow up email was sent on the 18th December 2025. Engagement continues in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/2 | Kent Sheet 6 | 104 square metres, or thereabouts, of scrubland and track situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Wallace John Wilson-Haffenden | 3258 | K273192 | Occupation |  |  | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting on the 14th November 2025 with the landowner's agent to discuss the proposed terms in more detail. 09.01.2026 – On 3rd December 2025, Dalcour Maclaren re-issued the Heads of Terms to the landowner’s agent to seek their feedback. A follow up email was sent on the 18th December 2025. Engagement continues in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/3 | Kent Sheet 1 | 40 square metres, or thereabouts, of private road (Whitehouse Drove) situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/3 | Kent Sheet 1 | 40 square metres, or thereabouts, of private road (Whitehouse Drove) situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
1/3 | Kent Sheet 1 | 40 square metres, or thereabouts, of private road (Whitehouse Drove) situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
1/3 | Kent Sheet 1 | 40 square metres, or thereabouts, of private road (Whitehouse Drove) situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/26 | Kent Sheet 3 | 255 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/26 | Kent Sheet 3 | 255 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 | TT104661 | Freehold | subsoil fronting land to the north of Ebbsfleet Farm Cottages, Ebbsfleet Lane |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/26 | Kent Sheet 3 | 255 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ebbsfleet Minster (Kent) Limited | 341 | K808893 | Freehold | subsoil fronting land to the south west of Cottington Hill, Ebbsfleet Lane North |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/26 | Kent Sheet 3 | 255 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold | subsoil fronting land to the south of Sevenscore Crossing, Ebbsfleet Lane North |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/26 | Kent Sheet 3 | 255 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/26 | Kent Sheet 3 | 255 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/3 | Kent Sheet 2 | 430 square metres, or thereabouts, of agricultural land and track situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/3 | Kent Sheet 2 | 430 square metres, or thereabouts, of agricultural land and track situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/3 | Kent Sheet 2 | 430 square metres, or thereabouts, of agricultural land and track situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/3 | Kent Sheet 2 | 430 square metres, or thereabouts, of agricultural land and track situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/3 | Kent Sheet 3 | 133 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North), Ramsgate, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/3 | Kent Sheet 3 | 133 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North), Ramsgate, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | K377019 | Freehold | subsoil fronting land to the south of Sevenscore Crossing, Ebbsfleet Lane North |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/3 | Kent Sheet 3 | 133 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North), Ramsgate, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Struan Gordon Robertson | 494 | K755310 | Freehold | subsoil fronting land to the south of Sevenscore Crossing, Ebbsfleet Lane North |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/3 | Kent Sheet 3 | 133 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North), Ramsgate, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | HMS Two Incorporated Limited | 576 | K670281 | Freehold | subsoil fronting land to the south of 6 Sevenscore Farm Cottage, Ebbsfleet Lane North |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-10-08
3/3 | Kent Sheet 3 | 133 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North), Ramsgate, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/3 | Kent Sheet 3 | 133 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North), Ramsgate, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/3 | Kent Sheet 4 | 47 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | K405978 | Freehold |  | excluding mines and minerals | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/3 | Kent Sheet 6 | 164 square metres, or thereabouts, of scrubland and track situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Trapoc Limited | 538 | K563834 | Freehold |  |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid intend to secure the rights of access through the terms issued for plots 6/1 and 6/1 (Kent). 03.10.2025 - Despite several attempts, no response has been received from this Landowner. 18.11.2025 - Dalcour Maclaren are engaging with the landowner regarding Heads of Terms. On 4th November 2025 the landowner confirmed they do not have any objection in principle to the proposals. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner regarding Heads of Terms. Dalcour Maclaren spoke to the landowner on 17th December 2025 who confirmed that they will provide feedback on the Terms in January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/3 | Kent Sheet 6 | 164 square metres, or thereabouts, of scrubland and track situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Trapoc Limited | 538 | K563834 | Occupation |  |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid intend to secure the rights of access through the terms issued for plots 6/1 and 6/1 (Kent). 03.10.2025 - Despite several attempts, no response has been received from this Landowner. 18.11.2025 - Dalcour Maclaren are engaging with the landowner regarding Heads of Terms. On 4th November 2025 the landowner confirmed they do not have any objection in principle to the proposals. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner regarding Heads of Terms. Dalcour Maclaren spoke to the landowner on 17th December 2025 who confirmed that they will provide feedback on the Terms in January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/4 | Kent Sheet 1 | 227 square metres, or thereabouts, of private road (Whitehouse Drove) situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/4 | Kent Sheet 1 | 227 square metres, or thereabouts, of private road (Whitehouse Drove) situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
1/4 | Kent Sheet 1 | 227 square metres, or thereabouts, of private road (Whitehouse Drove) situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
1/4 | Kent Sheet 1 | 227 square metres, or thereabouts, of private road (Whitehouse Drove) situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Jean Veronica Spanton | 39 | K617169 | Freehold | subsoil fronting Stoneless Farm Bungalow, Ebbsfleet Lane |  | Category 1 | N/A Joe Hearnden, BTF Partnership | Yes | RR-5840 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Positive engagement has continued with this landowner and or their agent and it is anticipated an agreement will be reached by the end of Examination. 18.11.2025 - Following a meeting held on 12th September 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on the reasoning behind the rights to be acquired. Dalcour Maclaren provided this and re-issued the Heads of Terms on the 29th October 2025, engagement is ongoing. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025, 1st December 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 29th October 2025. Dalcour Maclaren proceeded to contact the landowner’s son on the 07th January 2026 and issued a copy of the Heads of Terms directly to him for review and discussion. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Jean Veronica Spanton | 39 | K391707 | Freehold | subsoil fronting Stoneless House, Ebbsfleet lane |  | Category 1 | N/A Joe Hearnden, BTF Partnership | Yes | RR-5840 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Positive engagement has continued with this landowner and or their agent and it is anticipated an agreement will be reached by the end of Examination. 18.11.2025 - Following a meeting held on 12th September 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on the reasoning behind the rights to be acquired. Dalcour Maclaren provided this and re-issued the Heads of Terms on the 29th October 2025, engagement is ongoing. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025, 1st December 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 29th October 2025. Dalcour Maclaren proceeded to contact the landowner’s son on the 07th January 2026 and issued a copy of the Heads of Terms directly to him for review and discussion. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Natalie Anne Brudenell | 159 | K981650 | Freehold | subsoil fronting Stoneless Cottages, Ebbsfleet Lane |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-10-08
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | James Bedford Pace | 184 | K716057 | Freehold | subsoil fronting land to the north west of Stoneless Farm Bungalow, Ebbsfleet Lane |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Gavin Johnson | 524 | K981650 | Freehold | subsoil fronting Stoneless Cottages, Ebbsfleet Lane |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-10-08
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Alexandra Ruth Pace | 637 | K716057 | Freehold | subsoil fronting land to the north west of Stoneless Farm Bungalow, Ebbsfleet Lane |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Robert John Chapman | 654 | K651171 | Freehold | subsoil fronting land to the north of Stonelees Farm Bungalow, Ebbsfleet Lane |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Personal Representative to the Estate of Christopher John Spanton | 3526 | K617169 | Freehold | subsoil fronting Stoneless Farm Bungalow, Ebbsfleet Lane |  | Category 1 | Joe Hearnden, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Positive engagement has continued with this landowner and or their agent and it is anticipated an agreement will be reached by the end of Examination. OR This individual has passed away, see update in AP ref 39 | Heads of Terms negotiations ongoing |  | 2025-10-08
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Personal Representative to the Estate of Christopher John Spanton | 3526 | K391707 | Freehold | subsoil fronting Stoneless House, Ebbsfleet lane |  | Category 1 | Joe Hearnden, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Positive engagement has continued with this landowner and or their agent and it is anticipated an agreement will be reached by the end of Examination. OR This individual has passed away, see update in AP ref 39 | Heads of Terms negotiations ongoing |  | 2025-10-08
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Gas Networks plc | 547 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-5066 REP1-180 | [6 empty] | SU kit and apparatus | Draft under discussion |  | 09.01.2025 - Draft PPs issued on the 10th of Decemebr 2025. | No Heads of Terms Required |  | 2026-01-09
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/4 | Kent Sheet 2 | 12,153 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/4 | Kent Sheet 2 | 12,153 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/4 | Kent Sheet 2 | 12,153 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/4 | Kent Sheet 2 | 12,153 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/4 | Kent Sheet 2 | 12,153 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/4 | Kent Sheet 3 | 16 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | K377019 | Freehold |  | excluding mines and minerals below a depth of 300 feet from the surface | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/4 | Kent Sheet 3 | 16 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/4 | Kent Sheet 3 | 16 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/4 | Kent Sheet 4 | 151 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/4 | Kent Sheet 4 | 151 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | K405978 | Freehold | subsoil fronting land to the north west of Ebbsfleet Farm Cottages, Ebbsfleet Lane |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/4 | Kent Sheet 4 | 151 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | K377523 | Freehold | subsoil fronting land to the west of Ebbsfleet Farm Cottages, Ebbsfleet Lane |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/4 | Kent Sheet 4 | 151 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Struan Gordon Robertson | 494 | K834466 | Freehold | subsoil fronting land to the north west of Ebbsfleet Farm Cottages, Ebbsfleet Lane |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/4 | Kent Sheet 4 | 151 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/4 | Kent Sheet 4 | 151 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
6/4 | Kent Sheet 6 | 508 square metres, or thereabouts, of scrubland, track, drain and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Trapoc Limited | 538 | K563834 | Freehold |  | excluding mines and minerals | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid intend to secure the rights of access through the terms issued for plots 6/1 and 6/1 (Kent). 03.10.2025 - Despite several attempts, no response has been received from this Landowner. 18.11.2025 - Dalcour Maclaren are engaging with the landowner regarding Heads of Terms. On 4th November 2025 the landowner confirmed they do not have any objection in principle to the proposals. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner regarding Heads of Terms. Dalcour Maclaren spoke to the landowner on 17th December 2025 who confirmed that they will provide feedback on the Terms in January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/4 | Kent Sheet 6 | 508 square metres, or thereabouts, of scrubland, track, drain and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Trapoc Limited | 538 |  | Occupation |  |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid intend to secure the rights of access through the terms issued for plots 6/1 and 6/1 (Kent). 03.10.2025 - Despite several attempts, no response has been received from this Landowner. 18.11.2025 - Dalcour Maclaren are engaging with the landowner regarding Heads of Terms. On 4th November 2025 the landowner confirmed they do not have any objection in principle to the proposals. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner regarding Heads of Terms. Dalcour Maclaren spoke to the landowner on 17th December 2025 who confirmed that they will provide feedback on the Terms in January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/4 | Kent Sheet 6 | 508 square metres, or thereabouts, of scrubland, track, drain and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/5 | Kent Sheet 1 | 4,684 square metres, or thereabouts, of private road (Whitehouse Drove), agricultural land, track, drain and overhead electricity distribution lines situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/5 | Kent Sheet 1 | 4,684 square metres, or thereabouts, of private road (Whitehouse Drove), agricultural land, track, drain and overhead electricity distribution lines situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
1/5 | Kent Sheet 1 | 4,684 square metres, or thereabouts, of private road (Whitehouse Drove), agricultural land, track, drain and overhead electricity distribution lines situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
1/5 | Kent Sheet 1 | 4,684 square metres, or thereabouts, of private road (Whitehouse Drove), agricultural land, track, drain and overhead electricity distribution lines situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/5 | Kent Sheet 1 | 4,684 square metres, or thereabouts, of private road (Whitehouse Drove), agricultural land, track, drain and overhead electricity distribution lines situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
5/26 | Kent Sheet 5 | 402,291 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | N/A Mark Warnett, Ardent | Yes | RR-5384 |  |  |  | National Trust |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025 and are arranging a meeting with the landowner’s agent in January. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/26 | Kent Sheet 5 | 402,291 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent Wildlife Trust | 498 | TT41175 | Leasehold |  |  | Category 1 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/5 | Kent Sheet 2 | 1,651 square metres, or thereabouts, of agricultural land and track situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/5 | Kent Sheet 2 | 1,651 square metres, or thereabouts, of agricultural land and track situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/5 | Kent Sheet 2 | 1,651 square metres, or thereabouts, of agricultural land and track situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/5 | Kent Sheet 2 | 1,651 square metres, or thereabouts, of agricultural land and track situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/5 | Kent Sheet 3 | 7 square metres, or thereabouts, of road verge and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K377019 | Freehold |  | excluding mines and minerals below a depth of 300 feet from the surface | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/5 | Kent Sheet 3 | 7 square metres, or thereabouts, of road verge and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/5 | Kent Sheet 4 | 158 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ebbsfleet Minster (Kent) Limited | 341 | K808893 | Freehold |  | excluding mines and minerals | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/5 | Kent Sheet 4 | 158 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ebbsfleet Minster (Kent) Limited | 341 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/5 | Kent Sheet 4 | 158 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
6/5 | Kent Sheet 6 | 197 square metres, or thereabouts, of scrubland, track, drain and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Trapoc Limited | 538 | K563834 | Freehold |  |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid intend to secure the rights of access through the terms issued for plots 6/1 and 6/1 (Kent). 03.10.2025 - Despite several attempts, no response has been received from this Landowner. 18.11.2025 - Dalcour Maclaren are engaging with the landowner regarding Heads of Terms. On 4th November 2025 the landowner confirmed they do not have any objection in principle to the proposals. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner regarding Heads of Terms. Dalcour Maclaren spoke to the landowner on 17th December 2025 who confirmed that they will provide feedback on the Terms in January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/5 | Kent Sheet 6 | 197 square metres, or thereabouts, of scrubland, track, drain and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Trapoc Limited | 538 | K563834 | Occupation |  |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid intend to secure the rights of access through the terms issued for plots 6/1 and 6/1 (Kent). 03.10.2025 - Despite several attempts, no response has been received from this Landowner. 18.11.2025 - Dalcour Maclaren are engaging with the landowner regarding Heads of Terms. On 4th November 2025 the landowner confirmed they do not have any objection in principle to the proposals. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner regarding Heads of Terms. Dalcour Maclaren spoke to the landowner on 17th December 2025 who confirmed that they will provide feedback on the Terms in January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/5 | Kent Sheet 6 | 197 square metres, or thereabouts, of scrubland, track, drain and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/6 | Kent Sheet 1 | 481 square metres, or thereabouts, of private road (Whitehouse Drove) and yard situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/6 | Kent Sheet 1 | 481 square metres, or thereabouts, of private road (Whitehouse Drove) and yard situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
1/6 | Kent Sheet 1 | 481 square metres, or thereabouts, of private road (Whitehouse Drove) and yard situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
1/6 | Kent Sheet 1 | 481 square metres, or thereabouts, of private road (Whitehouse Drove) and yard situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/6 | Kent Sheet 2 | 130 square metres, or thereabouts, of drain and track situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/6 | Kent Sheet 2 | 130 square metres, or thereabouts, of drain and track situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/6 | Kent Sheet 2 | 130 square metres, or thereabouts, of drain and track situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/6 | Kent Sheet 2 | 130 square metres, or thereabouts, of drain and track situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/6 | Kent Sheet 3 | 711 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/6 | Kent Sheet 3 | 711 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/6 | Kent Sheet 3 | 711 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/6 | Kent Sheet 4 | 219 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
4/6 | Kent Sheet 4 | 219 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/6 | Kent Sheet 5 | 127,005 square metres, or thereabouts, of sea (North Sea) situated to the south east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporate the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/6 | Kent Sheet 5 | 127,005 square metres, or thereabouts, of sea (North Sea) situated to the south east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | RR-5371 | [6 empty] | SU and unknown operational | Not required |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
5/6 | Kent Sheet 5 | 127,005 square metres, or thereabouts, of sea (North Sea) situated to the south east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Ventures Limited | 3292 |  | Occupation | underground electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
6/6 | Kent Sheet 6 | 2,830 square metres, or thereabouts, of public adopted highway (Sandwich Bypass, A256), scrubland, track and overhead telecommunication lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | K524623 | Freehold |  | excluding mines and minerals | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/6 | Kent Sheet 6 | 2,830 square metres, or thereabouts, of public adopted highway (Sandwich Bypass, A256), scrubland, track and overhead telecommunication lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/6 | Kent Sheet 6 | 2,830 square metres, or thereabouts, of public adopted highway (Sandwich Bypass, A256), scrubland, track and overhead telecommunication lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
6/6 | Kent Sheet 6 | 2,830 square metres, or thereabouts, of public adopted highway (Sandwich Bypass, A256), scrubland, track and overhead telecommunication lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
6/6 | Kent Sheet 6 | 2,830 square metres, or thereabouts, of public adopted highway (Sandwich Bypass, A256), scrubland, track and overhead telecommunication lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/7 | Kent Sheet 1 | 17,936 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/7 | Kent Sheet 1 | 17,936 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
1/7 | Kent Sheet 1 | 17,936 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
1/7 | Kent Sheet 1 | 17,936 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
1/7 | Kent Sheet 1 | 17,936 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/7 | Kent Sheet 1 | 17,936 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/7 | Kent Sheet 2 | 103 square metres, or thereabouts, of agricultural land and drain situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/7 | Kent Sheet 2 | 103 square metres, or thereabouts, of agricultural land and drain situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/7 | Kent Sheet 2 | 103 square metres, or thereabouts, of agricultural land and drain situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/7 | Kent Sheet 2 | 103 square metres, or thereabouts, of agricultural land and drain situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/7 | Kent Sheet 3 | 1,266 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/7 | Kent Sheet 3 | 1,266 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/7 | Kent Sheet 3 | 1,266 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/7 | Kent Sheet 4 | 2,130 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Edward Martin Spanton | 154 | K960682 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR-5840 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
4/7 | Kent Sheet 4 | 2,130 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Edward Martin Spanton | 154 | K960682 | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR-5840 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
4/7 | Kent Sheet 4 | 2,130 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
1/8 | Kent Sheet 1 | 24,691 square metres, or thereabouts, of agricultural land, track, drain, sluice, electricity transmission pylons and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/8 | Kent Sheet 1 | 24,691 square metres, or thereabouts, of agricultural land, track, drain, sluice, electricity transmission pylons and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
1/8 | Kent Sheet 1 | 24,691 square metres, or thereabouts, of agricultural land, track, drain, sluice, electricity transmission pylons and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
1/8 | Kent Sheet 1 | 24,691 square metres, or thereabouts, of agricultural land, track, drain, sluice, electricity transmission pylons and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/8 | Kent Sheet 1 | 24,691 square metres, or thereabouts, of agricultural land, track, drain, sluice, electricity transmission pylons and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
1/8 | Kent Sheet 1 | 24,691 square metres, or thereabouts, of agricultural land, track, drain, sluice, electricity transmission pylons and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/8 | Kent Sheet 2 | 3,170 square metres, or thereabouts, of agricultural land, drain and track situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/8 | Kent Sheet 2 | 3,170 square metres, or thereabouts, of agricultural land, drain and track situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/8 | Kent Sheet 2 | 3,170 square metres, or thereabouts, of agricultural land, drain and track situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/8 | Kent Sheet 2 | 3,170 square metres, or thereabouts, of agricultural land, drain and track situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/8 | Kent Sheet 3 | 8,662 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/8 | Kent Sheet 3 | 8,662 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/8 | Kent Sheet 3 | 8,662 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/8 | Kent Sheet 4 | 2,818 square metres, or thereabouts, of agricultural land situated to the north east of Ebbsfleet Farm Cottages, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Edward Martin Spanton | 154 | K960682 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR-5840 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
4/8 | Kent Sheet 4 | 2,818 square metres, or thereabouts, of agricultural land situated to the north east of Ebbsfleet Farm Cottages, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Edward Martin Spanton | 154 | K960682 | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | Yes | RR-5840 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - On 21st May 2025 the landowner's agent requested copies of the Option Agreement and Deed of Easement. Dalcour Maclaren reissued Heads of Terms in August 2025 and are awaiting confirmation that these are agreed. Dalcour Maclaren emailed the agent on 7th November 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026 | Heads of Terms negotiations ongoing |  | 2026-01-09
5/8 | Kent Sheet 5 | 8,269 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporate the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/8 | Kent Sheet 5 | 8,269 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | RR-5371 | [6 empty] | SU and unknown operational | Not required |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
1/9 | Kent Sheet 1 | 1,662 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/9 | Kent Sheet 1 | 1,662 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
1/9 | Kent Sheet 1 | 1,662 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
1/9 | Kent Sheet 1 | 1,662 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/9 | Kent Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/9 | Kent Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/9 | Kent Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/9 | Kent Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/9 | Kent Sheet 3 | 24,864 square metres, or thereabouts, of agricultural land and electricity distribution poles situated to the north of Great Oaks Small School, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/9 | Kent Sheet 3 | 24,864 square metres, or thereabouts, of agricultural land and electricity distribution poles situated to the north of Great Oaks Small School, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/9 | Kent Sheet 3 | 24,864 square metres, or thereabouts, of agricultural land and electricity distribution poles situated to the north of Great Oaks Small School, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/9 | Kent Sheet 4 | 88 square metres, or thereabouts, of drain situated to the east of Ebbsfleet Farm Cottages, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [6 empty] | SU and disputed operational | Not required |  | 09.01.2026 - Discussions ongoing | No Heads of Terms Required |  | 2026-01-09
5/9 | Kent Sheet 5 | 3,756 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | N/A Mark Warnett, Ardent | Yes | RR-5384 |  |  |  | National Trust |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025 and are arranging a meeting with the landowner’s agent in January. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/9 | Kent Sheet 5 | 3,756 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent Wildlife Trust | 498 | TT41175 | Leasehold |  |  | Category 1 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/10 | Kent Sheet 1 | 69,078 square metres, or thereabouts, of agricultural land and drains situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/10 | Kent Sheet 1 | 69,078 square metres, or thereabouts, of agricultural land and drains situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
1/10 | Kent Sheet 1 | 69,078 square metres, or thereabouts, of agricultural land and drains situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
1/10 | Kent Sheet 1 | 69,078 square metres, or thereabouts, of agricultural land and drains situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
1/10 | Kent Sheet 1 | 69,078 square metres, or thereabouts, of agricultural land and drains situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/10 | Kent Sheet 2 | 70,932 square metres, or thereabouts, of agricultural land, track, drain, sluice and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/10 | Kent Sheet 2 | 70,932 square metres, or thereabouts, of agricultural land, track, drain, sluice and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/10 | Kent Sheet 2 | 70,932 square metres, or thereabouts, of agricultural land, track, drain, sluice and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/10 | Kent Sheet 2 | 70,932 square metres, or thereabouts, of agricultural land, track, drain, sluice and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/10 | Kent Sheet 2 | 70,932 square metres, or thereabouts, of agricultural land, track, drain, sluice and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/10 | Kent Sheet 3 | 1,308 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the south of Sevenscore Crossing, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/10 | Kent Sheet 3 | 1,308 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the south of Sevenscore Crossing, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Kent County Council | 97 | K377019 | Freehold | subsoil fronting land to the south of Sevenscore Crossing, Ebbsfleet Lane North |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/10 | Kent Sheet 3 | 1,308 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the south of Sevenscore Crossing, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Ebbsfleet Minster (Kent) Limited | 341 | K808893 | Freehold | subsoil fronting land to the south west of Cottington Hill, Ebbsfleet Lane North |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/10 | Kent Sheet 3 | 1,308 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the south of Sevenscore Crossing, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Struan Gordon Robertson | 494 | K755310 | Freehold | subsoil fronting land to the south of Sevenscore Crossing, Ebbsfleet Lane North |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/10 | Kent Sheet 3 | 1,308 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the south of Sevenscore Crossing, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | HMS Two Incorporated Limited | 576 | K670281 | Freehold | subsoil fronting land to the south of 6 Sevenscore Farm Cottage, Ebbsfleet Lane North |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-10-08
3/10 | Kent Sheet 3 | 1,308 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the south of Sevenscore Crossing, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert John Chapman | 654 | K651171 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/10 | Kent Sheet 4 | 4,860 square metres, or thereabouts, of track, drains, footbridges, golf course and premises (Stonelees Golf Centre) situated to the north of Stonelees Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Stonelees Golf Centre | 3413 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/10 | Kent Sheet 5 | 139,871 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent Wildlife Trust | 498 | K410629 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/11 | Kent Sheet 1 | 994 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/11 | Kent Sheet 1 | 994 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
1/11 | Kent Sheet 1 | 994 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
1/11 | Kent Sheet 1 | 994 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/11 | Kent Sheet 2 | 2,061 square metres, or thereabouts, of agricultural land and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/11 | Kent Sheet 2 | 2,061 square metres, or thereabouts, of agricultural land and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/11 | Kent Sheet 2 | 2,061 square metres, or thereabouts, of agricultural land and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/11 | Kent Sheet 2 | 2,061 square metres, or thereabouts, of agricultural land and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/11 | Kent Sheet 3 | 8,046 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/11 | Kent Sheet 3 | 8,046 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/11 | Kent Sheet 3 | 8,046 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/11 | Kent Sheet 4 | 219 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | K377523 | Freehold |  |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/11 | Kent Sheet 4 | 219 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
4/11 | Kent Sheet 4 | 219 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/11 | Kent Sheet 5 | 9,032 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The King`s Most Excellent Majesty in Right of His Crown | 458 |  | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 |  |  |  | Open Space | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage.In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. 09.01.2026 – Dalcour Maclaren exchanged emails with the landowner’s agent on 5th December 2025 in relation to outstanding principles in the commercial agreements. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/12 | Kent Sheet 1 | 12 square metres, or thereabouts, of agricultural land situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/12 | Kent Sheet 1 | 12 square metres, or thereabouts, of agricultural land situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
1/12 | Kent Sheet 1 | 12 square metres, or thereabouts, of agricultural land situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
1/12 | Kent Sheet 1 | 12 square metres, or thereabouts, of agricultural land situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/12 | Kent Sheet 2 | 17,089 square metres, or thereabouts, of agricultural land, track, electricity transmission pylon, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/12 | Kent Sheet 2 | 17,089 square metres, or thereabouts, of agricultural land, track, electricity transmission pylon, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/12 | Kent Sheet 2 | 17,089 square metres, or thereabouts, of agricultural land, track, electricity transmission pylon, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/12 | Kent Sheet 2 | 17,089 square metres, or thereabouts, of agricultural land, track, electricity transmission pylon, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/12 | Kent Sheet 2 | 17,089 square metres, or thereabouts, of agricultural land, track, electricity transmission pylon, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/12 | Kent Sheet 2 | 17,089 square metres, or thereabouts, of agricultural land, track, electricity transmission pylon, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
3/12 | Kent Sheet 3 | 127 square metres, or thereabouts, of agricultural land and private road (Jutes Lane) situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 | TT29616 | Freehold |  |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/12 | Kent Sheet 4 | 533 square metres, or thereabouts, of scrubland and overhead telecommunication lines situated to the east of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Kent County Council | 97 | K377523 | Freehold |  |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/12 | Kent Sheet 4 | 533 square metres, or thereabouts, of scrubland and overhead telecommunication lines situated to the east of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
4/12 | Kent Sheet 4 | 533 square metres, or thereabouts, of scrubland and overhead telecommunication lines situated to the east of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/12 | Kent Sheet 5 | 14,198 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The King`s Most Excellent Majesty in Right of His Crown | 458 |  | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 |  |  |  | Open Space | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage.In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. 09.01.2026 – Dalcour Maclaren exchanged emails with the landowner’s agent on 5th December 2025 in relation to outstanding principles in the commercial agreements. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/27 | Kent Sheet 2 | 11,594 square metres, or thereabouts, of agricultural land, drain, track, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | John Robert Collins | 698 | K56551 | Freehold |  | excluding mines and minerals | Category 1 | Martin Allen, Elgars | Yes | RR-1465 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 04 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 6th November 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - On 19th November 2025 Dalcour Maclaren wrote to the landowner to confirm that their agent continues to be instructed in relation to the Heads of Terms. No response has been received. On 7th January 2026 Dalcour Maclaren attempted to contact the landowner by phone call to discuss Heads of Terms further and have not had a response to their voicemail. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/27 | Kent Sheet 2 | 11,594 square metres, or thereabouts, of agricultural land, drain, track, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/27 | Kent Sheet 2 | 11,594 square metres, or thereabouts, of agricultural land, drain, track, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/27 | Kent Sheet 3 | 296 square metres, or thereabouts, of scrubland and hardstanding situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 | TT104661 | Freehold |  | excluding mines and minerals | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/27 | Kent Sheet 4 | 1,256 square metres, or thereabouts, of track,drain and overhead electricity distribution lines situated to the east of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Jean Veronica Spanton | 39 | K617169 | Freehold |  |  | Category 1 | N/A Joe Hearnden, BTF Partnership | Yes | RR-5840 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Positive engagement has continued with this landowner and or their agent and it is anticipated an agreement will be reached by the end of Examination. 18.11.2025 - Following a meeting held on 12th September 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on the reasoning behind the rights to be acquired. Dalcour Maclaren provided this and re-issued the Heads of Terms on the 29th October 2025, engagement is ongoing. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025, 1st December 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 29th October 2025. Dalcour Maclaren proceeded to contact the landowner’s son on the 07th January 2026 and issued a copy of the Heads of Terms directly to him for review and discussion. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/27 | Kent Sheet 4 | 1,256 square metres, or thereabouts, of track,drain and overhead electricity distribution lines situated to the east of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Personal Representative to the Estate of Christopher John Spanton | 3526 | K617169 | Freehold |  |  | Category 1 | Joe Hearnden, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Positive engagement has continued with this landowner and or their agent and it is anticipated an agreement will be reached by the end of Examination. OR This individual has passed away, see update in AP ref 39 | Heads of Terms negotiations ongoing |  | 2025-10-08
4/27 | Kent Sheet 4 | 1,256 square metres, or thereabouts, of track,drain and overhead electricity distribution lines situated to the east of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
4/27 | Kent Sheet 4 | 1,256 square metres, or thereabouts, of track,drain and overhead electricity distribution lines situated to the east of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/27 | Kent Sheet 5 | 150,347 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | N/A Mark Warnett, Ardent | Yes | RR-5384 |  |  |  | National Trust |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025 and are arranging a meeting with the landowner’s agent in January. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/27 | Kent Sheet 5 | 150,347 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent Wildlife Trust | 498 | TT41175 | Leasehold |  |  | Category 1 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/28 | Kent Sheet 2 | 3,368 square metres, or thereabouts, of agricultural land, private track and overhead electricity transmission lines situated to the south of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | John Robert Collins | 698 | K56551 | Freehold |  | excluding mines and minerals | Category 1 | Martin Allen, Elgars | Yes | RR-1465 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 04 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 6th November 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - On 19th November 2025 Dalcour Maclaren wrote to the landowner to confirm that their agent continues to be instructed in relation to the Heads of Terms. No response has been received. On 7th January 2026 Dalcour Maclaren attempted to contact the landowner by phone call to discuss Heads of Terms further and have not had a response to their voicemail. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/28 | Kent Sheet 2 | 3,368 square metres, or thereabouts, of agricultural land, private track and overhead electricity transmission lines situated to the south of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/28 | Kent Sheet 3 | 234 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ebbsfleet Minster (Kent) Limited | 341 | K808893 | Freehold |  | excluding mines and minerals | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/28 | Kent Sheet 3 | 234 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ebbsfleet Minster (Kent) Limited | 341 |  | Occupation |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/28 | Kent Sheet 4 | 408 square metres, or thereabouts, of public adopted highway (Ramsgate Road) situated to the north east of Ebbsfleet House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Kent County Council | 97 | K570106 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/28 | Kent Sheet 4 | 408 square metres, or thereabouts, of public adopted highway (Ramsgate Road) situated to the north east of Ebbsfleet House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/28 | Kent Sheet 4 | 408 square metres, or thereabouts, of public adopted highway (Ramsgate Road) situated to the north east of Ebbsfleet House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/28 | Kent Sheet 5 | 2,121 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | N/A Mark Warnett, Ardent | Yes | RR-5384 |  |  |  | National Trust |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025 and are arranging a meeting with the landowner’s agent in January. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/28 | Kent Sheet 5 | 2,121 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent Wildlife Trust | 498 | TT41175 | Leasehold |  |  | Category 1 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/28 | Kent Sheet 5 | 2,121 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Ventures Limited | 3292 |  | Occupation | underground electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/29 | Kent Sheet 2 | 3,227 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | John Robert Collins | 698 | K56551 | Freehold |  | excluding mines and minerals | Category 1 | Martin Allen, Elgars | Yes | RR-1465 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 04 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 6th November 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - On 19th November 2025 Dalcour Maclaren wrote to the landowner to confirm that their agent continues to be instructed in relation to the Heads of Terms. No response has been received. On 7th January 2026 Dalcour Maclaren attempted to contact the landowner by phone call to discuss Heads of Terms further and have not had a response to their voicemail. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/29 | Kent Sheet 2 | 3,227 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/29 | Kent Sheet 3 | 223 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/29 | Kent Sheet 3 | 223 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ebbsfleet Minster (Kent) Limited | 341 | K808893 | Freehold | subsoil fronting land to the south west of Cottington Hill, Ebbsfleet Lane North |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.10.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren continue to engage with the landowner's agent in relation to Heads of Terms. Dalcour Maclaren wrote to the landowner's agent on 7th November regarding a possible new interest in this plot and offered a meeting to discuss further. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/29 | Kent Sheet 3 | 223 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold | subsoil fronting land to the south of Sevenscore Crossing, Ebbsfleet Lane North |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/29 | Kent Sheet 3 | 223 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/29 | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/29 | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/29 | Kent Sheet 5 | 2,065 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | N/A Mark Warnett, Ardent | Yes | RR-5384 |  |  |  | National Trust |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025 and are arranging a meeting with the landowner’s agent in January. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/29 | Kent Sheet 5 | 2,065 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent Wildlife Trust | 498 | TT41175 | Leasehold |  |  | Category 1 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/29 | Kent Sheet 5 | 2,065 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Ventures Limited | 3292 |  | Occupation | underground electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/100 | Kent Sheet 2 | 962 square metres, or thereabouts, of drain, river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 2591 |  | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
2/103 | Kent Sheet 2 | 55 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 2591 |  | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
2/104 | Kent Sheet 2 | 7,465 square metres, or thereabouts, of grassland, track and drain situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Clive Robert Stevens | 2520 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | Harry Kenton, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with this landowner's agent and discussions are ongoing to address primary concerns including access arrangements. A further meeting is due to be scheduled with the landowner's agent in November 2025. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 24th November 2025 to follow up on previous queries in relation to the Heads of Terms and to confirm the landowner’s instruction on negotiating with the Applicant. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/104 | Kent Sheet 2 | 7,465 square metres, or thereabouts, of grassland, track and drain situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Christopher Russell John Domvile Barradale | 2521 | K839921 | Freehold |  | as Administrator to the Estate of Michael Cotton Garratt) (excluding mines and minerals | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/104 | Kent Sheet 2 | 7,465 square metres, or thereabouts, of grassland, track and drain situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Quex Park Estates Company Limited | 2568 |  | Leasehold |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/104 | Kent Sheet 2 | 7,465 square metres, or thereabouts, of grassland, track and drain situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Quex Park Estates Company Limited | 2568 |  | Occupation |  |  | Category 1 | Harry Kenton, BTF Partnership | Yes | RR-4326 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
2/105 | Kent Sheet 2 | 1,603 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The King`s Most Excellent Majesty in Right of His Crown | 458 | K933847,Crown Land Query - River Stour | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 |  |  |  | Open Space | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage.In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. 09.01.2026 – Dalcour Maclaren exchanged emails with the landowner’s agent on 5th December 2025 in relation to outstanding principles in the commercial agreements. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/106 | Kent Sheet 2 | 1,539 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The Marquess Conyngham | 2591 |  | Freehold |  | as reputed owner | Category 1 | Charlie Gooch, CW Gooch Limited | Yes | RR-5383 |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
2/107 | Kent Sheet 2 | 469 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Church Commissioners for England | 378 | K535742 | Freehold |  |  | Category 1 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/107 | Kent Sheet 2 | 469 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/107 | Kent Sheet 2 | 469 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/107 | Kent Sheet 2 | 469 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/107 | Kent Sheet 2 | 469 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/108 | Kent Sheet 2 | 30,519 square metres, or thereabouts, of agricultural land, drains and track situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Church Commissioners for England | 378 | K535742 | Freehold |  |  | Category 1 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/108 | Kent Sheet 2 | 30,519 square metres, or thereabouts, of agricultural land, drains and track situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/108 | Kent Sheet 2 | 30,519 square metres, or thereabouts, of agricultural land, drains and track situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/108 | Kent Sheet 2 | 30,519 square metres, or thereabouts, of agricultural land, drains and track situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [6 empty] | SU and disputed operational | Not required |  | 09.01.2026 - Discussions ongoing | No Heads of Terms Required |  | 2026-01-09
2/108 | Kent Sheet 2 | 30,519 square metres, or thereabouts, of agricultural land, drains and track situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/108 | Kent Sheet 2 | 30,519 square metres, or thereabouts, of agricultural land, drains and track situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | James Southorn | 3137 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/109 | Kent Sheet 2 | 2,185 square metres, or thereabouts, of agricultural land situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Church Commissioners for England | 378 | K535742 | Freehold |  |  | Category 1 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/109 | Kent Sheet 2 | 2,185 square metres, or thereabouts, of agricultural land situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/109 | Kent Sheet 2 | 2,185 square metres, or thereabouts, of agricultural land situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/109 | Kent Sheet 2 | 2,185 square metres, or thereabouts, of agricultural land situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/109 | Kent Sheet 2 | 2,185 square metres, or thereabouts, of agricultural land situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/110 | Kent Sheet 2 | 4,747 square metres, or thereabouts, of scrubland, railway (South Eastern & Chatham Railway), works and land situated to the north west of Weatherlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Network Rail Infrastructure Limited | 1271 |  | Freehold |  | as reputed owner | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/110 | Kent Sheet 2 | 4,747 square metres, or thereabouts, of scrubland, railway (South Eastern & Chatham Railway), works and land situated to the north west of Weatherlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Network Rail Infrastructure Limited | 1271 |  | Occupation |  |  | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/110 | Kent Sheet 2 | 4,747 square metres, or thereabouts, of scrubland, railway (South Eastern & Chatham Railway), works and land situated to the north west of Weatherlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/110 | Kent Sheet 2 | 4,747 square metres, or thereabouts, of scrubland, railway (South Eastern & Chatham Railway), works and land situated to the north west of Weatherlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | OCU Group Limited | 3407 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/111 | Kent Sheet 2 | 1,865 square metres, or thereabouts, of agricultural land and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Church Commissioners for England | 378 | K535742 | Freehold |  |  | Category 1 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/111 | Kent Sheet 2 | 1,865 square metres, or thereabouts, of agricultural land and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/111 | Kent Sheet 2 | 1,865 square metres, or thereabouts, of agricultural land and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/111 | Kent Sheet 2 | 1,865 square metres, or thereabouts, of agricultural land and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [6 empty] | SU and disputed operational | Not required |  | 09.01.2026 - Discussions ongoing | No Heads of Terms Required |  | 2026-01-09
2/111 | Kent Sheet 2 | 1,865 square metres, or thereabouts, of agricultural land and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/111 | Kent Sheet 2 | 1,865 square metres, or thereabouts, of agricultural land and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James Southorn | 3137 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/112 | Kent Sheet 2 | 289 square metres, or thereabouts, of stream (Minster Stream) and agricultural land situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Church Commissioners for England | 378 | K535742 | Freehold |  |  | Category 1 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/112 | Kent Sheet 2 | 289 square metres, or thereabouts, of stream (Minster Stream) and agricultural land situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/112 | Kent Sheet 2 | 289 square metres, or thereabouts, of stream (Minster Stream) and agricultural land situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/112 | Kent Sheet 2 | 289 square metres, or thereabouts, of stream (Minster Stream) and agricultural land situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [6 empty] | SU and disputed operational | Not required |  | 09.01.2026 - Discussions ongoing | No Heads of Terms Required |  | 2026-01-09
2/112 | Kent Sheet 2 | 289 square metres, or thereabouts, of stream (Minster Stream) and agricultural land situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/112 | Kent Sheet 2 | 289 square metres, or thereabouts, of stream (Minster Stream) and agricultural land situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Southorn | 3137 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/113 | Kent Sheet 2 | 24,026 square metres, or thereabouts, of agricultural land, drain and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Church Commissioners for England | 378 | K535742 | Freehold |  |  | Category 1 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/113 | Kent Sheet 2 | 24,026 square metres, or thereabouts, of agricultural land, drain and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/113 | Kent Sheet 2 | 24,026 square metres, or thereabouts, of agricultural land, drain and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/113 | Kent Sheet 2 | 24,026 square metres, or thereabouts, of agricultural land, drain and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 1 | N/A | Yes | RR-3936 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/113 | Kent Sheet 2 | 24,026 square metres, or thereabouts, of agricultural land, drain and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [6 empty] | SU and disputed operational | Not required |  | 09.01.2026 - Discussions ongoing | No Heads of Terms Required |  | 2026-01-09
2/113 | Kent Sheet 2 | 24,026 square metres, or thereabouts, of agricultural land, drain and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/113 | Kent Sheet 2 | 24,026 square metres, or thereabouts, of agricultural land, drain and stream (Minster Stream) situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James Southorn | 3137 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/114 | Kent Sheet 2 | 1,742 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land, drain and stream (Minster Stream) situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Freehold |  | as reputed owner | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/114 | Kent Sheet 2 | 1,742 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land, drain and stream (Minster Stream) situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Occupation |  |  | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/114 | Kent Sheet 2 | 1,742 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land, drain and stream (Minster Stream) situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 1 | N/A | Yes | RR-3936 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/114 | Kent Sheet 2 | 1,742 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land, drain and stream (Minster Stream) situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [6 empty] | SU and disputed operational | Not required |  | 09.01.2026 - Discussions ongoing | No Heads of Terms Required |  | 2026-01-09
2/114 | Kent Sheet 2 | 1,742 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land, drain and stream (Minster Stream) situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | OCU Group Limited | 3407 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/115 | Kent Sheet 2 | 717 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land situated to the north east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Freehold |  | as reputed owner | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/115 | Kent Sheet 2 | 717 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land situated to the north east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Occupation |  |  | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/115 | Kent Sheet 2 | 717 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land situated to the north east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 1 | N/A | Yes | RR-3936 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/116 | Kent Sheet 2 | 580 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land situated to the north east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Freehold |  | as reputed owner | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/116 | Kent Sheet 2 | 580 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land situated to the north east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Occupation |  |  | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/116 | Kent Sheet 2 | 580 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land situated to the north east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 1 | N/A | Yes | RR-3936 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/116 | Kent Sheet 2 | 580 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land situated to the north east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | OCU Group Limited | 3407 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/117 | Kent Sheet 2 | 591 square metres, or thereabouts, of agricultural land and drain situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 1 | N/A | Yes | RR-3936 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/117 | Kent Sheet 2 | 591 square metres, or thereabouts, of agricultural land and drain situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [6 empty] | SU and disputed operational | Not required |  | 09.01.2026 - Discussions ongoing | No Heads of Terms Required |  | 2026-01-09
2/118 | Kent Sheet 2 | 9,044 square metres, or thereabouts, of agricultural land and drains situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/118 | Kent Sheet 2 | 9,044 square metres, or thereabouts, of agricultural land and drains situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/118 | Kent Sheet 2 | 9,044 square metres, or thereabouts, of agricultural land and drains situated to the north west of Weatherlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [6 empty] | SU and disputed operational | Not required |  | 09.01.2026 - Discussions ongoing | No Heads of Terms Required |  | 2026-01-09
2/119 | Kent Sheet 2 | 1,620 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/119 | Kent Sheet 2 | 1,620 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/119 | Kent Sheet 2 | 1,620 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [6 empty] | SU and disputed operational | Not required |  | 09.01.2026 - Discussions ongoing | No Heads of Terms Required |  | 2026-01-09
2/120 | Kent Sheet 2 | 189 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/120 | Kent Sheet 2 | 189 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/120 | Kent Sheet 2 | 189 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [6 empty] | SU and disputed operational | Not required |  | 09.01.2026 - Discussions ongoing | No Heads of Terms Required |  | 2026-01-09
2/121 | Kent Sheet 2 | 69,924 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/121 | Kent Sheet 2 | 69,924 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/122 | Kent Sheet 2 | 1,228 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/122 | Kent Sheet 2 | 1,228 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/123 | Kent Sheet 2 | 148,221 square metres, or thereabouts, of agricultural land, pond, stream (Minster Stream), sluices, drains, footbridges and stream under bridge carrying track situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/123 | Kent Sheet 2 | 148,221 square metres, or thereabouts, of agricultural land, pond, stream (Minster Stream), sluices, drains, footbridges and stream under bridge carrying track situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/123 | Kent Sheet 2 | 148,221 square metres, or thereabouts, of agricultural land, pond, stream (Minster Stream), sluices, drains, footbridges and stream under bridge carrying track situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 1 | N/A | Yes | RR-3936 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/123 | Kent Sheet 2 | 148,221 square metres, or thereabouts, of agricultural land, pond, stream (Minster Stream), sluices, drains, footbridges and stream under bridge carrying track situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [6 empty] | SU and disputed operational | Not required |  | 09.01.2026 - Discussions ongoing | No Heads of Terms Required |  | 2026-01-09
2/124 | Kent Sheet 2 | 63 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/124 | Kent Sheet 2 | 63 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/125 | Kent Sheet 2 | 1,595 square metres, or thereabouts, of scrubland situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richborough Estates Limited | 718 | K518470 | Freehold |  | excluding mines and minerals | Category 1 | Martin Allen, Elgars | Yes | RR-1466 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 04 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 6th November 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - On 19th November 2025 Dalcour Maclaren wrote to the landowner to confirm continued appointment of their agent in relation to the Heads of Terms. No response has been received. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/126 | Kent Sheet 2 | 5,413 square metres, or thereabouts, of scrubland situated to the north west of Weatherlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Richborough Estates Limited | 718 | K518470 | Freehold |  | excluding mines and minerals | Category 1 | Martin Allen, Elgars | Yes | RR-1466 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 04 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 6th November 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 - On 19th November 2025 Dalcour Maclaren wrote to the landowner to confirm continued appointment of their agent in relation to the Heads of Terms. No response has been received. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/127 | Kent Sheet 2 | 391 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/127 | Kent Sheet 2 | 391 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/128 | Kent Sheet 2 | 55 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/128 | Kent Sheet 2 | 55 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/129 | Kent Sheet 2 | 93 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/129 | Kent Sheet 2 | 93 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/130 | Kent Sheet 2 | 230 square metres, or thereabouts, of drain and scrubland situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/130 | Kent Sheet 2 | 230 square metres, or thereabouts, of drain and scrubland situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/132 | Kent Sheet 2 | 3,789 square metres, or thereabouts, of agricultural land, stream (Minster Stream) and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James Bedford Pace | 184 | K838442 | Freehold |  | excluding mines and minerals below a depth of 300 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/132 | Kent Sheet 2 | 3,789 square metres, or thereabouts, of agricultural land, stream (Minster Stream) and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Alexandra Ruth Pace | 637 | K838442 | Freehold |  | excluding mines and minerals below a depth of 300 feet from the surface | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/132 | Kent Sheet 2 | 3,789 square metres, or thereabouts, of agricultural land, stream (Minster Stream) and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [6 empty] | SU and disputed operational | Not required |  | 09.01.2026 - Discussions ongoing | No Heads of Terms Required |  | 2026-01-09
2/133 | Kent Sheet 2 | 110,734 square metres, or thereabouts, of agricultural land, drains and stream (Minster Stream) situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/133 | Kent Sheet 2 | 110,734 square metres, or thereabouts, of agricultural land, drains and stream (Minster Stream) situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/133 | Kent Sheet 2 | 110,734 square metres, or thereabouts, of agricultural land, drains and stream (Minster Stream) situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [6 empty] | SU and disputed operational | Not required |  | 09.01.2026 - Discussions ongoing | No Heads of Terms Required |  | 2026-01-09
2/134 | Kent Sheet 2 | 40,904 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/134 | Kent Sheet 2 | 40,904 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/135 | Kent Sheet 2 | 8 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [6 empty] | SU and disputed operational | Not required |  | 09.01.2026 - Discussions ongoing | No Heads of Terms Required |  | 2026-01-09
2/136 | Kent Sheet 2 | 8 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | The River Stour (Kent) Internal Drainage Board | 1934 |  | Occupation | drain | as internal drainage board | Category 1 | No Agent Known | Yes | RR-4494 | [6 empty] | SU and disputed operational | Not required |  | 09.01.2026 - Discussions ongoing | No Heads of Terms Required |  | 2026-01-09
2/137 | Kent Sheet 2 | 19 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/137 | Kent Sheet 2 | 19 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/138 | Kent Sheet 2 | 20 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/138 | Kent Sheet 2 | 20 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/139 | Kent Sheet 2 | 148 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/139 | Kent Sheet 2 | 148 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/140 | Kent Sheet 2 | 50 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/140 | Kent Sheet 2 | 50 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/141 | Kent Sheet 2 | 97 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/141 | Kent Sheet 2 | 97 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/142 | Kent Sheet 2 | 8 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/142 | Kent Sheet 2 | 8 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/143 | Kent Sheet 2 | 2,716 square metres, or thereabouts, of agricultural land, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/143 | Kent Sheet 2 | 2,716 square metres, or thereabouts, of agricultural land, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/144 | Kent Sheet 2 | 1,238 square metres, or thereabouts, of scrubland and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K838442 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/144 | Kent Sheet 2 | 1,238 square metres, or thereabouts, of scrubland and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K838442 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/145 | Kent Sheet 2 | 585 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/145 | Kent Sheet 2 | 585 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/145 | Kent Sheet 2 | 585 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/146 | Kent Sheet 2 | 640 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/146 | Kent Sheet 2 | 640 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/146 | Kent Sheet 2 | 640 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/147 | Kent Sheet 2 | 35 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/147 | Kent Sheet 2 | 35 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/148 | Kent Sheet 2 | 34 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K868267 | Freehold |  |  | Category 1 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/149 | Kent Sheet 2 | 274 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian David Mather | 189 | K868267 | Freehold |  |  | Category 1 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/149 | Kent Sheet 2 | 274 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/150 | Kent Sheet 2 | 128 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James Bedford Pace | 184 | K838442 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/150 | Kent Sheet 2 | 128 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Alexandra Ruth Pace | 637 | K838442 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/150 | Kent Sheet 2 | 128 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/151 | Kent Sheet 2 | 14,882 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/151 | Kent Sheet 2 | 14,882 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/151 | Kent Sheet 2 | 14,882 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/152 | Kent Sheet 2 | 1,062 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Ian David Mather | 189 | K868267 | Freehold |  |  | Category 1 | N/A | Yes | RR-2091 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have continued to work with the landowner's agent and are seeking to agree Heads of Terms. Further clarity on the rights being sought was provided to the landowner's agent on 7th November 2025. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/152 | Kent Sheet 2 | 1,062 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/153 | Kent Sheet 2 | 98 square metres, or thereabouts, of woodland and track situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James Bedford Pace | 184 | K838442 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/153 | Kent Sheet 2 | 98 square metres, or thereabouts, of woodland and track situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Alexandra Ruth Pace | 637 | K838442 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/154 | Kent Sheet 2 | 30 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | James Bedford Pace | 184 | K838442 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/154 | Kent Sheet 2 | 30 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Alexandra Ruth Pace | 637 | K838442 | Freehold |  |  | Category 1 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 03.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Engagement has continued with the landowner and their agent. On 2nd October 2025 Dalcour Maclaren wrote to the agent to seek feedback on some of the terms, a holding response was received on 3rd November 2025 from the landowner's agent and more feedback is expected shortly. 09.01.2026 – On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Option Agreement to the landowner’s agent for their consideration. On 18th December 2025 Dalcour Maclaren re-issued the Heads of Terms to obtain feedback on the remainder of the clauses. Engagement is ongoing with the landowner’s agent in relation to the commercial terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/155 | Kent Sheet 2 | 636 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K834466 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/155 | Kent Sheet 2 | 636 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/156 | Kent Sheet 2 | 558 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Struan Gordon Robertson | 494 | K834466 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/156 | Kent Sheet 2 | 558 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/157 | Kent Sheet 2 | 1,534 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/157 | Kent Sheet 2 | 1,534 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/157 | Kent Sheet 2 | 1,534 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/158 | Kent Sheet 2 | 3,374 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Struan Gordon Robertson | 494 | K834466 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/158 | Kent Sheet 2 | 3,374 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/159 | Kent Sheet 2 | 9,347 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310,K834466 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/159 | Kent Sheet 2 | 9,347 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310,K834466 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/159 | Kent Sheet 2 | 9,347 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/160 | Kent Sheet 2 | 538 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Struan Gordon Robertson | 494 | K755310,K834466 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/160 | Kent Sheet 2 | 538 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Struan Gordon Robertson | 494 | K755310,K834466 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/161 | Kent Sheet 2 | 121 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Struan Gordon Robertson | 494 | K755310,K834466 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/161 | Kent Sheet 2 | 121 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Struan Gordon Robertson | 494 | K755310,K834466 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/162 | Kent Sheet 2 | 1,158 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/162 | Kent Sheet 2 | 1,158 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/163 | Kent Sheet 2 | 7,264 square metres, or thereabouts, of scrubland, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/163 | Kent Sheet 2 | 7,264 square metres, or thereabouts, of scrubland, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/164 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/164 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/165 | Kent Sheet 2 | 24 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/165 | Kent Sheet 2 | 24 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/166 | Kent Sheet 2 | 40 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/166 | Kent Sheet 2 | 40 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/167 | Kent Sheet 2 | 72 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/167 | Kent Sheet 2 | 72 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/168 | Kent Sheet 2 | 5,320 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Struan Gordon Robertson | 494 | K755310,K834466 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/168 | Kent Sheet 2 | 5,320 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Struan Gordon Robertson | 494 | K755310,K834466 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/168 | Kent Sheet 2 | 5,320 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/169 | Kent Sheet 2 | 11,991 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/169 | Kent Sheet 2 | 11,991 square metres, or thereabouts, of agricultural land and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/170 | Kent Sheet 2 | 1,866 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/170 | Kent Sheet 2 | 1,866 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/171 | Kent Sheet 2 | 757 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/171 | Kent Sheet 2 | 757 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/172 | Kent Sheet 2 | 418 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/172 | Kent Sheet 2 | 418 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/173 | Kent Sheet 2 | 1,075 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/173 | Kent Sheet 2 | 1,075 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/173 | Kent Sheet 2 | 1,075 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/174 | Kent Sheet 2 | 12,526 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/174 | Kent Sheet 2 | 12,526 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/174 | Kent Sheet 2 | 12,526 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/175 | Kent Sheet 2 | 10 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/175 | Kent Sheet 2 | 10 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/176 | Kent Sheet 2 | 22 square metres, or thereabouts, of agricultural land and scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/176 | Kent Sheet 2 | 22 square metres, or thereabouts, of agricultural land and scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/177 | Kent Sheet 2 | 35 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/177 | Kent Sheet 2 | 35 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/178 | Kent Sheet 2 | 89 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/178 | Kent Sheet 2 | 89 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/179 | Kent Sheet 2 | 10 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/179 | Kent Sheet 2 | 10 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/180 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/180 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/180 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/182 | Kent Sheet 2 | 14 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/182 | Kent Sheet 2 | 14 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/183 | Kent Sheet 2 | 14,820 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/183 | Kent Sheet 2 | 14,820 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/186 | Kent Sheet 2 | 113 square metres, or thereabouts, of private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 1 | N/A | Yes | RR-3936 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/187 | Kent Sheet 2 | 15,423 square metres, or thereabouts, of agricultural land, track and drains situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Church Commissioners for England | 378 | K535742 | Freehold |  |  | Category 1 | Ali Holmes, Savills | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to Heads of Terms. Additional information has been shared with the landowner's agent on 7th November and a number of meeting dates have been proposed. 09.01.2026 – On 8th December 2025 Dalcour Maclaren met with the landowner’s agent to discuss the Heads of Terms. A further meeting with the landowner’s agent was held on 9th December 2025 which also included the occupier and their agent. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/187 | Kent Sheet 2 | 15,423 square metres, or thereabouts, of agricultural land, track and drains situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Pippa Southorn | 2565 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/187 | Kent Sheet 2 | 15,423 square metres, or thereabouts, of agricultural land, track and drains situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James Southorn | 3137 |  | Leasehold |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/187 | Kent Sheet 2 | 15,423 square metres, or thereabouts, of agricultural land, track and drains situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 |  | Occupation | underground rail infrastructure |  | Category 1 | N/A | Yes | RR-3936 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/187 | Kent Sheet 2 | 15,423 square metres, or thereabouts, of agricultural land, track and drains situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Pippa Southorn | 2565 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | Yes | RR-4315 REP1-237 REP2-101 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
2/187 | Kent Sheet 2 | 15,423 square metres, or thereabouts, of agricultural land, track and drains situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James Southorn | 3137 |  | Occupation |  | as partner in D H Clifton | Category 1 | Peter Cole of Ceres Property | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2025-10-08
2/188 | Kent Sheet 2 | 105 square metres, or thereabouts, of scrubland situated to the west of Weatherlees Hill, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Freehold |  | as reputed owner | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/188 | Kent Sheet 2 | 105 square metres, or thereabouts, of scrubland situated to the west of Weatherlees Hill, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Occupation |  |  | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/100 | Kent Sheet 3 | 1,168 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/100 | Kent Sheet 3 | 1,168 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | St. Augustine`s Golf Club (Ramsgate) Limited | 553 |  | Freehold | subsoil fronting land to the south east of St Augustine`s Golf Course, Sandwich Road |  | Category 1 | Tom Brett, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/100 | Kent Sheet 3 | 1,168 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/100 | Kent Sheet 3 | 1,168 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/100 | Kent Sheet 3 | 1,168 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Gas Networks plc | 547 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-5066 REP1-180 | [6 empty] | SU kit and apparatus | Draft under discussion |  | 09.01.2025 - Draft PPs issued on the 10th of Decemebr 2025. | No Heads of Terms Required |  | 2026-01-09
3/100 | Kent Sheet 3 | 1,168 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/101 | Kent Sheet 3 | 1,336 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/101 | Kent Sheet 3 | 1,336 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/101 | Kent Sheet 3 | 1,336 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | National Grid Ventures Limited | 3292 |  | Occupation | underground electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/102 | Kent Sheet 3 | 423 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent County Council | 97 | K478221 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/102 | Kent Sheet 3 | 423 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Southern Water Services Limited | 411 |  | Occupation | underground sewage pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/102 | Kent Sheet 3 | 423 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | National Grid Ventures Limited | 3292 |  | Occupation | underground electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/104 | Kent Sheet 3 | 29 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent County Council | 97 | K478221 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/104 | Kent Sheet 3 | 29 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | National Grid Ventures Limited | 3292 |  | Occupation | underground electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/107 | Kent Sheet 3 | 7,957 square metres, or thereabouts, of scrubland, cycle way, path and pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent County Council | 97 | K478221 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/108 | Kent Sheet 3 | 745 square metres, or thereabouts, of pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporate the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/108 | Kent Sheet 3 | 745 square metres, or thereabouts, of pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | RR-5371 | [6 empty] | SU and unknown operational | Not required |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
3/109 | Kent Sheet 3 | 7,164 square metres, or thereabouts, of saltmarsh (Pegwell Nature Reserve) and pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | N/A Mark Warnett, Ardent | Yes | RR-5384 |  |  |  | National Trust |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025 and are arranging a meeting with the landowner’s agent in January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/109 | Kent Sheet 3 | 7,164 square metres, or thereabouts, of saltmarsh (Pegwell Nature Reserve) and pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent Wildlife Trust | 498 | TT41175 | Leasehold |  |  | Category 1 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 |  |  |  | National Trust |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/110 | Kent Sheet 3 | 3,495 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The National Trust for Places of Historic Interest or Natural Beauty | 237 | K527769 | Freehold |  | excluding mines and minerals below a depth of 100 feet from the surface | Category 1 | N/A Mark Warnett, Ardent | Yes | RR-5384 |  |  |  | National Trust |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Revised Heads of Terms are due to be issued for further negotiation once clarification on the construction methodology has been provided. 18.11.2025 - On 17th October 2025 Dalcour Maclaren proposed a number of dates for a meeting with the Landowner's agent to review the Heads of Terms in more detail. A meeting date has not yet been confirmed by the Landowner's agent but a follow up regarding these dates was sent on 7th November 2025. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Dalcour Maclaren followed up with the landowner’s agent in relation to outstanding queries on the Heads of Terms on 22nd December 2025 and are arranging a meeting with the landowner’s agent in January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/110 | Kent Sheet 3 | 3,495 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent Wildlife Trust | 498 | TT41175 | Leasehold |  |  | Category 1 | N/A Harry Kenton, BTF Partnership | Yes | RR-2980 REP1-152 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised Heads of Terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - A meeting was held with the landowner's agent on 12th September 2025 - it was confirmed that their agent does not have instruction to proceed with the negotiation of the Heads of Terms. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 22nd December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/111 | Kent Sheet 3 | 3,431 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | RR-5371 | [6 empty] | SU and unknown operational | Not required |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
3/111 | Kent Sheet 3 | 3,431 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/111 | Kent Sheet 3 | 3,431 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/112 | Kent Sheet 3 | 760 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporate the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/112 | Kent Sheet 3 | 760 square metres, or thereabouts, of track and hardstanding situated to the east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | RR-5371 | [6 empty] | SU and unknown operational | Not required |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
3/20a | Kent Sheet 3 | 318 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold |  | excluding mines and minerals | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/20a | Kent Sheet 3 | 318 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 |  | Occupation |  |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/97a | Kent Sheet 3 | 83 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the north east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/97a | Kent Sheet 3 | 83 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the north east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet District Council | 167 | K628577 | Freehold | subsoil fronting land on the south east side of Sandwich Road, Cliffsend, Ramsgate |  | Category 1 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporate the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/97a | Kent Sheet 3 | 83 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the north east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/97a | Kent Sheet 3 | 83 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the north east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Southern Water Services Limited | 411 |  | Occupation | underground water pipeline |  | Category 1 | N/A | No | [7 empty] | SU kit and apparatus | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
3/97a | Kent Sheet 3 | 83 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the north east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/97a | Kent Sheet 3 | 83 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the north east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/98a | Kent Sheet 3 | 34 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane), situated to the south west of Cottington Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 |  | Freehold |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/98a | Kent Sheet 3 | 34 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane), situated to the south west of Cottington Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 | TT104661 | Freehold | subsoil fronting land to the north of Ebbsfleet Farm Cottages, Ebbsfleet Lane |  | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/98a | Kent Sheet 3 | 34 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane), situated to the south west of Cottington Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Struan Gordon Robertson | 494 | K755310 | Freehold | subsoil fronting land to the south of Sevenscore Crossing, Ebbsfleet Lane North |  | Category 1 | Charlotte Bromley, Hobbs Parker Property Consultants LLP | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 13 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions. 18.11.2025 - Engagement has continued with the landowner and their agent. Revised Terms were issued on 6th November 2025, Dalcour Maclaren met with the landowner's agent to discuss Terms on 17th November 2025. 09.01.2026 – Following the in-person meeting on 17th November 2025, Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 22nd December 2025 . A follow up meeting proposed for 16th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/98a | Kent Sheet 3 | 34 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane), situated to the south west of Cottington Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Kent County Council | 97 |  | Occupation |  | as highway authority | Category 1 | Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/98a | Kent Sheet 3 | 34 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane), situated to the south west of Cottington Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/98a | Kent Sheet 3 | 34 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane), situated to the south west of Cottington Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown Occupier of Caravan | 3546 |  | Occupation |  |  | Category 1 |  | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations not commenced |  | 2026-01-09
4/19a | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland and overhead telecommunication lines situated to the north east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 | K708841 | Freehold |  |  | Category 1 | N/A | No | [7 empty] | SU rights in land | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
4/19a | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland and overhead telecommunication lines situated to the north east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Southern Water Services Limited | 411 | K708841 | Occupation |  |  | Category 1 | N/A | No | [7 empty] | SU rights in land | Draft under discussion |  | 25.03.2025 - Protective provisions are being negotiated with Southern Water Services Limited and the access rights required are being discussed alongside the protective provisions. 08.10.2025 - There are no longer any land rights from Southern Water Services Limited. See update on Protected Provisions. 18.11.2025 Please see update regarding the Protected Provisions on the application document: 9.75 Status of Negotiations with Statutory Undertakers and Schedule of Protective Provisions. | No Heads of Terms Required |  | 2026-01-09
4/19a | Kent Sheet 4 | 1 square metres, or thereabouts, of scrubland and overhead telecommunication lines situated to the north east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/30a | Kent Sheet 5 | 585 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K929702 | Freehold |  |  | Category 1 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporate the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/30a | Kent Sheet 5 | 585 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | RR-5371 | [6 empty] | SU and unknown operational | Not required |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
1/30 | Suffolk Sheet 1 | 1,135 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Nichol | 30 | SK346463 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/30 | Suffolk Sheet 1 | 1,135 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gerlinde Edmunds | 135 | SK346463 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/30 | Suffolk Sheet 1 | 1,135 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Nichol | 30 | SK346463 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/30 | Suffolk Sheet 1 | 1,135 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gerlinde Edmunds | 135 | SK346463 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/30 | Suffolk Sheet 2 | 88 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) situated to the west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Simon Nicholas Fulford | 406 | SK346948 | Freehold | subsoil fronting land to the south of The Lindens, Saxmundham Road |  | Category 1 | Megan Pemberton, Landbridge | Yes | RR-5020 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/30 | Suffolk Sheet 2 | 88 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) situated to the west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Blackheath Farms Limited | 425 | SK268898 | Freehold | subsoil fronting land to the south of The Lindens, Saxmundham Road |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/30 | Suffolk Sheet 2 | 88 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) situated to the west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Nicola Suzanne Fulford | 488 | SK346948 | Freehold | subsoil fronting land to the south of The Lindens, Saxmundham Road |  | Category 1 | Megan Pemberton, Landbridge | Yes | RR-3978 | [5 empty] | Not SU | Not SU |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required | 2025-10-08 | 2026-01-09
2/30 | Suffolk Sheet 2 | 88 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) situated to the west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/30 | Suffolk Sheet 2 | 88 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) situated to the west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
5/30 | Suffolk Sheet 5 | 463 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lindsay Peter Tomlinson | 335 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/30 | Suffolk Sheet 5 | 463 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sarah Tomlinson | 491 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
7/30 | Suffolk Sheet 7 | 103 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Highways Limited | 374 | SK313281 | Freehold |  |  | Category 1 |  | No | [11 empty] | No Heads of Terms Required |  | 2026-01-09
7/30 | Suffolk Sheet 7 | 103 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
7/30 | Suffolk Sheet 7 | 103 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/31 | Suffolk Sheet 1 | 19,614 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/31 | Suffolk Sheet 1 | 19,614 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/31 | Suffolk Sheet 1 | 19,614 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/31 | Suffolk Sheet 1 | 19,614 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
2/31 | Suffolk Sheet 2 | 7,480 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Simon Nicholas Fulford | 406 | SK346948 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | Yes | RR-5020 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/31 | Suffolk Sheet 2 | 7,480 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Nicola Suzanne Fulford | 488 | SK346948 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | Yes | RR-3978 | [5 empty] | Not SU | Not SU |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required | 2025-10-08 | 2026-01-09
2/31 | Suffolk Sheet 2 | 7,480 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Simon Nicholas Fulford | 406 | SK346948 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | Yes | RR-5020 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/31 | Suffolk Sheet 2 | 7,480 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Nicola Suzanne Fulford | 488 | SK346948 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | Yes | RR-3978 | [5 empty] | Not SU | Not SU |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required | 2025-10-08 | 2026-01-09
2/31 | Suffolk Sheet 2 | 7,480 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/31 | Suffolk Sheet 5 | 3,703 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Lindsay Peter Tomlinson | 335 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/31 | Suffolk Sheet 5 | 3,703 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sarah Tomlinson | 491 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
7/31 | Suffolk Sheet 7 | 1,362 square metres, or thereabouts, of public adopted highways (B1121 and A12, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 | SK348406 | Freehold |  |  | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
7/31 | Suffolk Sheet 7 | 1,362 square metres, or thereabouts, of public adopted highways (B1121 and A12, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/32 | Suffolk Sheet 1 | 673 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/32 | Suffolk Sheet 1 | 673 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/32 | Suffolk Sheet 1 | 673 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/32 | Suffolk Sheet 1 | 673 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
2/32 | Suffolk Sheet 2 | 3,034 square metres, or thereabouts, of agricultural land situated to the north of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Michael Neil Copinger Mahony | 174 | SK232978 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
5/32 | Suffolk Sheet 5 | 4,080 square metres, or thereabouts, of scrubland and track situated to the north east of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Elisabeth Lesley Lindores | 579 | SK266138 | Freehold |  | excluding mines and minerals | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Heads of Terms have been agreed, discussions are ongoing between legal advisors to draft and agree the Option Agreement. 09.01.2025 – The Option Agreement between The Applicant and the landowner legally completed on 11th December 2025. | Heads of Terms Agreed |  | 2026-01-09
5/32 | Suffolk Sheet 5 | 4,080 square metres, or thereabouts, of scrubland and track situated to the north east of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Anglian Water Services Limited | 82 |  | Occupation | underground sewage pipeline |  | Category 1 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
5/32 | Suffolk Sheet 5 | 4,080 square metres, or thereabouts, of scrubland and track situated to the north east of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Cadent Gas Limited | 1055 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-0656 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. | No Heads of Terms Required |  | 2026-01-09
1/33 | Suffolk Sheet 1 | 81 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/33 | Suffolk Sheet 1 | 81 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/33 | Suffolk Sheet 2 | 2,709 square metres, or thereabouts, of scrubland, electricity transmission pylons and overhead electricity transmission lines situated to the north of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Michael Neil Copinger Mahony | 174 | SK232978 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/33 | Suffolk Sheet 2 | 2,709 square metres, or thereabouts, of scrubland, electricity transmission pylons and overhead electricity transmission lines situated to the north of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/33 | Suffolk Sheet 5 | 1,379 square metres, or thereabouts, of grassland situated to the north east of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nicolas Jon Stuchfield | 32 | SK201392 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4009 REP1-230 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowner’s agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/33 | Suffolk Sheet 5 | 1,379 square metres, or thereabouts, of grassland situated to the north east of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Jill Stuchfield | 587 | SK201392 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/34 | Suffolk Sheet 1 | 3,901 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/34 | Suffolk Sheet 1 | 3,901 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/34 | Suffolk Sheet 2 | 257 square metres, or thereabouts, of public footpath (Friston Footpath, 017) and overhead electricity transmission lines situated to the north of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/34 | Suffolk Sheet 2 | 257 square metres, or thereabouts, of public footpath (Friston Footpath, 017) and overhead electricity transmission lines situated to the north of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Suffolk County Council | 755 |  | Occupation | public footpath |  | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
5/34 | Suffolk Sheet 5 | 49,357 square metres, or thereabouts, of grassland, wooded area, track, public footpath (Aldeburgh Footpath, 006) and drains situated to the east of Kings Legend, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Royal Society for the Protection of Birds | 618 | SK328388 | Freehold |  |  | Category 1 | John Coates, Bidwells | Yes | RR-4651 REP1-158 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in September 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd October 2025 and issued revised Heads of Terms on 6th November 2025. Dalcour Maclaren received comments on the revised Heads of Terms on 11th November 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 15th December 2025. Dalcour Maclaren discussed the Heads of Terms with the landowner’s agent and issued a further revision of the terms on 8th January 2026. Dalcour Maclaren believe all points raised by the landowner have now been addressed within the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/34 | Suffolk Sheet 5 | 49,357 square metres, or thereabouts, of grassland, wooded area, track, public footpath (Aldeburgh Footpath, 006) and drains situated to the east of Kings Legend, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Royal Society for the Protection of Birds | 618 | SK328388 | Occupation |  |  | Category 1 | John Coates, Bidwells | Yes | RR-4651 REP1-158 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in September 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd October 2025 and issued revised Heads of Terms on 6th November 2025. Dalcour Maclaren received comments on the revised Heads of Terms on 11th November 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 15th December 2025. Dalcour Maclaren discussed the Heads of Terms with the landowner’s agent and issued a further revision of the terms on 8th January 2026. Dalcour Maclaren believe all points raised by the landowner have now been addressed within the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/34 | Suffolk Sheet 5 | 49,357 square metres, or thereabouts, of grassland, wooded area, track, public footpath (Aldeburgh Footpath, 006) and drains situated to the east of Kings Legend, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Occupation | public footpath |  | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/35 | Suffolk Sheet 1 | 389 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/35 | Suffolk Sheet 1 | 389 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/35 | Suffolk Sheet 1 | 389 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/35 | Suffolk Sheet 1 | 389 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nathaniel Bacon | 3135 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-11-18
2/35 | Suffolk Sheet 2 | 1,793 square metres, or thereabouts, of scrubland, pond and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Ian Charles Rix | 692 | SK312683 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/35 | Suffolk Sheet 2 | 1,793 square metres, or thereabouts, of scrubland, pond and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/35 | Suffolk Sheet 2 | 1,793 square metres, or thereabouts, of scrubland, pond and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/35 | Suffolk Sheet 2 | 1,793 square metres, or thereabouts, of scrubland, pond and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Ian Charles Rix | 692 | SK312683 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/35 | Suffolk Sheet 3 | 31 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Freehold | subsoil fronting land to the north of West Lodge, Snape Road |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/35 | Suffolk Sheet 3 | 31 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
3/35 | Suffolk Sheet 3 | 31 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
3/35 | Suffolk Sheet 3 | 31 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | EXA Networks Limited | 3290 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | None Required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/36 | Suffolk Sheet 1 | 6,550 square metres, or thereabouts, of agricultural land and pond situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/36 | Suffolk Sheet 1 | 6,550 square metres, or thereabouts, of agricultural land and pond situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/36 | Suffolk Sheet 1 | 6,550 square metres, or thereabouts, of agricultural land and pond situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/36 | Suffolk Sheet 1 | 6,550 square metres, or thereabouts, of agricultural land and pond situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nathaniel Bacon | 3135 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/36 | Suffolk Sheet 2 | 4,050 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Ian Charles Rix | 692 | SK312683 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/36 | Suffolk Sheet 2 | 4,050 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner of part | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/36 | Suffolk Sheet 2 | 4,050 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/36 | Suffolk Sheet 2 | 4,050 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Woodside Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Ian Charles Rix | 692 | SK312683 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/37 | Suffolk Sheet 1 | 3,606 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/37 | Suffolk Sheet 1 | 3,606 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/37 | Suffolk Sheet 1 | 3,606 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/37 | Suffolk Sheet 1 | 3,606 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nathaniel Bacon | 3135 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/37 | Suffolk Sheet 2 | 11,246 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/37 | Suffolk Sheet 2 | 11,246 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/37 | Suffolk Sheet 2 | 11,246 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/37 | Suffolk Sheet 3 | 23 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the north of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Freehold | subsoil fronting land to the north of West Lodge, Snape Road |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/37 | Suffolk Sheet 3 | 23 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the north of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
3/37 | Suffolk Sheet 3 | 23 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the north of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
3/37 | Suffolk Sheet 3 | 23 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the north of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | EXA Networks Limited | 3290 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | None Required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/38 | Suffolk Sheet 1 | 47,383 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/38 | Suffolk Sheet 1 | 47,383 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/38 | Suffolk Sheet 1 | 47,383 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/38 | Suffolk Sheet 1 | 47,383 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nathaniel Bacon | 3135 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-11-18
2/38 | Suffolk Sheet 2 | 777 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Ian Charles Rix | 692 | SK312683 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/38 | Suffolk Sheet 2 | 777 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/38 | Suffolk Sheet 2 | 777 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Ian Charles Rix | 692 | SK312683 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/38 | Suffolk Sheet 3 | 784 square metres, or thereabouts, of agricultural land situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
1/39 | Suffolk Sheet 1 | 1,646 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/39 | Suffolk Sheet 1 | 1,646 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/39 | Suffolk Sheet 3 | 2,084 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
1/40 | Suffolk Sheet 1 | 968 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/40 | Suffolk Sheet 1 | 968 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/40 | Suffolk Sheet 2 | 742 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead electricity transmission lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK350290 | Freehold | subsoil fronting land to the west of Manor Farm, Grove Road |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/40 | Suffolk Sheet 2 | 742 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead electricity transmission lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 | SK312683 | Freehold | subsoil fronting land to the east of Little Moor Farm, Grove Road |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/40 | Suffolk Sheet 2 | 742 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead electricity transmission lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/40 | Suffolk Sheet 2 | 742 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead electricity transmission lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/40 | Suffolk Sheet 2 | 742 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead electricity transmission lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/40 | Suffolk Sheet 2 | 742 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead electricity transmission lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/40 | Suffolk Sheet 2 | 742 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead electricity transmission lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
2/40 | Suffolk Sheet 2 | 742 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead electricity transmission lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/40 | Suffolk Sheet 3 | 24,176 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | EXA Networks Limited | 3290 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | None Required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/41 | Suffolk Sheet 1 | 98,199 square metres, or thereabouts, of agricultural land, drain, pond and private road situated to the south east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/41 | Suffolk Sheet 1 | 98,199 square metres, or thereabouts, of agricultural land, drain, pond and private road situated to the south east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/41 | Suffolk Sheet 1 | 98,199 square metres, or thereabouts, of agricultural land, drain, pond and private road situated to the south east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/41 | Suffolk Sheet 1 | 98,199 square metres, or thereabouts, of agricultural land, drain, pond and private road situated to the south east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Nathaniel Bacon | 3135 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/41 | Suffolk Sheet 2 | 11,668 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of Woodside Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/41 | Suffolk Sheet 2 | 11,668 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of Woodside Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/41 | Suffolk Sheet 3 | 549 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/41 | Suffolk Sheet 3 | 549 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/42 | Suffolk Sheet 1 | 25,903 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/42 | Suffolk Sheet 1 | 25,903 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/42 | Suffolk Sheet 1 | 25,903 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/42 | Suffolk Sheet 1 | 25,903 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nathaniel Bacon | 3135 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-11-18
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK312683 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner of part | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK312683 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/42 | Suffolk Sheet 2 | 28,066 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/42 | Suffolk Sheet 3 | 23 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/43 | Suffolk Sheet 1 | 291 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/43 | Suffolk Sheet 1 | 291 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/43 | Suffolk Sheet 1 | 291 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/43 | Suffolk Sheet 1 | 291 square metres, or thereabouts, of agricultural land and drain situated to the west of Trust Farm, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nathaniel Bacon | 3135 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-11-18
2/43 | Suffolk Sheet 2 | 1,316 square metres, or thereabouts, of public adopted highway (Grove Road), overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold | subsoil fronting land to the west of Manor Farm, Grove Road |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/43 | Suffolk Sheet 2 | 1,316 square metres, or thereabouts, of public adopted highway (Grove Road), overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK312683 | Freehold | subsoil fronting land to the east of Little Moor Farm, Grove Road |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/43 | Suffolk Sheet 2 | 1,316 square metres, or thereabouts, of public adopted highway (Grove Road), overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/43 | Suffolk Sheet 2 | 1,316 square metres, or thereabouts, of public adopted highway (Grove Road), overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/43 | Suffolk Sheet 2 | 1,316 square metres, or thereabouts, of public adopted highway (Grove Road), overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/43 | Suffolk Sheet 2 | 1,316 square metres, or thereabouts, of public adopted highway (Grove Road), overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/43 | Suffolk Sheet 2 | 1,316 square metres, or thereabouts, of public adopted highway (Grove Road), overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
2/43 | Suffolk Sheet 2 | 1,316 square metres, or thereabouts, of public adopted highway (Grove Road), overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/43 | Suffolk Sheet 2 | 1,316 square metres, or thereabouts, of public adopted highway (Grove Road), overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/43 | Suffolk Sheet 3 | 945 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Guy Hilliard Heald | 109 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/43 | Suffolk Sheet 3 | 945 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lucinda Jane Fullerton Heald | 766 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/43 | Suffolk Sheet 3 | 945 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Guy Hilliard Heald | 109 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/43 | Suffolk Sheet 3 | 945 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lucinda Jane Fullerton Heald | 766 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/44 | Suffolk Sheet 1 | 3,268 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/44 | Suffolk Sheet 1 | 3,268 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/44 | Suffolk Sheet 2 | 15,716 square metres, or thereabouts, of agricultural land, electricity distribution pole, overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/44 | Suffolk Sheet 2 | 15,716 square metres, or thereabouts, of agricultural land, electricity distribution pole, overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/44 | Suffolk Sheet 2 | 15,716 square metres, or thereabouts, of agricultural land, electricity distribution pole, overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/44 | Suffolk Sheet 2 | 15,716 square metres, or thereabouts, of agricultural land, electricity distribution pole, overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/44 | Suffolk Sheet 3 | 1,181 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/44 | Suffolk Sheet 3 | 1,181 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/44 | Suffolk Sheet 3 | 1,181 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/44 | Suffolk Sheet 3 | 1,181 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/45 | Suffolk Sheet 1 | 4,035 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/45 | Suffolk Sheet 1 | 4,035 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/45 | Suffolk Sheet 1 | 4,035 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/45 | Suffolk Sheet 1 | 4,035 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/45 | Suffolk Sheet 1 | 4,035 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
1/45 | Suffolk Sheet 1 | 4,035 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Nathaniel Bacon | 3135 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-11-18
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/45 | Suffolk Sheet 3 | 1,301 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
1/46 | Suffolk Sheet 1 | 306 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/46 | Suffolk Sheet 1 | 306 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/46 | Suffolk Sheet 1 | 306 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/46 | Suffolk Sheet 1 | 306 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nathaniel Bacon | 3135 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-11-18
2/46 | Suffolk Sheet 2 | 273 square metres, or thereabouts, of agricultural land, track, electricity distribution poles and overhead electricity distribution lines situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK312683 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/46 | Suffolk Sheet 2 | 273 square metres, or thereabouts, of agricultural land, track, electricity distribution poles and overhead electricity distribution lines situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner of part | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/46 | Suffolk Sheet 2 | 273 square metres, or thereabouts, of agricultural land, track, electricity distribution poles and overhead electricity distribution lines situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK312683 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/46 | Suffolk Sheet 2 | 273 square metres, or thereabouts, of agricultural land, track, electricity distribution poles and overhead electricity distribution lines situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/46 | Suffolk Sheet 3 | 24,700 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
1/47 | Suffolk Sheet 1 | 2,692 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/47 | Suffolk Sheet 1 | 2,692 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/47 | Suffolk Sheet 1 | 2,692 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/47 | Suffolk Sheet 1 | 2,692 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Nathaniel Bacon | 3135 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-11-18
2/47 | Suffolk Sheet 2 | 4,369 square metres, or thereabouts, of agricultural land and track situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK312683 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/47 | Suffolk Sheet 2 | 4,369 square metres, or thereabouts, of agricultural land and track situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner of part | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/47 | Suffolk Sheet 2 | 4,369 square metres, or thereabouts, of agricultural land and track situated to the north west of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK312683 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/47 | Suffolk Sheet 3 | 16,266 square metres, or thereabouts, of agricultural land situated to the north of Park Farm Cottages, Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
1/48 | Suffolk Sheet 1 | 319 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/48 | Suffolk Sheet 1 | 319 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/48 | Suffolk Sheet 1 | 319 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/48 | Suffolk Sheet 1 | 319 square metres, or thereabouts, of agricultural land and drain situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nathaniel Bacon | 3135 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-11-18
2/48 | Suffolk Sheet 2 | 136 square metres, or thereabouts, of agricultural land and track situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK312683 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/48 | Suffolk Sheet 2 | 136 square metres, or thereabouts, of agricultural land and track situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK312683 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/48 | Suffolk Sheet 3 | 660 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, ﻿Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | ﻿Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/48 | Suffolk Sheet 3 | 660 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, ﻿Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | ﻿Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/48 | Suffolk Sheet 3 | 660 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, ﻿Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | ﻿Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/48 | Suffolk Sheet 3 | 660 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, ﻿Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | ﻿Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/49 | Suffolk Sheet 1 | 29,206 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK258213 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/49 | Suffolk Sheet 1 | 29,206 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK258213 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/49 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold | subsoil fronting land to the west of Manor Farm, Grove Road |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/49 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK312683 | Freehold | subsoil fronting land to the east of Little Moor Farm, Grove Road |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/49 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/49 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/49 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/49 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
2/49 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/49 | Suffolk Sheet 3 | 395 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
1/50 | Suffolk Sheet 1 | 232 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold | subsoil fronting land to the south west of Wardspring Farm, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/50 | Suffolk Sheet 1 | 232 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James John Skellorn | 476 | SK311155 | Freehold | subsoil fronting land to the north of Hill Farm, The Street |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/50 | Suffolk Sheet 1 | 232 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 | SK258213 | Freehold | subsoil fronting land to the north of Redhouse Farm, The Street |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/50 | Suffolk Sheet 1 | 232 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/50 | Suffolk Sheet 1 | 232 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold | subsoil fronting land to the north of Hill Farm, The Street |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/50 | Suffolk Sheet 1 | 232 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/50 | Suffolk Sheet 1 | 232 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-0656 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. | No Heads of Terms Required |  | 2026-01-09
1/50 | Suffolk Sheet 1 | 232 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/50 | Suffolk Sheet 2 | 22 square metres, or thereabouts, of grassland situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/50 | Suffolk Sheet 3 | 3,869 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/50 | Suffolk Sheet 3 | 3,869 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/50 | Suffolk Sheet 3 | 3,869 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/50 | Suffolk Sheet 3 | 3,869 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/51 | Suffolk Sheet 1 | 147 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold | subsoil fronting land to the south west of Wardspring Farm, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/51 | Suffolk Sheet 1 | 147 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/51 | Suffolk Sheet 1 | 147 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/51 | Suffolk Sheet 2 | 13 square metres, or thereabouts, of grassland situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/51 | Suffolk Sheet 2 | 13 square metres, or thereabouts, of grassland situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/51 | Suffolk Sheet 3 | 2,719 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
1/52 | Suffolk Sheet 1 | 3,645 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/52 | Suffolk Sheet 1 | 3,645 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/52 | Suffolk Sheet 1 | 3,645 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/52 | Suffolk Sheet 1 | 3,645 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nathaniel Bacon | 3135 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/52 | Suffolk Sheet 2 | 142 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK350290 | Freehold | subsoil fronting land to the west of Manor Farm, Grove Road |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/52 | Suffolk Sheet 2 | 142 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/52 | Suffolk Sheet 2 | 142 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/52 | Suffolk Sheet 2 | 142 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/52 | Suffolk Sheet 2 | 142 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
2/52 | Suffolk Sheet 2 | 142 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/52 | Suffolk Sheet 3 | 2,504 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/52 | Suffolk Sheet 3 | 2,504 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/52 | Suffolk Sheet 3 | 2,504 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/52 | Suffolk Sheet 3 | 2,504 square metres, or thereabouts, of agricultural land situated to the north west of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/53 | Suffolk Sheet 1 | 1,050 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Freehold | subsoil fronting land to the north of Hill Farm, The Street |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/53 | Suffolk Sheet 1 | 1,050 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/53 | Suffolk Sheet 1 | 1,050 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold | subsoil fronting land to the north of Hill Farm, The Street |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/53 | Suffolk Sheet 1 | 1,050 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/53 | Suffolk Sheet 1 | 1,050 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cadent Gas Limited | 1055 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-0656 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. | No Heads of Terms Required |  | 2026-01-09
2/53 | Suffolk Sheet 2 | 37 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK350290 | Freehold | subsoil fronting land to the west of Manor Farm, Grove Road |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/53 | Suffolk Sheet 2 | 37 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 | SK312683 | Freehold | subsoil fronting land to the east of Little Moor Farm, Grove Road |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/53 | Suffolk Sheet 2 | 37 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/53 | Suffolk Sheet 2 | 37 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/53 | Suffolk Sheet 2 | 37 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/53 | Suffolk Sheet 3 | 73,354 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/54 | Suffolk Sheet 2 | 1,397 square metres, or thereabouts, of private road situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/54 | Suffolk Sheet 3 | 28,735 square metres, or thereabouts, of agricultural land, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Bull`s Hall, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | June Bloomfield | 679 | SK248569 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 26.11.2025 – The Applicant’s land agent, Dalcour Maclaren have engaged with the landowner about the additional plots. Heads of Terms will be issued if appropriate. 09.01.2026 – Dalcour Maclaren issued template Heads of Terms to the landowner’s agent on 4th December 2025 ahead of the Change Request being accepted. Dalcour Maclaren issued populated Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | No Heads of Terms Required |  | 2026-01-09
3/54 | Suffolk Sheet 3 | 28,735 square metres, or thereabouts, of agricultural land, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Bull`s Hall, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/54 | Suffolk Sheet 3 | 28,735 square metres, or thereabouts, of agricultural land, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Bull`s Hall, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/55 | Suffolk Sheet 2 | 3,961 square metres, or thereabouts, of woodland and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/55 | Suffolk Sheet 2 | 3,961 square metres, or thereabouts, of woodland and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/55 | Suffolk Sheet 2 | 3,961 square metres, or thereabouts, of woodland and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
2/55 | Suffolk Sheet 2 | 3,961 square metres, or thereabouts, of woodland and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/55 | Suffolk Sheet 3 | 42 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/56 | Suffolk Sheet 1 | 273 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/56 | Suffolk Sheet 1 | 273 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/56 | Suffolk Sheet 1 | 273 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/56 | Suffolk Sheet 1 | 273 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nathaniel Bacon | 3135 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/56 | Suffolk Sheet 3 | 603 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/57 | Suffolk Sheet 1 | 233 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/57 | Suffolk Sheet 1 | 233 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/57 | Suffolk Sheet 1 | 233 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/57 | Suffolk Sheet 1 | 233 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), SuffolkClass 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nathaniel Bacon | 3135 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-11-18
2/57 | Suffolk Sheet 2 | 95 square metres, or thereabouts, of agricultural land and drain situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/57 | Suffolk Sheet 2 | 95 square metres, or thereabouts, of agricultural land and drain situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/57 | Suffolk Sheet 2 | 95 square metres, or thereabouts, of agricultural land and drain situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/57 | Suffolk Sheet 2 | 95 square metres, or thereabouts, of agricultural land and drain situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/57 | Suffolk Sheet 2 | 95 square metres, or thereabouts, of agricultural land and drain situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/57 | Suffolk Sheet 3 | 683 square metres, or thereabouts, of agricultural land, track and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/58 | Suffolk Sheet 1 | 2,356 square metres, or thereabouts, of agricultural land, drain and private road situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Ian Charles Rix | 692 | SK258213 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/58 | Suffolk Sheet 1 | 2,356 square metres, or thereabouts, of agricultural land, drain and private road situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Ian Charles Rix | 692 | SK258213 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/58 | Suffolk Sheet 2 | 50,052 square metres, or thereabouts, of agricultural land situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/58 | Suffolk Sheet 2 | 50,052 square metres, or thereabouts, of agricultural land situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/58 | Suffolk Sheet 2 | 50,052 square metres, or thereabouts, of agricultural land situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/58 | Suffolk Sheet 2 | 50,052 square metres, or thereabouts, of agricultural land situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/58 | Suffolk Sheet 2 | 50,052 square metres, or thereabouts, of agricultural land situated to the west of Woodside Cottages, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
3/58 | Suffolk Sheet 3 | 1,254 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Freehold | subsoil fronting land to the north of West Lodge, Snape Road |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/58 | Suffolk Sheet 3 | 1,254 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
3/58 | Suffolk Sheet 3 | 1,254 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | George William Barrington-Phillips | 3519 | SK222694 | Freehold | subsoil fronting 109 Snape Road |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/58 | Suffolk Sheet 3 | 1,254 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Connie Amber Peck | 3520 | SK222694 | Freehold | subsoil fronting 109 Snape Road |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/58 | Suffolk Sheet 3 | 1,254 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
3/58 | Suffolk Sheet 3 | 1,254 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/58 | Suffolk Sheet 3 | 1,254 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/59 | Suffolk Sheet 2 | 119 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/59 | Suffolk Sheet 2 | 119 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/59 | Suffolk Sheet 2 | 119 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/59 | Suffolk Sheet 2 | 119 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK312683 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/59 | Suffolk Sheet 2 | 119 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/59 | Suffolk Sheet 3 | 17 square metres, or thereabouts, of scrubland situated to the north east of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
1/60 | Suffolk Sheet 1 | 7 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/60 | Suffolk Sheet 1 | 7 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/60 | Suffolk Sheet 1 | 7 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/60 | Suffolk Sheet 1 | 7 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Nathaniel Bacon | 3135 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-11-18
2/60 | Suffolk Sheet 2 | 7 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Jeannie Ethel May Wright | 166 | SK244913 | Freehold |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/60 | Suffolk Sheet 2 | 7 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anne Elizabeth Wright | 518 | SK244913 | Freehold |  |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/60 | Suffolk Sheet 2 | 7 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/60 | Suffolk Sheet 2 | 7 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Jeannie Ethel May Wright | 166 | SK244913 | Occupation |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/60 | Suffolk Sheet 2 | 7 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anne Elizabeth Wright | 518 | SK244913 | Occupation |  |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/60 | Suffolk Sheet 3 | 571 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Freehold | subsoil fronting land to the north of West Lodge, Snape Road |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/60 | Suffolk Sheet 3 | 571 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
3/60 | Suffolk Sheet 3 | 571 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
3/60 | Suffolk Sheet 3 | 571 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/60 | Suffolk Sheet 3 | 571 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/60 | Suffolk Sheet 3 | 571 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | EXA Networks Limited | 3290 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | None Required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/61 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jeannie Ethel May Wright | 166 | SK244913 | Freehold |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/61 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anne Elizabeth Wright | 518 | SK244913 | Freehold |  |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/61 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/61 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jeannie Ethel May Wright | 166 | SK244913 | Occupation |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/61 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anne Elizabeth Wright | 518 | SK244913 | Occupation |  |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/61 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/61 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
3/61 | Suffolk Sheet 3 | 435 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Freehold | subsoil fronting land to the north of West Lodge, Snape Road |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/61 | Suffolk Sheet 3 | 435 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
3/61 | Suffolk Sheet 3 | 435 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
3/61 | Suffolk Sheet 3 | 435 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/61 | Suffolk Sheet 3 | 435 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/61 | Suffolk Sheet 3 | 435 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | EXA Networks Limited | 3290 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | None Required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/62 | Suffolk Sheet 2 | 89 square metres, or thereabouts, of public adopted highway (Grove Road) situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Jeannie Ethel May Wright | 166 | SK244913 | Freehold | subsoil fronting land to the south west of Grove Wood, Grove Road |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/62 | Suffolk Sheet 2 | 89 square metres, or thereabouts, of public adopted highway (Grove Road) situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anne Elizabeth Wright | 518 | SK244913 | Freehold | subsoil fronting land to the south west of Grove Wood, Grove Road |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/62 | Suffolk Sheet 2 | 89 square metres, or thereabouts, of public adopted highway (Grove Road) situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Freehold | subsoil fronting land to the west of Woodside Cottages, Grove Road |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/62 | Suffolk Sheet 2 | 89 square metres, or thereabouts, of public adopted highway (Grove Road) situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/62 | Suffolk Sheet 2 | 89 square metres, or thereabouts, of public adopted highway (Grove Road) situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
3/62 | Suffolk Sheet 3 | 604 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Freehold | subsoil fronting land to the north of West Lodge, Snape Road |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/62 | Suffolk Sheet 3 | 604 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | June Bloomfield | 679 | SK248569 | Freehold | subsoil fronting land to the west of Bulls Hall Cottage, Snape Road |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 26.11.2025 – The Applicant’s land agent, Dalcour Maclaren have engaged with the landowner about the additional plots. Heads of Terms will be issued if appropriate. 09.01.2026 – Dalcour Maclaren issued template Heads of Terms to the landowner’s agent on 4th December 2025 ahead of the Change Request being accepted. Dalcour Maclaren issued populated Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | No Heads of Terms Required |  | 2026-01-09
3/62 | Suffolk Sheet 3 | 604 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
3/62 | Suffolk Sheet 3 | 604 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
3/62 | Suffolk Sheet 3 | 604 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/62 | Suffolk Sheet 3 | 604 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/62 | Suffolk Sheet 3 | 604 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/63 | Suffolk Sheet 2 | 1,314 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jeannie Ethel May Wright | 166 | SK244913 | Freehold |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/63 | Suffolk Sheet 2 | 1,314 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anne Elizabeth Wright | 518 | SK244913 | Freehold |  |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/63 | Suffolk Sheet 2 | 1,314 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/63 | Suffolk Sheet 2 | 1,314 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jeannie Ethel May Wright | 166 | SK244913 | Occupation |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/63 | Suffolk Sheet 2 | 1,314 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anne Elizabeth Wright | 518 | SK244913 | Occupation |  |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/63 | Suffolk Sheet 3 | 178 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | EXA Networks Limited | 3290 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | None Required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/64 | Suffolk Sheet 1 | 1,609 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 | SK258213 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/64 | Suffolk Sheet 1 | 1,609 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 | SK258213 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/64 | Suffolk Sheet 2 | 3,149 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jeannie Ethel May Wright | 166 | SK244913 | Freehold |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/64 | Suffolk Sheet 2 | 3,149 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anne Elizabeth Wright | 518 | SK244913 | Freehold |  |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/64 | Suffolk Sheet 2 | 3,149 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/64 | Suffolk Sheet 2 | 3,149 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jeannie Ethel May Wright | 166 | SK244913 | Occupation |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/64 | Suffolk Sheet 2 | 3,149 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anne Elizabeth Wright | 518 | SK244913 | Occupation |  |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/64 | Suffolk Sheet 3 | 1,309 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Freehold | subsoil fronting land to the north of West Lodge, Snape Road |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/64 | Suffolk Sheet 3 | 1,309 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | June Bloomfield | 679 | SK248569 | Freehold | subsoil fronting land to the west of Bulls Hall Cottage, Snape Road |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 26.11.2025 – The Applicant’s land agent, Dalcour Maclaren have engaged with the landowner about the additional plots. Heads of Terms will be issued if appropriate. 09.01.2026 – Dalcour Maclaren issued template Heads of Terms to the landowner’s agent on 4th December 2025 ahead of the Change Request being accepted. Dalcour Maclaren issued populated Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | No Heads of Terms Required |  | 2026-01-09
3/64 | Suffolk Sheet 3 | 1,309 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
3/64 | Suffolk Sheet 3 | 1,309 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
3/64 | Suffolk Sheet 3 | 1,309 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/64 | Suffolk Sheet 3 | 1,309 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/64 | Suffolk Sheet 3 | 1,309 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/64 | Suffolk Sheet 3 | 1,309 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | EXA Networks Limited | 3290 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | None Required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/65 | Suffolk Sheet 2 | 461 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Jeannie Ethel May Wright | 166 | SK244913 | Freehold |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/65 | Suffolk Sheet 2 | 461 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anne Elizabeth Wright | 518 | SK244913 | Freehold |  |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/65 | Suffolk Sheet 2 | 461 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/65 | Suffolk Sheet 2 | 461 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Jeannie Ethel May Wright | 166 | SK244913 | Occupation |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/65 | Suffolk Sheet 2 | 461 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anne Elizabeth Wright | 518 | SK244913 | Occupation |  |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/65 | Suffolk Sheet 2 | 461 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/65 | Suffolk Sheet 2 | 461 square metres, or thereabouts, of scrubland situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
2/66 | Suffolk Sheet 2 | 36 square metres, or thereabouts, of scrubland situated to the north of Grove House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Guy Hilliard Heald | 109 | SK194564,SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/66 | Suffolk Sheet 2 | 36 square metres, or thereabouts, of scrubland situated to the north of Grove House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lucinda Jane Fullerton Heald | 766 | SK194564,SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/66 | Suffolk Sheet 2 | 36 square metres, or thereabouts, of scrubland situated to the north of Grove House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Guy Hilliard Heald | 109 | SK194564,SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/66 | Suffolk Sheet 2 | 36 square metres, or thereabouts, of scrubland situated to the north of Grove House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/66 | Suffolk Sheet 2 | 36 square metres, or thereabouts, of scrubland situated to the north of Grove House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lucinda Jane Fullerton Heald | 766 | SK194564,SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/66 | Suffolk Sheet 2 | 36 square metres, or thereabouts, of scrubland situated to the north of Grove House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
1/67 | Suffolk Sheet 1 | 7,683 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK258213 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/67 | Suffolk Sheet 1 | 7,683 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK258213 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/67 | Suffolk Sheet 2 | 791 square metres, or thereabouts, of public footpath (Friston Footpath, 017) situated to the north of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Jeannie Ethel May Wright | 166 |  | Occupation |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/67 | Suffolk Sheet 2 | 791 square metres, or thereabouts, of public footpath (Friston Footpath, 017) situated to the north of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anne Elizabeth Wright | 518 |  | Occupation |  |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/67 | Suffolk Sheet 2 | 791 square metres, or thereabouts, of public footpath (Friston Footpath, 017) situated to the north of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Suffolk County Council | 755 |  | Occupation | public footpath |  | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/68 | Suffolk Sheet 2 | 461 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Jeannie Ethel May Wright | 166 | SK244913 | Freehold |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/68 | Suffolk Sheet 2 | 461 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Anne Elizabeth Wright | 518 | SK244913 | Freehold |  |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/68 | Suffolk Sheet 2 | 461 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/68 | Suffolk Sheet 2 | 461 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Jeannie Ethel May Wright | 166 | SK244913 | Occupation |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/68 | Suffolk Sheet 2 | 461 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Anne Elizabeth Wright | 518 | SK244913 | Occupation |  |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/69 | Suffolk Sheet 1 | 5,005 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK363555 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/69 | Suffolk Sheet 1 | 5,005 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK363555 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/69 | Suffolk Sheet 1 | 5,005 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/69 | Suffolk Sheet 1 | 5,005 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/69 | Suffolk Sheet 2 | 15 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Jeannie Ethel May Wright | 166 | SK244913 | Freehold |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/69 | Suffolk Sheet 2 | 15 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anne Elizabeth Wright | 518 | SK244913 | Freehold |  |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/69 | Suffolk Sheet 2 | 15 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/69 | Suffolk Sheet 2 | 15 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Jeannie Ethel May Wright | 166 | SK244913 | Occupation |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/69 | Suffolk Sheet 2 | 15 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anne Elizabeth Wright | 518 | SK244913 | Occupation |  |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/70 | Suffolk Sheet 1 | 2,553 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK363555 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/70 | Suffolk Sheet 1 | 2,553 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK363555 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/70 | Suffolk Sheet 1 | 2,553 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/70 | Suffolk Sheet 2 | 3,605 square metres, or thereabouts, of agricultural land and track situated to the north east of Friston House, Suffolk, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/70 | Suffolk Sheet 2 | 3,605 square metres, or thereabouts, of agricultural land and track situated to the north east of Friston House, Suffolk, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/70 | Suffolk Sheet 2 | 3,605 square metres, or thereabouts, of agricultural land and track situated to the north east of Friston House, Suffolk, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/71 | Suffolk Sheet 1 | 3,558 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 | SK363555 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/71 | Suffolk Sheet 1 | 3,558 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 | SK363555 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/71 | Suffolk Sheet 2 | 298 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/71 | Suffolk Sheet 2 | 298 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/71 | Suffolk Sheet 2 | 298 square metres, or thereabouts, of agricultural land situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/72 | Suffolk Sheet 1 | 756 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Ian Charles Rix | 692 | SK363555 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/72 | Suffolk Sheet 1 | 756 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Ian Charles Rix | 692 | SK363555 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/72 | Suffolk Sheet 1 | 756 square metres, or thereabouts, of agricultural land situated to the north east of Red House Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/72 | Suffolk Sheet 2 | 84,009 square metres, or thereabouts, of agricultural land and track situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Jeannie Ethel May Wright | 166 | SK244913 | Freehold |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/72 | Suffolk Sheet 2 | 84,009 square metres, or thereabouts, of agricultural land and track situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anne Elizabeth Wright | 518 | SK244913 | Freehold |  |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/72 | Suffolk Sheet 2 | 84,009 square metres, or thereabouts, of agricultural land and track situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/72 | Suffolk Sheet 2 | 84,009 square metres, or thereabouts, of agricultural land and track situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Jeannie Ethel May Wright | 166 | SK244913 | Occupation |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/72 | Suffolk Sheet 2 | 84,009 square metres, or thereabouts, of agricultural land and track situated to the north east of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anne Elizabeth Wright | 518 | SK244913 | Occupation |  |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/73 | Suffolk Sheet 1 | 21 square metres, or thereabouts, of agricultural land situated to the east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK363555 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/73 | Suffolk Sheet 1 | 21 square metres, or thereabouts, of agricultural land situated to the east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK363555 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/73 | Suffolk Sheet 2 | 2,664 square metres, or thereabouts, of scrubland and public footpath (Friston Footpath, 017) and overhead telecommunication lines situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights – Drainage | Class 6. Compulsory Acquisition of Rights – Drainage | Anglian Water Services Limited | 82 |  | Occupation | underground sewage pipeline |  | Category 1 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/73 | Suffolk Sheet 2 | 2,664 square metres, or thereabouts, of scrubland and public footpath (Friston Footpath, 017) and overhead telecommunication lines situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights – Drainage | Class 6. Compulsory Acquisition of Rights – Drainage | Jeannie Ethel May Wright | 166 |  | Occupation |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/73 | Suffolk Sheet 2 | 2,664 square metres, or thereabouts, of scrubland and public footpath (Friston Footpath, 017) and overhead telecommunication lines situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights – Drainage | Class 6. Compulsory Acquisition of Rights – Drainage | Anne Elizabeth Wright | 518 |  | Occupation |  |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/73 | Suffolk Sheet 2 | 2,664 square metres, or thereabouts, of scrubland and public footpath (Friston Footpath, 017) and overhead telecommunication lines situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights – Drainage | Class 6. Compulsory Acquisition of Rights – Drainage | Suffolk County Council | 755 |  | Occupation | public footpath |  | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/73 | Suffolk Sheet 2 | 2,664 square metres, or thereabouts, of scrubland and public footpath (Friston Footpath, 017) and overhead telecommunication lines situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights – Drainage | Class 6. Compulsory Acquisition of Rights – Drainage | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/73 | Suffolk Sheet 2 | 2,664 square metres, or thereabouts, of scrubland and public footpath (Friston Footpath, 017) and overhead telecommunication lines situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights – Drainage | Class 6. Compulsory Acquisition of Rights – Drainage | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/73 | Suffolk Sheet 2 | 2,664 square metres, or thereabouts, of scrubland and public footpath (Friston Footpath, 017) and overhead telecommunication lines situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights – Drainage | Class 6. Compulsory Acquisition of Rights – Drainage | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Nichol | 30 | SK346463 | Freehold | subsoil fronting land to the east of The Manor House, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Nichol | 30 | SK346465 | Freehold | subsoil fronting land to the south of The Manor House, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gerlinde Edmunds | 135 | SK346463 | Freehold | subsoil fronting land to the east of The Manor House, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gerlinde Edmunds | 135 | SK346465 | Freehold | subsoil fronting land to the south of The Manor House, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK346465 | Freehold | subsoil fronting land to the south of The Manor House, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold | subsoil fronting land to the south west of Wardspring Farm, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laurence Justin Dowley | 1367 | SK390468 | Freehold | subsoil fronting land to the east of The Manor House, Leiston Road |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 -This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-11-18
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Emma Louise Dowley | 1368 | SK390468 | Freehold | subsoil fronting land to the east of The Manor House, Leiston Road |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 -This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-11-18
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cripps Trust Corporation Limited | 1369 | SK390468 | Freehold | subsoil fronting land to the east of The Manor House, Leiston Road | as trustee to The Dowley Family Discretionary Settlement 2018 | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 -This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-11-18
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cadent Gas Limited | 1055 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-0656 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. | No Heads of Terms Required |  | 2026-01-09
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/75 | Suffolk Sheet 1 | 220 square metres, or thereabouts, of private road (unnamed), public footpath (023), drain and overhead electricity distribution lines situated to the north of Drove Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Nichol | 30 | SK346465 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/75 | Suffolk Sheet 1 | 220 square metres, or thereabouts, of private road (unnamed), public footpath (023), drain and overhead electricity distribution lines situated to the north of Drove Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gerlinde Edmunds | 135 | SK346465 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/75 | Suffolk Sheet 1 | 220 square metres, or thereabouts, of private road (unnamed), public footpath (023), drain and overhead electricity distribution lines situated to the north of Drove Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK346465 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/75 | Suffolk Sheet 1 | 220 square metres, or thereabouts, of private road (unnamed), public footpath (023), drain and overhead electricity distribution lines situated to the north of Drove Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation | public footpath |  | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/75 | Suffolk Sheet 1 | 220 square metres, or thereabouts, of private road (unnamed), public footpath (023), drain and overhead electricity distribution lines situated to the north of Drove Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/75 | Suffolk Sheet 1 | 220 square metres, or thereabouts, of private road (unnamed), public footpath (023), drain and overhead electricity distribution lines situated to the north of Drove Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/75 | Suffolk Sheet 2 | 15 square metres, or thereabouts, of agricultural land and public footpath (Friston Footpath, 017) situated to the north west of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Jeannie Ethel May Wright | 166 |  | Occupation |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/75 | Suffolk Sheet 2 | 15 square metres, or thereabouts, of agricultural land and public footpath (Friston Footpath, 017) situated to the north west of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anne Elizabeth Wright | 518 |  | Occupation |  |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/75 | Suffolk Sheet 2 | 15 square metres, or thereabouts, of agricultural land and public footpath (Friston Footpath, 017) situated to the north west of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Suffolk County Council | 755 |  | Occupation | public footpath |  | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/76 | Suffolk Sheet 1 | 7,507 square metres, or thereabouts, of agricultural land, drain and overhead telecommunication lines situated to the west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Caroline Nichol | 30 | SK346463 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/76 | Suffolk Sheet 1 | 7,507 square metres, or thereabouts, of agricultural land, drain and overhead telecommunication lines situated to the west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Gerlinde Edmunds | 135 | SK346463 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/76 | Suffolk Sheet 1 | 7,507 square metres, or thereabouts, of agricultural land, drain and overhead telecommunication lines situated to the west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Caroline Nichol | 30 | SK346463 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/76 | Suffolk Sheet 1 | 7,507 square metres, or thereabouts, of agricultural land, drain and overhead telecommunication lines situated to the west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Gerlinde Edmunds | 135 | SK346463 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/76 | Suffolk Sheet 1 | 7,507 square metres, or thereabouts, of agricultural land, drain and overhead telecommunication lines situated to the west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/76 | Suffolk Sheet 1 | 7,507 square metres, or thereabouts, of agricultural land, drain and overhead telecommunication lines situated to the west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
1/76 | Suffolk Sheet 1 | 7,507 square metres, or thereabouts, of agricultural land, drain and overhead telecommunication lines situated to the west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/76 | Suffolk Sheet 1 | 7,507 square metres, or thereabouts, of agricultural land, drain and overhead telecommunication lines situated to the west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/76 | Suffolk Sheet 2 | 146 square metres, or thereabouts, of grassed area situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Jeannie Ethel May Wright | 166 | SK261792 | Freehold |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/76 | Suffolk Sheet 2 | 146 square metres, or thereabouts, of grassed area situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anne Elizabeth Wright | 518 | SK261792 | Freehold |  |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/76 | Suffolk Sheet 2 | 146 square metres, or thereabouts, of grassed area situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Jeannie Ethel May Wright | 166 | SK261792 | Occupation |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/76 | Suffolk Sheet 2 | 146 square metres, or thereabouts, of grassed area situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anne Elizabeth Wright | 518 | SK261792 | Occupation |  |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 – Following negotiations, Dalcour Maclaren issued revised Heads of Terms on 10th October 2025. Dalcour Maclaren met with the landowner and their agent on 10th November 2025 to discuss the revised Heads of Terms. A follow up Teams meeting has been scheduled with the landowner’s agent for early December 2025. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/77 | Suffolk Sheet 1 | 354 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Caroline Nichol | 30 | SK346463 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/77 | Suffolk Sheet 1 | 354 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Gerlinde Edmunds | 135 | SK346463 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/77 | Suffolk Sheet 1 | 354 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Caroline Nichol | 30 | SK346463 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/77 | Suffolk Sheet 1 | 354 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Gerlinde Edmunds | 135 | SK346463 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/77 | Suffolk Sheet 1 | 354 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/77 | Suffolk Sheet 1 | 354 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
2/77 | Suffolk Sheet 2 | 76 square metres, or thereabouts, of public adopted highway (Church Road) and track situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/77 | Suffolk Sheet 2 | 76 square metres, or thereabouts, of public adopted highway (Church Road) and track situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Pauline Violet Ellis | 2767 |  | Freehold | subsoil fronting Glenhurst, Church Road |  | Category 1 |  | No | [11 empty] | No Heads of Terms Required |  | 2026-01-09
2/77 | Suffolk Sheet 2 | 76 square metres, or thereabouts, of public adopted highway (Church Road) and track situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Michael Anthony Lewis | 3067 | SK131203 | Freehold | subsoil fronting Church Cottage, Church Lane |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/77 | Suffolk Sheet 2 | 76 square metres, or thereabouts, of public adopted highway (Church Road) and track situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Anglian Water Services Limited | 82 |  | Occupation | underground sewage pipeline |  | Category 1 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
2/77 | Suffolk Sheet 2 | 76 square metres, or thereabouts, of public adopted highway (Church Road) and track situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/77 | Suffolk Sheet 2 | 76 square metres, or thereabouts, of public adopted highway (Church Road) and track situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/77 | Suffolk Sheet 2 | 76 square metres, or thereabouts, of public adopted highway (Church Road) and track situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/77 | Suffolk Sheet 2 | 76 square metres, or thereabouts, of public adopted highway (Church Road) and track situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
2/77 | Suffolk Sheet 2 | 76 square metres, or thereabouts, of public adopted highway (Church Road) and track situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/77 | Suffolk Sheet 2 | 76 square metres, or thereabouts, of public adopted highway (Church Road) and track situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/78 | Suffolk Sheet 1 | 665 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Nichol | 30 | SK346463 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/78 | Suffolk Sheet 1 | 665 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gerlinde Edmunds | 135 | SK346463 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/78 | Suffolk Sheet 1 | 665 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Nichol | 30 | SK346463 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/78 | Suffolk Sheet 1 | 665 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gerlinde Edmunds | 135 | SK346463 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/78 | Suffolk Sheet 1 | 665 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/78 | Suffolk Sheet 1 | 665 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
2/78 | Suffolk Sheet 2 | 1,606 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 | SK432967 | Freehold |  |  | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
1/79 | Suffolk Sheet 1 | 7,945 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Caroline Nichol | 30 | SK346463 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/79 | Suffolk Sheet 1 | 7,945 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Gerlinde Edmunds | 135 | SK346463 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/79 | Suffolk Sheet 1 | 7,945 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Caroline Nichol | 30 | SK346463 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/79 | Suffolk Sheet 1 | 7,945 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Gerlinde Edmunds | 135 | SK346463 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/79 | Suffolk Sheet 2 | 954 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ernest Alexander Tait Wright | 342 | SK151617 | Freehold |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren emailed the landowner's agent on 6th September 2025 and 15th October 2025 requesting an update on the Heads of Terms issued in August. Dalcour Maclaren have scheduled a Teams meeting with the landowner’s agent in early December 2025 to discuss the Heads of Terms. Additionally, we understand there may be some changes to the ownership of this plot which will be discussed further. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 10th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/79 | Suffolk Sheet 2 | 954 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ernest Alexander Tait Wright | 342 | SK151617 | Occupation |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren emailed the landowner's agent on 6th September 2025 and 15th October 2025 requesting an update on the Heads of Terms issued in August. Dalcour Maclaren have scheduled a Teams meeting with the landowner’s agent in early December 2025 to discuss the Heads of Terms. Additionally, we understand there may be some changes to the ownership of this plot which will be discussed further. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 10th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/80 | Suffolk Sheet 1 | 2,636 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/80 | Suffolk Sheet 1 | 2,636 square metres, or thereabouts, of agricultural land situated to the south east of The Manor House, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/81 | Suffolk Sheet 1 | 2,732 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/81 | Suffolk Sheet 1 | 2,732 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/81 | Suffolk Sheet 1 | 2,732 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/81 | Suffolk Sheet 1 | 2,732 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
1/81 | Suffolk Sheet 1 | 2,732 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/81 | Suffolk Sheet 2 | 24 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Andrew Michael Hilliard Heald | 352 | SK276346 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | Yes | RR-0274 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 6 March. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 – Dalcour Maclaren have not received any response from the landowner or their agent after reissuing Heads of Terms on 29th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/81 | Suffolk Sheet 2 | 24 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Emma May Alexandra Heald | 545 | SK276346 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | Yes | RR-0274 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 6 March. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 – Dalcour Maclaren have not received any response from the landowner or their agent after reissuing Heads of Terms on 29th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/82 | Suffolk Sheet 1 | 194 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/82 | Suffolk Sheet 1 | 194 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/83 | Suffolk Sheet 1 | 70 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/83 | Suffolk Sheet 1 | 70 square metres, or thereabouts, of agricultural land situated to the south west of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/83 | Suffolk Sheet 2 | 232 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Andrew Michael Hilliard Heald | 352 | SK276346 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | Yes | RR-0274 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 6 March. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 – Dalcour Maclaren have not received any response from the landowner or their agent after reissuing Heads of Terms on 29th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/83 | Suffolk Sheet 2 | 232 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Emma May Alexandra Heald | 545 | SK276346 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | Yes | RR-0274 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 6 March. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 09.01.2026 – Dalcour Maclaren have not received any response from the landowner or their agent after reissuing Heads of Terms on 29th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/84 | Suffolk Sheet 1 | 119 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/84 | Suffolk Sheet 1 | 119 square metres, or thereabouts, of agricultural land, drain and track situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/84 | Suffolk Sheet 2 | 1,699 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution line situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Michael Guy Hilliard Heald | 109 | SK194564,SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/84 | Suffolk Sheet 2 | 1,699 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution line situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lucinda Jane Fullerton Heald | 766 | SK194564,SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/84 | Suffolk Sheet 2 | 1,699 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution line situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Michael Guy Hilliard Heald | 109 | SK194564,SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/84 | Suffolk Sheet 2 | 1,699 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution line situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/84 | Suffolk Sheet 2 | 1,699 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution line situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lucinda Jane Fullerton Heald | 766 | SK194564,SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/84 | Suffolk Sheet 2 | 1,699 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution line situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/84 | Suffolk Sheet 2 | 1,699 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution line situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
1/85 | Suffolk Sheet 1 | 193 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/85 | Suffolk Sheet 1 | 193 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/85 | Suffolk Sheet 1 | 193 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/85 | Suffolk Sheet 1 | 193 square metres, or thereabouts, of agricultural land situated to the south west of Trust Farm, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | Nathaniel Bacon | 3135 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-11-18
2/85 | Suffolk Sheet 2 | 26 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Michael Guy Hilliard Heald | 109 | SK194564,SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/85 | Suffolk Sheet 2 | 26 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Lucinda Jane Fullerton Heald | 766 | SK194564,SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/85 | Suffolk Sheet 2 | 26 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Michael Guy Hilliard Heald | 109 | SK194564,SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/85 | Suffolk Sheet 2 | 26 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Lucinda Jane Fullerton Heald | 766 | SK194564,SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/86 | Suffolk Sheet 1 | 10 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/86 | Suffolk Sheet 1 | 10 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/86 | Suffolk Sheet 1 | 10 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/86 | Suffolk Sheet 1 | 10 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/86 | Suffolk Sheet 1 | 10 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
1/86 | Suffolk Sheet 1 | 10 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Nathaniel Bacon | 3135 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-11-18
1/87 | Suffolk Sheet 1 | 135 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/87 | Suffolk Sheet 1 | 135 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/87 | Suffolk Sheet 1 | 135 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/87 | Suffolk Sheet 1 | 135 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/87 | Suffolk Sheet 1 | 135 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
1/87 | Suffolk Sheet 1 | 135 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Nathaniel Bacon | 3135 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-11-18
1/88 | Suffolk Sheet 1 | 75 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | James John Skellorn | 476 | SK311155 | Freehold | subsoil fronting land to the north of Hill Farm, The Street |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/88 | Suffolk Sheet 1 | 75 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/88 | Suffolk Sheet 1 | 75 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold | subsoil fronting land to the north of Hill Farm, The Street |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/88 | Suffolk Sheet 1 | 75 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/88 | Suffolk Sheet 1 | 75 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cadent Gas Limited | 1055 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-0656 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. | No Heads of Terms Required |  | 2026-01-09
1/89 | Suffolk Sheet 1 | 472 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK258213 | Freehold | subsoil fronting land to the north of Redhouse Farm, The Street |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/89 | Suffolk Sheet 1 | 472 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/89 | Suffolk Sheet 1 | 472 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/89 | Suffolk Sheet 1 | 472 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cadent Gas Limited | 1055 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-0656 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. | No Heads of Terms Required |  | 2026-01-09
1/90 | Suffolk Sheet 1 | 137 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/90 | Suffolk Sheet 1 | 137 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/90 | Suffolk Sheet 1 | 137 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/90 | Suffolk Sheet 1 | 137 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/90 | Suffolk Sheet 1 | 137 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
1/90 | Suffolk Sheet 1 | 137 square metres, or thereabouts, of agricultural land situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Nathaniel Bacon | 3135 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-11-18
2/90 | Suffolk Sheet 2 | 19 square metres, or thereabouts, of agricultural land and track situated to the east of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/91 | Suffolk Sheet 1 | 96 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James John Skellorn | 476 | SK311155 | Freehold | subsoil fronting land to the north of Hill Farm, The Street |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/91 | Suffolk Sheet 1 | 96 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 | SK258213 | Freehold | subsoil fronting land to the north of Redhouse Farm, The Street |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/91 | Suffolk Sheet 1 | 96 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/91 | Suffolk Sheet 1 | 96 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold | subsoil fronting land to the north of Hill Farm, The Street |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/91 | Suffolk Sheet 1 | 96 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/91 | Suffolk Sheet 1 | 96 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-0656 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. | No Heads of Terms Required |  | 2026-01-09
1/92 | Suffolk Sheet 1 | 18 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 | SK258213 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/92 | Suffolk Sheet 1 | 18 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/92 | Suffolk Sheet 1 | 18 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 | SK258213 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/92 | Suffolk Sheet 1 | 18 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
1/93 | Suffolk Sheet 1 | 991 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian Charles Rix | 692 | SK258213 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/93 | Suffolk Sheet 1 | 991 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/93 | Suffolk Sheet 1 | 991 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian Charles Rix | 692 | SK258213 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/93 | Suffolk Sheet 1 | 991 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
1/94 | Suffolk Sheet 1 | 687 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian Charles Rix | 692 | SK258213 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/94 | Suffolk Sheet 1 | 687 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/94 | Suffolk Sheet 1 | 687 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian Charles Rix | 692 | SK258213 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/94 | Suffolk Sheet 1 | 687 square metres, or thereabouts, of agricultural land situated to the south east of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
1/95 | Suffolk Sheet 1 | 184 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 | SK258213 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/95 | Suffolk Sheet 1 | 184 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/95 | Suffolk Sheet 1 | 184 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 | SK258213 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/95 | Suffolk Sheet 1 | 184 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
1/96 | Suffolk Sheet 1 | 44 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 | SK258213 | Freehold | subsoil fronting land to the north of Redhouse Farm, The Street |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/96 | Suffolk Sheet 1 | 44 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/96 | Suffolk Sheet 1 | 44 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/96 | Suffolk Sheet 1 | 44 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-0656 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. | No Heads of Terms Required |  | 2026-01-09
1/97 | Suffolk Sheet 1 | 19 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 10. Land that is not subject to powers of acquisition nor temporary use | Class 10. Land that is not subject to powers of acquisition nor temporary use | Robert Roy Jonas Nichol | 439 | SK391706 | Freehold | subsoil fronting land to the south of Wardspring Farm, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/97 | Suffolk Sheet 1 | 19 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 10. Land that is not subject to powers of acquisition nor temporary use | Class 10. Land that is not subject to powers of acquisition nor temporary use | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/97 | Suffolk Sheet 1 | 19 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 10. Land that is not subject to powers of acquisition nor temporary use | Class 10. Land that is not subject to powers of acquisition nor temporary use | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/98 | Suffolk Sheet 1 | 323 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jane Ruth Van Lennep | 383 | SK157041 | Freehold | subsoil fronting Meadow Farm, Saxmundham Road |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-10-08
1/98 | Suffolk Sheet 1 | 323 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK391706 | Freehold | subsoil fronting land to the south of Wardspring Farm, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/98 | Suffolk Sheet 1 | 323 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK258213 | Freehold | subsoil fronting land to the north of Redhouse Farm, The Street |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/98 | Suffolk Sheet 1 | 323 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/98 | Suffolk Sheet 1 | 323 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/98 | Suffolk Sheet 1 | 323 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/98 | Suffolk Sheet 1 | 323 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
1/98 | Suffolk Sheet 1 | 323 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cadent Gas Limited | 1055 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-0656 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. | No Heads of Terms Required |  | 2026-01-09
1/99 | Suffolk Sheet 1 | 699 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian Charles Rix | 692 | SK258213 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/99 | Suffolk Sheet 1 | 699 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/99 | Suffolk Sheet 1 | 699 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian Charles Rix | 692 | SK258213 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/99 | Suffolk Sheet 1 | 699 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
2/99 | Suffolk Sheet 2 | 274 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian Charles Rix | 692 | SK312683 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/99 | Suffolk Sheet 2 | 274 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/99 | Suffolk Sheet 2 | 274 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south west of Peartree Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian Charles Rix | 692 | SK312683 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/13 | Suffolk Sheet 1 | 1,175 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/13 | Suffolk Sheet 1 | 1,175 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/13 | Suffolk Sheet 1 | 1,175 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/13 | Suffolk Sheet 1 | 1,175 square metres, or thereabouts, of agricultural land and drain situated to the south of Happy Days (Camp Site), Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
2/13 | Suffolk Sheet 2 | 3,022 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK312683 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/13 | Suffolk Sheet 2 | 3,022 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/13 | Suffolk Sheet 2 | 3,022 square metres, or thereabouts, of agricultural land situated to the south east of Red House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK312683 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/13 | Suffolk Sheet 3 | 732 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/13 | Suffolk Sheet 4 | 2,559 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Hazlewood Hall Management Company Limited | 224 | SK258640 | Freehold | subsoil fronting land to the south west of Hazlewood Hall Cottages, Aldeburgh Road |  | Category 1 | N/A | Yes | RR-1953 | [6 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-01-09
4/13 | Suffolk Sheet 4 | 2,559 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK356298 | Freehold | subsoil fronting land to the south of Hazlewood Hall Cottages, Aldeburgh Road |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/13 | Suffolk Sheet 4 | 2,559 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Freehold | subsoil fronting land to the south west of Stackyard Cottage, Aldeburgh Road |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/13 | Suffolk Sheet 4 | 2,559 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
4/13 | Suffolk Sheet 4 | 2,559 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
4/13 | Suffolk Sheet 4 | 2,559 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/13 | Suffolk Sheet 4 | 2,559 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/13 | Suffolk Sheet 4 | 2,559 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Virgin Media Limited | 3289 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | None Required |  | 09.01.2026 - Engagement is ongoing | No Heads of Terms Required |  | 2025-10-08
4/13 | Suffolk Sheet 4 | 2,559 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Vodafone Limited | 3295 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | None Required |  | 09.01.2025 - Engagement is ongoing | No Heads of Terms Required |  | 2025-10-08
5/13 | Suffolk Sheet 5 | 3,233 square metres, or thereabouts, of scrubland situated to the south of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David John Beatton | 598 | SK382238 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/13 | Suffolk Sheet 5 | 3,233 square metres, or thereabouts, of scrubland situated to the south of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sarah Ann Beeton | 730 | SK382238 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent, on 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK150493 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
7/13 | Suffolk Sheet 7 | 145 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/14 | Suffolk Sheet 1 | 9 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Nichol | 30 | SK346465 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/14 | Suffolk Sheet 1 | 9 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gerlinde Edmunds | 135 | SK346465 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/14 | Suffolk Sheet 1 | 9 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK346465 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/14 | Suffolk Sheet 1 | 9 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation | public footpath |  | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/14 | Suffolk Sheet 1 | 9 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/14 | Suffolk Sheet 2 | 591 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Fristonmoor Barn, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK363555 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/14 | Suffolk Sheet 2 | 591 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Fristonmoor Barn, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK363555 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/14 | Suffolk Sheet 2 | 591 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north west of Fristonmoor Barn, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/14 | Suffolk Sheet 3 | 4,547 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/14 | Suffolk Sheet 3 | 4,547 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/14 | Suffolk Sheet 4 | 918 square metres, or thereabouts, of public unadopted highway (Sloe Lane) and agricultural land situated to the west of Great Wood, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lindsay Peter Tomlinson | 335 | SK307283 | Freehold | subsoil fronting land to the south of Hillbury, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Pauline Trudy Klauber | 396 | SK162921 | Freehold | subsoil fronting Hillbury, Leiston Road |  | Category 1 | No Agent Known | Yes | REP2-099 | [6 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Jane Elizabeth Walker | 400 | SK199083 | Freehold | subsoil fronting High Warren, Leiston Road |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | David Mcleod Walker | 459 | SK199083 | Freehold | subsoil fronting High Warren, Leiston Road |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sarah Tomlinson | 491 | SK307283 | Freehold | subsoil fronting land to the south of Hillbury, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | David Jeremy Jackson | 567 | SK271297 | Freehold | subsoil fronting Dulce Domum, Leiston Road |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | David John Beatton | 598 | SK382238 | Freehold | subsoil fronting land to the north of Warren Cottage, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sarah Ann Beeton | 730 | SK382238 | Freehold | subsoil fronting land to the north of Warren Cottage, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent, on 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Bridget Clare Youell | 764 | SK162921 | Freehold | subsoil fronting Hillbury, Leiston Road |  | Category 1 | No Agent Known | Yes | RR-0632 REP2-070 | [6 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Public Trustee | 825 | SK134793 | Freehold | subsoil fronting Foxborough House, Leiston Road | as Personal Representative to the Estate of Peter Dickinson | Category 1 | No Agent Known | Yes | RR-5322 | [6 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Bridget Jane Dickinson | 1454 | SK134793 | Freehold | subsoil fronting Foxborough House, Leiston Road |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Karen Jane Mountford | 1467 | SK192529 | Freehold | subsoil fronting North East, Leiston Road |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Peter Dickinson | 2754 | SK134793 | Freehold | subsoil fronting Foxborough House, Leiston Road |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-0656 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. | No Heads of Terms Required |  | 2026-01-09
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Virgin Media Limited | 3289 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | None Required |  | 09.01.2026 - Engagement is ongoing | No Heads of Terms Required |  | 2025-10-08
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Vodafone Limited | 3295 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | None Required |  | 09.01.2025 - Engagement is ongoing | No Heads of Terms Required |  | 2025-10-08
2/15 | Suffolk Sheet 2 | 50,016 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of High House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK363555 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/15 | Suffolk Sheet 2 | 50,016 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of High House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/15 | Suffolk Sheet 2 | 50,016 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of High House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner of part | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/15 | Suffolk Sheet 2 | 50,016 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of High House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK363555 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/15 | Suffolk Sheet 2 | 50,016 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of High House Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/15 | Suffolk Sheet 3 | 277 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/15 | Suffolk Sheet 3 | 277 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation | public footpath |  | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/15 | Suffolk Sheet 4 | 948 square metres, or thereabouts, of public footpath (Friston Footpath 013A) and track situated to the west of Great Wood, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
5/15 | Suffolk Sheet 5 | 187 square metres, or thereabouts, of grassland situated to the south of Foxborough House, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lindsay Peter Tomlinson | 335 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/15 | Suffolk Sheet 5 | 187 square metres, or thereabouts, of grassland situated to the south of Foxborough House, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sarah Tomlinson | 491 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK150493 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
7/15 | Suffolk Sheet 7 | 120 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/16 | Suffolk Sheet 1 | 1,455 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Nichol | 30 | SK346465 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/16 | Suffolk Sheet 1 | 1,455 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gerlinde Edmunds | 135 | SK346465 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/16 | Suffolk Sheet 1 | 1,455 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK346465 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/16 | Suffolk Sheet 1 | 1,455 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/16 | Suffolk Sheet 1 | 1,455 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation | public footpath |  | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/16 | Suffolk Sheet 1 | 1,455 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
1/16 | Suffolk Sheet 1 | 1,455 square metres, or thereabouts, of public footpath (023) situated to the south of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/16 | Suffolk Sheet 2 | 197 square metres, or thereabouts, of agricultural land situated to the south west of High House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK363555 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/16 | Suffolk Sheet 2 | 197 square metres, or thereabouts, of agricultural land situated to the south west of High House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK363555 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/16 | Suffolk Sheet 3 | 1,419 square metres, or thereabouts, of agricultural land, track, electricity pylon and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/16 | Suffolk Sheet 3 | 1,419 square metres, or thereabouts, of agricultural land, track, electricity pylon and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/16 | Suffolk Sheet 3 | 1,419 square metres, or thereabouts, of agricultural land, track, electricity pylon and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | electricity substation |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/16 | Suffolk Sheet 4 | 5,282 square metres, or thereabouts, of premises (Hazlewood Hall Farm), private road, agricultural land, overhead electricity distribution lines and electricity substation situated to the east of Meadowpiece Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
5/16 | Suffolk Sheet 5 | 77 square metres, or thereabouts, of scrubland situated to the north of Warren Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | David John Beatton | 598 | SK382238 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/16 | Suffolk Sheet 5 | 77 square metres, or thereabouts, of scrubland situated to the north of Warren Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sarah Ann Beeton | 730 | SK382238 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent, on 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
7/16 | Suffolk Sheet 7 | 32 square metres, or thereabouts, of public adopted highway (B1121, Main Road), situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Highways Limited | 374 | SK311340 | Freehold |  |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-01-09
7/16 | Suffolk Sheet 7 | 32 square metres, or thereabouts, of public adopted highway (B1121, Main Road), situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
7/16 | Suffolk Sheet 7 | 32 square metres, or thereabouts, of public adopted highway (B1121, Main Road), situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/17 | Suffolk Sheet 1 | 25,224 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Nichol | 30 | SK346463 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/17 | Suffolk Sheet 1 | 25,224 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gerlinde Edmunds | 135 | SK346463 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/17 | Suffolk Sheet 1 | 25,224 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Nichol | 30 | SK346463 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/17 | Suffolk Sheet 1 | 25,224 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gerlinde Edmunds | 135 | SK346463 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/17 | Suffolk Sheet 1 | 25,224 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/17 | Suffolk Sheet 1 | 25,224 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
2/17 | Suffolk Sheet 2 | 1,465 square metres, or thereabouts, of agricultural land situated to the south of High House Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian Charles Rix | 692 | SK363555 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/17 | Suffolk Sheet 2 | 1,465 square metres, or thereabouts, of agricultural land situated to the south of High House Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian Charles Rix | 692 | SK363555 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/17 | Suffolk Sheet 3 | 300 square metres, or thereabouts, of agricultural land, track, electricity pylon and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/17 | Suffolk Sheet 3 | 300 square metres, or thereabouts, of agricultural land, track, electricity pylon and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | ScottishPower (UK) Renewables Limited | 2298 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/17 | Suffolk Sheet 4 | 2,016 square metres, or thereabouts, of agricultural land situated to the north of Hazlewood Hall Farm, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lindsay Peter Tomlinson | 335 | SK307283 | Freehold | subsoil fronting land to the south of Hillbury, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sarah Tomlinson | 491 | SK307283 | Freehold | subsoil fronting land to the south of Hillbury, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | David John Beatton | 598 | SK382238 | Freehold | subsoil fronting land to the north of Warren Cottage, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sarah Ann Beeton | 730 | SK382238 | Freehold | subsoil fronting land to the north of Warren Cottage, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent, on 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Aldeburgh Golf Club Limited | 1668 | SK329337 | Freehold | subsoil fronting land to the north of Warren Cottage, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-0093 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. Dalcour Maclaren are scheduling a meeting with the landowner and their agent in early December 2025. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 9th December 2025 after discussions with their agent regarding points outstanding from previous meetings. A meeting is being arranged with the landowner and their agent in January, a previous meeting scheduled for 9th December 2025 was rescheduled at the landowner’s request. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Cadent Gas Limited | 1055 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-0656 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. | No Heads of Terms Required |  | 2026-01-09
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Virgin Media Limited | 3289 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | None Required |  | 09.01.2026 - Engagement is ongoing | No Heads of Terms Required |  | 2025-10-08
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Vodafone Limited | 3295 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | None Required |  | 09.01.2025 - Engagement is ongoing | No Heads of Terms Required |  | 2025-10-08
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK150493 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
7/17 | Suffolk Sheet 7 | 154 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/18 | Suffolk Sheet 1 | 1,699 square metres, or thereabouts, of private road situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Nichol | 30 | SK346465 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/18 | Suffolk Sheet 1 | 1,699 square metres, or thereabouts, of private road situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gerlinde Edmunds | 135 | SK346465 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/18 | Suffolk Sheet 1 | 1,699 square metres, or thereabouts, of private road situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK346465 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/18 | Suffolk Sheet 1 | 1,699 square metres, or thereabouts, of private road situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/18 | Suffolk Sheet 2 | 981 square metres, or thereabouts, of agricultural land situated to the south of High House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK363555 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/18 | Suffolk Sheet 2 | 981 square metres, or thereabouts, of agricultural land situated to the south of High House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK363555 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/18 | Suffolk Sheet 3 | 56 square metres, or thereabouts, of public adopted highway (School Road) and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Linda June Serpell | 461 | SK218542 | Freehold | subsoil fronting land to the south east of The Old School, School Road |  | Category 1 | N/A | Yes | RR-3186 | [6 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-01-09
3/18 | Suffolk Sheet 3 | 56 square metres, or thereabouts, of public adopted highway (School Road) and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Jean Frances Flick | 485 | SK187462 | Freehold | subsoil fronting land to the south east of The Old School, School Road |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-10-08
3/18 | Suffolk Sheet 3 | 56 square metres, or thereabouts, of public adopted highway (School Road) and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Peter Murray Mann | 508 | SK350290 | Freehold | subsoil fronting land to the south east of The Old School, School Road |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/18 | Suffolk Sheet 3 | 56 square metres, or thereabouts, of public adopted highway (School Road) and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
3/18 | Suffolk Sheet 3 | 56 square metres, or thereabouts, of public adopted highway (School Road) and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/18 | Suffolk Sheet 3 | 56 square metres, or thereabouts, of public adopted highway (School Road) and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
4/18 | Suffolk Sheet 4 | 3,601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Hazlewood Hall Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK323368 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/18 | Suffolk Sheet 4 | 3,601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Hazlewood Hall Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/18 | Suffolk Sheet 5 | 287 square metres, or thereabouts, of grass land and track situated to the east of Warren Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lindsay Peter Tomlinson | 335 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/18 | Suffolk Sheet 5 | 287 square metres, or thereabouts, of grass land and track situated to the east of Warren Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sarah Tomlinson | 491 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/18 | Suffolk Sheet 5 | 287 square metres, or thereabouts, of grass land and track situated to the east of Warren Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/18 | Suffolk Sheet 5 | 287 square metres, or thereabouts, of grass land and track situated to the east of Warren Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/19 | Suffolk Sheet 1 | 362 square metres, or thereabouts, of grassland and agricultural land situated to the south east of Hurts Hall, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Robert Roy Jonas Nichol | 439 | SK350196 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/19 | Suffolk Sheet 2 | 16,873 square metres, or thereabouts, of agricultural land situated to the south of Fristonmoor Barn, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | James Henry Rogers | 67 | SK290870 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/19 | Suffolk Sheet 2 | 16,873 square metres, or thereabouts, of agricultural land situated to the south of Fristonmoor Barn, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | James Henry Rogers | 67 | SK290870 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings in January. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner and their agent on 9th September 2025 to discuss Heads of Terms. Dalcour Maclaren provided further clarification on a number of queries on the 9th October 2025. The landowner's agent has stated it is unlikely that the landowner will engage further in relation to the Heads of Terms at this stage due to the restrictions the land would be subject to. Dalcour Maclaren will continue attempts to engage. 09.01.2026 – Dalcour Maclaren emailed the landowner’s agent on 18th November 2025 to follow up on previous correspondence and queries in relation to the project and to confirm if the landowner is willing to engage in relation the Heads of Terms. Dalcour Maclaren have not yet received a response. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/19 | Suffolk Sheet 3 | 8,691 square metres, or thereabouts, of agricultural land and electricity distribution poles and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/19 | Suffolk Sheet 3 | 8,691 square metres, or thereabouts, of agricultural land and electricity distribution poles and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/19 | Suffolk Sheet 4 | 5,557 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lindsay Peter Tomlinson | 335 | SK307035 | Freehold | subsoil fronting Gorse Hill, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lindsay Peter Tomlinson | 335 | SK307283 | Freehold | subsoil fronting land to the south of Hillbury, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sarah Tomlinson | 491 | SK307035 | Freehold | subsoil fronting Gorse Hill, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sarah Tomlinson | 491 | SK307283 | Freehold | subsoil fronting land to the south of Hillbury, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Pamela Tile | 1205 |  | Freehold | subsoil fronting Warren Cottage and Warren House, Leiston Road |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.205 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-10-08
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Aldeburgh Golf Club Limited | 1668 | SK329337 | Freehold | subsoil fronting land to the north of Warren Cottage, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-0093 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. Dalcour Maclaren are scheduling a meeting with the landowner and their agent in early December 2025. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 9th December 2025 after discussions with their agent regarding points outstanding from previous meetings. A meeting is being arranged with the landowner and their agent in January, a previous meeting scheduled for 9th December 2025 was rescheduled at the landowner’s request. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Aldeburgh Golf Club Limited | 1668 | SK330359 | Freehold | subsoil fronting South Warren Golf Course, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-0093 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. Dalcour Maclaren are scheduling a meeting with the landowner and their agent in early December 2025. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 9th December 2025 after discussions with their agent regarding points outstanding from previous meetings. A meeting is being arranged with the landowner and their agent in January, a previous meeting scheduled for 9th December 2025 was rescheduled at the landowner’s request. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-0656 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. | No Heads of Terms Required |  | 2026-01-09
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Virgin Media Limited | 3289 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | None Required |  | 09.01.2026 - Engagement is ongoing | No Heads of Terms Required |  | 2025-10-08
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Vodafone Limited | 3295 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | None Required |  | 09.01.2025 - Engagement is ongoing | No Heads of Terms Required |  | 2025-10-08
1/20 | Suffolk Sheet 1 | 94,770 square metres, or thereabouts, of agricultural land situated to the south east of Hurts Hall, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Caroline Nichol | 30 | SK346463 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/20 | Suffolk Sheet 1 | 94,770 square metres, or thereabouts, of agricultural land situated to the south east of Hurts Hall, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Gerlinde Edmunds | 135 | SK346463 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/20 | Suffolk Sheet 1 | 94,770 square metres, or thereabouts, of agricultural land situated to the south east of Hurts Hall, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Caroline Nichol | 30 | SK346463 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/20 | Suffolk Sheet 1 | 94,770 square metres, or thereabouts, of agricultural land situated to the south east of Hurts Hall, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Gerlinde Edmunds | 135 | SK346463 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/20 | Suffolk Sheet 2 | 246,834 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/20 | Suffolk Sheet 2 | 246,834 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/20 | Suffolk Sheet 2 | 246,834 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/20 | Suffolk Sheet 2 | 246,834 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/20 | Suffolk Sheet 2 | 246,834 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK312683 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/20 | Suffolk Sheet 2 | 246,834 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Suffolk County Council | 755 |  | Occupation | public footpath |  | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/20 | Suffolk Sheet 2 | 246,834 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/20 | Suffolk Sheet 2 | 246,834 square metres, or thereabouts, of agricultural land, drain, public footpaths (Friston Footpath, 017 and Knodishall Footpath, 006), electricity transmission pylons, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of High House Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
3/20 | Suffolk Sheet 3 | 7,515 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/20 | Suffolk Sheet 3 | 7,515 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/20 | Suffolk Sheet 3 | 7,515 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/20 | Suffolk Sheet 4 | 6,269 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK323368 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/20 | Suffolk Sheet 5 | 535 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lindsay Peter Tomlinson | 335 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/20 | Suffolk Sheet 5 | 535 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sarah Tomlinson | 491 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/21 | Suffolk Sheet 1 | 2,398 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Caroline Nichol | 30 | SK346463 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/21 | Suffolk Sheet 1 | 2,398 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Gerlinde Edmunds | 135 | SK346463 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/21 | Suffolk Sheet 1 | 2,398 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Caroline Nichol | 30 | SK346463 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/21 | Suffolk Sheet 1 | 2,398 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Gerlinde Edmunds | 135 | SK346463 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/21 | Suffolk Sheet 2 | 84 square metres, or thereabouts, of public adopted highway (Red Lane, Kiln Lane and Redbarn Lane) situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Blackheath Farms Limited | 425 | SK268898 | Freehold | subsoil fronting agricultural land situated to the north of 1 Friston Hall Cottages, Kiln Lane |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/21 | Suffolk Sheet 2 | 84 square metres, or thereabouts, of public adopted highway (Red Lane, Kiln Lane and Redbarn Lane) situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Richard Bruce Bloomfield | 630 | SK216487 | Freehold | subsoil fronting agricultural land situated to the north of 1 Friston Hall Cottages, Red Lane |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/21 | Suffolk Sheet 2 | 84 square metres, or thereabouts, of public adopted highway (Red Lane, Kiln Lane and Redbarn Lane) situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/21 | Suffolk Sheet 2 | 84 square metres, or thereabouts, of public adopted highway (Red Lane, Kiln Lane and Redbarn Lane) situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
3/21 | Suffolk Sheet 3 | 10,457 square metres, or thereabouts, of agricultural land situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/21 | Suffolk Sheet 3 | 10,457 square metres, or thereabouts, of agricultural land situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/21 | Suffolk Sheet 4 | 2,338 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK323368 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/21 | Suffolk Sheet 5 | 1,804 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lindsay Peter Tomlinson | 335 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/21 | Suffolk Sheet 5 | 1,804 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sarah Tomlinson | 491 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/21 | Suffolk Sheet 5 | 1,804 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
7/21 | Suffolk Sheet 7 | 719 square metres, or thereabouts, of railway, works and land situated to the east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Freehold |  | as reputed owner | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
7/21 | Suffolk Sheet 7 | 719 square metres, or thereabouts, of railway, works and land situated to the east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Occupation |  |  | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/22 | Suffolk Sheet 1 | 66,222 square metres, or thereabouts, of agricultural land situated to the north of Bloomfield`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Nichol | 30 | SK346463 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/22 | Suffolk Sheet 1 | 66,222 square metres, or thereabouts, of agricultural land situated to the north of Bloomfield`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gerlinde Edmunds | 135 | SK346463 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/22 | Suffolk Sheet 1 | 66,222 square metres, or thereabouts, of agricultural land situated to the north of Bloomfield`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Nichol | 30 | SK346463 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/22 | Suffolk Sheet 1 | 66,222 square metres, or thereabouts, of agricultural land situated to the north of Bloomfield`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gerlinde Edmunds | 135 | SK346463 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Blackheath Farms Limited | 425 | SK268898 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Richard William Mann | 64 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Peter Murray Mann | 508 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Christopher Mann | 2538 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Richard William Mann | 64 |  | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Blackheath Farms Limited | 425 | SK268898 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Peter Murray Mann | 508 |  | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Christopher Mann | 2538 |  | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/22 | Suffolk Sheet 2 | 1,980 square metres, or thereabouts, of public adopted highway (Redbarn Lane, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/22 | Suffolk Sheet 3 | 3,687 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/22 | Suffolk Sheet 3 | 3,687 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/22 | Suffolk Sheet 4 | 277 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK323368 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/22 | Suffolk Sheet 5 | 35,304 square metres, or thereabouts, of grassland and woodland situated to the north west of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lindsay Peter Tomlinson | 335 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/22 | Suffolk Sheet 5 | 35,304 square metres, or thereabouts, of grassland and woodland situated to the north west of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sarah Tomlinson | 491 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/22 | Suffolk Sheet 5 | 35,304 square metres, or thereabouts, of grassland and woodland situated to the north west of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/22 | Suffolk Sheet 5 | 35,304 square metres, or thereabouts, of grassland and woodland situated to the north west of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
7/22 | Suffolk Sheet 7 | 661 square metres, or thereabouts, of railway, works and land under bridge carrying public adopted highway (B1121, Main Road) situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold | bridge | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
7/22 | Suffolk Sheet 7 | 661 square metres, or thereabouts, of railway, works and land under bridge carrying public adopted highway (B1121, Main Road) situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Freehold |  | as reputed owner | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
7/22 | Suffolk Sheet 7 | 661 square metres, or thereabouts, of railway, works and land under bridge carrying public adopted highway (B1121, Main Road) situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation | bridge | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
7/22 | Suffolk Sheet 7 | 661 square metres, or thereabouts, of railway, works and land under bridge carrying public adopted highway (B1121, Main Road) situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Occupation |  | excluding bridge | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/23 | Suffolk Sheet 1 | 157,701 square metres, or thereabouts, of agricultural land situated to the east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/23 | Suffolk Sheet 1 | 157,701 square metres, or thereabouts, of agricultural land situated to the east of Wood Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/23 | Suffolk Sheet 2 | 11,189 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK268898 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/23 | Suffolk Sheet 2 | 11,189 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/23 | Suffolk Sheet 2 | 11,189 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/23 | Suffolk Sheet 2 | 11,189 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/23 | Suffolk Sheet 2 | 11,189 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/23 | Suffolk Sheet 2 | 11,189 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 |  | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/23 | Suffolk Sheet 2 | 11,189 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK268898 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/23 | Suffolk Sheet 2 | 11,189 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 |  | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/23 | Suffolk Sheet 2 | 11,189 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
2/23 | Suffolk Sheet 2 | 11,189 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
2/23 | Suffolk Sheet 2 | 11,189 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 |  | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/23 | Suffolk Sheet 2 | 11,189 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
3/23 | Suffolk Sheet 3 | 1,972 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Guy Hilliard Heald | 109 | SK194564,SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/23 | Suffolk Sheet 3 | 1,972 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lucinda Jane Fullerton Heald | 766 | SK194564,SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/23 | Suffolk Sheet 3 | 1,972 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Guy Hilliard Heald | 109 | SK194564,SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/23 | Suffolk Sheet 3 | 1,972 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lucinda Jane Fullerton Heald | 766 | SK194564,SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/23 | Suffolk Sheet 4 | 169 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK323368 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/23 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of grassland situated to the north of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lindsay Peter Tomlinson | 335 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/23 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of grassland situated to the north of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sarah Tomlinson | 491 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
7/23 | Suffolk Sheet 7 | 11 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Highways Limited | 374 | SK305809 | Freehold |  |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-01-09
7/23 | Suffolk Sheet 7 | 11 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
7/23 | Suffolk Sheet 7 | 11 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/24 | Suffolk Sheet 1 | 18,266 square metres, or thereabouts, of agricultural land, track and drain situated to the north east of Glebe Barn, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/24 | Suffolk Sheet 1 | 18,266 square metres, or thereabouts, of agricultural land, track and drain situated to the north east of Glebe Barn, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/24 | Suffolk Sheet 1 | 18,266 square metres, or thereabouts, of agricultural land, track and drain situated to the north east of Glebe Barn, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK268898 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 |  | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK268898 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 |  | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 |  | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/24 | Suffolk Sheet 2 | 36,186 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylons and overhead electricity transmission lines situated to the north east of 1 Friston Hall Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/24 | Suffolk Sheet 4 | 280 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
5/24 | Suffolk Sheet 5 | 207 square metres, or thereabouts, of grassland situated to the east of Foxborough House, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Lindsay Peter Tomlinson | 335 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/24 | Suffolk Sheet 5 | 207 square metres, or thereabouts, of grassland situated to the east of Foxborough House, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sarah Tomlinson | 491 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
7/24 | Suffolk Sheet 7 | 31 square metres, or thereabouts, of track situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 | SK351168 | Freehold |  |  | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Nathaniel Bacon | 3135 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
1/25 | Suffolk Sheet 1 | 1,295 square metres, or thereabouts, of agricultural land, drain, private road and overhead electricity distribution lines situated to the east of Glebe Barn, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK268898 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 |  | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK268898 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 |  | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 |  | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/25 | Suffolk Sheet 2 | 2,993 square metres, or thereabouts, of agricultural land and drain situated to the west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/25 | Suffolk Sheet 4 | 5,121 square metres, or thereabouts, of agricultural land situated to the north east of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
5/25 | Suffolk Sheet 5 | 795 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lindsay Peter Tomlinson | 335 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/25 | Suffolk Sheet 5 | 795 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sarah Tomlinson | 491 | SK307283 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3196 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent. On 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
7/25 | Suffolk Sheet 7 | 21 square metres, or thereabouts, of track situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 | SK348406 | Freehold |  |  | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/1 | Suffolk Sheet 1 | 3,628 square metres, or thereabouts, of public adopted highway (South Entrance, B1121) situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William Notcutt Estates Limited | 132 | SK336019 | Freehold | subsoil fronting land to the north of Four Feathers, Bigsbys Corner |  | Category 1 | William Mitcham, Wilson Wraight | Yes | REP1-291 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. 09.01.2026 – Dalcour Maclaren met with the landowner and their agent on 17th November 2026 to discuss the Heads of Terms. Discussions in relation to the proposed Heads of Terms have been positive and a further version of the Heads of Terms is being drafted. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/1 | Suffolk Sheet 1 | 3,628 square metres, or thereabouts, of public adopted highway (South Entrance, B1121) situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/1 | Suffolk Sheet 1 | 3,628 square metres, or thereabouts, of public adopted highway (South Entrance, B1121) situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/1 | Suffolk Sheet 1 | 3,628 square metres, or thereabouts, of public adopted highway (South Entrance, B1121) situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/1 | Suffolk Sheet 1 | 3,628 square metres, or thereabouts, of public adopted highway (South Entrance, B1121) situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cityfibre Holdings Limited | 3299 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Non Requested |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/26 | Suffolk Sheet 1 | 868 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/26 | Suffolk Sheet 1 | 868 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/1 | Suffolk Sheet 2 | 178 square metres, or thereabouts, of private road and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James John Skellorn | 476 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/1 | Suffolk Sheet 2 | 178 square metres, or thereabouts, of private road and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/1 | Suffolk Sheet 2 | 178 square metres, or thereabouts, of private road and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James John Skellorn | 476 | SK311155 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/1 | Suffolk Sheet 2 | 178 square metres, or thereabouts, of private road and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/1 | Suffolk Sheet 2 | 178 square metres, or thereabouts, of private road and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Nathaniel Bacon | 3135 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
3/1 | Suffolk Sheet 3 | 25,059 square metres, or thereabouts, of agricultural land, electricity pylons and overhead electricity transmission lines situated to the north of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/1 | Suffolk Sheet 3 | 25,059 square metres, or thereabouts, of agricultural land, electricity pylons and overhead electricity transmission lines situated to the north of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795 | Freehold | subsoil fronting land to the north of West Lodge, Aldeburgh Road |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lady Patricia Ann Hopkins | 533 | SK176970 | Freehold | subsoil fronting West Lodge, Aldeburgh Road |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-10-08
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sophie Clare Langmead | 2286 | SK418441 | Freehold | subsoil fronting land to the west of West Lodge, Aldeburgh Road |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 -This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-10-08
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Joel Hopkins | 2746 | SK176970 | Freehold | subsoil fronting West Lodge, Aldeburgh Road |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 -This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-10-08
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Abigail Hopkins | 2747 | SK176970 | Freehold | subsoil fronting West Lodge, Aldeburgh Road |  | Category 1 | N/A | Yes | RR-0010 | [6 empty] | Not SU |  |  | 25.03.2025 -This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-01-09
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sarah Younger | 2748 | SK176970 | Freehold | subsoil fronting West Lodge, Aldeburgh Road |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 -This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-10-08
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Virgin Media Limited | 3289 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | None Required |  | 09.01.2026 - Engagement is ongoing | No Heads of Terms Required |  | 2025-10-08
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | EXA Networks Limited | 3290 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | None Required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vodafone Limited | 3295 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | None Required |  | 09.01.2025 - Engagement is ongoing | No Heads of Terms Required |  | 2025-10-08
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/1 | Suffolk Sheet 5 | 14,640 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
6/1 | Suffolk Sheet 6 | 109,692 square metres, or thereabouts, of scrubland, drains, paths and track situated to the south of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Royal Society for the Protection of Birds | 618 | SK328388,SK354374 | Freehold |  |  | Category 1 | John Coates, Bidwells | Yes | RR-4651 REP1-158 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in September 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd October 2025 and issued revised Heads of Terms on 6th November 2025. Dalcour Maclaren received comments on the revised Heads of Terms on 11th November 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 15th December 2025. Dalcour Maclaren discussed the Heads of Terms with the landowner’s agent and issued a further revision of the terms on 8th January 2026. Dalcour Maclaren believe all points raised by the landowner have now been addressed within the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/1 | Suffolk Sheet 6 | 109,692 square metres, or thereabouts, of scrubland, drains, paths and track situated to the south of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Royal Society for the Protection of Birds | 618 | SK328388,SK354374 | Occupation |  |  | Category 1 | John Coates, Bidwells | Yes | RR-4651 REP1-158 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in September 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd October 2025 and issued revised Heads of Terms on 6th November 2025. Dalcour Maclaren received comments on the revised Heads of Terms on 11th November 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 15th December 2025. Dalcour Maclaren discussed the Heads of Terms with the landowner’s agent and issued a further revision of the terms on 8th January 2026. Dalcour Maclaren believe all points raised by the landowner have now been addressed within the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
7/1 | Suffolk Sheet 7 | 1,054 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Graham David Page | 44 | SK314433 | Freehold | subsoil fronting land to the south west of 9 Shotts Meadow, Main Road |  | Category 1 |  | No | [10 empty] | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-01-09
7/1 | Suffolk Sheet 7 | 1,054 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anthony Beverley Totton | 81 | SK314433 | Freehold | subsoil fronting land to the south west of 9 Shotts Meadow, Main Road |  | Category 1 |  | No | [10 empty] | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-01-09
7/1 | Suffolk Sheet 7 | 1,054 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Highways Limited | 374 | SK311340 | Freehold | subsoil fronting land to the south west of 9 Shotts Meadow, Main Road |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-01-09
7/1 | Suffolk Sheet 7 | 1,054 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Timothy Peter Singleton | 588 | SK314433 | Freehold | subsoil fronting land to the south west of 9 Shotts Meadow, Main Road |  | Category 1 |  | No | [10 empty] | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-01-09
7/1 | Suffolk Sheet 7 | 1,054 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK150493 | Freehold | subsoil fronting land to the south of 9 Shotts Meadow, Main Road |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
7/1 | Suffolk Sheet 7 | 1,054 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
7/1 | Suffolk Sheet 7 | 1,054 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Andrew Charles Clayton-Payne | 3446 | SK260246 | Freehold | subsoil fronting land to the west of Corner Cottages, Main Road |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-01-09
7/1 | Suffolk Sheet 7 | 1,054 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ghalia Nabil Clayton-Payne | 3447 | SK260246 | Freehold | subsoil fronting land to the west of Corner Cottages, Main Road |  | Category 1 |  | No | [10 empty] | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-01-09
7/1 | Suffolk Sheet 7 | 1,054 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Benhall Developments Limited | 3448 | SK379333 | Freehold | subsoil fronting land to the south of Corner Cottages, Main Road |  | Category 1 |  | No | [10 empty] | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-01-09
7/1 | Suffolk Sheet 7 | 1,054 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William Notcutt Estates Limited | 132 | SK336019 | Freehold |  |  | Category 1 | William Mitcham, Wilson Wraight | No | REP1-291 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. 09.01.2026 – Dalcour Maclaren met with the landowner and their agent on 17th November 2026 to discuss the Heads of Terms. Discussions in relation to the proposed Heads of Terms have been positive and a further version of the Heads of Terms is being drafted. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/2 | Suffolk Sheet 1 | 1,460 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William Notcutt Estates Limited | 132 | SK336019 | Occupation |  |  | Category 1 | William Mitcham, Wilson Wraight | No | REP1-291 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. 09.01.2026 – Dalcour Maclaren met with the landowner and their agent on 17th November 2026 to discuss the Heads of Terms. Discussions in relation to the proposed Heads of Terms have been positive and a further version of the Heads of Terms is being drafted. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/26 | Suffolk Sheet 2 | 30 square metres, or thereabouts, of drain situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Neil Copinger Mahony | 174 | SK232978 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/2 | Suffolk Sheet 2 | 164 square metres, or thereabouts, of public adopted highway (The Street, B1121) and overhead telecommunication lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Janet Francis Howard | 268 | SK97658 | Freehold | subsoil fronting Baldrys Cottage, The Street |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-10-08
2/2 | Suffolk Sheet 2 | 164 square metres, or thereabouts, of public adopted highway (The Street, B1121) and overhead telecommunication lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | James John Skellorn | 476 | SK311155 | Freehold | subsoil fronting land to the south of Hill Farm, The Street |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the Application under Change 5 which was accepted by the Examining Authority on 5th December 2025. A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/2 | Suffolk Sheet 2 | 164 square metres, or thereabouts, of public adopted highway (The Street, B1121) and overhead telecommunication lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 | SK258213 | Freehold | subsoil fronting land to the east of Baldrys Cottage, The Street |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/2 | Suffolk Sheet 2 | 164 square metres, or thereabouts, of public adopted highway (The Street, B1121) and overhead telecommunication lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Edward Howard | 719 | SK97658 | Freehold | subsoil fronting Baldrys Cottage, The Street |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-10-08
2/2 | Suffolk Sheet 2 | 164 square metres, or thereabouts, of public adopted highway (The Street, B1121) and overhead telecommunication lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/2 | Suffolk Sheet 2 | 164 square metres, or thereabouts, of public adopted highway (The Street, B1121) and overhead telecommunication lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Margaret Anne Bacon | 3146 | SK311155 | Freehold | subsoil fronting land to the south of Hill Farm, The Street |  | Category 1 | Oliver Holloway, Clarke & Simpson | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner's agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 to provide updates on the Heads of Terms. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 26th November 2025 and the proposals were discussed with the agent on 2nd December 2025. Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025 A meeting with the landowner and their agent is being arranged for early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/2 | Suffolk Sheet 2 | 164 square metres, or thereabouts, of public adopted highway (The Street, B1121) and overhead telecommunication lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/2 | Suffolk Sheet 2 | 164 square metres, or thereabouts, of public adopted highway (The Street, B1121) and overhead telecommunication lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/2 | Suffolk Sheet 3 | 42,340 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the south east of Peartree Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/2 | Suffolk Sheet 3 | 42,340 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the south east of Peartree Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/2 | Suffolk Sheet 4 | 164 square metres, or thereabouts, of woodland situated to the north of West Lodge, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/2 | Suffolk Sheet 5 | 901 square metres, or thereabouts, of agricultural land situated to the west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
1/3 | Suffolk Sheet 1 | 199 square metres, or thereabouts, of public adopted highway (South Entrance, B1121) situated to the north of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | William Notcutt Estates Limited | 132 | SK336019 | Freehold | subsoil fronting land to the north of Four Feathers, Bigsbys Corner |  | Category 1 | William Mitcham, Wilson Wraight | No | REP1-291 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. 09.01.2026 – Dalcour Maclaren met with the landowner and their agent on 17th November 2026 to discuss the Heads of Terms. Discussions in relation to the proposed Heads of Terms have been positive and a further version of the Heads of Terms is being drafted. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/3 | Suffolk Sheet 1 | 199 square metres, or thereabouts, of public adopted highway (South Entrance, B1121) situated to the north of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/3 | Suffolk Sheet 1 | 199 square metres, or thereabouts, of public adopted highway (South Entrance, B1121) situated to the north of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/3 | Suffolk Sheet 2 | 3,823 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Michael Neil Copinger Mahony | 174 | SK198325 | Freehold | subsoil fronting land to the south of Pond House, B1121 |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/3 | Suffolk Sheet 2 | 3,823 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 | SK258213 | Freehold | subsoil fronting land to the north west of Pond House, Saxmundham Road |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/3 | Suffolk Sheet 2 | 3,823 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/3 | Suffolk Sheet 2 | 3,823 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Georgeta Catargiu | 1270 | SK210743 | Freehold | subsoil fronting land to the south of Pond House, B1121 |  | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren emailed the landowner's agent on 6th September 2025 and 15th October 2025 requesting an update on the Heads of Terms issued in August. Dalcour Maclaren have scheduled a Teams meeting with the landowner’s agent in early December 2025 to discuss the Heads of Terms. Additionally, we understand there may be some changes to the ownership of this plot which will be discussed further. | Heads of Terms negotiations ongoing |  | 2025-11-18
2/3 | Suffolk Sheet 2 | 3,823 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Henry John Rix | 3202 | SK429737 | Freehold | subsoil fronting land to the south west of Pond House, Saxmundham Road |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-10-08
2/3 | Suffolk Sheet 2 | 3,823 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/3 | Suffolk Sheet 2 | 3,823 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/3 | Suffolk Sheet 2 | 3,823 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/3 | Suffolk Sheet 3 | 38 square metres, or thereabouts, of agricultural land situated to the north west of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/3 | Suffolk Sheet 4 | 744 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795 | Freehold | subsoil fronting land to the north of West Lodge, Snape Road |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/3 | Suffolk Sheet 4 | 744 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
4/3 | Suffolk Sheet 4 | 744 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
4/3 | Suffolk Sheet 4 | 744 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | EXA Networks Limited | 3290 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | None Required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | The Public Trustee | 825 | SK254614 | Freehold |  | as Personal Representative to the Estate of Terence James Martin Haworth | Category 1 | No Agent Known | Yes | RR-5322 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Personal Representative to the Estate of Terence James Martin Haworth | 831 | SK254614 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-5322 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. 09.01.2026 - Dalcour Maclaren continue to engage with the landowner’s agent, on 18th November 2025 Dalcour Maclaren requested a meeting to discuss the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/3 | Suffolk Sheet 5 | 318 square metres, or thereabouts, of agricultural land situated to the south west of Chapel Barn Lodges, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | J Haworth | 3136 |  | Occupation |  |  | Category 1 | No Agent Known | Yes | REP1-219 | [6 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2026-01-09
6/3 | Suffolk Sheet 6 | 38,818 square metres, or thereabouts, of public adopted highway (Thorpe Road), scrubland, path and shore situated to the south east of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | East Suffolk Council | 548 | SK292493 | Freehold |  |  | Category 1 | N/A | Yes | RR-1420 |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. A further version of the Heads of Terms was re-issued in August 2025. Dalcour Maclaren await substantive responses to the Heads of Terms from the landowners agent. 18.11.2025 - The landowner informed Dalcour Maclaren that they have instructed an agent on 9th October 2025. Dalcour Maclaren emailed the landowner’s agent on 13th and 24th October 2025 to request a meeting to progress negotiations. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 4th December 2025 to discuss the proposed Heads of Terms. Dalcour Maclaren emailed the agent on 22nd December 2025 to provide responses to the queries raised at the meeting and a further version of the Heads of Terms was provided for their consideration. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/3 | Suffolk Sheet 6 | 38,818 square metres, or thereabouts, of public adopted highway (Thorpe Road), scrubland, path and shore situated to the south east of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
6/3 | Suffolk Sheet 6 | 38,818 square metres, or thereabouts, of public adopted highway (Thorpe Road), scrubland, path and shore situated to the south east of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
6/3 | Suffolk Sheet 6 | 38,818 square metres, or thereabouts, of public adopted highway (Thorpe Road), scrubland, path and shore situated to the south east of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
6/3 | Suffolk Sheet 6 | 38,818 square metres, or thereabouts, of public adopted highway (Thorpe Road), scrubland, path and shore situated to the south east of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
6/3 | Suffolk Sheet 6 | 38,818 square metres, or thereabouts, of public adopted highway (Thorpe Road), scrubland, path and shore situated to the south east of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | William Notcutt Estates Limited | 132 | SK336019 | Freehold |  |  | Category 1 | William Mitcham, Wilson Wraight | No | REP1-291 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. 09.01.2026 – Dalcour Maclaren met with the landowner and their agent on 17th November 2026 to discuss the Heads of Terms. Discussions in relation to the proposed Heads of Terms have been positive and a further version of the Heads of Terms is being drafted. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/4 | Suffolk Sheet 1 | 1,388 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | William Notcutt Estates Limited | 132 | SK336019 | Occupation |  |  | Category 1 | William Mitcham, Wilson Wraight | No | REP1-291 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. 09.01.2026 – Dalcour Maclaren met with the landowner and their agent on 17th November 2026 to discuss the Heads of Terms. Discussions in relation to the proposed Heads of Terms have been positive and a further version of the Heads of Terms is being drafted. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/26 | Suffolk Sheet 4 | 46 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
2/4 | Suffolk Sheet 2 | 27 square metres, or thereabouts, of private accessway and scrubland situated to the west of Pond House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Georgeta Catargiu | 1270 |  | Freehold |  | As Personal Representative to the Estate of Martin Peter Handscombe | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren emailed the landowner's agent on 6th September 2025 and 15th October 2025 requesting an update on the Heads of Terms issued in August. Dalcour Maclaren have scheduled a Teams meeting with the landowner’s agent in early December 2025 to discuss the Heads of Terms. Additionally, we understand there may be some changes to the ownership of this plot which will be discussed further. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, which included a further revision of the Heads of Terms. Further feedback is anticipated. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/4 | Suffolk Sheet 2 | 27 square metres, or thereabouts, of private accessway and scrubland situated to the west of Pond House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/4 | Suffolk Sheet 3 | 258 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/4 | Suffolk Sheet 3 | 258 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/4 | Suffolk Sheet 3 | 258 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/4 | Suffolk Sheet 4 | 353 square metres, or thereabouts, of woodland situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | EXA Networks Limited | 3290 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | None Required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/4 | Suffolk Sheet 5 | 634 square metres, or thereabouts, of grassland situated to the south west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Aldeburgh Golf Club Limited | 1668 | SK329337 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-0093 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. Dalcour Maclaren are scheduling a meeting with the landowner and their agent in early December 2025. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 9th December 2025 after discussions with their agent regarding points outstanding from previous meetings. A meeting is being arranged with the landowner and their agent in January, a previous meeting scheduled for 9th December 2025 was rescheduled at the landowner’s request. | Heads of Terms negotiations ongoing |  | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Benhall Developments Limited | 3448 | SK379333 | Freehold |  |  | Category 1 |  | No | [10 empty] | 26.11.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network | No Heads of Terms Required |  | 2026-01-09
7/4 | Suffolk Sheet 7 | 2 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William Notcutt Estates Limited | 132 | SK336019 | Freehold |  |  | Category 1 | William Mitcham, Wilson Wraight | No | REP1-291 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. 09.01.2026 – Dalcour Maclaren met with the landowner and their agent on 17th November 2026 to discuss the Heads of Terms. Discussions in relation to the proposed Heads of Terms have been positive and a further version of the Heads of Terms is being drafted. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/5 | Suffolk Sheet 1 | 419 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William Notcutt Estates Limited | 132 | SK336019 | Occupation |  |  | Category 1 | William Mitcham, Wilson Wraight | No | REP1-291 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. 09.01.2026 – Dalcour Maclaren met with the landowner and their agent on 17th November 2026 to discuss the Heads of Terms. Discussions in relation to the proposed Heads of Terms have been positive and a further version of the Heads of Terms is being drafted. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/26 | Suffolk Sheet 5 | 308 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Royal Society for the Protection of Birds | 618 | SK328388 | Freehold |  |  | Category 1 | John Coates, Bidwells | Yes | RR-4651 REP1-158 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in September 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd October 2025 and issued revised Heads of Terms on 6th November 2025. Dalcour Maclaren received comments on the revised Heads of Terms on 11th November 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 15th December 2025. Dalcour Maclaren discussed the Heads of Terms with the landowner’s agent and issued a further revision of the terms on 8th January 2026. Dalcour Maclaren believe all points raised by the landowner have now been addressed within the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/26 | Suffolk Sheet 5 | 308 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Royal Society for the Protection of Birds | 618 | SK328388 | Occupation |  |  | Category 1 | John Coates, Bidwells | Yes | RR-4651 REP1-158 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in September 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd October 2025 and issued revised Heads of Terms on 6th November 2025. Dalcour Maclaren received comments on the revised Heads of Terms on 11th November 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 15th December 2025. Dalcour Maclaren discussed the Heads of Terms with the landowner’s agent and issued a further revision of the terms on 8th January 2026. Dalcour Maclaren believe all points raised by the landowner have now been addressed within the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/5 | Suffolk Sheet 2 | 1,639 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the west of Pond House, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK258213 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/5 | Suffolk Sheet 2 | 1,639 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the west of Pond House, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/5 | Suffolk Sheet 2 | 1,639 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the west of Pond House, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK258213 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/5 | Suffolk Sheet 2 | 1,639 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the west of Pond House, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/5 | Suffolk Sheet 3 | 2,976 square metres, or thereabouts, of private road, track, overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/5 | Suffolk Sheet 3 | 2,976 square metres, or thereabouts, of private road, track, overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/5 | Suffolk Sheet 3 | 2,976 square metres, or thereabouts, of private road, track, overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/5 | Suffolk Sheet 4 | 57,755 square metres, or thereabouts, of private road (unnamed), agricultural land and overhead electricity distribution lines situated to the south and west of Great Wood, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
5/5 | Suffolk Sheet 5 | 45,643 square metres, or thereabouts, of grassland, track, scrubland and public footpath (Aldeburgh Footpath, 016) situated to the west of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Aldeburgh Golf Club Limited | 1668 | SK329337 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-0093 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. Dalcour Maclaren are scheduling a meeting with the landowner and their agent in early December 2025. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 9th December 2025 after discussions with their agent regarding points outstanding from previous meetings. A meeting is being arranged with the landowner and their agent in January, a previous meeting scheduled for 9th December 2025 was rescheduled at the landowner’s request. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/5 | Suffolk Sheet 5 | 45,643 square metres, or thereabouts, of grassland, track, scrubland and public footpath (Aldeburgh Footpath, 016) situated to the west of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Suffolk County Council | 755 | SK254614,SK329337 | Occupation |  | in respect of public footpath | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
6/5 | Suffolk Sheet 6 | 18 square metres, or thereabouts, of public adopted highway (Thorpe Road) situated to the north east of Sluice Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | East Suffolk Council | 548 | SK292493 | Freehold |  |  | Category 1 | N/A | Yes | RR-1420 |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. A further version of the Heads of Terms was re-issued in August 2025. Dalcour Maclaren await substantive responses to the Heads of Terms from the landowners agent. 18.11.2025 - The landowner informed Dalcour Maclaren that they have instructed an agent on 9th October 2025. Dalcour Maclaren emailed the landowner’s agent on 13th and 24th October 2025 to request a meeting to progress negotiations. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 4th December 2025 to discuss the proposed Heads of Terms. Dalcour Maclaren emailed the agent on 22nd December 2025 to provide responses to the queries raised at the meeting and a further version of the Heads of Terms was provided for their consideration. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/5 | Suffolk Sheet 6 | 18 square metres, or thereabouts, of public adopted highway (Thorpe Road) situated to the north east of Sluice Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
6/5 | Suffolk Sheet 6 | 18 square metres, or thereabouts, of public adopted highway (Thorpe Road) situated to the north east of Sluice Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/6 | Suffolk Sheet 2 | 2,327 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK258213 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/6 | Suffolk Sheet 2 | 2,327 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/6 | Suffolk Sheet 2 | 2,327 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK258213 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/6 | Suffolk Sheet 2 | 2,327 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/6 | Suffolk Sheet 3 | 1,718 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/6 | Suffolk Sheet 4 | 4,715 square metres, or thereabouts, of agricultural land situated to the west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
5/6 | Suffolk Sheet 5 | 3,113 square metres, or thereabouts, of grassland, track and public footpath (Aldeburgh Footpath, 016) situated to the south west of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Aldeburgh Golf Club Limited | 1668 | SK329337 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-0093 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. Dalcour Maclaren are scheduling a meeting with the landowner and their agent in early December 2025. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 9th December 2025 after discussions with their agent regarding points outstanding from previous meetings. A meeting is being arranged with the landowner and their agent in January, a previous meeting scheduled for 9th December 2025 was rescheduled at the landowner’s request. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/6 | Suffolk Sheet 5 | 3,113 square metres, or thereabouts, of grassland, track and public footpath (Aldeburgh Footpath, 016) situated to the south west of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 | SK254614,SK329337 | Occupation |  | in respect of public footpath | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
6/6 | Suffolk Sheet 6 | 143 square metres, or thereabouts, of car park, scrubland and path situated to the east of Sluice Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | East Suffolk Council | 548 | SK292493 | Freehold |  |  | Category 1 | N/A | Yes | RR-1420 |  |  |  | Open Space |  |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. A further version of the Heads of Terms was re-issued in August 2025. Dalcour Maclaren await substantive responses to the Heads of Terms from the landowners agent. 18.11.2025 - The landowner informed Dalcour Maclaren that they have instructed an agent on 9th October 2025. Dalcour Maclaren emailed the landowner’s agent on 13th and 24th October 2025 to request a meeting to progress negotiations. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 4th December 2025 to discuss the proposed Heads of Terms. Dalcour Maclaren emailed the agent on 22nd December 2025 to provide responses to the queries raised at the meeting and a further version of the Heads of Terms was provided for their consideration. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/6 | Suffolk Sheet 6 | 143 square metres, or thereabouts, of car park, scrubland and path situated to the east of Sluice Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William Notcutt Estates Limited | 132 | SK336019 | Freehold |  |  | Category 1 | William Mitcham, Wilson Wraight | No | REP1-291 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. 09.01.2026 – Dalcour Maclaren met with the landowner and their agent on 17th November 2026 to discuss the Heads of Terms. Discussions in relation to the proposed Heads of Terms have been positive and a further version of the Heads of Terms is being drafted. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/7 | Suffolk Sheet 1 | 409 square metres, or thereabouts, of agricultural land situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | William Notcutt Estates Limited | 132 | SK336019 | Occupation |  |  | Category 1 | William Mitcham, Wilson Wraight | No | REP1-291 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. 09.01.2026 – Dalcour Maclaren met with the landowner and their agent on 17th November 2026 to discuss the Heads of Terms. Discussions in relation to the proposed Heads of Terms have been positive and a further version of the Heads of Terms is being drafted. | Heads of Terms negotiations ongoing |  | 2026-01-09
7/26 | Suffolk Sheet 7 | 944 square metres, or thereabouts, of railway, works and land situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Freehold |  | as reputed owner | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
7/26 | Suffolk Sheet 7 | 944 square metres, or thereabouts, of railway, works and land situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 |  | Occupation |  |  | Category 1 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025 – Format of Heads of Terms agreed with Network Rail in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/7 | Suffolk Sheet 2 | 14,306 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK258213 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/7 | Suffolk Sheet 2 | 14,306 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/7 | Suffolk Sheet 2 | 14,306 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Michael Guy Hilliard Heald | 109 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/7 | Suffolk Sheet 2 | 14,306 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ian Charles Rix | 692 | SK258213 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/7 | Suffolk Sheet 2 | 14,306 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Lucinda Jane Fullerton Heald | 766 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/7 | Suffolk Sheet 2 | 14,306 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/7 | Suffolk Sheet 3 | 72 square metres, or thereabouts, of agricultural land situated to the east of Swallow Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Blackheath Farms Limited | 425 | SK356298 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Blackheath Farms Limited | 425 | SK356298 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/7 | Suffolk Sheet 4 | 62,750 square metres, or thereabouts, of grassland, scrubland, track and overhead electricity distribution lines situated to the north east of Ash Covert, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/7 | Suffolk Sheet 5 | 443 square metres, or thereabouts, of grassland and track situated to the south of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Aldeburgh Golf Club Limited | 1668 | SK329337 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-0093 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. Dalcour Maclaren are scheduling a meeting with the landowner and their agent in early December 2025. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 9th December 2025 after discussions with their agent regarding points outstanding from previous meetings. A meeting is being arranged with the landowner and their agent in January, a previous meeting scheduled for 9th December 2025 was rescheduled at the landowner’s request. | Heads of Terms negotiations ongoing |  | 2026-01-09
6/7 | Suffolk Sheet 6 | 6,923 square metres, or thereabouts, of foreshore situated to the south east of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The King`s Most Excellent Majesty in Right of His Crown | 458 | SK298665 | Freehold |  |  | Category 1 | Peter Riches, Morley Riches | Yes | RR-5378 |  |  |  | Open Space | Crown Land |  | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this Landowner. It is believed that an agreement will be reached before the end of examination. 18.11.2025 - Dalcour Maclaren have been in correspondence with this landowner's agent throughout 2025 to progress Heads of Terms. Template s135 documents have been drafted by the Applicant and were issued to the landowner’s agent on 22nd October 2025. The most recent email exchange on 7th November 2025 provided Dalcour Maclaren's availability for a Teams meeting on 13th November 2025 or 18th November 2025 – a date has not yet been finalised but Dalcour Maclaren continue attempts to engage.In addition, the Applicant has had discussions with the Crown Estate directly throughout October and November 2025 in relation to land rights required across the Crown Estate’s property. 09.01.2026 – Dalcour Maclaren exchanged emails with the landowner’s agent on 5th December 2025 in relation to outstanding principles in the commercial agreements. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | William Notcutt Estates Limited | 132 | SK336019 | Freehold |  |  | Category 1 | William Mitcham, Wilson Wraight | No | REP1-291 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. 09.01.2026 – Dalcour Maclaren met with the landowner and their agent on 17th November 2026 to discuss the Heads of Terms. Discussions in relation to the proposed Heads of Terms have been positive and a further version of the Heads of Terms is being drafted. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/8 | Suffolk Sheet 1 | 1,269 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | William Notcutt Estates Limited | 132 | SK336019 | Occupation |  |  | Category 1 | William Mitcham, Wilson Wraight | No | REP1-291 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. 09.01.2026 – Dalcour Maclaren met with the landowner and their agent on 17th November 2026 to discuss the Heads of Terms. Discussions in relation to the proposed Heads of Terms have been positive and a further version of the Heads of Terms is being drafted. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/8 | Suffolk Sheet 2 | 19,637 square metres, or thereabouts, of agricultural land, scrubland, track and overhead electricity distribution lines situated to the north east of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Georgeta Catargiu | 1270 |  | Freehold |  | As Personal Representative to the Estate of Martin Peter Handscombe | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren emailed the landowner's agent on 6th September 2025 and 15th October 2025 requesting an update on the Heads of Terms issued in August. Dalcour Maclaren have scheduled a Teams meeting with the landowner’s agent in early December 2025 to discuss the Heads of Terms. Additionally, we understand there may be some changes to the ownership of this plot which will be discussed further. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, which included a further revision of the Heads of Terms. Further feedback is anticipated. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/8 | Suffolk Sheet 2 | 19,637 square metres, or thereabouts, of agricultural land, scrubland, track and overhead electricity distribution lines situated to the north east of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/8 | Suffolk Sheet 2 | 19,637 square metres, or thereabouts, of agricultural land, scrubland, track and overhead electricity distribution lines situated to the north east of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/8 | Suffolk Sheet 3 | 1,336 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/8 | Suffolk Sheet 4 | 2,209 square metres, or thereabouts, of private road (unnamed) and agricultural land situated to the east of Park Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
5/8 | Suffolk Sheet 5 | 3,918 square metres, or thereabouts, of grassland, scrubland and track situated to the south east of Chapel Barn Lodges, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Aldeburgh Golf Club Limited | 1668 | SK329337 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-0093 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. Dalcour Maclaren are scheduling a meeting with the landowner and their agent in early December 2025. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 9th December 2025 after discussions with their agent regarding points outstanding from previous meetings. A meeting is being arranged with the landowner and their agent in January, a previous meeting scheduled for 9th December 2025 was rescheduled at the landowner’s request. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | William Notcutt Estates Limited | 132 | SK336019 | Freehold |  |  | Category 1 | William Mitcham, Wilson Wraight | No | REP1-291 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. 09.01.2026 – Dalcour Maclaren met with the landowner and their agent on 17th November 2026 to discuss the Heads of Terms. Discussions in relation to the proposed Heads of Terms have been positive and a further version of the Heads of Terms is being drafted. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/9 | Suffolk Sheet 1 | 7,433 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 4. Compulsory Acquisition of Rights - Construction Compound | Class 4. Compulsory Acquisition of Rights - Construction Compound | William Notcutt Estates Limited | 132 | SK336019 | Occupation |  |  | Category 1 | William Mitcham, Wilson Wraight | No | REP1-291 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. 09.01.2026 – Dalcour Maclaren met with the landowner and their agent on 17th November 2026 to discuss the Heads of Terms. Discussions in relation to the proposed Heads of Terms have been positive and a further version of the Heads of Terms is being drafted. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/9 | Suffolk Sheet 2 | 1,938 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Georgeta Catargiu | 1270 |  | Freehold |  | As Personal Representative to the Estate of Martin Peter Handscombe | Category 1 | Sam Jennings, Strutt & Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren emailed the landowner's agent on 6th September 2025 and 15th October 2025 requesting an update on the Heads of Terms issued in August. Dalcour Maclaren have scheduled a Teams meeting with the landowner’s agent in early December 2025 to discuss the Heads of Terms. Additionally, we understand there may be some changes to the ownership of this plot which will be discussed further. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 12th December 2025 to follow up from the Teams meeting, which included a further revision of the Heads of Terms. Further feedback is anticipated. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/9 | Suffolk Sheet 2 | 1,938 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/9 | Suffolk Sheet 3 | 163 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/9 | Suffolk Sheet 4 | 4,223 square metres, or thereabouts, of agricultural land situated to the south west of Great Wood, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
5/9 | Suffolk Sheet 5 | 1,075 square metres, or thereabouts, of grassland situated to the south of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Aldeburgh Golf Club Limited | 1668 | SK329337 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-0093 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. Dalcour Maclaren are scheduling a meeting with the landowner and their agent in early December 2025. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 9th December 2025 after discussions with their agent regarding points outstanding from previous meetings. A meeting is being arranged with the landowner and their agent in January, a previous meeting scheduled for 9th December 2025 was rescheduled at the landowner’s request. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | William Notcutt Estates Limited | 132 | SK336019 | Freehold |  |  | Category 1 | William Mitcham, Wilson Wraight | No | REP1-291 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. 09.01.2026 – Dalcour Maclaren met with the landowner and their agent on 17th November 2026 to discuss the Heads of Terms. Discussions in relation to the proposed Heads of Terms have been positive and a further version of the Heads of Terms is being drafted. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/10 | Suffolk Sheet 1 | 607 square metres, or thereabouts, of agricultural land situated to the north east of Four Feathers, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | William Notcutt Estates Limited | 132 | SK336019 | Occupation |  |  | Category 1 | William Mitcham, Wilson Wraight | No | REP1-291 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. 09.01.2026 – Dalcour Maclaren met with the landowner and their agent on 17th November 2026 to discuss the Heads of Terms. Discussions in relation to the proposed Heads of Terms have been positive and a further version of the Heads of Terms is being drafted. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/10 | Suffolk Sheet 2 | 3,364 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK363555 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/10 | Suffolk Sheet 2 | 3,364 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK363555 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/10 | Suffolk Sheet 2 | 3,364 square metres, or thereabouts, of agricultural land, electricity distribution pole and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/10 | Suffolk Sheet 3 | 50 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/10 | Suffolk Sheet 3 | 50 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/10 | Suffolk Sheet 4 | 1,897 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
5/10 | Suffolk Sheet 5 | 823 square metres, or thereabouts, of grassland situated to the south east of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Aldeburgh Golf Club Limited | 1668 | SK329337 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-0093 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. Dalcour Maclaren are scheduling a meeting with the landowner and their agent in early December 2025. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 9th December 2025 after discussions with their agent regarding points outstanding from previous meetings. A meeting is being arranged with the landowner and their agent in January, a previous meeting scheduled for 9th December 2025 was rescheduled at the landowner’s request. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | William Notcutt Estates Limited | 132 | SK336019 | Freehold |  |  | Category 1 | William Mitcham, Wilson Wraight | No | REP1-291 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. 09.01.2026 – Dalcour Maclaren met with the landowner and their agent on 17th November 2026 to discuss the Heads of Terms. Discussions in relation to the proposed Heads of Terms have been positive and a further version of the Heads of Terms is being drafted. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Anglian Water Services Limited | 82 |  | Occupation | underground sewage pipeline |  | Category 1 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | William Notcutt Estates Limited | 132 | SK336019 | Occupation |  |  | Category 1 | William Mitcham, Wilson Wraight | No | REP1-291 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the Landowner on 2nd October 2025 to discuss Heads of Terms. Dalcour Maclaren met with the landowner's agent on 17th November 2025 to discuss Heads of Terms. 09.01.2026 – Dalcour Maclaren met with the landowner and their agent on 17th November 2026 to discuss the Heads of Terms. Discussions in relation to the proposed Heads of Terms have been positive and a further version of the Heads of Terms is being drafted. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/11 | Suffolk Sheet 1 | 267,322 square metres, or thereabouts, of agricultural land, woodland, grassland, tracks, drains and overhead electricity distribution lines situated to the north east of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/11 | Suffolk Sheet 2 | 1,479 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ian Charles Rix | 692 |  | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/11 | Suffolk Sheet 2 | 1,479 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/11 | Suffolk Sheet 3 | 2,246 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/11 | Suffolk Sheet 3 | 2,246 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 | SK257795 | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Richard William Mann | 64 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK257795 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Peter Murray Mann | 508 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Christopher Mann | 2538 | SK257795 | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/11 | Suffolk Sheet 4 | 34,035 square metres, or thereabouts, of agricultural land situated to the north east of Meadowpiece Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
5/11 | Suffolk Sheet 5 | 849 square metres, or thereabouts, of grassland situated to the south west of Dolce Domum, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Aldeburgh Golf Club Limited | 1668 | SK329337 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-0093 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. Dalcour Maclaren are scheduling a meeting with the landowner and their agent in early December 2025. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 9th December 2025 after discussions with their agent regarding points outstanding from previous meetings. A meeting is being arranged with the landowner and their agent in January, a previous meeting scheduled for 9th December 2025 was rescheduled at the landowner’s request. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/12 | Suffolk Sheet 1 | 2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK391706 | Freehold | subsoil fronting land to the south of Wardspring Farm, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/12 | Suffolk Sheet 1 | 2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold | subsoil fronting land to the south west of Wardspring Farm, Leiston Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/12 | Suffolk Sheet 1 | 2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK258213 | Freehold | subsoil fronting land to the north of Redhouse Farm, The Street |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/12 | Suffolk Sheet 1 | 2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/12 | Suffolk Sheet 1 | 2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kevin Russell Armstrong | 1365 | SK189163 | Freehold | subsoil fronting Wardspring Farm, Leiston Road |  | Category 1 | N/A | Yes | RR-2996 | [6 empty] | Not SU |  |  | 25.03.2025 -This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-01-09
1/12 | Suffolk Sheet 1 | 2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jennifer Louise Armstrong | 1366 | SK189163 | Freehold | subsoil fronting Wardspring Farm, Leiston Road |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 -This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-11-18
1/12 | Suffolk Sheet 1 | 2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Laurence Justin Dowley | 1367 | SK390468 | Freehold | subsoil fronting land to the east of The Manor House, Leiston Road |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 -This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-11-18
1/12 | Suffolk Sheet 1 | 2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Emma Louise Dowley | 1368 | SK390468 | Freehold | subsoil fronting land to the east of The Manor House, Leiston Road |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 -This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-11-18
1/12 | Suffolk Sheet 1 | 2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cripps Trust Corporation Limited | 1369 | SK390468 | Freehold | subsoil fronting land to the east of The Manor House, Leiston Road | as trustee to The Dowley Family Discretionary Settlement 2018 | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 -This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-11-18
1/12 | Suffolk Sheet 1 | 2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lily Armstrong | 2336 |  | Freehold | subsoil fronting Wardspring Farm, Leiston Road |  | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 -This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2025-11-18
1/12 | Suffolk Sheet 1 | 2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/12 | Suffolk Sheet 1 | 2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cadent Gas Limited | 1055 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-0656 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. | No Heads of Terms Required |  | 2026-01-09
1/12 | Suffolk Sheet 1 | 2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-11-18
1/12 | Suffolk Sheet 1 | 2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-11-18
2/12 | Suffolk Sheet 2 | 57 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK363555 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/12 | Suffolk Sheet 2 | 57 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/12 | Suffolk Sheet 2 | 57 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ian Charles Rix | 692 | SK363555 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/12 | Suffolk Sheet 2 | 57 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south east of Red House Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
3/12 | Suffolk Sheet 3 | 762 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/12 | Suffolk Sheet 3 | 762 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK356298 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Blackheath Farms Limited | 425 | SK356298 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | overhead telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
4/12 | Suffolk Sheet 4 | 11,176 square metres, or thereabouts, of grassland, track and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/12 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of scrubland situated to the south of Dulce Domum, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Aldeburgh Golf Club Limited | 1668 | SK329337 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-0093 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren have been in discussions with the landowner’s agent regarding the Heads of Terms. Dalcour Maclaren emailed the agent on 10th September 2025 and 15th October 2025 requesting a meeting to discuss Heads of Terms. Dalcour Maclaren are scheduling a meeting with the landowner and their agent in early December 2025. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 9th December 2025 after discussions with their agent regarding points outstanding from previous meetings. A meeting is being arranged with the landowner and their agent in January, a previous meeting scheduled for 9th December 2025 was rescheduled at the landowner’s request. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/27 | Suffolk Sheet 1 | 2,180 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/27 | Suffolk Sheet 1 | 2,180 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/27 | Suffolk Sheet 2 | 554 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Neil Copinger Mahony | 174 | SK232978 | Freehold | subsoil fronting land to the north west of The Lindens, Saxmundham Road |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/27 | Suffolk Sheet 2 | 554 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Blackheath Farms Limited | 425 | SK268898 | Freehold | subsoil fronting land to the south west of The Lindens, Saxmundham Road |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/27 | Suffolk Sheet 2 | 554 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/27 | Suffolk Sheet 2 | 554 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/27 | Suffolk Sheet 2 | 554 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/27 | Suffolk Sheet 2 | 554 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/27 | Suffolk Sheet 5 | 70 square metres, or thereabouts, of track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Elisabeth Lesley Lindores | 579 | SK266138 | Freehold |  | excluding mines and minerals | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Heads of Terms have been agreed, discussions are ongoing between legal advisors to draft and agree the Option Agreement. 09.01.2025 – The Option Agreement between The Applicant and the landowner legally completed on 11th December 2025. | Heads of Terms Agreed |  | 2026-01-09
5/27 | Suffolk Sheet 5 | 70 square metres, or thereabouts, of track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Anglian Water Services Limited | 82 |  | Occupation | underground sewage pipeline |  | Category 1 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
5/27 | Suffolk Sheet 5 | 70 square metres, or thereabouts, of track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Cadent Gas Limited | 1055 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-0656 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. | No Heads of Terms Required |  | 2026-01-09
7/27 | Suffolk Sheet 7 | 85 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Highways Limited | 374 | SK305809 | Freehold |  |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-01-09
7/27 | Suffolk Sheet 7 | 85 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
7/27 | Suffolk Sheet 7 | 85 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/28 | Suffolk Sheet 1 | 2,602 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Caroline Nichol | 30 | SK346463 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/28 | Suffolk Sheet 1 | 2,602 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Gerlinde Edmunds | 135 | SK346463 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/28 | Suffolk Sheet 1 | 2,602 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Caroline Nichol | 30 | SK346463 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/28 | Suffolk Sheet 1 | 2,602 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Gerlinde Edmunds | 135 | SK346463 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Neil Copinger Mahony | 174 | SK232978 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Openreach Limited | 3287 |  | Occupation | underground telecommunication lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Not required |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
5/28 | Suffolk Sheet 5 | 661 square metres, or thereabouts, of grassland and track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Royal Society for the Protection of Birds | 618 | SK328388 | Freehold |  |  | Category 1 | John Coates, Bidwells | Yes | RR-4651 REP1-158 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in September 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd October 2025 and issued revised Heads of Terms on 6th November 2025. Dalcour Maclaren received comments on the revised Heads of Terms on 11th November 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 15th December 2025. Dalcour Maclaren discussed the Heads of Terms with the landowner’s agent and issued a further revision of the terms on 8th January 2026. Dalcour Maclaren believe all points raised by the landowner have now been addressed within the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/28 | Suffolk Sheet 5 | 661 square metres, or thereabouts, of grassland and track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Royal Society for the Protection of Birds | 618 | SK328388 | Occupation |  |  | Category 1 | John Coates, Bidwells | Yes | RR-4651 REP1-158 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in September 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd October 2025 and issued revised Heads of Terms on 6th November 2025. Dalcour Maclaren received comments on the revised Heads of Terms on 11th November 2025. Engagement is ongoing. 09.01.2026 – Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 15th December 2025. Dalcour Maclaren discussed the Heads of Terms with the landowner’s agent and issued a further revision of the terms on 8th January 2026. Dalcour Maclaren believe all points raised by the landowner have now been addressed within the Heads of Terms. | Heads of Terms negotiations ongoing |  | 2026-01-09
7/28 | Suffolk Sheet 7 | 673 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Highways Limited | 374 | SK305809 | Freehold | subsoil fronting land to the south west of 9 Shotts Meadow, Main Road |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-01-09
7/28 | Suffolk Sheet 7 | 673 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
7/28 | Suffolk Sheet 7 | 673 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 | SK348406,SK351168 | Freehold | subsoil fronting land to the south west of 9 Shotts Meadow, Main Road |  | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
7/28 | Suffolk Sheet 7 | 673 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/29 | Suffolk Sheet 1 | 95,060 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/29 | Suffolk Sheet 1 | 95,060 square metres, or thereabouts, of agricultural land situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert Roy Jonas Nichol | 439 | SK345175 | Occupation |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-4545 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren had a meeting with the landowner’s agent on 30th September 2025 to discuss the impact of the proposals on the holding. Dalcour Maclaren issued revised Terms to the landowner’s agent on 29th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 – Dalcour Maclaren are continuing to engage positively with the landowner’s agent. Discussions are ongoing in relation to the commercial terms proposed. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/29 | Suffolk Sheet 2 | 2,149 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Michael Neil Copinger Mahony | 174 | SK232978 | Freehold |  |  | Category 1 | Oliver Holloway, Clarke & Simpson | Yes | RR-3700 REP1-226 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid propose to rely on existing land rights and have not issued voluntary terms for additional rights. | No Heads of Terms Required |  | 2026-01-09
5/29 | Suffolk Sheet 5 | 161 square metres, or thereabouts, of scrubland and track situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Elisabeth Lesley Lindores | 579 | SK266138 | Freehold |  | excluding mines and minerals | Category 1 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Heads of Terms have been agreed, discussions are ongoing between legal advisors to draft and agree the Option Agreement. 09.01.2025 – The Option Agreement between The Applicant and the landowner legally completed on 11th December 2025. | Heads of Terms Agreed |  | 2026-01-09
5/29 | Suffolk Sheet 5 | 161 square metres, or thereabouts, of scrubland and track situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Anglian Water Services Limited | 82 |  | Occupation | underground sewage pipeline |  | Category 1 | No Agent Known | Yes | RR-0334 REP1-170 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 09.01.2026 - Anglian Water has confirmed that it will not provide comments on the Statement of Common Ground before Deadline 3 but have confirmed recipt of undertaking to allow commencement of clash assessment to inform the Protective Provisions. A meeting is being set for February. | No Heads of Terms Required |  | 2026-01-09
5/29 | Suffolk Sheet 5 | 161 square metres, or thereabouts, of scrubland and track situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Cadent Gas Limited | 1055 |  | Occupation | underground gas mains |  | Category 1 | No Agent Known | Yes | RR-0656 | [6 empty] | SU kit and apparatus | Bespoke PPs |  | 09.01.2026 - Comments on the PPs were received from Cadent before the 25th December 2025. PPs are in internal review by the Applicant. | No Heads of Terms Required |  | 2026-01-09
7/29 | Suffolk Sheet 7 | 48 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Highways Limited | 374 | SK305809 | Freehold |  |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-01-09
7/29 | Suffolk Sheet 7 | 48 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
7/29 | Suffolk Sheet 7 | 48 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian Charles Rix | 692 | SK258213 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Ian Charles Rix | 692 | SK258213 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/100 | Suffolk Sheet 1 | 899 square metres, or thereabouts, of agricultural land situated to the south east of Trust Farm, Suffolk, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
1/49a | Suffolk Sheet 1 | 23,700 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK363555 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/49a | Suffolk Sheet 1 | 23,700 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Ian Charles Rix | 692 | SK363555 | Occupation |  |  | Category 1 | Simon Gilbey, Brown & Co | Yes | RR-5010 REP1-203 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren met with the landowner and their agent on 8th September 2025 to discuss Heads of Terms. Dalcour Maclaren held a Teams meeting with the landowner's agent on 13th October 2025 to discuss outstanding matters. Dalcour Maclaren met with the landowner and their agent on 3rd November 2025 to discuss Heads of Terms. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025, which incorporated the changes to the application under Change 5 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
1/49a | Suffolk Sheet 1 | 23,700 square metres, or thereabouts, of agricultural land, private road and overhead electricity distribution lines situated to the south of Trust Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
1/5a | Suffolk Sheet 1 | 0.88 square metres, or thereabouts, of hardstanding situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | J.T.Pegg & Sons Limited | 2460 | SK164618 | Freehold |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms negotiations ongoing |  | 2025-10-08
2/100 | Suffolk Sheet 2 | 54 square metres, or thereabouts, of public adopted highway (Grove Road), track and overhead electricity distribution lines situated to the east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Michael Guy Hilliard Heald | 109 | SK194564 | Freehold | subsoil fronting land to the west of Church Farm, Grove Road |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/100 | Suffolk Sheet 2 | 54 square metres, or thereabouts, of public adopted highway (Grove Road), track and overhead electricity distribution lines situated to the east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/100 | Suffolk Sheet 2 | 54 square metres, or thereabouts, of public adopted highway (Grove Road), track and overhead electricity distribution lines situated to the east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Lucinda Jane Fullerton Heald | 766 | SK194564 | Freehold | subsoil fronting land to the west of Church Farm, Grove Road |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/100 | Suffolk Sheet 2 | 54 square metres, or thereabouts, of public adopted highway (Grove Road), track and overhead electricity distribution lines situated to the east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Northumbrian Water Limited | 628 |  | Occupation | underground water pipeline |  | Category 1 |  | No | [10 empty] | 09.01.2026 - Draft PPs inssued on the 10th of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/100 | Suffolk Sheet 2 | 54 square metres, or thereabouts, of public adopted highway (Grove Road), track and overhead electricity distribution lines situated to the east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/100 | Suffolk Sheet 2 | 54 square metres, or thereabouts, of public adopted highway (Grove Road), track and overhead electricity distribution lines situated to the east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | overhead electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/100 | Suffolk Sheet 2 | 54 square metres, or thereabouts, of public adopted highway (Grove Road), track and overhead electricity distribution lines situated to the east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Essex and Suffolk Water Limited | 1034 |  | Occupation | underground water pipeline |  | Category 1 | No Agent Known | Yes | tbc | [6 empty] | SU kit and apparatus | Bespoke PPs |  | No Negotiations | No Heads of Terms Required |  | 2026-01-09
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Michael Guy Hilliard Heald | 109 | SK194564,SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Lucinda Jane Fullerton Heald | 766 | SK194564,SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Michael Guy Hilliard Heald | 109 | SK194564,SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/101 | Suffolk Sheet 2 | 2,904 square metres, or thereabouts, of agricultural land and track situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Lucinda Jane Fullerton Heald | 766 | SK194564,SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/102 | Suffolk Sheet 2 | 1,900 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/102 | Suffolk Sheet 2 | 1,900 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/103 | Suffolk Sheet 2 | 891 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/103 | Suffolk Sheet 2 | 891 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/104 | Suffolk Sheet 2 | 287 square metres, or thereabouts, of agricultural land and track situated to the east of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Peter Murray Mann | 508 | SK350290 | Freehold |  |  | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/104 | Suffolk Sheet 2 | 287 square metres, or thereabouts, of agricultural land and track situated to the east of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 |  | Occupation | underground electricity distribution lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/105 | Suffolk Sheet 2 | 373 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Guy Hilliard Heald | 109 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/105 | Suffolk Sheet 2 | 373 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lucinda Jane Fullerton Heald | 766 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/105 | Suffolk Sheet 2 | 373 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Guy Hilliard Heald | 109 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/105 | Suffolk Sheet 2 | 373 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lucinda Jane Fullerton Heald | 766 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/107 | Suffolk Sheet 2 | 1,424 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Guy Hilliard Heald | 109 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/107 | Suffolk Sheet 2 | 1,424 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lucinda Jane Fullerton Heald | 766 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/107 | Suffolk Sheet 2 | 1,424 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Guy Hilliard Heald | 109 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/107 | Suffolk Sheet 2 | 1,424 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lucinda Jane Fullerton Heald | 766 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/108 | Suffolk Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Guy Hilliard Heald | 109 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/108 | Suffolk Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lucinda Jane Fullerton Heald | 766 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/108 | Suffolk Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Michael Guy Hilliard Heald | 109 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/108 | Suffolk Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Lucinda Jane Fullerton Heald | 766 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/109 | Suffolk Sheet 2 | 15,635 square metres, or thereabouts, of agricultural land, track and public bridleway (Y354/002/0) situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/110 | Suffolk Sheet 2 | 5,598 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/110 | Suffolk Sheet 2 | 5,598 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/110 | Suffolk Sheet 2 | 5,598 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/110 | Suffolk Sheet 2 | 5,598 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/111 | Suffolk Sheet 2 | 782 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/111 | Suffolk Sheet 2 | 782 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/111 | Suffolk Sheet 2 | 782 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/111 | Suffolk Sheet 2 | 782 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/112 | Suffolk Sheet 2 | 1,445 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/112 | Suffolk Sheet 2 | 1,445 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564 | Freehold |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/112 | Suffolk Sheet 2 | 1,445 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Michael Guy Hilliard Heald | 109 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/112 | Suffolk Sheet 2 | 1,445 square metres, or thereabouts, of agricultural land situated to the east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Lucinda Jane Fullerton Heald | 766 | SK194564 | Occupation |  |  | Category 1 | Megan Pemberton, Landbridge | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. Populated Heads of Terms were issued on 28 February. The landowner and agent have not yet engaged in relation to these Heads of Terms. 08.10.2025 - Despite ongoing efforts by Dalcour Maclaren, including revised heads of terms being issued in August 2025 the landowners agent has stated they will not engage further in relation to the Heads of Terms. It is unlikely that agreement will be reached in relation to these plots before the end of Examination. 18.11.2025 - The landowner's agent has made Dalcour Maclaren aware that they do not have instruction to progress negotiations for the Heads of Terms. Dalcour Maclaren are continuing to make attempts to engage and have written to the landowner on 29th October 2025 with copies of the Heads of Terms for their consideration. 26.11.2025 – Heads of Terms have been issued for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner and their agent on 15th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Heads of Terms and have provided comments for review. Dalcour Maclaren are setting up a meeting with the landowner’s agent in early January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/20a | Suffolk Sheet 2 | 4 square metres, or thereabouts, of agricultural land situated to the north west of Laurel Covert, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | ScottishPower (UK) Renewables Limited | 2298 |  | Freehold |  | as reputed owner | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Blackheath Farms Limited | 425 | SK268898 | Freehold |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Suffolk County Council | 755 |  | Freehold |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Richard William Mann | 64 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Peter Murray Mann | 508 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Christopher Mann | 2538 |  | Leasehold |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | National Grid Electricity Transmission plc | 7 |  | Occupation | overhead electricity transmission lines |  | Category 1 | No Agent Known | No | [7 empty] | SU kit and apparatus | Agreed |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Richard William Mann | 64 |  | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Blackheath Farms Limited | 425 | SK268898 | Occupation |  |  | Category 1 | Gwyn Church, Brooks Leney | Yes | RR-0641 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Engagement since has been positive and, subject to engagement continuing, National Grid believe Heads of Terms will be agreed by the end of Examination. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner's agent on 3rd September 2025 to discuss the Heads of Terms. Revised Heads of Terms were issued to the Landowner's agent on 3rd October 2025. A Teams meeting was held on 27th October 2025 and engagement in ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner’s agent on 18th December 2025 which incorporated the changes to the application under Change 3 which was accepted by the Examining Authority on 5th December 2025. The landowner’s agent has acknowledged receipt of the revised Head of Terms. Dalcour Maclaren have arranged a meeting with the landowner’s agent on 4th February 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Peter Murray Mann | 508 |  | Occupation |  | trading as Mann Potatoes | Category 1 | Simon Gilbey, Brown & Co | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 28 February and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and or their agent. Following positive discussions, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren held a meeting with the landowner and their agent on the 8th September 2025. Dalcour Maclaren issued revised Heads of Terms and updated plan on 15th October 2025. Engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss overlapping project proposals and progressing Heads of Terms. Engagement with the landowner’s agent is ongoing. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Suffolk County Council | 755 |  | Occupation |  | as highway authority | Category 1 | N/A | Yes | RR-5209 | [6 empty] | Not SU | Draft under discussion |  | 25.03.2025 - Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. 09.01.2026 - PPs issued on the 22nd of December 2025 | No Heads of Terms Required |  | 2026-01-09
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Sovereign Turf Limited | 2533 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | West Country Trees Limited | 2534 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Christopher Mann | 2538 |  | Occupation |  | trading as Mann Potatoes | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | No Heads of Terms Required |  | 2025-10-08
2/22a | Suffolk Sheet 2 | 1,884 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Langley Dairies Limited | 2733 |  | Occupation |  |  | Category 1 | No Agent Known | No | [7 empty] | Not SU |  |  | No Negotiations | Heads of Terms to be agreed |  | 2025-10-08
2/78a | Suffolk Sheet 2 | 1,717 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ernest Alexander Tait Wright | 342 | SK151617 | Freehold |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren emailed the landowner's agent on 6th September 2025 and 15th October 2025 requesting an update on the Heads of Terms issued in August. Dalcour Maclaren have scheduled a Teams meeting with the landowner’s agent in early December 2025 to discuss the Heads of Terms. Additionally, we understand there may be some changes to the ownership of this plot which will be discussed further. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 10th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/78a | Suffolk Sheet 2 | 1,717 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ernest Alexander Tait Wright | 342 | SK151617 | Occupation |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren emailed the landowner's agent on 6th September 2025 and 15th October 2025 requesting an update on the Heads of Terms issued in August. Dalcour Maclaren have scheduled a Teams meeting with the landowner’s agent in early December 2025 to discuss the Heads of Terms. Additionally, we understand there may be some changes to the ownership of this plot which will be discussed further. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 10th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/78b | Suffolk Sheet 2 | 303 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ernest Alexander Tait Wright | 342 | SK151617 | Freehold |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren emailed the landowner's agent on 6th September 2025 and 15th October 2025 requesting an update on the Heads of Terms issued in August. Dalcour Maclaren have scheduled a Teams meeting with the landowner’s agent in early December 2025 to discuss the Heads of Terms. Additionally, we understand there may be some changes to the ownership of this plot which will be discussed further. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 10th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/78b | Suffolk Sheet 2 | 303 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Ernest Alexander Tait Wright | 342 | SK151617 | Occupation |  |  | Category 1 | Sam Jennings, Strutt and Parker | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. Following positive discussions with their agent, a further version of the Heads of Terms was re-issued in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren emailed the landowner's agent on 6th September 2025 and 15th October 2025 requesting an update on the Heads of Terms issued in August. Dalcour Maclaren have scheduled a Teams meeting with the landowner’s agent in early December 2025 to discuss the Heads of Terms. Additionally, we understand there may be some changes to the ownership of this plot which will be discussed further. 09.01.2026 – Dalcour Maclaren held a Teams meeting with the landowner’s agent on 3rd December 2025 to discuss the Heads of Terms and changes to landownership. Dalcour Maclaren emailed the landowner’s agent on 10th December 2025 to follow up from the Teams meeting, this included a further revision of the Heads of Terms. Further feedback is awaited. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/79a | Suffolk Sheet 2 | 122 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ScottishPower (UK) Renewables Limited | 2298 | SK432967 | Freehold |  |  | Category 1 | No Agent Known | Yes | RR-4903 REP2-046 | [6 empty] | SU and unknown operational | Draft under discussion |  | 09.01.2026 – The Applicant has engaged with Scottish Power Renewables Limited in anticipation of them confirming their land rights to allow the Applicant to commence negotiations for the Heads of Terms. | No Heads of Terms Required |  | 2026-01-09

## Category 1 Unknowns
South East Anglia Link: Detailed Land and Rights Negotiations Tracker - Category 1 interests
Notes:
1. All interests which are not already acquired at the point of submission should be entered in this tracker and marked as complete (column 'w') when agreement with known interests is reached
2. Any non-agreement is also counted as an objection by an affected person(s) for the purpose of this tracker
Book of Reference plot number | Plan reference number | Description of land and rights requested | Class of Rights and Type of Acquisition | PIL Name | PIL Reference/Land Referencing PartyID | Title Number(s) | Interest Type | Interest Description | Party Interest capacity | Category | Agent/ representative (if any) | Relevant Representation | When available Relevant representation reference number | When available Written representation reference number | Other document reference number | Applicant's response references | Special category (allotment, National Trust etc) (Select from drop down list) | Crown | Special category - other information including confirmation of status | Is the affected person a statutory undertaker and is the land operational? (Select from drop down list) | Protective provision status (Select from drop down list) | Side agreements (Select from drop down list) | Summary of Negotation Status | Heads of Terms (Select from drop down list) | Complete (Select from drop down list) | Last Updated [DD/MM/YYYY]
2/30 | Kent Sheet 2 | 6,023 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 650 | K56551 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-09
2/30 | Kent Sheet 2 | 6,023 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2594 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-10
3/30 | Kent Sheet 3 | 735 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south east of Sevenscore Crossing, Kent, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Unknown | 937 | TT104661 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-11
2/31 | Kent Sheet 2 | 290 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1543 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-12
2/31 | Kent Sheet 2 | 290 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2649 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-13
3/31 | Kent Sheet 3 | 5,195 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Oast, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 536 | K808893 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-14
2/32 | Kent Sheet 2 | 316 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 650 | K56551 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-15
2/32 | Kent Sheet 2 | 316 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2594 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-16
3/32 | Kent Sheet 3 | 818 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 536 | K808893 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-17
2/33 | Kent Sheet 2 | 152 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 1543 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-18
2/33 | Kent Sheet 2 | 152 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2649 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-19
3/33 | Kent Sheet 3 | 3,845 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south east of Sevenscore Crossing, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 937 | TT104661 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-20
2/34 | Kent Sheet 2 | 88 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1543 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-21
2/34 | Kent Sheet 2 | 88 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 2649 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-22
3/34 | Kent Sheet 3 | 371 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Oast, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 937 | TT104661 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-23
5/34 | Kent Sheet 5 | 1,129 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 329 | K527769 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-24
5/34 | Kent Sheet 5 | 1,129 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2635 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-25
2/35 | Kent Sheet 2 | 87 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1543 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-26
2/35 | Kent Sheet 2 | 87 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2649 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-27
3/35 | Kent Sheet 3 | 1,084 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 3437 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-28
2/36 | Kent Sheet 2 | 1,470 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 2593 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-29
3/36 | Kent Sheet 3 | 16 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Oast, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 937 | TT104661 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-30
2/37 | Kent Sheet 2 | 73 square metres, or thereabouts, of drain, track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1543 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-01-31
2/37 | Kent Sheet 2 | 73 square metres, or thereabouts, of drain, track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2649 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-01
3/37 | Kent Sheet 3 | 306 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Oast, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 937 | TT104661 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-02
5/37 | Kent Sheet 5 | 1,220 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1487 | K410629 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-03
5/37 | Kent Sheet 5 | 1,220 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3405 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-04
2/38 | Kent Sheet 2 | 60 square metres, or thereabouts, of drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1543 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-05
2/38 | Kent Sheet 2 | 60 square metres, or thereabouts, of drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2649 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-06
3/38 | Kent Sheet 3 | 28,006 square metres, or thereabouts, of agricultural land situated to the west of St. Augustine`s Golf Course, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 536 | K808893 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-07
5/38 | Kent Sheet 5 | 82 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1487 | K410629 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-08
5/38 | Kent Sheet 5 | 82 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3583 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-09
2/39 | Kent Sheet 2 | 27,228 square metres, or thereabouts, of grassland, drains and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2593 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-10
3/39 | Kent Sheet 3 | 5,301 square metres, or thereabouts, of agricultural land situated to the south east of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 536 | K808893 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-11
2/40 | Kent Sheet 2 | 2,835 square metres, or thereabouts, of grassland, track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2593 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-12
3/40 | Kent Sheet 3 | 6,289 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south east of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 937 | TT104661 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-13
5/40 | Kent Sheet 5 | 8,496 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 329 | K527769 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-14
5/40 | Kent Sheet 5 | 8,496 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3427 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-15
2/41 | Kent Sheet 2 | 5,222 square metres, or thereabouts, of agricultural land, electricity transmission pylon and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2593 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-16
3/41 | Kent Sheet 3 | 8,369 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 536 | K808893 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-17
5/41 | Kent Sheet 5 | 23 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 329 | K527769 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-18
5/41 | Kent Sheet 5 | 23 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3427 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-19
2/42 | Kent Sheet 2 | 5,319 square metres, or thereabouts, of grassland, track, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2593 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-20
3/42 | Kent Sheet 3 | 78 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 820 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-21
3/42 | Kent Sheet 3 | 78 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2625 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-22
5/42 | Kent Sheet 5 | 144 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 329 | K527769 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-23
5/42 | Kent Sheet 5 | 144 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3427 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-24
2/43 | Kent Sheet 2 | 14 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1543 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-25
2/43 | Kent Sheet 2 | 14 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3368 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-26
3/43 | Kent Sheet 3 | 248 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 820 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-27
3/43 | Kent Sheet 3 | 248 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2625 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-02-28
5/43 | Kent Sheet 5 | 4 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 329 | K527769 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-01
5/43 | Kent Sheet 5 | 4 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3427 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-02
2/44 | Kent Sheet 2 | 50 square metres, or thereabouts, of drain under bridge carrying track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 1543 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-03
2/44 | Kent Sheet 2 | 50 square metres, or thereabouts, of drain under bridge carrying track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 3550 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-04
5/44 | Kent Sheet 5 | 2 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 329 | K527769 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-05
5/44 | Kent Sheet 5 | 2 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3427 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-06
2/45 | Kent Sheet 2 | 968 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1543 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-07
2/45 | Kent Sheet 2 | 968 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3395 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-08
2/46 | Kent Sheet 2 | 26 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2253 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-09
2/46 | Kent Sheet 2 | 26 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2597 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-10
3/46 | Kent Sheet 3 | 2,942 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 536 | K808893 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-11
2/47 | Kent Sheet 2 | 50 square metres, or thereabouts, of drain under bridge carrying track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2253 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-12
3/47 | Kent Sheet 3 | 17,155 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 536 | K808893 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-13
2/48 | Kent Sheet 2 | 11 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2253 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-14
2/48 | Kent Sheet 2 | 11 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3286 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-15
3/48 | Kent Sheet 3 | 189 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 820 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-16
3/48 | Kent Sheet 3 | 189 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2625 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-17
2/49 | Kent Sheet 2 | 108 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1543 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-18
2/49 | Kent Sheet 2 | 108 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3368 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-19
2/50 | Kent Sheet 2 | 3,952 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 638 | K57595 | Freehold | mines and minerals below a depth of 500 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-20
2/51 | Kent Sheet 2 | 3,852 square metres, or thereabouts, of agricultural land, track, drain and overhead electricity distribution lines situated to the south and south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 638 | K57595 | Freehold | mines and minerals below a depth of 500 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-21
2/52 | Kent Sheet 2 | 3,701 square metres, or thereabouts, of grassland and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 638 | K57595 | Freehold | mines and minerals below a depth of 500 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-22
3/52 | Kent Sheet 3 | 1,079 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 820 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-23
3/52 | Kent Sheet 3 | 1,079 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2625 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-24
2/53 | Kent Sheet 2 | 12,613 square metres, or thereabouts, of grassland, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 638 | K57595 | Freehold | mines and minerals below a depth of 500 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-25
3/53 | Kent Sheet 3 | 16 square metres, or thereabouts, of track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1552 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-26
2/54 | Kent Sheet 2 | 40,844 square metres, or thereabouts, of grassland, track, drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 638 | K57595 | Freehold | mines and minerals below a depth of 500 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-27
2/55 | Kent Sheet 2 | 4,844 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 638 | K57595 | Freehold | mines and minerals below a depth of 500 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-28
2/56 | Kent Sheet 2 | 28 square metres, or thereabouts, of grassland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2253 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-29
2/57 | Kent Sheet 2 | 343 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2253 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-30
2/57 | Kent Sheet 2 | 343 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2639 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-03-31
2/58 | Kent Sheet 2 | 434 square metres, or thereabouts, of river, bed and bank (River Stour), overhead electricity distribution lines and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line: Open Space (River Stour Navigation) | Class 2. Compulsory Acquisition of Rights - Overhead Line: Open Space (River Stour Navigation) | Unknown | 3551 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-01
3/58 | Kent Sheet 3 | 337 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1549 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-02
3/58 | Kent Sheet 3 | 337 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 3424 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-03
2/59 | Kent Sheet 2 | 620 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights – Overhead Line | Class 2. Compulsory Acquisition of Rights – Overhead Line | Unknown | 638 | K57595 | Freehold | mines and minerals below a depth of 500 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-04
2/60 | Kent Sheet 2 | 8,781 square metres, or thereabouts, of grassland, drains, sluices, track, electricity transmission pylon and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 638 | K57595 | Freehold | mines and minerals below a depth of 500 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-05
2/61 | Kent Sheet 2 | 122 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2253 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-06
2/61 | Kent Sheet 2 | 122 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2639 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-07
2/62 | Kent Sheet 2 | 2,242 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3396 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-08
3/62 | Kent Sheet 3 | 162 square metres, or thereabouts, of drain situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1549 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-09
3/62 | Kent Sheet 3 | 162 square metres, or thereabouts, of drain situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 3424 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-10
2/63 | Kent Sheet 2 | 2,701 square metres, or thereabouts, of grassland, sluice, drain and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 638 | K57595 | Freehold | mines and minerals below a depth of 500 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-11
2/64 | Kent Sheet 2 | 1,771 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3282 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-12
2/64 | Kent Sheet 2 | 1,771 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3369 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-13
3/64 | Kent Sheet 3 | 996 square metres, or thereabouts, of drain situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1549 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-14
3/64 | Kent Sheet 3 | 996 square metres, or thereabouts, of drain situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 3424 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-15
2/66 | Kent Sheet 2 | 28 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2253 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-16
3/66 | Kent Sheet 3 | 22,214 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 3283 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-17
2/67 | Kent Sheet 2 | 76 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2253 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-18
2/68 | Kent Sheet 2 | 123 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2253 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-19
2/68 | Kent Sheet 2 | 123 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2639 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-20
3/74 | Kent Sheet 3 | 601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 536 | K808893 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-21
3/75 | Kent Sheet 3 | 6,551 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 536 | K808893 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-22
3/76 | Kent Sheet 3 | 3,447 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 536 | K808893 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-23
2/77 | Kent Sheet 2 | 288 square metres, or thereabouts, of track and scrubland situated to the south west of Boxlees Hill, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 1556 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-24
2/77 | Kent Sheet 2 | 288 square metres, or thereabouts, of track and scrubland situated to the south west of Boxlees Hill, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 3371 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-25
2/80 | Kent Sheet 2 | 113 square metres, or thereabouts, of scrubland and drain situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1556 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-26
2/80 | Kent Sheet 2 | 113 square metres, or thereabouts, of scrubland and drain situated to the west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3430 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-27
3/80 | Kent Sheet 3 | 1,637 square metres, or thereabouts, of scrubland, agricultural land and track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1552 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-28
3/80 | Kent Sheet 3 | 1,637 square metres, or thereabouts, of scrubland, agricultural land and track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3581 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-29
2/81 | Kent Sheet 2 | 921 square metres, or thereabouts, of agricultural land and private road situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1897 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-04-30
3/81 | Kent Sheet 3 | 430 square metres, or thereabouts, of scrubland situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3403 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-01
2/82 | Kent Sheet 2 | 569 square metres, or thereabouts, of scrubland situated to the north west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1555 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-02
2/82 | Kent Sheet 2 | 569 square metres, or thereabouts, of scrubland situated to the north west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2645 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-03
2/83 | Kent Sheet 2 | 2,958 square metres, or thereabouts, of public adopted highway (Marsh Farm Road), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1897 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-04
3/84 | Kent Sheet 3 | 19 square metres, or thereabouts, of scrubland situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3377 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-05
2/85 | Kent Sheet 2 | 7,282 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2599 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-06
3/85 | Kent Sheet 3 | 2,026 square metres, or thereabouts, of scrubland, electricity distribution pole and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 3406 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-07
2/86 | Kent Sheet 2 | 6,648 square metres, or thereabouts, of river, bed, bank (River Stour), drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3282 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-08
2/86 | Kent Sheet 2 | 6,648 square metres, or thereabouts, of river, bed, bank (River Stour), drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2659 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-09
3/86 | Kent Sheet 3 | 33 square metres, or thereabouts, of scrubland and track (Cottington Lane) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2251 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-10
3/86 | Kent Sheet 3 | 33 square metres, or thereabouts, of scrubland and track (Cottington Lane) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3435 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-11
2/87 | Kent Sheet 2 | 43 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1543 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-12
2/87 | Kent Sheet 2 | 43 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3370 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-13
3/87 | Kent Sheet 3 | 106 square metres, or thereabouts, of public adopted highway (Cottington Road) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1552 |  | Freehold | subsoil fronting land to the north of Club House, Cottington Road |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-14
3/87 | Kent Sheet 3 | 106 square metres, or thereabouts, of public adopted highway (Cottington Road) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2251 |  | Freehold | subsoil fronting railway land to the west of Great Cliffsend Farm House, Cottington Road |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-15
3/87 | Kent Sheet 3 | 106 square metres, or thereabouts, of public adopted highway (Cottington Road) situated to the west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3284 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-16
2/88 | Kent Sheet 2 | 2,138 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3393 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-17
3/88 | Kent Sheet 3 | 1,220 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3283 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-18
2/89 | Kent Sheet 2 | 29 square metres, or thereabouts, of sluice situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1543 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-19
2/89 | Kent Sheet 2 | 29 square metres, or thereabouts, of sluice situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2649 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-20
3/89 | Kent Sheet 3 | 404 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), path and footbridge over drain situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3283 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-21
2/90 | Kent Sheet 2 | 579 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-22
2/91 | Kent Sheet 2 | 114 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2599 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-23
3/91 | Kent Sheet 3 | 355 square metres, or thereabouts, of agricultural land situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 3263 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-24
3/91 | Kent Sheet 3 | 355 square metres, or thereabouts, of agricultural land situated to the north east of Cliffsend Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 3263 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-25
2/92 | Kent Sheet 2 | 109 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3282 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-26
2/92 | Kent Sheet 2 | 109 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2659 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-27
2/93 | Kent Sheet 2 | 138 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-28
2/94 | Kent Sheet 2 | 7,226 square metres, or thereabouts, of grassland, drain and track situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-29
2/95 | Kent Sheet 2 | 1,900 square metres, or thereabouts, of agricultural land, grassland and drain situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-30
3/95 | Kent Sheet 3 | 3 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 820 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-05-31
3/95 | Kent Sheet 3 | 3 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2625 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-01
2/96 | Kent Sheet 2 | 81 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-02
3/96 | Kent Sheet 3 | 105 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the north east of Cliffsend Farm Cottages, Kent, ﻿Class 9. ﻿Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | ﻿Class 9. ﻿Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3517 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-03
2/97 | Kent Sheet 2 | 20 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2231 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-04
2/97 | Kent Sheet 2 | 20 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2661 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-05
2/98 | Kent Sheet 2 | 889 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2599 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-06
3/98 | Kent Sheet 3 | 218 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-07
2/99 | Kent Sheet 2 | 1,113 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-08
3/99 | Kent Sheet 3 | 14,375 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course), drains, track and footbridges situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 3283 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-09
1/13 | Kent Sheet 1 | 455 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-10
2/13 | Kent Sheet 2 | 3,834 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-11
4/13 | Kent Sheet 4 | 1,156 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 3439 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-12
5/13 | Kent Sheet 5 | 92,778 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1487 | K410629 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-13
1/14 | Kent Sheet 1 | 8,833 square metres, or thereabouts, of grassland, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-14
2/14 | Kent Sheet 2 | 2,555 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-15
3/14 | Kent Sheet 3 | 429 square metres, or thereabouts, of agricultural land and private road (Jutes Lane), situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 2588 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-16
4/14 | Kent Sheet 4 | 18 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 2615 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-17
5/14 | Kent Sheet 5 | 4,138 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2662 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-18
1/15 | Kent Sheet 1 | 894 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-19
2/15 | Kent Sheet 2 | 204 square metres, or thereabouts, of drain, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1543 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-20
2/15 | Kent Sheet 2 | 204 square metres, or thereabouts, of drain, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2649 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-21
4/15 | Kent Sheet 4 | 166 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 2615 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-22
5/15 | Kent Sheet 5 | 94,015 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3382 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-23
1/16 | Kent Sheet 1 | 754 square metres, or thereabouts, of agricultural land, track and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-24
2/16 | Kent Sheet 2 | 75 square metres, or thereabouts, of drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2253 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-25
2/16 | Kent Sheet 2 | 75 square metres, or thereabouts, of drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2597 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-26
3/16 | Kent Sheet 3 | 247 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3434 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-27
4/16 | Kent Sheet 4 | 72 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 3384 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-28
5/16 | Kent Sheet 5 | 2,940 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2663 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-29
1/17 | Kent Sheet 1 | 1,129 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-06-30
2/17 | Kent Sheet 2 | 34 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2253 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-01
2/17 | Kent Sheet 2 | 34 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2597 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-02
3/17 | Kent Sheet 3 | 3,830 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-03
4/17 | Kent Sheet 4 | 719 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 2614 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-04
1/18 | Kent Sheet 1 | 8,477 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-05
2/18 | Kent Sheet 2 | 10 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 2253 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-06
2/18 | Kent Sheet 2 | 10 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 2597 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-07
3/18 | Kent Sheet 3 | 104 square metres, or thereabouts, of private road (Jutes Lane) situated to the south of Sevenscore Oast, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 3429 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-08
3/18 | Kent Sheet 3 | 104 square metres, or thereabouts, of private road (Jutes Lane) situated to the south of Sevenscore Oast, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 3552 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-09
4/18 | Kent Sheet 4 | 2,404 square metres, or thereabouts, of wooded area, private road, track and overhead electricity distribution lines situated to the south west of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2615 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-10
5/18 | Kent Sheet 5 | 25,439 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1487 | K410629 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-11
1/19 | Kent Sheet 1 | 8 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-12
2/19 | Kent Sheet 2 | 68 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1543 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-13
2/19 | Kent Sheet 2 | 68 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 2649 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-14
3/19 | Kent Sheet 3 | 123 square metres, or thereabouts, of public adopted highway (Richborough Way, A256) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 3434 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-15
1/20 | Kent Sheet 1 | 2,896 square metres, or thereabouts, of agricultural land, track and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-16
2/20 | Kent Sheet 2 | 44 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1543 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-17
2/20 | Kent Sheet 2 | 44 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2649 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-18
3/20 | Kent Sheet 3 | 75 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-19
1/21 | Kent Sheet 1 | 6,595 square metres, or thereabouts, of agricultural land, track, drain, electricity transmission pylon and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-20
2/21 | Kent Sheet 2 | 1,322 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-21
3/21 | Kent Sheet 3 | 55 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-22
1/22 | Kent Sheet 1 | 4,461 square metres, or thereabouts, of agricultural land situated to the north west of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-23
2/22 | Kent Sheet 2 | 190 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1543 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-24
2/22 | Kent Sheet 2 | 190 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2649 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-25
3/22 | Kent Sheet 3 | 258 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-26
4/22 | Kent Sheet 4 | 700 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 3585 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-27
2/23 | Kent Sheet 2 | 1,908 square metres, or thereabouts, of grassland and drain situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2593 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-28
3/23 | Kent Sheet 3 | 53 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 3431 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-29
4/23 | Kent Sheet 4 | 129 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3585 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-30
2/24 | Kent Sheet 2 | 711 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 650 | K56551 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-07-31
2/24 | Kent Sheet 2 | 711 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 2594 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-01
3/24 | Kent Sheet 3 | 25 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 3436 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-02
4/24 | Kent Sheet 4 | 18 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3585 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-03
2/25 | Kent Sheet 2 | 34 square metres, or thereabouts, of drain situated to the south east Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1543 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-04
2/25 | Kent Sheet 2 | 34 square metres, or thereabouts, of drain situated to the south east Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2649 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-05
3/25 | Kent Sheet 3 | 6 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Unknown | 3436 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-06
1/1 | Kent Sheet 1 | 114 square metres, or thereabouts, of public adopted highway (Richborough Road) and overhead telecommunication lines situated to the south east of Richborough Farm Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3203 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-07
2/1 | Kent Sheet 2 | 5,962 square metres, or thereabouts, of agricultural land and drain situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-08
3/1 | Kent Sheet 3 | 79 square metres, or thereabouts, of private road (Brook Lane) situated to the south west of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1559 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-09
3/1 | Kent Sheet 3 | 79 square metres, or thereabouts, of private road (Brook Lane) situated to the south west of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2641 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-10
4/1 | Kent Sheet 4 | 363 square metres, or thereabouts, of agricultural land situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-11
5/1 | Kent Sheet 5 | 11,625 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 329 | K527769 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-12
5/1 | Kent Sheet 5 | 11,625 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3580 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-13
1/2 | Kent Sheet 1 | 2,988 square metres, or thereabouts, of private road (Whitehouse Drove), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Castle Farm, Kent, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-14
1/2 | Kent Sheet 1 | 2,988 square metres, or thereabouts, of private road (Whitehouse Drove), overhead telecommunication lines and overhead electricity distribution lines situated to the north of Castle Farm, Kent, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Unknown | 2653 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-15
2/26 | Kent Sheet 2 | 582 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 1543 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-16
2/26 | Kent Sheet 2 | 582 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2649 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-17
2/2 | Kent Sheet 2 | 41,204 square metres, or thereabouts, of agricultural land, drain and sluice situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-18
3/2 | Kent Sheet 3 | 531 square metres, or thereabouts, of private road (Brook Lane), overhead telecommunication lines and overhead electricity distribution lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-19
4/2 | Kent Sheet 4 | 37 square metres, or thereabouts, of agricultural land situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 2580 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-20
1/3 | Kent Sheet 1 | 40 square metres, or thereabouts, of private road (Whitehouse Drove) situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-21
3/26 | Kent Sheet 3 | 255 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 3431 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-22
2/3 | Kent Sheet 2 | 430 square metres, or thereabouts, of agricultural land and track situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-23
3/3 | Kent Sheet 3 | 133 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North), Ramsgate, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2226 |  | Freehold | subsoil fronting land to the south west of Sevenscore Crossing, Ebbsfleet Lane North |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-24
3/3 | Kent Sheet 3 | 133 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North), Ramsgate, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2227 |  | Freehold | subsoil fronting land to the south of Sevenscore Crossing, Ebbsfleet Lane North |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-25
3/3 | Kent Sheet 3 | 133 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North), Ramsgate, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3432 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-26
4/3 | Kent Sheet 4 | 47 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 700 | K405978 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-27
4/3 | Kent Sheet 4 | 47 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2619 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-28
1/4 | Kent Sheet 1 | 227 square metres, or thereabouts, of private road (Whitehouse Drove) situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-29
4/26 | Kent Sheet 4 | 3,696 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane and Ramsgate Road), grassland, electricity distribution poles, overhead telecommunication lines and overhead electricity distribution lines situated to the east of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 3585 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-30
2/4 | Kent Sheet 2 | 12,153 square metres, or thereabouts, of agricultural land, drain and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-08-31
3/4 | Kent Sheet 3 | 16 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 857 | K377019,K377019 | Freehold | mines and minerals below a depth of 300 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-01
4/4 | Kent Sheet 4 | 151 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 820 |  | Freehold | subsoil fronting land to the north west of Ebbsfleet Farm Cottages, Ebbsfleet Lane |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-02
4/4 | Kent Sheet 4 | 151 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane) and overhead telecommunication lines situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3438 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-03
6/4 | Kent Sheet 6 | 508 square metres, or thereabouts, of scrubland, track, drain and overhead electricity distribution lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 833 | K563834 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-04
1/5 | Kent Sheet 1 | 4,684 square metres, or thereabouts, of private road (Whitehouse Drove), agricultural land, track, drain and overhead electricity distribution lines situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-05
5/26 | Kent Sheet 5 | 402,291 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 329 | K527769 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-06
5/26 | Kent Sheet 5 | 402,291 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2635 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-07
2/5 | Kent Sheet 2 | 1,651 square metres, or thereabouts, of agricultural land and track situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-08
3/5 | Kent Sheet 3 | 7 square metres, or thereabouts, of road verge and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 857 | K377019,K377019 | Freehold | mines and minerals below a depth of 300 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-09
4/5 | Kent Sheet 4 | 158 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 536 | K808893 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-10
1/6 | Kent Sheet 1 | 481 square metres, or thereabouts, of private road (Whitehouse Drove) and yard situated to the north east of Rubery Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-11
2/6 | Kent Sheet 2 | 130 square metres, or thereabouts, of drain and track situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-12
3/6 | Kent Sheet 3 | 711 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the south of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-13
4/6 | Kent Sheet 4 | 219 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 820 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-14
4/6 | Kent Sheet 4 | 219 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2625 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-15
6/6 | Kent Sheet 6 | 2,830 square metres, or thereabouts, of public adopted highway (Sandwich Bypass, A256), scrubland, track and overhead telecommunication lines situated to the south east of Richborough Castle, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 14 | K524623 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-16
1/7 | Kent Sheet 1 | 17,936 square metres, or thereabouts, of agricultural land, drain, electricity transmission pylon and overhead electricity distribution lines situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-17
2/7 | Kent Sheet 2 | 103 square metres, or thereabouts, of agricultural land and drain situated to the south west of Weatherlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-18
3/7 | Kent Sheet 3 | 1,266 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-19
1/8 | Kent Sheet 1 | 24,691 square metres, or thereabouts, of agricultural land, track, drain, sluice, electricity transmission pylons and overhead electricity transmission lines situated to the north of Drove Cottage, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-20
2/8 | Kent Sheet 2 | 3,170 square metres, or thereabouts, of agricultural land, drain and track situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-21
3/8 | Kent Sheet 3 | 8,662 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-22
1/9 | Kent Sheet 1 | 1,662 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-23
2/9 | Kent Sheet 2 | 7,279 square metres, or thereabouts, of agricultural land and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-24
3/9 | Kent Sheet 3 | 24,864 square metres, or thereabouts, of agricultural land and electricity distribution poles situated to the north of Great Oaks Small School, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-25
4/9 | Kent Sheet 4 | 88 square metres, or thereabouts, of drain situated to the east of Ebbsfleet Farm Cottages, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1549 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-26
4/9 | Kent Sheet 4 | 88 square metres, or thereabouts, of drain situated to the east of Ebbsfleet Farm Cottages, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 3428 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-27
5/9 | Kent Sheet 5 | 3,756 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1487 | K410629 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-28
5/9 | Kent Sheet 5 | 3,756 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3405 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-29
1/10 | Kent Sheet 1 | 69,078 square metres, or thereabouts, of agricultural land and drains situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-09-30
2/10 | Kent Sheet 2 | 70,932 square metres, or thereabouts, of agricultural land, track, drain, sluice and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-01
3/10 | Kent Sheet 3 | 1,308 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the south of Sevenscore Crossing, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 3433 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-02
5/10 | Kent Sheet 5 | 139,871 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1487 | K410629 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-03
5/10 | Kent Sheet 5 | 139,871 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3583 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-04
1/11 | Kent Sheet 1 | 994 square metres, or thereabouts, of agricultural land and drain situated to the north of Drove Cottage, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-05
2/11 | Kent Sheet 2 | 2,061 square metres, or thereabouts, of agricultural land and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-06
3/11 | Kent Sheet 3 | 8,046 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Farm Cottages, Kent, ﻿Class 1. Compulsory Acquisition of Land | ﻿Class 1. Compulsory Acquisition of Land | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-07
4/11 | Kent Sheet 4 | 219 square metres, or thereabouts, of agricultural land and track situated to the north of Ebbsfleet Farm Cottages, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2620 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-08
5/11 | Kent Sheet 5 | 9,032 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2592 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-09
1/12 | Kent Sheet 1 | 12 square metres, or thereabouts, of agricultural land situated to the north of Drove Cottage, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-10
2/12 | Kent Sheet 2 | 17,089 square metres, or thereabouts, of agricultural land, track, electricity transmission pylon, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-11
3/12 | Kent Sheet 3 | 127 square metres, or thereabouts, of agricultural land and private road (Jutes Lane) situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 3377 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-12
4/12 | Kent Sheet 4 | 533 square metres, or thereabouts, of scrubland and overhead telecommunication lines situated to the east of Ebbsfleet Farm Cottages, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 3359 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-13
5/12 | Kent Sheet 5 | 14,198 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2592 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-14
2/27 | Kent Sheet 2 | 11,594 square metres, or thereabouts, of agricultural land, drain, track, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 650 | K56551 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-15
2/27 | Kent Sheet 2 | 11,594 square metres, or thereabouts, of agricultural land, drain, track, overhead electricity transmission lines and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2594 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-16
3/27 | Kent Sheet 3 | 296 square metres, or thereabouts, of scrubland and hardstanding situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 937 | TT104661 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-17
3/27 | Kent Sheet 3 | 296 square metres, or thereabouts, of scrubland and hardstanding situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 3379 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-18
4/27 | Kent Sheet 4 | 1,256 square metres, or thereabouts, of track,drain and overhead electricity distribution lines situated to the east of Stonelees House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 3387 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-19
5/27 | Kent Sheet 5 | 150,347 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 329 | K527769 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-20
5/27 | Kent Sheet 5 | 150,347 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2635 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-21
2/28 | Kent Sheet 2 | 3,368 square metres, or thereabouts, of agricultural land, private track and overhead electricity transmission lines situated to the south of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 650 | K56551 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-22
2/28 | Kent Sheet 2 | 3,368 square metres, or thereabouts, of agricultural land, private track and overhead electricity transmission lines situated to the south of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2594 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-23
3/28 | Kent Sheet 3 | 234 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Crossing, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 536 | K808893 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-24
4/28 | Kent Sheet 4 | 408 square metres, or thereabouts, of public adopted highway (Ramsgate Road) situated to the north east of Ebbsfleet House, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 647 | K570106 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-25
5/28 | Kent Sheet 5 | 2,121 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 329 | K527769 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-26
5/28 | Kent Sheet 5 | 2,121 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2635 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-27
2/29 | Kent Sheet 2 | 3,227 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 650 | K56551 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-28
2/29 | Kent Sheet 2 | 3,227 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2594 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-29
3/29 | Kent Sheet 3 | 223 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane North) situated to the north of Ebbsfleet Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3436 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-30
5/29 | Kent Sheet 5 | 2,065 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 329 | K527769 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-10-31
5/29 | Kent Sheet 5 | 2,065 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2635 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-01
2/100 | Kent Sheet 2 | 962 square metres, or thereabouts, of drain, river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3282 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-02
2/100 | Kent Sheet 2 | 962 square metres, or thereabouts, of drain, river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2659 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-03
2/101 | Kent Sheet 2 | 24 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2231 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-04
2/101 | Kent Sheet 2 | 24 square metres, or thereabouts, of grassland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2661 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-05
2/102 | Kent Sheet 2 | 184 square metres, or thereabouts, of agricultural land and drain situated to the north west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2231 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-06
2/102 | Kent Sheet 2 | 184 square metres, or thereabouts, of agricultural land and drain situated to the north west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2661 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-07
2/103 | Kent Sheet 2 | 55 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3282 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-08
2/103 | Kent Sheet 2 | 55 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2659 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-09
2/104 | Kent Sheet 2 | 7,465 square metres, or thereabouts, of grassland, track and drain situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 3353 | K839921 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-10
2/105 | Kent Sheet 2 | 1,603 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2599 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-11
2/106 | Kent Sheet 2 | 1,539 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 3282 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-12
2/106 | Kent Sheet 2 | 1,539 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2659 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-13
2/110 | Kent Sheet 2 | 4,747 square metres, or thereabouts, of scrubland, railway (South Eastern & Chatham Railway), works and land situated to the north west of Weatherlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2246 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-14
2/114 | Kent Sheet 2 | 1,742 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land, drain and stream (Minster Stream) situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2246 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-15
2/115 | Kent Sheet 2 | 717 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land situated to the north east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2246 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-16
2/116 | Kent Sheet 2 | 580 square metres, or thereabouts, of railway (South Eastern & Chatham Railway), works and land situated to the north east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2246 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-17
2/117 | Kent Sheet 2 | 591 square metres, or thereabouts, of agricultural land and drain situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1544 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-18
2/117 | Kent Sheet 2 | 591 square metres, or thereabouts, of agricultural land and drain situated to the north east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3390 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-19
2/125 | Kent Sheet 2 | 1,595 square metres, or thereabouts, of scrubland situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 704 | K518470 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-20
2/125 | Kent Sheet 2 | 1,595 square metres, or thereabouts, of scrubland situated to the west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2606 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-21
2/126 | Kent Sheet 2 | 5,413 square metres, or thereabouts, of scrubland situated to the north west of Weatherlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 704 | K518470 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-22
2/126 | Kent Sheet 2 | 5,413 square metres, or thereabouts, of scrubland situated to the north west of Weatherlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2606 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-23
2/131 | Kent Sheet 2 | 1,038 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 1557 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-24
2/131 | Kent Sheet 2 | 1,038 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 2642 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-25
2/132 | Kent Sheet 2 | 3,789 square metres, or thereabouts, of agricultural land, stream (Minster Stream) and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 503 | K838442 | Freehold | mines and minerals below a depth of 300 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-26
2/132 | Kent Sheet 2 | 3,789 square metres, or thereabouts, of agricultural land, stream (Minster Stream) and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 3397 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-27
2/133 | Kent Sheet 2 | 110,734 square metres, or thereabouts, of agricultural land, drains and stream (Minster Stream) situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-28
2/135 | Kent Sheet 2 | 8 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 1545 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-29
2/136 | Kent Sheet 2 | 8 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 1545 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-11-30
2/138 | Kent Sheet 2 | 20 square metres, or thereabouts, of drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-01
2/139 | Kent Sheet 2 | 148 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-02
2/140 | Kent Sheet 2 | 50 square metres, or thereabouts, of agricultural land and drain situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | ﻿Class 7. ﻿Compulsory Acquisition of Rights - Mitigation | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-03
2/142 | Kent Sheet 2 | 8 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-04
2/144 | Kent Sheet 2 | 1,238 square metres, or thereabouts, of scrubland and drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Unknown | 2615 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-05
2/145 | Kent Sheet 2 | 585 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 2615 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-06
2/147 | Kent Sheet 2 | 35 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 3373 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-07
2/148 | Kent Sheet 2 | 34 square metres, or thereabouts, of scrubland situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 3373 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-08
2/149 | Kent Sheet 2 | 274 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Unknown | 3373 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-09
2/150 | Kent Sheet 2 | 128 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Unknown | 3373 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-10
2/152 | Kent Sheet 2 | 1,062 square metres, or thereabouts, of scrubland and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 3391 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-11
2/153 | Kent Sheet 2 | 98 square metres, or thereabouts, of woodland and track situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3372 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-12
2/154 | Kent Sheet 2 | 30 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 3362 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-13
2/155 | Kent Sheet 2 | 636 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Unknown | 3363 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-14
2/156 | Kent Sheet 2 | 558 square metres, or thereabouts, of agricultural land, drain and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights – Mitigation | Class 7. Compulsory Acquisition of Rights – Mitigation | Unknown | 3422 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-15
2/158 | Kent Sheet 2 | 3,374 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 3374 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-16
2/162 | Kent Sheet 2 | 1,158 square metres, or thereabouts, of agricultural land situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-17
2/163 | Kent Sheet 2 | 7,264 square metres, or thereabouts, of scrubland, drain and track situated to the north west of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-18
2/164 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-19
2/165 | Kent Sheet 2 | 24 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-20
2/167 | Kent Sheet 2 | 72 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-21
2/173 | Kent Sheet 2 | 1,075 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-22
2/174 | Kent Sheet 2 | 12,526 square metres, or thereabouts, of agricultural land, path and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-23
2/177 | Kent Sheet 2 | 35 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-24
2/178 | Kent Sheet 2 | 89 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-25
2/179 | Kent Sheet 2 | 10 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 7. Compulsory Acquisition of Rights - Mitigation | Class 7. Compulsory Acquisition of Rights - Mitigation | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-26
2/180 | Kent Sheet 2 | 161 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-27
2/181 | Kent Sheet 2 | 2,861 square metres, or thereabouts, of scrubland and private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 1559 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-28
2/181 | Kent Sheet 2 | 2,861 square metres, or thereabouts, of scrubland and private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 2641 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-29
2/182 | Kent Sheet 2 | 14 square metres, or thereabouts, of agricultural land situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-30
2/183 | Kent Sheet 2 | 14,820 square metres, or thereabouts, of agricultural land and path situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2026-12-31
2/184 | Kent Sheet 2 | 1,812 square metres, or thereabouts, of private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 1559 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-01
2/184 | Kent Sheet 2 | 1,812 square metres, or thereabouts, of private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 2641 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-02
2/185 | Kent Sheet 2 | 633 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 1630 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-03
2/185 | Kent Sheet 2 | 633 square metres, or thereabouts, of drain situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 2647 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-04
2/186 | Kent Sheet 2 | 113 square metres, or thereabouts, of private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1559 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-05
2/186 | Kent Sheet 2 | 113 square metres, or thereabouts, of private road (Brook Lane) situated to the north of Weatherlees Hill Wastewater Treatment Works, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2641 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-06
2/188 | Kent Sheet 2 | 105 square metres, or thereabouts, of scrubland situated to the west of Weatherlees Hill, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2246 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-07
3/100 | Kent Sheet 3 | 1,168 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1894 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-08
3/100 | Kent Sheet 3 | 1,168 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2230 |  | Freehold | subsoil fronting land to the south east of St Augustine`s Golf Course, Sandwich Road |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-09
3/101 | Kent Sheet 3 | 1,336 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 3285 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-10
3/102 | Kent Sheet 3 | 423 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 663 | K478221 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-11
3/103 | Kent Sheet 3 | 30 square metres, or thereabouts, of scrubland, path, pond and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 3285 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-12
3/104 | Kent Sheet 3 | 29 square metres, or thereabouts, of scrubland, path and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 663 | K478221 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-13
3/105 | Kent Sheet 3 | 112 square metres, or thereabouts, of scrubland, path, pond and cycle way situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 3285 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-14
3/106 | Kent Sheet 3 | 69 square metres, or thereabouts, of pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 3285 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-15
3/106 | Kent Sheet 3 | 69 square metres, or thereabouts, of pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2634 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-16
3/107 | Kent Sheet 3 | 7,957 square metres, or thereabouts, of scrubland, cycle way, path and pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 663 | K478221 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-17
3/109 | Kent Sheet 3 | 7,164 square metres, or thereabouts, of saltmarsh (Pegwell Nature Reserve) and pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 329 | K527769 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-18
3/109 | Kent Sheet 3 | 7,164 square metres, or thereabouts, of saltmarsh (Pegwell Nature Reserve) and pond situated to the south west of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2635 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-19
3/110 | Kent Sheet 3 | 3,495 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 329 | K527769 | Freehold | mines and minerals below a depth of 100 feet from the surface |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-20
3/110 | Kent Sheet 3 | 3,495 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2635 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-21
3/20a | Kent Sheet 3 | 318 square metres, or thereabouts, of agricultural land and track situated to the north west of Ebbsfleet Farm Cottages, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 537 | K755310 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-22
3/97a | Kent Sheet 3 | 83 square metres, or thereabouts, of public adopted highway (Sandwich Road) situated to the north east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3517 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-23
3/98a | Kent Sheet 3 | 34 square metres, or thereabouts, of public adopted highway (Ebbsfleet Lane), situated to the south west of Cottington Hill, Kent, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 3429 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-24
2/30 | Suffolk Sheet 2 | 88 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) situated to the west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 2285 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-25
5/30 | Suffolk Sheet 5 | 463 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3327 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-26
5/31 | Suffolk Sheet 5 | 3,703 square metres, or thereabouts, of grassland situated to the north east of Kings Legend, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 3328 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-27
2/32 | Suffolk Sheet 2 | 3,034 square metres, or thereabouts, of agricultural land situated to the north of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 2671 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-28
5/32 | Suffolk Sheet 5 | 4,080 square metres, or thereabouts, of scrubland and track situated to the north east of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1063 | SK266138 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-29
5/32 | Suffolk Sheet 5 | 4,080 square metres, or thereabouts, of scrubland and track situated to the north east of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 3410 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-30
2/33 | Suffolk Sheet 2 | 2,709 square metres, or thereabouts, of scrubland, electricity transmission pylons and overhead electricity transmission lines situated to the north of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2671 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-01-31
5/33 | Suffolk Sheet 5 | 1,379 square metres, or thereabouts, of grassland situated to the north east of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2698 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-01
2/34 | Suffolk Sheet 2 | 257 square metres, or thereabouts, of public footpath (Friston Footpath, 017) and overhead electricity transmission lines situated to the north of Friston House, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 3549 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-02
3/35 | Suffolk Sheet 3 | 31 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1905 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-03
3/37 | Suffolk Sheet 3 | 23 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the north of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1905 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-04
2/39 | Suffolk Sheet 2 | 14 square metres, or thereabouts, of agricultural land situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Unknown | 3414 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-05
2/39 | Suffolk Sheet 2 | 14 square metres, or thereabouts, of agricultural land situated to the south west of Peartree Farm, Suffolk, Class 5. Compulsory Acquisition of Rights – Access | Class 5. Compulsory Acquisition of Rights – Access | Unknown | 3351 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-06
2/40 | Suffolk Sheet 2 | 742 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead electricity transmission lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1896 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-07
2/41 | Suffolk Sheet 2 | 11,668 square metres, or thereabouts, of agricultural land and overhead electricity transmission lines situated to the north of Woodside Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-08
3/41 | Suffolk Sheet 3 | 549 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-09
3/42 | Suffolk Sheet 3 | 23 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-10
2/43 | Suffolk Sheet 2 | 1,316 square metres, or thereabouts, of public adopted highway (Grove Road), overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1896 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-11
2/44 | Suffolk Sheet 2 | 15,716 square metres, or thereabouts, of agricultural land, electricity distribution pole, overhead electricity distribution lines and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-12
2/49 | Suffolk Sheet 2 | 74 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1896 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-13
1/50 | Suffolk Sheet 1 | 232 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1895 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-14
2/50 | Suffolk Sheet 2 | 22 square metres, or thereabouts, of grassland situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-15
1/51 | Suffolk Sheet 1 | 147 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 1895 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-16
2/51 | Suffolk Sheet 2 | 13 square metres, or thereabouts, of grassland situated to the north of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-17
2/52 | Suffolk Sheet 2 | 142 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1896 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-18
1/53 | Suffolk Sheet 1 | 1,050 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1895 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-19
2/53 | Suffolk Sheet 2 | 37 square metres, or thereabouts, of public adopted highway (Grove Road) and overhead telecommunication lines situated to the north of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1896 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-20
2/54 | Suffolk Sheet 2 | 1,397 square metres, or thereabouts, of private road situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-21
3/54 | Suffolk Sheet 3 | 28,735 square metres, or thereabouts, of agricultural land, overhead telecommunication lines and overhead electricity distribution lines situated to the south west of Bull`s Hall, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 3547 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-22
3/58 | Suffolk Sheet 3 | 1,254 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1905 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-23
3/60 | Suffolk Sheet 3 | 571 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north of Park Farm Cottages, Suffolk, ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | ﻿Class 5. ﻿Compulsory Acquisition of Rights - Access | Unknown | 1905 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-24
3/61 | Suffolk Sheet 3 | 435 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1905 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-25
2/62 | Suffolk Sheet 2 | 89 square metres, or thereabouts, of public adopted highway (Grove Road) situated to the west of Grove Wood, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 1896 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-26
3/62 | Suffolk Sheet 3 | 604 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1905 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-27
3/64 | Suffolk Sheet 3 | 1,309 square metres, or thereabouts, of public adopted highway (Snape Road, B1069), overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Park Farm Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1905 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-02-28
2/67 | Suffolk Sheet 2 | 791 square metres, or thereabouts, of public footpath (Friston Footpath, 017) situated to the north of Friston House, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 3553 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-01
2/73 | Suffolk Sheet 2 | 2,664 square metres, or thereabouts, of scrubland and public footpath (Friston Footpath, 017) and overhead telecommunication lines situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights – Drainage | Class 6. Compulsory Acquisition of Rights – Drainage | Unknown | 3554 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-02
1/74 | Suffolk Sheet 1 | 7,300 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the east of The Manor House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1895 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-03
2/75 | Suffolk Sheet 2 | 15 square metres, or thereabouts, of agricultural land and public footpath (Friston Footpath, 017) situated to the north west of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 3555 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-04
2/77 | Suffolk Sheet 2 | 76 square metres, or thereabouts, of public adopted highway (Church Road) and track situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 3421 |  | Freehold | subsoil fronting land to the north west of St Mary`s Church, Church Lane |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-05
2/77 | Suffolk Sheet 2 | 76 square metres, or thereabouts, of public adopted highway (Church Road) and track situated to the north west of St Mary`s Church, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 3556 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-06
2/78 | Suffolk Sheet 2 | 1,606 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 3584 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-07
2/80 | Suffolk Sheet 2 | 2 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2577 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-08
2/80 | Suffolk Sheet 2 | 2 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2577 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-09
2/81 | Suffolk Sheet 2 | 24 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3313 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-10
2/82 | Suffolk Sheet 2 | 49 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 2577 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-11
2/82 | Suffolk Sheet 2 | 49 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 2577 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-12
2/83 | Suffolk Sheet 2 | 232 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 3313 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-13
1/88 | Suffolk Sheet 1 | 75 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1895 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-14
1/89 | Suffolk Sheet 1 | 472 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1895 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-15
2/90 | Suffolk Sheet 2 | 19 square metres, or thereabouts, of agricultural land and track situated to the east of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-16
1/91 | Suffolk Sheet 1 | 96 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Happy Days (Camp Site), Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1895 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-17
1/96 | Suffolk Sheet 1 | 44 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1895 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-18
1/97 | Suffolk Sheet 1 | 19 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 10. Land that is not subject to powers of acquisition nor temporary use | Class 10. Land that is not subject to powers of acquisition nor temporary use | Unknown | 1895 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-19
1/98 | Suffolk Sheet 1 | 323 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119) situated to the south east of Trust Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1895 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-20
3/13 | Suffolk Sheet 3 | 732 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-21
4/13 | Suffolk Sheet 4 | 2,559 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) and overhead telecommunication lines situated to the north east of Horseshoe Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1900 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-22
5/13 | Suffolk Sheet 5 | 3,233 square metres, or thereabouts, of scrubland situated to the south of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2695 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-23
3/14 | Suffolk Sheet 3 | 4,547 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-24
5/14 | Suffolk Sheet 5 | 1,047 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) and overhead telecommunication lines situated to the south east of High Warren, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1903 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-25
3/15 | Suffolk Sheet 3 | 277 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-26
5/15 | Suffolk Sheet 5 | 187 square metres, or thereabouts, of grassland situated to the south of Foxborough House, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 3344 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-27
3/16 | Suffolk Sheet 3 | 1,419 square metres, or thereabouts, of agricultural land, track, electricity pylon and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-28
5/16 | Suffolk Sheet 5 | 77 square metres, or thereabouts, of scrubland situated to the north of Warren Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2695 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-29
5/17 | Suffolk Sheet 5 | 401 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122) situated to the south of Hillbury, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 3417 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-30
1/18 | Suffolk Sheet 1 | 1,699 square metres, or thereabouts, of private road situated to the east of Hurts Hall, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2714 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-03-31
3/18 | Suffolk Sheet 3 | 56 square metres, or thereabouts, of public adopted highway (School Road) and overhead electricity transmission lines situated to the east of Swallow Cottage, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 2287 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-01
4/18 | Suffolk Sheet 4 | 3,601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Hazlewood Hall Farm, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3334 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-02
5/18 | Suffolk Sheet 5 | 287 square metres, or thereabouts, of grass land and track situated to the east of Warren Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 3318 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-03
1/19 | Suffolk Sheet 1 | 362 square metres, or thereabouts, of grassland and agricultural land situated to the south east of Hurts Hall, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 2710 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-04
3/19 | Suffolk Sheet 3 | 8,691 square metres, or thereabouts, of agricultural land and electricity distribution poles and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-05
5/19 | Suffolk Sheet 5 | 1,541 square metres, or thereabouts, of public adopted highway (Leiston Road, B1122), premises (Gorse Hill) and overhead telecommunication lines situated to the south of Hillbury, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3418 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-06
3/20 | Suffolk Sheet 3 | 7,515 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south of Swallow Cottages, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-07
4/20 | Suffolk Sheet 4 | 6,269 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 3315 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-08
5/20 | Suffolk Sheet 5 | 535 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3319 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-09
2/21 | Suffolk Sheet 2 | 84 square metres, or thereabouts, of public adopted highway (Red Lane, Kiln Lane and Redbarn Lane) situated to the north of 1 Friston Hall Cottages, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 2284 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-10
3/21 | Suffolk Sheet 3 | 10,457 square metres, or thereabouts, of agricultural land situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-11
4/21 | Suffolk Sheet 4 | 2,338 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3336 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-12
5/21 | Suffolk Sheet 5 | 1,804 square metres, or thereabouts, of grassland situated to the north east of Warren House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3320 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-13
7/21 | Suffolk Sheet 7 | 719 square metres, or thereabouts, of railway, works and land situated to the east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3451 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-14
3/22 | Suffolk Sheet 3 | 3,687 square metres, or thereabouts, of agricultural land and track situated to the south of Swallow Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-15
4/22 | Suffolk Sheet 4 | 277 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3316 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-16
5/22 | Suffolk Sheet 5 | 35,304 square metres, or thereabouts, of grassland and woodland situated to the north west of Brick Kiln Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 3321 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-17
7/22 | Suffolk Sheet 7 | 661 square metres, or thereabouts, of railway, works and land under bridge carrying public adopted highway (B1121, Main Road) situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3449 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-18
4/23 | Suffolk Sheet 4 | 169 square metres, or thereabouts, of agricultural land situated to the north of Miller`s Covert, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3317 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-19
5/23 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of grassland situated to the north of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3322 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-20
5/24 | Suffolk Sheet 5 | 207 square metres, or thereabouts, of grassland situated to the east of Foxborough House, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 3323 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-21
7/24 | Suffolk Sheet 7 | 31 square metres, or thereabouts, of track situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3548 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-22
5/25 | Suffolk Sheet 5 | 795 square metres, or thereabouts, of grassland and track situated to the east of Foxborough House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3324 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-23
7/25 | Suffolk Sheet 7 | 21 square metres, or thereabouts, of track situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3548 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-24
1/1 | Suffolk Sheet 1 | 3,628 square metres, or thereabouts, of public adopted highway (South Entrance, B1121) situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2167 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-25
3/1 | Suffolk Sheet 3 | 25,059 square metres, or thereabouts, of agricultural land, electricity pylons and overhead electricity transmission lines situated to the north of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-26
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1900 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-27
4/1 | Suffolk Sheet 4 | 1,589 square metres, or thereabouts, of public adopted highway (Aldeburgh Road, A1094) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2177 |  | Freehold | subsoil fronting private road to the east of West Lodge, Aldeburgh Road |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-28
7/1 | Suffolk Sheet 7 | 1,054 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the west of 1 Shotts Meadow, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3449 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-29
2/26 | Suffolk Sheet 2 | 30 square metres, or thereabouts, of drain situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3415 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-04-30
2/2 | Suffolk Sheet 2 | 164 square metres, or thereabouts, of public adopted highway (The Street, B1121) and overhead telecommunication lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2165 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-01
3/2 | Suffolk Sheet 3 | 42,340 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the south east of Peartree Farm, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-02
6/2 | Suffolk Sheet 6 | 1,436 square metres, or thereabouts, of drain and scrubland situated to the south west of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 1041 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-03
6/2 | Suffolk Sheet 6 | 1,436 square metres, or thereabouts, of drain and scrubland situated to the south west of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2716 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-04
1/3 | Suffolk Sheet 1 | 199 square metres, or thereabouts, of public adopted highway (South Entrance, B1121) situated to the north of Four Feathers, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 2167 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-05
2/3 | Suffolk Sheet 2 | 3,823 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity distribution lines situated to the west of Baldrys Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1899 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-06
3/3 | Suffolk Sheet 3 | 38 square metres, or thereabouts, of agricultural land situated to the north west of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-07
4/3 | Suffolk Sheet 4 | 744 square metres, or thereabouts, of public adopted highway (Snape Road, B1069) situated to the south west of Park Farm New Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1905 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-08
2/4 | Suffolk Sheet 2 | 27 square metres, or thereabouts, of private accessway and scrubland situated to the west of Pond House, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2686 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-09
3/4 | Suffolk Sheet 3 | 258 square metres, or thereabouts, of agricultural land and overhead telecommunication lines situated to the north of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-10
5/4 | Suffolk Sheet 5 | 634 square metres, or thereabouts, of grassland situated to the south west of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 2693 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-11
6/4 | Suffolk Sheet 6 | 28 square metres, or thereabouts, of scrubland situated to the west of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 791 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-12
6/4 | Suffolk Sheet 6 | 28 square metres, or thereabouts, of scrubland situated to the west of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2700 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-13
3/5 | Suffolk Sheet 3 | 2,976 square metres, or thereabouts, of private road, track, overhead electricity distribution lines and overhead telecommunication lines situated to the north east of Woodside Cottages, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-14
5/5 | Suffolk Sheet 5 | 45,643 square metres, or thereabouts, of grassland, track, scrubland and public footpath (Aldeburgh Footpath, 016) situated to the west of Dulce Domum, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2693 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-15
3/6 | Suffolk Sheet 3 | 1,718 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-16
5/6 | Suffolk Sheet 5 | 3,113 square metres, or thereabouts, of grassland, track and public footpath (Aldeburgh Footpath, 016) situated to the south west of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2693 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-17
6/6 | Suffolk Sheet 6 | 143 square metres, or thereabouts, of car park, scrubland and path situated to the east of Sluice Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3330 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-18
7/26 | Suffolk Sheet 7 | 944 square metres, or thereabouts, of railway, works and land situated to the south east of Stewart`s Covert, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3451 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-19
3/7 | Suffolk Sheet 3 | 72 square metres, or thereabouts, of agricultural land situated to the east of Swallow Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-20
5/7 | Suffolk Sheet 5 | 443 square metres, or thereabouts, of grassland and track situated to the south of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2693 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-21
6/7 | Suffolk Sheet 6 | 6,923 square metres, or thereabouts, of foreshore situated to the south east of Sluice Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 3331 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-22
2/8 | Suffolk Sheet 2 | 19,637 square metres, or thereabouts, of agricultural land, scrubland, track and overhead electricity distribution lines situated to the north east of Moor Farm, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 3305 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-23
3/8 | Suffolk Sheet 3 | 1,336 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-24
5/8 | Suffolk Sheet 5 | 3,918 square metres, or thereabouts, of grassland, scrubland and track situated to the south east of Chapel Barn Lodges, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2693 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-25
2/9 | Suffolk Sheet 2 | 1,938 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the north of Moor Farm, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3306 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-26
3/9 | Suffolk Sheet 3 | 163 square metres, or thereabouts, of agricultural land and track situated to the east of Swallow Cottage, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-27
5/9 | Suffolk Sheet 5 | 1,075 square metres, or thereabouts, of grassland situated to the south of Chapel Barn Lodges, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 3338 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-28
3/10 | Suffolk Sheet 3 | 50 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-29
5/10 | Suffolk Sheet 5 | 823 square metres, or thereabouts, of grassland situated to the south east of Chapel Barn Lodges, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3339 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-30
3/11 | Suffolk Sheet 3 | 2,246 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-05-31
5/11 | Suffolk Sheet 5 | 849 square metres, or thereabouts, of grassland situated to the south west of Dolce Domum, Suffolk, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Unknown | 3340 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-06-01
1/12 | Suffolk Sheet 1 | 2,453 square metres, or thereabouts, of public adopted highway (Leiston Road, B1119), drain and overhead telecommunication lines situated to the south of Happy Days (Camp Site), Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1895 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-06-02
3/12 | Suffolk Sheet 3 | 762 square metres, or thereabouts, of agricultural land, track and overhead electricity distribution lines situated to the east of Swallow Cottage, Suffolk, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-06-03
5/12 | Suffolk Sheet 5 | 356 square metres, or thereabouts, of scrubland situated to the south of Dulce Domum, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3341 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-06-04
2/27 | Suffolk Sheet 2 | 554 square metres, or thereabouts, of public adopted highway (Saxmundham Road, B1121) and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1899 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-06-05
5/27 | Suffolk Sheet 5 | 70 square metres, or thereabouts, of track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1063 | SK266138 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-06-06
5/27 | Suffolk Sheet 5 | 70 square metres, or thereabouts, of track situated to the north east of Kings Legend, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3325 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-06-07
2/28 | Suffolk Sheet 2 | 26,785 square metres, or thereabouts, of agricultural land, electricity transmission pylons and overhead electricity transmission lines situated to the north west of Friston House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 2671 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-06-08
7/28 | Suffolk Sheet 7 | 673 square metres, or thereabouts, of public adopted highway (B1121, Main Road) situated to the east of Mitford House, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3449 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-06-09
2/29 | Suffolk Sheet 2 | 2,149 square metres, or thereabouts, of agricultural land situated to the north west of Friston House, Suffolk, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | Unknown | 2671 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-06-10
5/29 | Suffolk Sheet 5 | 161 square metres, or thereabouts, of scrubland and track situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 1063 | SK266138 | Freehold | mines and minerals |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-06-11
5/29 | Suffolk Sheet 5 | 161 square metres, or thereabouts, of scrubland and track situated to the north east of Kings Legend, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3326 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-06-12
1/5a | Suffolk Sheet 1 | 0.88 square metres, or thereabouts, of hardstanding situated to the north of Four Feathers, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 3304 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-06-13
2/100 | Suffolk Sheet 2 | 54 square metres, or thereabouts, of public adopted highway (Grove Road), track and overhead electricity distribution lines situated to the east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 1896 |  | Freehold |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-06-14
2/102 | Suffolk Sheet 2 | 1,900 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-06-15
2/103 | Suffolk Sheet 2 | 891 square metres, or thereabouts, of agricultural land situated to the north east of St Mary`s Church, Suffolk, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-06-16
2/104 | Suffolk Sheet 2 | 287 square metres, or thereabouts, of agricultural land and track situated to the east of Woodside Cottages, Suffolk, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Unknown | 2590 | SK350290 | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-06-17
2/20a | Suffolk Sheet 2 | 4 square metres, or thereabouts, of agricultural land situated to the north west of Laurel Covert, Suffolk, Class 1. Compulsory Acquisition of Land | Class 1. Compulsory Acquisition of Land | Unknown | 3582 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-06-18
2/79a | Suffolk Sheet 2 | 122 square metres, or thereabouts, of agricultural land situated to the north of St Mary`s Church, Suffolk, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Unknown | 3584 |  | Occupation |  |  | Category 1 | [12 empty] | 09.01.2026 - The Applicant has appointed a professional land referencing company who have undertaken due diligence following the methodology to identify all those who have rights in land affected by the project. This included both desktop and contact land referencing and the use of Land Information Questionnaires and Site Notices |  |  | 2027-06-19

## Category 2
South East Anglia Link: Detailed Land and Rights Negotiations Tracker - Category 2 interests
Notes:
1. All interests which are not already acquired at the point of submission should be entered in this tracker and marked as complete (column 'w') when agreement with known interests is reached
2. Any non-agreement is also counted as an objection by an affected person(s) for the purpose of this tracker
Book of Reference plot number | Plan reference number | Description of land and rights requested | Class of Rights and Type of Acquisition | PIL Name | PIL Reference/Land Referencing PartyID | Title Number(s) | Interest Type | Interest Description | Party Interest capacity | Category | Agent/ representative (if any) | Relevant Representation | When available Relevant representation reference number | When available Written representation reference number | Other document reference number | Applicant's response references | Special category (allotment, National Trust etc) (Select from drop down list) | Crown | Special category - other information including confirmation of status | Is the affected person a statutory undertaker and is the land operational? (Select from drop down list) | Protective provision status (Select from drop down list) | Side agreements (Select from drop down list) | Summary of Negotiation Status | Heads of Terms (Select from drop down list) | Complete (Select from drop down list) | Last Updated [DD/MM/YYYY]
2/30 | Kent Sheet 2 | 6,023 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | K56551 | Easement Right or Privilege | Rights relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 24 July 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
2/30 | Kent Sheet 2 | 6,023 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | K56551 | Restrictive Covenant | Restrictive covenants relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 24 July 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
5/30 | Kent Sheet 5 | 10,705 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet Offshore Wind Limited | 76 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/30 | Kent Sheet 5 | 10,705 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm | as reputed owner | Category 2 | No Agent Known | Yes | RR-5371 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions not requested. Assumed to rely upon the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/30 | Kent Sheet 5 | 10,705 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K929702,TT46617 | Restrictive Covenant | Restrictive covenant not to interfere with or damage electricity cables or access to electricity cables as contained in a Deed dated 26 May 2016 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/30 | Kent Sheet 5 | 10,705 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 3579 |  | Easement Right or Privilege | foreshore rights |  | Category 2 |  | Yes | RR-5383 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
3/31 | Kent Sheet 3 | 5,195 square metres, or thereabouts, of agricultural land situated to the south of Sevenscore Oast, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Statkraft UK Limited | 2741 | K808893 | Easement Right or Privilege | Unilateral notice in respect of an Option to Lease pursuant to an Option Agreement dated 9 December 2022 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/31 | Kent Sheet 5 | 16,280 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet Offshore Wind Limited | 76 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/31 | Kent Sheet 5 | 16,280 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm | as reputed owner | Category 2 | No Agent Known | Yes | RR-5371 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions not requested. Assumed to rely upon the DCO provisions | No Heads of Terms Required |  | 2026-01-09
5/31 | Kent Sheet 5 | 16,280 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K929702,TT46617 | Restrictive Covenant | Restrictive covenant not to interfere with or damage electricity cables or access to electricity cables as contained in a Deed dated 26 May 2016 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/31 | Kent Sheet 5 | 16,280 square metres, or thereabouts, of sea (North Sea) situated to the east of Cliffsend Point, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 3579 |  | Easement Right or Privilege | foreshore rights |  | Category 2 |  | Yes | RR-5383 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
3/32 | Kent Sheet 3 | 818 square metres, or thereabouts, of agricultural land situated to the north of Ebbsfleet Farm Cottages, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Statkraft UK Limited | 2741 | K808893 | Easement Right or Privilege | Unilateral notice in respect of an Option to Lease pursuant to an Option Agreement dated 9 December 2022 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/32 | Kent Sheet 5 | 105,621 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet Offshore Wind Limited | 76 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/32 | Kent Sheet 5 | 105,621 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm | as reputed owner | Category 2 | No Agent Known | Yes | RR-5371 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions not requested. Assumed to rely upon the DCO provisions | No Heads of Terms Required |  | 2026-01-09
5/32 | Kent Sheet 5 | 105,621 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Nemo Link Limited | 771 | K929702,TT46617 | Restrictive Covenant | Restrictive covenant not to interfere with or damage electricity cables or access to electricity cables as contained in a Deed dated 26 May 2016 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/32 | Kent Sheet 5 | 105,621 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Marquess Conyngham | 3579 |  | Easement Right or Privilege | foreshore rights |  | Category 2 |  | Yes | RR-5383 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
5/33 | Kent Sheet 5 | 14,518 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet Offshore Wind Limited | 76 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/33 | Kent Sheet 5 | 14,518 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm | as reputed owner | Category 2 | No Agent Known | Yes | RR-5371 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions not requested. Assumed to rely upon the DCO provisions | No Heads of Terms Required |  | 2026-01-09
5/33 | Kent Sheet 5 | 14,518 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Nemo Link Limited | 771 | K929702,TT46617 | Restrictive Covenant | Restrictive covenant not to interfere with or damage electricity cables or access to electricity cables as contained in a Deed dated 26 May 2016 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/34 | Kent Sheet 5 | 1,129 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet Offshore Wind Limited | 76 | K527769 | Easement Right or Privilege | Right of entry and rights to maintain service media as contained in a Deed dated 27 April 2009 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/34 | Kent Sheet 5 | 1,129 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | K527769 | Easement Right or Privilege | Right of entry to maintain a sea wall and a right of way with or without vehicles and rights relating to service media as contained in a Transfer dated 4 December 1981 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/34 | Kent Sheet 5 | 1,129 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | K478221,K527769 | Restrictive Covenant | Restrictive covenants not to permit vehicular use of land over which there is a right of way, not to use land for any purpose other than those authorised by the National Trust Acts 1907 to 1971, not to interfere with a sea wall and other restrictive coven |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/34 | Kent Sheet 5 | 1,129 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet District Council | 167 | K527769 | Easement Right or Privilege | Right relating to tipping of refuse as contained in a Conveyance dated 25 September 1978 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/34 | Kent Sheet 5 | 1,129 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Right of entry and rights to use and maintain service media as contained in a Deed dated 27 May 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/34 | Kent Sheet 5 | 1,129 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of a lease for an easement as contained in an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/34 | Kent Sheet 5 | 1,129 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/34 | Kent Sheet 5 | 1,129 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Vattenfall Wind Power Limited | 841 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/34 | Kent Sheet 5 | 1,129 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Vattenfall Wind Power Limited | 841 | K527769 | Option to Purchase | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/34 | Kent Sheet 5 | 1,129 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Vattenfall Wind Power Limited | 841 | K527769 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate is to be registered without a written consent |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/34 | Kent Sheet 5 | 1,129 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | The Marquess Conyngham | 3579 |  | Easement Right or Privilege | foreshore rights |  | Category 2 |  | Yes | RR-5383 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
5/35 | Kent Sheet 5 | 191,908 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet Offshore Wind Limited | 76 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/35 | Kent Sheet 5 | 191,908 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet OFTO Limited | 152 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm | as reputed owner | Category 2 | No Agent Known | Yes | RR-5371 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions not requested. Assumed to rely upon the DCO provisions | No Heads of Terms Required |  | 2026-01-09
5/35 | Kent Sheet 5 | 191,908 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nemo Link Limited | 771 | K929702,TT46617 | Restrictive Covenant | Restrictive covenant not to interfere with or damage electricity cables or access to electricity cables as contained in a Deed dated 26 May 2016 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/35 | Kent Sheet 5 | 191,908 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | The Marquess Conyngham | 3579 |  | Easement Right or Privilege | foreshore rights |  | Category 2 |  | Yes | RR-5383 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
2/36 | Kent Sheet 2 | 1,470 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | South Eastern Power Networks plc | 263 | K458450 | Easement Right or Privilege | Rights relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 17 December 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/36 | Kent Sheet 2 | 1,470 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | South Eastern Power Networks plc | 263 | K458450 | Easement Right or Privilege | Rights relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 24 July 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/36 | Kent Sheet 2 | 1,470 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | South Eastern Power Networks plc | 263 | K458450 | Restrictive Covenant | Restrictive covenants relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 17 December 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/36 | Kent Sheet 2 | 1,470 square metres, or thereabouts, of agricultural land situated to the south east of Boxlees Hill, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | South Eastern Power Networks plc | 263 | K458450 | Restrictive Covenant | Restrictive covenants relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 24 July 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/36 | Kent Sheet 5 | 9,869 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet Offshore Wind Limited | 76 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/36 | Kent Sheet 5 | 9,869 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm | as reputed owner | Category 2 | No Agent Known | Yes | RR-5371 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions not requested. Assumed to rely upon the DCO provisions | No Heads of Terms Required |  | 2026-01-09
5/36 | Kent Sheet 5 | 9,869 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K929702,TT46617 | Restrictive Covenant | Restrictive covenant not to interfere with or damage electricity cables or access to electricity cables as contained in a Deed dated 26 May 2016 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/36 | Kent Sheet 5 | 9,869 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 3579 |  | Easement Right or Privilege | foreshore rights |  | Category 2 |  | Yes | RR-5383 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
5/37 | Kent Sheet 5 | 1,220 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet Offshore Wind Limited | 76 | K527769 | Easement Right or Privilege | Right of entry and rights to maintain service media as contained in a Deed dated 27 April 2009 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/37 | Kent Sheet 5 | 1,220 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K527769 | Easement Right or Privilege | Right of entry to maintain a sea wall and a right of way with or without vehicles and rights relating to service media as contained in a Transfer dated 4 December 1981 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/37 | Kent Sheet 5 | 1,220 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K478221,K527769 | Restrictive Covenant | Restrictive covenants not to permit vehicular use of land over which there is a right of way, not to use land for any purpose other than those authorised by the National Trust Acts 1907 to 1971, not to interfere with a sea wall and other restrictive coven |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/37 | Kent Sheet 5 | 1,220 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K527769 | Easement Right or Privilege | Right relating to tipping of refuse as contained in a Conveyance dated 25 September 1978 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/37 | Kent Sheet 5 | 1,220 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Right of entry and rights to use and maintain service media as contained in a Deed dated 27 May 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/37 | Kent Sheet 5 | 1,220 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of a lease for an easement as contained in an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/37 | Kent Sheet 5 | 1,220 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Option to Purchase | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/38 | Kent Sheet 3 | 28,006 square metres, or thereabouts, of agricultural land situated to the west of St. Augustine`s Golf Course, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Statkraft UK Limited | 2741 | K808893 | Easement Right or Privilege | Unilateral notice in respect of an Option to Lease pursuant to an Option Agreement dated 9 December 2022 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/38 | Kent Sheet 5 | 82 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Pfizer Limited | 131 | K410629 | Easement Right or Privilege | Rights relating to the construction, maintenance and use of a ground pipe for the conveyance of trade effluent as contained in a Conveyance dated 26 April 1954 for the benefit of unknown land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/38 | Kent Sheet 5 | 82 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mining Remediation Authority | 866 | K410629 | Easement Right or Privilege | Rights relating to the working, getting and carrying away by underground workings coal and other minerals as contained in a Conveyance dated 2 June 1958 |  | Category 2 |  | No | [13 empty] | 2026-01-09
5/38 | Kent Sheet 5 | 82 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mining Remediation Authority | 866 | K410629 | Restrictive Covenant | Restrictive covenant not to erect buildings as contained in a Conveyance dated 2 June 1958 |  | Category 2 |  | No | [13 empty] | 2026-01-09
2/39 | Kent Sheet 2 | 27,228 square metres, or thereabouts, of grassland, drains and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | South Eastern Power Networks plc | 263 | K458450 | Easement Right or Privilege | Rights relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 17 December 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/39 | Kent Sheet 2 | 27,228 square metres, or thereabouts, of grassland, drains and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | South Eastern Power Networks plc | 263 | K458450 | Easement Right or Privilege | Rights relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 24 July 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/39 | Kent Sheet 2 | 27,228 square metres, or thereabouts, of grassland, drains and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | South Eastern Power Networks plc | 263 | K458450 | Restrictive Covenant | Restrictive covenants relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 17 December 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/39 | Kent Sheet 2 | 27,228 square metres, or thereabouts, of grassland, drains and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | South Eastern Power Networks plc | 263 | K458450 | Restrictive Covenant | Restrictive covenants relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 24 July 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/39 | Kent Sheet 3 | 5,301 square metres, or thereabouts, of agricultural land situated to the south east of Sevenscore Farm Cottages, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Statkraft UK Limited | 2741 | K808893 | Easement Right or Privilege | Unilateral notice in respect of an Option to Lease pursuant to an Option Agreement dated 9 December 2022 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/39 | Kent Sheet 5 | 317,744 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet Offshore Wind Limited | 76 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/39 | Kent Sheet 5 | 317,744 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet OFTO Limited | 152 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm | as reputed owner | Category 2 | No Agent Known | Yes | RR-5371 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions not requested. Assumed to rely upon the DCO provisions | No Heads of Terms Required |  | 2026-01-09
5/39 | Kent Sheet 5 | 317,744 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K929702,TT46617 | Restrictive Covenant | Restrictive covenant not to interfere with or damage electricity cables or access to electricity cables as contained in a Deed dated 26 May 2016 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/39 | Kent Sheet 5 | 317,744 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | The Marquess Conyngham | 3579 |  | Easement Right or Privilege | foreshore rights |  | Category 2 |  | Yes | RR-5383 | [9 empty] | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowner’s appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Landowner has passed away; applicant will continue to progress voluntary agreement with the estate representatives. 18.11.2025 - It is understood that the landowner's agent awaits further instruction on this matter. Dalcour Maclaren contacted the landowner's agent on 7th November 2025 to request an update in relation to the Heads of Terms. 09.01.2026 – On 2nd December 2025, Dalcour Maclaren met with the landowner’s agent who confirmed that there were no objections to the Heads of Terms in principle. Heads of Terms were re-issued to the agent for review on 3rd December 2025. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek an update on the Heads of Terms. | Heads of Terms Negotations ongoing |  | 2026-01-09
2/40 | Kent Sheet 2 | 2,835 square metres, or thereabouts, of grassland, track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | South Eastern Power Networks plc | 263 | K458450 | Easement Right or Privilege | Rights relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 17 December 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/40 | Kent Sheet 2 | 2,835 square metres, or thereabouts, of grassland, track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | South Eastern Power Networks plc | 263 | K458450 | Easement Right or Privilege | Rights relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 24 July 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/40 | Kent Sheet 2 | 2,835 square metres, or thereabouts, of grassland, track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | South Eastern Power Networks plc | 263 | K458450 | Restrictive Covenant | Restrictive covenants relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 17 December 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/40 | Kent Sheet 2 | 2,835 square metres, or thereabouts, of grassland, track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | South Eastern Power Networks plc | 263 | K458450 | Restrictive Covenant | Restrictive covenants relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 24 July 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/40 | Kent Sheet 5 | 8,496 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet Offshore Wind Limited | 76 | K527769 | Easement Right or Privilege | Right of entry and rights to maintain service media as contained in a Deed dated 27 April 2009 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/40 | Kent Sheet 5 | 8,496 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K527769 | Easement Right or Privilege | Right of entry to maintain a sea wall and a right of way with or without vehicles and rights relating to service media as contained in a Transfer dated 4 December 1981 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/40 | Kent Sheet 5 | 8,496 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K478221,K527769 | Restrictive Covenant | Restrictive covenants not to permit vehicular use of land over which there is a right of way, not to use land for any purpose other than those authorised by the National Trust Acts 1907 to 1971, not to interfere with a sea wall and other restrictive coven |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/40 | Kent Sheet 5 | 8,496 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K527769 | Easement Right or Privilege | Right relating to tipping of refuse as contained in a Conveyance dated 25 September 1978 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/40 | Kent Sheet 5 | 8,496 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Right of entry and rights to use and maintain service media as contained in a Deed dated 27 May 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/40 | Kent Sheet 5 | 8,496 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of a lease for an easement as contained in an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/40 | Kent Sheet 5 | 8,496 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/40 | Kent Sheet 5 | 8,496 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/40 | Kent Sheet 5 | 8,496 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Option to Purchase | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/40 | Kent Sheet 5 | 8,496 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate is to be registered without a written consent |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/41 | Kent Sheet 2 | 5,222 square metres, or thereabouts, of agricultural land, electricity transmission pylon and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | South Eastern Power Networks plc | 263 | K458450 | Easement Right or Privilege | Rights relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 17 December 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/41 | Kent Sheet 2 | 5,222 square metres, or thereabouts, of agricultural land, electricity transmission pylon and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | South Eastern Power Networks plc | 263 | K458450 | Easement Right or Privilege | Rights relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 24 July 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/41 | Kent Sheet 2 | 5,222 square metres, or thereabouts, of agricultural land, electricity transmission pylon and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | South Eastern Power Networks plc | 263 | K458450 | Restrictive Covenant | Restrictive covenants relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 17 December 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/41 | Kent Sheet 2 | 5,222 square metres, or thereabouts, of agricultural land, electricity transmission pylon and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | South Eastern Power Networks plc | 263 | K458450 | Restrictive Covenant | Restrictive covenants relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 24 July 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/41 | Kent Sheet 3 | 8,369 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Statkraft UK Limited | 2741 | K808893 | Easement Right or Privilege | Unilateral notice in respect of an Option to Lease pursuant to an Option Agreement dated 9 December 2022 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/41 | Kent Sheet 5 | 23 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet Offshore Wind Limited | 76 | K527769 | Easement Right or Privilege | Right of entry and rights to maintain service media as contained in a Deed dated 27 April 2009 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-10-08
5/41 | Kent Sheet 5 | 23 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K527769 | Easement Right or Privilege | Right of entry to maintain a sea wall and a right of way with or without vehicles and rights relating to service media as contained in a Transfer dated 4 December 1981 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/41 | Kent Sheet 5 | 23 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K478221,K527769 | Restrictive Covenant | Restrictive covenants not to permit vehicular use of land over which there is a right of way, not to use land for any purpose other than those authorised by the National Trust Acts 1907 to 1971, not to interfere with a sea wall and other restrictive coven |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/41 | Kent Sheet 5 | 23 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K527769 | Easement Right or Privilege | Right relating to tipping of refuse as contained in a Conveyance dated 25 September 1978 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/41 | Kent Sheet 5 | 23 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Right of entry and rights to use and maintain service media as contained in a Deed dated 27 May 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/41 | Kent Sheet 5 | 23 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of a lease for an easement as contained in an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/41 | Kent Sheet 5 | 23 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/41 | Kent Sheet 5 | 23 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/41 | Kent Sheet 5 | 23 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Option to Purchase | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/41 | Kent Sheet 5 | 23 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate is to be registered without a written consent |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/42 | Kent Sheet 2 | 5,319 square metres, or thereabouts, of grassland, track, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | South Eastern Power Networks plc | 263 | K458450 | Easement Right or Privilege | Rights relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 17 December 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/42 | Kent Sheet 2 | 5,319 square metres, or thereabouts, of grassland, track, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | South Eastern Power Networks plc | 263 | K458450 | Easement Right or Privilege | Rights relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 24 July 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/42 | Kent Sheet 2 | 5,319 square metres, or thereabouts, of grassland, track, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | South Eastern Power Networks plc | 263 | K458450 | Restrictive Covenant | Restrictive covenants relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 17 December 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/42 | Kent Sheet 2 | 5,319 square metres, or thereabouts, of grassland, track, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | South Eastern Power Networks plc | 263 | K458450 | Restrictive Covenant | Restrictive covenants relating to access and maintenance of electricity lines and pylon as contained in a Deed dated 24 July 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/42 | Kent Sheet 5 | 144 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet Offshore Wind Limited | 76 | K527769 | Easement Right or Privilege | Right of entry and rights to maintain service media as contained in a Deed dated 27 April 2009 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-10-08
5/42 | Kent Sheet 5 | 144 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K527769 | Easement Right or Privilege | Right of entry to maintain a sea wall and a right of way with or without vehicles and rights relating to service media as contained in a Transfer dated 4 December 1981 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/42 | Kent Sheet 5 | 144 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K478221,K527769 | Restrictive Covenant | Restrictive covenants not to permit vehicular use of land over which there is a right of way, not to use land for any purpose other than those authorised by the National Trust Acts 1907 to 1971, not to interfere with a sea wall and other restrictive coven |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/42 | Kent Sheet 5 | 144 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K527769 | Easement Right or Privilege | Right relating to tipping of refuse as contained in a Conveyance dated 25 September 1978 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/42 | Kent Sheet 5 | 144 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Right of entry and rights to use and maintain service media as contained in a Deed dated 27 May 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/42 | Kent Sheet 5 | 144 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of a lease for an easement as contained in an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/42 | Kent Sheet 5 | 144 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/42 | Kent Sheet 5 | 144 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/42 | Kent Sheet 5 | 144 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Option to Purchase | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/42 | Kent Sheet 5 | 144 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate is to be registered without a written consent |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/43 | Kent Sheet 5 | 4 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet Offshore Wind Limited | 76 | K527769 | Easement Right or Privilege | Right of entry and rights to maintain service media as contained in a Deed dated 27 April 2009 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-10-08
5/43 | Kent Sheet 5 | 4 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K527769 | Easement Right or Privilege | Right of entry to maintain a sea wall and a right of way with or without vehicles and rights relating to service media as contained in a Transfer dated 4 December 1981 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/43 | Kent Sheet 5 | 4 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K478221,K527769 | Restrictive Covenant | Restrictive covenants not to permit vehicular use of land over which there is a right of way, not to use land for any purpose other than those authorised by the National Trust Acts 1907 to 1971, not to interfere with a sea wall and other restrictive coven |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/43 | Kent Sheet 5 | 4 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K527769 | Easement Right or Privilege | Right relating to tipping of refuse as contained in a Conveyance dated 25 September 1978 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/43 | Kent Sheet 5 | 4 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Right of entry and rights to use and maintain service media as contained in a Deed dated 27 May 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/43 | Kent Sheet 5 | 4 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of a lease for an easement as contained in an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/43 | Kent Sheet 5 | 4 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/43 | Kent Sheet 5 | 4 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/43 | Kent Sheet 5 | 4 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Option to Purchase | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/43 | Kent Sheet 5 | 4 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate is to be registered without a written consent |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/44 | Kent Sheet 3 | 11,247 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sunsave 1 Limited | 584 | K960682,K985672 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/44 | Kent Sheet 3 | 11,247 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants not to interfere with or damage service media or interfere with or obstruct access to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/44 | Kent Sheet 5 | 2 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet Offshore Wind Limited | 76 | K527769 | Easement Right or Privilege | Right of entry and rights to maintain service media as contained in a Deed dated 27 April 2009 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-10-08
5/44 | Kent Sheet 5 | 2 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K527769 | Easement Right or Privilege | Right of entry to maintain a sea wall and a right of way with or without vehicles and rights relating to service media as contained in a Transfer dated 4 December 1981 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/44 | Kent Sheet 5 | 2 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K478221,K527769 | Restrictive Covenant | Restrictive covenants not to permit vehicular use of land over which there is a right of way, not to use land for any purpose other than those authorised by the National Trust Acts 1907 to 1971, not to interfere with a sea wall and other restrictive coven |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/44 | Kent Sheet 5 | 2 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Thanet District Council | 167 | K527769 | Easement Right or Privilege | Right relating to tipping of refuse as contained in a Conveyance dated 25 September 1978 |  | Category 2 | N/A | Yes | RR-5372 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowner in January 2025. The template terms and rights being sought were discussed with the landowner at meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has taken place with this landowner who confirmed they will be appointing an agent. We await confirmation of the appointment before proceeding further with negotiations. 18.11.2025 - Dalcour Maclaren have continued attempts to progress Heads of Terms, however there has been limited engagement from the landowner resulting in no material progression. The landowner has not, based on current understanding, appointed an agent to progress negotiations on their behalf. Dalcour Maclaren continue attempts to engage by email and telephone and have also made visits to the Council offices on 13th August and 22nd October 2025. 26.11.2025 – Heads of Terms have been provided for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren issued revised Heads of Terms to the landowner on 16th December 2025 which incorporated the changes to the application under Change 1 which was accepted by the Examining Authority on 5th December 2025. Thanet District Council have acknowledged receipt of the updated Terms and Dalcour Maclaren await feedback from the landowner. | Heads of Terms negotiations ongoing |  | 2026-01-09
5/44 | Kent Sheet 5 | 2 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Right of entry and rights to use and maintain service media as contained in a Deed dated 27 May 2016 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/44 | Kent Sheet 5 | 2 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of a lease for an easement as contained in an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/44 | Kent Sheet 5 | 2 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Nemo Link Limited | 771 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Agreement dated 3 September 2015 |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/44 | Kent Sheet 5 | 2 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Easement Right or Privilege | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/44 | Kent Sheet 5 | 2 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Option to Purchase | Unilateral notice in respect of an Option Agreement dated 10 January 2020 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/44 | Kent Sheet 5 | 2 square metres, or thereabouts, of saltmarsh and sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Vattenfall Wind Power Limited | 841 | K527769 | Restrictive Covenant | No disposition of the registered estate by the proprietor of the registered estate is to be registered without a written consent |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Kent Sheet 3 | 7,705 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sunsave 1 Limited | 584 | K960682,K985672 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/45 | Kent Sheet 3 | 7,705 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants not to interfere with or damage service media or interfere with or obstruct access to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/45 | Kent Sheet 5 | 6,544 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet Offshore Wind Limited | 76 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/45 | Kent Sheet 5 | 6,544 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm | as reputed owner | Category 2 | No Agent Known | Yes | RR-5371 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions not requested. Assumed to rely upon the DCO provisions | No Heads of Terms Required |  | 2026-01-09
5/45 | Kent Sheet 5 | 6,544 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Nemo Link Limited | 771 | K929702,TT46617 | Restrictive Covenant | Restrictive covenant not to interfere with or damage electricity cables or access to electricity cables as contained in a Deed dated 26 May 2016 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
2/46 | Kent Sheet 2 | 26 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | TT103406 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Kent Sheet 3 | 2,942 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | South Eastern Power Networks plc | 263 | K808893 | Easement Right or Privilege | Right of entry and rights to; lay and maintain electric lines, fell trees and break up ground surface as contained in a Deed dated 16 March 2006 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Kent Sheet 3 | 2,942 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | South Eastern Power Networks plc | 263 | K808893 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electric lines as contained in a Deed dated 16 March 2006 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/46 | Kent Sheet 3 | 2,942 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Statkraft UK Limited | 2741 | K808893 | Easement Right or Privilege | Unilateral notice in respect of an Option to Lease pursuant to an Option Agreement dated 9 December 2022 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/46 | Kent Sheet 5 | 14,098 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet Offshore Wind Limited | 76 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/46 | Kent Sheet 5 | 14,098 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Thanet OFTO Limited | 152 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm | as reputed owner | Category 2 | No Agent Known | Yes | RR-5371 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions not requested. Assumed to rely upon the DCO provisions | No Heads of Terms Required |  | 2026-01-09
5/46 | Kent Sheet 5 | 14,098 square metres, or thereabouts, of sea (North Sea) situated to the south east of Pegwell Service Station, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Nemo Link Limited | 771 | K929702,TT46617 | Restrictive Covenant | Restrictive covenant not to interfere with or damage electricity cables or access to electricity cables as contained in a Deed dated 26 May 2016 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
2/47 | Kent Sheet 2 | 50 square metres, or thereabouts, of drain under bridge carrying track and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | TT103406 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Kent Sheet 3 | 17,155 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent County Council | 97 | K808893 | Easement Right or Privilege | Right of entry and rights relating to the use and maintenance of drainage apparatus as contained in a Transfer dated 12 December 2016 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/47 | Kent Sheet 3 | 17,155 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Kent County Council | 97 | K808893 | Restrictive Covenant | Restrictive covenants not to connect to, interfere with or damage drainage apparatus as contained in a Transfer dated 12 December 2016 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/47 | Kent Sheet 3 | 17,155 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | South Eastern Power Networks plc | 263 | K808893 | Easement Right or Privilege | Right of entry and rights to; lay and maintain electric lines, fell trees and break up ground surface as contained in a Deed dated 16 March 2006 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Kent Sheet 3 | 17,155 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | South Eastern Power Networks plc | 263 | K808893 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electric lines as contained in a Deed dated 16 March 2006 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/47 | Kent Sheet 3 | 17,155 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Statkraft UK Limited | 2741 | K808893 | Easement Right or Privilege | Unilateral notice in respect of an Option to Lease pursuant to an Option Agreement dated 9 December 2022 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/47 | Kent Sheet 5 | 1,166 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet Offshore Wind Limited | 76 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/47 | Kent Sheet 5 | 1,166 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm | as reputed owner | Category 2 | No Agent Known | Yes | RR-5371 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions not requested. Assumed to rely upon the DCO provisions | No Heads of Terms Required |  | 2026-01-09
5/47 | Kent Sheet 5 | 1,166 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Nemo Link Limited | 771 | K929702,TT46617 | Restrictive Covenant | Restrictive covenant not to interfere with or damage electricity cables or access to electricity cables as contained in a Deed dated 26 May 2016 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
2/48 | Kent Sheet 2 | 11 square metres, or thereabouts, of drain situated to the south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | TT103406 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
5/48 | Kent Sheet 5 | 9,902 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet Offshore Wind Limited | 76 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land | No agreement on final version |  | 08.10.2025- Thanet Offshore Wind Ltd have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
5/48 | Kent Sheet 5 | 9,902 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Thanet OFTO Limited | 152 | K929702 | Restrictive Covenant | Restrictive covenants not to cause damage to electricity cables as contained in a Deed dated 10 December 2009 for the benefit of Thanet Wind Farm | as reputed owner | Category 2 | No Agent Known | Yes | RR-5371 | [6 empty] | SU rights in land | Not required |  | 08.10.2025- Bespoke Protective Provisions not requested. Assumed to rely upon the DCO provisions | No Heads of Terms Required |  | 2026-01-09
5/48 | Kent Sheet 5 | 9,902 square metres, or thereabouts, of sea (North Sea) and hard standing situated to the south east of Cliffsend Point, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Nemo Link Limited | 771 | K929702,TT46617 | Restrictive Covenant | Restrictive covenant not to interfere with or damage electricity cables or access to electricity cables as contained in a Deed dated 26 May 2016 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No |  |  |  |  | Open Space |  |  | SU rights in land | No agreement on final version |  | 08.10.2025- Nemo Link have not requested any Bespoke Protective Provisions and as such will be covered by the DCO provisions | No Heads of Terms Required |  | 2025-11-18
2/49 | Kent Sheet 2 | 108 square metres, or thereabouts, of drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | TT103406 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Kent Sheet 3 | 683 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sunsave 1 Limited | 584 | K960682,K985672 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/49 | Kent Sheet 3 | 683 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants not to interfere with or damage service media or interfere with or obstruct access to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/50 | Kent Sheet 2 | 3,952 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K57595 | Easement Right or Privilege | Rights and restrictions relating to electricity apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/50 | Kent Sheet 2 | 3,952 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K57595 | Restrictive Covenant | Rights and restrictive covenants relating to electricity apparatus as contained in a Deed dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/50 | Kent Sheet 2 | 3,952 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul James Saunders | 931 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/50 | Kent Sheet 2 | 3,952 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul James Saunders | 931 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/50 | Kent Sheet 2 | 3,952 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/50 | Kent Sheet 2 | 3,952 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/50 | Kent Sheet 3 | 1,186 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Sunsave 1 Limited | 584 | K960682,K985672 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/50 | Kent Sheet 3 | 1,186 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants not to interfere with or damage service media or interfere with or obstruct access to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/51 | Kent Sheet 2 | 3,852 square metres, or thereabouts, of agricultural land, track, drain and overhead electricity distribution lines situated to the south and south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K57595 | Easement Right or Privilege | Rights and restrictions relating to electricity apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/51 | Kent Sheet 2 | 3,852 square metres, or thereabouts, of agricultural land, track, drain and overhead electricity distribution lines situated to the south and south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K57595 | Restrictive Covenant | Rights and restrictive covenants relating to electricity apparatus as contained in a Deed dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/51 | Kent Sheet 2 | 3,852 square metres, or thereabouts, of agricultural land, track, drain and overhead electricity distribution lines situated to the south and south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul James Saunders | 931 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/51 | Kent Sheet 2 | 3,852 square metres, or thereabouts, of agricultural land, track, drain and overhead electricity distribution lines situated to the south and south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Paul James Saunders | 931 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/51 | Kent Sheet 2 | 3,852 square metres, or thereabouts, of agricultural land, track, drain and overhead electricity distribution lines situated to the south and south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/51 | Kent Sheet 2 | 3,852 square metres, or thereabouts, of agricultural land, track, drain and overhead electricity distribution lines situated to the south and south east of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Kent Sheet 3 | 1,518 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | Sunsave 1 Limited | 584 | K960682,K985672 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/51 | Kent Sheet 3 | 1,518 square metres, or thereabouts, of agricultural land and track under construction situated to the south west of Great Cliffsend Farm House, Kent, Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | Class 3. ﻿Compulsory Acquisition of Rights - Underground Cable System | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants not to interfere with or damage service media or interfere with or obstruct access to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/52 | Kent Sheet 2 | 3,701 square metres, or thereabouts, of grassland and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K57595 | Easement Right or Privilege | Rights and restrictions relating to electricity apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/52 | Kent Sheet 2 | 3,701 square metres, or thereabouts, of grassland and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K57595 | Restrictive Covenant | Rights and restrictive covenants relating to electricity apparatus as contained in a Deed dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/52 | Kent Sheet 2 | 3,701 square metres, or thereabouts, of grassland and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul James Saunders | 931 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/52 | Kent Sheet 2 | 3,701 square metres, or thereabouts, of grassland and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul James Saunders | 931 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/52 | Kent Sheet 2 | 3,701 square metres, or thereabouts, of grassland and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/52 | Kent Sheet 2 | 3,701 square metres, or thereabouts, of grassland and drain situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/52 | Kent Sheet 3 | 1,079 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | South Eastern Power Networks plc | 263 | K808893 | Easement Right or Privilege | Right of entry and rights to; lay and maintain electric lines, fell trees and break up ground surface as contained in a Deed dated 16 March 2006 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/52 | Kent Sheet 3 | 1,079 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | South Eastern Power Networks plc | 263 | K808893 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electric lines as contained in a Deed dated 16 March 2006 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/53 | Kent Sheet 2 | 12,613 square metres, or thereabouts, of grassland, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | K57595 | Easement Right or Privilege | Rights and restrictions relating to electricity apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/53 | Kent Sheet 2 | 12,613 square metres, or thereabouts, of grassland, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | K57595 | Restrictive Covenant | Rights and restrictive covenants relating to electricity apparatus as contained in a Deed dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/53 | Kent Sheet 2 | 12,613 square metres, or thereabouts, of grassland, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Paul James Saunders | 931 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/53 | Kent Sheet 2 | 12,613 square metres, or thereabouts, of grassland, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Paul James Saunders | 931 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/53 | Kent Sheet 2 | 12,613 square metres, or thereabouts, of grassland, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/53 | Kent Sheet 2 | 12,613 square metres, or thereabouts, of grassland, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Kent Sheet 3 | 16 square metres, or thereabouts, of track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants relating to construction, earthworks and excavation as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/53 | Kent Sheet 3 | 16 square metres, or thereabouts, of track (Cottington Lane) situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Manston Thorne Limited | 620 | TT27715 | Easement Right or Privilege | Caution against first registration in relation to rights contained in a Deed of Easement for Underground Service Media dated 4 August 2014 |  | Category 2 | No Agent Known | Yes | REP1-238 | [6 empty] | Not SU | No agreement on final version |  | 08.10.2025- Negotiations for Protective Provisions will take place now the Statement of Common Ground has been drafted | Heads of Terms negotiations not commenced |  | 2026-01-09
2/54 | Kent Sheet 2 | 40,844 square metres, or thereabouts, of grassland, track, drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K57595 | Easement Right or Privilege | Rights and restrictions relating to electricity apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/54 | Kent Sheet 2 | 40,844 square metres, or thereabouts, of grassland, track, drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K57595 | Restrictive Covenant | Rights and restrictive covenants relating to electricity apparatus as contained in a Deed dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/54 | Kent Sheet 2 | 40,844 square metres, or thereabouts, of grassland, track, drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul James Saunders | 931 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/54 | Kent Sheet 2 | 40,844 square metres, or thereabouts, of grassland, track, drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul James Saunders | 931 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/54 | Kent Sheet 2 | 40,844 square metres, or thereabouts, of grassland, track, drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/54 | Kent Sheet 2 | 40,844 square metres, or thereabouts, of grassland, track, drain and overhead electricity distribution lines situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/54 | Kent Sheet 3 | 17,794 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sunsave 1 Limited | 584 | K960682,K985672 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/54 | Kent Sheet 3 | 17,794 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants not to interfere with or damage service media or interfere with or obstruct access to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/54 | Kent Sheet 3 | 17,794 square metres, or thereabouts, of agricultural land, electricity distribution poles and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants relating to construction, earthworks and excavation as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/55 | Kent Sheet 2 | 4,844 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K57595 | Easement Right or Privilege | Rights and restrictions relating to electricity apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/55 | Kent Sheet 2 | 4,844 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K57595 | Restrictive Covenant | Rights and restrictive covenants relating to electricity apparatus as contained in a Deed dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/55 | Kent Sheet 2 | 4,844 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul James Saunders | 931 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/55 | Kent Sheet 2 | 4,844 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul James Saunders | 931 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/55 | Kent Sheet 2 | 4,844 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/55 | Kent Sheet 2 | 4,844 square metres, or thereabouts, of grassland and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Kent Sheet 3 | 3,331 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Sunsave 1 Limited | 584 | K960682,K985672 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/55 | Kent Sheet 3 | 3,331 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants not to interfere with or damage service media or interfere with or obstruct access to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/56 | Kent Sheet 2 | 28 square metres, or thereabouts, of grassland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | TT103406 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/56 | Kent Sheet 2 | 28 square metres, or thereabouts, of grassland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/56 | Kent Sheet 2 | 28 square metres, or thereabouts, of grassland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/56 | Kent Sheet 2 | 28 square metres, or thereabouts, of grassland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ludowika Walburga Von Walburg-Zeil | 2317 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/56 | Kent Sheet 2 | 28 square metres, or thereabouts, of grassland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/56 | Kent Sheet 2 | 28 square metres, or thereabouts, of grassland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jorinde Maria Augustina Herrmann | 2319 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/56 | Kent Sheet 2 | 28 square metres, or thereabouts, of grassland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mary Patricia Lacey | 2320 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Kent Sheet 3 | 7,939 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sunsave 1 Limited | 584 | K960682,K985672 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/56 | Kent Sheet 3 | 7,939 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 6. Compulsory Acquisition of Rights - Drainage | Class 6. Compulsory Acquisition of Rights - Drainage | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants not to interfere with or damage service media or interfere with or obstruct access to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/57 | Kent Sheet 2 | 343 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | TT103406 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Kent Sheet 3 | 762 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sunsave 1 Limited | 584 | K960682,K985672 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/57 | Kent Sheet 3 | 762 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants not to interfere with or damage service media or interfere with or obstruct access to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/58 | Kent Sheet 2 | 434 square metres, or thereabouts, of river, bed and bank (River Stour), overhead electricity distribution lines and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line: Open Space (River Stour Navigation) | Class 2. Compulsory Acquisition of Rights - Overhead Line: Open Space (River Stour Navigation) | National Grid Electricity Transmission plc | 7 | K933847 | Easement Right or Privilege | Rights relating to a grid station and lines as contained in a Deed of Grant dated 20 January 1967 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/59 | Kent Sheet 2 | 620 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights – Overhead Line | Class 2. Compulsory Acquisition of Rights – Overhead Line | National Grid Electricity Transmission plc | 7 | K57595 | Easement Right or Privilege | Rights and restrictions relating to electricity apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/59 | Kent Sheet 2 | 620 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights – Overhead Line | Class 2. Compulsory Acquisition of Rights – Overhead Line | National Grid Electricity Transmission plc | 7 | K57595 | Restrictive Covenant | Rights and restrictive covenants relating to electricity apparatus as contained in a Deed dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/59 | Kent Sheet 2 | 620 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights – Overhead Line | Class 2. Compulsory Acquisition of Rights – Overhead Line | Paul James Saunders | 931 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/59 | Kent Sheet 2 | 620 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights – Overhead Line | Class 2. Compulsory Acquisition of Rights – Overhead Line | Paul James Saunders | 931 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/59 | Kent Sheet 2 | 620 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights – Overhead Line | Class 2. Compulsory Acquisition of Rights – Overhead Line | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/59 | Kent Sheet 2 | 620 square metres, or thereabouts, of river, bed and bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights – Overhead Line | Class 2. Compulsory Acquisition of Rights – Overhead Line | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K651171 | Easement Right or Privilege | Rights and restrictions relation to electricity apparatus as contained in a Deed dated 15 November 1989 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Jean Veronica Spanton | 39 | K617169,K651171 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | N/A Joe Hearnden, BTF Partnership | Yes | RR-5840 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Positive engagement has continued with this landowner and or their agent and it is anticipated an agreement will be reached by the end of Examination. 18.11.2025 - Following a meeting held on 12th September 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on the reasoning behind the rights to be acquired. Dalcour Maclaren provided this and re-issued the Heads of Terms on the 29th October 2025, engagement is ongoing. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025, 1st December 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 29th October 2025. Dalcour Maclaren proceeded to contact the landowner’s son on the 07th January 2026 and issued a copy of the Heads of Terms directly to him for review and discussion. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Natalie Anne Brudenell | 159 | K651171,K981650 | Easement Right or Privilege | Rights to enter to maintain drains and conduits as contained in a Transfer dated 16 June 2011 |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | South Eastern Power Networks plc | 263 | K651171 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 15 November 1989 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | South Eastern Power Networks plc | 263 | K651171 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 9 January 2008 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | South Eastern Power Networks plc | 263 | K651171 | Restrictive Covenant | Restrictive covenant relating to electricity apparatus as contained in a Deed dated 9 January 2008 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right of entry and rights relating to a drain and pumping station as contained in a Transfer dated 14 April 1990 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right to enter and to construct a drain as contained in a Transfer dated 24 April 1990 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Catharina Nadina Chapman | 302 | K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Gavin Johnson | 524 | K651171,K981650 | Easement Right or Privilege | Rights to enter to maintain drains and conduits as contained in a Transfer dated 16 June 2011 |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-01-09
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert John Chapman | 654 | K651171,K688725 | Easement Right or Privilege | Right of entry and rights relating to a drain and pumping station as contained in a Transfer dated 14 April 1990 |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert John Chapman | 654 | K651171,K688725 | Easement Right or Privilege | Right to enter and to construct a drain as contained in a Transfer dated 24 April 1990 |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert John Chapman | 654 | K985109 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Robert John Chapman | 654 | K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | UK Power Networks Services (South East) Limited | 1009 | K651171 | Easement Right or Privilege | Rights and restrictions relating to electricity apparatus |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid intend to secure the rights of access through the terms issued for plots 6/1 and 6/1 (Kent). 03.10.2025 - Despite several attempts, no response has been received from this Landowner. 18.11.2025 - Dalcour Maclaren are engaging with the landowner regarding Heads of Terms. On 4th November 2025 the landowner confirmed they do not have any objection in principle to the proposals. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | American Golf (Trading) Limited | 1052 | K651171,K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/59 | Kent Sheet 3 | 3,408 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Personal Representative to the Estate of Christopher John Spanton | 3526 | K617169,K651171 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | N/A Joe Hearnden, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued in March 2025. This individual has passed away, see update in AP ref 39 | Heads of Terms negotiations ongoing |  | 2025-10-08
2/60 | Kent Sheet 2 | 8,781 square metres, or thereabouts, of grassland, drains, sluices, track, electricity transmission pylon and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K57595 | Easement Right or Privilege | Rights and restrictions relating to electricity apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/60 | Kent Sheet 2 | 8,781 square metres, or thereabouts, of grassland, drains, sluices, track, electricity transmission pylon and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K57595 | Restrictive Covenant | Rights and restrictive covenants relating to electricity apparatus as contained in a Deed dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/60 | Kent Sheet 2 | 8,781 square metres, or thereabouts, of grassland, drains, sluices, track, electricity transmission pylon and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul James Saunders | 931 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/60 | Kent Sheet 2 | 8,781 square metres, or thereabouts, of grassland, drains, sluices, track, electricity transmission pylon and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul James Saunders | 931 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/60 | Kent Sheet 2 | 8,781 square metres, or thereabouts, of grassland, drains, sluices, track, electricity transmission pylon and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/60 | Kent Sheet 2 | 8,781 square metres, or thereabouts, of grassland, drains, sluices, track, electricity transmission pylon and overhead electricity distribution lines situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | National Grid Electricity Transmission plc | 7 | K651171 | Easement Right or Privilege | Rights and restrictions relation to electricity apparatus as contained in a Deed dated 15 November 1989 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Jean Veronica Spanton | 39 | K617169,K651171 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | N/A Joe Hearnden, BTF Partnership | Yes | RR-5840 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Positive engagement has continued with this landowner and or their agent and it is anticipated an agreement will be reached by the end of Examination. 18.11.2025 - Following a meeting held on 12th September 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on the reasoning behind the rights to be acquired. Dalcour Maclaren provided this and re-issued the Heads of Terms on the 29th October 2025, engagement is ongoing. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025, 1st December 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 29th October 2025. Dalcour Maclaren proceeded to contact the landowner’s son on the 07th January 2026 and issued a copy of the Heads of Terms directly to him for review and discussion. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Natalie Anne Brudenell | 159 | K651171,K981650 | Easement Right or Privilege | Rights to enter to maintain drains and conduits as contained in a Transfer dated 16 June 2011 |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | South Eastern Power Networks plc | 263 | K651171 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 15 November 1989 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | South Eastern Power Networks plc | 263 | K651171 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 9 January 2008 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | South Eastern Power Networks plc | 263 | K651171 | Restrictive Covenant | Restrictive covenant relating to electricity apparatus as contained in a Deed dated 9 January 2008 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right of entry and rights relating to a drain and pumping station as contained in a Transfer dated 14 April 1990 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right to enter and to construct a drain as contained in a Transfer dated 24 April 1990 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Catharina Nadina Chapman | 302 | K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Gavin Johnson | 524 | K651171,K981650 | Easement Right or Privilege | Rights to enter to maintain drains and conduits as contained in a Transfer dated 16 June 2011 |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-01-09
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert John Chapman | 654 | K651171,K688725 | Easement Right or Privilege | Right of entry and rights relating to a drain and pumping station as contained in a Transfer dated 14 April 1990 |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert John Chapman | 654 | K651171,K688725 | Easement Right or Privilege | Right to enter and to construct a drain as contained in a Transfer dated 24 April 1990 |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert John Chapman | 654 | K985109 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert John Chapman | 654 | K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 | K651171 | Easement Right or Privilege | Rights and restrictions relating to electricity apparatus |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid intend to secure the rights of access through the terms issued for plots 6/1 and 6/1 (Kent). 03.10.2025 - Despite several attempts, no response has been received from this Landowner. 18.11.2025 - Dalcour Maclaren are engaging with the landowner regarding Heads of Terms. On 4th November 2025 the landowner confirmed they do not have any objection in principle to the proposals. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | American Golf (Trading) Limited | 1052 | K651171,K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/60 | Kent Sheet 3 | 1,978 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course), electricity distribution poles, and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Personal Representative to the Estate of Christopher John Spanton | 3526 | K617169,K651171 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | N/A Joe Hearnden, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued in March 2025. This individual has passed away, see update in AP ref 39 | Heads of Terms negotiations ongoing |  | 2025-10-08
2/61 | Kent Sheet 2 | 122 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | TT103406 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K651171 | Easement Right or Privilege | Rights and restrictions relation to electricity apparatus as contained in a Deed dated 15 November 1989 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jean Veronica Spanton | 39 | K617169,K651171 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | N/A Joe Hearnden, BTF Partnership | Yes | RR-5840 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Positive engagement has continued with this landowner and or their agent and it is anticipated an agreement will be reached by the end of Examination. 18.11.2025 - Following a meeting held on 12th September 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on the reasoning behind the rights to be acquired. Dalcour Maclaren provided this and re-issued the Heads of Terms on the 29th October 2025, engagement is ongoing. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025, 1st December 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 29th October 2025. Dalcour Maclaren proceeded to contact the landowner’s son on the 07th January 2026 and issued a copy of the Heads of Terms directly to him for review and discussion. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Natalie Anne Brudenell | 159 | K651171,K981650 | Easement Right or Privilege | Rights to enter to maintain drains and conduits as contained in a Transfer dated 16 June 2011 |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | South Eastern Power Networks plc | 263 | K651171 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 15 November 1989 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right of entry and rights relating to a drain and pumping station as contained in a Transfer dated 14 April 1990 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right to enter and to construct a drain as contained in a Transfer dated 24 April 1990 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Catharina Nadina Chapman | 302 | K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Gavin Johnson | 524 | K651171,K981650 | Easement Right or Privilege | Rights to enter to maintain drains and conduits as contained in a Transfer dated 16 June 2011 |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-01-09
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert John Chapman | 654 | K651171,K688725 | Easement Right or Privilege | Right of entry and rights relating to a drain and pumping station as contained in a Transfer dated 14 April 1990 |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert John Chapman | 654 | K651171,K688725 | Easement Right or Privilege | Right to enter and to construct a drain as contained in a Transfer dated 24 April 1990 |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert John Chapman | 654 | K985109 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Robert John Chapman | 654 | K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | UK Power Networks Services (South East) Limited | 1009 | K651171 | Easement Right or Privilege | Rights and restrictions relating to electricity apparatus |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid intend to secure the rights of access through the terms issued for plots 6/1 and 6/1 (Kent). 03.10.2025 - Despite several attempts, no response has been received from this Landowner. 18.11.2025 - Dalcour Maclaren are engaging with the landowner regarding Heads of Terms. On 4th November 2025 the landowner confirmed they do not have any objection in principle to the proposals. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | American Golf (Trading) Limited | 1052 | K651171,K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/61 | Kent Sheet 3 | 364 square metres, or thereabouts, of golf course and premises (Stonelees Golf Course) situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Personal Representative to the Estate of Christopher John Spanton | 3526 | K617169,K651171 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | N/A Joe Hearnden, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued in March 2025. This individual has passed away, see update in AP ref 39 | Heads of Terms negotiations ongoing |  | 2025-10-08
2/62 | Kent Sheet 2 | 2,242 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K933847 | Easement Right or Privilege | Rights relating to a grid station and lines as contained in a Deed of Grant dated 20 January 1967 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/62 | Kent Sheet 2 | 2,242 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K932081 | Easement Right or Privilege | Unilateral notice in respect of a lease of rights dated 23 July 2018 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/63 | Kent Sheet 2 | 2,701 square metres, or thereabouts, of grassland, sluice, drain and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K57595 | Easement Right or Privilege | Rights and restrictions relating to electricity apparatus as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/63 | Kent Sheet 2 | 2,701 square metres, or thereabouts, of grassland, sluice, drain and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K57595 | Restrictive Covenant | Rights and restrictive covenants relating to electricity apparatus as contained in a Deed dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/63 | Kent Sheet 2 | 2,701 square metres, or thereabouts, of grassland, sluice, drain and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul James Saunders | 931 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/63 | Kent Sheet 2 | 2,701 square metres, or thereabouts, of grassland, sluice, drain and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Paul James Saunders | 931 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/63 | Kent Sheet 2 | 2,701 square metres, or thereabouts, of grassland, sluice, drain and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Right of way and use of service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/63 | Kent Sheet 2 | 2,701 square metres, or thereabouts, of grassland, sluice, drain and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Helen Michelle Caroline Saunders | 932 | K57595,K718480 | Easement Right or Privilege | Rights relating to service media as contained in a Transfer dated 31 July 1992 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Kent Sheet 3 | 456 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sunsave 1 Limited | 584 | K960682,K985672 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/63 | Kent Sheet 3 | 456 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sunsave 1 Limited | 584 | K960682,K985672 | Restrictive Covenant | Restrictive covenants not to interfere with or damage service media or interfere with or obstruct access to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Easement Right or Privilege | Right of entry with or without vehicles, machinery and equipment and rights to maintain electricity lines as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Easement Right or Privilege | Right of way with or without vehicles, machinery and equipment and rights to lop trees and bushes as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Restrictive Covenant | Covenants not to obstruct or interfere with the enjoyment of rights of way as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electricity lines and not to store goods or materials within a 15 metre radius of any pylons as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | South Eastern Power Networks plc | 263 | K535742 | Easement Right or Privilege | Right of entry and rights to maintain underground electric lines and associated supports as contained in a Deed of Grant dated 24 September 2018 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | South Eastern Power Networks plc | 263 | K535742 | Easement Right or Privilege | Rights of access with or without vehicles, plant apparatus and equipment and the right to park vehicles as contained in a Deed of Grant dated 24 September 2018 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | South Eastern Power Networks plc | 263 | K535742 | Restrictive Covenant | Restrictive covenants not to interfere with or damage underground electric lines and associated supports and not to install any other service media as contained in a Deed of Grant dated 24 September 2018 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ludowika Walburga Von Walburg-Zeil | 2317 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jorinde Maria Augustina Herrmann | 2319 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/65 | Kent Sheet 2 | 6,116 square metres, or thereabouts, of agricultural land, drain, track, drain under footbridge carrying track and overhead electricity distribution lines situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mary Patricia Lacey | 2320 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | National Grid Electricity Transmission plc | 7 | K651171 | Easement Right or Privilege | Rights and restrictions relation to electricity apparatus as contained in a Deed dated 15 November 1989 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Jean Veronica Spanton | 39 | K617169,K651171 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | N/A Joe Hearnden, BTF Partnership | Yes | RR-5840 | [6 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued in March 2025. 08.10.2025 - Positive engagement has continued with this landowner and or their agent and it is anticipated an agreement will be reached by the end of Examination. 18.11.2025 - Following a meeting held on 12th September 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on the reasoning behind the rights to be acquired. Dalcour Maclaren provided this and re-issued the Heads of Terms on the 29th October 2025, engagement is ongoing. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025, 1st December 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 29th October 2025. Dalcour Maclaren proceeded to contact the landowner’s son on the 07th January 2026 and issued a copy of the Heads of Terms directly to him for review and discussion. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Natalie Anne Brudenell | 159 | K651171,K981650 | Easement Right or Privilege | Rights to enter to maintain drains and conduits as contained in a Transfer dated 16 June 2011 |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2025-10-08
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | South Eastern Power Networks plc | 263 | K651171 | Easement Right or Privilege | Rights relating to electricity apparatus as contained in a Deed dated 15 November 1989 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right of entry and rights relating to a drain and pumping station as contained in a Transfer dated 14 April 1990 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Catharina Nadina Chapman | 302 | K651171,K688725 | Easement Right or Privilege | Right to enter and to construct a drain as contained in a Transfer dated 24 April 1990 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Catharina Nadina Chapman | 302 | K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Gavin Johnson | 524 | K651171,K981650 | Easement Right or Privilege | Rights to enter to maintain drains and conduits as contained in a Transfer dated 16 June 2011 |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - This land interest relates to subsoil interest in the highway. Whilst engagement is ongoing with the local highway authority as part of the DCO process, no voluntary rights are being sought in relation to the subsoil beneath the highway network. | No Heads of Terms Required |  | 2026-01-09
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert John Chapman | 654 | K651171,K688725 | Easement Right or Privilege | Right of entry and rights relating to a drain and pumping station as contained in a Transfer dated 14 April 1990 |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert John Chapman | 654 | K651171,K688725 | Easement Right or Privilege | Right to enter and to construct a drain as contained in a Transfer dated 24 April 1990 |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert John Chapman | 654 | K985109 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Robert John Chapman | 654 | K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | Mark Chandler, Finn's (1865) Ltd | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners and their appointed agents in January 2025. The template terms and rights being sought were discussed with the landowners appointed agent in meetings throughout February. Populated Heads of Terms were issued on 03 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the template Heads of Terms was re-issued to their agent in August 2025. Discussions are ongoing between Dalcour Maclaren and the landowners agent. 18.11.2025 - Dalcour Maclaren are continuing to engage with the landowner's agent in relation to the Heads of Terms. Dalcour Maclaren proposed some meeting dates to the landowner's agent on 7th November 2025 to progress matters. 09.01.2026 - On 5th December 2025, Dalcour Maclaren issued further details of the restrictions within the Deed of Easement to the landowner’s agent for their consideration. Dalcour Maclaren emailed the landowner’s agent on 22nd December 2025 to seek feedback and a Teams meeting has been arranged with the landowner's agent on 14th January 2026. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | UK Power Networks Services (South East) Limited | 1009 | K651171 | Easement Right or Privilege | Rights and restrictions relating to electricity apparatus |  | Category 2 | N/A | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid intend to secure the rights of access through the terms issued for plots 6/1 and 6/1 (Kent). 03.10.2025 - Despite several attempts, no response has been received from this Landowner. 18.11.2025 - Dalcour Maclaren are engaging with the landowner regarding Heads of Terms. On 4th November 2025 the landowner confirmed they do not have any objection in principle to the proposals. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | American Golf (Trading) Limited | 1052 | K651171,K688725 | Easement Right or Privilege | Rights relating to service media and rights to use a driving golf range simulator and putting green, pass and repass over common areas and retain air-conditioning machinery as contained in a Lease dated 28 November 2019 for the benefit of adjoining land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/65 | Kent Sheet 3 | 10,894 square metres, or thereabouts, of golf course and premises (St Augustine`s Golf Course) situated to the south of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights - Underground Cable System | Class 3. Compulsory Acquisition of Rights - Underground Cable System | Personal Representative to the Estate of Christopher John Spanton | 3526 | K617169,K651171 | Easement Right or Privilege | Rights relating to drainage as contained in a Conveyance dated 28 October 1986 for the benefit of adjoining land |  | Category 2 | N/A Joe Hearnden, BTF Partnership | No | [7 empty] | Not SU |  |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. A meeting was offered to discuss the template terms and rights being sought in February. Populated Heads of Terms were issued in March 2025. This individual has passed away, see update in AP ref 39 | Heads of Terms negotiations ongoing |  | 2025-10-08
2/66 | Kent Sheet 2 | 28 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | TT103406 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/66 | Kent Sheet 2 | 28 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/66 | Kent Sheet 2 | 28 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/66 | Kent Sheet 2 | 28 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ludowika Walburga Von Walburg-Zeil | 2317 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/66 | Kent Sheet 2 | 28 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/66 | Kent Sheet 2 | 28 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jorinde Maria Augustina Herrmann | 2319 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/66 | Kent Sheet 2 | 28 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mary Patricia Lacey | 2320 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/67 | Kent Sheet 2 | 76 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | TT103406 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/67 | Kent Sheet 2 | 76 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/67 | Kent Sheet 2 | 76 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/67 | Kent Sheet 2 | 76 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Ludowika Walburga Von Walburg-Zeil | 2317 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/67 | Kent Sheet 2 | 76 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/67 | Kent Sheet 2 | 76 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Jorinde Maria Augustina Herrmann | 2319 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/67 | Kent Sheet 2 | 76 square metres, or thereabouts, of river, bed, bank (River Stour) and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Mary Patricia Lacey | 2320 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/68 | Kent Sheet 2 | 123 square metres, or thereabouts, of river, bed and bank (River Stour) situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | TT103406 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/69 | Kent Sheet 2 | 108 square metres, or thereabouts, of agricultural land and track situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Easement Right or Privilege | Right of entry with or without vehicles, machinery and equipment and rights to maintain electricity lines as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/69 | Kent Sheet 2 | 108 square metres, or thereabouts, of agricultural land and track situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Easement Right or Privilege | Right of way with or without vehicles, machinery and equipment and rights to lop trees and bushes as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/69 | Kent Sheet 2 | 108 square metres, or thereabouts, of agricultural land and track situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Restrictive Covenant | Covenants not to obstruct or interfere with the enjoyment of rights of way as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/69 | Kent Sheet 2 | 108 square metres, or thereabouts, of agricultural land and track situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electricity lines and not to store goods or materials within a 15 metre radius of any pylons as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/69 | Kent Sheet 2 | 108 square metres, or thereabouts, of agricultural land and track situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/69 | Kent Sheet 2 | 108 square metres, or thereabouts, of agricultural land and track situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/70 | Kent Sheet 2 | 2,290 square metres, or thereabouts, of scrubland, track and drain situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Easement Right or Privilege | Right of entry with or without vehicles, machinery and equipment and rights to maintain electricity lines as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/70 | Kent Sheet 2 | 2,290 square metres, or thereabouts, of scrubland, track and drain situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Easement Right or Privilege | Right of way with or without vehicles, machinery and equipment and rights to lop trees and bushes as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/70 | Kent Sheet 2 | 2,290 square metres, or thereabouts, of scrubland, track and drain situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Restrictive Covenant | Covenants not to obstruct or interfere with the enjoyment of rights of way as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/70 | Kent Sheet 2 | 2,290 square metres, or thereabouts, of scrubland, track and drain situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electricity lines and not to store goods or materials within a 15 metre radius of any pylons as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/70 | Kent Sheet 2 | 2,290 square metres, or thereabouts, of scrubland, track and drain situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/70 | Kent Sheet 2 | 2,290 square metres, or thereabouts, of scrubland, track and drain situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/70 | Kent Sheet 2 | 2,290 square metres, or thereabouts, of scrubland, track and drain situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ludowika Walburga Von Walburg-Zeil | 2317 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/70 | Kent Sheet 2 | 2,290 square metres, or thereabouts, of scrubland, track and drain situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/70 | Kent Sheet 2 | 2,290 square metres, or thereabouts, of scrubland, track and drain situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jorinde Maria Augustina Herrmann | 2319 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/70 | Kent Sheet 2 | 2,290 square metres, or thereabouts, of scrubland, track and drain situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mary Patricia Lacey | 2320 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/71 | Kent Sheet 2 | 460 square metres, or thereabouts, of scrubland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Easement Right or Privilege | Right of entry with or without vehicles, machinery and equipment and rights to maintain electricity lines as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/71 | Kent Sheet 2 | 460 square metres, or thereabouts, of scrubland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Easement Right or Privilege | Right of way with or without vehicles, machinery and equipment and rights to lop trees and bushes as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/71 | Kent Sheet 2 | 460 square metres, or thereabouts, of scrubland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Restrictive Covenant | Covenants not to obstruct or interfere with the enjoyment of rights of way as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/71 | Kent Sheet 2 | 460 square metres, or thereabouts, of scrubland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electricity lines and not to store goods or materials within a 15 metre radius of any pylons as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/71 | Kent Sheet 2 | 460 square metres, or thereabouts, of scrubland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/71 | Kent Sheet 2 | 460 square metres, or thereabouts, of scrubland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/71 | Kent Sheet 2 | 460 square metres, or thereabouts, of scrubland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ludowika Walburga Von Walburg-Zeil | 2317 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/71 | Kent Sheet 2 | 460 square metres, or thereabouts, of scrubland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/71 | Kent Sheet 2 | 460 square metres, or thereabouts, of scrubland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jorinde Maria Augustina Herrmann | 2319 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/71 | Kent Sheet 2 | 460 square metres, or thereabouts, of scrubland situated to the south of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mary Patricia Lacey | 2320 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/72 | Kent Sheet 2 | 5,521 square metres, or thereabouts, of agricultural land and drain situated to the south west of Boxlees, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Easement Right or Privilege | Right of entry with or without vehicles, machinery and equipment and rights to maintain electricity lines as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/72 | Kent Sheet 2 | 5,521 square metres, or thereabouts, of agricultural land and drain situated to the south west of Boxlees, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Easement Right or Privilege | Right of way with or without vehicles, machinery and equipment and rights to lop trees and bushes as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/72 | Kent Sheet 2 | 5,521 square metres, or thereabouts, of agricultural land and drain situated to the south west of Boxlees, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Restrictive Covenant | Covenants not to obstruct or interfere with the enjoyment of rights of way as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/72 | Kent Sheet 2 | 5,521 square metres, or thereabouts, of agricultural land and drain situated to the south west of Boxlees, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electricity lines and not to store goods or materials within a 15 metre radius of any pylons as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/72 | Kent Sheet 2 | 5,521 square metres, or thereabouts, of agricultural land and drain situated to the south west of Boxlees, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/72 | Kent Sheet 2 | 5,521 square metres, or thereabouts, of agricultural land and drain situated to the south west of Boxlees, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | South Eastern Power Networks plc | 263 | K535742 | Easement Right or Privilege | Right of entry and rights to maintain underground electric lines and associated supports as contained in a Deed of Grant dated 24 September 2018 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/72 | Kent Sheet 2 | 5,521 square metres, or thereabouts, of agricultural land and drain situated to the south west of Boxlees, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | South Eastern Power Networks plc | 263 | K535742 | Easement Right or Privilege | Rights of access with or without vehicles, plant apparatus and equipment and the right to park vehicles as contained in a Deed of Grant dated 24 September 2018 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/72 | Kent Sheet 2 | 5,521 square metres, or thereabouts, of agricultural land and drain situated to the south west of Boxlees, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | South Eastern Power Networks plc | 263 | K535742 | Restrictive Covenant | Restrictive covenants not to interfere with or damage underground electric lines and associated supports and not to install any other service media as contained in a Deed of Grant dated 24 September 2018 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/72 | Kent Sheet 2 | 5,521 square metres, or thereabouts, of agricultural land and drain situated to the south west of Boxlees, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/72 | Kent Sheet 2 | 5,521 square metres, or thereabouts, of agricultural land and drain situated to the south west of Boxlees, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ludowika Walburga Von Walburg-Zeil | 2317 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/72 | Kent Sheet 2 | 5,521 square metres, or thereabouts, of agricultural land and drain situated to the south west of Boxlees, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/72 | Kent Sheet 2 | 5,521 square metres, or thereabouts, of agricultural land and drain situated to the south west of Boxlees, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jorinde Maria Augustina Herrmann | 2319 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/72 | Kent Sheet 2 | 5,521 square metres, or thereabouts, of agricultural land and drain situated to the south west of Boxlees, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mary Patricia Lacey | 2320 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/73 | Kent Sheet 2 | 11,831 square metres, or thereabouts, of agricultural land, track, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | K535742 | Easement Right or Privilege | Right of entry with or without vehicles, machinery and equipment and rights to maintain electricity lines as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/73 | Kent Sheet 2 | 11,831 square metres, or thereabouts, of agricultural land, track, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | K535742 | Easement Right or Privilege | Right of way with or without vehicles, machinery and equipment and rights to lop trees and bushes as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/73 | Kent Sheet 2 | 11,831 square metres, or thereabouts, of agricultural land, track, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | K535742 | Restrictive Covenant | Covenants not to obstruct or interfere with the enjoyment of rights of way as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/73 | Kent Sheet 2 | 11,831 square metres, or thereabouts, of agricultural land, track, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | National Grid Electricity Transmission plc | 7 | K535742 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electricity lines and not to store goods or materials within a 15 metre radius of any pylons as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/73 | Kent Sheet 2 | 11,831 square metres, or thereabouts, of agricultural land, track, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/73 | Kent Sheet 2 | 11,831 square metres, or thereabouts, of agricultural land, track, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | South Eastern Power Networks plc | 263 | K535742 | Easement Right or Privilege | Right of entry and rights to maintain underground electric lines and associated supports as contained in a Deed of Grant dated 24 September 2018 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/73 | Kent Sheet 2 | 11,831 square metres, or thereabouts, of agricultural land, track, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | South Eastern Power Networks plc | 263 | K535742 | Easement Right or Privilege | Rights of access with or without vehicles, plant apparatus and equipment and the right to park vehicles as contained in a Deed of Grant dated 24 September 2018 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/73 | Kent Sheet 2 | 11,831 square metres, or thereabouts, of agricultural land, track, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | South Eastern Power Networks plc | 263 | K535742 | Restrictive Covenant | Restrictive covenants not to interfere with or damage underground electric lines and associated supports and not to install any other service media as contained in a Deed of Grant dated 24 September 2018 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/73 | Kent Sheet 2 | 11,831 square metres, or thereabouts, of agricultural land, track, drains, electricity transmission pylon and overhead electricity transmission lines situated to the south east of Boxlees Hill, Kent, Class 2. Compulsory Acquisition of Rights - Overhead Line | Class 2. Compulsory Acquisition of Rights - Overhead Line | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/74 | Kent Sheet 2 | 832 square metres, or thereabouts, of track and scrubland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | TT103405 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 | Caution against first registration | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/74 | Kent Sheet 2 | 832 square metres, or thereabouts, of track and scrubland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Easement Right or Privilege | Right of entry with or without vehicles, machinery and equipment and rights to maintain electricity lines as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/74 | Kent Sheet 2 | 832 square metres, or thereabouts, of track and scrubland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Easement Right or Privilege | Right of way with or without vehicles, machinery and equipment and rights to lop trees and bushes as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/74 | Kent Sheet 2 | 832 square metres, or thereabouts, of track and scrubland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Restrictive Covenant | Covenants not to obstruct or interfere with the enjoyment of rights of way as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/74 | Kent Sheet 2 | 832 square metres, or thereabouts, of track and scrubland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electricity lines and not to store goods or materials within a 15 metre radius of any pylons as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/74 | Kent Sheet 2 | 832 square metres, or thereabouts, of track and scrubland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/74 | Kent Sheet 2 | 832 square metres, or thereabouts, of track and scrubland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/74 | Kent Sheet 2 | 832 square metres, or thereabouts, of track and scrubland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ludowika Walburga Von Walburg-Zeil | 2317 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/74 | Kent Sheet 2 | 832 square metres, or thereabouts, of track and scrubland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/74 | Kent Sheet 2 | 832 square metres, or thereabouts, of track and scrubland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jorinde Maria Augustina Herrmann | 2319 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/74 | Kent Sheet 2 | 832 square metres, or thereabouts, of track and scrubland situated to the south east of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mary Patricia Lacey | 2320 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/74 | Kent Sheet 3 | 601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | K808893 | Easement Right or Privilege | Right of entry and rights relating to the use and maintenance of drainage apparatus as contained in a Transfer dated 12 December 2016 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/74 | Kent Sheet 3 | 601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | K808893 | Restrictive Covenant | Restrictive covenants not to connect to, interfere with or damage drainage apparatus as contained in a Transfer dated 12 December 2016 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/74 | Kent Sheet 3 | 601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | South Eastern Power Networks plc | 263 | K808893 | Easement Right or Privilege | Right of entry and rights to; lay and maintain electric lines, fell trees and break up ground surface as contained in a Deed dated 16 March 2006 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/74 | Kent Sheet 3 | 601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | South Eastern Power Networks plc | 263 | K808893 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electric lines as contained in a Deed dated 16 March 2006 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/74 | Kent Sheet 3 | 601 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Statkraft UK Limited | 2741 | K808893 | Easement Right or Privilege | Unilateral notice in respect of an Option to Lease pursuant to an Option Agreement dated 9 December 2022 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/75 | Kent Sheet 2 | 12,129 square metres, or thereabouts, of agricultural land situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Easement Right or Privilege | Right of entry with or without vehicles, machinery and equipment and rights to maintain electricity lines as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/75 | Kent Sheet 2 | 12,129 square metres, or thereabouts, of agricultural land situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Easement Right or Privilege | Right of way with or without vehicles, machinery and equipment and rights to lop trees and bushes as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/75 | Kent Sheet 2 | 12,129 square metres, or thereabouts, of agricultural land situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Restrictive Covenant | Covenants not to obstruct or interfere with the enjoyment of rights of way as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/75 | Kent Sheet 2 | 12,129 square metres, or thereabouts, of agricultural land situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | National Grid Electricity Transmission plc | 7 | K535742 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electricity lines and not to store goods or materials within a 15 metre radius of any pylons as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/75 | Kent Sheet 2 | 12,129 square metres, or thereabouts, of agricultural land situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/75 | Kent Sheet 2 | 12,129 square metres, or thereabouts, of agricultural land situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/75 | Kent Sheet 2 | 12,129 square metres, or thereabouts, of agricultural land situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Ludowika Walburga Von Walburg-Zeil | 2317 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/75 | Kent Sheet 2 | 12,129 square metres, or thereabouts, of agricultural land situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/75 | Kent Sheet 2 | 12,129 square metres, or thereabouts, of agricultural land situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Jorinde Maria Augustina Herrmann | 2319 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/75 | Kent Sheet 2 | 12,129 square metres, or thereabouts, of agricultural land situated to the south west of Boxlees Hill, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Mary Patricia Lacey | 2320 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/75 | Kent Sheet 3 | 6,551 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K808893 | Easement Right or Privilege | Right of entry and rights relating to the use and maintenance of drainage apparatus as contained in a Transfer dated 12 December 2016 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/75 | Kent Sheet 3 | 6,551 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Kent County Council | 97 | K808893 | Restrictive Covenant | Restrictive covenants not to connect to, interfere with or damage drainage apparatus as contained in a Transfer dated 12 December 2016 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/75 | Kent Sheet 3 | 6,551 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Statkraft UK Limited | 2741 | K808893 | Easement Right or Privilege | Unilateral notice in respect of an Option to Lease pursuant to an Option Agreement dated 9 December 2022 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/76 | Kent Sheet 2 | 2,173 square metres, or thereabouts, of agricultural land and track situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K535742 | Easement Right or Privilege | Right of entry with or without vehicles, machinery and equipment and rights to maintain electricity lines as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/76 | Kent Sheet 2 | 2,173 square metres, or thereabouts, of agricultural land and track situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K535742 | Easement Right or Privilege | Right of way with or without vehicles, machinery and equipment and rights to lop trees and bushes as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/76 | Kent Sheet 2 | 2,173 square metres, or thereabouts, of agricultural land and track situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K535742 | Restrictive Covenant | Covenants not to obstruct or interfere with the enjoyment of rights of way as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/76 | Kent Sheet 2 | 2,173 square metres, or thereabouts, of agricultural land and track situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | National Grid Electricity Transmission plc | 7 | K535742 | Restrictive Covenant | Restrictive covenants not to interfere with or damage electricity lines and not to store goods or materials within a 15 metre radius of any pylons as contained in a General Vesting Declaration dated 20 June 2019 |  | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/76 | Kent Sheet 2 | 2,173 square metres, or thereabouts, of agricultural land and track situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Kent County Council | 97 | K535742 | Easement Right or Privilege | Right of entry and rights related to surface water drains as contained in a Deed dated 1 June 1949 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/76 | Kent Sheet 2 | 2,173 square metres, or thereabouts, of agricultural land and track situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Network Rail Infrastructure Limited | 1271 | K535742 | Easement Right or Privilege | Rights relating to a level crossing as contained in a Deed dated 25 January 1979 and varied in a Deed dated 3 November 1980 |  | Category 2 | N/A | Yes | RR-3936 | [6 empty] | Not SU | Bespoke PPs |  | 25.03.2025 - National Grid are negotiating terms with Network Rail for the rights required over these plots. 08.10.2025- Format of Heads of Terms agreed in line with the existing framework between Network Rail and National Grid. Further engineering information required to finalise this agreement. 26.11.2025 – Heads of Terms are in an agreed form for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. | Heads of Terms negotiations ongoing |  | 2026-01-09
2/76 | Kent Sheet 2 | 2,173 square metres, or thereabouts, of agricultural land and track situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Ludowika Walburga Von Walburg-Zeil | 2317 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/76 | Kent Sheet 2 | 2,173 square metres, or thereabouts, of agricultural land and track situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Caroline Mary Concordia Scott | 2318 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/76 | Kent Sheet 2 | 2,173 square metres, or thereabouts, of agricultural land and track situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Jorinde Maria Augustina Herrmann | 2319 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/76 | Kent Sheet 2 | 2,173 square metres, or thereabouts, of agricultural land and track situated to the west of Boxlees Hill, Kent, Class 5. Compulsory Acquisition of Rights - Access | Class 5. Compulsory Acquisition of Rights - Access | Mary Patricia Lacey | 2320 | K535742,K545599 | Easement Right or Privilege | Right of drainage as contained in a Transfer dated 24 June 1982 for the benefit of neighbouring land |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/76 | Kent Sheet 3 | 3,447 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Kent County Council | 97 | K808893 | Easement Right or Privilege | Right of entry and rights relating to the use and maintenance of drainage apparatus as contained in a Transfer dated 12 December 2016 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/76 | Kent Sheet 3 | 3,447 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Kent County Council | 97 | K808893 | Restrictive Covenant | Restrictive covenants not to connect to, interfere with or damage drainage apparatus as contained in a Transfer dated 12 December 2016 |  | Category 2 | N/A Steven Drennan, Carter Jonas | Yes | RR-2977 | [6 empty] | Not SU | Not required |  | 25.03.2025 - National Grid's Agent (Dalcour Maclaren) issued template Heads of Terms to landowners in January 2025. The template terms and rights being sought were discussed with the landowner in meetings throughout February. Populated Heads of Terms were issued on 06 March and are subject to ongoing discussion. 08.10.2025 - Engagement has continued with this landowner and their agent. A further version of the Heads of Terms will be re-issued imminently following recent positive discussions recently. 18.11.2025 - Following a meeting held on 9th July 2025 between the landowner's agent and Dalcour Maclaren, the landowner and their agent requested additional clarity on a number of matters. Dalcour Maclaren provided further information and re-issued the Heads of Terms on the 20th October 2025, engagement is ongoing. 26.11.2025 – Heads of Terms are under negotiation for the wider holding. The additional plots will be incorporated into the Heads of Terms if appropriate. 09.01.2026 - Dalcour Maclaren contacted the landowner’s agent on 24th November 2025 and 22nd December 2025 to seek feedback on the most recent Heads of Terms which were issued on 20th October 2025. | Heads of Terms negotiations ongoing |  | 2026-01-09
3/76 | Kent Sheet 3 | 3,447 square metres, or thereabouts, of agricultural land situated to the south west of Great Cliffsend Farm House, Kent, Class 3. Compulsory Acquisition of Rights – Underground Cable System | Class 3. Compulsory Acquisition of Rights – Underground Cable System | Statkraft UK Limited | 2741 | K808893 | Easement Right or Privilege | Unilateral notice in respect of an Option to Lease pursuant to an Option Agreement dated 9 December 2022 |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
2/77 | Kent Sheet 2 | 288 square metres, or thereabouts, of track and scrubland situated to the south west of Boxlees Hill, Kent, Class 9. Temporary Use for Access | Class 9. Temporary Use for Access | National Grid Electricity Transmission plc | 7 | TT103405 | Easement Right or Privilege | Caution against first registration in respect of rights and restrictions created by a General Vesting Declaration dated 20 June 2019 | Caution against first registration | Category 2 | No Agent Known | No | [7 empty] | SU rights in land |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09
3/77 | Kent Sheet 3 | 7,380 square metres, or thereabouts, of agricultural land and overhead electricity distribution lines situated to the south west of Great Cliffsend Farm House, Kent, Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Class 8. Temporary Use for Construction, Mitigation, Maintenance, and Dismantling of Redundant Infrastructure | Sunsave 1 Limited | 584 | K960682,K985672 | Easement Right or Privilege | Rights relating to service media as contained in a Deed dated 4 August 2014 for the benefit of Thornhill Solar Park |  | Category 2 | No Agent Known | No | [7 empty] | Not SU |  |  | 08.10.2025 - no voluntary agreements are being sought in relation to this right, as no further land rights being sought from this PIL | No Heads of Terms Required |  | 2026-01-09